## Annual Review

Title: Climate Adaptation Water and Energy Programme (CAWEP)
Programme Value £ (full life): £19,550,000		Review date: 10 February 2024
Programme Code : 300164	AMP start date: 10 November 2019	AMP end date: 30 March 2026

Summary of Programme Performance
Year	2021	2022	2023	2024
Overall Output Score	B	B	A	A
Risk Rating	Major	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	https://devtracker.fcdo.gov.uk/projects/GB-GOV-1-300164
DevTracker Link to results framework:

A. SUMMARY AND OVERVIEW

A.1 Description of programme
The Foreign Commonwealth and Development Office (FCDO) in Zimbabwe is funding the implementation of CAWEP through the United Nations Development Programme (UNDP) and United Nations Children's Fund (UNICEF). The programme works to strengthen the ability of vulnerable communities to withstand climate shocks. Through this programme, the FCDO is supporting the development of climate resilient water and renewable energy infrastructure in the most vulnerable communities of Zimbabwe to enable: (i) continued access to water for productive and household use, including during droughts and floods, and (ii) improved access to clean and affordable energy to support economic activities and ensure more sustainable livelihoods. CAWEP is strengthening Early Warning Systems (EWS) in vulnerable districts, enabling timely access to and use of weather & climate information to better anticipate and respond to climate shocks. The programme will provide technical assistance to the government as well as non-state actors to support the wider use of climate science in designing and delivering resilient water and energy infrastructure. Evidence generated through this programme will be used to influence climate policy improvement and support national climate adaptation plans. As such, it aims to build and demonstrate an understanding of what works and what challenges must be overcome to deliver resilient and sustainable outcomes.

FCDO supports the delivery of this programme in twenty districts across the country and intends to help over seven hundred thousand people to better adapt to the effects of climate change through sustainable access to solar powered multiple use water and energy systems including through access to reliable weather and climate information.
[note] Buhera, Mutare rural, Makoni, Mutasa, Gweru, Zaka, Chiredzi, Gutu, Chikomba, Chipinge, Chimanimani, Nyanga, Binga, Insiza, Lupane, Bubi, Umguza, Nkayi, Chivi, Tsholotsho.

The programme has two main components that this review looks at. The components are briefly explained below:

A.1.1 Adaptive & Flexible Water and Energy supply- Component 1
This component was designed to flexibly respond to emerging water & clean energy priorities including providing infrastructure support to avert the impact of potential climate or weather-related disasters. This £2.5 million funded component was implemented through UNICEF, providing sustainable basic water supply using climate resilient infrastructure, through the installation of solar powered water schemes in nine districts. It was implemented between July 2021 to June 2022.

A.1.2 Climate Adaptation - Community water & renewable energy infrastructure & Early Warning Systems (EWS) – Component 2
This is the main CAWEP component that seeks to contribute towards community and institutional climate resilience in Zimbabwe. Work under this component is designed to boost climate change adaptation through enhanced climate proofing and development of climate resilient community water and renewable energy infrastructure and strengthening EWS and response in selected vulnerable districts. The total funding for this component is £12 million starting August 2022 to November 2025.
[note] Measures taken to prevent infrastructure from being vulnerable to potential long-term climate impacts. Under this project, this involves infrastructure improvements, solar pumping, and water-use efficient, irrigation technologies (drip, sprinkler systems)

A.2 Summary supporting narrative for the overall score in this review
This review rates CAWEP performance over the past year at A score. This implies the programme largely delivered as expected at this stage of programme implementation. The justification being that three out of the four programme outputs have scored A or A+, performing as expected or moderately exceeding expectations. This has significantly contributed to achieving the overall outcome. The main outcome the programme seeks to deliver is to help poor and vulnerable households become more adaptive to the effects of climate change through sustainable access to long term climate resilient and multiple-use water and renewable energy infrastructure. As a result of good performance in delivering outputs, the programme has so far helped 149,652 people against an expected milestone of reaching 99,512 people at this stage (February 2024). Some notable achievements on delivering outputs include completion of climate proofed water and energy infrastructure for multiple use in Binga and Chipinge districts. This include installing a solar mini grid with a capacity of 200 kilowatt-peak (kWp) accounting for 9.5% of Zimbabwe’s Nationally Determined Contribution (NDC) target of installing additional 2.098 megawatts through microgrids by 2028. The programme has also supported the development of strategic policies such as the National Energy Efficiency Policy which is expected to improve energy security by optimising existing local energy sources and tackling the detrimental effects of climate change and environmental degradation.
[note] This is the peak power of a PV system or panel. Solar panel systems are given a rating in kilowatts peak (kWp) which is the rate at which they generate energy at peak performance, such as on a sunny day in the afternoon.
[note] Zimbabwe Nationally Determined Contribution, 2021

A.3 Major lessons and recommendations for the year ahead
The following sections highlight key lessons learnt in the year under review and provides the main strategic recommendations to be taken forward in the coming year.

A.3.1 Key lessons learnt
Public financing is critical in helping to meet national climate commitments. Government of Zimbabwe’s contribution towards CAWEP through the Rural Electrification Fund (REF) has brought multiple benefits including reduced programme delivery cost, expertise and strengthened partnership.
A.3.2 Key Recommendations
Below are high level strategic recommendations. Other output related recommendations are provided in Section C.

The year ahead UNDP, working with government should focus on rolling out the approved programme Business Development Strategy which sets out existing opportunities and actions to create multiple sources for revenue generation to (i) sustain CAWEP investments and (ii) develop local economies, creating jobs and sustainable livelihoods. The sustainability of CAWEP outcomes and impact is anchored on ensuring viable business models are built around productive water and energy infrastructure to generate income. The Business Development Strategy involves strategic market development, building important linkages between the targeted communities and different value chain actors including the private sector.

Draft and sign a Memorandum of Understanding (MoU) that communicates the mutually accepted expectations, current and future roles, and responsibilities of all of the parties involved in CAWEP. Parties include FCDO represented by the British Embassy in Harare (BEH), Government of Zimbabwe (GoZ), represented by partner departments and UNDP. This will strengthen collaboration and accountability, which are critical in ensuring programme success and sustainability.
[note] Zimbabwe National Water Authority (ZINWA), Rural Electrification Agency (REA), Agricultural and Rural Development Advisory Services (ARDAS), Meteorological Services Department (MSD) and Department of Irrigation, Agriculture Rural Development Authority (ARDA)

Government of Zimbabwe (GoZ) is encouraged to continue to invest more towards developing climate resilient infrastructure and sustaining it, complementing work being delivered through CAWEP. Creating a conducive environment to promote private partnerships is critical – for both scale and sustainability – as grant funded projects alone will not deliver Zimbabwe’s ambitions and needs. Final approval of the National Adaptation Plan (NAP) is crucial to help mobilising more climate finance for adaptation.
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

B.1 Theory of Change Description
The long-term impact that CAWEP seeks to make is to help communities and public institutions in Zimbabwe to become more resilient to respond to adverse effects of climate change such as droughts and floods. To achieve this, the programme logic is that poor and vulnerable households and government institutions are supported to become more adaptive to the effects of climate change through sustainable access to long term climate resilient and multiple use water and renewable energy infrastructure, and Early Warning Systems (EWS). The programme is still following this logic and so the theory of change (ToC) has not changed in the past year. Results from the baseline survey that was concluded in the past year confirm the programme relevance and appropriateness to address the problem. See the baseline report in Annex 1. This review also finds that outputs are on course to deliver the desired outcomes. See the Theory of Change below in Fig 1.

Fig 1: CAWEP Theory of Change (ToC)

B.1.2 Stakeholder and beneficiary engagement
Given the multidimensional approach underpinning CAWEP, the programme continues to work extensively with a range of stakeholders at all government levels, the private sector, and communities. This has contributed to positive progress made to date. The programme engages with government stakeholders at all levels. Through the Steering Committee (SC), the FCDO and UNDP engage with senior government officials from partner ministries on policy and strategy while at sub-national levels, the UNDP technical team and technical government departments are responsible for direct delivery, working with communities. Strong stakeholder and community engagement has so far helped to meet key milestones as seen in section c under output reporting. Examples of community engagement that has happened over the year include local planning meetings for resource mobilisation in constructing water works and on operation and maintenance. This also helped the programme to remain on track to deliver good Value for Money (VfM). Please see VfM dashboard in Annex 2

B.1.3 Progress towards achieving Outcomes and Impact
This review judges that CAWEP is on track to achieve the outcomes and desired impact. CAWEP is on track to meet expected outcomes and make a meaningful contribution towards improving climate change resilience in Zimbabwe. The review observed an upward trend on most outcome indicators. For example, in 2023, 77,768 people were helped to adapt to effects of climate change. In 2024, the reach has increased to 149,652 surpassing the expected target of 99,512. Overall, good progress on delivering all the four outputs suggests programme outcomes will be achieved although in the year ahead, programme teams must work hard to ensure the outcomes are sustainable. There is also a need to closely analyse potential challenges and risks that could affect the programme sustainability plan and put in place a strategy to mitigate and avoid slippage. From the review, the following are likely to be the main challenges and risks: (i) delays in rolling out the programme business development strategy which is one of the main anchors for sustainability in CAWEP, (ii) poor stakeholder coordination between key government departments namely Agricultural Advisory and Rural Development Services (ARDAS) and Agricultural and Rural Development Authority (ARDA)

Figure 2 below shows progress delivering one of the main outcome indicators.

Fig 1: Progress towards achieving outcome 1.

B.1.4 Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
This review assessed the programme relevance, looking at (i) strategic fit into global, UK and Zimbabwe climate strategies on tackling climate change, (ii) whether CAWEP is addressing underlying problems affecting targeted communities and institutions’ ability to adapt and become more resilient to climate change, (iii) programme potential to deliver sustainable outcomes and still delivering at good value for money. The review recommends that the programme should continue based on these reasons:

- The UK, in the recently launched White Paper on International Development, identifies helping developing countries to adapt to the impacts of climate change as a critical priority and commits to focus adaptation resources on the most climate vulnerable countries and communities. Zimbabwe remains among the most climate-vulnerable countries in the world: it was ranked second most affected by severe climate-driven weather events in the Global Climate Risk Index 2021. CAWEP is directly delivering UK commitments on climate adaptation and resilience while helping Zimbabwe to better adapt to effects of climate change.
  [note] https://www.germanwatch.org/sites/default/files/Global%20Climate%20Risk%20Index%202021_2.pdf
- CAWEP is addressing the underlying factors inhibiting communities and institutions’ ability to cope with the effects of climate change, which include, (i) lack of access to weather and climate information to better understand, plan for and reduce the risks and impacts of climate change and of weather extremes and (ii) lack of productive and climate proofed water and energy infrastructure that help to build sustainable livelihoods reducing risk of experiencing severe impacts of climate shocks. CAWEP has already helped 149,652 to better adapt to climate change through improving access to weather and climate information, multiple use water and clean energy. The Government of Zimbabwe (GoZ) recognises the positive impact that CAWEP is making which they showcased at the 28th Conference of Parties (COP28) held in Dubai from 30th November to 12th December 2023.
- Overall, the programme continues to represent good value for money through its multiple use water and energy approach which is showing potential and having an impact on other UK development priorities on girls’ education, health, and energy efficiency.

## C. DETAILED OUTPUT SCORING

Output Title	Developed climate resilient multiple use water and energy infrastructure
Output number:		1	Output Score:	A
Impact weighting (%):		40	Weighting revised since last AR?

Indicator(s)	Milestone(s) for this review	Progress
1.1 No. of community multipurpose water & clean energy infrastructure developed/rehabilitated with special technical designs and features that respond to climate risks. Disaggregated by type (i) Solar Piped Water Systems (PWS) (i) mini/micro grids, (iii) small dams (iv) Irrigation systems/networks	36 PWS Solar mini grid (1) Small dam (0) Irrigation systems/networks- 1ha, Mlibizi 20ha (2)	172 (Installed units) PWS (36) / Solar mini grid (1) Small dam (0) / Irrigation systems/networks (4) Institutional Solar Modules (12) / Biogas Digestors (120)
1.2 Proportion of functional water and renewable energy infrastructure	80%	100%
1.3 Proportion of water and renewable energy infrastructure with a community management structure and business model for maintenance	80%	100%

C.1 Briefly describe the output’s activities and provide supporting narrative for the score.
The main expectations on this output at this stage of the programme were met and, in some cases, delivered above expectations. As shown in the table above under output indicator 1.1, additional multipurpose institutional solar systems and biogas digesters were installed, although not initially planned to be delivered in the year under review. Other key and impressive results include completing four solar powered drip irrigation systems on separate one-hectare plots and a solar powered centre pivot to irrigate fifteen hectares in Binga district. This demonstrates the programme adaptability and consciousness on the importance of taking up opportunities that deliver good value for money. For example, the project accelerated procurement for Mlibizi and awarded a single contract for the whole scope of Mlibizi Piped Water System (PWS) rehabilitation, irrigation development, solarisation of social institutions). This led to the delivery of this component in 2023. The project was able to reach ten schools instead of five by reducing the size of the solar systems initially planned for. An analysis of the structures at the schools and clinics and the energy uses showed that the bigger 10-kilowatt (Kw) units initially planned would be underutilised hence 5kw and 8kw systems were installed instead. Output indicators 1.2 and 1.3 also performed above expectations. However, some installations are fairly new and have not yet gone through longer testing on robustness of the systems and effectiveness of community-based management regimes.

Other main highlights from the field visit conducted as part of this review are.

1. Evidence on the programme directly responding to known and predicted climate shocks. For example, in Binga, solar powered submersible pumps have been mounted on a floating raft (pontoon) as a response to receding water levels during droughts but ensuring water availability. CAWEP has also built additional water storage capacity (over 750m³) to support irrigation. This means farmers could have more water for irrigation and become less dependent on rainfed agriculture. There is also a significant increase in pumping capacity while seeing a significant reduction in pumping costs because of investment in solar pumping systems. In Binga, (Mlibizi) solar is now the primary source of energy for water pumping.
2. Innovation to improve efficiency through using radio links making the system easier to run, improve demand- supply management and early detecting of anomalies, enabling timely response.
All the water and renewable energy and infrastructure have functional community management structures and business model for maintenance. In the past year, nine Asset Management committees were established and trained to operate and manage the infrastructure. The Irrigation schemes will be managed under the government’s Agriculture Rural Development Authority (ARDA) commercial model, whilst in smaller gardens operations and maintenance will be financed through subscriptions and Village Savings and Lending.

This review also assessed thirty-five additional older solar powered PWS installed through UNICEF in 2022. Functionality is still at 100%. Based in this assessment, this review scored this output an A and on track to achieve end of programme target.

C.1.1 Challenges
Late completion of some key works is attributed to two main challenges faced during the year which are: (i) delay in shipment of the solar mini grid components due to instability in the Red Sea and (ii) unexpected government commitments such as by-elections in Binga district.

C.1.2 Describe any changes to this output during the past year, and any planned changes as a result of this review.
There were no significant changes to this output that negatively affected delivery and progress towards delivering outcomes. Additional works were delivered under this output as described in section C.1 above. As a result, this review recommends the following changes on this output:

Updating key performance indicator 1.1 to reflect new deliverables and future targets that are not captured in the current logframe.
C.1.3 Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

C.1.3.1 Recommendations from the previous AR
The previous AR recommended the following under this output:

Recommendation	Progress
Recommendation 1: Continue to support outstanding beneficiary communities to finalize insurance policies for piped water schemes already completed. (By June 2023). / UNDP to scale up the insurance initiative, collaborating with other partners such as UNICEF to come up with a policy brief that could be used lobby for the adoption of this as a national approach to sustainability. (By December 2023)	Still in progress –In pursuit of the most effective and efficient delivery model, programme spend more time learning from existing policies including consultations with government, local authorities, and insurance brokers. The model is now in place and costed. FCDO will provide additional funding as part of the business development strategy to roll out this. Full roll out should commence by June 2024 until June 2025.
Recommendation 2: Update milestones for the coming year in view of the risk around general elections. (By May 2023)	Completed – There were no major disruptions during the election period.
Recommendation 3: CAWEP should work up a plan and set aside resources to monitor thirty-five solar powered piped water systems installed in the past year. Monitoring will focus on functionality, aptitude of operation and maintenance structures put in place to keep then running and robustness of business models that have been put in place to help sustain these facilities. (By December 2023)	Not completed yet - Programme planning to make this as part of the light touch mid-term evaluation scheduled to take place on in the year 24/25.

C.1.3.2 Lessons learnt
The following is key lessons learnt under this output in the past year:
The multi stakeholder approach is effective as it facilitates speed in progress and project delivery as evidenced by the delivery progress in Mlibizi, where the district stakeholders are actively monitoring progress, and the progress in Hakwata where REF and the Ministry of Energy and Power development are hands on in the installation of the Photovoltaic (PV) array and the construction of biogas digestors.
C.1.3.3 Recommendations for the year ahead
In the coming year, this review makes the following specific recommendations under this output.
- Full roll out of the business development strategy (June 2024)
- Closely monitoring the functionality of established infrastructure. (Ongoing)
- Ensure technical trainings on operation and maintenance of irrigation equipment to ensure proper use (UNDP/Contractors) by June 2024
- Strengthening security of assets at all sites. UNDP to work with ZINWA and REA on this. The programme has a draft security strategy which should be implemented. This review is recommending ZINWA and REA to take up most of security responsibilities, acknowledging community limitations in providing maximum security. (March 2024)
- Work out the most appropriate and sustainable tariff system for water and power. The adopted tariff system should (i) motivate consumers to pay, (ii) balance affordability/ability to pay of consumers, (iii) be sustainable and able to cover maintenance costs and (iv) be replicable and demonstrate this as viable and attractive to others to adopt the models elsewhere. (UNDP, REA, ZINWA) by June 2024

Output Title	Established/resuscitated community governance structures are effective in managing installed infrastructure.
Output number:		2	Output Score:	A+
Impact weighting (%):		30	Weighting revised since last AR?

Indicator(s)	Milestone(s) for this review	Progress
2.1 No. of governance structures trained to operate, manage, and maintain installed infrastructure are operational. Disaggregated by community/ districts referred to as Asset Management Committees (AMCs)	8 AMCs	9 AMCs IMC (3), Garden Committees (5) / Energy Committee (1)
2.2 % of people in community governance structures who are women	65%	67%
2.3 % of representative community governance structures engage effectively with both community and external stakeholders, including maintenance service providers.	65%	78%
2.4 % of the households that pay for water and/or power use/maintenance.	60%	100%
2.5 % of targeted communities with a functional income generation/Business model to finance operation and maintenance	50%	100%
[note] Irrigation Management Committee

C.2 Briefly describe the output’s activities and provide supporting narrative for the score.
The purpose of this output is to empower communities to organise themselves and have full control, access and management of infrastructure built or upgraded through CAWEP. This is one of the programme’s key strategies to sustain built community water and energy infrastructure and the intended outcomes. In this review, all the five indicators exceeded expectations resulting in the output being scored an A+. It is encouraging to see 60% of households being able to pay for services. Field visits during the review period confirmed the existence of vibrant community-based structures that were set up to have an oversight of water and energy infrastructure. Most of them have demonstrated capability to mobilise and generate income for basic operation and maintenance. For example, in Binga district 39 groups with a membership of 434 (83 males, 351 females) cumulatively saved ZAR 37 411 and US$ 30,910 while in Hakwata, thirteen Village Savings and Lending (VSALs) groups comprised of 242 members (44 male and 198 female) have cumulatively saved ZAR 350,740.35 since May 2023 when they got support from CAWEP. While this looks very positive at this stage, the review noted that not all groups are articulate on how they would use some of their savings toward operation and maintenance of infrastructure. It was mostly well explained in Chipinge. If operation and maintenance funds are not ring fenced, there is risk that communities may fail to pay for basic repairs or provide security services as intended.

C.2.1 Challenges
Although there were no major challenges experienced in implementing activities under this output, there is potential challenge of savings not being used to fund operation and maintenance. This needs to be avoided. Continuous community sensitisation and regular monitoring could help in averting this challenge.

C.2.2 Describe any changes to this output during the past year, and any planned changes as a result of this review.
No changes were made to this output in the past year. This review is not recommending any significant changes besides strengthening the operation and maintenance fund management and ensuring community owned and inclusive business models. Please see section C.2.3.3 below for specific recommendations for the year ahead.

C.2.3 Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

C.2.3.1 Recommendations from the previous AR
The previous AR recommended the following:

Recommendation	Progress
Recommendation 1: CAWEP budget be allocated to support local production of agricultural produce, provide nutritional advice, technical support on productive use of renewable energy, to support women’s economic empowerment. This will ensure sustainability and success of the projects through enhanced community ownership and direct access & benefits to basic needs such as food and income. The programme should ensure and work with existing extension services. Local Government should be engaged to commit to complement this work by coordinating and providing extension services to local communities.	Still in progress – This is still being considered. It was put on hold in the year under review due to budget uncertainty. A decision is expected to be made by June 2024.
Recommendation 2: Track and understand possible barriers that could affect community capacity to pay for water and explore ways to support them.	Still in progress - Some barriers have been identified in the baseline survey and a plan to address these is being developed and will be implemented in the year ahead.

C.2.3.2 Lessons learnt
Members in community governance structures require more training for them to deliver on their mandate. Among the critical training is conflict and dispute resolution as the committees deal with conflicts that often arise.

C.2.3.3 Recommendations for the year ahead
Based on the findings of this review, the following recommendations are made under this output for the coming year:

- Ring fencing the operation and maintenance funding plan, ensuring funds are always there and an up-to-date record is kept. UNDP to help identifying how savings should be used for operations and maintenance. (March 2024)
- UNDP to ensure community-based business plans are inclusive and community owned to get maximum support and everyone’s contribution (ongoing)

Output Title	Enhanced Early Warning Systems (EWS), helping vulnerable communities to better anticipate, plan and respond to negative impacts of climate change and extreme weather events
Output number:		3	Output Score:	A+
Impact weighting (%):		20	Weighting revised since last AR?

Indicator(s)	Milestone(s) for this review	Progress
3.1 No. of districts/communities that receive EWS strengthening support from CAWEP. Disaggregated by type of support e.g. Hardware (Equipment), Software (Training)	16 Chipinge Chimanimani Buhera Makoni Mutasa Nyanga Binga Insiza Lupane Hwange Bubi Umguza Nkayi Chivi Tsholotsho Mutare	16 Chipinge Chimanimani Buhera / Makoni Mutasa Nyanga Binga / Insiza Lupane Hwange / Bubi Umguza Nkayi Chivi Tsholotsho Mutare
3.2 No. of people that regularly (monthly) receive and understand weather & climate information	100,000 Chipinge (40000) Binga (40000) Insiza (10000) Chivi (10 000)	172,554 Chipinge-10074 Binga 58086 Chivi 7626 Insiza 59538 Bubi- 2622 Buhera-336 Hwange-8064 Lupane -3540 Makoni-1998 Nkayi-18000 Tsholotsho-270 Umguza-2700

C.3 Briefly describe the output’s activities and provide supporting narrative for the score.
Through this output, CAWEP is seeking to build people and government institutional capacity to adapt to the effects of climate change and become resilient by supporting the setting up and upgrading of Early Warning Systems (EWS) in sixteen districts of Zimbabwe. The programme is improving the generation and use of innovative weather and climate information, enabling communities and governments to better understand, plan for and reduce the risks and impacts of climate change and of weather extremes, including from flooding and droughts. In the past year, the programme delivered this output as planned. Milestone for indicator 3.1 was met, sixteen districts were supported with Automated Weather Stations (AWS) and various enablers that improve transmission. Districts received training on the operation, data analysis, interpretation and how to maintain installed infrastructure. Indicator 3.2 exceeded expectations. An additional 72,554 people, over the 100,000 planned were reached with weather and climate information, mostly in vernacular language and were able to interpret and respond. Based on this performance, an A score is given on this output in this review. The scoring has also considered most of this work is recently delivered and need a longer period to be fully assessed on performance. This output was delivered in partnership with the Zimbabwe’s Meteorological Services Department (MSD).

C.3.1 Challenges
No significant challenges were experienced in delivering this output in the past twelve months.

C.3.2 Describe any changes to this output during the past year, and any planned changes as a result of this review
Under output indicator 3.2, the number of targeted districts increased from four planned districts to sixteen. The reason being a quick roll out of AWS installations across the targeted sixteen districts and made sense to do trainings alongside AWS installations. During field visits, reviewers had an opportunity to talk to trained community members who have used warning messages. Overall, they demonstrated competence in interpreting the messages and responding. Receiving the messages in vernacular dialects was very welcome. Besides updating the results on this output in the logframe, this review is not recommending any significant changes to this output although the performance of this output need to be continuously monitored and improved considering the output importance towards achieving the outcome on strengthening capacity to adapt to climate change and extreme weather.

C.3.3 Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

C.3.3.1 Recommendations from the Previous Annual Review
The table below show recommendations that were made on this output in the previous review. Progress on implementing these recommendations is also provided against each recommendation.

Recommendation	Progress
Recommendation 1: Ensure the foundation work is continued and built on so that the programme catches up and achieves the targets for the coming year.	Achieved
Recommendation 2: Preparing for unforeseen shocks such as funding delays. Programme should build in flexibility to respond to such shocks while still able to deliver this output.	Achieved. Output delivered without major challenges. Programme remains flexible to adapt to shocks.

C.3.3.2 Recommendations for the year ahead
To ensure the intended outcome on enhancing community adaptation is achieved and sustained, this review recommends the following for the year ahead:

Continuous monitoring of set up EWS functionality and use and address any technical, policy and social issues that prevent effectiveness or application. UNDP to continue assessing effectiveness of training methods and how well users demonstrate the skills after training.

Output Title	Improved National Climate adaptation policies/Strategies/learning material supported/developed
Output number:		4	Output Score:	B
Impact weighting (%):		10	Weighting revised since last AR?

Indicator(s)	Milestone(s) for this review	Progress
4.1 No. of policies or strategies developed/supported as a result of programme influence. Disaggregated by Type e.g., specific policy, strategy, learning paper, operational manuals	3 (National Adaptation Plan (NAP), Piped Water Scheme Protocol, Energy Efficiency Policy.	2 (National Energy Efficiency Policy, Piped Water Scheme Protocol)
4.2 No. of policy briefs developed using evidence generated by the programme to influence upscaling or changes to different approached to climate adaptation/resilience	0	0

C.4 Briefly describe the output’s activities and provide supporting narrative for the score.
This output is designed to improve the climate policy environment to help sustaining the overall outcomes and impact that CAWEP is aiming to achieve in Zimbabwe. To deliver this output, the programme is generating and using evidence from delivering the above outputs to (i) support and influence policy improvement and (ii) support implementation of policies on climate adaptation and resilience. The expectation at this stage was to have influenced and supported the finalisation of three key policies or strategies. However, CAWEP has only managed to influence and support two tangible policies as in the table above. In addition to the Solar Piped Water Scheme protocol that was supported through the programme, CAWEP contributed to the finalisation of the National Energy Efficiency Policy (NEEP), which is now before cabinet for approval. The programme contribution include.
1. Working with the Ministry of Energy and Power Development to align the NEEP with key national policies and strategies that have an impact on energy efficiency such as the National Renewable Energy Policy, Distributed Renewable Energy Policy, and other key sector policies in agriculture and climate change. CAWEP is directly affected by these policies, hence this support.
2. Simplifying the technical language largely used in the draft, making it easy to read and understood by a range of stakeholders or users.
Based on the above, this review scores performance of this output at B. While CAWEP continues to invest in helping Zimbabwe to deliver national adaptation priority actions in the revised Nationally Determined Contribution (NDC, 2021). These are:
1. Improving access to weather and climate information services.
2. Sustainable intensification and commercialization of agriculture through efficient irrigation systems,
3. Water use efficient systems and
4. Developing climate resilient infrastructure.
Finalization and approval of the National Adaptation Plan (NAP) is still outstanding. Supporting the development and implementation of NAP in Zimbabwe is aligned to UK’s policy position and commitment to help vulnerable countries to better adapt to climate change, hence a strategic policy that CAWEP should help deliver.

C.4.1 Describe any changes to this output during the past year, and any planned changes as a result of this review.
There were no major changes on this output in the past year. Neither is this review recommending any big changes on this output for the year ahead.

C.4.2 Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

C.4.2.1 Recommendations from the Previous Annual Review
The previous AR made the following recommendation. Progress on implementing this recommendation is also provided.

Recommendation	Progress
Recommendation: Identify and mention specific policies or strategies that could be influenced by delivering this programme. Indicators should also be updated accordingly. This review identifies the National Adaptation Plan (NAP) as one of the priority and relevant strategy CAWEP could engage with and influence the planning process and delivery. The programme team needs to work closely with the Government’s Climate Change Management Department to prioritise work that CAWEP can support. Explorations should continue to look at climate change mainstreaming in education, health, and agriculture sectors.	Partially achieved – Specific policies that can either help in sustaining CAWEP outcomes or contributing to national policy priorities have been identified. FCDO and UNDP continue to engage government on the NAP. Under this workstream, CAWEP is also supporting the National Clean Cooking Strategy.

C.4.2.2 Recommendations for the year ahead
FCDO/UNDP to continue lobbying the government on approval and finalisation of NAP. This is also important to help mobilising public and private financing for adaptation. (Ongoing)
## D: VALUE FOR MONEY

D.1 Key cost drivers and performance
Programme cost drivers are largely on direct programme delivery costs which is largely made up of procurement of goods and services on water supply, Automated Weather Stations (AWS), solar pumping, solar minigrid and household solar systems. Although procurement is still ongoing for other project sites such as Wanezi (Insiza) and Gororo (Chivi), the current trend shows no significant shift on cost drivers. Expenditure is still within the budget although from this review, there are additional activities that were not initially budgeted for that this review is recommending for additional funding to enable sustainability. UNDP continues to use the competitive bidding strategy on all procurement which helps in managing cost drivers.

D.2 Value for Money (VfM) performance compared to the original VfM proposition in the business case
The Business Case committed to assessing VfM during the life of the programme. It sets out clear VfM indicators for major costs drivers. Please see Annex 2. CAWEP is still tracking VfM using these indicators. This review finds that the programme is on course to deliver at good value for money. This is based on the following achievements under each of FCDO VfM parameters:

D.2.1 Economy: This review establishes that the competitive bidding that UNDP uses on procurement has helped in ensuring CAWEP buys goods and services of appropriate quality at the right price. For example, the programme has paid US$1,497,376.90 for all project components in Hakwata against the average market price of US$2,257,935 as determined by the programme feasibility study, based on data from the Ministry of Finance. Based on project site visits conducted during this review the quality of works on water and energy systems is good.
[note] Solar mini grid, Biogas digesters, Borehole Drilling, installation of the solar pumping systems, water reticulation and storage facilities to community and institutional water points, Ablution Facilities

D.2.2 Efficiency: As set in the Business Case, efficiency in CAWEP is measured by how well inputs are used to deliver sustainable outputs while avoiding unnecessary loss of resources including financial resources, time, human or natural capital. This review assessed the programme delivery strategies on each output and how well is expertise being deployed. This review observed several initiatives to improve efficiency. These include (i) UNDP continues to implement CAWEP directly in partnership with key government ministries and communities. This is recognising the limited budget against scope of works, (ii) using a relatively small budget to support the development of a strategic national energy efficiency policy which will have long term benefits on improving energy security and mitigating the detrimental effects of climate change and environmental degradation across all sectors of the economy, (iii) programme water project in Binga is directly improving efficiency through reducing water pumping costs. Through CAWEP, solar is now the primary power source for water pumping. The programme is also supporting with innovative water supply and demand techniques. Based on these examples, the programming is performing well on efficiency at this stage.

D.2.3 Effectiveness: Performance assessment in this review show that all outputs are largely being delivered as expected at this stage. In some cases, targets were exceeded. For example, 137 more multipurpose water and clean energy infrastructure were installed, and this has resulted in 149,652 people being supported to be more adaptive to effects of climate change at this stage against a target of 99,512. More social institutions have also with improved access to clean energy. This signals the programme effectiveness and showing the outputs are achieving the desired outcome on to helping people to better adapt to the effects of climate change and become more resilient.

D.2.4 Equity: Programme is performing well on equity. CAWEP is being implemented in marginalised districts that experience worst impacts of climate change. Equity performance indicators are being met. This review establishes CAWEP is helping to close the gap between on access to energy between school children in rural and urban areas. CAWEP is deliberately targeting women and female headed households with interventions such as biogas digestor, gardens, solar home systems and Village Savings and Lending (VSL) schemes. The project established nine Asset Management Committees (AMCs) and 66% of the committee members are female and they occupy key positions.

D.3 Assessment of whether the programme continues to represent value for money
Good progress being made on VfM indicators as described above show the programme delivering at good VfM, although this could still improve.

E: RISK

E.1 Overview of risk management
The overall risk rating for the CAWEP was moderate. All risks remained within FCDO risk appetite. Programme risk and associated mitigating strategies were updated every quarter as part of the formal reporting to FCDO. In addition, FCDO and UNDP used monthly progress meetings to review key or emerging risks ensuring the right mitigations are in place to minimise impact on the programme. This has resulted in the programme not experiencing any significant impact from identified risks. The table below shows main risks the programme anticipated in the year under review and mitigation put in place.

Risk Type and Appetite	Risk description, update, and mitigation actions
Strategy and Context / (Receptive & Moderate)	Risk: Restricted access to project areas due to political activities, especially during election period, causing delays in project implementation / Update: This risk did not materialise although the programme continued to monitor it throughout the election period. / Mitigation: If this had materialised, CAWEP was going to use strategic and implementing partnerships with government line ministries to get exemption.
Financial and Fiduciary / (Cautious & Moderate)	Risk: Risks of financial exposure and abuse of project budgets by partners (contractors, UN Staff) leading to funds misappropriation. / Update: There is no evidence of this risk happening in the past year, although it remains a live risk that the programme continues to monitor closely. / Mitigation: 1. UNDP undertakes extensive supplier/contract checks. / 2. Direct payment modality is being used where UNDP make the payments direct to the suppliers upon receiving requests with full support documents from the Government Partners.
Safeguarding / (Cautious & Moderate)	Risk: Programme activities causing negative environmental and social impact including land degradation, disruption of social norms and values and specific. Contractors and partner staff exploiting communities. / Update: Minimal disruptions on the environment were experiences at project sites. Environmental/conservation practices are embedded in ongoing works. / Mitigation: Adopting conservation agriculture practices, implement pollution prevention approaches; materials handling and control procedures; Reputable contractors with good track record on environmental management and have ISO 140001 certification are engaged.
Environment (Cautious, moderate)	Risk: Impact of El Nino (drought, extreme heat) result in extensive crop failure, livestock death and other heat stress related diseases. / Update: The delay in the start of the rainfall season is attributed to El Nino phenomena. The impact is yet to be established. Negative impacts are still expected despite significant rains received across the country. / Mitigation: CAWEP is working on contingency plan to minimise the impact on the programme. Actions include using programme structures to disseminate of early warning messages to targeted communities, climate proofing infrastructure, and capacity building of communities and government entities and invoking localised crisis modifier interventions
Reputational / (Cautious & Moderate)	Risk: Politicisation of support which may exclude deserving and vulnerable people from participating in the project. / Update: There is no evidence to suggest this risk materialised during the year. / Mitigation: / UNDP ensured the selection was clear for all project participants at local and national levels. They Involved appropriate and diverse actors to ensure that decisions are made with clear rationale. 2. UNDP ensured inclusion of vulnerable groups (elderly, youth, women and disabled) into local management committees ensuring their voices were heard. 3. Branding of materials used by partners during the intervention. 4. CAWEP work continued to be amplified on FCDO, UNDP & UNICEF Social media platforms such as twitter and Facebook.
[note] Internationally recognized standard for environmental management systems (EMS). It provides a framework for organizations to design and implement an EMS, and continually improve their environmental performance. By adhering to this standard, organizations can ensure they are taking pro-active measures to minimize their environmental footprint.

In the coming year, the programme will continue to track most of the above risks and will continue to watch out for new risks.

E.2 Update on Partnership Principles
It remains UK policy that no UK aid should be under the management or direct control of the Government of Zimbabwe. The Partnership principles are reviewed regularly. FCDO’s contribution to the CAWEP programme is in line with this policy and no UK money is used to directly fund the Government of Zimbabwe.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

F.1 Programme Overview
The full Business Case value is £19,550,000, funding the delivery of four different components. This review assessed delivery, commercial and financial management of the main and currently active component on Community Water & Renewable Energy Infrastructure & Early Warning Systems (EWS). UNDP is implementing this component with £12,000,000 funding from FCDO. By 31st December 2023, FCDO disbursed £8,298,634 which is 69.2% of the total project budget.

F.1.1 Financial Management
UNDP are responsible for day-to-day financial management of programme finances and submit monthly and quarterly reports to FCDO for review and approval. This review assessed financial performance over the past year. Key findings are that the programme is spending as planned and no slippages were observed. The programme ended the year with all forecasted funds being paid. Resource accounting was used under this programme. FCDO analysed payment requests and invoices to ensure that they comply with programme delivery rules. A financial quarterly report covering up to the end of December 2023 was provided and showed the total expenditure to date and the balance of the disbursed is already committed. The most recent UNDP audited financial statement on CAWEP issued in May 2023 show UNDP is satisfactory in audited areas which are finance, human resources, procurement, asset management cash management and general administration.

F.1.2 Progress on partnerships
Success achieved so far on this programme is attributed strong and working partnership between FCDO and UNDP. The partnership between the programme and government departments has been very effective. Besides technical and policy expertise different government departments provided over the year, there were also financial contributions from the government’s Rural Electrification Agency. CAWEP is working effectively with the Ministry of Energy and Power Development in the construction of biogas digestors where the ministry provided training costs for 20 biogas masons and provided food and accommodation for the trainers.

F1.2 Asset monitoring and control
CAWEP, through UNDP holds an accurate and up to date asset inventory for the vehicles, laptops, printers, and office furniture. As per the Due Diligence Assessment and Framework agreements UNDP provides assurance to FCDO on all asset procured with FCDO funds. In the past year no asset has been lost

F1.3 Governance and Accountability
The programme Steering Committee (SC) is the highest programme decision making body and provides strategic guidance to programme implementation. It is co-chaired by FCDO and the Government of Zimbabwe through the Ministry of Environment, Climate and Wildlife. In the past year, the SC met four times as planned to review progress and made strategic decisions on several issues including the programme business development strategy and policy work such as the National Energy Efficiency policy. UNDP are the programme management unit and are accountable to the steering committee.

F1.4 Programme Branding
UNDP has demonstrated an understanding of FCDO branding guidance as evidenced by the erection of billboards in Hakwata area in Chipinge. During field visits, verbal statements were used to acknowledge UK support with beneficiaries displaying full knowledge of FCDO.

G: MONITORING, EVIDENCE AND LEARNING

G.1 Monitoring
Monitoring and evaluation remained an important part of the programme, enabling FCDO, UNDP and government partners to (i) provide technical, policy and strategic advice and (ii) tracking progress towards delivering outputs and outcome. Field visits, quarterly review meetings and progress report analysis were the main activities used to monitor programme performance including assessing the operating context and risk management. FCDO and the Programme Steering Committee conducted two joint quarterly field visits to project sites in Binga and Chipinge districts. Both visits provided technical and strategic recommendations that continue to guide programme delivery. In the past year, the programme trained district and provincial stakeholders on monitoring and evaluation, empowering them to regularly monitor projects. The training includes designing monitoring tools, data analysis and reporting. The aim is to help them understand and be accountable to the change the programme would like to achieve.

G.2 Evidence
CAWEP delivery approach and objectives are still built on original evidence used at design stage which remain relevant to the programme. This includes the UK’s’ best buys’ paper on climate change, Global Climate Risk Indices reports (2021-22) and several other pieces of evidence. The programme continues to look for more evidence that can help to improve and consolidate CAWEP work to achieve sustainable outcomes and impact. The focus is on evidence that helps to come up with business models that can be used sustain multiple water and energy infrastructure. This evidence will be crucial for policy influencing and support.
G.3 Learning
Learning is an integral part of CAWEP given the programme’s intention to support and influence national policies on climate change adaptation and resilience. In the coming year key learning areas that CAWEP will focus on are:

1. Effectiveness and impact of taking a multidimensional approach using water and renewable energy to help people to adapt and become more resilient through enhancing outcomes on livelihoods, health, education, nutrition, entrepreneurship,
2. Sustainability built around business models on renewables, irrigation, and markets, private partnerships and working with Micro Financial institutions.
3. Understanding the impact of low-cost approach to adaptation through Early Warning Systems (EWS) and institutional systems strengthening on climate adaptation? The programme would like to understand if there is a risk of maladaptation if implemented in isolation.
4. Understanding the cost and affordability of climate proofing and what innovation is needed to make it affordable? It also involves identifying opportunities for the private sector in climate adaptation?

This learning is expected to help shaping the wider FCDO and Zimbabwe’s approach to climate change policy and programme strategies. Drafting of learning products will happen in the year ahead. Some learning will help in shaping policy briefs that will be used to recommend policy improvements and best practices.

Date of last narrative financial report	31 December 2023	Date of last audited annual statement	May 2023

    Annex 1 Annex 2