Programme Completion Review

Title: Appui au Système de Santé en République Démocratique du Congo (ASSR) – Support to the health system in the Democratic Republic of Congo (DRC)
Final Programme Spend £ (full life): £53,272,932.24 (against original budget of £54,000,000)	Review Date:	24/05/2022
Programme Code: [AMP ID#] 300158	Start Date: 01/04/2019	End Date: / 31/03/2022

Summary of Programme Performance

Year	1 / April 19 – March 20	2 / Sept 20 – Sept 21	3 / Sept 21 – March 22
Programme Score	A	A	A+
Residual Risk Exposure Rating	Major	Major	Major

DevTracker Link to Business Case (and any addendum):	https://devtracker.dfid.gov.uk/projects/GB-GOV-1-300158
DevTracker Links to all logframes used during programme lifetime:	https://devtracker.dfid.gov.uk/projects/GB-GOV-1-300158

## List of Acronyms
AC	Animateur Communautaire (Community Facilitator)
ADRA	Adventist Development and Relief Agency)
ASSP	Accès aux Soins de Santé Primaires (Access to Primary Health Care)
ASSR	Appui au Système de Santé en RDC (Support for Health Systems in DRC)
BCZS	Bureau Central de Zone de Santé (Office of the Health Zone Team)
BEK	British Embassy Kinshasa
CBA	Cost–Benefit Analysis
CDR	Centrale de Distribution Régionale (Regional Distribution Centre)
CODESA	Comité de Développement de l’Aire de Santé (Health Development Committee)
CYP	Couple Years of Protection
DHIS2	District Health Information Software two
DiD	Difference in Difference
DPS	Division Provinciale de Santé (Provincial Directorate of Health)
DRC	Democratic Republic of Congo
DSNIS	Division du Système National d’Information Sanitaire (Directorate of National Health Management Information System)
ECC-DOM	Eglise du Christ au Congo (Church of Christ in Congo)-Direction des Œuvres Médicales
ECZS	Équipe Cadre de Zone de Santé (Health Zone Management Team)
EmONC	Emergency Obstetric and Newborn Care
ESPK	École de Santé Publique de Kinshasa (Public Health School of Kinshasa)
EUP	Etablissement d’Utilité Publique
FCDO	Foreign, Commonwealth and Development Office
FOB	Free on Board
HGR	Hôpital Général de Référence (General Referral Hospital)
HRH	Human Resources for Health
HMIS	Health Management Information System
ICP	Infection Control and Prevention
iHRIS	Health Workforce Information Systems Software
IMA	IMA World Health
IPT	Intermittent Preventive Treatment - Malaria
IPS	Inspection Provinciale de la Santé (Provincial Health Inspection)
LQAS	Lot Quality Assurance Sampling
M&E	Monitoring & Evaluation
MoH	Ministry of Health
MSP	Ministère de la Santé Publique (Ministry of Public Health)
PCR	Project Completion Review
PEP	Post-Exposure Prophylaxis
PPE	Personal Protective Equipment
ReCo	Relais Communautaire (Community Health Worker)
RUFT	Ready to Use Therapeutic Food
SGBV	Sexual and Gender-Based Violence
SNIS	Système National d’Information Sanitaire (National Health Management Information System)
ToT	Training of Trainers
TPM	Third-Party Monitoring
UHC	Universal Health Care
VfM	Value for Money
ZS	Zone de Santé (Health zone)

## A: Summary and Overview
Description of the programme and what it has achieved
The Foreign, Commonwealth & Development Office (FCDO)’s health programme, Appui au Système de Santé en République Démocratique du Congo (ASSR) (Support to the health system in the Democratic Republic of Congo (DRC)) was established in April 2019 and aimed to support 10 million people living within 50 health zones in 4 provinces (Kasaï, Kasaï Central, Nord Ubangi and Maniema) to increase access to quality healthcare.
[note] Out of a total of 26 provinces and 516 health zones nationally. The 50 supported health zones have 50 hospitals (hôpital general de reference – HGR) and 1,679 health centres (Centres de santé) and clinics (Postes de santé)
The programme had three components:
1. Health system strengthening and support for delivery of basic services focusing on improving maternal, new-born, child and adolescent health (up to £51,000m).
2. Health Emergency Preparedness and Response. This started in March 2020 and used £4.5m (£3m in the programme which was budgeted for health emergencies and £1.5m reprogrammed from savings) to fund an emergency public health response to the COVID-19 pandemic in 15 health zones of Kinshasa city/province (epicentre of the outbreak in DRC) and to a lesser extent in Kasaï, Kasaï Central, Nord Ubangi and Maniema provinces.
3. Third-Party Monitoring (TPM) and operational research mechanism (up to £1m), implemented from December 2019 to June 2022 was used to provide an enhanced monitoring function due to FCDO access issues, results validation, and operational research
ASSR was initially designed as an 18-month bridging programme to bridge the gap between FCDO’s previous health programme Accès aux Soins de Santé Primaires (Access to Primary Healthcare, ASSP) and a successor health programme in DRC. It was delivered through a consortium led by International Non-Governmental Organisation (INGO) IMA World Health (with downstream partner SANRU, and with technical assistance from Pathfinder and BAO systems) and was supported by a Third-Party Monitoring (TPM) consortium contract managed by HERA (with downstream partners of BlueSquare, AidWorks and the Kinshasa School of Public Health). The COVID-19 component was delivered through IMA, ECC/DOM, Armée du Salut and ADRA in Kinshasa.
ASSR was due to commence in April 2019 and was expected to implement for 18 months until September 2020. However, the programme got off to a slow start. Output 1 did not start full implementation until July 2019 due to late finalisation of the contract (end of April 2019) and output 3 in December 2019. Delays were also driven by a breakdown in the supply chain for malaria commodities and delays in the completion of baseline surveys for some indicators. The programme was extended twice, initially from October 2020 to September 2021, with exit from Maniema reducing the number of covered health zones to 40 and the supported population to 9.25m. A second extension saw implementation continue from October 2021 to March 2022.
This Programme Completion Review builds on previous Annual Reviews, and should be read in conjunction with:
Annual Review 1 – 2019: https://iati.fcdo.gov.uk/iati_documents/54292138.odt
Annual Review 2 – 2020: https://iati.fcdo.gov.uk/iati_documents/60770302.odt

 DRC remains a challenging operating environment, with some of the highest maternal and infant mortality rates in the world. Historically women have given birth at home without a trained attendant. However, today a host of cultural and clinical factors contribute to (improving but still comparatively poor) maternal and infant mortality rates. These include a limited workforce (especially trained midwives), varied levels of competence and poor quality of care. Some women may not be able to access facilities due to lack of money (either for transport or to cover traditional in-kind service fees of food, livestock, soap etc.); men traditionally control household funds and may decline to invest in facility-based births.
Additionally, ASSR faced two major events: (i) the global COVID-19 pandemic beginning in 2020, (ii) the strike of non-physician health workers in 2021.
Systemic weaknesses in the health system also made delivery more challenging, including: (i) supply shortages and irregularity of drug availability; (ii) reliability of staff receiving salaries and risk-based top-ups (primes de risque) from government; (ii) delays in payment to facilities to reimburse care provided to the poor; (iv) delays in payment to zonal provincial teams to support supervision. Despite this, ASSR delivered well on core outputs and was able to successfully adapt to address the COVID-19 pandemic in the targeted provinces as well as to open activities in Kinshasa which was the epicentre.
Key results over the programme include:
- 860,082 pregnant women received three doses of intermittent preventive treatment (IPT) anti-malarials during antenatal care;
- 860,085 “Couple Years of Protection” (CYP) were provided through the provision of modern contraceptive methods to protect against unwanted pregnancies;
  [note] Couple Years of Protection (CYP) is a measure that estimates the protection from pregnancy provided by contraceptive methods during a one-year period. Different methods such as a year-long course of the contraceptive pill, or approximately 120 condoms can be provided to make up one CYP. A 5-year IUD provides 3.3 CYPs, or a 3-year implant provides 2.5 CYPs.
- 1,122,968 labour deliveries were assisted by a skilled birth attendant;
- 1,015,289 children were immunised against measles; and
- Prevalence of malnutrition fell from 7.7% in Q1 to 4.3% in Q12 in Kasaï Central, Kasaï and North Ubangi.
Pivoting to support the response to the COVID-19 pandemic in four provinces, including the capital Kinshasa. The programme facilitated response coordination at the provincial and health zone level, and provided personal protective equipment to 594 health facilities in the context of global supply shortages. Major lessons learned, evidence generated and recommendations:
1. The availability of essential medicines, a motivated and well-trained workforce force and community engagement are essential to build trust with communities and to build demand for quality health services;
2. The functionality and reliability of the supply chain for medical products and commodities remains a major challenge to the provision of essential health services. FCDO should continue to work with key stakeholders to improve the procurement, supply, and quality assurance of health commodities that underpin the availability of essential services, working through core systems where feasible to avoid parallel systems.
3. A functional Human Resources for Health (HRH) database (such as the iHRIS system implemented by ASSR/P) is vital to unlock significant efficiencies in health financing; to mitigate risks of corruption; and to ensure that the allocation of human resources reflects demand for services. However, to ensure sustainability and realise the benefits of a HRH database, future investments must achieve both a high-level political commitment and scale. FCDO should continue to make an investment case and advocate to key decision makers for the implementation and scaling of iHRIS.
4. The implementation of an affordable and transparent flat-rate user fee (tarification forfaitaire) enhances access to services, but is not sufficient to reach the poorest;
5. Community engagement is central to health promotion, building demand for health services and strengthening accountability between communities and health service providers. For example, Community Health Workers (Relais Communautaires - ReCo) played a key role in empowering communities to grow and use locally available foods in support of the cost-effective management of moderate and severe acute malnutrition.
6. The FCDO’s future provincial governance programme should coordinate closely with future health and education activities to address systemic issues (e.g. human resource management) that undermine sustainable service delivery.
7. FCDO should incorporate a stronger Value for Money (VfM) analysis at the beginning of future health sector investments, developing a VfM framework and better integrating VfM into working practices to implement and assess VfM of both service delivery and health system strengthening.
How this review was conducted
This review was undertaken by the British Embassy in Kinshasa’s Human Development Team, with supporting evidence drawn from third party monitoring and IMA reports. Assessments were undertaken by health advisers, programme managers, risk, results, and commercial specialists.
Actions following approval of this report
Following the approval of this report, it will be uploaded to Development Tracker and shared in final copy with delivery partners and key stakeholders. Lessons learned have already been fed into the development of the successor health programme and will be monitored for their ongoing operationalisation by the Human Development Team.

## B: Theory of Change and Outcome Assessment

Outcome Indicator	Target	Achieved	Achieved against target	Expectations Met
1. Number of pregnant women who received three doses of Intermittent Preventive Treatment (IPT) while attending antenatal care	751,908	873,402	116.2% / (+121,494)	Substantially exceeded expectations (A++)
2. Percent of births at surveyed health facilities for which required elements of partograph were correctly completed	70%	82%	+12%	Substantially exceeded expectations (A++)
3. Number of 1-yr-old children vaccinated against measles (KPI)	901,403	1,015,289	112.6% / (+113,886)	Substantially exceeded expectations (A++)
4. Number of Couple Years of Protection (CYPs) achieved through family planning service provision	801,599	860,082	107.3% / (+58,483)	Moderately exceeded expectations (A++)

Outcomes, Value for Money and Sustainability
Outcomes
Overall, the programme substantially exceeded outcome expectations and delivered Value for Money (VfM). Under the first outcome indicator, 873,402 pregnant women received three doses of intermittent preventative treatment for malaria. This substantially exceeded expectations, and represented 116.2% of the target, and an average end-of-project coverage of 77% of expected pregnant women. Under outcome indicator 2, a survey to evaluate maternal health services in health facilities was scheduled every six months. The proportion of deliveries with correctly completed partographs increased from 11% (first survey), to 49% (second survey), to 72% (third survey) and finally to 82% (in the fourth and fifth surveys). For outcome indicator 3, 113% of the projected target children were vaccinated against measles. This also represents an average end-of-project vaccination coverage of 102% of expected children. Finally, under outcome indicator 4, 860,082 couples were protected for one year from unwanted pregnancies using modern contraceptive methods which represented an overall achievement of 107% against the planned target. High levels of achievement under outcome indicator 4 were underpinned by family planning campaigns carried out in all health zones and re-training of community-based distributers.
A rapid impact assessment reviewing data from the National Health Management Information System (SNIS) and using a ‘Difference in Difference (DiD)’ methodology found that ASSR supported Health Zones slightly outperformed zones supported by other donors and substantially outperformed those zones which received no external support across key outcome indicators (see Table 1 below). The impact assessment found that over the lifespan of the project, 5,713 additional facility-based maternal deaths were avoided in ASSR supported health zones compared to non-supported zones. ASSR supported health zones in 3 provinces also proved more resilient (demonstrating better outcomes) throughout a prolonged health workers’ strike in 2021.
[note] Whilst the difference observed in the impact assessment suggest the programme contributed to better outcomes in supported health zones (i.e. lower maternal and child mortality), there are factors that the methodology could not control for (such as socio-economic characteristics across health zones) that may, in part, also account for these observed differences.
Table 1: Differences over the first 33 months of the ASSR project of outcome indicators and maternal and neonatal facility-based mortality rates between ASSR supported and non-supported control health zones.
Outcome	Indicator	Cumulative difference over the first 33 months of the ASSR project
1	Number of pregnant women who received three doses of IPT while attending antenatal care (KPI)	+145 women /100k pregnant women/year
3	Number of children under 1 year of age that have received the measles vaccine (KPI)	+274/100k targeted children/year
5	Number of couple years of protection (CYPs) achieved through the provision of family planning services (KPI)	+2885/100k people/year
Maternal mortality	Facility based maternal mortality rate per 100K facility based live births	-3,343/100k facility based live births over 33 months
Neonatal mortality	Facility based neonatal mortality rate per 100K facility based live births	-13,672/100k facility based live births over 33 months

Figure 1: Number of pregnant women who received three doses of IPT while attending antenatal care supported by ASSR (orange line) as compared by facilities supported by other donors (blue line) or facilities with no external support (green line):

Despite budgetary constraints, IMA piloted new innovations throughout the programme duration. Notably, a moto-ambulance service for emergency transport in Nord Ubangi and a clinical mentoring initiative for emergency obstetrics and neonatal care (EmONC) demonstrated encouraging results. In addition, data on nutritional status from the earlier ASSP project showed that the programme’s approach to addressing moderate and acute malnutrition achieved significant measurable impact and high value-for-money. The model is now being considered by other donors for scale-up across other provinces.
Figure 2: Number of deliveries attended by a skilled birth attendant (KPI) through ASSR supported facilities (blue line) as compared to facilities supported by other donors (green line) or with no external support (orange line)

Value for Money (VfM)
As with its programme predecessor (Accès aux Soins de Santé Primaires ASSP) we assess that the ASSR programme has delivered strong value for money: this is assessed through the lenses of economy, effectiveness, efficiency and equity:
Economy
It is notable that the economy of ASSR has increased when compared to earlier programme phases. Achievement against outcome level indicators has largely met (or exceeded) expectations, despite a dramatic (>50%) reduction in investment when compared with previous programme phases. The overall investment per capita during ASSR Extension I is calculated at £ 1.06. By comparison, ASSP expenditure was estimated at £3.66 per capita. The continued attainment of outcome targets, despite a reduction in per capita investment, partly reflects the benefit the ASSR programme derived from earlier FCDO capital investment in health infrastructure and equipment and demonstrates the cost-effectiveness of a long-term and systems approach to health system development.
The capping of overheads/non-programme attributable costs at 10% of overall costs contributed to safeguarding VfM. Throughout the life of the programme, human resources and office costs were a significant proportion of programme management costs. IMA reduced these costs over the programme’s lifetime by changing their resourcing structure and integrating downstream partner SANRU’s technical staff into IMA’s hierarchy and office space. This eliminated staffing duplication and improved coordination of activities.
Programme economy was also strengthened by high-value advances in the quality of the procurement and supply chain management which reduced stock-outs and wastage of medicines and essential medical commodities. The total value of drugs expired during the 4th quarter of ASSR Extension I was $14,200, representing just 0.27% of the value of unexpired stock available at provincial warehouses at the end of the quarter. This was well within the target range of less than 2% (Output indicator 5.3). Across the duration of the programme IMA reported a reduction of expiry of medicines/commodities from 2.5% to 0.1%.
Programme inputs to support nutritional rehabilitation of children with severe and moderate acute malnutrition have also demonstrated outstanding economy. Interventions including home visits, nutrition counselling, home gardening and use of locally grown foods have proven effective at a fraction of the cost ($1.73 per child recovered) when compared with intervention based on internationally available Ready to Use Therapeutic Foods (RUTF), where optimised costs can exceed $70 per recovered child. Furthermore, the programme has generated preliminary evidence that suggests a regime of home visits and counselling on the use of locally available foods can deliver recovery rates which exceed those delivered by commercially available RUTFs. A planned FCDO supported results validation exercise will interrogate and evidence these findings further.
[note] RUTF is an energy-dense, mineral- and vitamin-enriched food that requires no preparation and is specifically designed to treat severe acute malnutrition (SAM).
[note] Economic evaluation of a reduced dosage of ready-to-use therapeutic foods to treat uncomplicated severe acute malnourished children aged 6–59 months in Burkina Faso; Dieynaba S. N'Diaye et al.; Maternal & Child nutrition, 2020
Effectiveness
Effectiveness (the extent to which programme outputs realise outcomes) was high. Outcome targets were (except for outcome 4) exceeded at a per capita cost of between £1.00-£3.50 across the duration of the programme. This is a greater than 50% reduction compared with earlier programme phases and, considering the comprehensive nature of basic quality healthcare the programme supported, is significantly lower than the sub-Saharan average health expenditure per capita ($79.36 in 2019).
[note] The programme per capita figure excludes significant governmental, donor and individual health expenditure
Other evidence of programme effectiveness includes a measurable increase in the availability of quality basic and comprehensive Emergency Obsetric and Newborn Care (EmONC) from a baseline of 11% (November 2019) to 86% (August 2021).
Efficiency
As outlined above, the achievement of target outcomes at a greatly reduced cost compared with earlier programme phases demonstrates that significant efficiencies were realised under ASSR. Continued efforts to ensure programme efficiency were rooted in the implementation of evidence-based and highly cost-effective primary and public health care interventions, as per the business case. For example, during the programme 291,554 pregnant women received three doses of Intermittent Preventative Treatment (IPT) for malaria at a cost to the project of £ 1.05 per pregnant woman. Data from comparable contexts suggest that IPT is a highly cost-effective intervention; one study found that per 1000 pregnant women treated, 22 neonatal deaths; 56 outpatient consultations and 4.5 malaria admissions were averted.
[note] Cost-Effectiveness of Intermittent Preventive Treatment of Malaria in Pregnancy in Southern Mozambique; Sicuri et al.; PLoS One. 2010; 5(10): e13407.
Programmatic choices to increase efficiency included consolidating implementing partners into one office space and significantly reducing project staff and combining responsibilities in provinces (e.g. pharmacist/logician).
Equity
Advancing more equitable access for the poorest to affordable, quality healthcare was an important objective of the ASSR programme. The programme has supported more equitable health provision in target provinces, but there remain significant challenges.
District Health Information System 2.0 (DHIS2) is an open-source health data management system used in more than 50 countries to collect national public health data. ASSR support in the deployment of DHIS (infrastructure, IT and telecommunications equipment/maintenance, training) increased the availability of quality health information with the proportion of health zones submitting quality data on a regular basis increasing from a baseline of 65% of health zones to 85% over the programme period.
ASSR’s main intervention to improve equitable access to care is through the negotiation and agreement of flat rate user fees (tariffication forfaitaire). This has increased access to affordable healthcare, but also faced a range of implementation challenges detailed under Output 6 below. The programme has also implemented a reimbursement system to fund free care for the poorest by providing a monthly payment of $50 per health centre and an average of $1,000 per hospital. During the lifespan of the project, 311,377 ‘individuals most in need’ were assisted in health facilities and hospitals supported by ASSR. This data is captured routinely in the health management information systems but is not disaggregated by age, gender or socio-economic status, which limits the extent to which a fuller analysis of equity can be undertaken.
The programme’s support and revitalisation of participative community structures for health has also contributed to equity. For example, the programme has increased women’s representation and leadership in health area development committees (CODESA). Other initiatives that have sought to strengthen the programme’s contribution towards gender equality and social inclusion include the launch of a “clean cook stove” initiative to support women in providing for their families; consultations with women on the gender responsiveness of building plans for new clinics; provision of water cisterns in safe locations to reduce the risk and incidence of violence for women and girls fetching water; and provision of birthing kits to encourage facility-based deliveries.
Sustainability
The continued achievement of outcomes during ASSR, despite a greater than 50% reduction in overall funding, demonstrates the sustained impact of earlier capital investments during predecessor programme ASSP. This suggests that ASSP’s goal to invest for long-term sustainability was, to some extent, realised.
One example of sustainable programme inputs that have yielded benefits throughout 2 programme phases can be seen in the programme’s enabling support to vaccination. 320,764 children under 1 year of age received the measles vaccine in supported health zones during the project period, in close coordination with GAVI. The per capita cost of measles vaccination is valued at £0.97 per child. This low cost is underpinned by FCDO investments to improve the cold chain (for vaccine storage) with direct drive solar refrigerators that do not require batteries. Such capital investments in cold chain infrastructure have an expected durability of 10-15 years and will therefore help to sustain the effectiveness and low overall cost of vaccination in targeted areas.
Programme inputs to strengthen the management of human resources for health are central to building a sustainable health system. ASSP introduced new human resource management software (iHRIS) to support the improved management of health workers. An initial pilot of the software in 4 provinces enabled the identification of a significant number of ‘ghost workers’ on existing payrolls, unlocking a saving to the government of $82,884 per month. This was subsequently reallocated to support salary payments, bringing 780 previously unremunerated health workers onto payroll. iHRIS’s application in human resource management has the potential to unlock transformative, long-term and sustained impact in the development of a skilled, incentivised and affordable workforce.
However, whilst ASSR and earlier phases of FCDO investment have sought to deliver sustainable outcomes, longer term sustainability rests on increased domestic expenditure for health. DRC cannot sustain its health service with continued low and stagnating levels a government health expenditure of around £2.7 per capita which risks undermining equitable, affordable and quality health care. The UK continues to advocate with the government of DRC for greater allocations and transfers to the health sector, alongside improved efficiency, in order to improve the sustainability of these services.
[note] In 2021, the DRC population was estimated at 92.3m (https://knoema.com/atlas/Democratic-Republic-of-the-Congo/Population) and the Ministry of Health (MoH) executed budget at £341m, out of which £86m were external resources (source: FCDO Public Financial Management Support Technical Assistance). The MoH own budget was thus £255m or £2,7 per capita or £3.7 if external resources are included.
#### Summarise the programme’s theory of change and results framework including any change to outcome indicators.
The overall impact statement for ASSR is to ensure a reduction in mortality and morbidity of women, adolescents, children and newborns and the building of human capital through a stronger health system and empowered communities. Its high-level outcome is that women, adolescents, children and new-borns benefit from improved nutrition and access to quality basic health services and the health system is better prepared and able to respond to health-related emergencies. The Theory of Change (ToC) has not been changed over the lifetime of the project.
ASSR annual reviews and this PCR find that programme inputs have, in general, consistently supported the attainment of expected results (outputs) and contributed to the realisation of outcomes.
Inputs to directly support health service delivery (the procurement of medicines & commodities, enhanced technical supervision and training) have consistently delivered expected outputs and contributed to improved access to better quality health care at outcome level. However, varied implementation of flat rate pricing (which is contingent on political will and domestic health financing) continues to limit the long-term sustainability of improved access to health care.
Inputs in support of the improved availability and access to medicines and commodities including family planning have consistently delivered expected outputs and contributed to quality care. However, gains remain fragile and sustained engagement to further strengthen supply chain management and health outcomes is necessary.
Programme support to increase the availability of health information and human resource management information have improved the quality and availability of management information. However, this has not yet fully translated into improved use of data for planning and decision making or realisation of strengthened governance as per the theory of change.
FCDO recognises that major investments in information management systems (for human resources and health information) are critical to enabling health system reform, and to building a sustainable health system capable of delivering quality, affordable and equitable care. However, to achieve sustained impact at outcome level both investments rely on achieving scale, ensuring that data inputters and decision makers derive value from systems, and sustained investment in training and infrastructure. At the conclusion of the programme, it is clear that achieving the improved use of such information for decision making requires a longer-term timeframe and depends on wider inputs, reforms and political will that underpins improved governance. This should be more explicitly recognised in the theory of change for future programmes (e.g. through intermediate outcomes).
For example, work to strengthen human resource management for health through the iHRIS system has begun to demonstrate value but has not yet achieved transformative impact. Experience from the programme highlights that, despite improvements in the accuracy and availability of human resource management information, there is limited evidence that this has improved management practices. For example, the proliferation of political appointments of health workers has continued, despite clear evidence from the iHRIS database highlighting the inequitable (and in some cases excess) distribution of sometimes unqualified staff. Continued efforts to scale iHRIS must be coupled with sustained engagement to improve governance and demonstrate the benefits that improved human resource management can unlock for government at every level.

## C: Detailed Output Assessment

Output Number and Title	1. Service Delivery: enhanced health service delivery and quality in FCDO-supported health zones
Output Score	Moderately exceeded expectations (A+)
Impact weighting (%)	50%	Impact weighting revised since last AR?	Yes, increased from 46%

Output Indicator	Quarters	Baseline	Final Logframe Target	Final Result Achieved	Achieved against target	Expectations Met
1.1 – Number of deliveries attended by a skilled birth attendant (KPI)	All	96% of expected deliveries	Final target 100% of expected deliveries / (Cumulative total of 1,050,513 expected deliveries over programme period)	107% of expected deliveries / (Cumulative total of 1,122,968 actual deliveries)	+72,455more deliveries than expected	Moderately exceeded expectations (A+)
1.2 – Service utilisation for curative services, number of consultations	All	63% (numerical data not available)	64% service utilisation / (Cumulative total of 16,161,683 consultations)	106% service utilisation / (Cumulative total of 18,692,814 actual consultations	+42 percentage point achievement over target / + 2,351,131 more consultations than expected	Substantially exceeded expectations (A++)
1.3 – Average proportion of children between 6 and 59 months screened for malnutrition by community volunteers each month	All	7%	85% of eligible children screened each month	110% of eligible children screened each month	+25 percentage point achievement over target	Substantially exceeded expectations (A++)
[CLOSED] – 1.4 Number of pregnant women and children under one year of age who received a long-lasting insecticide-treated bed net (LLINs) through routine distribution	The original indicator 1.4 was dropped with the first extension of ASSR, Q7 (Oct-Dec 2020) due to its reliance on Global Fund supply chain consistency which proved a challenge throughout the programme and was outside of IMA’s control.
[NEW] – 1.4 Recovery rate of malnourished children between 6 to 59 months at 5th visit (Source: SNIS community level)	Q4	N/A	50%	50.5%	+0.5%	Met expectations (A)
	Q5		50%	62.9%	+12.9%	Moderately exceeded expectations (A+)
	Q6		50%	60.8%	+10.8%	Moderately exceeded expectations (A+)
	Q7		50%	59.1%	+9.1%	Moderately exceeded expectations (A+)
	Q8		50%	60.9%	+10.9%	Substantially exceeded expectations (A++)
	Q9		50%	63.8%	+13.8%	Substantially exceeded expectations (A++)
	Q10		50%	65.1%	+15.1%	Substantially exceeded expectations (A++)
	Q11		50%	69.8%	+19.8%	Substantially exceeded expectations (A++)
	Average		50%	61.6%	+11.6%	Substantially exceeded expectations (A++)
1.5 – Percent of sexual and gender-based violence (SGBV) survivors arriving at a health facility within 72 hours who have received Post-Exposure Prophylaxis (PEP) Kits (Source: SNIS)	Q1-4	64%	69%	91%	+22%	Substantially exceeded expectations (A++)
	Q5-6		74%	96%	+22%	Substantially exceeded expectations (A++)
	Q7-8		96%	96%	0	Met expectations (A)
	Q9-10		96%	97%	+1%	Met expectations (A)
	Q11-12		96%	98%	+2%	Met expectations (A)
	Average		86.2%	95.6%	+9.4%	Moderately exceeded expectations (A+)
[note] https://www.who.int/data/gho/indicator-metadata-registry/imr-details/25
[note] The baseline figure is derived from the National Health Information System, SNIS (Système National d'Information Sanitaire) and represents a national average. We consider that, due to gaps in national data availability, this figure is likely an overestimate and skewed by those (potentially better resourced) facilities reporting data.
[note] The milestones for output indicators 1.1; 1.2; 1.3 were calculated on the basis of existing health zone population and national fertility data. We consider it likely that available population data underestimates true numbers. In addition to the impact of the programme (e.g. in driving demand for health services) these population underestimates may partly account for programme achievement exceeding 100% of expected service provision.

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score.
This output aimed to enhance health service delivery and quality in FCDO-supported health zones including by increasing the number of deliveries attended by skilled birth attendants; providing malnutrition screening; and PEP kits for sexual and gender-based violence survivors. All indicators under this output were exceeded either moderately or substantially. Overall, FCDO assesses that this output moderately exceeded expectations, and therefore scored an A+. This scoring is consistent with the trajectory of previous annual reviews which scored A (2020) and A+ (2021).
For indicator 1.1, across key milestones the proportion of deliveries attended by a skilled birth attendant in health facilities often exceeded more than 100% of expected deliveries. This reflects the programme's success in building demand for, and provision of, quality maternal care. Performance was steady throughout the duration of the programme, with the only noticeable dip occurring during Q10 and Q11 in North Ubangi and attributed to a health workers’ strike.
Indicator 1.2 measured service utilisation, tracking the number of consultations at health facilities with a total of 18,692,814 new consultations across the programme period, substantially exceeding expectations despite the impact of the COVID-19 pandemic and prolonged health workers strikes on service utilisation. Strikes did lead to the reduced provision of some interventions. Programme supported Community Care Sites (CCS), which provide early diagnosis, treatment and/or referral, proved to be well utilised, especially for under 5s. In Q12 alone, 47,125 patients were managed by CSS. Primary reasons for consultation remained static over the programme: fever, malaria, diarrhoea, acute respiratory infection.
For indicator 1.3 (proportion of eligible children screened for malnutrition), in total the programme facilitated 6,532,782 malnutrition screenings of children between 6 and 59 months which substantially exceeded expectations and, in the final 2 quarters of delivery, included screening of 110% of the expected number of children. The programme adopted a targeted approach to those areas with the highest prevalence of malnutrition, co-developing action plans with affected communities. When a health worker strike in North Ubangi (August-November 2021) negatively affected screening rates a recovery plan was implemented to make up for the delay. Screening and rehabilitation in target provinces contributed to a reduction in the average prevalence of malnutrition of children 6 to 59 months from 7.7% in Q1 of the intervention to 4.3% in Q12.
Indicator 1.4 measured the recovery rate of malnourished children between the ages of 6 to 59 months following programme supported intervention. Achievement against this indicator improved over time, reflecting a lag between the training of community volunteers, intervention, and impact. Achievement against milestones for this indicator moderately exceeded expectations.
Achievement against targets for Indicator 1.5 (percent of SGBV survivors arriving at a health facility within 72 hours who received Post-Exposure Prophylaxis - PEP) also moderately exceeded expectations. By the tenth quarter of intervention, early presentation to a programme supported health centre in most provinces essentially guaranteed a victim would be able to access PEP. The increase in coverage was attributed to programme supported activities that enabled: 1) heightened community awareness about SGBV; 2) awareness and buy-in by health and administrative authorities and religious leaders; 3) improved quality of medical care for survivors of sexual violence; 4) consistent availability of PEP kits and; 5) actioning feedback from service providers.
Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme
Overall, this output has delivered good value for money, enhancing service delivery and quality of care (through technical assistance, training and procurement of commodities) with reduced expenditure. The overall investment per capita during ASSR Extension I is calculated at £ 1.06. By comparison, ASSP expenditure was estimated at £3.66 per capita. This reflects the sustained benefits of capital investments in infrastructure and equipment by earlier programme phases.
Lessons learned through this output, and recommendations for future programming
Overall, this output was assessed to be enhancing service delivery and quality of care through training, technical support, coaching and supervision, and provision of equipment and materials. However, COVID-19 travel restrictions proved challenging for the piloted Emergency Obstetric and Neonatal Care (EmONC) training in Kasai and Nord Ubangi. While measures were undertaken to continue training where possible throughout the lockdowns (via online supervisor briefings), the training of clinical mentors required in-person contact and so the training in Nord-Ubangi had to be postponed until after the lockdown measures were lifted.
Improved uptake of quality health services such as SGBV survivor care depends on well-funded, broad-based, and culturally sensitive community sensitization and ongoing advocacy is needed to sustain subsidies for key services to vulnerable groups. Future phases of intervention could incorporate equity indicators into routine monitoring to enable improved insights into access for different socioeconomic groups.

Output Number and Title	2. Human Resources: Improved and sustained Human Resources to support enhanced health service delivery
Output Score	Met expectations (A)
Impact weighting (%)	5%	Impact weighting revised since last AR?	No

Output Indicator	Quarters	Baseline	Final Logframe Target	Final Result Achieved	Overall achieved	Expectations Met
2.1 – Number of provincial health departments (PHD) using statistics from iHRIS to develop Annual HR Report each year	All	4	7	7	100%	Met expectations (A)
2.2 – Number and percentage* of health zones with at least 50% of staff’ HR data regularly submitted in iHRIS / *Total number of health zones = 40	Q5-Q12	6 (15%)	32 (80%)	34 (85%)	34 (85%)	Met expectations (A)

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score.
DRC has a comparatively small health workforce (1.1 nurses per 1000 population vs Ghana’s 2.3 nurses per 1000) and staff are inequitably distributed, with disproportionate concentrations in Kinshasa and other main cities. A large proportion of health workers are unpaid, underpaid and/or paid late resulting in high absenteeism, low motivation and retention of health personnel.
[note] World Health Organization's Global Health Workforce Statistics, OECD, supplemented by country data, 2018
Indicators under output 2 aimed to capture the availability, quality and access to human resource management information to inform decision making, for example through the compilation and validation of ‘human resource for health directories’ that allow a determination of staffing and skill distribution and costing. Widespread adoption and uptake of iHRIS is necessary to ensure sufficiently complete data to inform decision making an ensure e.g. equitable allocation of human resources. Regular updating of iHRIS is necessary to ensure human resource data remains accurate and e.g. payrolls remain accurate and free of ‘ghost workers’. Indicator 2.2 was added to allow the programme to track uptake and completeness of iHRIS data. Overall, this output met expectations, with both indicators scoring As. This is an improvement on the previous annual review which scored a B. In the first annual review, it scored an A (2020).
This output consisted of several key activities, including lobbying relevant government departments and partners to discuss existing Human Resource for Health (HRH) management efforts and their approaches to managing electronic data; supporting the MoH to update their budget and workplan for HR management activities; sustained technical assistance to the MoH HRH Directorate to launch a national multiannual HR development plan, and introduce a nationwide rollout of a digitally enabled Health Workforce Information System (iHRIS) by 2022. iHRIS is an easy to use, open-source, free software that is centrally accessible online or by a local network and has interoperability with other open-source software, such as the health information system (DHIS2). The system captures high quality data on the health workforce, including at the individual level (key demographics, skills, qualifications, and locations). This allows for improved workforce management. The system also provides harmonization with the budget and allows for reporting to be developed and disseminated at the provincial level. The system was the government’s database of choice under the predecessor programme due to its capacity to address not only payroll, but also tracking professional development and competencies.
A 2016 FCDO supported pilot of iHRIS in four provinces demonstrated that with modest investment (£24K per province to achieve regular data submission for at least 50% of staff) the rollout of iHRIS had enormous potential to drive more equitable distribution of human resources and enhance the overall efficiency and efficacy of the health system. Such data enabled the identification of inaccurate or fraudulent “ghost worker” salaries, and the re-allocation of these resources to active but unpaid health workers instead.
Following the results of the pilot, a range of donors have supported the rollout of iHRIS in a further 4 provinces (Kongo Central; North Kivu; Haut Katanga and Ituri). Piloting of iHRIS in the capital, Kinshasa, is planned for 2023 with World Bank support. It is hoped that a Kinshasa pilot could act as a precursor to the national adoption of iHRIS.
Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme
Programme inputs to strengthen the management of human resources for health are central to building a sustainable health system and have the potential to deliver excellent value for money. An initial pilot of the iHRIS software in 4 provinces enabled the identification of a significant number of ‘ghost workers’ on existing payrolls, unlocking a monthly saving to the government of $48,000 per month. This recurrent benefit will quickly exceed an initial investment of $8400 per health zone. Whilst the reform of human resource management is a long-term ambition, fully realising the value for money of this investment remains contingent on improved management information being used for decision making, which in turn is dependent on improved governance.
Lessons learned through this output, and recommendations for future programming
- Effective management of human resources is essential in the development of an equitable, sustainable and quality health system that is equipped to deliver improved health outcomes.
- Political will, modest financial investment and commitment to the implementation of an HRH management system can realise significant efficiencies and improve the remuneration of underpaid health workers. FCDO should use relevant results, case studies and data of iHRIS enabled savings to demonstrate the investment case (and advocate) for the further scaling and roll out of iHRIS.
- To maximise impact, FCDO and implementing partners should continue to share the pilot results of iHRIS, helping to build an investment case for national scale up. iHRIS is already integrated within the National Human Resources for Health Development Plan and National Plan for Health Information Development. Future programmes should advocate for iHRIS to be incorporated within DRC’s Digital Health Strategy, as a key digital tool underpinning the health system.
- Over the programme period, contrary to expectations, instances of overstaffing and arbitrary transfers increased in some working areas, demonstrating that the availability of an HRH management system (such as iHRIS) is not alone sufficient to ensure better staff management. Alongside enhanced management information the programme should continue to utilise detailed political economy analysis in orientating its advocacy and inputs to human resource management.
- Future programmes should consider adopting indicators that enable the monitoring of adherence to ‘normal’ and needs based staffing ratios and progression/remuneration linked to qualifications and experience as a means to capture effectiveness.

Output Number and Title	3. Information Systems: Appropriate and enhanced use of Information Systems to support decision-making to improve health service
Output Score	Did not meet expectations (B)
Impact weighting (%)	10%	Impact weighting revised since last AR?	No

Output Indicator	Quarters	Baseline	Final Logframe Target	Final Result Achieved	Overall achieved	Expectations Met
3.1 – Number of health zones with a DHIS2 data quality score of 80% or more on the data quality reporting appraisal scheme	All	26 (65%)	34 (85%)	33 (82.5%)	33 (82.5%)	Met expectations (A)
3.2 – Average number of monthly feedback reports sent by provincial health information office to health zones	Q5-12	0	34 (85%) / (average)	27 (67.5%) / (average)	27 (67.5%) / (average)	Substantially did not meet expectations (C)

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score.
Activities in support of this output focused on improving the timeliness, completeness and quality of data reported through the Digital Health Information System (DHIS2). To improve data quality, ASSR provided and trained technicians on the maintenance of satellite (VSAT) antennas, provided computer equipment and installed solar panels to ensure all targeted health zones had capacity for data entry, analysis and transmission to enable informed and timely decision making.
Additional training was provided to IT technicians to help reduce wait time and reduce costs of soliciting technicians from Kinshasa; enhance communication and supervision between local and national technicians; and strengthen the capacity of human resources for sustainability and continuation of this output beyond the programme’s end date.
Overall, FCDO assess that this output has scored an B which is not an improvement on previous annual review which scored a B (2021). In the first annual review, it scored an A (2020).
While the final average result against indicator 3.1 (number of health zones with a data quality score over 85%) was slightly lower than the target, it was significantly affected by just two quarters of substantial under-delivery in North Ubangi during a health workers strike that was outside the programme’s control. Additionally, at the beginning of the programme, and based on initial results, the target was increased in ambition from 80% to 85% of health zones which on reflection may have been too ambitious. FCDO would therefore assess that, overall indicator 3.1 met expectations.
Indicator 3.2 was added because regular, tailored, feedback from data analysts to data inputters is crucial to ensure the timeliness, completeness and quality of data reported through the DHIS2 system. In turn, quality health information is essential to inform strategic decision making, for example DHIS2 data enabled corrective action when reporting showed a significant drop in immunisation coverage following a health workers strike in North Ubangi.
Performance against indicator 3.2 (monthly feedback reports by provincial office to health zones) substantially did not meet expectations. Feedback from provincial health divisions to health zones decreased dramatically from 98% in Q11 to 48% in Q12. Similar declines in feedback reports were observed in Q4-Q7. The exact reasons for reductions in feedback provided are unclear and require further investigation. In some instances, it may be that provincial actors were not sufficiently motivated, or convinced of the value of feedback, to prioritise this activity. Other challenges included limited staffing levels and occasionally technical difficulties. Future phases of investment should consider how best to evidence the impact of feedback on data quality and timeliness to improve the motivation of provincial actors.
Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme
Programme investments supporting the timeliness, completeness and quality of health information have the potential to demonstrate excellent value for money, especially if such data informs more equitable resource allocation.
In the longer term, the cost-effectiveness of investments under output 3 rest on: (1) ensuring incentives are in place for maintaining the data (2) ensuring data is used for decision making and (3) increased government spending (or donor support) for the implementation of DHIS2. For example, costs can be anticipated in maintaining ICT infrastructure and internet connectivity through the VSAT satellite system (which has recurrent costs of up to £144,550 per year). Programme exit from Maniema province in 2020 has highlighted these risks; the VSAT satellite subscription could no longer be paid and ICT maintenance deteriorated.
Lessons learned through this output, and recommendations for future programming
- The successful implementation of DHIS2 requires sustained resourcing (human and financial) training, and supervision. The completeness and utility of data for decision making depends on timely and quality inputs by motivated and trained data inputters. In turn, evidence-based decision-making requires that decision makers have access to, and trust, health information.
- Because regular feedback is key to highlighting demand for regular and quality data inputs, future FCDO investments should consider how best to strengthen systems of feedback. This could include:
  - gathering qualitative information on how data informs management at provincial, zonal and facility level;
  - capturing the impact of regular feedback on DHIS2 data quality and on improving services with a view to advocating for more regular feedback
- Future phases of programme support on DHIS2 should consider whether a cost-sharing model (sharing costs between government and donors) could be employed to ensure greater sustainability of programme investments (especially infrastructure and connectivity) for DHIS2.
- Health Area Development Committees (CODESA) and community members’ participation in the health system could be enhanced by visualising key DHIS2 data for community use. Community scorecards evaluating health service delivery could become a two-way information sharing tool, with community assessments complemented by feedback from local health authorities that incorporates insights from DHIS2.

Output Number and Title	4. Increased leadership and governance, including empowerment and accountability, in health service planning and delivery
Output Score	Met expectations (A)
Impact weighting (%)	10%	Impact weighting revised since last AR?	No

Output Indicator	Quarters	Baseline	Final Logframe Target	Final Result Achieved	Overall achieved	Expectations Met
4.1 – Cumulative number of assisted health centres with at least one community score card exercise in the last 12 months	All	244	1,464	1,496	102.2% (+32)	Met expectations (A)
4.2 – Average number of Comité de Développement de l’Aire de Santé (Health Development Committee), CODESAs, that were operational	All	N/A	704	700	99.4% (-4)	Met expectations (A)

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score.
Overall, FCDO assess that this output has scored an A which is similar to previous annual reviews that scored A+ (2021) and A (2020). Output 4 was intended to increase the participation of community health structures in the planning, delivery and monitoring of health activities (especially health promotion). Indicators under this output were therefore designed to measure the functionality (and activity) of participative community health structures.
The functionality of CODESA, as measured in indicator 4.2, is defined as the number of CODESA having quarterly meetings with minutes. Overall, logframe targets for output 4 were met. Key inputs contributing to these results included: training for CODESA members, and support to develop a Trainer of Trainers (ToT) manual for community health workers (Relais Communitaries – ReCos). This was used to train provincial and health zone master trainers in project areas. CODESA and ReCos also received regular coaching from programme supported Community Facilitators, drawn from the Health Zone Management Team, who received a monthly allowance of $30. In addition, alongside a contribution by health facilities of 2% of their revenue, the programme funded CODESA US$10 monthly, enabling them to facilitate a yearly community score card exercise to assess the accessibility and quality of health service provision. Community score cards have boosted community engagement and sense of ownership in planning and delivery of health services, enhancing social accountability.
Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme
During the first project extension, these outputs were achieved at a cost to the programme of £453 per community card completed (indicator 4.1) and £265 per operational CODESA (indicator 4.2) which includes capital development costs, specifically, printing of the CODESA Manual. We consider this represents good value for money as there is evidence (from Maniema, where the programme withdrew early) that supported CODESAs remained active up to two years after the project withdrew, with some continuing to produce community score cards, demonstrating that activities and impact were sustained in the medium-long term.
Lessons learned through this output, and recommendations for future programming
Efforts to strengthen participative community structures for health, including CODESA, have generally proven successful in strengthening community engagement and monitoring of health service provision. However, the responsiveness of decision-makers to results of community scorecards remains limited. To ensure that community engagement and scorecards strengthen the accountability of health service providers it is recommended to: i) replicate the community score card approach at higher levels; ii) develop an indicator to track the implementation of the CODESA recommendations and plans and iii) develop a leadership and governance programme targeted at provincial and national politicians, developing political champions for health, strengthening alliances with relevant stakeholders such as parliamentarians and transforming evidence gathered into clear messages for reform.

Output Number and Title	5. Enhanced and appropriate use of Medicines and Technologies to support health service delivery.
Output Score	Substantially exceeded expectations (A++)
Impact weighting (%)	15%	Impact weighting revised since last AR?	Yes, increased by 5%

Output Indicator	Quarters	Baseline	Final Logframe Target	Final Result Achieved	Overall achieved	Expectations Met
5.1 Percentage of surveyed health facilities able to offer basic or comprehensive emergency obstetric and neonatal care	All	1.3%	40%	73%	73%	Substantially exceeded expectations (A++)
5.2 Percentage of days that health facilities report stockouts of priority/tracer drugs	All	N/A	<13%	7.8%	7.8% (-5.2%)	Substantially exceeded expectations (A++)
5.3 Percentage of medicines that are wasted due to expiration as a proportion of overall stock at the provincial warehouse	All	N/A	<2%	0.04%	0.04% (-1.96%)	Moderately exceeded expectations (A+)

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score.
Output 5 reflects programme inputs to enhance the provision of quality health care, including inputs to strengthen supply chain management for those essential medicines and commodities that underpin basic medical care (especially for women and newborns). Achievement has moderately or substantially exceeded targets. Overall, this output substantially exceeded expectations, an A++. This is a substantial improvement on previous annual reviews which scored B (2020) and A (2021). The lower results are predominantly because of delays in baseline/milestones being established for the 2020 AR, and according to the 2021 AR, beneficiaries and respondents during field visits confirmed that drug availability was the weakest component of the programme. The stock-outs were a result of many challenges, including technical (mis-quantification), natural disasters, poor infrastructure and systems challenges, administrative delays and losses.
Significant reductions in stockouts and expiry of essential medicines and commodities reflect the success of programme supported ‘Medication Working Groups’ established in each province. These groups strengthened supply chain management for essential medicines by improving the monitoring, analysis, and application of data for decision making, at every step of the supply chain. The piloting of new software for stock management (‘Basic Hospital Information Management - BHIMA’) also contributed to these achievements and the tool will be scaled under FCDO’s future health programme. Other critical inputs to strengthen the provision of quality care included the procurement and distribution of new medical equipment, clinical supervision and mentorship.
Although the programme significantly reduced the frequency of stock-outs for essential medicines, ruptures in supply are still a significant problem and affect continuity of service delivery. In some locations, continued weaknesses in supply chain management were attributed to poor reporting of data; high turnover of trained staff; weak coordination and occasional losses of stock (including a major fire at a drugs warehouse, which the programme re-constructed). These factors sometimes led to delays in the distribution of project supplies, exacerbated by limited infrastructure (road and telecoms). At times, the failure of other partners to supply particular medicines or health commodities also contributed to stock-outs (e.g. of family-planning and antimalarial commodities).
Regional Distribution Centres (CDR) for medicines and commodities are central to delivering Output 5 and were therefore important targets for programme support. However, the relatively new CDR model (non-profit, non-governmental institutions charged with drug procurement, management and distribution) has faced challenges. Despite programme interventions, the efficiency, effectiveness and financial sustainability of CDR has sometimes been undermined by their limited commercial and procurement capabilities. One CDR in North Ubangi was forced to file for bankruptcy. If scaled, the BHIMA drug inventory module (piloted by the programmme), will provide better data for procurement and supply chain management. However, under a future programme, the effectiveness and sustainability of the CDR model would require a continued focus on building the business management and procurement capabilities of CDR.
Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme
Ensuring the availability and access to essential medicines and commodities is central to the provision of quality healthcare. Programme inputs have enabled target outputs to be exceeded. There is good evidence that economy in drug procurement was achieved through competitive bidding with ASSR obtaining prices similar (or better) than those offered by national drug purchasing entities. Programme economy was also strengthened by high-value advances in the quality of the procurement and supply chain management which reduced stock-outs and wastage of medicines and essential medical commodities. The total value of drugs expired during the 4th quarter of ASSR Extension I was $14,200, representing just 0.27% of the value of unexpired stock available at provincial warehouses at the end of the quarter. This was well within the target range of less than 2%.
Lessons learned through this output, and recommendations for future programming
The full medicines and health commodities procurement and supply chain system must be strengthened to deliver sustainable results. Continued institutional weaknesses within CDR risk undermining the sustainability of programme investments. Future programmes should continue to support the institutional capacity of CDR, working in collaboration with IPS (health inspection) to tighten drug control from provincial to facility level, and promote rational drug use.

Output Number and Title	6. Health Financing to support access to health services
Output Score	Moderately exceeded expectations (A+)
Impact weighting (%)	5%	Impact weighting revised since last AR?	No

Output Indicator	Quarters	Baseline	Final Logframe Target	Final Result Achieved	Overall achieved	Expectations Met
6.1 Proportion of surveyed health centres displaying negotiated pricing plan in public space of health facility	All	50%	85%	93%	93% (+8%)	Moderately exceeded expectations (A+)

Output 6 was designed to increase the number of health facilities displaying negotiated “flat fee” rates which covered all services and commodities needed for a visit/episode. The primary objective is to empower beneficiaries to demand the services at lower prices, to ensure equitable access to services. Overall, FCDO assesses that this output moderately exceeded expectations, and therefore scored an A+. This is consistent with the trajectory of previous annual reviews which both technically scored A (although in the 2019 AR, this was an assessment based on progress as the baseline had not been completed).
Data suggest that in DRC around 42% of healthcare costs are met by out-of-pocket expenditure, 16% by government and 39% by donors. In this context, the agreement of negotiated pricing (including free care for disadvantaged groups) is a key measure to increase equitable access to essential healthcare. The programme supported the re-adjustment of tariffs at the beginning of implementation, working with stakeholders to agree tariffs and support community verification of groups that would receive an entitlement to free healthcare.
During the first 18 months of ASSR, health centres and hospitals were paid ($50/month and on average $1,000/month respectively) to provide free services to 126,449 (“indigents”) clients living in extreme poverty, as defined by community criteria. Through increased awareness, the number of people with access to free services increased gradually from 0.20% of the population to peak at 0.35% by end September 2020. Over the project lifetime, 622,754 clients benefited.
Indicator 6.1, public display of negotiated pricing plans at health facilities, is intended as a proxy indicator for the implementation of negotiated pricing. From a baseline of 50% of health facilities, 93% of health facilities were publicly displaying negotiated pricing at the completion of the programme, moderately exceeding the logframe target.
Whilst dissemination of negotiated pricing plans to clients is an important step, as an indicator it does not fully capture the extent to which negotiated pricing is known, understood and implemented. The display of pricing plans in French (which clients may not speak) and reports of continued ‘informal fees’ highlight some of the constraints to the implementation of negotiated pricing. In addition, the charging of full fee rates when medicines are unavailable (and a partial fee should be applicable) is common. In such cases clients must then purchase prescribed medicines from the private sector, often at a higher cost, and in addition to full negotiated fees.
[note] Free mobile phone based online service used to report fraud, sexual and gender-based violence etc.
To some extent, the implementation of negotiated fees is undermined by systemic challenges to human resource management. ASSR analysis using the iHRIS system (output 2) revealed that more than 50% of health workers received no salary or formal remuneration, increasing a reliance formal and informal user fees. In Kasaï province, per agreements with provincial authorities, health workers may retain between 65% and 73% of the facility revenues, this is often their sole source of income. The practice of political or patronage-based appointment to large numbers of roles within the health system, has led to a growing workforce that is inequitably distributed and rarely reflects needs. This trend reduces individual staff incomes, decreases the viability of moving more staff onto payroll and further incentivises the charging of informal or inflated fees, reducing access and affordability to essential care.
Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme
Health financing to support access to care for the poorest directly enabled 622,754 people most in need to access essential health care, demonstrating strong VFM by exceeding the number of clients targeted. However, the wider impact on equity through flat pricing initiatives is harder to determine. This is because displaying fees is a necessary but not sufficient step to increase access to healthcare and because the health information system provides limited disaggregation of data by age, sex and socio-economic status.
Lessons learned through this output, and recommendations for future programming
Future projects should better interrogate compliance and barriers to the implementation of flat user fees, for example by enabling the monitoring and reporting of user fees through the community score cards initiative (BCPs). Future investments should also place a renewed emphasis on the policy to fund free care for the poorest. One option for revision of the policy would be setting up Health Equity Funds (HEF) or reviving Community Health Endowments (CHE), in line with DRC’s UHC strategy.

Output Number and Title	7. COVID-19 response in 15 health zones in Kinshasa
Output Score	Moderately exceeded expectations (A+)
Impact weighting (%)	4%	Impact weighting revised since last AR?	Yes, reduced by 1%

Output Indicator	Quarters	Baseline	Final Logframe Target	Final Result Achieved	Overall achieved	Expectations Met
7.1 Number and proportion of health zones with a functional Local Covid-19 Coordination Committee (‘CLC’)	Q7-12	0	13	15	115.4% (+2)	Substantially exceeded expectations (A++)
7.2 Number and proportion of health facilities supported with PPE equipment	Q8-12	0	198 per quarter	176 average per quarter	88.9% (-22)	Moderately did not meet expectations (B)

Following initial detection of COVID-19 in March 2020, Kinshasa saw the country’s largest COVID-19 epidemic with more than 50% of cases and deaths nationally. The ASSR programme adapted quickly to make a valuable contribution to the pandemic response in extremely challenging circumstances, and this output was created to support ASSR to measure this. This focussed on supporting response coordination (in Kinshasa health zones) and the provision of drugs and medical commodities (including personal protective equipment) in both Kinshasa and programme provinces. Working in coordination with FCDO’s private sector development and energy programme, ASSR also supported the comprehensive rehabilitation of 15 health facilities in Kinshasa to improve their resilience during the pandemic. Overall, FCDO assesses that this output moderately exceeded expectations, and therefore scored an A+. This is consistent with trajectory of the previous annual review which scored A (2021).
The targets for indicator 7.1 were substantially exceeded, with the programme supporting a larger than expected number of health zones in Kinshasa to coordinate their response to COVID-19. COVID-19 Coordination Committees were considered functional when at least 2-3 meetings per month involving key actors were evidenced by written minutes. Achievement against targets for indicator 7.2 were below expectations. However, evidence collection for this indicator was particularly challenging and costly as the project had to physically collect delivery notes from health facilities receiving commodities, which was often not possible.
In the context of highly constrained global supply chains, the programme’s provision of personal protective equipment was essential to better protect health workers and reduce the risk of health facility acquired infections. To help mitigate supply challenges, the programme contracted female faith-based groups to produce over 40,000 cloth face masks. Moderate underachievement against targets is partially explained by allocative decisions of local health authorities which meant that some (planned) target facilities were not supported by the programme. In addition, some planned target facilities were supported by other donors, negating the need for ASSR inputs.
The wider COVID-19 project in Kinshasa was tracked through a dedicated logical framework with four output indicators covering: i) infection prevention and control (IPC); ii) surveillance; iii) case management; and iv) continuity of essential healthcare services. The project supported the DPS and 15 health zones in Kinshasa, covering 183 health centres and 15 hospitals. IMA implemented activities jointly with faith-based NGOs who had long-established relationships with the communities. Activities in Kinshasa covered training of health workers and communities in COVID-19 response, supply of IPC equipment, oxygen concentrators, reporting forms and phones to improve surveillance, and rehabilitation of 15 facilities to reduce health facility acquired infections during April 2020 to September 2021. Rehabilitation included basic and essential building repairs, installation of 5 wells with solar driven pumps, 25 water cisterns, waste management, rehabilitation or construction of toilets, garbage pits and incinerators in selected facilities
In response to the government’s request to reduce delays in delivering COVID-19 test results, the ASSR project also supported laboratory training to health facilities equipped with GeneXpert machines for confirmatory testing. This training targeted laboratory technicians in assisted and other HZ in Kinshasa, the Kongo Central’s provincial laboratory, and the IME Kimpese hospital.
[note] These machines had been bought for HIV-Tuberculosis testing and can be used for COVID-19 testing
Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme
The response was well implemented, though its effectiveness cannot be assessed as the initial effectiveness indicators (the IPC score card and the DHIS2 daily COVID-19 alerts) were dropped as they were not deemed feasible within the very short intervention period. The project could not closely monitor the final use of its contributions, amongst others due to the myriad of COVID-19 assistance interventions and challenges to the governance of the COVID-19 response.
[note] Covid business en RDC : Repenser la Riposte aux épidémies, Groupe d’étude sur le Congo and Centre on International Cooperation, NYU, Oct 2021
Lessons learned through this output, and recommendations for future programming
Short term and reactive programme changes (e.g. in an emergency context) should be accompanied by a proportionate approach to M&E including the selection of indicators for which data will be available. Future programmes should take account of wider lesson learning exercises stemming from the COVID-19 pandemic, to inform future programme design and readiness to support response to health emergencies.

Output Number and Title	8. Enhanced independent monitoring of ASSR to support programme accountability and improved capacity to respond to emerging research need.
Output Score	Met expectations (A)
Impact weighting (%)	1%	Impact weighting revised since last AR?	No (This is a new output).

Output Indicator	Quarters	Baseline	Final Logframe Target	Final Result Achieved	Overall achieved	Expectations Met
8.1 Timely submission of agreed progress reports, annual review and programme completion review	Q5-12	N/A	9	9	9 (100%)	Met expectations (A)
8.2 Number of compliance checks (i.e. spot checks) completed on finance, fraud, safeguarding or assets etc.	Q5-12	N/A	6	Met	Met	Met expectations (A)
8.3 Number of the pre-defined operational research pieces agreed on and submitted as per the agreed timeline	Q5-12	N/A	9	6	6 (66.7%)	Moderately did not meet expectations (B)
8.4 The quality and usefulness of HERA’s findings, identified gaps, suggested improvement actions and proposed solutions rated positively (3 or more) by relevant partners on a five-point scale (sources: BEK, IMA, SANRU and Pathfinder)	Q7-12	N/A	3 out of 5	4 out of 5	4 out of 5 (+1)	Moderately exceeded expectations (A+)

Overall, FCDO assesses that this output met expectations, and therefore scored an A. This output is new and was not measured in previous annual reviews but was created to enhance programme monitoring.
Generally, Third-Party Monitoring (TPM) targets were met or exceeded. TPM visited 43/50 supported health zones, plus 9 in Kinshasa (5 at the mid-term review, and 4 at the final review of the COVID-19 response support), focusing on the project contribution to the health system building blocks and the diligent use of project assets.
[note] One of these 4 had been visited during mi-term review.
[note] In line with local COVID-19 preventive measures, travel was suspended during the COVID-19 lockdown from end March to August 15th, 2020, while the overseas TPM deputy Team Leader continued to provide remote support and resumed in-country travel in November 2021.
The need for operational research (I8.3) is determined by FCDO in consultation with IMA. Thus, TPM conducted six studies including one not originally planned by the programme (assessment of the cost benefit of using IHRIS). These are:
Assessment of the National Drug Supply Chain. This reviewed the current national system and the parallel system used by IMA and made recommendations for a future FCDO health programme.

Emergency transport in Nord Ubangi. This study assessed the innovative introduction of motorcycles for obstetric emergencies and found it both efficient and effective.

Potential impact of the strike on the implementation of (project) activities in Kasai province. This assessment was shared with the Groupe Inter-Bailleurs de Sante (GIBS) to inform donor discussions with the authorities on the impact of the strikes.
Effects of home visits on the nutritional behaviour of households and the nutritional status of children. This study demonstrated the added value and high cost-effectiveness of the innovative IMA approach to rely solely on home grown foods and home visits by ReCo/CHW.

Quality of care study. The study shows that IMA supported health facilities to perform better than non-IMA supported facilities, but still have shortcomings related to the quality of care provided. Government stakeholders claim to be insufficiently involved in the formulation of research questions, and their delayed availability reduced utility for evidence-based decision making during ASSR implementation.
[note] Yet, the FCDO operational research requests were based on past ASSP experiences. They took however little account of the time needed for their implementation and eventual use within the short timeframe of a transition project, initially planned for a mere 18 months. The COVID-19 epidemic and the low responsiveness to TPM proposals for studies and their protocols further compounded the delays, reducing the value of the studies.

Assessment of the cost-benefit of using iHRIS. This study shows encouraging results, which will be useful for advocacy. In addition, TPM conducted reviews, including on the ASSR gender strategy which has been well received, and analysed the data collected by the former ASSP project on the ASSP/ ASSR nutrition intervention at community level, which showed a high relevance and effectiveness.
[note] IMA had collected the gender strategy data during ASSP and TPM conducted the data cleaning and analysis.
Overall, the above reports were met expectations in terms of quality and usefulness of TPM’s findings. Some recommendations were felt as non-actionable within the limited budget and time frame of the ASSR project. A few recommendations for a future project were considered.
Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme
The TPM component was designed to provide ongoing, high-quality, critical, and constructive review of the ASSR programme and to work with programme provides to improve efficiency of the programme. It has helped FCDO to monitor the programme in hard-to-reach areas, and to deliver compliance expectations of due diligence, fraud and safeguarding.
Lessons learned through this output, and recommendations for future programming
While operational studies were a TPM contractual obligation, rapid monitoring assessments yielding timely information for decision-making is more appropriate for short-term projects. External monitoring contributes to flexible project steering, and its efficiency and effectiveness would be enhanced if the TPM is involved in development of the logical framework. Underutilisation of the operational studies affects their effectiveness. It is recommended: i) not to include OR in such a short project; ii) to involve TPM from the very beginning of project design and implementation; and iii) to include a research utilisation indicator.
## D: Risk
#### Overview of risk management
The overall programme risk remained major at closure, which is within FCDO DRC’s risk appetite. Risk discussions were held with partners on a monthly basis during a monthly coordination meeting.
The context in DRC remained challenging throughout the duration of the programme and delivering through a public health system poses significant risk. Systemic weaknesses, combined with a fragile political situation, made it difficult for the Ministry of Health to focus on delivering reform. In the Kasais in particular, the consequences of the 2016-17 violence means that pressure on the health system has remained high and population displacement makes accurate information about population and services even harder to collect and use. There is a lack of funding to the health system, often resulting in salaries not being paid fully or in time and undermining essential services. This impacted the programme when widespread strikes occurred in the final year of the programme.
Risk Management: British Embassy Kinshasa and IMA continued to work closely throughout the programme to ensure risks were effectively identified and mitigated or escalated when appropriate. The risk register was regularly updated and discussed with the programme team on a quarterly basis. A large-scale revision of the risk register was undertaken for the cost-extension phase of the programme, which reflected IMA’s increase in risk awareness.
Key risk themes that were managed or materialised over the course of the programme are discussed below. More detail about individual risks can be found in relevant annual reviews. The risks that materialised were within the overall risk appetite of the Embassy and were managed proactively by IMA and the Embassy team.
COVID-19
COVID-19 predominantly impacted the management of ASSR rather than the deliverables. The main problems ASSR faced were due to travel restrictions which cancelled or postponed activities including TPM monitoring visits, partner meetings and field visits, some of which could be conducted online instead. Technical support from consortium partners also had to be postponed to March 2021. To mitigate these consequences, the consortium established an online approach to provide remote support for field actors, to ensure continuation of routine interventions and maintain planned outputs and programme performance. Local partners such as the MoH staff were more affected as they often have no reliable internet access from home to engage as required. Commercial flights became more erratic after the lifting of the restrictive measures.
Medical supply chain management
Throughout the programme, supply chain management for medical commodities, including drugs, remained a key risk that posed several challenges. Weak national supply chain management capabilities affected accurate quantification of needs, procurement, distribution, storage and management of commodities. These difficulties meant that occasional stockouts of drugs continued to impact programme implementation.
Following a major fire in January 2020 at the Kasai provincial drugs warehouse, the programme team undertook a full review of the management of supply chain risks, with new mitigations put in place throughout the supply chain. For example, enhanced security and safety measures were implemented for warehouses and performance-based contracts were introduced for drug distribution centres. Based on learning from the earlier ASSP programme, inputs to strengthen stock management and planning were incorporated from the programme outset to prioritise the use of medicines near expiry, minimising wastage.

Fraud and safeguarding
FCDO has a zero-tolerance approach to fraud and safeguarding issues, which has been clearly communicated to partners. Fiduciary and safeguarding risks were realised at points the programme, as would be expected when operating in a context such as DRC, but partners demonstrated effective management of these cases. Governance systems for the management of active fraud cases was strengthened over the life of the programme, to ensure that ASSR’s senior management team at IMA were fully sighted on all cases.
Fraud cases generally reflected theft of medicines, equipment, and cash. This was done by health workers and army officers, or criminals. Most cases were identified through IMA’s hotline, advertised in every community served by the project. IMA had effective mitigating measures and introduced effective recommendations where appropriate: for example, IMA stopped transferring project advances used to reimburse the facility in-charges for expenses, including CODESA operational costs, by cash and instead used newly established health zone bank accounts. This reduced the risk of fraud as the funds were easier to trace. Some stock was lost and written off as a result of criminal theft, but in many cases stock or funds were recovered.
In terms of safeguarding, there were fewer cases reported throughout the duration of the programme, which potentially demonstrates under-reporting of cases. FCDO has provided feedback and recommendations to strengthen safeguarding case reporting in future programmes. IMA continue to work with local government on recommendations for management of an ongoing safeguarding case, despite the closure of ASSR.
Future programmes should continue to work to improve fraud and safeguarding mitigation and response, ensuring that all downstream partners fully understand the expectations on reporting and that beneficiaries understand their rights.
Governance
Systemic challenges in governance of the health sector continued to pose a major risk to the sustainable achievement of outcomes. Notable issues included high turnover of political appointees at the national and provincial level, which in turn affected key appointments within national and provincial health structures, affecting the value of some programme investments (e.g. training) and continuity of programme activities.
Continuity of health sector leadership is critical to fully realise programme benefits and advance longer-term reforms (for example in human resource management and public financial management). However, the programme faced a context in which more than 80% of health zone chief doctors were changed during programme implementation. Similar challenges in turnover within the Provincial Health Directorate were also seen. This level of turnover undermined aspects of the programme’s capacity building efforts. The programme (and FCDO) attempted to mitigate systemic governance challenges through sustained advocacy at the provincial and national level, calling for improved human resource management, and through the introduction and roll out of iHRIS – a new human resource management software.
Donor coordination
Donor coordination and the implementation of harmonised approaches was achieved across many aspects of programme delivery. On the procurement, supply and transportation of medicines and health commodities the programme worked to complement inputs by the Global Fund, World Bank and UNFPA. For example, the programme constructed medicines warehouse, logistics and inputs to strengthen supply chain management also benefited the management and distribution of drugs and commodities from these partners. However, challenges in coordinating a coherent approach to the financing, procurement, and distribution of drugs across government and donors was an ongoing risk. In particular, the adoption of different models by the programme and World Bank risked creating challenges for health workers and the establishment of parallel systems. During the programme these risks were mitigated by careful communication to health workers and ongoing monitoring. However, a future programme should work with provincial authorities and other donors to agree a singular aligned approach. Occasional unexpected interruptions in health commodities supplied by other actors on which the programme relied (including the Global Fund and UNFPA) also risked undermining delivery. The programme sought to mitigate these challenges through regular coordination and information sharing, including of medical supply chain management information.

## E: Programme Management: Commercial and Financial Performance, Monitoring and Evaluation
#### Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including VfM measures of economy and efficiency.
Partner performance
The ASSR programme was complex, with multiple components, activities and downstream partners. Despite difficulties coordinating and managing a large and complex programme in a challenging environment, IMA performed well. More details of partner performance can be found in the previous annual reviews. Some highlights include:
- IMA’s demonstrated capacity to programme flexibly by responding actively and rapidly to the COVID-19 pandemic: As a result, ASSR was able to respond to meet the need for support in Kinshasa health zones for better coordination and distribution of PPE.
- ASSR piloted clinical mentoring in Emergency Obstetric and Neonatal Care (EmONC) using seasoned obstetrics providers paired with newer front-line nurses and midwives to engage in continuous learning. Part of this pilot was to increase correct use of the partograph which is a simple tool that can help alert to early warnings of complications. At the start of the pilot, only 11% surveyed health facilities used partographs correctly which rose to 82% at the end of this period.
Generally, performance of the third-party monitoring component was good, but a lot of management oversight was required, and some challenges were identified, particularly toward the beginning of the contract, and additionally during the PCR process. In the second annual review, it was noted that at the beginning of the relationship between FCDO and HERA, there were some initial “teething” challenges in terms of format and length of reporting and evidence provided. A regular discussion between IMA, FCDO and HERA to discuss emerging issues from the validation reports done by HERA proved useful, and mutual understanding of expectations between partners improved. FCDO should ensure that expectations on third party monitoring contracts, including on quality of products, are established early and continually monitored throughout the duration of the programme, with performance issues addressed promptly, and that FCDO allow plenty of time to ensure feedback can be provided on reports received.
Quality of reporting
Generally, IMA submitted high-quality narrative and financial reports, managed requests from the FCDO programme team to adapt quickly and well and were responsive to feedback to improve from both TPM and FCDO. It was noted within the previous annual review that there was room for improvement in the data quality as some discrepancies were noticed between the data verified by IMA and the data verified by the TPM. The TPM and IMA worked to correct these issues, however, some issues persisted in the final reporting. Unfortunately, this PCR was unable to use data validated by the TPM because this was incomplete. Therefore, for consistency, it was decided to use IMA’s data. For those datasets which were validated by the TPM, programme achievement was higher than those figures reported by the supplier, IMA. In addition, when compared with validated TPM data, IMA reported results were largely concordant, albeit slightly lower. For these reasons FCDO is assured that the use of IMA’s data in this PCR is a fair reflection (and likely minor underestimation) of programme performance.
Financial performance
The programme had a total budget of £54m, of which £53m was spent (98%). Generally, IMA financial management was strong, and the quality of expenditure reports was high. However, in the most recent annual review, there were some fairly high levels of variance between forecast and spend.
An example of strong financial performance is when IMA successfully reprogrammed budget to support FCDO to respond to the COVID-19 outbreak. This was done by identifying savings to be repurposed and adapting in a timely manner to formulate a response in Kinshasa where there were no previous programme activities (although it is the location of IMA HQ).
#### Programme-level approach to monitoring and evaluation
Overall approach
Throughout the programme, FCDO maintained monthly meetings with partners to discuss progress, chaired by HERA; partners produced quarterly narrative and financial reporting and annual audited accounts; FCDO facilitated annual reviews and undertook additional monitoring discussions when needed. Monthly meetings between FCDO and IMA were established to further discuss updates on finance and risk.
IMA conducted internal monitoring of programme performance. Thus, 10 staff at central level and 7 at provincial level, plus an additional 7 SANRU staff (until 1st October 2020, when both national teams merged) supervised all levels of programming and maintained an indicator database derived from the national DHIS2 database. They also supported and conducted special surveys for certain indicators.
Third-party monitoring
TPM was used to validate programme data to ensure the programme is on track, identify problems and address them on time. This was necessary as FCDO capacity to undertake extensive and regular visits was limited, especially due to COVID-19 travel restrictions, but also due to the design of the programme, covering a number of provinces. Unfortunately, the TPM data validation was not used for this PCR as the validation did not cover all indicators, and using a mix of unvalidated and validated data would make the analysis problematic. There were no large discrepancies between the TPM verified data and the programme data (less than 5%).
The monitoring and validation are judged to have been valuable over the life of the programme, as it led to TPM-IMA on-going refinements of the indicator definitions, and a more objective measuring of the project effectiveness and scoring. Through this work the independent TPM monitoring greatly assisted BEK in steering the project and deliver the expected results.
The TPM team leader led 19 external monitoring visits according to terms of reference developed with FCDO, IMA, and the provincial coordination teams for each visit. TPM visited the following locations: Kasaï (7), Kasaï Central (6), Nord-Ubangi (4), Maniema (2). The visits covered 43 of the 50 supported health zones and 53% (19/36) of the contractual requirement of 1 visit/province/quarter. This was lower than planned because of COVID-19 travel restrictions and strikes. FCDO and IMA joined some missions, and reports were submitted to FCDO after presentation of the key points with the implementing partners. The reports highlighted lessons learnt, recommendations, and managerial issues with medicines and health commodities, including the supply chain, with materials and equipment, the quality of the newly recruited DPS managers in Kasaï, and of supervision/coaching missions at all levels. The implementation of the recommendations was followed up during the monthly coordination meetings with FCDO and IMA/SANRU and documented in the quarterly reports. TPM validated the IMA quarterly reports and indicator tracking and developed, in conjunction with IMA and BEK, a metadata dictionary to reduce ambiguities, even though no consensus could be reached for a few indicators.

Date of last narrative financial report	IMA: N/A as only consolidated invoices are submitted / TPM: Financial report integrated into quarterly report of January 2022	Date of last audited annual statement	IMA: Consolidated audit from Parent company: 30 September 2021