## Narrative Report Tables
Sheet is password protected, all cells link to the logframe or metrics tables.
| NARRATIVE REPORT TABLES | UKRAINE | Q4
OUTPUT TABLES (quarterly reporting)
| Table 1: HALO Cumulative Progress on KPIs Q4 |  |  |  | Table 3: HALO Output 3 Progress, Iterative Q4 |  |  |  | Table 4: HALO Output 4 Progress, Iterative Q4
| KPI | Planned | Achieved | % Achieved | Output Indicator | Planned | Achieved | % Achieved | Output Indicator | Planned | Achieved | % Achieved
| Land cleared (sqm) | 50000 | 102759 | 205.5% | Land cleared (sqm) | 17000 | 46851 | 275.6% | EORE sessions | 600 | 1322 | 220.3%
| Land reduced (sqm) | 0 | 1012 | #DIV/0! | Land reduced (sqm) | 0 | 0 | #DIV/0! | Direct Beneficiaries of EORE (W) | 0 | 8369 | #DIV/0!
| EORE sessions | 675 | 2084 | 308.7% | Land cancelled (sqm) | N/A | 0 | N/A | Direct Beneficiaries of EORE (M) | 0 | 5521 | #DIV/0!
| Direct Beneficiaries of EORE (W) | 0 | 11414 | N/A | *No cancellation target but will report progress. |  |  |  | Direct Beneficiaries of EORE (G) | 0 | 4120 | #DIV/0!
| Direct Beneficiaries of EORE (M) | 0 | 7531 | N/A |  |  |  |  | Direct Beneficiaries of EORE (B) | 0 | 4269 | #DIV/0!
| Direct Beneficiaries of EORE (G) | 0 | 6076 | N/A |  |  |  |  | Total EORE Beneficiaries | 0 | 22279 | #DIV/0!
| Direct Beneficiaries of EORE (B) | 0 | 6075 | N/A
| Total Direct Beneficiaries of EORE | 0 | 31096 | #DIV/0!
OUTCOME TABLES (6 monthly reporting)
| *there are no outcome KPIs. | [11 empty] | Table 5: HALO Cumulative Progress Outcome Indicator 1.1 Q4
[13 empty] | Disaggregation | Direct Beneficaries Reached
[13 empty] | Women | 2544
[13 empty] | Men | 2038
[13 empty] | Girls | 369
[13 empty] | Boys | 390
[13 empty] | Total | 5341
*No target
Table 6: HALO Cumulative Progress Outcome Indicator 1.2 Q4
[13 empty] | Disaggregation | Indirect Beneficiaries Reached
[13 empty] | Women | 19972
[13 empty] | Men | 15690
[13 empty] | Girls | 2787
[13 empty] | Boys | 3018
[13 empty] | Total | 41467
*No target
Table 7: HALO Cumulative Progress Outcome 2 Q4
[13 empty] | Anticipated Land Use (sqm) | Achieved
[13 empty] | Residential | 34934.14
[13 empty] | Agricultural/pastoral | 36070.79
[13 empty] | Community development | 106.36
[13 empty] | Natural resources | 21690.54
[13 empty] | Infrastructure | 750.62
[13 empty] | Access | 10218.58
[13 empty] | Total | 103771.03
*No target
Table 10: HALO Outcome 3 Progress, Iterative Q4
[13 empty] | Output Indicator | Planned | Achieved | % Achieved
[13 empty] | Land cleared and reduced | 17000 | 46851 | 2.7559
Ukraine programmes: Cut & paste this table from your logframe/metrics file.

## Ukraine logframe
GMAP3 Ukraine Mine Action immediate response programme
Ukraine COUNTRY LOGFRAME |  |  | Baseline Data | Milestone 30th June 2022 |  | Milestone 30 September 2022 |  | Milestone 31st December 2022 |  | Milestone 31st March 2023
|  |  | DATE (TBC) | Planned | Achieved | Planned | Achieved | Planned | Achieved | Planned | Achieved
|  |  |  | Q1 |  | Q2 |  | Q3 |  | Q4
OUTCOME 1 | Outcome Indicator 1.1 | [10 empty] | Assumptions
Men, women, boys & girls benefit from land cleared and reduced | Number of direct beneficiaries from land cleared and reduced (SADD) [and percentage with disabilities] | Direct (Women) | 0 | 0 | 171 | 0 | 259 | 0 | 423 | 0 | 2544 | • Security situation remains as it is or improves in key areas where HALO seeks to conduct activities in Ukraine. • HALO secures permissions to conduct activities other than EORE and access to affected areas. • HALO employees conducting activities are exempted from conscription to the Ukrainian armed forces. • Importation of specialist dual-purpose equipment is facilitated to ensure humanitarian demining activities to take place. • COVID-19, natural disasters, or other outbreaks of disease do not hinder deployment of personnel. • Data (or approximate data) on population of settlements where HALO is working is available and data (or approximations) is available on displacement of populations in Ukraine. • No re-contamination of cleared areas takes place. • IDPs return to their original communities. • Data about disability within the population is available on at least an oblast level, and preferably as district level, and the methodology used to collect it can be ascertained. Failing this, the programme is able to start pre-clearance assessments prior to the end of the projects and gather sufficient to provide beneficiary disaggregation by disability.
|  | Direct (Men) | 0 | 0 | 141 | 0 | 212 | 0 | 342 | 0 | 2038
|  | Direct (Girls) | 0 | 0 | 26 | 0 | 36 | 0 | 61 | 0 | 369
|  | Direct (Boys) | 0 | 0 | 32 | 0 | 44 | 0 | 74 | 0 | 390
|  | Total (WMG&B) | 0 | 0 | 370 | 0 | 551 | 0 | 900 | 0 | 5341
|  | # of total with disabilities | 0 | 0 | #VALUE! | 0 | #VALUE! | 0 | #VALUE! | 0 | #VALUE!
|  | % of total with disabilities | 0% | #DIV/0! | #VALUE! | #DIV/0! | #VALUE! | #DIV/0! | #VALUE! | #DIV/0! | #VALUE!
(Data from pre-clearance assessments, targets set from baseline assessment and results from six-monthly reports)
Outcome Indicator 1.2
| Number of indirect beneficiaries from land cleared and reduced (SADD) | Indirect (Women) | 0 | 0 | 9894 | 0 | 11060 | 0 | 11957 | 0 | 19972
|  | Indirect (Men) | 0 | 0 | 7773 | 0 | 8690 | 0 | 9393 | 0 | 15690
|  | Indirect (Girls) | 0 | 0 | 1380 | 0 | 1543 | 0 | 1668 | 0 | 2787
|  | Indirect (Boys) | 0 | 0 | 1496 | 0 | 1672 | 0 | 1806 | 0 | 3018
|  | Total (WMG&B) | 0 | 0 | 20543 | 0 | 22965 | 0 | 24824 | 0 | 41467
|  | # of total with disabilities | 0 | 0 | #VALUE! | 0 | 0 | #VALUE! | 0 | #VALUE! | 0
|  | % of total with disabilities | 0% | #DIV/0! | #VALUE! | #DIV/0! | 0% | #VALUE! | 0% | #VALUE! | 0%
(Data from pre-clearance assessments, targets set from baseline assessment and results from six-monthly reports)
INPUTS (£) |  |  | FCDO
INPUTS (HR) |  |  | FCDO (FTEs)
*targets may increase after Q12 reporting
OUTCOME 2 | Outcome Indicator 2.1: Infrastructure, private & public property, land & public facilities are made available for potential use. | [10 empty] | Assumptions
Infrastructure, private & public property, land & public facilities are made available for potential use | m2 of formerly contaminated land either a) in use, or b) with plans in place for use following land release activities for i) residential purposes, ii) agricultural/ pastoral purposes, iii) community development/public services, iv) natural resources, v) infrastructure, vi) roads, bridges, paths and other access routes | Residential | 0 | 0 | 7.17 | 0 | 8345.99 | 0 | 32865.59 | 0 | 34934.14 | • Security situation remains as it is or improves in key areas where HALO seeks to conduct activities in Ukraine. • HALO secures permissions to conduct activities other than EORE and access to affected areas. • HALO employees conducting activities are exempted from conscription to the Ukrainian armed forces. • Importation of specialist dual-purpose equipment is facilitated to ensure humanitarian demining activities to take place. • COVID-19, natural disasters, or other outbreaks of disease do not hinder deployment of personnel. • Data (or approximate data) on population of settlements where HALO is working is available and data (or approximations) is available on displacement of populations in Ukraine. • No re-contamination of cleared areas takes place. • IDPs return to their original communities.
|  | Agricultural/pastoral | 0 | 0 | 11596.42 | 0 | 11960.17 | 0 | 12749.37 | 0 | 36070.79
|  | Community dev | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106.36
|  | Natural resources | 0 | 0 | 1179.2 | 0 | 2556.6 | 0 | 5012.01 | 0 | 21690.54
|  | Infrastructure | 0 | 0 | 89.45 | 0 | 197.72 | 0 | 574.9 | 0 | 750.62
|  | Access | 0 | 0 | 2537.76 | 0 | 2653.53 | 0 | 5718.15 | 0 | 10218.58
|  | Total | 0 | 0 | 15410 | 0 | 25714.01 | 0 | 56920.02 | 0 | 103771.03
(Data from pre-clearance assessments, targets set from baseline assessment and results from six-monthly reports)
INPUTS (£) |  |  | FCDO
INPUTS (HR) |  |  | FCDO (FTEs)
OUTCOME 3 | Outcome Indicator 3: Risk of harm reduced increases safety and normalisation | [10 empty] | Assumptions
Risk of death & injury to women, men, girls & boys | Area of land cleared and reduced (m2) |  | 0 | 2000 | 14398 | 18000 | 24702 | 33000 | 55908 | 50000 | 102759 | • Security situation remains as it is or improves in key areas where HALO seeks to conduct activities in Ukraine. • HALO secures permissions to conduct activities other than EORE and access to affected areas. • HALO employees conducting activities are exempted from conscription to the Ukrainian armed forces. • Importation of specialist dual-purpose equipment is facilitated to ensure humanitarian demining activities to take place. • COVID-19, natural disasters, or other outbreaks of disease do not hinder deployment of personnel. • Data (or approximate data) on population of settlements where HALO is working is available and data (or approximations) is available on displacement of populations in Ukraine. • No re-contamination of cleared areas takes place. • IDPs return to their original communities.
(Data from operational statistics, targets set from baseline assessment and results from six-monthly reports)
INPUTS (£) |  |  | FCDO
INPUTS (HR) |  |  | FCDO (FTEs)
OUTCOME 4 | [11 empty] | Assumptions
National mine action stakeholders have the skills & knowledge to regulate, manage & coordinate mine action more effectively with minimal outside technical support. | To be reported in the narrative | [10 empty] | • Good relations are maintained with relevant national mine action stakeholders. • Personnel from national mine action stakeholders have time, capacity and permission to attend trainings.
INPUTS (£) |  |  | FCDO
INPUTS (HR) |  |  | FCDO (FTEs)
Output 1
Increased collaboration with humanitarian, peace, stabilisation & development actors | To be reported in the narrative
OUTPUT 2 | Output 2 - not a KPI | [10 empty] | Assumptions
Community participation in HMA planning & activities as a result of CL visits | Number of CL visits |  | 0 | 0 | 102 | 0 | 172 | 0 | 247 | 0 | 370 | • Security situation remains as it is or improves in key areas where HALO seeks to conduct activities in Ukraine. • HALO secures permissions to conduct activities other than EORE and access to affected areas. • HALO employees conducting activities are exempted from conscription to the Ukrainian armed forces. • COVID-19, natural disasters, or other outbreaks of disease do not hinder deployment of personnel. • Data (or approximate data) on population of settlements where HALO is working is available and data (or approximations) is available on displacement of populations in Ukraine. • IDPs return to their original communities.
(Data from pre and post clearance household and community level assessments, NTS reports, handover reports and EOD callouts. Targets set from baseline assessment and resuts from quarterly reports)
INPUTS (£) |  |  | FCDO
INPUTS (HR) |  |  | FCDO (FTEs)
OUTPUT 3 | Output Indicator 3.1 | [10 empty] | Assumptions
Land has been cleared, reduced & cancelled in accordance with IMAS/NMAS | Area of land cleared (m2) |  | 0 | 2000 | 14398 | 18000 | 24702 | 33000 | 55908 | 50000 | 102759 | • Security situation remains as it is or improves in key areas where HALO seeks to conduct activities in Ukraine. • HALO secures permissions to conduct activities other than EORE and access to affected areas. • HALO employees conducting activities are exempted from conscription to the Ukrainian armed forces. • Importation of specialist dual-purpose equipment is facilitated to ensure humanitarian demining activities to take place. • COVID-19, natural disasters, or other outbreaks of disease do not hinder deployment of personnel. • No re-contamination of cleared areas takes place. • HALO either continues to work in close partnership with the SES and MOD to ensure the destruction of explosive hazards or HALO is granted permissions or an exemption from legislative that enables it to move explosive ordnance and/or conduct demolitions of ordnance found.
(Data from operational statistics, targets set from baseline assessment and results from quarterly reports)
Outpur Indicator 3.2
| Area of land reduced (m2) |  | 0 | 0 | 1012 | 0 | 1012 | 0 | 1012 | 0 | 1012
(Data from operational statistics, targets set from baseline assessment and results from quarterly reports)
Output Indicator 3.3
| Area of land cancelled (m2) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NO TARGET
Output Indicator 3.4
| # of EOD spot tasks |  | 0 | 0 | 6 | 0 | 9 | 0 | 11 | 0 | 25
NO TARGET
Output Indicator 3.5
| Items of EO destroyed (LR and EOD) (excluding SAA) |  | 0 | 0 | 29 | 0 | 32 | 0 | 36 | 0 | 167
NO TARGET
Output Indicator 3.6
| # of AP Mines |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
NO TARGET
Output Indicator 3.7
| # of Cluster Munitions |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NO TARGET
INPUTS (£) |  |  | FCDO
INPUTS (HR) |  |  | FCDO (FTEs)
OUTPUT 4 | Output Indicator 4.1 | [10 empty] | Assumptions
Men, women, boys and girls are more aware of the risk of harm from mines & ERW | Number of EORE sessions delivered |  | 0 | 0 | 39 | 0 | 120 | 75 | 762 | 675 | 2084 | • Explosive ordnance risk education is effective in increasing beneficiary knowledge and thereby changing behaviours. • Security situation remains as it is or improves in key areas where HALO seeks to conduct activities in Ukraine. • HALO employees conducting activities are exempted from conscription to the Ukrainian armed forces. • COVID-19, natural disasters, or other outbreaks of disease do not hinder deployment of personnel.
(Data from MRE session reports, targets set from baseline assessment and results from quarterly reports)
Output Indicator 4.2
| Number of direct beneficiaries of MRE (SADD and percentage with disabilities) | Direct (Women) | 0 | 0 | 75 | 0 | 696 | 0 | 3045 | 0 | 11414
|  | Direct (Men) | 0 | 0 | 84 | 0 | 400 | 0 | 2010 | 0 | 7531
|  | Direct (Girls) | 0 | 0 | 7 | 0 | 403 | 0 | 1956 | 0 | 6076
|  | Direct (Boys) | 0 | 0 | 10 | 0 | 384 | 0 | 1806 | 0 | 6075
|  | Total (WMG&B) | 0 | 0 | 176 | 1125 | 1883 | 2250 | 8817 | 6750 | 31096
|  | # of total with disabilities |  | 0 | #VALUE! | 78.7359 | 131.81 | 157.4717 | 617.0792 | 157.4717 | 2176.3291
|  | % of total with disabilites |  | #DIV/0! |  | 6.999% | 7% | 6.999% | 6.999% | 6.999% | 6.999%
(Data from MRE session reports, targets set from baseline assessment and results from quarterly reports)
Output Indicator 4.3
| Percentage of EORE beneficiaries surveyed who demonstrate increased knowledge of EORE safety messages |  | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
NO TARGET
INPUTS (£) |  |  | FCDO
INPUTS (HR) |  |  | FCDO (FTEs)
OUTPUT 5 | Output Indicator 5.1 | [10 empty] | Assumptions
Capacity of national mine action stakeholders is enhanced | Number of personnel from mine action stkeholders (SES) trained or supported by CD activities | Women | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | • Good relations are maintained with relevant national mine action stakeholders. • Personnel from national mine action stakeholders have time, capacity and permissions to attend trainings.
|  | Men | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
|  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
INPUTS (£) |  |  | FCDO
INPUTS (HR) |  |  | FCDO (FTEs)
Note on B90: Shamsa Hussain: CHECK IF THIS IS THE TOTAL OF ALL ITEMS DESTORYED?)

## Ukraine Metrics
Sheet is password protected. Forumas link to the individual Partnership Metrics Tables.
Quarterly Metrics Table for: | GMAP3 Ukraine Mine Action immediate response programme
KPIs (targets) |  | *contract began on 18th May
No Targets or measurement
Indicators | Disaggregation | Ukraine Emergency April 2022-March 2023 | [10 empty] | Overall Contract (Apr 2022 - 31 Mar 2023)
|  | Q1 Planned (April-June 2022) | Q1 Achieved (April-June 2022) | Q2 Planned (July-Sept 2022) | Q2 Achieved (July-Sept 2022) | Q3 Planned (Oct-Dec 2022) | Q3 Achieved (Oct-Dec 2022) | Q4 Planned (Jan-Mar 2023) | Q4 Achieved (Jan-Mar 2023) | EC GMAP 3 KPI Targets Planned Target | EC GMAP 3 KPI Achieved | % KPIs Complete | Overall Contract Target for KPIs | Overall Contract Achieved Total To Date | % KPIs Complete
Outcome 1: Men, women, boys & girls benefit from land cleared and reduced
1.1. Number of direct beneficiaries from land cleared & reduced (SADD and percentage with disabilities) | Direct Beneficiaries - Women (#) |  | 171 |  | 88 |  | 164 |  | 2121 | 0 | 2544 | #DIV/0! | 0 | 2544 | #DIV/0!
| Direct Beneficiaries - Men (#) |  | 141 |  | 71 |  | 130 |  | 1696 | 0 | 2038 | #DIV/0! | 0 | 2038 | #DIV/0!
| Direct Beneficiaries - Girls (#) |  | 26 |  | 10 |  | 25 |  | 308 | 0 | 369 | #DIV/0! | 0 | 369 | #DIV/0!
| Direct Beneficiaries - Boys (#) |  | 32 |  | 12 |  | 30 |  | 316 | 0 | 390 | #DIV/0! | 0 | 390 | #DIV/0!
| Total Direct | 0 | 370 | 0 | 181 | 0 | 349 | 0 | 4441 | 0 | 5341 | #DIV/0! | 0 | 5341 | #DIV/0!
| # of total with disabilities |  | ND |  | ND |  | ND |  | ND | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0!
| % of total with disabilities |  | ND |  | ND |  | ND |  | ND | 0 | 0 | #DIV/0! | #DIV/0! | 0% | #DIV/0!
1.2. Number of indirect beneficiaries from land cleared & reduced (SADD and percentage with disabilities) | Indirect Beneficiaries - Women (#) |  | 9894 |  | 1166 |  | 897 |  | 8015 | 0 | 19972 | #DIV/0! | 0 | 19972 | #DIV/0!
| Indirect Beneficiaries - Men (#) |  | 7773 |  | 917 |  | 703 |  | 6297 | 0 | 15690 | #DIV/0! | 0 | 15690 | #DIV/0!
| Indirect Beneficiaries - Girls (#) |  | 1380 |  | 163 |  | 125 |  | 1119 | 0 | 2787 | #DIV/0! | 0 | 2787 | #DIV/0!
| Indirect Beneficiaries - Boys (#) |  | 1496 |  | 176 |  | 134 |  | 1212 | 0 | 3018 | #DIV/0! | 0 | 3018 | #DIV/0!
| Total Indirect | 0 | 20543 | 0 | 2422 | 0 | 1859 | 0 | 16643 | 0 | 41467 | #DIV/0! | 0 | 41467 | #DIV/0!
| # of total with disabilities |  | NA |  | NA |  | NA |  | NA | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0!
| % of total with disabilities |  | NA |  | NA |  | NA |  | NA | #DIV/0! | 0% |  | #DIV/0! | 0% | #DIV/0!
Outcome 2: Infrastructure, private & public property, land & public facilities are made available for potential use
Area of formerly contaminated land either a) in use, or b) with plans in place for use following land release activities for i) residential purposes, ii) agricultural/pastoral purposes, iii) community development/public services, iv) natural resources, v) infrastructure, vi) roads, bridges, paths & other access routes (m2) | Residential |  | 7.17 |  | 8338.82 |  | 24519.6 |  | 2068.55 | 0 | 34934.14 | #DIV/0! | 0 | 34934.14 | #DIV/0!
| Agricultural/pastoral |  | 11596.42 |  | 363.75 |  | 789.2 |  | 23321.42 | 0 | 36070.79 | #DIV/0! | 0 | 36070.79 | #DIV/0!
| Community dev |  | 0 |  | 0 |  | 0 |  | 106.36 | 0 | 106.36 | #DIV/0! | 0 | 106.36 | #DIV/0!
| Natural resources |  | 1179.2 |  | 1377.4 |  | 2455.41 |  | 16678.53 | 0 | 21690.54 | #DIV/0! | 0 | 21690.54 | #DIV/0!
| Infrastructure |  | 89.45 |  | 108.27 |  | 377.18 |  | 175.72 | 0 | 750.62 | #DIV/0! | 0 | 750.62 | #DIV/0!
| Access |  | 2537.76 |  | 115.77 |  | 3064.62 |  | 4500.43 | 0 | 10218.58 | #DIV/0! | 0 | 10218.58 | #DIV/0!
| Total land | 0 | 15410 | 0 | 10304.01 | 0 | 31206.01 | 0 | 46851.01 | 0 | 103771.03 | #DIV/0! | 0 | 103771.03 | #DIV/0!
Outcome 3: Risk of harm reduced increases safety and normalisation
3. Area of land cleared and reduced (m2) |  |  | 15410 |  | 10304 |  | 31206 |  | 46851 | 0 | 103771 | #DIV/0! | 0 | 103771 | #DIV/0!
Output 2: Community participation in HMA planning & activities as a result of CL visits & Information on the presence & impact of mines & ERW
2. Number of CL visits |  |  | 102 |  | 70 |  | 75 |  | 123 | 0 | 370 | #DIV/0! | 0 | 370 | #DIV/0!
Output 3: Risk from Explosive Ordnance removed.
3.1. Area of land cleared (m2) | Mineclearance
| Land Cleared (m2) | 2000 | 14398 | 16000 | 10304 | 15000 | 31206 | 17000 | 28499 | 50000 | 84407 | 168.8% | 50000 | 84407 | 168.8%
| Areas Cleared (#) |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0!
| BAC |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0!
| Subsurface Battle Area Cleared (m2) |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0!
| Surface Battle Area Cleared (m2) |  | 0 |  | 0 |  | 0 |  | 18352 | 0 | 18352 | #DIV/0! | 0 | 18352 | #DIV/0!
| Areas Cleared (#) |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0!
| Total Land Cleared | 2000 | 14398 | 16000 | 10304 | 15000 | 31206 | 17000 | 46851 | 50000 | 102759 | 205.5% | 50000 | 102759 | 205.5%
| Road Cleared/reduced (km) |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0!
3.2. Area of land reduced (m2) | Land Reduced by Technical Survey (m2) | 0 | 1012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1012 | #DIV/0! | 0 | 1012 | #DIV/0!
| Areas Reduced (#) |  | 3 |  | 0 |  | 0 |  | 0 | 0 | 3 | #DIV/0! | 0 | 3 | #DIV/0!
3.2. Area of land cancelled (m2) | Tasks Resurveyed by NTS(#) |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0!
| Area Resurveyed by NTS(m2) |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0!
| Tasks Cancelled by NTS(#) |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0!
| Area Cancelled (m2) |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0!
| Tasks remaining after NTS(#) |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0!
| Area remaning after NTS(m2) |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0!
| Newly identified Area (m2) |  | 1082157 |  | 216446 |  | 231799 |  | 390288 | 0 | 1920690 | #DIV/0! | 0 | 1920690 | #DIV/0!
| Newly Identified Areas (#) |  | 16 |  | 7 |  | 4 |  | 7 | 0 | 34 | #DIV/0! | 0 | 34 | #DIV/0!
Additional Information | Total land released (sqm) |  | 15410 |  | 10304 |  | 31206 |  | 46851 | 0 | 103771 | #DIV/0! |  | 103771 | #DIV/0!
| Total Areas Released (#) |  | 0 |  | 3 |  | 0 |  | 2 | 0 | 5 | #DIV/0! |  | 5 | #DIV/0!
| EOD Call-outs / Spot Tasks (#) |  | 6 |  | 3 |  | 2 |  | 14 | 0 | 25 | #DIV/0! |  | 25 | #DIV/0!
| AP Mines (#) |  | 0 |  | 0 |  | 0 |  | 6 | 0 | 6 | #DIV/0! |  | 6 | #DIV/0!
| AT Mines (#) |  | 1 |  | 0 |  | 0 |  | 44 | 0 | 45 | #DIV/0! |  | 45 | #DIV/0!
| UXO (#) |  | 28 |  | 2 |  | 1 |  | 84 | 0 | 115 | #DIV/0! |  | 115 | #DIV/0!
| Abandoned Explosive Ordnance ≥20mm (#) |  | 0 |  | 1 |  | 3 |  | 3 | 0 | 7 | #DIV/0! |  | 7 | #DIV/0!
| Small Arms Ammunition <20mm (#) |  | 0 |  | 0 |  | 1 |  | 184 | 0 | 185 | #DIV/0! |  | 185 | #DIV/0!
| IED (#) |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | #DIV/0! |  | 0 | #DIV/0!
| Cluster Munitions (#) |  | 0 |  | 0 |  | 0 |  | 16 | 0 | 16 | #DIV/0! |  | 16 | #DIV/0!
Output 4: Men, women, boys & girls are more aware of the risk of harm from mines & ERW
4.1 Number of EORE sessions delivered |  | 0 | 39 |  | 81 | 75 | 642 | 600 | 1322 | 675 | 2084 | 308.7% | 675 | 2084 | 308.7%
4.2. Number of direct beneficiaries of MRE (SADD and percentage with disabilities) | Direct EORE Beneficiaries - Women (#) |  | 75 |  | 621 |  | 2349 |  | 8369 | 0 | 11414 | #DIV/0! | 0 | 11414 | #DIV/0!
| Direct EORE Beneficiaries - Men (#) |  | 84 |  | 316 |  | 1610 |  | 5521 | 0 | 7531 | #DIV/0! | 0 | 7531 | #DIV/0!
| Direct EORE Beneficiaries - Girls (#) |  | 7 |  | 396 |  | 1553 |  | 4120 | 0 | 6076 | #DIV/0! | 0 | 6076 | #DIV/0!
| Direct EORE Beneficiaries - Boys (#) |  | 10 |  | 374 |  | 1422 |  | 4269 | 0 | 6075 | #DIV/0! | 0 | 6075 | #DIV/0!
| Direct EORE Beneficiaries - Total | 0 | 176 | 1125 | 1707 | 1125 | 6934 | 4500 | 22279 | 6750 | 31096 | 460.7% | 6750 | 31096 | 460.7%
| # of total with disabilities (include from WGSS) |  | ND |  | 23 |  | 1 |  | 3 | 0 | 27 | 0% | 0 | 27 | 0%
| % of total with disabilities |  | ND |  | 1.347% | 0% | 0.01442% | 0% | 0.9434% | #DIV/0! | 8.491% | 0% | 0% | 0.08683% | 0
4.3 Percentage of EORE beneficiaries surveyed who demonstrate increased knowledge of EORE safety messages | # people surveyed |  | 0 |  | 0 |  | 0 |  | 318 | 0 | 318 | 0.07 | 0 | #REF! | #DIV/0!
| # of people surveyed who demonstrate increased knowledge of EORE safety messages |  | 0 |  | 0 |  | 0 |  | 189 | 0 | 189 | 0.07 | 0 | 189 | #DIV/0!
| % (automatic calculation) |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 59.43% | #DIV/0! | 100% | 100% | #DIV/0! | 1 | #DIV/0!
Output 5: Enhanced capacity of national mine action authorities
5.1. Number of personnel from mine action stakeholders (SES) trained or supported by CD activities | Women |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0!
| Men |  | 0 |  | 0 |  | 0 |  | 6
| Total trained | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 6 | #DIV/0! | 0 | 6 | #DIV/0!
Note on J55: Serhii Hryshyn: Changed from 3 to 4 as an additional NTS report was checked and added to the database. The m2 above were adjusted accordingly.
Note on J62: Serhii Hryshyn: Number of AXO changed from 2 to 3 following the database review