Programme Completion Review

Title: Annual assessed contribution over four calendar year-period 2020-2023 to the United Nations Educational, Scientific and Cultural Organisation
Final Programme Spend £ (full life): £47,031,276.45 (£~12m p/a)	Review Date:	15 March 2024
Programme Code: 300677	Start Date: 25 March 2020	End Date: 31 December 2023

Summary of Programme Performance

Year	2016	2017	2018	2019	2020	2021	2022	2023
Programme Score	C	B	A	A	A	A	A	A
Residual Risk Exposure Rating	Major	Major	Major	Major	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case (and any addendum):	N/A (at the time of programme inception, mandatory international subscriptions such as this were business case exempt)
DevTracker Links to all logframes used during programme lifetime:	N/A

A. Summary and Overview

Description of the programme and what it has achieved

The Foreign, Commonwealth & Development Office (FCDO) is the lead department for the UK’s relationship with the United Nations Educational, Scientific and Cultural Organisation (UNESCO) and is responsible for paying the UK’s annual assessed contribution to UNESCO. This programme was the mechanism through which the UK paid its annual assessed contribution to UNESCO between 2020 and 2023 (4 annual payments). This assessed contribution is mandatory and pays for the UK’s membership of this multilateral organisation. UNESCO member
states’ assessed contributions are based on the UN scale of assessment, which calculates a country’s dues based on their “capacity to pay”. This is the same formula used to determine each country’s contributions to the UN regular budget and the peacekeeping budget.

UNESCO is a specialised agency of the UN with 193 member states. As an intergovernmental organisation it provides a normative forum for the negotiation of global agreements, and a facility for policy exchange and capacity building. The UK works with UNESCO for the delivery and promotion of international collaboration in education, science, culture, and information and communication. The Organisation is a key partner for the UK on issues including: the delivery of global education (including our SDG4 girls’ access and learning objectives); protection of cultural heritage; ensuring the protection of journalists and a free media; the promotion of open science; the ethics of AI; oceans; and climate change. UNESCO is also responsible for biosphere reserves, UNESCO University Chairs, World Heritage Sites, Creative Cities and other similar accreditations.

Our assessed contribution goes towards UNESCO’s regular budget, which can be used flexibly by the organisation to support any of the objectives in its medium term strategy. As such, UK funds provided through this programme cannot be attributed to specific programmes or projects. Furthermore, during the period of this programme the UK was not a member of the Executive Board – the principal governing body which determines the shape and direction of UNESCO’ programme and budget. Therefore, a set of proxy indicators were chosen in order to monitor and assess UNESCO performance throughout the lifetime of this programme, including the UK’s top policy interest at UNESCO (education) and a range of operational and reform-related priorities.

During the period covered by this programme, UNESCO completed its ‘strategic transformation programme’, the flagship change initiative led by the current Director-General, Audrey Azoulay. These reform efforts enabled UNESCO to lay the foundations for a better management culture, greater openness to partnerships, better approach to evaluation and greater staff mobility. The organisation demonstrated its agility by pivoting to respond to emerging technological developments (eg adopting the Recommendation on the Ethics of AI), and crises and conflicts (in particular in Ukraine and Israel/Gaza). UNESCO has also made progress on repositioning itself within the UN system.

UNESCO scored well in the 3 of the 4 outputs measured in this review, meeting expectations across impact reporting, operational effectiveness and risk management, and partnerships and effective coordination. In each of these fields, the UNESCO Secretariat made significant progress towards the identified indicators. UNESCO partially met expectations in relation to leadership of the education 2030 agenda as, under UNESCO’s leadership (but driven largely by the Covid-19 pandemic), insufficient progress has been made towards the realisation of SDG4.

Major lessons learned, evidence generated and recommendations

UNESCO should:
- continue proactively learning from other technical agencies, sharing experience and best practice expertise (eg in the field of impact reporting).
- more ruthlessly prioritise and be more proactive/open about closely under performing projects and programmes.

The UK should:
- be as explicit as possible about our expectations of the organisation (eg the types of actors we would like to see them partnering with, and data requirements for SDG4).
- use its positions on the Executive Board and the High Level Steering Committee on SDG4 to build support for priority programmatic and reform objectives.

Together UNESCO and the UK should:
- champion the importance of education data (including SDG indicator 4.1.1a).
- raise UNESCO’s profile within the wider UN system.

How this report was conducted

As this programme was business case exempt, a proportionate approach has been taken to this report. Key evidence was drawn from the DfID/FCDO annual reviews conducted during this period, together with consultation with the UK Delegation to UNESCO and and key HMG stakeholders. This was supplemented with a field visit to the Southern Africa regional UNESCO office (based in Harare, Zimbabwe), and the inaugural UK-UNESCO Strategic Dialogue (held in London in February 2024).

Actions following approval of this report

The successor programme for the payment of the UK’s assessed contribution to UNESCO will, under current programme management rules, now be subject to a business case. This is currently going through the FCDO internal approvals process, after which attention will turn to refreshing the outcomes against which that successor programme will be assessed. There are no outstanding actions with respect to final payments or unspent funds.

## B: Theory of Change and Outcome Assessment

	Starting point	Final result
Budget	This programme was expected to cost ~£12m per year, paid partly in USD and partly in EUR (a total of £48m over the 4 year period)	Due to fluctuating exchange rates, the total spend under this programme was £47,031,276.45
Timeframe	45 months (one payment made in each calendar year, 2020-2023)	45 months
Outcomes / Outputs	As there was no business case or theory of change for this programme, there was no one outcome-level target. Instead, progress was measured across 4 key output indicators: / 1. UNESCO’s progress in reporting on results and impact so that it is able to demonstrate the difference it is making, with a greater focus on measuring outcomes rather than outputs and demonstrating that it is engaging with partners in the process. / 2. UNESCO’s demonstration of its leadership of the education 2030 agenda and sector, effectively convening and coordinating members states and global education actors in education, and influencing governments with its policy analysis, advocacy and capacity building roles. / 3. Organisational effectiveness and risk management (with particular emphasis on reform, transparency, accountability and efficiency) / 4. Partnerships and effective coordination	There were no changes to these indicators during this programme. Details against each of these outputs are provided on the following pages.

Overall assessment of programme outcomes, sustainability and VfM

As noted in the table above, this programme was business case and theory of change exempt. That, together with the not attributable nature of this funding, means that there were no outcome-level indicators for this programme. UNESCO’s performance against the four output indicators is considered in detail in the following sections, and in the three annual reviews conducted during the lifecycle of this programme.

During this programme period our assessed contribution remained constant and therefore sustainable. Despite rising operational and staffing costs associated with inflation, the return of the United States to UNESCO’s membership should mean no increased to the assessed contribution in the near future. UNESCO’s financial situation is better now, at the end of the programme, than at the start or throughout most of this period. The organisation’s ability to deliver on its mandate (and make further progress against the output indicators highlighted in this review) is therefore also now on a more sustainable footing for the immediate future.

As explained in Section D, below, value for money of multilateral assessed contributions are conceptually problematic. However, considering the significant steps UNESCO has taken in recent years to improve its internal operations and delivery, the organisation offers better value than it did at the time of the last Multilateral Development Review in 2016.

Summarise the programme’s theory of change and results framework, including any changes to outcome indicators.

A business case and theory of change were not applicable for this programme. UK funding provided through this programme is an international subscription, an assessed contribution which is an obligation of membership. The funding is provided in accordance with the pre-agreed schedules and spent as per the budget agreed by the governing bodies. In light of this, any business case loses its central rationale (whether or not to fund). For this reason, the UK’s assessed contribution to UNESCO through this programme was business case exempt.

There were no changes to outcome indicators during this programme period. UNESCO reports on its own performance through a system of key performance indicators. The latest reporting against these can be found here.
## C: Detailed Output Assessment [aim for max. 1 page per output. Repeat for each output]

Output Number and Title	1. UNESCO develops reporting on results and impact so that it is able to demonstrate the difference it is making, with a greater focus on measuring outcomes rather than outputs and demonstrating that it is engaging with partners in the process.
Output Score	A
Impact weighting (%)	30	Impact weighting revised since last AR?	No

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

This programme scored an A for this output across all 3 annual reviews completed. The output indicators (discussed below) remained consistent for the lifecycle of the programme.

1: UNESCO adopts a more strategic approach to assessing and defining the impact of programmes and the concrete results they are producing on the ground, with an increased focus on measuring outcomes rather than just outputs.

UNESCO maintained an increasing focus on measuring outcomes rather than outputs over the lifetime of the programme. During this period, the Medium Term Strategy for 2022-29 included an innovative reframing of UNESCO’s strategic and enabling objectives in the context of their corresponding outcomes. This strategic framework underpins the Programme and Budget for 2022-25 and provides the structure for the Secretariat’s improved reporting process to Member States through the twice yearly Executive Boards. Through a process of iteration of the programme period, the new, single C5 Implementation Report (replacing the Performance Implementation Report and the Financial Management Report) has streamlined reporting and support a more focussed, strategic discussion at the Executive Board. Discussions between the UK and the Secretariat indicate ongoing appetite within the organisation to better understand and communicate their impact, particularly to donors.

2: UNESCO clearly evaluates and reports on results, impact and partnerships, and enhances the use of results in decision making.

While there have been improvements over this period in the way in which UNESCO seeks to evaluate its activities (for example through a new set of performance indicators as part of the C5 Implementation Report), the UK (and others) consistently raised concerns that the Internal Oversight Service was underfunded to enable it to gather a broad enough sample of data to accurately assess performance across the span of the organisation’s portfolio and geographical network. The return of the United States in July 2023, and the consequent increase in the organisation’s funding, has allowed the Secretariat to put the IOS onto a more sustainable financial footing in the 2024-25 biennium. The challenge remains to ensure all IOS recommendations (for example those pertaining to field office audits) are effectively implemented.

Lessons learned through this output, and recommendations for future programming

While the Secretariat, under the leadership of the current Director General, has been institituionally open to developing and improving how it reports of results, the quickest progress during this programme period has been the result of new senior staff appointments, drawn from elsewhere in the UN system. This suggests that UNESCO should look to continue learning from other technical agencies, sharing experience and best practice expertise.

Despite the influx of additional funding following the United States’ return, it will remain important for the UK (and others) to champion to work of the IOS, and argue for commensurable funding from the regular budget. Recognising this will mean less money for programme delivery, we should continue to push for prioritisation and ward against competence creep.

Output Number and Title	2. UNESCO demonstrates its leadership of the education 2030 agenda and sector, effectively convening and coordinating member states and global education actors in education, and influencing governments with its policy analysis, advocacy and capacity building roles.
Output Score	B
Impact weighting (%)	30	Impact weighting revised since last AR?	No

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

This programme scored an A in the 2021 annual review, but a B in the subsequent 2022 and 2023 reviews. This reflects, in large part, the impact of the Covid-19 pandemic on global learning and progress towards SDG4 (now very much off track).

The output indicators (discussed below) remained consistent for the lifecycle of the programme.

1: UNESCO progresses work on the SDG4 agenda up to and beyond 2030 with vision, policy and impact results reporting.

UNESCO is the lead UN agency for the realisation of SDG4 (quality education for all), and as such has maintained a keen focus on this strand of work for the duration of the programme period. UNESCO codified SDG4 as ‘strategic objective 1’ in the 2022-29 Medium Term Strategy, and co-convened the UN Transforming Education Summit (TES) in New York in September 2022. The UNESCO Secretariat listened to our (and others’) concerns regarding what we saw as the overly broad (not tightly prioritised enough) scope of their initial TES plans, and adapted accordingly. The TES delivered 6 global initiatives to be tracked through the High Level Steering Committee on SDG4 (the HLSC). Progress towards SDG4 remains significantly off track, however, and we would like to see UNESCO providing much needed global leadership to galvanise swift progress. As discussed during the recent UK-UNESCO Strategic Dialogue, this should include a (joint) push on the importance of data – there remain substantial gaps in the data we need to track progress against SDG4, and too little disaggregation of data.

2: UNESCO is able to demonstrate an improved approach to convening and coordinating member states and global education actors in its Education work, and to demonstrate its advocacy, policy setting and capacity-building engagement with member states.

UNESCO consistently met expectations against this indicator during this programme period, demonstrating increasingly coordinated action with MS donors, other UN agencies and private sector actors. UNESCO is a permanent member of the SDG Education 2030 Steering Committee, convened Global Education Meetings, and completed a much needed reform of the SDG4 High Level Steering Committee. UNESCO coordinated well between global education actors in advance of the TES, however it is unclear how well the TES reached decision-makers outside of the education sector.

3: Utilise and demonstrate the value of UNESCO’s specialised education institutes (Category 1 institutes) around the world in advancing work on SDG4.

Enhancing coordination and cooperation between UNESCO HQ and its category 1 institutes is a work in progress. Although progress has been achieved over this period, it has been slow, likely because this is not a high priority for MS nor for an (until recently) financially stretched Secretariat. UNESCO now publishes the annual reports of category 1 institutes on its website, but clearer direct reporting to the Executive Board on cooperation and performance would be welcome.

Lessons learned through this output, and recommendations for future programming

As the UK-UNESCO Strategic Dialogue demonstrated, there are opportunities to work more closely together on the SDG4 data agenda. To achieve best results, the UK should be as explicit as possible about our expectations – for example about the types of non-educator sector actors we would like UNESCO to engage with (eg climate funds) and data requirements (eg protection of SDG indicator 4.1.1.a). The UK should also use its new seat on the HLSC (elected November ‘24) to build on UNESCO’s reforms, ensuring transparency and appropriate consultation with the donor constituency.

Output Number and Title	3. Organisational effectiveness and risk management - reform, transparency, accountability and efficiency
Output Score	A
Impact weighting (%)	20	Impact weighting revised since last AR?	No

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

This programme scored a B in the 2021 annual review, but an A in the subsequent 2022 and 2023 reviews, reflecting progress achieved through UNESCO’s ‘strategic transformation’ programme. The output indicators (discussed below) remained consistent for the lifecycle of the programme.

1: UNESCO shows commitment to, and demonstrates, improving transparency.

During this programme period, UNESCO updated and relaunched an improved transparency portal, and made welcome progress in improving the timeliness and accuracy of the data provided through the portal. Central to the organisation’s Medium Term Strategy is the requirement to embed a culture of transparency and accountability. For the most part, we are satisfied that UNESCO’s systems of internal audits and reporting to the Executive Board maintain a high degree of transparency. However, a recent issue regarding a $5.6m overspend in 2023 demonstrates that there is scope for further transparency with Member States.

2: UNESCO has robust systems in place to prevent and respond to fraud.

UNESCO consistently scored ‘partially met expectations’ on this indicator throughout the programme period. Although UNESCO has appropriate policies in place, the organisation has lacked sufficient resources to fully manage financial risk. UNESCO, aware of this risk, took measures to strengthen the Secretariat’s capacity to manage this type of risk. At the time of the last annual review, the new team was in place. Although the above mentioned overspend suggests UNESCO would benefit from tighter internal financial risk controls, there is nothing to suggest there was any element of fraud.

3: UNESCO works to streamline services and reduce costs.

UNESCO consistently met expectations against this indicator throughout the programme period. Over recent years, much progress has been made to improve the operational effectiveness of the Secretariat – for example the adoption of a new intersectoral approach through the Medium Term Strategy, designed to incentivise sectors to work and deliver jointly.  Significant initiatives are also underway to exploit opportunities for efficiencies through collaboration with other multilaterals within the field network, including a series of strategic dialogues with UNICEF and other relevant UN agencies. Work continues on the reform of the field network, while more could be done to align UNESCO with other agencies in the field (including but not limited to the use of common premises and services). There remains a sense, however, that UNESCO is institutionally reticent to close projects even where performance cannot be clearly evidenced – more detailed reporting to MS on when this does occur would be helpful.

4: UNESCO to demonstrate further progress on its reform programme.

UNESCO’s performance against this indicator improved over the lifecycle of this programme. The reforms instituted through the ‘strategic transformation programme’ enabled UNESCO to lay the foundations for a better management culture, greater openness to partnerships, better approach to evaluation and greater staff mobility. Despite the closure of that programme, the UK has welcomed UNESCO’s continued commitment to organisational reform, particularly the Secretariat’s approach to revamping reporting and improving field operations. UNESCO now reports annually on ‘the repositioning of the UN development system’, and through the UK-UNESCO Strategic Dialogue it was clear that UNESCO is proactively engaged with planning for the UN Summit of the Future, and raising the organisation’s profile in wider UN circles.

Lessons learned through this output, and recommendations for future programming

There was a risk that with the closure of the ‘strategic transformation programme’, UNESCO would cease any further reformation activity. This has not been the case, in part due to good practices within the Secretariat and in part due to MS expectations communicated through the Executive Board. Care should be taken to maintain this ‘pressure’, continue to encourage behaviour in line with the UN Reform agenda, and to maintain close oversight of UNESCO’s internal financial risk management.

Output Number and Title	4. Partnerships and effective coordination
Output Score	A
Impact weighting (%)	20	Impact weighting revised since last AR?	No

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

This programme scored a B in the 2021 annual review, but an A in the subsequent 2022 and 2023 reviews – largely the result of a more concerted effort by UNESCO to engage more proactively with the wider UN system.

The output indicators (discussed below) remained consistent for the lifecycle of the programme.

1: UNESCO has a clear strategy regarding its interaction with other international organisations that overlap with/ complement areas of its mandate.

UNESCO consistently met expectations against this indicator throughout the programme period. UNESCO has a ‘comprehensive partnership strategy’ and the C5 Implementation Report (presented annually to the Executive Board) details how UNESCO works with partners on the funding and delivery of each strategic objective. Indeed, voluntary funding from partners makes up a substantial part of UNESCO’s funding - $816.4m was secured in 2022-23, an increase of 8% from the previous biennium. The organisation’s ‘resource mobilisation strategy’ sets out how partnership agreements will be streamlined and simplified to facilitate getting more such funding, without compromising the integrity of due diligence assessments. Most of the focus, however, is on HQ to HQ complementarity and coordination. While UNESCO field offices collaborate closely with other UN agencies on the ground, it is not clear how systematic their engagement is with other international organisations/donors.

2: UNESCO demonstrates full engagement and coordination with UNSG’s UN reform efforts.

UNESCO’s performance against this indicator improved over the lifecycle of this programme. UNESCO has taken concrete steps to improve its engagement with UN reform efforts at both HQ and network level. The organisation is directly involved in the implementation of a number of the ‘Our Common Agenda’ recommendations, has sought a more substantial role on the UN stage (eg co-leading the TES), participates in the UNSDG Task Force on Resident Coordinator Talent Management and is also engaged in a multi-year development process for a new coordination instrument to support the work of UN Development and Resident Coordinators. UNESCO actively advocates for deeper integration of UNESCO work within Cooperation Frameworks across the regions, and co-hosted the first round table with United Nations Resident Coordinators on indigenous knowledge systems and their role in delivering the Sustainable Development Goals.

3: UNESCO further improves collaboration between headquarters, institutes, regional and country offices to translate the emerging priorities into coherent action.

UNESCO consistently scored ‘partially met expectations’ on this indicator throughout the programme period. The new ‘intersectoral’ approach is still bedding in, and as recently as last year there were concerns that coordination between HQ and field offices was lacking. There are signs in the latest C5 Implementation Report that UNESCO’s recent focus on field network reform is starting to bear fruit – for example, capacity building at the regional and country level for stratefic engagement in UN country programmes and joint resource mobilisation, and increased provision of regional L&D workshops.

Lessons learned through this output, and recommendations for future programming

The overriding lesson from this output, and indeed the other three, is that organisational change takes time. This is of course not unique to UNESCO, but now the UK is back on the Executive Board, there are increased opportunities for championing the reform agenda alongside our programmatic priorities. It will be important to raise our concerns and express our expectations clearly and consistently, and to invest in maintaining the constructive relationship with the UNESCO leadership forged through the recent UK-UNESCO Strategic Dialogue. There is appetite within the Secretariat both for the UK to act as a critical friend on reform issues, and to help champion the organisation’s role and voice in the wider UN system.

D: Value for Money

The UK’s contribution via this programme is an assessed contribution which is an obligation of membership. The funding is provided in accordance with the pre-agreed schedules and spent as per the budget agreed by the organisation’s governing bodies.

Multilateral organisations generally perform a wide range of functions, and many operate across multiple sectors.  This gives rise to conceptual difficulties in assessing their value for money, often compounded by practical problems of gaps in the data on both outcomes and costs.   However, UNESCO has taken significant steps to improve its internal operations and delivery, and offers better value than it did at the time of the last Multilateral Development Review in 2016. The embedding and implementation of transformation recommendations (drawn from the Strategic Transformation plan, which addressed the optimisation of administrative and management issues), remains UNESCO’s best route for maximising progress on effectiveness and organisational capability.  Assessing the results of UNESCO’s new Medium-Term Strategy and ongoing transformation efforts will provide for a good measure of the organisation’s effectiveness and organisational capability and will inform the value for money question in coming years.

E: Risk

The overall risk of the programme during this period has remained moderate, reflecting UNESCO’s ongoing efforts to strengthen internal corporate and management policies and processes, while recognising there are still some areas in need of improvement.  As such, we were able to deliver this programme within the FCDO’s risk appetite for the duration. The FCDO has assessed the top risks as follows:

    - Strategy & context:  The UK lacks the capacity to effectively counteract malign states' influence at UNESCO (major residual risk).
    - Policy & programme delivery: 'Mandate creep', facilitated by the increase to the regular budget (US funding), results in UNESCO duplicating work more properly undertaken by other agencies, reducing the vfm of UK funding contributions and risking delivery of the organisation's core mandate (moderate residual risk).
    - Policy & programme delivery: UNESCO is unable to effectively utilise the influx of additional funding owing to the US return (an additional $150m per biennium), impacting the strategic impact of the organisation.  Most of the proposed spending is on people costs, but recruitment into UNESCO can be a lengthy process, so there is a contingent risk that the money is not spent within the biennium timeframe (moderate residual risk).
    - Financial & fiduciary: Gaps in UNESCO's due diligence process could lead to the engagement of partners lacking the capacity (or reputation) to effectively support the delivery of UNESCO’s mandate (moderate residual risk).

F: Programme Management: Commercial and Financial Performance, Monitoring and Evaluation

UNESCO has a broad mandate which, for this programme period, was not adequately served by its regular budget.  This is not due to financial mismanagement, but global rising costs and the cessation of the United State’s contributions in 2011 (which alone left a 22% hole in the organisation’s budget).  It is also not uncommon for many member states to pay their assessed contributions late in the year (including the UK), or to be in arrears, which further complicates UNESCO’s in-year financial planning.

UNESCO absorbed these budgetary pressures as far as possible through the streamlining of staff structures and administrative costs, but this led to a growing overreliance on voluntary funding to plug the gaps. While an increase in voluntary funding in recent years is symptomatic of the trust and confidence of UNESCO’s donors and the success of UNESCO’s outreach activity, such donations are often earmarked and so cannot be used to fund central functions.  An overreliance on voluntary contributions is neither stable nor sustainable, and can lead to the political manipulation of UNESCO’s budgetary resources by those member states who invest most in this regard. With the return of the United States in July 2023, UNESCO’s financial affairs are back on a much more sustainable footing. The challenge will be restraining institutional ambition, ensuring appropriate prioritisation, and avoiding mandate creep/duplication of work better led by other agencies.

Date of last narrative financial report	8 September 2023	Date of last audited annual statement	8 September 2023