Strategic Impact Evaluation and Learning (SIEL) Programme Business Case – May 2023

Summary Sheet

Portfolio/ Business/Country Plan Summary: / The FCDO Evaluation strategy aims to support the full breadth of FCDO diplomatic and development work. Under the lead of the Evaluation Unit, the strategy aims to deliver: new evaluation evidence on key strategic issues; programmes offering independent quality assurance and technical assistance; efficient access to high-quality evaluation suppliers; improved communication of evaluation findings and lessons; and, build evaluation capacity across the organisation. The Strategic Impact Evaluation and Learning (SIEL) Programme will contribute to these goals by generating impact evaluation evidence about new as well as previously evaluated programmes and build capacity in FCDO around impact evaluation.

Programme summary (100 words maximum): / The Strategic Impact Evaluation and Learning (SIEL) programme will support FCDO to use Randomised Controlled Trials (RCTs), quasi -experimental methods and other techniques as appropriate to rigorously assess the impact of FCDO’s interventions. It will fund evaluations with high potential to generate actionable knowledge. SIEL will follow up where previous studies have measured impact to assess long term sustainability, and raise capacity in FCDO to commission, manage and interpret impact evaluation evidence. This will enable better decision-making, maximising Value for Money and the long run effectiveness of FCDO activities for reducing poverty and improving UK influence around the world.
What is the rationale for UK Aid spending? (200 words maximum): / Appropriately used, RCTs and other forms of impact evaluation can provide robust evidence on whether interventions work and their value for money. These methodologies are already used in FCDO, but there are two key issues which SIEL will address: / Impact evaluations are not always used where needed to fill evidence gaps related to FCDO’s strategic priorities; / Impact evaluations happen only in programmes with a generous budget to finance them and where relevant expertise is already in place. / SIEL will make FCDO’s evaluation portfolio more robust, strategic, and aligned with the organisation’s priorities. The programme is critical for operationalising the Evaluation Strategy published in July 2022 and will contribute to FCDO meeting its scrutiny and accountability obligations as an Official Development Assistance (ODA) spending department, under the 2015 International Development Act. SIEL will contribute to the aims of the 2023 Integrated Review Refresh and the International Development Strategy including investment in ‘what works’ and filling evidence gaps in priority areas which could include women and girls, humanitarian, and climate and nature.
Programme Value: / £ 13m		Country/ Region or Sector: / Economics and Evaluation
Department/Country Office confirmation of review processes		Confirmed
Contact name		Jonathan Stern
Threshold for final approval of Business Case: / Economics and Evaluation Director/ Chief Economist or deputy
Date of Approval of Concept Note:	30/05/2022	Vicky Ford, Minister of State for Development
Date of Approval of Business Case:	24/05/2023	Name and role of Approver / Nick Lea, Deputy Chief Economist
Programme Code: / 300623	AMP Start Date: June 2023	AMP End Date: March 2030
Overall programme risk rating:	Moderate

## Strategic Case

The Strategic Case presents:
- Strategic Overview
- Mandatory Assurances

Strategic Overview

1. In the context of a limited Official Development Assistance (ODA) budget, FCDO spend needs to be more strategic than ever, supporting policies and interventions with the highest impact and VfM. We also need to learn more about how to influence other countries effectively through our diplomatic work, including meeting the aims of the Integrated Review Refresh (2023).
2. FCDO’s Evaluation Strategy, published in 2022, sets out key aims that 1) strategic evaluation evidence is produced and used in strategy, policy and programming, 2) evaluation evidence is systematic and objective 3) learning from evaluation is shared and used in decision making 4) FCDO has an evaluative culture, the right evaluation expertise and capability. This programme will constitute a key pillar in delivering on all of these aims and in particular 1) and 2), through the production of rigorous evaluations.
3. Impact Evaluation (IE) methodologies like Randomised Controlled Trials (RCTs) and quasi-experimental methods allow us to assess the impact of interventions robustly and their contribution is well recognized. In 2019, the Nobel Prize in Economic Sciences was awarded to Abhijit Banerjee, Esther Duflo, and Michael Kremer for their use of RCTs to achieve global poverty alleviation.
  [note] RCTs and quasi-experiments are not the only way to conduct impact evaluations. However, since this programme will focus on these two methodologies, this Business Case will use “Impact Evaluation” and “RCTs and quasi-experimental methodologies” interchangeably.
  [note] https://www.nobelprize.org/prizes/economic-sciences/2019/press-release/
4. FCDO already conducts impact evaluations. By July 2021, they constituted nearly 20% of active evaluations of FCDO’s programmes, for a total spend of over £45m. However, three issues currently prevent us realising the full potential of Impact Evaluation:
  1. Decisions on which programmes to evaluate and on the approach to evaluation are largely taken by local operational units. While this arrangement tailors the evaluation to the needs of the programme, it is sometimes in tension with the need to direct evaluation investments strategically to where the need-to-know what works is most pressing.
  2. Evaluation budgets remain linked to programme budgets; this precludes the possibility of both conducting evaluative activities outside the programme life cycle (e.g., to assess long-run impact) and conducting rigorous IEs of smaller programmes but with high potential to answer important questions.
  3. Producing relevant and robust IEs requires dedicated technical skills from the design stage and through the lifetime of programmes. Rigorous IEs only take place where programme teams have access from the pre-pipeline stage to the deep technical skills required to design and manage them. This means that IEs might not be taking place where they can generate the most useful knowledge for the organisation but rather where the expertise happens to be.
5. Impact evaluations are currently used in research commissioned by FCDO’s Research and Evidence Directorate. Examples include the Governance, Crime and Conflict Initiative and the IE Connect Programme. These have demonstrated that IE methodologies continue to deliver exceptional value in contributing to the global evidence base, but their focus has not generally been on FCDO programmes. SIEL will differ from these programmes through its exclusive focus on FCDO interventions, and where possible, delivering adaptive tools (e.g., nimble RCTs) to improve the effectiveness of these.
  [note] DevTracker Programme GB-GOV-1-300049 (fcdo.gov.uk)
6. SIEL will:
  1. Generate evidence on what is (or is not) working to inform policy and programme decision-making through robust impact evaluations.
  2. Assess the impact of interventions after programme completion and in the longer term.
  3. Build capacity in FCDO to commission, manage, interpret, and identify opportunities for future rigorous impact evaluation.
7. The ultimate goal is to inform and influence policy decision-making with rigorous, relevant, and timely evidence and to maximise impact of FCDO investments across strategic policy and geographic priorities.
8. We will build on the Evaluation Unit’s experience with the “Fund for Impact Evaluation” programme carried out in partnership with the Development Impact Evaluation (DIME) Department at the World Bank. The programme was successful in both generating a wealth of impact evaluation studies (including but not limited to of FCDO programmes) and improving awareness, demand, and use of evaluation evidence.
  [note] DevTracker Programme GB-1-203872 (fcdo.gov.uk)
9. The Fund for Impact Evaluation programme provides many examples of how to support fast learning in adaptive programming using RCTs to maximise VfM of an intervention. For example, in Senegal the programme used an RCT to test two different campaign delivery strategies to support HIV prevention (community and peer-led sensitisation campaigns) to inform scale-up. The evaluation found that community sensitisation was more effective for women and peer-led sensitisation was more effective for men. Based on this evidence, rather than a one-measure-fits-all approach, the government decided to tailor the delivery of the intervention by gender sub-group, maximising the VfM of their investment.
  [note] https://assets.publishing.service.gov.uk/media/57a08ad4ed915d3cfd00097c/Community-Response-to-HIV-and-AIDS-Evaluation-Research-Highlights-Senegal1.pdf
10. Similar examples have shown the effectiveness of impact evaluations in improving project delivery. Legovini et al. (2015) show that projects incorporating impact evaluations avoid common delays and the gap between planned and actual disbursements is reduced by half. This is because incorporating an impact evaluation in a programme facilitates evidence-based mid-course corrections, strengthens capacity on the ground and increases transparency to third parties about how the programme was delivered.
  [note] Legovini et al. (2015). Impact evaluation helps deliver development projects. World Bank Policy Research Working Paper No. 7157.
11. Within HMG, the Cross-Government Evaluation and Trials Advice Panel (ETAP) constitutes a clear example of how technical expertise can incentivise the use of RCTs to evaluate the impact of government programmes. ETAP has contributed to building a culture of experimentation, tackling complex policy issues, maximising the VfM of evaluation budgets, raising awareness of rigorous methodologies and driving policy-relevant academic research.

Mandatory Assurances
#### Due diligence
FCDO will carry out due diligence assessments on the selected SIEL provider/consortium lead, which in turn will carry out due diligence assessments on all implementing partners in line with FCDO requirements, including maintaining regular and up to date information on delivery chain partners and associated risks. This will be reported to FCDO throughout the implementation to ensure the information is kept up to date and FCDO funds are being followed at every stage of the delivery. The due diligence assessment will include checks to ensure their systems and procedures provide adequate protection against the risk of terrorist financing.

#### Counter Terrorist Financing
Our assessment is that the risk of programme resources being used to fund terrorism is low. When activities involve conducting research in fragile and conflict-affected contexts, the SIEL provider will be required to co-ordinate with FCDO Posts to align with FCDO risk appetite and agree a practical approach to ensuring robust financial management throughout the supply chain.

#### Climate and environment
The impact on climate and environment will be considered by the programme at the operational level of SIEL to ensure appropriate strategies are in place to reduce the climate and environmental impact, which includes carbon footprint and waste management. Projects will consider climate and environmental implications within the research remit.

#### Equality and Diversity
The SIEL team and joint FCDO/SIEL bid assessment panels will be gender balanced. In addition, SIEL will drive inclusion through high quality evidence and data disaggregation. SIEL will also incentivise opportunities for equitable partnerships at local level, where research takes place whilst ensuring beneficiaries and most marginalised groups are engaged through every step of the research process, using appropriate methods and technologies.

#### Safeguarding
SIEL will adhere to the principle of ‘do no harm’, ensuring that all evaluations commissioned and funded meet the highest level of ethical standards and necessary approvals to ensure the highest level of safeguarding best practice is required throughout the delivery chain.
[note] FCDO worked with other funders and UKCDR to develop a set of principles and best practice guidance on safeguarding to anticipate, mitigate and address potential and actual harms in the funding, design, delivery and dissemination of research. Available at: https://www.ukcdr.org.uk/resource/guidance-on-safeguarding-in-international-development-research/

#### Compliance
The agreement between the SIEL provider and FCDO will include clear direction and means of reviewing compliance with mandatory assurances:

  1. Gender equality, International Development Act (Gender Equality) 2014
  2. Counter Terrorist Financing
  3. Public Sector Equality Duty, Equality Act 2010
  4. Climate and Environment
  5. Partnership Principles

## Appraisal Case

The Appraisal case comprises:
- What will SIEL do?
- Delivery Options
- Choosing the Best Value for Money Option for SIEL
- Appraisal of the Options using Multi-Criteria Analysis
- Theory of Change
- SIEL Procurement Route
- Value for Money of the Chosen Option

WHAT WILL SIEL DO?

SIEL will address the issues identified in the strategic case to achieve an Impact Evaluation portfolio which provides greater value for money for FCDO through three key outputs:

#### Strategic and rigorous Impact Evaluations (IEs)
1. SIEL will contribute to the evidence base in under-evaluated areas through impact evaluation studies. It will answer critical evaluation questions which speak to FCDO objectives, filling internationally recognized gaps in the evidence base.
2. SIEL will de-link evaluation budget from programme budget which will enable impact evaluations for smaller programmes without compromising the resources available to those programmes. Furthermore, through SIEL, FCDO will be able to spend evaluation resources outside the lifecycle of the programme: before a programme starts (for example to test alternative delivery strategies before scaling-up) and after a programme is finished (for example to assess-long term impact of an intervention).
3. SIEL will trial innovative methods where appropriate. For example, the experience of the Centre of Excellence for Development Impact and Learning (CEDIL) programme suggests that structural models and machine learning, as well as qualitative methods, can combine well with experimental methodologies to build understanding of how and why an intervention works or does not work.
  [note] Masset E, Rathinam F, Nath M, Vigneri M, Wood B 2019 Successful Impact Evaluations: Lessons from DFID and 3ie. CEDIL Inception Paper No 6: London
4. SIEL will support rigorous and evidence-based adaptive programme support. This could include ex-ante data collection for diagnostic purposes, lab-in-the-field experiments for proof of concept ahead of the programme initiation, and nimble adaptive trials testing the best delivery options before scaling-up. This will improve the effectiveness and efficiency of programmes collaborating with SIEL.

#### Follow-up evaluative activities to assess programmes’ impact and sustainability in the long-run.
1. SIEL will make it possible to carry out follow-up studies in areas of strategic priority for the organisation. These may be desirable where:
  1. Programmes have been impact-evaluated at closure, but there is lack of evidence around the persistence of the effect; or,
  2. Programmes are expected to produce long-run impacts which are not fully realised at closure (for example, education programmes targeting primary school children and aiming to improve their future labour-market outcome(s)).
  3. Follow up evaluations have the potential to fill evidence gaps in FCDO priority areas.
2. It is customary for IEs to measure impact on short-term outcomes as a proxy for longer-term changes based on a theory of change. SIEL will generate robust evidence of the long run impact of programmes by using data from already closed programmes, applying impact evaluation techniques.
3. We anticipate criteria for selection of these studies to include quality of the original IE design, likelihood of success in recontacting intervention beneficiaries and respondents, alignment with FCDO strategic priorities, ability to address evidence gaps as well as to influence future programmes and policies.
4. Where possible we will seek interested partners to co-finance these follow up studies to leverage our funding and increase the potential take-up of their findings.

#### Capacity Building, Engagement and Dissemination
1. SIEL will build capacity in FCDO through a dedicated technical support component for FCDO staff. This could include:
  1. Engagement with FCDO’s advisory cadres (with a focus on evaluation) to build the technical skills to advise on, commission, interrogate and manage future impact evaluation studies.
  2. Workshops and engagement with policy advisors and other cadres designing programmes to build their understanding of what impact evaluation can offer, how and when to consider it and seek support to design it into a programme. This should include Senior Civil Servants to strengthen cultural commitment to IE within FCDO.
2. SIEL’s ultimate aim is to influence programme and policy design both within and outside FCDO, including at the global level. Following the model of the Centre of Excellence for Development Impact and Learning (CEDIL), SIEL will have a research uptake and communication workstream, and the implementing partner will be required to allocate staff resources to this, including a research uptake lead.
  [note] Centre of Excellence for Development Impact and Learning CEDIL (cedilprogramme.org)
3. Like CEDIL, SIEL will require the implementing partner to produce a stakeholder engagement and evidence use plan (or to include this within a broader Evidence and Learning plan), including communication products and activities as key deliverables (see Annex 2- indicative logframe). CEDIL’s 2022 Annual Review indicates the programme achieved a high degree of engagement through attendance at online seminars and through social media using such an approach.
4. SIEL will involve ongoing engagement with decision makers to build strong ownership and understanding of its findings, as was the case with the Fund for Impact Evaluation Programme. This should include Senior Civil Servants.

#### How will this be achieved?
1. The inputs required to achieve these outputs are funding, technical and policy skills and a governance structure in FCDO centred on the Evaluation Unit.
2. The funding to deliver the SIEL programme is £13m over seven years. Since impact evaluations are an R&D activity, this will principally be capital budget, from Official Development Assistance, but non-ODA budget will be included for evaluation of influencing or other activities that do not classify as ODA eligible spend. For further details see the Financial Case.
3. SIEL will provide access to evaluation specialists with deep expertise not only in IE methodologies but also in the thematic areas where SIEL will operate. Deployed to support programme teams that are considered an appropriate match, the IE experts will work on developing evidence for an intervention from design to closure. Their role will be to:
  1. Support FCDO in identifying evidence gaps and questions for SIEL to target.
  2. Engage with FCDO programme teams, policy makers and advisors to build understanding of and demand for impact evaluation, leading to a pipeline of expressions of interest to be developed into full impact evaluations.
  3. Develop an Evidence and Learning plan for interventions and wider uptake of that evidence- this sets out what evidence will be developed to improve VFM as the programme is rolled out and also to assess the final impact of the intervention;
  4. Co-design impact evaluation studies and related data collection and management together with FCDO teams and implementing partners. This could include supporting theory of change development;
  5. Draw from a network of thematic and evaluation experts (academics, data scientists, etc) including those from the relevant country(ies).
  6. Ensure ethical approval is obtained and that inclusive data protocols and strategies that ensure safety and security of respondents and enumerators are developed;
  7. Procure data collection services where needed;
  8. Conduct data analysis and write evaluation reports and briefs;
  9. Engage with FCDO programme teams and programme implementing partners to ensure IE findings are understood and implemented where appropriate;
  10. Contribute to wider dissemination of IE findings and policy implication beyond FCDO.
  11. Build capacity in FCDO to understand, commission and deploy impact evaluation studies.
4. Evaluation Unit will manage the SIEL programme, and in collaboration with partners in Research and Evidence Directorate (RED) and relevant experts, will decide what to evaluate and how. For further details see the Management Case.
5. Evaluations will be chosen following a three-step process. Firstly, the Evaluation Unit together with the Implementing Partner will identify evidence gaps and high-level evaluation questions related to strategic priorities for the department through expert consultations and workshops. Secondly, outreach and awareness raising with programme and policy teams will follow, which may inform changes to the questions and evidence gaps. Thirdly, expressions of interest will be invited from policy and programme teams at Concept Note stage (or equivalent) in multiple rounds. The SIEL Steering Committee will then choose which evaluations to finance based on their strategic relevance, potential to fill an evidence gap, relevance to upcoming policy decision-making, feasibility, and additionality. The goal of the SIEL Steering Committee and this process is to maximise the Value for Money of knowledge generated through the programme. For further details see paragraphs 47-51, and a worked example in Box 1.

#### What’s Different About this Programme?
1. Impact evaluations are currently used in research commissioned by FCDO’s Research and Evidence Directorate. Examples include the Governance, Crime and Conflict Initiative and the IE Connect Programme. These have demonstrated that IE methodologies deliver exceptional value in contributing to the global evidence base, but their focus has not generally been on FCDO programmes. SIEL will differ from these programmes through its exclusive focus on FCDO interventions, and the co-creation of questions for evaluation with FCDO programmes under design. It will also lay new ground in delivering adaptive tools (e.g. nimble RCTs) to improve the effectiveness of programmes.
2. SIEL IEs will differ from impact evaluations of FCDO programmes currently commissioned in-country using programme budgets by selecting evaluation questions based on an assessment of global evidence gaps which are strategically relevant to the department as well as using adaptive learning. SIEL will be able to evaluate smaller and more innovative programmes with robust methodologies.
3. Little impact evaluation work has entered the diplomatic and influencing field. SIEL will seek to apply robust methodologies here through its non-ODA budget.

SIEL DELIVERY OPTIONS

To address the challenges identified in the Strategic Case, the appraisal case assesses three options:
Table 1: SIEL Options
Option	Description
Option 1: Business as usual	Impact Evaluations will continue to be commissioned by programme teams if there is appetite, budget, and access to technical expertise to do so. Follow-up evaluations will rarely, if ever, be carried out. EVU staffing resource could be used to advocate for and support impact evaluations to a limited degree.
Option 2 – Partnership with an organisation with recognised impact evaluation leadership expertise.	Impact evaluations and capacity building will be commissioned and delivered through a partnership with a leading supplier or consortium. The implementing partner will be expected to have capacity to directly deliver impact evaluations through their own resources but could also form a consortium and/or contract out some of the work.
Option 3 – Delivery through a Fund manager	SIEL implementing partner commissions the evaluations individually according to FCDO’s requirements. The partner still needs to have expertise in impact evaluation but their rigour and credibility as an impact evaluator is not as critical as under Option 2.

#### Option 1: Business as usual (BAU) option:
1. Under this option, some IEs will continue to be commissioned by programmes themselves in a decentralised manner but there will be fewer than in past years due to the constrained fiscal environment for ODA programming. Programme teams will decide if they want to conduct an IE and, if they have enough technical and financial resources, will design and procure one under the supervision of an M&E adviser. However, there is a high degree of risk that these evaluations will not match up with evidence gaps at the departmental- strategic level and could represent poor VFM. Impact evaluations of predominantly non-FCDO programmes will also continue to be commissioned by RED.
2. Under the BAU option, evaluation budgets continue to be linked to programme budgets. It remains challenging to commission evaluative activities outside of the programme lifecycle, making follow-up evaluations to assess long-term impact a viable option only for teams with enough resources and appetite to keep the programme open even if the intervention is finished. In practice there are no known examples of this occurring in FCDO, so it is very unlikely that follow-up studies will take place under this option.
3. Given that Option 1 leaves the needs identified in the Strategic Case unfulfilled, Option 1 is ruled out at this stage and not further appraised.
#### Options 2 and 3: SIEL Programme delivers impact evaluations, follow up studies and capacity building.
1. Figure 1 summarises the process under both Option 2 and Option 3. Under Option 2 SIEL will be implemented through a partner who will centralise delivery of the programme while under Option 3 many/ most of the evaluations will be contracted out by a fund manager.
2. Steps i)-iii) below are the same under Options 2 and 3, but after that the processes differ in how the research will be taken forward.

Figure 1: SIEL operational model, Options 2 and 3.
Engagement and influencing

  1. Identifying Evidence Gaps relevant to Strategic Priority Areas
1. As a first step, Evaluation Unit, facilitated by the Implementing Partner and in consultation with relevant stakeholders, identifies a set of thematic areas from FCDO’s strategic priorities where evidence gaps could be filled through investment in impact evaluation. Strategic priorities are identified in FCDO’s International Development Strategy (2022), Integrated Review Refresh (2023), and Country Diagnostics exercises. Evidence Gap Maps and systematic reviews from 3IE and others could also inform this process, in addition to FCDO’s Best Buys.
  [note] UK government's strategy for international development - GOV.UK (www.gov.uk)
  [note] Integrated Review Refresh 2023: Responding to a more contested and volatile world - GOV.UK (www.gov.uk)
2. The implementing partner will then facilitate workshops on a discrete number of thematic areas to produce a refined set of evidence gaps and evaluation questions. These workshops will draw on academic knowledge, the Best Buys and other Evidence Gap Maps in conjunction with a practical perspective from policy makers about what is needed to improve the quality of programming and activities in FCDO. The implementing partner may also contribute evidence synthesis and expertise to the evidence gap identification process.

  1. Outreach to policy/programme teams.
1. Once evidence gaps and high-level questions have been identified, the implementing partner together with EVU will carry out outreach to programme teams to engage them in SIEL, using the network of Heads of Profession (HOPs) in FCDO to identify possible programmes to target, as well as engagement with Heads of Mission and Development Directors.
2. The implementing partner will conduct seminars with programmes at design (Concept Note approval) stage. These seminars will raise awareness of the evidence gaps and questions identified in stage i) and potentially garner feedback for some further refinement of the questions. Principally, they will build demand from policy/programme teams, highlighting the opportunity to learn ‘what works’ and to make a programme distinctive and lead to better future programming. They will also ensure teams are aware of the timing and requirements of impact evaluation, including building in the study at the outset and carrying out randomisation of the intervention and/or data collection. This involves the programme team ceding some control of the intervention to the research team, and spending considerable time engaging with them in return for robust evidence which will inform better VFM.

  1. Call for Expressions of Interest
1. After seminars and outreach, EVU together with the implementing partner will launch a call for Expressions of Interest (EOIs) for each thematic area inviting programme teams to submit a short 5-6 page proposal for their programme. The high-level evidence gaps and questions identified in i) will be clearly set out in the Call for EOIs. Bids should indicate the proposed evaluation topic and question(s) including a high-level indication of methodology, how the IE will fill an identified evidence gap and/or question; and how results will be used by the programme team (and more broadly) to inform programme and policy decisions, including key deadlines or policy decision points.
2. Projects will then be selected by a team of reviewers from Economics and Evaluation Directorate, Research and Evidence Directorate and the implementing partner, potentially with an expert from the Evaluation Quality Assurance Service (EQUALS) service. Criteria are likely to include (but not be limited to) strategic relevance, meaningful contribution to the evidence base, relevance to upcoming policy decision making, feasibility and an assessment of additionality, meaning the evaluation would be unlikely to go ahead in the absence of SIEL due to the size, novelty, topic, or other unique feature(s) of the programme. Box 1 gives a hypothetical example of how a programme and question might be chosen.
  [note] The EQUALS service provides independent QA and advice to FCDO evaluations on an ongoing basis.

Box 1: Illustrative example of evaluation question development / FCDO’s International Development Strategy (2022) and Integrated Review Refresh (2023) identifiy climate change as a major priority. FCDO’s internal synthesis product, the Best Buy for Climate Change (2019) identifies a number of areas with mixed or low evidence in the area of Climate change adaptation, including climate smart agriculture, irrigation and community based adaptation. / Firstly EVU in collaboration with RED and other stakeholders, supported by the implementing partner would hold a workshop to consider areas of focus for the SIEL programme. It is possible climate change could emerge as one of a number of thematic priorities for SIEL. A second workshop could then focus on climate change mitigation and adaptation. In this workshop FCDO experts, policy makers and relevant external actors could consider the Climate Best Buy and complementary products including evidence gap maps and synthesis products and select where they think the greatest evidence gaps lie. Hypothetically, they could decide that these are in climate smart agriculture and community based adaptation but that recent/ other studies have filled the gap on irrigation. They would produce a set of high level evaluation questions, e.g: / Which climate smart agriculture interventions are effective and why? / What approaches to promoting them are most cost effective? / Are there combinations of climate-smart practices which are more cost effective than the sum of their parts when combined? / In stage ii) policy/ programme teams designing climate adaptation interventions would be called to a seminar, using the HoP networks, SCS and EVU’s networks across the department. Those with climate smart agriculture and community based adaptaiton interventions would be particularly targeted (amongst other identified gaps from stage i). The meeting would then involve a conversation between practitioners and impact evaluation/ evidence experts which would build understanding of impact evaluation and demand from programme teams to participate in SIEL. / Following this seminar, EVU could put out a call for Expressions of Interest, inviting those teams that attended to submit a bid. The programme teams would then propose their own evaluation questions, which would need to have some alignment with stage i) identified questions to be selected but might also further develop the questions, considering the particularities of their programme and the evidence needs of their area. The list could include (hypothetically): / Is no-till agriculture cost effective in the Horn of Africa? / Which is more effective for reaching farmers with information about improved practices- SMS, radio or field schools? / Is it more cost effective to combine promotion of no-till farming with intercropping and mulching or are the approaches as cost effective on their own? / The selection panel for SIEL would then meet, and select EOIs and evaluation questions to take forward in that round. These would be further developed when research teams are formed around each selected impact evaluation, resulting in a final set of evaluation questions.

1. Should an intervention be selected for a SIEL impact evaluation, EVU will agree clear roles and responsibilities with the programme team setting out expectations for the duration of the programme and the evaluation, which would be signed off by a Senior Civil Servant. In the case of programmes, EVU will require the team to include a summary of the evaluation plan(s) worked out at design stage in the final Business case for the programme. For further details of this process, see the following section under ‘Option 2’.
2. Depending on the response to the first bidding round, additional bidding rounds could respond to priorities as they arise. However due to the need for impact evaluations to run over the lifetime of a programme to evaluate its full impact, evaluations starting after year 3 of the programme would likely need to focus on short-term/ nimble RCT studies and/or follow up studies.
3. The diagram in REF _Ref133941919 \h Figure 2 illustrates the SIEL operational model under Options 2 and 3.
Figure 2: SIEL operating model for delivering Impact Evaluations under Options 2 & 3

Evaluation design
Baseline data collection (if needed)
Endline data collection
Analysis reporting dissemination
Before intervention delivery:
- Engagement with policy/ programme teams to build interest, Expressions of Interest and Selection of studies to take forward by Steering Committee.
- Collaboration with programme in developing Theory of Change
- Evidence and Learning Plan to include:
- Research questions and methodology
- Data strategy, tools and protocols.
- Pre-analysis plan, to be registered in advance.
- Ethical approvals
- Stakeholder engagement and Evidence Use plan.

During intervention delivery:
- Real-time monitoring, when suitable using innovative sources of data (geo-spatial, social media, etc.);
- Nimble & adaptive RCTs to test delivery options;
- Policy and wider stakeholder engagement and feedback;
- Mid-line data collection and evaluation (if appropriate).

After intervention delivery:
- Data analysis;
- Evaluation report, Working Paper and policy briefs produced and QA’d;
- Publication in peer-reviewed journal where appropriate
- Results discussion and dissemination;
- Data anonymised and made public.

Evidence-based policy engagement and influencing activities through the lifetime of an IE study.

#### Option 2: SIEL Implementing Partner Centralises the delivery of Impact Evaluations, with the option to deliver through others
1. Under this model the Implementing Partner is expected to possess substantial in-house impact evaluation expertise that covers FCDO’s priorities, in addition to capacity building and research dissemination, such that they could conduct the major elements of the programme themselves. However external collaboration is expected and required as detailed below, and the Implementing Partner could also form a consortium with other organisations to achieve the required coverage to deliver on FCDO’s priorities.
2. Once programmes that constitute a suitable match for SIEL are identified by steps i-iii) above, research teams to conduct each study are formed by the Implementing Partner. These teams will each have a lead researcher from the implementing partner’s pool of experts which could include academics, researchers, and experts in the field. The implementing partner will be expected to leverage their network to bring on board relevant complementary expertise to conduct the study. Qualitative work and other methods e.g. structural models, machine learning could have an important role in shedding light on how and why the intervention worked. It is important that the relevant expertise is brought on board at design stage to shape the IE.
3. Following a co-production model, the implementing partner’s research team will work together with programme teams to develop their theory of change and an Evidence and Learning Plan which will include at its core the IE design and data strategy. This document will also set out the way ahead for the study implementation and for stakeholder engagement.
4. Data collection usually constitutes the key cost driver of an IE study. When suitable, use of innovative sources of data that do not require face-to-face data collection will be explored and tested (for example geo-satellite, web-scraped or social media data). If data collection is needed, the implementing partner will procure and manage this. The partner(s) will be responsible for data protocols, safety and security and to make sure they conform with FCDO guidance and policies. They will also be responsible for ensuring each IE study receives ethical approval and that research protocols and design are adhered to.
5. We envisage an active collaboration between the research team, the programme team and implementing partner(s) during intervention delivery. By offering continuity of research delivery organisation, Option 2 is particularly strong in this regard.
6. We want to promote an Impact Evaluation model that goes beyond measuring impact at the end of an intervention, by providing an embedded learning function, generating the right evidence at the right time to inform delivery. Therefore, the Evidence and Learning Plan will also allow for generation of evidence to inform programme adaptation and decision making. This approach is informed by DIME’s ‘Trial and Adopt’ agenda, which Legovini et al (2015) show contributes to improved delivery efficiency. We expect the SIEL implementing partner to be adaptive themselves, seizing opportunities for evidence generating activities (e.g., nimble RCTs, experimental games) that could help optimise the delivery of the programme as they arise.
7. Engagement and policy and programme influencing activities need to happen on an ongoing basis. This is to make sure that SIEL evidence feeds into decision making through the lifecycle of programmes and to ensure that IE studies are seen by programme teams and implementing partners as an integral part of delivery.
8. The implementing partner must provide dedicated resources for ensuring engagement with key stakeholders around each IE, liaising between FCDO Evaluation Unit, Programme teams and implementing partners, SIEL research teams and any other stakeholders we would like to influence through IE studies. A robust stakeholder engagement and communication plan should be developed as part of the Evidence and Learning Plan.

#### Option 3 – SIEL Implementing partner commissions IE studies to FCDO’s requirements.
1. The main difference which makes Option 3 different from Option 2 is once the successful EOIs for evaluations have been chosen by FCDO, the implementing partner will source suppliers for them from their network and potentially the wider market, aiming to marry the best thematic, methodological, and geographic expertise with the chosen IE study.
2. Funds will then be disbursed by the SIEL implementing partner to the research institution(s) that they contract to implement the chosen FCDO evaluations. After this point, the process follows the same trajectory as Option 2, except that the technical expertise and programme engagement is largely provided by the research institution delivering the specific impact evaluation study rather than by the SIEL implementing partner. The latter will continue to play a Fund management and coordination role and will also be expected to contribute their expertise to being an ’intelligent customer’ for the work of the evaluation supplier, working with FCDO to maximise the VFM of the work.
3. Policy and stakeholder engagement under Option 3 may need dedicated resources from both the implementing partner and contracted research team, depending on their relevant expertise.
4. Depending on the technical expertise of the implementing partner, capacity building activities may be delivered by them directly or contracted out in addition, potentially as add-ons to the individual research contracts for impact evaluation studies.

#### Follow Up Studies: Common to Options 2 & 3
REF _Ref134114172 \h Figure 3 shows the envisaged operating model for SIEL to identify and conduct follow-up evaluations for already concluded programmes. Suitable IE studies could be identified through a mixture of a bidding window made available to advisors in FCDO and/or the use of Management Information (MI) data to identify IE studies that have recently concluded or about to be concluded (at the earliest, endline data collection should be happening), leading to a direct approach from EVU to the relevant advisor(s).

Figure 3: SIEL operational model for follow-up evaluations.

1. For follow-up studies the design, data strategy and identification of respondents (which cannot be shared with other organisations for security reasons) is usually held by the institution that conducted the original IE. Therefore, the best VfM option is to invite the research teams who conducted the IE in the first place to also conduct the follow-up study.
2. EVU together with the implementing partner will engage Programme and country teams to build policy demand for follow-up studies.
3. Proposals will be reviewed by a panel composed by Economics and Evaluation Directorate, Research and Evidence Directorate and SIEL implementing partner and selected based on pre-agreed criteria that will be defined in collaboration with the implementing partner. We anticipate criteria to include quality of the original IE design, likelihood of success in recontacting intervention beneficiaries and respondents, alignment with FCDO strategic priorities, ability to address evidence gaps as well as to influence future programmes and policies.
4. Once follow-up evaluations are identified, research teams leading the studies are responsible for making sure that ethical approvals are updated, data protocols and strategies are revived and data collection services are procured to conduct the follow-up studies. Research teams will also be responsible for making sure the follow-up evaluation reports are drafted and finalised incorporating FCDO comments, policy briefs are produced and results are disseminated. Since the programmes that delivered the intervention are likely closed, Evaluation Unit will make sure evaluation reports are Quality Assured, internally communicated, and made public.

CHOOSING THE BEST VALUE FOR MONEY DELIVERY OPTION FOR SIEL

1. In this section we select the delivery option to ensure the best VfM. We compare Options 2 and 3 based on the following criteria:
  1. Potential to deliver an adaptive, programme responsive learning agenda;
  2. Ability to develop FCDO capabilities for designing, procuring and managing IE studies;
  3. Delivery Cost Drivers
  4. Performance Management
  5. Speed of getting IE research teams in place;
  6. Implications on internal resources and staff time.
  7. Thematic and geographic expertise
  8. Ability to deliver follow-up studies
2. The conclusion is that Option 2, a close partnership with an implementing organisation, is the best option provided that a suitable partner or consortium can be found, because it has greater potential for adaptive learning, high quality capacity building, and getting impact evaluations running rapidly with low overhead costs.

#### Potential to deliver an adaptive, programme responsive learning agenda;
In principle, adaptive learning can take place through either Option 2 or Option 3. However, if the SIEL implementing partner plays a central role in most of the evaluations (either delivering themselves or through a consortium partner), there is a greater opportunity to develop a unique approach for SIEL whereby both FCDO and the implementing partner learn together about delivering responsive evidence to enable programmes to adapt iteratively to improve VFM. Under Option 3 with a range of different research providers working on different studies, it is likely that learning would be going on in parallel, with disparate approaches in place. At times the implementing partner with the best subject/geographic expertise for a given study may not be the most well-placed to deliver adaptive learning. A Fund manager approach as per Option 3 also creates more challenges in capturing and synthesising lessons. However, there would be the opportunity for different organisations to try different approaches, and for the SIEL core implementing partner to draw out lessons from each of the different approaches and try to ensure learning is shared across programmes and research teams.
#### Assessing potential to build FCDO capabilities.
1. Under both options, the implementing partner and/or contracted research teams will deliver capacity building sessions for programme teams and hands-on sessions collaborating with experts refining and developing the ToC and the evidence plan for the programme.
2. However, under Option 2 the SIEL implementing partner will build up a body of experience through delivering the SIEL impact evaluations, which could then be drawn on for capacity building activities for FCDO. The same will occur to a lesser extent through option 3, as although the implementing partner will learn from working with the contracted-out evaluation teams, it will not be to the same extent as if they carry out the work themselves.
3. Under Option 3 it is possible that a wider range of expertise for capacity building could be sourced through contracting out. However bringing this together to a coherent whole would depend on the skills of the implementing partner.
#### Cost Drivers
1. Although FCDO would invest the same sum in either Option 2 or Option 3, overhead and data collection costs could differ between options, leaving more funds for carrying out IE studies and capacity building.
2. With two or more tiers of suppliers, overheads are likely to be higher under Option 3. FCDO would disburse funds to a main implementing partner that would manage the thematic windows and disburse research grants to relevant institutions that will conduct the research; the latter in turn may procure data collection from an additional tier of suppliers. This means that under Option 3 we would have at the very least two tiers of suppliers implementing SIEL each with its own overhead costs.
3. In Option 2 we would only have two tiers of suppliers much of the time: the SIEL main implementing partner and the data collection providers on the ground which (where needed) would constitute the second tier. However, under Option 2, there may be instances where the main supplier would contract out some evaluations where they lack thematic or geographic expertise. Figure 4 visualises the different structures of partners’ and suppliers’ tiers under the two envisaged delivery options.

Figure 4: SIEL tiers of suppliers under Options 2 and 3 (simplified)

1. By centralising common survey tools, data collection and management protocols and storage functions under the main SIEL supplier, Option 2 could reduce the need for each data collection provider on the ground to develop or provide their own (as it would be under Option 3) but rather to suggest adaptations for the specific operating contexts. Therefore, we predict Option 2 to generate some cost efficiencies related to data collection and management.
2. Option 3 could drive cost efficiencies if the process for allocating studies between suppliers is competitive, leading to a reduction in fee rates. However the greater the extent of formal competition introduced, the more this is likely to add to the time it takes to allocate a supplier to meet an identified IE need, potentially jeopardising hitting the narrow window between Concept Note stage and inception, when the bulk of the work designing-in an IE needs to take place (see 5 below).
#### Performance management
Managing and measuring performance would be easier under Option 2. Under Option 3 information about the delivery status and monitoring of progress would need to be collected from the various research teams implementing the IEs. FCDO would get second hand aggregation of information done by the main implementing partner. This requires more effort to put together the reporting and the information will inevitably be less consistent because reported by different organisations. On the other hand, with IEs delivered by different partners there will be the opportunity to compare performance across suppliers under Option 3, creating some internal competition within the programme and an additional incentive for strong delivery. Overall, the two options may be similar for FCDO in terms of the quality of performance management which would be delivered.
#### Timing
1. There is a limited time window between identifying a suitable project to be evaluated at around Concept Note Stage and the implementation of that programme starting on the ground, and the SIEL impact evaluations need to be designed-in during that window. Delivering the programme through an organisation that can carry out a large part of the evaluations internally offers clear advantages in ensuring that evaluations can be designed in the required time, as contracting out will take time. The degree of difference will depend on how efficient the contracting process is - something where the implementing partner draws on partners may be less time consuming than a more formalised and competitive contracting process. In addition, the implementing partner under Option 3 will become increasingly skilled at contracting out evaluations over time, while the centralised partner under Option 2 may find it more difficult to source external implementing partners where their internal expertise is lacking, thus some projects may have extended lead times.
2. We do not anticipate a significant difference between the two options in terms of how quickly the implementing partner can be procured and carry out the inception phase.
#### Burden on internal resources
1. Both options require a significant but manageable amount of EvU resources: Resource implications for EvU under either option would be around 0.8 Full Time Equivalent (FTE) Programme Responsible Owner and 0.5 FTE Programme Manager, with 0.1 FTE oversight from a Senior Responsible Owner (SRO). The role of the PRO and PM is to ensure that programme delivery is in line with FCDO Programme Operating Framework rules, sound financial management, and to capitalise opportunities to disseminate evidence from IEs across FCDO.
2. In addition to Evaluation Unit resources, time from programme teams receiving SIEL support could include up to 0.2 FTE of a PRO in interacting with the SIEL team and managing risks.
3. Table 2 summarises SIEL delivery options’ burden on FCDO staff:
Table 2: Internal resources demand under each delivery option (expressed in FTE).
	Option 2	Option 3
SRO (G6 EVU Team Lead)	0.1	0.1
PRO (G7 Evaluation Adviser)	0.8	0.8
Programme Manager (HEO)	0.5	0.5
Programme team PRO	0.2	0.2
Total	1.6	1.6

Assuming either option would be delivered through the same procurement route, we do not foresee significant differences in Programme Management time needed to manage SIEL between Option 2 and 3. Option 3 could be a little higher due to the need to capture the lessons from different evaluations using different approaches.

#### Thematic and geographic expertise
Contracting out the evaluations as per option 3 is likely to give SIEL the broadest reach in terms of expertise in possible topics, geographies and types of intervention. However, Option 2 includes the option for the implementing partner to form a consortium which could improve their breadth of expertise. Furthermore, even under option 2, the partner could choose to contract out some of the evaluations.

#### Follow-up Studies
As set out in the previous section, we think that the least cost and most feasible way to deliver follow-up studies will be to return to the original evaluator and invite them to carry out the follow up study (figure 3). If this is not workable, then the evaluation could either be carried out by a central implementing partner as per Option 2 or contracted out to a third party as per Option 3. An option 3 setup, where the implementing partner is accustomed to contracting third parties and delivering through them may work most seamlessly in the case where the original evaluator is carrying out the follow up studies. However, a flexible provider under Option 2 could also deliver if they are willing and able to work with other organisations.

APPRAISAL OF THE OPTIONS USING MULTI CRITERIA ANALYSIS

1. Neither benefits nor costs for the two options can be valued, therefore to rank appraisal options, advantages and constrains of each option have been channelled into a simplified version of Multi Criteria Analysis (MCA). Weights are assigned to criteria, and then options are scored in terms of how well they perform against those weighted criteria. The weighted scores are then summed to compare options.
2. We used a scale of 1 - 5 (where 1 is ‘poor’ and 5 is ‘strong’) to score and compare benefits of the feasible options. Table 3 summarises the results of the MCA

Table 3: Multi-Criteria Analysis to assess appraisal options for SIEL. Scores out of 5.
	Criteria	Weight	Option 2	Option 3
1	Potential to deliver an adaptive, programme responsive learning agenda	0.15	4	2
2	Ability to develop FCDO capabilities for designing, procuring, and managing IE studies;	0.15	5	3
3	Cost Drivers	0.1	4	3
4	Performance Management	0.1	3	3
5	Speed of getting IE research teams in place	0.1	4	3
6	Internal resources and staff time	0.1	3	3
7	Thematic and geographic expertise	0.15	2	4
8	Follow-Up Studies	0.15	2	4
	Total/ Weighted Averages	1	3.35	3.15

1. Based on the considerations in this Options appraisal and on the MCA, Option 2 would constitute better VfM for FCDO to deliver SIEL.
2. Given that Option 3 scores higher for follow up studies, the possibility arises that follow up studies could be split out from the remainder of SIEL, contracting them through a fund manager as per Option 3 and an Option 2 style arrangement used to deliver the remainder of the programme. However, given than Option 2 includes some third-party collaboration and contacting-out capability, we consider that the efficiency gains from delivering follow ups in this way are outweighed by the extra cost and complexity of splitting SIEL into two components which must be separately procured.

THEORY OF CHANGE (ToC)
1. The programme’s ToC aims to address the following key issues:
  1. IEs are not systematically happening in areas of strategic priority for the organisation and/or where the evidence gap is larger;
  2. To conduct an impact evaluation, dedicated technical expertise is needed from pre-pipeline stage; not all teams have this expertise available, and
  3. Evaluation budget is linked to programme budget, meaning that rigorous impact evaluations are only happening in programmes with a more generous budget. But this is not necessarily where interesting evaluation questions are.
2. To overcome these issues, the SIEL programme will provide dedicated expertise and funds.
3. Once strategically relevant programmes for collaboration with SIEL have been identified, technical support will be flexibly deployed to help develop the Theory of Change (ToC) for the programme or activity and identify key assumptions and supporting evidence. This will create a better, shared understanding of what the programme aims to achieve and identify key gaps where there is little and/or anecdotal evidence supporting assumptions.
4. An impact evaluation provides evidence of whether the theory underlying the intervention(s) was right and holds true in the operating context of the intervention. I.e., an IE will tell if the programme worked and “how much” it worked. It can also enable estimation of cost-effectiveness of activities.
5. To maximise VfM of programmes and to ensure validity of IE results, SIEL will promote an adaptive approach to programme management and IEs: the programme will evaluate the overall impact of the intervention but before that it will also make sure the intervention is made as effective as possible through adaptive learning.
6. To achieve this, technical experts will support programme teams to develop not only the overall IE design for the programme (or one or more of its components) but also an evidence and learning plan to generate evidence needed at the beginning and along the lifetime of the programme to enable evidence-based, adaptive decision making able to maximise VfM of the intervention along its life-cycle.
7. Publishing IE results and pro-active communication and dissemination of findings will give the opportunity to influence programmes and policies operating in strategic areas of FCDO interest on a global scale. This will not only magnify the impact of IE investments, but it will also develop UK’s reputation as a science power and an evidence-committed force for good in the world.
8. The Theory of Change described here is summarised by Figure 4 below and an assessment of the assumptions behind it is considered in Table 4.

Figure 5: Theory of Change for SIEL

Table 4: Key assumptions underlying SIEL's Theory of Change, supporting evidence and mitigation and monitoring considerations
Assumption	Evidence and considerations	Mitigation/M&E
Ministers and Leadership must continue to put data and evidence high in the agenda of the organisation for staff to have bandwidth to meaningfully engage. / Decision makers understand and use the evidence generated. / Decision makers understand evidence generated and know how to use it to inform decisions	A policy influencing survey produced by the Fund for Impact Evaluation proves that IE evidence is often used by decision-makers when properly engaged. However, few of the programme’s IEs evaluated FCDO interventions. We have limited evidence that the same results would replicate in FCDO environment. / An FCDO evidence generating programme in Nepal suggests that staff often have the right capability to understand evidence but not enough time to interact with it.	Evidence must be robust but proportionate for teams to absorb and packaged in a format that it is easy to understand and use for decision-makers. / Engagement between the evaluation/research team, FCDO team and implementing partners to make sure that the evaluation results are well received and understood. Role for SIEL steering committee in overseeing this. / SIEL programme to incorporate a capacity building component for FCDO to better understand, absorb and use evaluative evidence for decision making. / Evaluations will have stakeholder engagement and evidence use plans including indicators. The programme will monitor understanding and use of evidence generated on a yearly basis (at minimum) and conduct evaluative activities to understand bottlenecks to evidence use if needed.
SIEL can adapt to shifting FCDO priorities	A challenge faced by many programmes and activities is that they have a lot of traction at the onset but with rapidly shifting priorities and high turn-over of staff they often end up being off-focus after just few years. / This could be an issue both for SIEL itself and for programmes SIEL will collaborate with, as IE studies must last for the entire duration of the programme evaluated (usually 5 years).	A necessary criterion for an evaluation to be selected will be senior (SCS) buy-in and commitment of staff on the programming/ intervention side to manage their side of the evaluation. / SIEL to incorporate some flexibility to respond to changes in strategic direction to keep portfolio of IE studies in line with current priorities. This could be achieved by phasing thematic windows or by choosing thematic areas that are likely to stay high priority in the long-run (considering long term trends and horizon scanning). / A diversified portfolio including long-term IEs, nimble experiments and follow-up evaluation studies must be built to minimise the risk that the IE portfolio will become obsolete after just 1 or 2 years. / All Studies should not be identified on the first year of the programme but rather in a phased way. / Expectations around how much a long-term IE research study can flex and bend to respond to current priorities must be clear at the outset. Some aspects will be flexible but others won’t to preserve the rigour of the study.
IE results are robust, timely, well communicated, and transferable to other contexts.	The Fund for Impact Evaluation experience suggests that when the implementation partner has experience conducting research and has a network on the ground this assumption holds true. / The generalisability of evaluations can be maximised through their design. The CEDIL programme experience suggests that robust sample sizes, standardising outcome metrics and designing-in analysis of why interventions work, as well as contextual factors that affect this, could help the evaluations generate findings that apply in other contexts	Identifying IEs that fill evidence gaps at the strategic level will contribute to usefulness of findings for other contexts. / RCT methods can be complemented with other methods, e.g., structural models and machine learning to builder deeper understanding. / Adopting a Partnership approach with an organisation with robust IE capability provides some reassurance that the output of the studies will be of rigorous quality and timely available for decision making. / Use of the Evaluation Quality Assurance Service offered by Evaluation Unit. / Annual monitoring of the quality of evidence produced (once findings are available)
SIEL can identify enough programmes in pre-pipeline (or follow-up) stage that are a good match to collaborate with	Matching top-down offer with bottom-up demand is likely going to constitute the main operational challenge. / Experience identifying studies for the Fund for Impact Evaluation programme using workshops was successful, and it included some FCDO studies. However, the different context of SIEL and alignment of investment to strategic priorities will limit the number of eligible programmes to partner with.	We will replicate the successful experience of the DIME Fund for Impact Evaluation workshops as a venue where demand and offer of technical support (and funds) for IE can successfully be matched; / SIEL will conduct systematic engagement with programmes we think can present feasible opportunities to collaborate to stimulate demand. / Communication during early stages of the programme will be crucial to ensure the organisation is aware of the opportunities that SIEL will offer. Head of Profession mailing lists will be an important channel to reach advisors in country posts. / We can use the first thematic window as a pilot to test the effectiveness of seminars and EOIs to identify programmes to partner with in a second window.

#### SIEL PROCUREMENT ROUTE

1. The technical skills required to deliver SIEL are extensive and at present those with the track record for carrying out the type of end-to end solution envisaged including robust impact evaluation, follow up studies and integrated capacity building are limited to a very small number of largely academic, multilateral, and non-profit organisations.
2. Some of these organisations cannot enter fully competitive tendering exercises and excluding them from the possibility of delivering SIEL would severely limit VFM. As such we believe SIEL should be procured through an accountable grant and/or MOU.
3. The question is then how to choose among the limited selection of possible providers? We considered a direct award but given that we believe more than one organisation can deliver the model of SIEL set out in this appraisal case the best option will be to carry out a Call for Proposals whereby identified candidates have the opportunity to answer a questionnaire setting out how they would deliver SIEL.
4. Further justification for this procurement route is set out in the Commercial Case.
5. Responses to this Call for Proposals will be considered by a Panel made up of EED and RED officials, who will make a recommendation to the Chief Economist and Chief Scientist for the chosen implementing partner for SIEL.
6. Depending on whether the chosen partner is a multilateral organisation or a not-for-profit or academic organisation, either an MOU or an accountable grant will then be drawn up.
7. We will explore whether it makes sense to deliver the programme through the Research and Evidence Division’s Commissioning Centre at this stage. The decision will hinge on whether the chosen proposal is a good fit with the Commissioning Centre’s operating model and whether it will deliver efficiencies in terms of reduced overheads.

VALUE FOR MONEY OF THE CHOSEN OPTION

#### Economy
The key cost drivers associated with the preferred option are the overheads of the implementing partner, the costs of data collection, and analysis as well as interactions with policy teams, advisors and project beneficiaries (including travel where appropriate). By choosing to centralise as much as possible the delivery with a single partner/ consortium we hope to minimise overheads such that more is available for the delivery of benefits. In our view this outweighs potential savings through a competitive process driven by a fund manager, since that will add to time putting together teams to deliver IE studies which is very limited.

#### Efficiency and (Cost) Effectiveness
1. With UK ODA reducing from 0.7% to 0.5% of Gross National Income (GNI) in 2020, funds available for evaluation have become tighter. Nevertheless, the case for getting the most from the limited funds we have available has never been stronger.
2. SIEL offers the opportunity to do this by generating evidence about the cost effectiveness of our activities. By partnering with an established expert and leader in the Impact Evaluation field, we maximise not only the chance to deliver high quality IEs, but also the benefits in terms of adaptive learning and capacity building for FCDO. Building FCDO staff capability will improve intervention design (efficiency) and focus resources on what works and is cost effective.
3. Delivering SIEL in this way will also enable FCDO to manage the programme more efficiently since it will streamline management information and reporting .
4. SIEL could have long run and global benefits for UK influence and reducing global poverty, since improvements in intervention design as a result of this programme could lead to further improvements in interventions by FCDO and partners into the future, so that over time the programme could pay for itself many times over.
5. Having carried out informal Early Market Engagement (EME) activities and by doing a light touch Call for Proposals, FCDO will ensure that the best option is chosen in the fastest time amongst the limited selection of not for profit, academic and multilateral operators who could deliver SIEL.
6. How VFM will be measured throughout the programme: A full logframe will be developed during the inception phase; example VFM indicators which draw on the successfully implemented Fund for Impact Evaluation and CEDIL programme are included in Annex 2. VFM evidence will also be gathered from:
  1. Reports from the implementing partner
  2. Through regular dialogue with the implementing partner and stakeholders
  3. Through evidence gathered for annual reviews throughout the programme lifecycle.

#### Equity
1. The focus of the programme is to improve the lives of poor people around the world and improve the UK’s influence. The selection of geographies, themes and partners for evaluation will be based on need and data disaggregated by sex, disability, location, income quantile and other relevant characteristics will be collected.
2. Gender equality and social inclusion expertise and objectives will be embedded across all the activities, including the implementing partner for SIEL.

#### Value for Money Summary
1. In the context of increased pressure on FCDO’s ODA budgets and the organisation’s aim to regain ‘development superpower’ status, a renewed focus on impact evaluation across the department has the potential to both maximise the impact of FCDO’s spending and position it as a key player in evidence-based development and influencing.
2. By delivering SIEL through a partner with deep expertise in impact evaluation who can implement capacity building and adaptive management, FCDO will be able to obtain high quality impact evaluations while ensuring overhead costs are minimised.
3. Given very few organisations globally have the above capacity, we have chosen to procure SIEL following our Early Market Engagement with a Call for Proposals exercise, which will lead to an MOU or accountable grant with a leading multilateral, not for profit or academic organisation.

## Commercial Case

The Commercial Case Presents:
- Market Analysis and Design Process
- Funding Mechanism
- Call for Proposals
- Managing Conflicts of Interest
- SIEL Scope
- Capability
- Capacity
- Performance Management
- Commercial Risks

#### Market Analysis and Design Process
An Early Market Engagement (EME) was carried out through discussions with leading players in the impact evaluation research field, over September 2022- April 2023. Programme leads in FCDO and other donor partners who manage impact evaluation programmes were also consulted and engaged in the design process. During these conversations the concept for SIEL was presented to seek feedback which was used to inform this Business Case. Based on these conversations we believe that the focus on innovation and learning envisaged for SIEL is best delivered through a partnership approach where we work with an organisation with deep expertise in this field.

#### Funding Mechanism
1. As per the appraisal case, the recommended route to market is a Call for Proposals leading to an accountable grant or an MOU with a non-profit or research organisation. The following are the key factors justifying why these are the most appropriate instruments to deliver the objectives of this investment.
  1. FCDO is looking to partner with an organisation with world-class impact evaluation, dissemination, and capacity building expertise across a broad thematic spectrum. Currently the organisations known to have capacity to do this are not eligible to enter a competitive tender exercise, so it is likely such an exercise would limit VFM, and possibly result in a failed procurement. An MOU or grant is considered more appropriate for such partnerships.
  2. A commercial organisation would likely need to subcontract a pool of highly-skilled expertise. This would significantly increase overall cost which can be avoided if partnering directly with specialist providers.
  3. As per FCDO’s Programme Operating Framework (PrOF), contracts are only used where FCDO can draw up a detailed programme specification or Terms of Reference (i.e. specify what exactly to be delivered and how). In this case, we have a high-level framework of what we are looking to achieve and look to proven examples (Fund for Impact Evaluation, 3IE Programme), but do not know how this can be done in detail.
    [note] FCDO Programme Operating Framework at https://www.gov.uk/government/publications/fcdo-programme-operating-framework
  4. Developing and piloting SIEL could require frequent changes to adjust to lessons learned. Therefore, the outcomes are less certain and more appropriate for delivery through a grant or MOU rather than a contract.
  5. FCDO will be buying activities (evaluation designs in response to departmental demand, partnership with policy teams, responsive analysis), and it is not possible to set out all the outputs in advance which would be a requirement for a contract.
  6. A Call for Proposals will support the control of key cost drivers relative to a direct award. The key cost drivers are data collection, analysis and engagement with FCDO staff and implementing partners. Costs will be assessed as part of the evaluation of proposals submitted through the bidding process, and the competitive nature of this process incentivises bidders to minimise costs. FCDO will benchmark fee rates to ensure competitive rates.
  7. A Call for Proposals would also allow the programme to begin sooner, relative to a Commercial competition. The procurement process is expected to take approximately two months (including the 3-4 week window for proposals), compared to between 12-24 months via a commercial route.
  8. An accountable grant or MOU with a non-commercial organisation will offer better strategic fit, unlock innovation, and drive better VfM over a long period of time whilst allowing FCDO to exercise robust control and accountability, by incorporating bespoke clauses.
#### Call for Proposals
1. Since we believe that more than one organisation has the capacity to deliver SIEL, we think VFM will be maximised through a Call for Proposals process where brief written bids are invited.
2. We will manage a Call for Proposals in a fair, open and transparent manner by:
  1. Publishing the objectives of this Business Case and requesting Expressions of Interest;
  2. Evaluating and moderating of the proposals by the FCDO panel against published criteria; and
  3. Communicating the outcome and providing feedback to all applicants.
Proposals will be invited from organisations setting out approaches, activities and outcomes that will help FCDO achieve the objectives of this investment. Competitive proposals will be appraised against the same criteria, which will include strategic fit with objectives, technical feasibility, risks and VfM.

#### Managing Conflicts of interest (CoI)
We expect that a substantial body of the SIEL evaluations and related work will be carried out by a partner or consortium of partners. However, there may be a need for the partner to commission out some of the work where there are gaps in their expertise, or practical necessity e.g., where the data for a follow up study is owned by another organisation. In this case, FCDO already has clear CoI procedures for the funding of research which can be applied, e.g., academic experts invited to join panels to assess bids declare their CoI. If there are bidders from their own department or university, they recuse themselves during the consideration of that bid.

#### SIEL Scope
1. SIEL could seek to evaluate programmes and influencing activities in any thematic area in development and diplomacy, in any part of the world;
2. FCDO’s current key priority areas set out in the International Development Strategy are: investment, women and girls, humanitarian, climate change, nature and global health. There is also potential for the programme to address topics highlighted in the Integrated Review Refresh (2023).
3. This could expand further and/or change over time in response to Ministerial preferences.

#### Capability
1. The partner(s) will need to demonstrate proven expertise to:
  1. Deliver impact evaluations employing randomized controlled trials and quasi-experimental methods. The supplier should either offer the full spectrum of activities from design, working with in-country partners and FCDO central office, data collection, analysis and evaluation writing or have strong abilities in one or more parts of this chain and the ability to contract out the remainder to offer FCDO an end-to-end service.
  2. Use impact evaluation methods to enable course correction and adaptive learning in programmes.
  3. Drive uptake of impact evaluation evidence including through expertise in effective communication activity to non-technical audiences.
  4. Manage/build effective networks to support delivery of the work.
  5. Carry out follow up studies, potentially including working with the organisation that originally conducted the impact evaluation.
  6. Build capacity in FCDO related to impact evaluation.

#### Capacity
1. A partner or consortium will need to be able to demonstrate that they can develop and implement multiple impact evaluations across a broad thematic spectrum, working closely with FCDO policy teams and advisors. Other core capacities will include:
  1. Ability to adapt to new priorities/areas, including scale down or up depending on demand, need and available budget.
  2. Ability to maintain a) core technical team/consortium to deliver the core objectives; provide credible, world-leading expertise; and collaborate with FCDO technical leads and PRO/ SROs; b) flexible pool on demand: to respond to FCDO’s rapid needs and changing priorities; and c) specialist functions: for strategic uptake and lessons sharing; and capacity building of FCDO staff.
#### Performance management

1. SIEL’s log frame, progress reporting and review processes will be key performance management tools. A set of indicators for monitoring progress in the delivery of outputs, the dissemination of these outputs and their use will be established, with annual targets. Some initial ideas are set out in Annex 2. Progress against these targets will be monitored on a quarterly basis and assessed continuously.
2. SIEL will be managed by FCDO’s Evaluation Unit. An Evaluation Unit Advisor will act as PRO for SIEL. The PRO will review quarterly progress reports submitted by the implementing partner. The Evaluation Unit’s management of the programme will be supported by the Programme Steering Committee, which will be chaired by the SIEL SRO and meet quarterly to review programme progress and risks. More detail on SIEL’s management and governance structure is included in the Management Case.
3. SIEL’s payment structure will also support performance management. Payment will be made in arrears, or at least not in advance of need, and the approval process will involve checks on quality and timeliness of outputs. FCDO has mechanisms to manage underperformance, including reducing payments.
4. Payments could include a mixture of output-based payments and payments for time and expenses, depending on the agreement with the implementing partner.

#### Commercial Risks

Commercial risks related to the programme, including mitigation, are set out in the Management Case.

## Financial Case

The Financial Case Presents
- Source and Type of Funding
- Cost Profile and Disbursement of Funds
- Expected Deliverables
- Currency and Taxes
- Spending Review Limits and Break Points
- Monitoring and Financial Risks

#### Source and Type of Funding

FCDO will assign up to £13m of CDEL research funds, over seven years from April 2023 to March 2030, including up to £2.5m of non-ODA. The programme will also have the option to apply for a costed or no-cost extension for a further three years, to March 2033, subject to the appropriate approvals.
#### Cost Profile and Disbursement of Funds

An indicative cost profile for SIEL is as follows:

Table 5: SIEL indicative spend profile. Figures in Pounds Sterling (£)
Year	2023/4	2024/5	2025/6	2026/7	2027/8	2028/9	2029/30	%
Overheads/ administration	35,000	140,000	140,000	140,000	140,000	140,000	175,000	7%
Impact Evaluations	300,000	1,200,000	1,200,000	1,200,000	1,200,000	1,200,000	1,500,000	60%
Follow up studies	75,000	300,000	300,000	300,000	300,000	300,000	375,000	15%
Capacity building and dissemination	75,000	300,000	300,000	300,000	300,000	300,000	375,000	15%
M&E	15,000	60,000	60,000	60,000	60,000	60,000	75,000	3%
Total	500,000	2,000,000	2,000,000	2,000,000	2,000,000	2,000,000	2,500,000	13,000,000
Of Which non-ODA	400,000	400,000	400,000	300,000	300,000	300,000	400,000	2,500,000

1. The first year will mainly comprise procuring the programme and setting up the new evaluation function, including carrying out workshops to identify priority evidence gaps, build interest and identify an initial portfolio of projects to evaluate. From year two, there will be heavy impact evaluation activity as the bulk of the work on study design and engagement will be carried out in Years two and three. Year two may also feature more capacity building work. From years three and four there will be more of a focus on nimble evaluations and follow up studies that can be delivered within year, and years five to seven will feature analysis and reporting on the evaluations.
2. The choice of funding model will depend on the chosen supplier(s) and any constraints on their way of working but will be consistent with FCDO policies. Funds could be disbursed through a hybrid of output/ deliverable based payments and costs for time and expenses, for example to cover travel and/or staff overheads. FCDO will agree with the implementing partner during the inception phase whether monthly invoicing is required; FCDO’s preference here is quarterly. The approval process will include checks on quality and timeliness of outputs.

#### Expected Deliverables

1. Evaluation Unit will seek to extend the reach of this funding and increase buy-in from country/ programme teams by requiring co-funding. Leverage was key to the Fund for Impact Evaluation reaching the figure of 162 impact evaluations, with FCDO covering approximately 25% of the cost of an evaluation. The degree of co-funding is likely to be lower here, reflecting the tightness of country bilateral ODA budgets at the present time, but some degree of co-funding is likely to increase buy-in from local teams.
2. The number of impact evaluations delivered will depend on the balance of full-scale impact evaluations (from programme start to close) and nimble RCTs which could be carried out at programme inception or to inform in-course corrections. Since co-funding cannot be depended upon, if we use the full cost of the Fund for Impact Evaluation studies of approximately £560,000 we can estimate that SIEL could deliver around 14 impact evaluation studies with the £7.8m allocated to IEs. However this number could vary widely depending on the sample size, number of treatment arms, extent of face- to -face data collection and duration of studies.
  [note] DevTracker Programme GB-1-203872 Documents (fcdo.gov.uk)
3. Similarly, we estimate that the £1.95m allocated to follow up studies should deliver approximately four of these, but the final figure will depend on the bids received from the Call for Proposals and the practical arrangements for carrying these out, which will involve a degree of ‘learning by doing’ given the novelty of this element.

#### Currency and taxes

1. All financial commitments will be made by FCDO in sterling. Downstream partners will be expected to monitor and make provisions for potential exchange rate movements over the life of their projects.
2. Since the main outputs of the SIEL programme can be considered as ‘research services’ under the ProF, VAT, where charged by the supplier should be reclaimable under rule N74.
  [note] PrOF Guide_VAT.docx (sharepoint.com)

#### Spending Review limits and Break points
1. As the programme budget goes beyond March of financial year 2024/25 (current limit of FCDO delegated authority) we will seek approval from Management Accounts Group for the full programme commitment which goes beyond the current SR.
2. We will also include a break clause in the agreement/s to reserve the right to revise or discontinue the programme funding beyond this point in line with Spending Review limits, FCDO needs and priorities. This approach is in line with current FCDO PrOF guidelines (for approval processes) and has been used for a range of FCDO research funding mechanisms.

#### Monitoring and financial risks
1. The FCDO programme team will undertake a due diligence assessment before disbursing any funds to obtain the necessary assurances.
2. The FCDO project manager for SIEL will be responsible for analysing financial reports and will review invoices to ensure consistency with agreed budget, progress and VfM. This work will be overseen by the SRO. Our assessment is that the risk of fraud is moderate and will be manageable, ensuring mitigating strategies are in place.

## Management Case

The management case presents:
- Governance and decision-making structure
- Risk Appetite and Risk Register
- How the risk management approach will ensure we deliver within risk appetite
- Monitoring & Evaluation
- Exit strategy

#### Governance and decision-making structure
1. The SIEL programme will be overseen by a steering committee comprising key figures from Economics and Evaluation Directorate, EVU and Research and Evidence Directorate at working level.
2. The steering committee will ensure the strategic alignment and ongoing relevance of the SIEL programme. Evaluation unit will work with the Implementing Partner to generate demand, and working with policy teams, carry out dissemination of and ensure learning from results.
3. The steering committee will also make recommendations about which evaluations to take forward, but for these meetings an independent expert from The Evaluation Quality Assurance Service (EQUALS) with impact evaluation expertise could be added to the panel, as well as one or more expert representatives from the SIEL supplier.
4. Decisions about which evaluations are taken forward will be approved by the Chief Economist in consultation with the Chief Scientist. If there are differences of opinion which they are unable to resolve, they may also consult the Director General.
5. At the programme level, management arrangements will be:
  1. A Programme Responsible Owner (PRO) will drive procurement and delivery of the programme and ensure its continued relevance. This will involve extensive engagement with stakeholders including the chosen implementing partner, programme teams and across FCDO to tackle the practical challenges of delivering impact evaluations and related capacity building. The PRO will ensure financial management responsibilities are fully discharged, overseeing the work of a Project Manager who will arrange the funding agreement with the implementing partner, regularly reviewing forecasts and budgets and processing of payments. The PRO will also monitor risk working with the project manager and escalate risks outside appetite to the Senior Responsible Owner. The PRO and project manager will meet the implementing partners every quarter (monthly during inception) to discuss progress, finances and any issues arising.
  2. A Senior Responsible Owner (SRO) will oversee programme strategy, performance, financial management and reviews. The Senior Responsible Owner will seek to ensure that the programme remains within risk appetite.
6. FCDO Programme teams receiving SIEL support will also be expected to set aside resources to work with the SIEL implementing partner and EVU on the evaluation. Programme teams will be expected to track and manage risks related to their programme-specific evaluation and work with the SIEL implementing partner on an ongoing basis. Depending on the scale of the impact evaluation this could be 0.1-0.2 FTE for a PRO.

#### Risk Appetite & Register
1. This programme will take a Receptive approach to risk in line with FCDO’s Risk Management Policy for Policy and Programme Delivery. At the time of writing the Business Case, the overall residual risk level is Moderate, which fits within FCDO and EvU’s risk appetite.
  [note] FCDO Risk Management Policy.docx (sharepoint.com)
2. Annex 1 provides a draft Risk Register for the SIEL programme.

#### How the risk management approach will ensure we deliver within risk appetite
1. The PRO will monitor risks – i.e., they will:
  1. Consider the continued relevance of existing risks
  2. Note emerging risks
  3. Review the success of mitigating actions
  4. Record changing levels of risk
2. If any risk or risks detailed above increase beyond our risk appetite, the PRO will escalate to the SRO and together they will act quickly to take controlling actions.

#### Monitoring & Evaluation
1. The programme’s results framework will be agreed and regularly reviewed between FCDO and the implementing partner. The logframe will include indicators on the quantity, quality and timeliness of outcomes, outputs, effectiveness of dissemination activities and the use of outputs.
2. A draft logframe, informed by the Fund for Impact Evaluation and CEDIL Programme, is contained in Annex 2.
3. A mandatory, published Annual Review of SIEL will formally track progress against logframe indicators, assess VfM, Risks, Supply Chains and examine trajectory towards ultimate impacts and provide learning and recommendations to improve the programme.
4. Other key performance review points anticipated through the year will be:
  1. Monthly meetings on finance, risks and other emerging issues.
  2. Quarterly narrative and financial reports, focusing on operational effectiveness against the workplan, in a standardised and simplified format, including summary of progress against agreed budgets, key lessons and improvements for the coming quarter; value for money; updated risk register and workplan.
  3. Mid-year reports focusing on progress against logframe targets, strategic challenges and lessons learned, including performance against KPIs.
5. FCDO Programme and policy teams collaborating with SIEL will be expected to have their own results frameworks. These could also assess and report progress of SIEL evaluations. These teams will be expected to regularly report progress back to EVU to inform annual reporting on the SIEL programme.

#### Exit Strategy

1. Major delivery, operational, external context, safeguarding, financial, fiduciary or reputational issues may trigger consideration of early closure of the programme. In these cases, FCDO will review the range of available options, which include continuing, pausing, scaling back, adapting, or closing the programme, the likely impacts of these options, including on value for money, and the potential risks and their mitigation.
2. An exit plan should be included in proposals at the bid stage and developed further at inception of the programme. This should include maximising the learning from the impact evaluations for the long run, after the programme has closed.

## Annex 1: Risk Register

Risk	Impact	Probability	Mitigation	Probability after mitigation
Budgetary Pressures - FCDO priorities are required to shift to respond to global events, and so resources dedicated to SIEL could be subject to change.	Major	Possible	SIEL needs to demonstrate its ability to establish and improve the Value for Money of limited funds, e.g. through cost effectiveness analysis	Possible
Quality and timing of demand is poor The SIEL Partner organisation must be aware programmes/ projects at Concept Note stage and be able to allocate research teams to them sufficiently quickly to design-in an impact evaluation.	Moderate	Likely	Workshops and Communications materials setting out clear offer, timing and criteria for selection will be developed. If demand is low, EvU could consider providing additional support to interested potential users. / EVU will also facilitate relationships between the Partner organisation and the Implementing Partner. / Implementing partner with in-house delivery capacity and/or good networks of partner organisations. / Flexibility in selection of evaluation questions and topics to ideas and insights from programme and policy teams.	Possible
Duration of programmes and evaluations do not match up- SIEL is due to run for seven years from 2023-30. Most impact evaluations last for the duration of a programme and beyond. Evaluations starting in year 3 risk not having funding to evaluate the final impact of the programme.	Major	Possible	Focus from year 3 will be on nimble, shorter evaluations and follow up studies. / Programme to be set up with possibility for both cost and no-cost extensions	Possible
Strength of demand/ institutional issues limit engagement with SIEL– the launch of SIEL will be a key opportunity to understand the nature of demand and whether there is a need to manage excess demand or to generate demand for impact evaluation, if there is limited interest. In addition a key issue is building institutional willingness to engage in an IE, accepting that it may provide negative feedback about a programme’s effectiveness.	Moderate	Possible	EvU to engage key users via Evaluation Cadre and HoP networks and assess feedback to tailor outreach to potential users accordingly. Offer includes access to a tailored package of support, including technical advice and streamlined procurement approach for all evaluations funded through SIEL. / Flexibility in selection of evaluation questions and topics to ideas and insights from programme and policy teams.		Possible
Staff turnover – most teams submitting EoIs will experience staff turnover during the life-cycle of the evaluations commissioned, potentially resulting in lower ownership of evaluation outputs and reduced capacity to management implementation and assure quality. / EVU could also be subject to resource fluctuations.	Moderate	Likely	EoIs should provide confirmation of senior leadership endorsement and a named individual who will provide an ongoing point of contact. / Sharing of information/ learning about SIEL within EVU to manage any short-term fluctuations in resource due to e.g. surges.		Likely
Evidence generated by SIEL does not influence decision-making	Major	Possible	Continuous engagement by EVU and the implementing partner with policy/ programme teams, country-based SCS, and HOP networks. / SIEL evaluations to include Evidence and Learning plans, including stakeholder engagement and evidence use. Logframe to include indicators on use and uptake.		Unlikely

## Annex 2: Indicative Logframe Indicators (based on EVU’s previous Fund for Impact Evaluation and CEDIL programme)
Outcomes	Indicators	Definition of indicator

1. Improved awareness, demand for and use of evidence in decision making in key sectors	Proportion of project teams participating in SIEL workshops that improve their knowledge of impact evaluation techniques	% of IE teams participating in workshops with a teaching component that show improvement on pre-post knowledge test
	Proportion of project teams participating in an impact evaluation workshop that submit a proposal in the relevant SIEL funding window	% of teams participating in SIEL initiating workshops that submit a proposal to the relevant call for proposals
	Proportion of impact evaluations with multi-arm evaluation designs to test project innovations.	% SIEL IEs that have more than one treatment arm
	Proportion of impact evaluations that influence project during design or implementation	% of IEs that improved design based on clear understanding of the underlying theory of change or whose baseline results were used to stimulate policy dialogue / help identify problems and solutions
	Proportion of completed impact evaluations that generate evidence used to support project adoption, scale-up, scale-down, continuation or cancelation decisions
	Robust online and social media attendance and engagement with SIEL	Number of blog and vlog posts published on the SIEL website.
2. Improved effectiveness and impact of new and existing development interventions from FCDO and wider community	Proportion of impact evaluations that have influenced the design or implementation of other projects outside of the IE itself	Proportion of impact evaluations that have influenced the design or implementation of other projects outside of the IE itself - Measured through feedback survey of relevant programmes?
	Proportion of completed and published impact evaluations that are cited in the academic literature
	Percentage of SIEL products disseminated to policymakers in the SIEL networks that are downloaded	% of emails sent to relevant policymakers in the SIEL networks that result in the opening of IE product attached, including working papers, policy briefs, and papers
Outputs	Indicators	Definition of indicator
1. Increased quantity, quality and relevance of evidence available to improve policy design and implementation in underserved areas	Number of new SIEL-supported datasets (baseline or follow-ups)	Stock of datasets produced during SIEL support cycle (since selection) across SIEL-supported IEs.
	Number of impact evaluations completed and reported	Number of SIEL-supported IEs with final products (final report, working paper, policy brief, and/or publication)
	Proportion of ongoing impact evaluations that have produced an intermediate report	% of IEs that have a baseline or mid-term output (report, working paper, and/or publication)
	Thematic knowledge reviews for policymaking	Stock of thematic knowledge reviews, e.g., mechanism, sector, country, pillar reviews
	Number of SIEL-supported IEs	Number of SIEL-supported IEs
	Thematic distribution:	% and number of SIEL-supported IEs
	SIEL themes tbd
	Regional distribution:	% and number of SIEL-supported IEs covering that area.
	Sub-Saharan Africa
	Middle East/North Africa
	Europe and Central Asia
	Latin America/ Caribbean
	East Asia and the Pacific
	South Asia
	Income level distribution:	% and number of SIEL-supported IEs
	Low income and lower-middle income
	Upper middle income
	Gender:	% and number of SIEL-supported IEs
	Proportion of IEs with a gender specific intervention
	Proportion of IEs performing gender analysis	(for IEs with household and individual level data)
	Number of events (workshops, training sessions, and dissemination events) with FCDO audience	Number of events (workshops, training sessions, and dissemination events) with FCDO participation
2. Increased capacity of FCDO policymakers, implementers, researchers, and partners to incorporate rigorous evidence/tools into policymaking	Number of FCDO staff trained in SIEL capacity building events	Number of people from FCDO trained in SIEL workshops and capacity building events
	Proportion of IEs that improve project team’s M&E	% of IE whose data requirements led to improvements in M&E data collection and/or reporting activities of the project teams
	Number of organisations participating in SIEL workshops	Stock of organizations (donors, Multilateral Development Banks, government agencies, academic institutions, NGOs, etc) that have participated in at least one SIEL workshop
	Number of organisations, universities, research centres, and government agencies participating in SIEL networks	Stock of organizations engaged in SIEL-supported IEs (researcher and counterpart affiliation)
	Number of SIEL seminars	Number of SIEL seminars, which show case ongoing and completed IE work
	Number of IE dissemination events to policymakers	Number of events organized to disseminate IE results (baseline or final) to policymakers
3. Increased Communities of Practice and knowledge platforms for sharing of evidence and its application for policy making	Number of organisations, universities, research centres, and government agencies participating in SIEL networks	Stock of organizations engaged in SIEL-supported IEs (researcher and counterpart affiliation)
	Number of SIEL seminars	Number of SIEL seminars, which showcase ongoing and completed IE work