## CAWEP LF
Please refer to the PrOF Guide for advice on completing the various fields in the logframe.
Smart Guide
PROJECT TITLE | [9 empty] | Working Notes
IMPACT | Impact Indicator 1 |  | Baseline | Milestone 1 (February 2022) | Milestone 2 (February 2023) | Milestone 3 (February 2024) | Milestone 4 (February 2025) | Milestone 5 (November 2025) | Assumptions An enabling environment for implementation of the CAWEP interventions at community, subnational and national level Occurring shocks and hazards don't set back completely any progress made. Communities effectively utilise water and renewable energy infratructure, weather and climate information. The government and government departments remain committed to climate adaptation and resilience building. The vulnerable people and districts identified are able to incorporate climate change adaptation and DRR into their decision making
Communities and public institutions supported by CAWEP are more resilient to respond to adverse effects of climate Change (droughts & floods) | Number of people whose resilience has been improved. This will be assessed by the number of people and communities in vulnerable districts being able to recover during/post climate shocks using water, clean renewable energy and access to weather/climate info and avoid complete loss of livelihoods and access to health and education. | Planned |  | 0 | 0 |  | 280 000 (40% ) | 420000 (60%) | i) Target based on the baseline which shows that 79% of the target beneficiaries have a low Resilience capacity score (a score of less than 33,) 20% have a Medium RCS (34-65) and 1% have a High RCS (66 and above). The target takes into account the shock environment (droughts and floods, cyclones) whose frequency and intensity is increasing due to Climate Change, which may discrupt/stall the resilience building efforts. 2023/2024 has been declared an Elnino year. (ii)the indicator will measure improvement from low to medium, low to high, medium to high. iii)The theory of change hypothesises that by installing sustainable multiple use water and renewable energy infrastucture, then households and social instituitions have improved access to water and energy for multi-purpose use, reducing burden on individuals especially women and girls of fetching water and gathering fuel; improving service provision to the communities, increasing agriculture production, diversified non farming livelihood opportunities leading to improved health and education outcomes, increased household income with these contributing to community resilience. Similarly, improved access to timely and reliable weather and climate information,capacity building of institutions and communities in early warning systems, weather and climate information generation, intepretation and dissemination then there is increased capacity at community, local and national levels to adapt & respond to the increasing risks of climate change. iv)The Implementing Partner will analyse this data to report against the logframe, examining trends over time and comparisons to baseline, where applicable. Depending on needs or requests, data may be compared with data from other sources to benchmark or compare reach, impact or similar. | Resilience score is calculated using the World Food Programme (WFP) Resilience Capacity Score (RCS) approach to measure the resilience capacity against adverse effects of climate induced shocks and disasters.. The RCS is based on the Subjectively Evaluated Resilience Score (SERS) designed by L. Jones (2019) and WFP’s Climate Resilience Capacity Score (CRCS) and uses a subjective approach to resilience measurement. This model of resilience measurement prioritizes participants’ perspectives and knowledge to provide bottom-up insights on what ‘resilience’ means to them. The framework measures a household’s perception of their resilience capacities against area-specific climate-induced shocks and disasters. It focuses on two major capacities namely resilience capacities and livelihood capacities. Resilience capacities: anticipatory (ability to minimize exposure through preventive measures), absorptive capacity (Ability to reduce, and cope with, the immediate impact of shocks), adaptive capacity (ability to make alternative livelihood choices) and transformation (ability to reduce the impact of shocks by major changes/investments in livelihoods/food systems). Livelihood capital: Considers human capital (skills, knowledge, and practices useful in adapting livelihoods to future shocks), financial capital (ability to make savings, access to financial services, and regular income or inflows of money that act as a buffer in absorbing the effects of shocks), social capital (relationships of trust, reciprocity, and exchange that households can draw upon in times of need), institutional capital (capacity of households to rely on external support received from the government and other institutions in case of shock) and Informational capital (access to information needed for appropriate decisions to protect the household and livelihoods from shocks). The RCS components satisfy the 3As Resilience model which is recommended in the DFID KPI4 and was used to track resilience in the DFID funded Building Resilience and Adaptation to Climate Extremes and Disasters (BRACED) programme which was launched in 2015 with the aim to build the resilience of up to 5 million vulnerable people against climate extremes and disasters in 13 countries in East Africa, the Sahel and Asia. The 3As Model components are: Adaptive Capacity – “the ability of social systems to adapt to multiple, long-term, and future climate change risks, and to learn and adjust after a disaster. Anticipatory Capacity – “the ability of social systems to anticipate and reduce the impact of climate variability and extremes through preparedness and planning” (Bahadur et al, 2015: p. 23). Absorptive Capacity – “ability of social systems to absorb and cope with the impacts of climate variability and extremes. The RCS also satisfies Transformative Capacity - where households and communities can change their primary income or source of livelihood if needed during times of hardships. The RCS is an acceptable quantitative resilience measurement for FCDO’s KPI4 as it is a score. “It is Categorical, or score based, through assigning a beneficiary a score (e.g., 0-3 or 0-5) representing a category or level of resilience (e.g., low, moderate, high). Score-based indicators” (page 15 of DFID’s methodology for reporting against KPI4). The RCS gives a quantitative measure of the resilience score against area-specific climate-induced shocks. Application of the RCS Using the above capacity variables, RCS places households’ capacities into three categories or terciles (each category being a 3rd of the total data set) i.e., % of targeted households with a low RCS, % of targeted households with a medium RCS and % of targeted households with a high RCS. Calculating resilience score The RCS is calculated from 9 sub-statements (Statement 1 to Statement 9) using a five-point Likert scale (strongly disagree, disagree, neutral, agree, strongly agree) to capture the household perception of existing resilience capacities or livelihood capital. The Resilience Capacity Score aggregates the unweighted answers to the nine statements to provide a score ranging from 0 to 100. Individual answers are then used to compute an overall resilience score for each household as an equally weighted average of the nine answers. The resilience score is standardized by minmax normalization , transforming the results in a score that ranges from 0 (not at all resilient) to 100 (fully resilient). Using the formula RCS i = {{[(Q1_i+Q2_i+Q3_i +Q4_i +Q5_i +Q6_i +Q7_i +Q8_i +Q9_i)/9]-1} / (5-1)} x100, all households are divided in terciles (low-medium and high) to show the distribution of the RCS within the target population as follows: a) If RCS<33 the household is classified as reporting a low RCS, b) If 33>RCS<66 the household is classified as reporting a medium RCS and c) If RCS>=66 then the household is classified as reporting a high RCS.
|  | Achieved | RCS- 20.17 Chipinge RCS - 21.48 Chivi RCS- 19.08 Insiza RCS- 19.67 Binga RCS- 20.46 HRCS- 1% Medium RCS- 20% Low RCS- 79% | 0 | 0
Source: CAWEP Feasibility Study reports (for baselines), February 2022, CAWEP Baseline, GCF Baseline,Zimbabwe Resilience Building Fund Outcome Monitoring Survey Report (for baselines), CAWEP OMS, Endline survey
OUTCOME 1 | Outcome Indicator 1.1 |  | Baseline | Milestone 1 (February 2022) | Milestone 2 (February 2023) | Milestone 3 (February 2024) | Milestone 4 (February 2025) | Milestone 5 (November 2025) | Assumptions An enabling environment for implementation of the CAWEP interventions at community, subnational and national level Community interest and leadership Local market can support diversification and business development | Working Notes
Poor & vulnerable households become more adaptive to effects of climate change through sustainable access to long term climate resilient and multiple use water and renewable energy infrastructure | Number of people supported to better adapt to the effects of climate change through sustainable access to solar powered multiple use water systems, Renewable Energy and Early Warning Systems Disaggregated by sex | Planned |  | 48651 25062 (f) 23333 (m) 256 (disabled) | 63090 32807 (f) 30283 (m) 0000 tba (disabled) | 99512 54903 (f) 44609 (m) 544 (disabled) | 400000 208000 (f) 192000 (m) tba (disabled) | 700000 364000(f) 336000 (m) tba (disabled) | (i) Target based of potential number of people to be reached as identified by the feasibility study. (ii) Sex disagregation is based on 2012 average ratio of males & females which is 48% and 52% respectively. (iii) The Theory of Change hypothesizes that by installing climate resilient water abstraction infrastructure, using solar power, generated solar power can be utilised by social institutions improving their ability to service the community, and by households, with both of these contributing to community resilience. Similarly, improved access to potable water reduces the time individuals spend queueing for water or gathering fuel for and purifying water, increasing the time available for them for other pursuits, and household members are more likely to have improved health outcomes. (iv)The Implementing Partner will analyse this data to report against the logframe, examining trends over time and comparisons to baseline, where applicable. Depending on needs or requests, data may be compared with data from other sources to benchmark or compare reach, impact or similar. | Indicator aligned to ICF KPI 1. Indicator Calculation Calculation to include Indirect Beneficiaries. Indirect Beneficiaries to be derived from, Village, Ward and District Population figures. For AWS MSD to provide acceptable radius of Indirect reach for AWSs.
|  | Achieved | 77768 | 48651 25062(f) 23333 (m) 256 (disabled) | 77768 39639(f) 37521(m) 608 (disabled) | 149652 people (81118 Females, 68534 Males) 716 Disabled | 0 | 0
Source: CAWEP Feasibility Study reports February 2022 & UNICEF CAWEP Final Report 2022 (for Baseline). Project Progress Reports and database, DDF Reports
| Outcome Indicator 1.2 |  | Baseline | Milestone 1 (February 2022) | Milestone 2 (February 2023) | Milestone 3 (February 2024) | Milestone 4 (February 2025) | Milestone 5 (November 2025)
| Number of people with improved access to clean energy as a result of set up/connected to solar micro/minigrids/Solar Home systems/Biogas Digestors/Solarised Social Institutions. Disaggregated by (i) community (ii) sex (iii) age (iv) disability | Planned |  | 0 | 0 | 3900 1842 (f) 2058 (m) 30 (disabled) | 20000 11000 (f) 9000 (m) 100 (disabled) | 20000 11000 (f) 9000 (m) 100 (disabled) |  | Indicator aligned to ICF KPI 2.1
|  | Achieved | Solar mini grid-0 Solar home systems-200 i) Sex: 46.5%M, 23.2F ii)Age: 36.6%Youth, 38.9%Adults, 29% Elderly iii)Disability14% Biogas Digestors- 0 |  | 0 | 8351 (3658M, 4693F, 42 Disabled) 993- biogas digestors (595F,398M, 24 Disabled) Chipinge- Biogas- 774 Chivi-219 7358- Solar Modules (3260M, 4098F, 18 Disabled Learners)- Binga Age: Children (0-16)- 3412: (Solar modules 3241, Biogas 171) Youth (17-25)-169 Adults- (26-64) 4676 Elderly- (65+) 93
Source:CAWEP Feasibility Study &Baseline reports (for Baseline), Rural Electrification Agency customer reports, Project Progress Reports & database
| Outcome Indicator 1.3 |  | Baseline | Milestone 1 (February 2022) | Milestone 2 (February 2023) | Milestone 3 (February 2024) | Milestone 4 (February 2025) | Milestone 5 (November 2025) |  |  | 56
| Number of social institutions with improved access to clean energy as a result of set-up solar micro-mini grids, solar modules disaggregated by 1. community and 2 type of institution. | Planned |  | 27 24 Schools 3 Clinics | 54 46 Schools 8 Clinics | 61 (2 UNDP) Chipinge, 52 Schools (1 UNDP) Chipinge, 9 Clinics (1 UNDP) Chipinge | 80 (21 UNDP) 62 Schools (11 UNDP) 10 Clinics (3 UNDP) 10 Agritex Offices (UNDP) | 82 (24 UNDP) 62 Schools (11 UNDP) 10 Clinics (3 UNDP) 10 Agritex Offices (UNDP)
|  | Achieved | 59: UNICEF Type: 51 Schools 8 Clinics UNDP: 0 | 27 24 Schools 3 Clinics | 59 51 Schools 8 Clinics | 71 UNDP-12 Social Institutions Binga: 10 Schools, 1 Clinic, 1 ZINWA Office Complex
Source: CAWEP Feasibility Study & Baseline reports, Rural Electrification Agency customer reports, Project Progress Reports
| Outcome Indicator 1.6 |  | Baseline | Milestone 1 (February 2022) | Milestone 2 (February 2023) | Milestone 3 (February 2024) | Milestone 4 (February 2025) | Milestone 5 (November 2025)
| Percentage of businesses/ enterprises demonstrating sustainable growth as a result of access to solar powered multiple use water systems, Renewable Energy Disaggregated by (i) Solar Mini Grid, (ii) Irrigation Systems, (iii) Sex, (iv) Age, | Planned |  |  |  |  | 40% | 50%
|  | Achieved | 0
Source:CAWEP baseline Report, Feasibility Study Reports for baseline. Project Project Reports, VTC , Ministry of Youth, Min of Women Affairs Reports, CAWEP OMS, Endline Reports
| Outcome Indicator 1.7 |  | Baseline | Milestone 1 (February 2022) | Milestone 2 (February 2023) | Milestone 3 (February 2024) | Milestone 4 (February 2025) | Milestone 5 (November 2025)
| Number of green jobs created or improved as a result of developed/rehabilitated multi purpose water and clean energy infrastructure Disaggregated by (i) Type, (ii) sex | Planned |  |  |  |  | 500 Female 250 Male 250 | 500 Female 250 Male 250
|  | Achieved | 0
Source:CAWEP baseline Report, Feasibility Study Reports for baseline. Project Project Reports, Ministry of Youth, Min of Women Affairs Reports, CAWEP OMS, Endline Report
OUTCOME 2 | Outcome Indicator 2.1 |  | Baseline | Milestone 1 (February 2022) | Milestone 2 (February 2023) | Milestone 3 (February 2024) | Milestone 4 (February 2025) | Milestone 5 (November 2025) | Assumptions Community interest and leadership Sustainable demand for high value crops Resilient markets Local market can support diversification | Working Notes
Community livelihoods are improved through reliable access to and use of irrigation infrastructure. | Percentage of targeted land under irrigation | Planned |  | 0% | 0% | 15% | 80% | 100% | i) Targets based on the feasibility study for Chipinge, revision of scope of works in Mlibizi and the Feasibility study for Chivi and Insiza irrigation schemes and water development. (ii) The Theory of Change hypothesizes that by empowering communities by providing access to irrigation infrastructure, communities will improve their climate resilience, by improving the reliability of their domestic, and where appropriate, commercial agriculture. Providing irrigation infrastructure that is well planned, well installed, and well maintained contributes to increasing the climate resilience of the communities. | Targets revised after the programme budget allocated to UNDP has been reduced from £14-12 million. Targets also revised after the feasibility study for Gororo and Wanezi, which revealed that Wanezi Dam can supply water for irrigation for 37ha. Mlibizi 25ha (20ha Irrigation scheme, 5x1ha gardens), Gororo 50ha, Hakwata 2ha
|  | Achieved | 0 | 0 | 0 | 21%
Source: CAWEP Feasibility Study & baseline reports (for baseline), GoZ Department of Irrigation report, AGRITEX reports, Project Progress Reports
| Outcome Indicator 2.2 |  | Baseline | Milestone 1 (February 2022) | Milestone 2 (February 2023) | Milestone 3 (February 2024) | Milestone 4 (February 2025) | Milestone 5 (November 2025)
| Irrigation infrastructure functionality rate is at least x% | Planned |  | 0% | 0% | 60% | 80% | 90% |  | A %ge of all irrigation facilities supported through CAWEP
|  | Achieved | 0 | 0 | 0 | 100%
Source: CAWEP Feasibility Study & Baseline reports (For baseline), GoZ Department of Irrigation O&M reports, Project Progress Reports
OUTCOME 3 | Outcome Indicator 3.1 |  | Baseline | Milestone 1 (February 2022) | Milestone 2 (February 2023) | Milestone 3 (February 2024) | Milestone 4 (February 2025) | Milestone 5 (November 2025) | Assumptions Community, institution capacity & appropriate, applicable training EWS data is appropriate, applicable, & easily understood by community Multi stakeholder approach to EWSs.
Community climate change adaptation capacity improved as a result of access to reliable weather and climate informantion (EWS). | Percentage of people trained that timely receive weather & climate information. | Planned |  | 0% | 0% | 40% | 60% | 80% | (i) The Theory of Change hypothesizes that by empowering communities by providing access to climate related data, they will have information on which to base decisions that will positively impact their livelihoods by opting to adapt their crop cycles, harvesting times, living conditions, etc. improving their resilience to climate change.
|  | Achieved | 15% | 0 | 0 | 76.6%
Source: CAWEP Feasibility Study reports (for baseline), GoZ Metereological Services Department report, Outcome monitoring reports and endline survey.
| Outcome Indicator 3.2 |  | Baseline | Milestone 1 (February 2022) | Milestone 2 (February 2023) | Milestone 3 (February 2024) | Milestone 4 (February 2025) | Milestone 5 (November 2025)
| Percentage of people trained that timely use weather & climate information to plan and timely respond to anticipated weather & climate disasters | Planned |  | 0% | 0% | 50% | 60% | 60%
|  | Achieved | 94.6% of 15% | 0 | 0 | 100%
Source: CAWEP Feasibility Study reports (for baseline), GoZ Metereological Services Department report, Outcome monitoring reports and endline survey.
| Outcome Indicator 3.3 |  | Baseline | Milestone 1 (February 2022) | Milestone 2 (February 2023) | Milestone 3 (February 2024) | Milestone 4 (February 2025) | Milestone 5 (November 2025)
| Use of climate information products/services in key decision making government departments (Met Services, AGRITEX & ZINWA) | Planned |  | 0% | 0% | 40% | 60% | 80% |  | Working Notes
|  | Achieved | Met Services- 90% Agritex- 25% ZINWA-N/A | 0 | 0 | 66% Met Services-100% Agritex- 100% ZINWA-No data |  |  |  | A %ge of all government institutions supported through CAWEP. A 4 part criteria score for the 3 departments i.e ZINWA, AGRITEX & MSD. The 4 part criteria can relate to Localized weather, climate and hydrological model forecasts generated regularly and Use of water resource models and translation of forecasts into impact for ZINWA and MSD. FOr AGRITEX this can relate to the development of tailored forecasts, dissemination of forecasts and advisories to at risk communities. In terms of measurement, the staff in in the departments should score at least 75% across all four criteria.
Source: CAWEP Feasibility Study &Baseline reports (for baseline), GoZ Metereological Services Department report, Outcome monitoring reports and endline survey.
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Milestone 1 (February 2022) | Milestone 2 (February 2023) | Milestone 3 (February 2024) | Milestone 4 (February 2025) | Milestone 5 (November 2025) | Assumptions an enabling environment for implementation of the CAWEP interventions at community, subnational and national level Communities effectively utilise water and renewable energy infratructure. Effective sustainability, Operation and maintence business models. | Working Notes
Developed climate resilient multiple use water and energy infrastructure | Number of community multipurpose water & clean energy infrastructure developed/rehabilitated with special technical designs and features that respond to climate risks.Disagregated by type (i) Solar Piped Water Systems (PWS) (i) mini/micro grids, (iii) small dams (iv) Irrigation systems/networks (v) Biogas Digestors | Planned |  | 28PWS | 35 Piped Water Systems | 36 Piped Water Systems UNDP-1 PWS -Chipinge 1 mini/micro grids-Chipinge, -UNDP 0 small dam 2 Irrigation systems/networks- Chipinge 1ha, Mlibizi 20ha UNDP | 195 38 Piped Water Systems (2 UNDP) 1 mini/micro grids- UNDP 1 small dam- UNDP 5 Irrigation systems/networks - UNDP 150 Biogas Digestors-UNDP | 200 40 Piped Water Systems (4 UNDP) 1 mini/micro grids, UNDP 1 small dam UNDP 8 Irrigation systems/networks UNDP 150 Biogas Digestors-UNDP | (i) The Theory of Change hypothesizes that installing climate resilient water abstraction and irrigation infrastructure is a foundational step in improving the climate resilience of the targeted communities. (ii)The Implementing Partner will analyse this data to report against the logframe, examining trends over time and comparisons to baseline, where applicable. Depending on needs or requests, data may be compared with data from other sources to benchmark or compare reach, impact or similar.
|  | Achieved | 28 PWS | 28 PWS | 35 Piped Water Systems | 172 UNDP-137 1 PWS-Binga 120 Biogas Digestors- (90 Chipinge, 30 Chivi) 4 Irrigation systems Gardens -Binga 12 Solar Modules-Binga
Source:Progress UNICEF Final Report fro baseline. Reports & Infrastructure completion certificates
| Output Indicator 1.2 |  | Baseline | Milestone 1 (February 2022) | Milestone 2 (February 2023) | Milestone 3 (February 2024) | Milestone 4 (February 2025) | Milestone 5 (November 2025)
| Proportion.of functional water and renewable energy infrastructure | Planned |  |  | 80% | 80% | 80% | 90% |  | Milestone 1 & 2 are against work that UNICEF has already delivered
|  | Achieved | Water: 67.6% Renewable Energy- 0 | 100% | 100% | 100%
Source:CAWEP Feasibility Study &Baseline reports (for baseline), Committee minutes, Project progress reports, RIDA, DDF, RDC reports
| Output Indicator 1.3 |  | Baseline | Milestone 1 (February 2022) | Milestone 2 (February 2023) | Milestone 3 (February 2024) | Milestone 4 (February 2025) | Milestone 5 (November 2025)
| Proportion of water and renewable energy infrastructure with a community management structure and business model for maintenance | Planned |  |  | 80% | 80% | 80% | 90%
|  | Achieved | Water- Management structure- 91%, Management Structure +Business Model- 0 Renewable Energy- 0 |  | 100% | 100%
Source:CAWEP Feasibility Study & Baseline reports (for baseline), Committee Registers, constitutions, Project progress reports
IMPACT WEIGHTING (40%)
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Milestone 1 (February 2022) | Milestone 2 (February 2023) | Milestone 3 (February 2024) | Milestone 4 (February 2025) | Milestone 5 (November 2025) | Assumptions Community interest and leadership. Continued local level government support. Enabling environment for women participation on decision making and governance. Community capacity and appropriate trainings Improved knowledge and capacity leads to changes in practice and action. Technical Skills and business trainings are utlised and translate into sustainable enterprises Economic Environment is conducive for the establishment of viable enterprises Enabling environment fro women and youth participation in economic activiries Private sector and finance institutions are willing to partcipate and provide services for tragetted rural communities | Working Notes
Established/resuscitated community governance structures are effective in managing installed infrastrcuture. | Number of governance structures trained to operate, manage, and maintain installed infrastructure are operational. Disaggregated by (i) community/ districts | Planned |  | 28 PWS | 35PWS | 8 AMCs | 10 AMCs | 10 AMCs | (i) The Theory of Change hypothesizes that by providing water, power (where applicable) and capacity building to the community, it will increase the economic opportunities to community members to improve their livelihoods. These improved livelihoods will (i) allow the communities to pay for their use of water and power, which contributes to the maintenance of the utility infrastructure, and (ii) improves the climate resilience of the community. Having representative community structures to oversee the financial and maintenance aspects of the infrastructure is a central component of ensuring this community empowerment. (ii) The Implementing Partner will analyse this data to report against the logframe, examining trends over time and comparisons to baseline, where applicable. Depending on needs or requests, data may be compared with data from other sources to benchmark or compare reach, impact or similar. | Milestones for indicator 2.1 set based on 10 committees at Hakwata (8 for the solarised boreholes, 1 for the solar mini grid, 1 for the garden), 5 at Wanezi (for the water points at the clinic, school and community then 1 for the dam and 1 for irrigation), Mlibizi 6 (1 clinic, school, community water system, 2 irrigation) and 1 committee for Gororo. These will need to be updated in due course after the new scope of work at Wanezi and Mlibizi has been defined. Committees may increase depending on the # of infrastructure eg if the drilling and solarisation of boreholes is to be done at Mlibizi (proposed +/_ 20) then more committees/ governance structures. For now we maintain the exisiting values for Wanezi and Mlibizi.
|  | Achieved | 28 PWS | 28 PWS | 35PWS | UNDP 9 AMCs Binga- 1 IMC, 5 Garden Committees Chipinge-1 Energy Committee Chivi-1 IMC Insiza-1 IMC
Source: UNICEF Final Report CAWEP Feasibility Study reports (for baselines), Committee Registers, Constitutions and Project Progress Reports
| Output Indicator 2.2 |  | Baseline | Milestone 1 (February 2022) | Milestone 2 (February 2023) | Milestone 3 (February 2024) | Milestone 4 (February 2025) | Milestone 5 (November 2025)
| Percentage of people in community governance structures who are women | Planned |  | 0 | 50% | 65% | 70% | 70%
|  | Achieved | 62% | 0 | 70%- UNICEF | 67%-UNDP
Source:CAWEP Feasibility Study & Baseline reports, Committee Registers, Constitutions and Project Progress Reports
| Output Indicator 2.3 |  | Baseline | Milestone 1 (February 2022) | Milestone 2 (February 2023) | Milestone 3 (February 2024) | Milestone 4 (February 2025) | Milestone 5 (November 2025)
| Percentage of representative community governance structures engage effectively with both community and external stakeholders, including maintenance service providers. Measured by No.of regular community & stakeholder meetings | Planned |  | 0 | 60% | 65% | 80% | 85%
|  | Achieved | 0% | 0 | 100%- UNICEF | 78%
Source:CAWEP Feasibility Study & Baseline reports, CAWEP Baseline report (for baseline), Project Progress Reports, Endline Survey
| Output Indicator 2.4 |  | Baseline | Milestone 1 (February 2022) | Milestone 2 (February 2023) | Milestone 3 (February 2024) | Milestone 4 (February 2025) | Milestone 5 (November 2025)
| %ge of the households that pay for water and/or power use/maintenance. Disaggregated by (i) community | Planned |  | 50% | 60% | 60% | 65% | 70%
|  | Achieved | water use 14.5% Water maintenance-49.3% Power use and Maintenance-0 Community Disaggregation Binga Water use- 47.7% Maintenance- 30.1% Chipinge Water use- 10.4% Maintenance- 84.7% Chivi Water Use- 0 Maintenance- 65.8% Insiza Water Use- 0 Maintenance- 14.3% |  | 80%- UNICEF | 100%- Water Maintenance Binga
Source: CAWEP Baseline Report (for baseline) ZINWA and REF Reports, Project progress reports
| Output Indicator 2.5 |  | Baseline | Milestone 1 (February 2022) | Milestone 2 (February 2023) | Milestone 3 (February 2024) | Milestone 4 (February 2025) | Milestone 5 (November 2025)
| Percentage of functional income generation/Business models to finance operation and maintenance in the targeted communities. | Planned |  | 0 | 50% | 50% | 70% | 90%
|  | Achieved | 0 |  | 90%- UNICEF | UNDP-100%
Source: CAWEP Baseline report (for baseline) ZINWA and REF Reports, Committee constituitionsProject progress reports
OUTPUT 2.1 | Output Indicator 2.1.1 |  | Baseline | Milestone 1 (February 2022) | Milestone 2 (February 2023) | Milestone 3 (February 2024) | Milestone 4 (February 2025) | Milestone 5 (November 2025)
| Number of women & youth-led enterprises established as a result of technical and business skills training. Disaggregated by (i)Type of training, (ii) Sex, (iii) Age, iv) Type of business | Planned |  |  |  |  | 40 Chipinge 10 Chivi 10 Binga 10 Insiza 10 | 40 Chipinge 10 Chivi 10 Binga 10 Insiza 10 |  | Measuring enterprises which are credit worth to access finance
|  | Achieved | 0
Source: : Portfolio reports from financial institutions
| Output Indicator 2.1.2 |  | Baseline | Milestone 1 (February 2022) | Milestone 2 (February 2023) | Milestone 3 (February 2024) | Milestone 4 (February 2025) | Milestone 5 (November 2025)
| Percentage of women-led enterprises accessing credit from financial institutions Disaggregated by (i) sex, (ii) Type of business | Planned |  |  |  |  | 50% | 55% |  | Measures women led enterprises accessing formal finance to understand the impact of the RLF on women and their capabilities to access finance regardless of gender related barriers
|  | Achieved | 0
Source: : Portfolio reports from financial institutions
| Output 2.1.3 |  | Baseline | Milestone 1 (February 2022) | Milestone 2 (February 2023) | Milestone 3 (February 2024) | Milestone 4 (February 2025) | Milestone 5 (November 2025)
| Percentage of youth-led enterprises accessing credit from financial institutions Disaggregated by (i) sex, (ii) Type of business | Planned |  |  |  |  | 30% | 40% |  | Measure of improvement of youth led which are high light to be start-ups or emerging enterprises accessing credit from the RLF to understand if barriers of entry in the financial market can be easy unlocked… youth predominately considered as high credit risk
|  | Achieved | 0
Source: : Portfolio reports from financial institutions
| Output 2.1.4 |  | Baseline | Milestone 1 (February 2022) | Milestone 2 (February 2023) | Milestone 3 (February 2024) | Milestone 4 (February 2025) | Milestone 5 (November 2025)
| No. of loans disbursed from the Revolving Loan Fund (disaggregated by gender) | Planned |  |  |  |  | 90 Female 45 Male 45 | 100 Female 45 Male 45 |  | To measure number of total loans disbursed and establish if there were any repeat loans. Measure of any loan defaults
|  | Achieved | 0
Source: : Portfolio reports from financial institutions
| Output Indicator 2.1.5 |  | Baseline | Milestone 1 (February 2022) | Milestone 2 (February 2023) | Milestone 3 (February 2024) | Milestone 4 (February 2025) | Milestone 5 (November 2025)
| Total annual value of loans disbursed to women and youth-led enterprises through the Revolving Loan Fund | Planned |  |  |  |  | 120000 | 150000 |  | Measuring of the total value of funding unlocked from financial institutions to support both women-owned and youth-owned enterprises
|  | Achieved | 0
Source: : Portfolio reports from financial institutions
| Output Indicator 2.1.6 |  | Baseline | Milestone 1 (February 2022) | Milestone 2 (February 2023) | Milestone 3 (February 2024) | Milestone 4 (February 2025) | Milestone 5 (November 2025)
| Percentage of Portfolio at Risk (PAR) | [5 empty] | 5% | 5% |  | Measure of the value of the outstanding balance of all loans in arrears (principal)
TBA
Source: : Portfolio reports from financial institutions
IMPACT WEIGHTING (30%)
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | Milestone 1 (February 2022) | Milestone 2 (February 2023) | Milestone 3 (February 2024) | Milestone 4 (February 2025) | Milestone 5 (November 2025) | Assumptions Community, institution capacity & appropriate, applicable training EWS data is appropriate, applicable, & easily understood by community Multi stakeholder approach to EWSs. | Working Notes
Enhanced Early Warning Systems (EWS), helping vulnerable communities to better anticipate, plan and respond to negative impacts of climate change and extreme weather events | Number of districts/communities that receive EWS strengthening support from CAWEP. Disagregated by type of support e.g Hardware (Equipment), Software (Training) | Planned |  |  | 0 | 16 Chipinge Chimanimani Buhera Makoni Mutasa Nyanga Binga Insiza Lupane Hwange Bubi Umguza Nkayi Chivi Tsholotsho Mutare | 16 Chipinge Chimanimani Buhera Makoni Mutasa Nyanga Binga Insiza Lupane Hwange Bubi Umguza Nkayi Chivi Tsholotsho Mutare | 16 Chipinge Chimanimani Buhera Makoni Mutasa Nyanga Binga Insiza Lupane Hwange Bubi Umguza Nkayi Chivi Tsholotsho Mutare | (i) The Theory of Change hypothesizes that installing EWS and related training within the communities is a foundational step in providing information to the communities that allow them to make decision regarding adaptation to climate change thus improving their climate resilience (ii) The Theory of Change hypothesizes that by providing EWS systems, data will be available to the communities regarding impending climate events, understanding this data is the first step to developing actionable plans to adapt to these climate events. For these actionable plans to be developed this data needs to be interpreted into information and then into messaging which is communicated to the community members in an understandable manner using appropriate communication methods and vehicles.
|  | Achieved | 0 |  | 0 | 16
Source: MSD & DCP Reports, Project progress reports, Database
| Output Indicator 3.2 |  | Baseline | Milestone 1 (February 2022) | Milestone 2 (February 2023) | Milestone 3 (February 2024) | Milestone 4 (February 2025) | Milestone 5 (November 2025)
| Number of people that regularly (monthy) receive and understand weather & climate information | Planned |  | 0 | 0 | 100000 Chipinge (40000) Binga (40000) Insiza (10000) Chivi (10 000) | 300000 Chipinge Chimanimani Buhera Makoni Mutasa Nyanga Binga Insiza Lupane Hwange Bubi Umguza Nkayi Chivi Tsholotsho Mutare | 544130 Chipinge Chimanimani Buhera Makoni Mutasa Nyanga Binga Insiza Lupane Hwange Bubi Umguza Nkayi Chivi Tsholotsho Mutare
|  | Achieved | 0 |  | 0 | 172554 Chipinge-10074 Binga-58086 Chivi-7626 Insiza-59538 Bubi- 2622 Buhera-336 Hwange-8064 Lupane -3540 Makoni-1998 Nkayi-18000 Tsholotsho-270 Umguza-2700
Source: MSD & DCP Reports, Project progress reports, Database
IMPACT WEIGHTING (20%) |  | Source
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 4 | Output Indicator 4.1 |  | Baseline | Milestone 1 (February 2022) | Milestone 2 (February 2023) | Milestone 3 (February 2024) | Milestone 4 (February 2025) | Milestone 5 (November 2025) | Assumptions Improved knowledge and capacity leads to changes in practice and action. Government and partners are willing to use and apply the knowledge generated from the analytical tools in its policy making decisions. Improved knowledge and capacity leads to changes in practice and action | Working Notes
Improved National Climate adaptation policies/Strategies/learning material supported/developed | Number of policies or strategies developed/supported as a result of programme influence. Disaggregated by Type e.g specific policy, strategy, learning paper,operational manuals | Planned |  | 0 | 2 | 3 (NAP, Piped Water Scheme Protocol, Energy Efficiency Policy. | 4 (NAP, Piped Water Scheme Protocol, Energy Efficiency Policy, water policy) | 5 (NAP, Piped Water Scheme Protocol, Energy Efficiency Policy, water policy, National Clean Cooking Strategy/Framework) | The theory of change hypothesises that by providing technical support & advocacy to improve policy context for climate adaptation & improve renewable energy investment opportunities, there will be increased capacity at community, local and national levels to adapt & respond to increasing risks of climate change, increased investment in disaster preparedness, technical efficiency in climate sensitive services,increased uptake of renwable energy technologies, integrated water resources management & climate risk screening, leading to an improvement in transformative capacities and resilience. | Through CAWEP, the project will influence and raise awareness on NAP/National Clean Cooking Strategy/framework, Water policy and Energy Efficiency Policy.
|  | Achieved | 0 | 0 | 0 | 3 1 (NEEP Policy finalised) 1 Clean Cooking Strategy draft produced 1 NAP sensitization for National Level Government Ministries
Source: Policy and Strategy Documents
| Output Indicator 4.2 |  | Baseline | Milestone 1 (February 2022) | Milestone 2 (February 2023) | Milestone 3 (February 2024) | Milestone 4 (February 2025) | Milestone 5 (November 2025)
| Number of policy briefs developed using evidence generated by the programme to influence upscaling or changes to different approaches to climate adaptation/resilience | Planned |  | 0 | 0 | 0 | 2 | 3
|  | Achieved | 0 | 0 | 0 |  |  |  |  | Indicator aligned to ICF KPI 15 contributing to transformational change
Source: CAWEP Policy and Strategy Documents
IMPACT WEIGHTING (10%)
Planned
Achieved
Source
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£)
INPUTS (HR) | FCDO (FTEs)

## Change frame
Use this change log to record all changes to the logframe over the life of the project.
ID | LOGFRAME SECTION | DETAILS OF CHANGE | AUTHOR | DATE
E.g. | Output 1, Indictor 2 | Indicator amended from 'No of children enrolled in primary schools' to 'Number of children enrolled in UNICEF supported primary schools (disagregated by sex) | Joe Bloggs | 2018-01-01
1 | Outcome1, Indicator 1.2 | Indicator amended from "Number of people with improved access to clean energy as a result of set up/connected to solar micro/minigrids/Solar Home systems. Disaggregated by (i) community (ii) sex (iii) age (iv) disability" to 'Number of people with improved access to clean energy as a result of set up/connected to solar micro/minigrids/Solar Home systems/Biogas Digestors. Disaggregated by (i) community (ii) sex (iii) age (iv) disability' | Fadzai Ncube | 2023-06-15
2 | Outcome1, Indicator 1.1 | Indcator amended from "Number of people supported to better adapt to the effects of climate change through sustainable access to solar powered multiple water use systems, Disaggregated by sex" to "Number of people supported to better adapt to the effects of climate change through sustainable access to solar powered multiple use water systems, Renewable Energy and Early Warning Systems Disaggregated by sex" | Fadzai Ncube | 2023-10-26
3 | Output 1, Indictor 1.1 | Added (v) Biogas Digestors | Fadzai Ncube | 2023-12-31
4 | Impact Indicator 1 | Indicator Amended from "%ge of targeted households with an improved resilience score. This will be assessed by %ge.of communities in vulnerable districts being able to recover during/post climate shocks using water, clean renewable energy and access to weather/climate info and avoid complete loss of livelihoods and access to health and education". to "Number of people whose resilience has been improved" to align with ICF KPI1 on Resilience | Fadzai Ncube | 2024-04-19
5 | Outcome Indicator 1.1 | No Changes. However, Calculation to include Indirect Beneficiaries. Indirect Beneficiaries to be derived from, Village, Ward and District Population figures. For AWS MSD to provide acceptable radius of Indirect reach for AWSs. Indicator Definition to be updated accordingly. | Fadzai Ncube | 2024-04-19
6 | Outcome Indicator 1.2 | LOP Target increased to 20000 from 12499, Feb 2025 Target increased from 6000 to 20000. Indicator updated to include "Solarised Social Institutions" | Fadzai Ncube | 2024-04-19
7 | Outcome Indicator 1.3 | LOP Target increased to 82 from 70, Feb 2025 Target increased from 70 to 82. Indicator updated to include Solarisation of AGRITEX offices/Homes to facilitate data download and dissemination of EWS. | Fadzai Ncube | 2024-04-19
8 | Output Indicator 1.1 | LOP Target Increased from 40 to 200. Feb 2025 Milestone increased from 40 to 195 | Fadzai Ncube | 2024-04-19
9 | Output Indicator 2.1 | LOP Target increased from 7 to 10 | Fadzai Ncube | 2024-04-19
10 | Output Indicator 2.5 | Indicator wording changed from "%ge of targeted communities with a functional income generation/Business model to finance operation and maintenance" to "Percentage of functional income generation/Business models to finance operation and maintenance in the targeted communities". This will measure percentage of Output indicator 1.3 result that is functional. | Fadzai Ncube | 2024-04-19
11 | Output Indicator 2.3 | LOP Target increased from 70% to 85%. Feb 2025 milestone increased to 80% | Fadzai Ncube | 2024-04-19
| Outcome Indicator 1.6 | Percentage of businesses/ enterprises demonstrating sustainable growth as a result of access to solar powered multiple use water systems, Renewable Energy Disaggregated by (i) Solar Mini Grid, (ii) Irrigation Systems, (iii) Sex, (iv) Age- New Indicator | Fadzai Ncube | 2024-04-19
| Outcome Indicator 1.7 | Number of green jobs created or improved as a result of developed/rehabilitated multi purpose water and clean energy infrastructure Disaggregated by (i) Type, (ii) sex | Fadzai Ncube | 2024-04-19
| Output 2.1 | New Sub Output of Output 2.
| Output Indicator 2.1.1 | Number of women & youth-led enterprises established as a result of technical and business skills training. Disaggregated by (i)Type of training, (ii) Sex, (iii) Age, iv) Type of business | Fadzai Ncube | 2024-04-19
| Output Indicator 2.1.2 | Percentage of women-led enterprises accessing credit from financial institutions | Fadzai Ncube | 2024-04-19
| Output Indicator 2.1.3 | Percentage of youth-led enterprises accessing credit from financial institutions | Fadzai Ncube | 2024-04-19
| Output Indicator 2.1.4 | No. of loans disbursed from the Revolving Loan Fund (disaggregated by gender) | Fadzai Ncube | 2024-04-19
| Output Indicator 2.1.5 | Total annual value of loans disbursed to women and youth-led enterprises through the Revolving Loan Fund | Fadzai Ncube | 2024-04-19
| Output Indicator 2.1.6 | Percentage of Portfolio at Risk (PAR) | Fadzai Ncube | 2024-04-19

## Guidance Notes
Smart Guide
Teams should use the guide below to complete the logframe template.
PROJECT TITLE
A meaningful, easily understood (plain English) Project Title.
IMPACT
Long term goal to which the project will contribute towards achieving. When drafting the impact statement, consider how your project fits with other efforts from FCDO and partners to achieve the impact, ie is your project nested within a broader undertaking?
OUTCOME
The outcome of your project identifies what will change, who will benefit and how it will contribute to reducing poverty, including contributions to the Millenium Development Goals (MDGs) or Climate Change.
An assessment of whether your project achieved the Outcome will be included in the Project Completion Review (PCR). Ongoing monitoring of progress against outcome milestones should still take place as an assessment of whether you expect to achieve the Outcome by the end of the programme will be included in Annual Reviews.
OUTPUTS
Outputs are the specific, direct deliverables of your project. These will provide the conditions necessary to achieve the Outcome. The logic of the chain from Output to Outcome therefore needs to be clear.
Progress against Output milestones and results achieved will be assessed and scored during Annual Reviews and the Project Completion Review.
IMPACT WEIGHTING
Once you have defined your Outputs, assign a percentage for the contribution each is likely to make towards the achievement of the overall Outcome.
The impact weights of all the Outputs will total 100% and each are rounded to the nearest 5%.
Impact weightings for Outputs are intended to:
l | Promote a more considered approach to the choice of Outputs at project design stage; and
l | Provide a clearer link to how Output performance relates to project Outcome performance.
INPUTS
Clarification of inputs is a key part of results-chain thinking. Inputs are specified at the country-level in country operational plans and the project information contained in logframes should feed up into these.
The input-level boxes show the amount of money provided by FCDO and any partners (£) including, where relevant, the government’s own contribution. This only relates to monetary (not in kind) contributions. At Outcome level this is equal to the sum of Inputs for all Outputs. The FCDO share at Outcome Level is a simple, pro rata calculation of DFID’s contribution in monetary terms for all outputs.
Information should also be provided for the total number of Annual DFID Full-Time Equivalents (FTEs) allocated to this project, based on the time individual staff members will spend on the project. It is understood that this may change through the project cycle, and is intended as a management tool.
INDICATORS
Indicators are performance measures, which tell us what will be measured not what is to be achieved. Avoid including elements of the baseline or target.
What makes a good indicator?
l | Specific – what will be measured? And how?
l | Measurable - data can be collected
l | Relevant - to the results chain
l | Useful – for management decision making
l | Does not include any element of the target
l | Can be disaggregated if relevant
l | Good mix of qualitative and quantitative
l | Already defined - if relevant include indicators which towards the DRF / OP / ICF KPIs / MDGs.
l | Consider using standard indicators / best practice indicators / learning from other projects
The basic principle is that “if you can measure it, you can manage it”.
Top Tip – select indicators based on relevance to the Results Chain and the availability of data.
Best Practice suggests a maximum of three Indicators per Output.
Some example indicators for a WASH project are shown below.
BASELINE
Baselines set the starting point and provide a measure of the situation before your project starts (could be zero if a new project).
The baseline is used to measure change and monitor progress.
Include a baseline for each of your indicators. The first 6 months of a project may exceptionally be used for assembling baseline data at output level if agreed by your PRO.
Use existing data where possible, but check reliability and seek assurances regarding the data quality eg use data from national statistical systems / MIS.
If you need to collect your own data - collect baseline data early – as soon as beneficiaries have been identified but before any results are expected.
MILESTONES
Milestones are the desired trajectory from baseline to target, helping you to track progress and make changes to underperforming areas.
Will depend on sequencing of activities and data availability.
Include REALISTIC milestones given resources and capacity.
At the output level include annual milestones for each year of the project (or monthly if short term). At outcome & impact level data may not be available annually.
TARGET (DATE)
Targets set the desired point, showing what is achievable within the timeframe available.
The target is often the last year of the project (or month if its short term).
Include realistic targets given resources and capacity, the baseline situation, funding available and country/operational context. Project targets might be informed by evidence about what has worked in the past and take into account lessons learned from other projects.
Include targets dissaggregated by sex/geography/income etc where appropriate.
Consider using government targets although if they are too ambitious then make a more realistic estimate.
Top Tip - A good Theory of Change will help you think about what is realistic and achievable as it will enable critical reflection of context, external influences & assumptions.
SOURCE
Each Indicator will have a data source to verify the results achieved.
List the specific data sources i.e. give the specific data collection e.g. named survey / report and avoid just naming the organisation.
State the frequency of the data source and ensure consistency with milestones and targets.
Check the source can provide disaggregated data as required.
Consider and specify the data collection and reporting responsibilities to ensure the results planned and forecast rows in the logframe are updated on a regular basis.
Top Tip - Before using a data source, assess its quality and seek assurances from data providers where needed ie consider its validity, reliability and availability.
ASSUMPTIONS
Define any assumptions which are linked to the realisation of your project's individual outputs, as well as those which are critical to the realisation of the outcome and impact: these will not all be the same.
VALUE FOR MONEY
Ensure the outputs and outcome projected represent good value for the invested resources, at the beginning of the project, and through its life.
Consider including VfM metrics in the logframe (or other documents such as the Delivery Plan) to allow VfM to be measured through the life of the project and to provide assurance at Annual Review.
VfM is achieved at different stages of the results chain. Thus for each result we seek to achieve we should aim to have metrics for each of the following:
Economy - Are we (or our agents) buying inputs of the appropriate quality at the right price?
Efficiency - How well are we (or our agents) converting inputs into outputs? (‘Spending well’)
Effectiveness - How well are the outputs produced by an intervention having the intended effect? (‘Spending wisely’)
Cost-effectiveness - What is the intervention’s ultimate impact on poverty reduction, relative to the inputs that we or our agents invest in it?
FCDO’s Approach to Value for Money (PrOF Guide) provides further advice on ensuring VfM.