ADDENDUM TO BUSINESS CASE

INCLUDING FOR BRIDGE FUNDING AND SCALE-UP COST EXTENSIONS

SUMMARY INFORMATION
Project Name	St Helena Economic Development Investment Programme (300714)
Country or region targeted	St Helena Overseas Territories
Type of cost extension (if applicable)	No Cost Extension
Original project budget	£30,000,000
Original project start and end dates	21/06/2019 – 31/03/2025
Cost extension value (if applicable)	n/a
New reduced budget (if applicable)	n/a
New project end date (if applicable)	31/03/2028
Business Case Teams	EDIP Business Case (Final).docx

INFORMATION
What is the project’s purpose?
The purpose of the current Capital Programme is to invest in critical infrastructure required for economic development and expansion of the private sector. Current low revenue potential constrains the St Helena Government’s (SHG’s) ability to undertake infrastructure development without UK financial assistance.
What is the objective of the no cost extension or other changes?
The proposed no cost extension of three years is intended to allow SHG to make full use of the current financial allocation under EDIP, as recommended by a recent independent breakpoint review of the programme. SHG has demonstrated a lower capacity to implement projects than originally anticipated, which combined with irregular shipping schedules and the impact of COVID-19 has resulted in slower delivery of project activities under EDIP. This has been exacerbated by procurement delays, a small supplier base on St Helena, and long lead-times on project development. The no cost extension will allow for the delivery of a newly endorsed pipeline of projects, including renewable energy and water security projects and the construction of a new prison facility, as well as the continued development of St Helena’s project management and delivery capacity.
What is the additional and total support the UK will provide?
There is no additional support required. The total support remains at £30,000,000
What are the expected results?
EDIP’s recently approved project pipeline prioritises: / A new wastewater facility for Half-Tree Hollow and Jamestown / A new prison facility to replace the current [non compliant and full] prison / An out-of-town industrial and storage complex (eco-storage park) / Completion of improved cargo and freight facilities in Rupert’s Valley / Completion of improved road infrastructure around Rupert’s Valley and Jamestown / The development of a new water resource management plan / Renewable energy design works and ‘quick win’ implementation of elements of this design / These projects are intended to meet St Helena’s critical infrastructure needs as well as improving the economic prospects of the island, including the attractiveness for private sector investment. The no cost extension will allow the delivery of these projects in a realistic timescale, in parallel with further development of St Helena’s project management and delivery capacity.
What is the approach to implementation?
Projects are to be funded by FCDO via SHG, where SHG is responsible for procurement and project delivery except where it is necessary for FCDO to directly procure services on behalf of SHG. Where possible projects will be delivered by local suppliers. All projects under EDIP fall under authority and oversight of the joint FCDO-SHG governance structure, comprised of an EDIP Programme Board and a strategic level Steering Committee. SHGs delivery is agreed through an MOU with FCDO which will be updated following approval of this addendum. / The UK based programme team, including infrastructure and economics advisors, alongside the St Helena based Governor’s Office, will support SHG in the design and management of projects, including facilitation of access to broader UKG expertise where necessary.
Describe any key changes to the original business case including the theory of change or new evidence from ongoing monitoring, evaluation or learning work?
There are no significant changes to the original business case or theory of change. This extension is necessary to account for the slower pace of delivery, due to low capacity of project implementing partners and small construction sector on St Helena. A new pipeline of projects has been developed for the remainder of the programme, and has been approved by SHG and EDIP governance bodies. Although progress has been slower than originally envisioned, the new governance process is working well and confidence in the partnership, and in project delivery, is building. The breakpoint review made a series of practical recommendations for programme improvement which have been actioned. / Some minor changes to the initial Theory of Change include: / The reconstitution of governance mechanisms to allow for more effective decision making / The compact described in the theory of business case has not been developed / Potential private sector interest and participation is limited by St Helena’s small economy / Economic development following the opening of the St Helena Airport has not yet met predicted levels, in part due to disruption caused by the global pandemic. / The programme has also expanded, as recommended in the breakpoint review of 2022, beyond an economic development focus to also consider infrastructure facilitating social development.