Programme Completion Review

Title: Peacebuilding Opportunities Fund (POF), South Sudan
Final Programme Spend £ (full life): £5,464,452.23	Review Date:	January 2024
Programme Code: 300676	Start Date: July 2019	End Date: December 2023

Summary of Programme Performance

Year	2019	2020	2021	2022	2023
Programme Score	A	B	A	A	A
Residual Risk Exposure Rating	Major	Major	Major	Major	Major

DevTracker Link to Business Case (and any addendum):	DevTracker Programme GB-GOV-1-300676 Documents (fcdo.gov.uk)
DevTracker Links to all logframes used during programme lifetime:	DevTracker Programme GB-GOV-1-300676 Documents (fcdo.gov.uk)

Description	Score
Outputs substantially exceeded expectation	A++
Outputs moderately exceeded expectation	A+
Outputs met expectation	A
Outputs moderately did not meet expectation	B
Outputs substantially did not meet expectation	C

A. Summary and Overview

Description of the programme and what it has achieved

The Peacebuilding Opportunities Fund (POF) in South Sudan was delivered from July 2019 to December 2023. POF was a context-driven programme aimed at reducing violence between communities in targeted areas.

POF sought to support efforts of South Sudanese institutions and groups that showed signs of success in reducing conflict and promoting positive civic attitudes and practices (‘peacebuilding opportunities’). This included facilitating inter- and intra- community peace dialogues. POF was a flexible and adaptive programme. It delivered five outputs:

1. evidence-based analysis and learning to drive and review decision-making;
2. engaging with local actors in the conflict system, targeting those who can most influence conflict, especially cultural and traditional actors;
3. incorporating sustainability into its implementation approach;
4. strengthening coordination and engagement between diverse local actors to promote peace and responsiveness to conflict triggers; and
5. identifying and implementing activities across locations and funding windows.

The context in which POF operated changed over the delivery period. POF was initiated just after the Revitalised Agreement on the Resolution of the Conflict in the Republic of South Sudan (R-ARCSS) was signed in September 2018. This brought an end to South Sudan’s five-year national civil war, though violent localised conflict persisted. The COVID-19 pandemic also caused operational constraints during which time the POF team were able to keep the delivery of the programme going in a very challenging and uncertain context. Given the shifting and uncertain context, POF maintained flexibility in its implementation, as reflected in its adaptive results framework.

POF was initially a 2-year programme from July 2019 to June 2021 with a full life value of up to £3,200,000. It was extended to 4.5 years ending December 2023 with a full life value of £5,465,927. The procurement of the programme was a competitive process under the CSSF framework.

The programme was originally co-funded by the Conflict Security and Stability Fund (CSSF) and the Department for International Development (DFID), managed by DFID South Sudan. The Foreign Commonwealth & Development Office (FCDO) took over its management through the British Embassy Juba (BEJ) in 2020. Uncertainty over FCDO budget allocations resulted in four cost extensions. This had the benefit of enabling a smooth transition between POF and its new second phase, POF2.

The delivery approach and model of POF changed over the course of the programme. It was initially implemented by a consortium led by Oxford Policy Management Limited (OPM) with CAFOD & Trócaire in Partnership (CTP) (CTP) and Forcier Consulting. In 2021 OPM established Peace Canal, a national non-governmental organisation (NNGO), and worked as their sole funding partner. As a result, the role of OPM as the original grant-making ‘fund manager’ model, as set out in the business case, shifted to an ‘advisory-led’ model offering partnership and capacity building to local actors and processes.

The original business case stated that the POF would focus on two geographies at a sub-national level. Following the inception phase OPM proposed to expand geographical coverage to four areas, with the same budget, to maximise learning across a wider range of project locations, and to minimise the risk to programme learning if one project site should become inaccessible. Expanding geographical coverage remained within the budget envelope and therefore was assessed as demonstrating strong value for money (VfM). During the inception period, POF and British Embassy Juba (BEJ) selected four geographical areas in which there were high levels of localised violence as the focus of the programme: Rumbek (Greater Rumbek in Lakes State), Torit (Eastern Equatoria State), Bor (Jonglei state), and Bentiu (Unity State). In the inception period an uplift from the original contract value of £2,765,927 to the approved business case value of £3,200,000 was agreed in principle to meet the geographical scope in the inception report. The reduction in the Department for International Development’s overall budget in 2020 meant the uplift did not happen. In 2021, as part of a time and cost extension of the programme, a case was made to continue programme delivery in Rumbek and Bor only. The annual review of POF in 2020 recommended reviewing the VfM of targeting four areas. Expanding to four areas had initially been assessed as demonstrating good value for money because this was delivered with the same budget originally intended for two areas. However, further assessment highlighted the potential risk that this stretched resources and diluted effectiveness and the proposed budget uplift did not go ahead due to the impact of COVID-19. Rumbek and Bor were assessed as the locations where POF had the most traction and so POF focused resources on building on their achievements and deepening the relationships that had been established. Activities therefore ceased in in Bentiu and Torit in 2021.

In Jonglei / GPAA, the POF’s key achievements included the groundbreaking 2021 Pieri Peace Agreement between the Lou Nuer, Murle and Dinka Bor communities, with the Gawaar Nuer community joining later. The agreement provided a new foundation for peace between communities of Jonglei / GPAA and remains the key reference point for local communities and peace and humanitarian partners. POF remained involved in the management of the agreement in order to ensure its longevity.

In Rumbek, POF created the Akut de door project where armed youth leaders, previously perpetrators of conflict, became ambassadors and managers of dispute resolution. POF’s intra-Agar cattle migration dialogues significantly reduced violence and killing, resulting in the peaceful migration of around one million cattle annually without death or injury to community members or cattle-keepers for three years in a row (2020-2023). Before POF, between 2011-2020, there were 307 deaths and 279 people injured in intra-Agar violence; averaging 34 deaths and 31 injuries a year. Since the 2020 cattle migration conference there have been less than 10 deaths and 10 injuries on average per year, and none registered during the migration.

Peace Canal has built a strong reputation amongst peacebuilding partners and has influenced the peace building programmes of other partners. Due to Peace Canal’s success in reducing inter-communal violence, partners including the UN World Food Programme (WFP), the UN South Sudan Reconciliation, Stabilisation and Resilience Trust Fund (South Sudan RSRTF), and the USAID Shejeh Salam programme, adopted some of POF’s design and delivery approaches.

Overall POF made good progress on the programme’s outcomes. While outcome indicators were not fully achieved over the life of the programme, POF made a strong contribution to reducing violence and insecurity in the areas targeted, despite the contextual challenges. It led to improved community perceptions that leaders were effective at reducing conflict, and good progress on inclusive interaction and collaboration between key institutions. POF enhanced South Sudanese capacity to resolve potential conflicts without resorting to violence, which consequently resulted in a reduction in violence in the areas targeted. POF also improved community perceptions of safety and of reduced conflict impact in programme locations.

The programme has scored consistently well in Annual Reviews. In 2021 a FCDO team external to BEJ conducted the annual review. The programme met expectations in 2019, 2021, and 2022, scoring an A each year. In 2020 the programme scored a B. It only partially met outcome expectations, due to a longer than envisaged inception phase and challenges in understanding programme achievements. In 2022 Forcier conducted an external evaluation, which found some progress towards the programme outcomes, however there was a mixture of progress in the different locations. An additional independent gender-sensitive review was also conducted by the FCDO Women, Peace and Security (WPS) Helpdesk in 2023, which found that POF activities had a positive effect on women’s participation in peace processes, however barriers including harmful gender norms remained persistent.

POF met the targets for its outputs over the lifetime of the programme and scored an A.

In this Programme Completion Review (PCR) POF scored an A for all outputs. POF was successful in incorporating knowledge into its activity design and using iterative stakeholder consultations to strengthen implementation. POF acted on learning by adapting workplans and producing lessons-learnt papers and concept notes. POF mapped its project locations and updated this to capture lessons and changing contexts through conflict monitoring reports and mapping stakeholders and systems. POF incorporated sustainability into the programme through its establishment of an NNGO and supporting peace dialogues, although full sustainability was not achieved in the lifetime of the programme. POF frequently interacted with relevant and diverse actors and built relationships with key stakeholders to ensure community-led design of peace dialogues and activities.

Major lessons learned, evidence generated and recommendations

The key themes for lessons learnt and recommendations over the life of the programme included:

Working with other organisations. Evidence of what works from POF supported other partners’ programming, and collaboration with other organisations. This included the Conflict Sensitivity Resource Facility (CSRF), WFP, the International Organisation for Migration (IOM), and Nonviolent Peaceforce by contributing to papers, producing new evidence papers and engaging in the design of programmes. It was clear from stakeholder interviews that POF had built a strong reputation. Stakeholders suggested that the second phase POF should consider how to engage partners more strategically and increase engagement with women’s rights organisations.

Adaptive programming and gender. POF was an adaptive programme, which enabled it to take advantage of emerging opportunities and respond quickly to threats of escalating violence. The second phase of the programme should build on this success. Challenges in tracking and monitoring gender equality should be addressed in the second phase.

Capacity building. A central part of POF’s sustainability and exit strategy was the creation of the National NGO Peace Canal. POF had an ‘accompaniment’ approach. The approach is defined by building local and national capacity through long-term partnerships. The second phase of the programme should expand on this.

Increased focus on Peace dividends and livelihoods. To address some of the socio-economic drivers of conflict and generate peace dividends, learning from the implementation of POF suggests a need to invest in climate-sensitive livelihoods in addition to peace dialogue processes. The target areas of POF were characterised by weak cattle trading systems, lack of access to markets due to poor infrastructure, and subsistence farming methods vulnerable to climate change. Generating peace dividends through livelihoods programming is likely to encourage communities' engagement in peacebuilding.

Working with BEJ. The programme helped inform BEJ strategy and engagement. BEJ has been able to draw from POF’s knowledge and network to identify emerging conflict dynamics and support its engagement with key South Sudanese Government interlocuters. The programme also supported the BEJ’s Joint Analysis of Conflict and Stability (JACS) renewal. There is scope for further collaboration and to expand its role supporting BEJ’s broader strategic engagement. Increased coordination with other BEJ programming would also be beneficial, for example programming addressing gender-based violence.

Safeguarding. There is a high risk of sexual exploitation, abuse and harassment (SEAH) in South Sudan. BEJ and POF should work with partners to strengthen the programme’s approach to safeguarding in the second phase. This should take into consideration challenges in reporting cases due to access to standard reporting mechanisms and the stigma associated with being a survivor of SEAH.

The key recommendations to take forward to the second phase of POF are:

Recommendation 1: POF’s approach to community and evidence-based peacebuilding started to gain traction over the course of the programme with evidence of influencing other partners’ programming. For the second phase, the evidence from this approach should be disseminated more widely, and POF should share learning and coordinate with other partners in South Sudan on peacebuilding activities and peace dividends.

Recommendation 2: The second phase of the programme should build on POF’s adaptive programming approach and incorporate a rapid response mechanism for emerging conflicts. POF had a successful approach to analysing the situation on the ground and they should use this to respond quickly to unexpected local violence.

Recommendation 3: The second phase of the programme should ensure that gender equality and social inclusion is maintained throughout implementation and is well-documented in programme documents, including the results framework.

Recommendation 4: The second phase of the programme should ensure that a results framework is in place that meets the needs of an adaptive programme, whilst also ensuring that there is a clear link between outputs and outcomes and a clear way to track outputs with specific, measurable, achievable and timebound (SMART) indicators.

Recommendation 5: BEJ should consider how to utilise POF analysis to inform strategic and political thinking, and POF should make suggestions on what the BEJ team can do to support their work in the field such as strengthening collaboration between partners.

Recommendation 6: POF2 should use its accompaniment approach to support more NNGOs to become effective and self-sustaining, thereby increasing peacebuilding NGOs in target areas.

Recommendation 7: POF should work with partners to ensure that there are robust, community-based reporting and support mechanisms for SEAH, and strengthen the programme’s safeguarding approach.

Recommendation 8: Where appropriate, POF should increase engagement with women’s rights organisations, to expand women’s meaningful participation in peace processes further.

Recommendation 9: BEJ should also look for opportunities for the second phase to coordinate more effectively with other BEJ programmes, including resilience and gender programmes.

Recommendation 10: For the second phase of the programme, BEJ and POF should consider more engagement with BEJ conflict, gender, livelihoods and results advisers.

How this report was conducted

This PCR was carried out by a BEJ team, including the Conflict Adviser, Senior Programme Manager, and Programme Officer. Stakeholder interviews were carried out by the POF team, Peace Canal, CAFOD & Trócaire in Partnership (CTP), the Conflict Sensitivity Resource Facility (CSRF), United Nations (UN) organisations, including WFP with whom POF worked closely, and the programme Senior Responsible Owner (SRO). The programme team reviewed: annual reviews, the business case and its addendums, POF reports and publications, the results framework, and the risk register.

Actions following approval of this report

Lessons learnt and recommendations from the PCR will be used to inform the second phase of the POF, as part of the overarching South Sudan Peacebuilding Programme. The second phase of POF is from October 2023 – October 2026. Learning will be shared across BEJ and other FCDO teams, such as the Conflict Cadre and the Office for Conflict Stabilisation and Mediation as a successful example of an innovative approach to local level peacebuilding. BEJ/FCDO will also share learning with external partners.

## B: Theory of Change and Outcome Assessment

	Starting point	Final result
Budget	£3,200,000	£5,465,927
Timeframe	July 2019 – July 2021	July 2019 – December 2023
	Outcome 1: Targeted communities are more harmonious and resilient to conflict.
	Indicator 1.1: Contribution of POF activities on reported frequency of violent conflict and/or insecurity since start of targeted activity / Indicator 1.2: Contribution of POF activities on respondents’ perceived likelihood of conflict with other groups	POF met expectations. It contributed to reducing violence and insecurity in project locations, particularly Rumbek. / POF moderately did not meet expectations. It contributed to respondents’ perceived likelihood of conflict with other groups, however this is varied across project locations.
	Outcome 2: More inclusive political, socio-economic, and cultural institutions, which are key for handling conflict and establishing the conditions for sustained peace, are strengthened at all levels.
	Indicator 2.1: Contribution of POF activities on community perceptions that leaders are effective at reducing conflict and desire to prevent conflict. / Indicator 2.2: Change in inclusive interaction and collaboration (strength and density) between key institutions.		POF moderately did not meet expectations. There was some progress towards contribution of activities to community perceptions that leaders are effective at reducing conflict, however this varied over the lifetime of the programme. / POF met expectations. There was good progress towards change in inclusive interaction and collaboration between key institutions.

Overall assessment of programme outcomes, sustainability and VfM

POF made good progress on the programme outcomes but outcome indicators were not fully achieved over the life of the programme. POF operated in a challenging context, following a post-independence civil war with complex and varied conflict dynamics. Stakeholders also commented that the programme had made notable improvements. They also noted that although the drivers of conflict could be mitigated they remained outside the control of the programme.

One of POF’s key strengths was its innovative ‘accompaniment’ approach, which prioritises the process of creating sustainable peacebuilding over one-off peace events such as conferences. Accompaniment ensures that work to promote peace takes place before and continues after the formal event, with peacebuilding actors working to accompany communities throughout the process.

POF’s accompaniment approach, including pre-dialogues to maximise the likelihood of positive outcomes to peace dialogues, as well as continued work to ensure effective implementation of agreements was key to the approach and success of the programme. POF initiatives have started to lay the foundations for sustainability, including the establishment of Peace Canal, however initiatives are not yet fully sustainable without further programme support. The good progress in a number of areas forms a strong foundation for the second phase of the programme.

Outcome 1: Targeted communities are more harmonious and resilient to conflict

Indicator 1.1 - Contribution of POF activities on reported frequency of violent conflict and/or insecurity since start of targeted activity

POF made a strong contribution to reducing violence and insecurity over the course of the programme particularly in Lakes state amongst the five sections of the Dinka Agar community (Rumbek East, Rumbek Central and Rumbek North). A 2022 independent evaluation by Forcier noted that in Rumbek, the overwhelming majority of interviewees reported a decrease in violence due to a combination of POF activities and a new Governor. In Lekwangole, Gumruck, Pibor and Vertet, four counties in the Greater Pibor Administrative Area (GPAA), improvements attributed to POF activities were also reported in the 2022 Forcier independent evaluation.

Jonglei/GPAA

Anecdotal evidence suggests that there were improvements in the three counties of Greater Bor (Bor South, Twic East, Duk), and the three Lou Nuer counties of Greater Akobo, Uror, Nyirol and Akobo, and the Gawar Nuer county of Ayod.

Stakeholders noted POF’s role in preventing armed conflict and reducing its intensity when it did break out. For example, in Jonglei / GPAA there were reportedly seven occasions when armed actors prepared or attempted to attack in the area, the POF-Peace Canal rapid response approach de-escalated tensions and avoided conflict. However, the programme was unable to prevent armed conflict in December 2022. There were however, reports that the intensity of the December 2022 attack was reduced by the communication channels established between Peace Canal advisers and the armed youth leading the attack. These were conduits through which they were able to encourage de-escalation. The comprehensive multi-agency community engagement that followed the attack, also mitigated the risk of retaliation. Trends and anecdotal evidence from communities and other stakeholders indicate that without POF and the UN South Sudan Reconciliation, Stabilisation and Resilience Trust Fund (South Sudan RSRTF) interventions, the intensity and frequency of conflict over the last two years would have been much higher.

Core stakeholders reported that some communities continued to become more harmonious and resilient as a result of the programme. While improvements are tangible, building sustainable solutions requires further effort, suggesting that communities will benefit from continued support through the second phase of POF.

In Jonglei / GPAA, POF’s key achievement was the groundbreaking 2021 Pieri Peace Agreement, which brought together the Lou Nuer, Murle and Dinka Bor communities, with the Gawaar Nuer and served as a base to build peace between communities who have suffered the effects of inter-communal violence over decades. Despite a Lou Nuer-led mobilisation of December 2022 in the Greater Pibor Administrative Area (GPAA), and continued isolated attacks by Murle youth, the Pieri Peace Agreement remains a key example of what works. The reduction in conflict following the Pieri Peace Agreement was noted by stakeholders as evidence of the success of the programme. The increased speed at which communities engaged with one another to address issues was noted by stakeholders. Prior to the Pieri agreement it took at least 9 months of engagement and effort to get communities to engage and address tensions after the agreement parties came together in a matter of weeks to address conflict drivers and de-escalate tensions.

Lakes

In Rumbek, POF created a grassroots peace committee of cattle camp youth leaders called the Akut de door. This mitigated conflict across the five Agar sections. The committee’s approach was adopted and developed by the state government.

The successful Intra-Agar dialogue on cattle migration routes demonstrates POF’s impact in reducing and preventing armed conflict. It significantly reduced violence and killing and was formalised by state authorities in annual migration conferences. This facilitated the peaceful migration of around one million cattle annually, without death or injury to community members or cattle keepers for three years in a row from 2020. From 2011-2020 there were 307 deaths and 279 people injured in intra-Agar violence. Since the 2020 Migration conference there have been 34 deaths and 39 injured. There have been no deaths or injuries registered during the migration. There remains a significant level of violence however between communities on the periphery of the Agar system, particularly with the Luacjang. Pakam-Luacjang violence resulted in 151 killed and 67 injured in March 2023.

POF has promoted women’s participation and leadership in peacebuilding activities, including specific engagement with Agar women on their role both in exacerbating conflict and promoting peace. A POF led research project looked at women’s roles in encouraging conflict through perpetuating narratives which encouraged young men to fight. This helped frame a new approach with women in the Agar community, bringing together women from the five Agar Women’s Associations in Rumbek and providing training in leadership and management skills to strengthen women’s meaningful participation in dialogue. Through the ‘Women’s Peace Caravan’ project in 2021, women visited five cattle camps and five villages to strengthen women’s participation in peace, make them aware of their contribution to peace, and discourage their participation in conflict. The engagement with Agar women was successful as it involved women at grassroots level. Women responded to the approach and could see that space was being created for their participation. The 2022 evaluation by Forcier noted that Rumbek respondents found that POF’s approach has been different from that of other peacebuilding actors and that active participation of women in conflict-resolution and peacebuilding work has been particularly successful.

Bentiu and Torit

Success was reported in Bentiu and Torit, despite POF activities ending in 2021. In Bentiu, POF established Women Peace and Security (WPS) committees within each sector of the Protection of Civilians (POC) site, which strengthened community capacity to address conflict and insecurity by creating local structures to facilitate conflict resolution. The WPS Committees established by POF worked within the POC community by visiting each house to explore how to improve security, by raising issues of insecurity with churches, and by working with the youth to conduct patrols to strengthen security. POC community leaders attributed a reduction in violence and revenge killings to the creation of the WPS Committees. In Torit, and the Equatorias, POF supported engagement between local government authorities, local communities, traditional and religious leaders, military forces, cattle keepers and refugees in both Pageri / Nimule (Eastern Equatoria) and Kajo Keji (Central Equatoria) to address the legacy of insecurity following the civil war in 2016-18. The implementation of the Pageri Peace Forum resolutions resulted in military personnel not carrying guns or wearing military uniform when off duty, while military commanders used POF-funded radio programmes to rebuild their relationship with local communities, including by guaranteeing returnees’ security.

Indicator 1.2 – Contribution of POF activities on respondents’ perceived likelihood of conflict with other groups

The programme had a more varied effect on the perceived likelihood of conflict. POF-targeted communities in Rumbek were positive about the trend in violence reduction and the sustainability of the impact of POF activities. However, respondents in Jonglei / GPAA were not optimistic about the future and predicted that both inter- and intra-communal violence would continue. Rebuilding trust in these areas was challenging, reciprocal cattle raiding between communities continues despite the Pieri Peace Agreement. Communities’ perceptions of conflict were impacted by external factors and conflict drivers in Jonglei GPAA and Lakes States are different and specific.

POF’s approach to engaging community leaders changed over the lifetime of the programme to include more women and youth leaders. The programme used improved understanding of different leadership structures to engage with diverse groups and leadership at all levels. The political and cultural landscape is particularly complex in Jonglei / GPAA so it is important to engage with diverse groups. POF has built relationships and brought together representatives from each county as part of the Inter-communal Governance Structures (ICGS) that were established as part of the Pieri Peace Agreement. The ICGS created three inter-communal governance structures of youth, traditional chiefs, and women. Meetings were held with the representatives of these groups to discuss addressing community issues without resort to violence and with agreed actions.

Outcome 2: More inclusive political, socio-economic, and cultural institutions, which are key for handling conflict and establishing the conditions for sustained peace, are strengthened at all levels

Indicator 2.1 - Contribution of POF activities on community perceptions that leaders are effective at reducing conflict and desire to prevent it

There was some progress towards community perceptions that leaders are effective at reducing conflict. The 2022 Forcier evaluation found that in Rumbek, leaders were more effective and capable at resolving conflict after participating in POF activities. There was also an improvement in the quality and quantity of their engagement the community. Communities reported improved interaction with their leaders and involvement in decision-making. Since this evaluation, anecdotal reports indicate that have shifted. The Governor was accused of human rights violations and extra-judicial killings. In Jonglei, respondents were generally satisfied with their leaders’ effectiveness and level of interaction, which some reported was due to POF interventions. POF made significant progress engaging with different leadership structures over the programme lifecycle and increased its understanding of varied leadership structures across South Sudan.

Indicator 2.2 - Change in inclusive interaction and collaboration (strength and density) between key institutions

There was good progress towards inclusive interaction and collaboration between key institutions. The understanding of key institutions also evolved over the life of the programme. POF established new institutions including the Akut de door and the cattle migration pre-dialogue and conference (Greater Rumbek), and the ICGS (where leaders from different counties discuss where and how peace partners should work in support of local communities) and Murle Age Set Council (Jonglei / GPAA). The Murle Age Set Youth Council addressed the need for a Murle armed youth interlocutor to engage with the Nuer and Dinka armed youth, and part of the ICGS. Stakeholders reported that POF has got community structures, groups and individuals to understand their roles in peace, and had altered youth identities as ‘warriors’, by offering a respected role in the community as a peace mobiliser. One stakeholder said ‘POF has made it cool to be a peacebuilder’. POF has also collaborated with other aid partners including the UN Mission in South Sudan (UNMISS), the WFP the UN South Sudan Reconciliation, Stabilisation and Resilience Trust Fund (South Sudan RSRTF), Nonviolent Peaceforce, the UN High Commissioner for Refugees (UNHCR), Save the Children, the USAID Shejeh Selam programme, to coordinate on programming, share analysis, contribute to papers, and collaborate at the Area Reference Group in Jonglei / GPAA.

POF partnered closely with other actors to create alternative livelihood opportunities. In Rumbek, POF supported the development of Peace Farms with the payam administrator and community chiefs to provide food and alternate livelihoods through the allocation of land for Akut de door members, and for women’s associations. POF was able to start some initiatives in this area. WFP worked with Peace Canal to target armed youth in Jonglei / GPAA as part of a food for work project on road clearance, providing youth with a meaningful alternative to cattle raiding. This reduced attacks and allowed WFP to deliver humanitarian assistance in these areas. The livelihoods work in POF was included in the results framework through quarterly milestones.

In the original business case, indicative metrics proposed were based on the ‘fund manager’ grant-making model and so included some metrics that were not relevant to the ‘advisory-led’ model. The metrics were updated as part of the inception phase of the programme where POF developed a VfM strategy and metrics. The VfM metrics were updated in 2021 and remained the same from 2021-2023. Cost drivers (fees, accommodation, air travel and office rent) also remained the same throughout the lifetime of the programme. The programme made good progress in its structural value for money efforts – supporting Peace Canal to leverage FCDO funding further, strengthening equity arrangements, and continuing to manage economy drivers. However, under effectiveness, whilst the programme has strongly mitigated many of the conflict drivers, the context of conflict in South Sudan remains fragile. POF’s performance on ‘economy’ was the weakest out of all the VfM areas assessed, with a mixed performance to secure value. The programme’s workplan was delivered to plan, allowing for flexibility through its adaptive approach. If non-POF funding received by Peace Canal from other donors is taken into account, the proportion of funds that went to frontline delivered compared to the original budget was excellent, as Peace Canal received an additional 56% of additional non-POF funding. POF overall made good progress towards programme outcomes (demonstrating ‘effectiveness’). POF performed well under equity, focusing programme design and interventions on marginalised groups, including women and youth leaders.

Summarise the programme’s theory of change and results framework, including any changes to outcome indicators.

The results framework for POF was adaptive. The programme outputs, outcomes and impact were set. Milestones were agreed quarterly with BEJ. The theory of change was updated in January 2021 to reflect the changed delivery model from the grant-making fund manager to an advisory-led model with in-house advisory support and accompaniment to local actors and processes. The outcomes in the theory of change remained unchanged.

The impact of the programme was: enhanced South Sudanese capacity to manage conflicts without violence, and there is a reduction in violence in targeted areas. Impact indicator one measured the change in level of community perceptions of safety. As discussed under outcome one, the programme had a varied effect on the perceived likelihood of conflict, which could also be linked to community perceptions of safety. There was more optimism found in Rumbek than in Jonglei / GPAA among respondents. Impact indicator two measured the change in level of conflict impact in POF locations. As discussed under outcome one, POF made a strong contribution to reducing conflict in Rumbek. Although there was an incident of mobilisation in December 2022 in Jonglei / GPAA, there, stakeholders noted that POF had a role in reducing its intensity.

If…
- design is based on and generates analysis and learning, and facilitates sharing of learning across programmes locations
- and if the programme team engages local actors in the conflict system and works with cultural and traditional actors
- and implements sustained action arising from learning
- and strengthens coordination and response between local actors
- and is creative and courageous in exploring potential responses, supporting existing peace engagement and identifies new and/or enhanced opportunities

…then opportunities to address conflict and promote peace are supported
- structured, sustained engagement consolidates the impact of interventions
- interventions are more grounded in traditional good practice
- local actors are better resourced and draw on cross-system learning
- responsiveness to early warning capacity is strengthened across the states

leading towards…enhanced South Sudanese capacity to manage conflicts without violence and reduction in violence in targeted areas.

The steps to achieving outcome and impact remained valid. Programme adaptation was based on learning, including through engaging with different actors. Understanding of key institutions evolved over the life of the programme. From identifying institutions that showed signs of successfully managing conflicts and promoting civic attitudes and practices (for example formal, informal, and traditional institutions such as the Church, customary authorities, chiefs’ courts) to identifying successful spaces for peacebuilding, such as engaging youth and women with the creation of the Akut de door. Understanding of ‘leaders’ also evolved over the life of the programme, emphasising the importance of engaging with different leadership structures at all levels and adapting this to different contexts.

Over the lifetime of the programme, the focus was primarily on local and regional level activity, following a steer from the SRO as other UK efforts would focus on the national level. There was indirect interaction with the national level as local conflicts were influenced by national politicisation. Overall, the output targets were met and whilst there was progress towards the outcomes, they were not fully achieved within the lifetime of the programme.
## C: Detailed Output Assessment

Output Number and Title	POF uses evidence-based analysis and learning to drive and review decision-making.
Output Score	A
Impact weighting (%)	20%	Impact weighting revised since last AR?	No
Output Indicator Final Logframe Target Final Result Achieved / 1.1 Rigour of learning and evidence basis to activity selection Knowledge and learning incorporated in POF activity design, and iterative stakeholder consultation used to strengthen design and implementation. Score: A – met expectations: POF achieved 100% of planned quarterly activities over the lifetime of the programme. This included: / At least 5 POF activity concept notes approved by BEJ and implemented. / 4 POF Learning Papers, including: POF’s approach to using evidence and learning in activity design and implementation; effectiveness of POF approach to incorporating evidence and learning in activity design and implementation (x2); and learning on the Pieri Action Plan for Peace through a Dealing with the Past Analytical Framework. / POF Learning Papers publicly available in diverse location - (CSRF and Peace Canal websites). / Activity proposals include statement on application of learning. / Programmatic response to CSRF triple nexus paper / primary input to Center for Security Studies Paper on peacebuilding / Integration of key programme learnings into workplan; and evidence that activity implementation reflects concept design and approach. / Programme exit strategy developed and submitted; and evidence of implementing the strategy. / POF database updated with recent Peace Agreements, video and photo evidence. / POF and HMG jointly hold a workshop on learning from POF implementation and approach. / 1.2 Functionality of learning, review and decision-making system that ensures adaptive management of the activities Learning acted on. POF Area Advisers demonstrate ways in which workplans were adapted based on learning and review. Score A met expectations: POF achieved 100% of planned quarterly activities over the lifetime of the programme. This included: / 10 Area Adviser meeting reports, including section outlining specific instances of review and adaptation based on learnings/evolving context. / At least 4 POF Lessons Learned Papers / 2 South Sudan Peacebuilding Practitioner paper. / 24 Adviser teams posts and 60 replies / Monthly POF newsletters/updates which documented programme learning / 4 Quarterly reports that reflect analysis of the role of national elites in subnational peace and violence.

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score.

Output indicator 1.1 – Rigour of learning and evidence basis to activity selection. Final logframe target: Knowledge and learning incorporated in POF activity design, and iterative stakeholder consultation used to strengthen design and implementation. Score: A

POF used political economy and conflict analysis (PECA) throughout the lifetime of the programme in all geographical locations with a range of stakeholders, including local authorities, government officials, traditional and spiritual leaders, international partners and local communities. This ensured interventions were based on evidence. Gender and conflict analysis was integrated within the PECAs.

POF engaged local communities in decision-making processes. For example, POF adapted its engagement with the Lou community following two intra-Lou dialogues that had not resolved the root causes of conflict. A third dialogue was agreed if the community were willing to contribute their own resources alongside the programme’s to ensure commitment to the dialogue. Another example followed the breakdown of the Pieri Peace Agreement and the mobilisation by armed Lou-Nuer youth against GPAA communities in December 2022. POF explored the gaps in the implementation of the agreement, and in response created the Murle Age Set Council in recognition that there had been no reliable and credible representative body. Peace Canal led a consultation in partnership with Nonviolent Peace Force and UNHCR with communities across all counties of Jonglei / GPAA to determine concerns and priorities, playing a key role in driving the process forward.

Peace Canal has Area Advisers based in programme locations to provide evidence and insights from the field and inform analysis. Other partners also reported during stakeholder interviews that they utilise Peace Canal Area Adviser contacts to get relevant information for their organisations and commented that their reporting is always credible, timely, and helpful in their conflict analysis.

POF shared information through learning products, the majority of which are publicly available through the Conflict Sensitivity Resource Facility (CSRF) and Peace Canal websites. Stakeholders reported that these are used often. POF’s target over the lifetime of the programme was to develop 10 papers (including learning papers, lessons learnt papers, and practitioner papers). In total, POF completed 13 learning products, of which 11 are published.

Evidence and learning from POF also supported other partners’ programming. BEJ used POF learning to influence the content of renewal of the UNMISS mandate in March 2023 so that UN peacebuilding activities and interventions had a greater community-informed evidence base. Evidence and learning from the programme also informed UK engagement with UNMISS.

POF also engaged with other organisations, including the CSRF, WFP, the IOM, and Nonviolent Peaceforce. This included contributing to a CSRF paper on triple nexus programming (the interlinkages between humanitarian, development and peace programmes). The POF / Peace Canal approach was used as a case study on adaptive programming, exploring lessons and strategic insights for local level peacebuilding initiatives in a paper by the Centre for Security Studies at the Federal Institute of Technology Zurich (ETH Zurich). POF / Peace Canal advised USAID’s Shejah Salam programme.

The programme worked with the UN South Sudan RSRTF which was launched in 2019 as a pooled fund to reduce conflict in hotspots and marginalised areas of the country through area-based peacebuilding programmes. The second phase of South Sudan RSRTF’s peacebuilding strategies in Jonglei and GPAA drew on POF’s access to and ways of working with local communities, to ensure the integration of lessons learned into broader peacebuilding strategies. Peace Canal was asked to lead the Reconciliation Pillar for the two-year programme.

Peace Canal was invited by WFP to be part of a successful consortium bid for the South Sudan RSRTF in Kuajok area, to replicate POF approaches. Peace Canal was also invited to join the process for the Partnership for Peace, Recovery and Resilience (PfPRR), a platform for the humanitarian, development, peace triple nexus in South Sudan, as a national partner, feeding into strategic discussions on PfPRP operations. In Rumbek, the state government adopted and built on the ‘Akut de door’ community peacebuilding engagement approach, where Akut de door members have instituted customary courts for resolving cases of revenge killing and stolen cattle, creating a sustainable outcome.

POF also showed some evidence of moderately exceeding expectations for indicator 1.1 The target for exceeding was that POF evidence and learning supports non-POF programming - other stakeholders using POF learning for programmatic thinking. There were examples of POF / Peace Canal’s approach having some influence on other partners’ programming, including through the UN, research and academic institutions because this was to a limited extent, the indicator scored A.

Output indicator 1.2 – Functionality of learning, review and decision-making system that ensures adaptive management of the activities. Final logframe target: Learning acted on. POF Area Advisors demonstrate ways in which workplans were adapted based on learning and review. Score: A.

Adaptive programming was central to POF’s implementation, allowing for flexibility and community ownership. For example, immediate funding was provided to transport Murle leaders to Pieri in December 2021 in response to a seven-day ultimatum from Lou Nuer leaders for a face-to-face dialogue to stop a planned mobilisation, successfully preventing an attack. Funding was also provided to bring Lou Nuer leaders to Kongor in GPAA in March 2022, to conduct urgent peace rituals between the Lou Nuer and Murle communities.

POF paused programming when needed. This included pausing the final stage of the Greater Dinka Bor dialogue process after the Twic East community decided that they no longer considered themselves as Dinka Bor, but as Jieng Jonglei. They also paused and adapted programming in Jonglei / GPAA following the mobilisation by armed Lou-Nuer youth against GPAA communities.

The example of Akut de door transformation of armed youth leaders into peace ambassadors and managers of conflict was shared twice in other areas during the programme. POF brought armed youth of the Murle and Dinka Bor communities from Jonglei / GPAA to Rumbek where they were hosted by the Akut de door to demonstrate what is possible if leaders can find a way of working together. This resulted in a peace agreement between the youth leaders and reduced violence between the communities. They brought the Murle Age-Set leaders from four GPAA counties to visit Rumbek as part of POF’s work to create a meaningful Murle interlocuter for the other communities.

The programme transferred knowledge and lessons learned to different areas. POF appointed the Rumbek Gender Adviser to work with Area teams, transferring learning from Rumbek Area to the design of peace activities in Jonglei / GPAA, strengthening women’s participation and leadership through the inclusion of women in peacebuilding work. The Gender adviser worked with the GPAA team and designed engagement with the Gawaar community, facilitating the meeting of women from both communities in Ayod and Gumuruk. The Gender adviser also designed of an Akobo activity where women from Jonglei / GPAA met, the first of its kind in the area.

The complexities of different contexts meant that a successful approach in one area could not be duplicated in another but learning was applied to other areas. POF learnt the significance of spiritual leaders and rituals within local peace agreements from Rumbek and Bentiu, which informed their approach to the Pieri peace process. Following mobilisation and attacks in Jonglei / GPAA in 2022, POF drew on evidence and analysis of the conflict before deciding on whom they needed to engage. POF learnt that communities were not getting what they needed from the Pieri Peace Agreement and adapted their approach.

The adaptive approach enabled the programme to take advantage of emerging opportunities, it also posed some challenges. For instance, ensuring that gender equality aspects of programme activities were effectively prioritised, tracked and monitored throughout implementation. The results framework did not explicitly include indicators and requirements on gender equality, this, combined with budget constraints reduced follow-up on gender-focused interventions.

There were also examples of POF meeting some of the criteria for moderately exceeding expectations. The target for exceeding was: Learning transferred. Activities effective in one location considered for scale-up in the same area or roll-out in other regions. Activities found to be not effective are revised or stopped. The programme facilitated knowledge exchange and revised and stopped activities. Evidence of scaling up activities in the same areas or rolling out activities in other regions was limited. Overall, this indicator scored an A.

Lessons learned through this output, and recommendations for future programming

Changes in 2021 to the scope of the programme and strategy changed it from developing new concept notes to building on existing areas of activity and analysis. This was reflected in the adaptive quarterly activities / milestones that were updated each quarter.

Recommendation 1: POF’s approach to community and evidence-based peacebuilding started to gain traction over the course of the programme with evidence of influencing other partners’ programming. For the second phase, this the evidence from this approach should be disseminated more widely, and POF should share learning and coordinate with other partners in South Sudan on peacebuilding activities and peace dividends.
Recommendation 2: The second phase of the programme should build on POF’s adaptive programming approach and incorporate a rapid response mechanism to respond to emerging conflicts. POF had a successful approach to analysing the situation on the ground and they should use this to respond quickly to unexpected local violence.

Recommendation 3: The second phase of the programme should ensure that gender equality and social inclusion is maintained throughout implementation and is well-documented in programme documents, including the results framework.

Recommendation 4: The second phase of the programme should ensure that a results framework is in place that meets the needs of an adaptive programme, whilst also ensuring that there is a clear link between outputs and outcomes and a clear way to track outputs with specific, measurable, achievable and timebound (SMART) indicators.

Output Number and Title	POF engages with local actors in the conflict system, targeting those who can most influence conflict, especially cultural and traditional actors
Output Score	A
Impact weighting (%)	20%	Impact weighting revised since last AR?	No
Output Indicator Final Logframe Target Final Result Achieved / 2.1 Quality of iterative conflict and actor mapping Mapping undertaken in each location and updated to capture lessons and changing context. Conflict monitoring tracks conflict incidents and trends over time. A: POF achieved 95% of planned quarterly activities over the lifetime of the programme. / POF also achieved some criteria of A+ in that mapping informed other partners’ programming and BEJ strategy and engagement. POF informed BEJ strategy and engagement to a more limited extent and so the overall score is A. / Activities achieved included: / 9 x conflict monitoring reports for JACS. / 4 PECAs developed and updated. / 1 Conflict Trends Review paper (July 2020 - June 2021). / Updated stakeholder mapping for Jonglei/Rumbek. / Mapping of Jonglei Community Governance system. / Review of representation at inter-communal meetings and review of approach. / Review and identification of lessons learned (including proposed next steps) from engagement with Nanaam age-set youth. / Management work with the programme gender adviser to identify areas where the inclusion of women could be strengthened. / Evidence of POF targeting those who can most influence conflict, e.g. Jonglei/GPAA state and national government actors. / POF partially completed the following activity as emergence of internal issues within the Dinka of Jonglei meant the summative dialogue of the three counties was not, and is still not possible: / Report on Dinka Bor Dialogue process (key issues and actors documented)

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

Indicator 2.1 – Quality of iterative conflict and actor mapping. Final logframe target: Mapping undertaken in each location and updated to capture lessons and changing context. Conflict monitoring tracks conflict incidents and trends over time. Score: A

POF carried out mapping in each project location. This included PECA updates and actor mapping and stakeholder analyses, which were revised and updated throughout the lifetime of the programme to provide information on local conflict systems and changing contexts. The strength of POF’s relationship with traditional and spiritual leaders and youth leaders has been particularly notable. A recent example is actor mapping to include national elites in a workshop held in Ayod and a dialogue in Duk County. Actor mapping was important to identify participants instrumental in local conflict dynamics. The workshop in Ayod county made significant progress in reconciling internal differences within the Gawaar community. At the Duk County dialogue leaders were held to account and agreed to end revenge killings and to pay compensation.

POF informed other partners’ programming. Organisations and partners, including WFP, Nonviolent Peaceforce, and CTP used actor mapping to inform strategies as noted in Output One. For example, Nonviolent Peaceforce supported activities within GPAA, in response to POF political economy analysis and actor mapping, leading to some joint programming. The annual review in 2021 noted that RSRTF and WFP found that analysis produced by POF strengthened their understanding of conflict dynamics and enabled them to identify peacebuilding gaps and connected them with relevant actors.

POF also informed BEJ strategy and engagement. Actor mapping of the Dinka Bor community became increasingly sensitive and political, requiring engagement with senior Juba-based political figures, including Madam Rebecca, the Vice-President responsible for the humanitarian cluster. BEJ supported this engagement and attended high-level meetings with key and relevant interlocutors in Juba. Knowledge of the dynamics in Jonglei generated by POF, enabled BEJ to play a role in mobilising a cohesive and appropriate international response to the escalation of violence in the region in May 2021. BEJ used learning from POF to influence the renewal of the UNMISS mandate in March 2023, successfully advocating for more community-informed evidence in UN peacebuilding activities and interventions. Information shared by POF has also facilitated BEJ conversations with UNMISS and peace agreement monitoring actors. In 2020, POF also provided two inputs for the development of the South Sudan JACS update.

There were also examples of POF meeting some of the criteria for moderately exceeding expectations (A+). The target for exceeding was Mapping informs non-POF programming and FCDO strategy and engagement as there were examples of mapping and analysis informing other programming but only to a limited extent.

Lessons learned through this output, and recommendations for future programming

POF provided evidence of influencing other partners’ programming and BEJ strategy and engagement, however this can be improved. POF had previously provided BEJ with quarterly conflict monitoring of incidents and trends, but this was discontinued in 2022 due to budget constraints. BEJ should also look at how we can work with POF as a strategic partner, ensuring we consult them as experts on the ground should conflict incidents occur, and joining forces to ensure we direct our diplomatic and political capital at the right contexts to de-escalate and prevent conflict.

Recommendation 5: BEJ should consider how to utilise POF analysis to inform strategic and political thinking, and POF should make suggestions on what the BEJ team can do to support their work in the field such as strengthening collaboration between partners.

Output Number and Title	(3) POF incorporates sustainability into its implementation approach
Output Score	A
Impact weighting (%)	10%	Impact weighting revised since last AR?	No
Output Indicator Final Logframe Target Final Result Achieved / 3.1 Level at which sustainability is incorporated into the decision-making process for engagements and activities. Sustainability beyond the programme life-cycle. Evidence that activities and or institutions/structures will be sustained beyond the lifecycle of the programme. A: POF achieved 92% of planned quarterly activities over the lifetime of the programme. This included: / 2 sustainability strategy papers / Implementation of 4 peace dialogues monitored / 2 peace dialogue resolutions monitored; / 6 project proposals developed / 3 local peacebuilding governance mechanism meetings with co-contribution / National NGO supported to (a) develop required systems and process; and (b) submit project proposal for funding / Evidence that areas for improvement from initial partner capacity assessments (Save the Children / Shejah Selam) have been implemented / Establishment and induction of NGO Board / 1 Expert Advisory network sustainability discussion paper / Peace Canal Board meeting conducted / Peace Canal updates and submits quarterly its systems progress / Peace Canal submits audit report. / POF did not complete the following two activities: / Not complete: 1 Expert Advisory Network sustainability discussion paper – this was agreed to be changed to a workshop. / Not complete: Peace Canal Annual Report developed – this is still in progress.

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

Indicator 3.1 - Level at which sustainability is incorporated into the decision-making process for engagements and activities. Final logframe target: Sustainability beyond the programme life-cycle. Evidence that activities and or institutions/structures will be sustained beyond the lifecycle of the programme. Score: A.

A central part of POF’s sustainability and exit strategy was the creation of Peace Canal, an NNGO established in 2021. The formation of Peace Canal included registering the organisation as a national legal entity, establishing the governance board, transferring existing national programme staff, sub-contracting Peace Canal as a national delivery partner, and providing fiduciary oversight and capacity building support alongside the implementation of frontline delivery activities. Establishing Peace Canal is a key achievement of the POF, and the organisation continues to be strengthened. Peace Canal has successfully attracted funding from other donors to carry out programme activities and has started to build a positive reputation and has been asked to lead the Reconciliation Pillar for the South Sudan RSRTF. Although Peace Canal has made significant progress it remains dependent on POF funding with only limited funding from other sources and is not yet sustainable.

The programme also established the Akut de door, where armed youth leaders became peace ambassadors and managers of conflict and dispute resolution between the Agar sections. The state government has adopted and built on the Akut de door community peacebuilding engagement approach. Akut de door members support customary courts to resolve cases of revenge killing and recovery of stolen cattle. The State’s Adoption of this approach, and increased peacebuilding skills in youth groups means the approach to now self-sustaining.

Another key achievement of the programme was the intra-Agar cattle migration dialogues that significantly reduced violence and killing, succeeding in the peaceful migration of around one million cattle annually without death or injury to community members or cattle keepers for three years in a row. Migration conference agreements since 2020 have held, but questions remain on the sustainability of this intervention as it is not clear whether it would continue without POF involvement. The pre-dialogues are linked to the annual Cattle Migration Conference and serve an important preparatory role for the actual conference itself in pre-agreeing the migration routes and issues to be addressed in the conference. The pre-dialogues would not continue without the Cattle Migration Conference as a milestone and so it is unlikely they would continue without POF support.

POF showed evidence of influencing other actors’ interventions and funding decisions. Learning from POF analyses, papers, and mapping informed the design of South Sudan RSRTF projects in Jonglei / GPAA and Kuajok, Nonviolent Peaceforce’s project in Jonglei / GPAA, and CTP’s project in Lakes State. The programme also influenced the design of USAID Shejah Salam peace programme and the type of local partnerships it supports. Partners highlighted that POF / Peace Canal played an important role in the CSRF’s research groups. In POF’s collaboration with WFP, stakeholders commented that POF / Peace Canal provided detailed analysis and evidence based suggestions, and identified how WFP and POF could work together. POF’s provided advice on how to respond to attacks on WFP convoys driving through communities in Jonglei. POF supported community engagement and advised that WFP provide opportunities for young people to work on the roads which ended the attacks.

The programme laid the foundations for peace in its targeted locations, through its work facilitating peace dialogues and the development of the Pieri Peace Agreement in Jonglei / GPAA and Akut de door in Rumbek but is important that these are sustained. In Bentiu, where POF ended activities, beneficiaries reported that they had increased confidence in their own community’s ability to peacefully manage conflict. However, they still perceived a high risk of conflict with communities outside of the camp for Protection of Civilians / Internally Displaced People and did not feel confident enough to instigate dialogue without the support of POF.

Peace Canal, and other initiatives developed under POF including the cattle migration conference are not yet sustainable without funding from the programme. The review found that there was some evidence of POF moderately exceeded expectations (A+). The target for exceeding was Evidence of POF influence on other actors' (local, national, or international) intervention design and/or funding decisions. This was demonstrated by the influence of the Akut de door on the Lakes State Government and the interest generated amongst other actors in POF approach to peacebuilding. However as further work is required for initiatives to be sustainable overall, this output scored an A.

Lessons learned through this output, and recommendations for future programming

POF made considerable progress on the sustainability of the programme. It is important that the interest by communities, delivery partners, and donors in its approach to peacebuilding is sustained. The establishment of Peace Canal has been a key achievement, and the second phase should continue to explore opportunities to build the capacity of local peacebuilding organisations.

Recommendation 6: POF2 should use its accompaniment approach to support more NNGOs to become effective and self-sustaining, thereby increasing peacebuilding NGOs in target areas.

Output Number and Title	(4) POF strengthens coordination and engagement between diverse local actors to promote peace and responsiveness to conflict triggers
Output Score	A
Impact weighting (%)	20%	Impact weighting revised since last AR?	No
Output Indicator Final Logframe Target Final Result Achieved / 4.1 Frequency of interaction and collaboration between all relevant groups and organisations, including government (national and local), NGOs, INGOs, traditional leadership, etc. Interactions are frequent and diverse, with evidence that POF has identified networks of relevant actors and POF actively supporting actors to convene. A: POF achieved 100% of planned quarterly activities over the lifetime of the programme, including: / 1 peace structure supported x 2 / 10 consultative meetings conducted with action points documented for monitoring x 2 / 12 peace dialogues facilitated / 1 location map of actor collaboration x 2 / 2 local mechanisms supported to meet (not necessarily funded by POF, but with POF personnel support), 1 each in the Rumbek and Jonglei systems x6 / Evidence of POF-Peace Canal engaging in coordination/collaboration activities (through ARG & Social Cohesion Group in Jonglei-GPAA and generally in Rumbek) / Evidence of POF-Peace Canal engaging in coordination/collaboration activities (through ARG & Social Cohesion Group in Jonglei-GPAA and generally in Rumbek). / Brief technical review of Akut de door Peace Farms. / Quarterly Report highlights evidence of initiating a joint/coordinated approach to responding to mobilisations In Jonglei and GPAA. / Quarterly Report highlights evidence of coordination and engagement with diverse local and external actors to promote peace and responsiveness to conflict triggers, particularly UNMISS Civil Affairs Division.

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score.

Indicator 4.1 - Frequency of interaction and collaboration between all relevant groups and organisations, including government (national and local), NGOs, INGOs, traditional leadership, etc. Final logframe target: Interactions are frequent and diverse, with evidence that POF has identified networks of relevant actors and POF actively supporting actors to convene. Score: A.

Over the programme lifecycle, the programme has engaged frequently with relevant and diverse actors in geographical locations and built relationships with key stakeholders to ensure community-led design of peace dialogues and activities. Peace Canal leads the South Sudan RSRTF Reconciliation Pillar and this role supports communication and collaboration through regular partner coordination meetings. POF has also engaged with other peace actors including Nonviolent Peaceforce, WFP and Shejah Selam as part of humanitarian, development, peace triple nexus programming linking peace dividends to peace dialogue and community engagement. Stakeholders confirmed that they have built strong partnerships with POF / Peace Canal and that they have provided a strong contribution to triple nexus programming. Although POF has successfully collaborated with a range of institutions, a gender review of the programme found that there is scope for POF to more effectively engage with Women's Rights Organisations (WROs), drawing on their knowledge and expertise to feed into analysis and design of programme activities.

The programme engaged with state authorities, particularly in Jonglei / GPAA where the POF team provided regular updates on planned activities. State authorities and government are key actors in conflict and peacebuilding, and can either support peace activities or act as spoilers to peace, engaging with them is key to successful and sustainable peace initiatives. There has also been engagement with diverse groups including chiefs at all levels, women leaders, cattle camp youth leaders (armed youth), and spiritual leaders. POF facilitated an Inter-Communal Governance Structure in Jonglei and GPAA where leadership meets on a quarterly basis in support of implementation of the Pieri Peace Agreement. However, there were some challenges. POF recently drafted a Memorandum of Understanding with Jonglei State Government to reduce the risks associated with the State Government withdrawing its commitment to the process.

There was some progress towards the A+ criterion of Interaction with impact. Decisions taken between relevant actors are implemented and sustained. For example, communities and government in Rumbek see the importance of the Annual Migration Conference but the government has not yet committed funds.

Lessons learned through this output, and recommendations for future programming

There was interaction between POF the International Community and coordination forums and the programme has cultivated strong partnerships has a strong reputation. This can be built on as part of the second phase.

Output Number and Title	(5) POF identifies and implements activities across locations and funding windows
Output Score	A
Impact weighting (%)	30%	Impact weighting revised since last AR?	No
Output Indicator Final Logframe Target Final Result Achieved / 5.1 Extent to which POF-funded activities are making expected progress through implementation and/or strengthening understanding of effectiveness principles. At least 75% of activities and 75% of outputs delivered A: POF completed 95% of activities under this output. This included: / Learnings from past national level processes translated into strategic priorities paper. / Agreement reached on cattle migration patterns to guide the movement of cattle and people. / Women's engagement coordination meeting in Rumbek. / Radio programmes disseminating results of dialogues (Torit). / 12-month participatory review of Akut de door (Rumbek). / Report on implementation of Akut de door participatory review recommendations (Rumbek). / Conducting Community Governance Structures inception workshop (Jonglei) / Gawaar-Murle phase two dialogue complete (Jonglei) / Inaugural meeting of Internal Cattle Migration Monitoring Committee (Rumbek) / Intra-Nuer Dialogue process complete; Nanaam outreach activities conducted (Jonglei) / Internal Cattle Migration review and identification of lessons learned (Rumbek) / 1 National level reconciliation follow-up paper (national); / 1 migration agreement delivered (Rumbek) / 1 trust building workshop for government (Bentiu); / 1 women's engagement coordination meeting (Rumbek) / Evidence of POF engaging Greater Jonglei authorities on inter-community ventures, e.g. Wuno, Weikol, Gadiang. / POF partially completed the following activity: / Ritual peace ceremonies from Pieri Action for Peace conducted on Lou-Murle border and Dinka Bor-Murle border (Jonglei) – It was again not possible to conduct the Murle-Dinka peace ritual carried over from previous quarter. This was not possible as there was violence in Bor which led to mistrust. / POF did not complete the following activity: / Trust-building initiative in Bentiu. The workshop for government in Bentiu was not possible as formation of government was delayed. Subsequently, Bentiu was dropped as a POF location.

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score.
Indicator 5.1 – Extent to which POF-funded activities are making expected progress through implementation and/or strengthening understanding of effectiveness principles.
This output measures the implementation of activities and the outputs and evaluates how the process driven outputs 1-4 culminate in actions under each of the four workstreams. The milestones and activities were reviewed and updated quarterly in agreement with BEJ. It was expected that at least 75% of milestones and activities were delivered and that at least 75% programme outputs were delivered. POF delivered 97% of milestones / activities over the lifetime of the programme and met their targets for all outputs 1 – 4. There was insufficient evidence of POF exceeding expectations of their outputs and so overall output 5 scored an A.

	Milestones/ activities	Status	% complete
Output indicator 1.1	15	15 complete	100%
Output indicator 1.2	19	19 complete	100%
Output indicator 2.1	20	19 complete / 1 partially complete	95%
Output indicator 3.1	25	23 complete / 2 not complete	92%
Output indicator 4.1	23	23 complete	100%
Output indicator 5	39	37 complete / 1 partially complete / 1 not complete	95%
Total	160	155 complete / 2 partially complete / 3 not complete	97%

Lessons learned through this output, and recommendations for future programming
The fifth output was added in Q3 of financial year 2020-21 to evaluate how the process driven outputs 1-4 led to actions under each of the four workstreams. There were some overlaps between outputs 1-4 and output 5. Output 5 was included to ensure that outputs 1-4 resulted in completed implementation activities, and so more closely tracks programme activities. The next phase of the programme should develop a more effective approach to tracking actions and results and consider a comprehensive monitoring framework.

D: Value for Money

Key cost drivers and performance

In the original business case, indicative metrics proposed were based on the ‘fund manager’ grant-making model and so included metrics some that were not relevant to the ‘advisory-led’ model, such as ‘greater harmonisation amongst partners of key input costs’. The metrics were updated as part of the inception phase of the programme where POF developed a VfM strategy and metrics based on the ‘King-OPM’ model, which is an OPM approach to assessing value for money. This approach includes ‘criteria’ for each of the five areas of VfM which are assessed through ‘performance standards’ (‘Excellent’, ‘Good’, ‘Adequate’ and ‘Poor’) with corresponding indicators to judge performance and VfM.

The VfM strategy was reported against every six months and POF tracked value for money (VfM) indicators against the 5Es – i.e., economy, efficiency, effectiveness, equity, and cost-effectiveness. The quality of the VfM reports were very good and included a detailed breakdown of cost drivers. The key costs throughout POF implementation period have been fees, accommodation, air travel and office rent. POF programme received four cost extensions to ensure a smooth transition between POF and its second phase. POF was initially a 2-year programme from July 2019 to July 2021 with a full life value of £3,200,000 and was extended to 4.5 years until December 2023 with a full life value of £5,465,927. The final programme spend was £5,464,452.23.

The VfM metrics were updated in 2020-2021. This included removing indicators related to a decrease to the international advisor costs under economy, with a new indicator under equity on the proportion of non-South Sudanese personnel fees versus South Sudanese personnel fees. It also replaced efficiency indicators looking at the ratio of overheads to activities of individual investments, replacing these with indicators relating to POF’s performance in the delivery of the workplan. The metrics remained the same from 2021-2023.

Economy

The criterion for economy was ‘POF procurement is linked directly to delivery requirements of an appropriate quality and quantity for the delivery of required outputs’. The performance standards / indicators were:

Performance standard	Indicator
Excellent	POF demonstrates significant examples of sound competitive bidding/procurement of accommodation, air travel and office rent or leveraging of funds to secure value.
Good	POF demonstrates examples of sound procurement or leveraging of funds to secure value. / Procurement of supplies in site locations includes an economy/equity statement.
Adequate	POF demonstrates mixed performance of procurement or leveraging of funds to secure value. / Advisor pay and benefits are at market rates, ensuring equity and conformity with local labour laws.
Poor	Any of the conditions for adequate are not met

Overall POF met the criteria against the ‘Adequate’ performance standard, demonstrating a mixed performance of procurement or leveraging funds to secure value. POF did not meet the indicators against the ‘Good’ or ‘Excellent’ performance standards.

The unit costs have generally demonstrated moderate performance during the review period. The key indicators used to assess economy were the unit costs of the major cost drivers. All the unit costs were benchmarked and reflected the competitive market rates. OPM negotiated cost savings for staff accommodation, a reduction of 40% (from $100 to $60) for short term housing and negotiated for a reduction from $1,500 to $1,200 per month for long-term accommodation for the Programme Manager. OPM procured supplies locally rather than from Juba or internationally to get cheaper unit rates and promote local industries. OPM provided enough information on costs drivers such as staff costs, cost of accommodation, flights and overheads. Staff costs remain the key cost driver and there was limited scope for gains around the unit costs given that South Sudan is a high-cost operating environment.

Efficiency

The criterion for efficiency was ‘POF produces expected deliverables within the resources available, and optimises use of resources through flexible and adaptive management’. The performance standards / indicators were:

Performance standard	Indicator
Excellent	POF workplan deliverables all met and some significantly exceeded / Programme demonstrates significant enhanced performance through adaptation and learning / Frontline delivery expenditure increases significantly compared to original budget (>10%)
Good	POF workplan delivered to plan (allowing for reasonable exceptions explained by external factors or emergent strategy) / Delivery is on track against all outputs, with no serious gaps in delivery. / Programme demonstrates some examples of enhanced performance through adaption and learning / Frontline delivery expenditure increases appreciably compared to original budget (>5%)
Adequate	POF workplan generally on track, sufficient to meet bottom-line expectations and showing satisfactory progress overall. / Delivery largely on track against most outputs, with some gaps in delivery. / Frontline delivery expenditure is as budgeted. / Processes are in place to support adaptive management.
Poor	Any of the conditions for adequate are not met

POF met the corresponding indicator against ‘Good’ that the workplan was delivered to plan and that delivery remained on track over the lifetime of the programme. Although POF overall met its targets over the lifetime of the programme, the production of conflict monitoring reports under Output Two was discontinued in 2022 due to budget constraints. Not all deliverables were met and so it did not meet the indicator for ‘Excellent’ on workplan delivery.

POF did however meet some indicators for ‘Excellent’ including that the programme delivered well through adaption and learning. For example, following the mobilisation of armed youth in December 2022 the POF responded by convening partners to develop a collective response and mobilised 16 partners to join different configurations of teams travelling across all 11 target counties in a Community Re-engagement Initiative. This allowed the collective area-based partners to re-establish the foundations for moving forward with the peacebuilding activities, confirming that the overall appetite remained, despite some further mistrust that had been engendered between the communities through the mobilisation.

Proposed milestones were reviewed and updated quarterly in agreement with BEJ and the programme adapted its delivery approach, for example focusing resources in two project locations instead of four after a reassessment of what would provide the best value for money. The original business case stated that POF would focus on two geographies at a sub-national level. Following the inception phase OPM proposed to expand geographical coverage to four areas, with the same budget, to maximise learning across a wider range of project locations, and to minimise the risk to programme learning if one project site should become inaccessible. In 2021, as part of a time and cost extension of the programme, a case was made to continue programme delivery in Rumbek and Bor only. The annual review of POF in 2020 recommended reviewing the value for money of targeting four areas. Expanding to four areas had initially been assessed as demonstrating good VfM because this was delivered with the same budget originally intended for two areas. However, further assessment highlighted the potential risk that this stretched resources and diluted effectiveness. Rumbek and Bor were assessed as the locations where POF had the most traction and so POF focused resources on building on their achievements and deepening the relationships that had been established. Activities therefore ceased in in Bentiu and Torit in 2021.

POF also met the ‘Excellent’ indicator that delivery expenditure increases significantly compared to original budget (>10%), however noting that this includes non-POF funding. POF established the National NGO Peace Canal, which has been able to secure additional funding sources from third party donors, resulting in approximately an additional 56% of additional funding.

Effectiveness

The criteria for effectiveness was ‘POF achieves its intended outcomes: (i) targeted communities are more harmonious and resilient to conflict, and (ii) more inclusive political, socio-economic, and cultural institutions are established, which are key for handling conflict and establishing the conditions for sustained peace.’ The performance standards / indicators were:

Performance standard	Indicator
Excellent	POF meets intended outcomes, with examples of performance above expectations (e.g., greater than expected influence over actions of key stakeholders)
Good	POF demonstrates significant progress towards achieving intended outcomes / Programme consistently and to a high standard follows good practice to manage effectiveness drivers (i.e. understanding of political economy, successful engagement at local levels etc)
Adequate	POF demonstrates some progress towards achieving intended outcomes (i.e. emergent signs of improvement, or a few examples of progress) / Programme generally follows good practice to manage effectiveness drivers (i.e. understanding of political economy, successful engagement at local levels etc)
Poor	Any of the conditions for adequate are not met

POF made progress towards achieving the programme outcomes, particularly on Indicator 1.1: Contribution of POF activities on reported frequency of violent conflict and/or insecurity since start of targeted activity and Indicator 2.2 Change in inclusive interaction and collaboration (strength and density) between key institutions but less so on Indicator 1.2: Contribution of POF activities on respondents’ perceived likelihood of conflict with other groups and Indicator 2.2 Change in inclusive interaction and collaboration (strength and density between key institutions). Although POF may not have reached the standard of ‘significant’ progress, the programme made good progress overall. POF interventions were informed by Political Economy and Conflict Analysis (PECA) in project locations. POF engaged with local actors in the conflict system who would have the most influence.

Outcomes were not met over the lifetime of the programme, recognising that POF operated in a challenging context, following a post-independence civil war with complex and varied conflict dynamics.
Equity

The criterion for equity was ‘POF approach is both aware of, and proactively developing, approaches to enhancing the reach of the programme from a gender and social inclusion perspective.’ The performance standards / indicators were:

Performance standard	Indicator
Excellent	POF interventions and influence over local processes demonstrate benefits to marginalised groups (equity impact).
Good	POF's inclusive advisory networks support the programme to incorporate considerations of equity meaningfully into programme decisions. / Non-South Sudanese personnel fees decreasing as a proportion of overall personnel fees.
Adequate	POF interventions include provision for social inclusion, where applicable. / POF ensures that geographical focus areas are sufficiently varied (ethnically, geographically, in terms of conflict, etc.), and that selection reflects wider donor activity (i.e. selection does not focus on areas already receiving disproportionate attention).
Poor	Any of the conditions for adequate are not met

POF met criteria for ‘Good’ as the programme focused on reaching marginalised groups as part of its peacebuilding approach. This included designing activities to promote women’s participation in peace processes and working with women and youth in the creation of the Akut de door, Peace Farms and the Inter-communal Governance Structures.

Non-South Sudanese personnel fees decreased as a proportion of overall personnel fees over the lifetime of the programme. This was as its lowest in Year 3 with approximately 20% of expenditure allocated to non-South Sudanese personnel versus approximately 30% of expenditure allocated to South Sudanese personnel. The proportion of non-South Sudanese personnel fees increased in Year 4 when approximately 15% of expenditure was allocated to non-South Sudanese personnel versus approximately 10% of expenditure allocated to South Sudanese personnel. In the final Year 5, approximately 20% of expenditure was allocated to non-South Sudanese personnel versus approximately 25% of expenditure allocated to South Sudanese personnel.

Overall cost-effectiveness
POF’s approach to overall cost-effectiveness was to consider how it performed under the other 4 ‘Es’ of value for money. Overall, POF met the performance standard for ‘Good’. The programme made good progress in its structural value for money efforts – supporting Peace Canal to leverage FCDO funding further, strengthening equity arrangements, and continuing to manage economy drivers. However, under effectiveness, whilst the programme has strongly mitigated many of the conflict drivers, the context of conflict in South Sudan remains fragile.

E: Risk

Overview of programme risk during the past year and over the life of the programme, drawing on FCDO’s Risk Management Policy and Risk Appetite Statement and wider risk guidance.

The overall risk rating of the programme remained major throughout its lifetime within the risk appetite of BEJ. The programme operates in a high risk and very volatile context which required a proactive risk management approach. The risk appetites for strategy and context and safeguarding were receptive; cautious for policy and programme delivery; and minimal for public service delivery & operations, people, financial & fiduciary, and reputational. The risks identified remained the same over the life of the programme, except for a risk on the programme’s ability to deliver due to the COVID-19 pandemic, which was added in 2020 and closed in financial year 2022-23. Major risks for the programme over its lifetime were risks around safeguarding; reduced ability to operate in certain locations due to security risks, lack of progress of the peace agreement, or lack of support from key stakeholders; and the sustainability of the programme.

Safeguarding risks and mitigations were monitored throughout the programme, including the risks around SEAH of project beneficiaries. The annual review in 2019-20 recommended that all Peace Canal Area Advisers undertake training on safeguarding, fraud and anticorruption and OPM provided online safeguarding training to POF and Peace Canal teams. All POF and Peace Canal personnel signed a code of conduct as part of their contracts. Reporting mechanisms included a dedicated OPM email address to receive and deal with complaints, and community members reaching out to Peace Canal management directly to raise complaints.

There were no safeguarding cases reported to FCDO over the lifetime of the programme. There is significant underreporting of SEAH and GBV in South Sudan. Although this is due in part to stigma, harmful social norms, and lack accessible reporting mechanisms and service provision, no reporting remains unusual given substantial risks of sexual exploitation, abuse and harassment related to the programme context. Safeguarding risks and mitigations should be monitored closely in the second phase of the programme to make sure they are sufficient.

Recommendation 7: POF should work with partners to ensure that there are robust, community-based reporting and support mechanisms for SEAH, and strengthen the programme’s safeguarding approach.

Another safeguarding risk was the tracing, return, and reunification of abductees undertaken by mandated agencies could be poorly executed due to lack of coordination, inflexibility or speed of response. This could result in confusion or negative community reaction, impacting negatively on POF’s peace dialogue. There was also a risk that POF engaged in activities which breach the Modern Slavery Act (2015), including when working in environments with abducted women. OPM established policies on Anti-Slavery and Human Trafficking, and it is a requirement that POF and all POF partners and sub-contractors adhere to the policy, which is recorded in contracts.

Fraud risks included incomplete financial reporting, corruption and bribes resulting in diversion of funds. There were no cases reported over the lifetime of the programme. The programme also supported Peace Canal to strengthen fiduciary compliance systems but further support to this is needed.

Strategy and context: included risks around the progress of the peace agreement, the volatile political environment, and the security situation in South Sudan impacting on programme access. There was a risk that reforms and establishment of new institutions planned in the peace agreement and within the transitional government could reduce POF’s ability to operate in certain locations. Sub-national interventions could also threaten the interests and generate conflict with key personalities in national government, the military and political elites. The risk register also considered conflict sensitivity risks around unintentionally exacerbating tensions between key people. POF regularly monitored the political environment through analysis and consultation with BEJ and other key stakeholders at national and state levels.

Policy and programme delivery: included risks around a lack of cooperation from key stakeholders and the sustainability of the programme with the risk that after the POF exits a project location there would be renewed conflict. There was also a risk that Peace Canal would be unable to implement activities and retain personnel beyond the lifetime of the programme without securing core costs from donors. Whilst it was assessed that there was progress towards sustainability, this was not fully achieved within the lifetime of the programme. There was a risk that the programme’s work could be undermined if there were excessive demands on Peace Canal as it engages with other donors and partners beyond BEJ. There was also a risk that POF’s engagement with cultural institutions and traditional actors could inadvertently reinforce patriarchal norms and practices. The programme was monitored to ensure that women and youth voices were included.
F: Programme Management: Commercial and Financial Performance, Monitoring and Evaluation

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including VfM measures of economy and efficiency.

Over the lifetime of the programme there were periods of financial uncertainty and late budget allocations due to an overall reduction in the UK ODA budget. Financial management of the programme has been good with limited variances against forecasts. Financial reports were received on time with payments made in arrears. Audits were submitted each financial year, by both OPM and Peace Canal from financial year 2021-22.

BEJ and OPM have maintained a strong working relationship and collaboration improved over the lifetime of the programme with more regular meetings organised by BEJ. BEJ and OPM met fortnightly, and quarterly reports were always submitted on time. OPM submitted a final exit strategy for POF in 2023, which focused on continued momentum around core POF peacebuilding activities; facilitating the transfer of responsibilities and ownership of peacebuilding processes to Peace Canal, and facilitation of the transition processes to the POF2.

The original business case of POF proposed a fund manager model which would allow a greater field of access and scalability, with the option of bringing in funding from other donors and using multiple partners to balance risk. During the five-month inception period, OPM explored different delivery models and generated evidence to support the decision to move from a fund manager model to an advisory-led model. The benefit of this model was that area advisers could support communities to find a create solutions and opportunities to address the issues they were facing, ultimately strengthening the sustainability of POF. The fund manager model was assessed not to represent good value for money as contracting third party grantees would have added an additional cost. This approach was also resisted by the communities POF was supporting. The programme therefore shifted these funds to direct delivery of peacebuilding support and in-kind assistance. The assessment of the fund manager model also found that there were limited local CSOs and local actors in target areas for effective sub-granting. This led to the creation of Peace Canal which supports the expansion national peacebuilding organisations in South Sudan. The advisory-led model allowed POF area advisers to understand the location specific context and build levels of trust critical for establishing local peace agreements. This approach allowed POF to create a peace building system that is locally and culturally understood, and where issues can be raised and addressed.

Programme-level approach to monitoring and evaluation

POF programme was reviewed annually and included stakeholder interviews with beneficiaries and other organisations that collaborated with POF / Peace Canal. There were also field visits to programme locations. The programme was independently reviewed by Forcier in 2022 and the FCDO Women Peace and Security (WPS) Helpdesk in 2023. One FCDO annual review was carried out by a team independent of the BEJ programme team.

To support adaptive programming, the results framework was developed in a way that provided some flexibility, with milestones proposed and agreed each quarter by the BEJ. Output 5 was developed to enable BEJ to track activities and deliverables.

Women, Peace and Security (WPS)

In 2020, POF developed a WPS Strategy in support of the UK National Action Plan on Women, Peace and Security (2018-2022). This focused on women’s participation and addressing gender-based violence. A number of guiding principles set out in the Strategy informed activity design across all locations:

1. Working through existing women’s groups and leadership, aiming to strengthen relevant coordination and collaboration among them;
2. Ensuring women’s attendance at dialogue events and designing dialogue events to amplify women’s voice and designing in a way that their voice is reflected in decision-making at the dialogue;
3. Ensuring dissemination of examples of strengthening coordination and collaboration of women’s groups and leadership, and of amplifying women’s voices which are also reflected in decision-making. Ensuring follow-up have targeted mechanisms to implement and promote women-focussed elements;
4. Capturing qualitative women’s perspectives in ongoing monitoring, and evaluations of activities

An independent gender-sensitive review of POF found that the second phase of the programme should make integration of gender equality and social inclusion more explicit in programme documents, including the results framework (Recommendation 3). The programme could also seek to engage more with women’s rights organisations, to progress their work on women’s meaningful participation in peace processes further (Recommendation 8). BEJ should also look for opportunities for the second phase to coordinate with other programming that focuses on transforming gender norms and preventing gender based violence (Recommendation 9).

Date of last narrative financial report	22nd January 2024	Date of last audited annual statement	18th December 2023