Project Completion Review - Top Sheet

This Top Sheet captures the headlines on the programmes performance over the course of its lifetime. Teams should attach summary sheets from each annual review over the life of the programme.

Review Date:	February 2017

Title: Burma Education Programme
Programme Code: 202267	Start Date 6/12/2010	End Date: 31/12/2016
If programme was closed >1 month early please describe in a few words why.	N/A

Summary of Programme Performance

Year	2012	2013	2014	2015
Programme Score	A	A	A	A
Risk Rating	Moderate	Moderate	Moderate	Moderate

Financial Position

Original Programme Value	£10.5m
Extensions/ amendments	An £800,000 costed extension was approved in September 2015 to ensure continuity of support to the education sector up to December 2016. This provided flexibility for DFID Burma to respond to opportunities presented by the transition to a democratically elected government in early 2016.
Log-frame revisions (with dates)	December 2015 to cover extension to the programme and reflect recommendations from the Quality Basic Education Programme (QBEP) and Myanmar Education Consortium (MEC) mid-term reviews.
Total programme spend	£11.3m

Follow up actions required following closure
- Incorporation of lessons learnt into design of DFID Burma’s new education programme, cost and value for money (VFM) analysis.
- Review MEC evaluation report when received in July 2017 and support dissemination of learning including across the DFID office.
- Continued engagement with MEC through Steering Committee, including ensuring that recommendations from the evaluation are responded to.
- DFID to continue to press MEC to ensure transition plans are in place in areas where it is exiting, including for children with disabilities. Where possible building on efforts that have taken place in the last year to identify innovative practice, share lessons learnt and build partner capacity to identify alternative sources of funding and/or generate income.
DFID to continue to encourage and support UNICEF’s dissemination of learning from the programme, particularly on the findings of School-based In-service Teacher Education (SITE) evaluation and follow up dialogue with ministry and Teacher Education sub-sector working group (co-chaired by DFID) on teacher effectiveness, and on Township Education Improvement Plan (TEIP) to inform future activities to strengthen planning and management capacity at the township level.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-202267/documents
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-202267/documents

Outline of programme and what it has achieved
The Burma Education Programme (BEP) was a £11.3million investment over 5 years (2011-2016) which aimed to increase education access, improve systems efficiency and raise learning levels at basic education level in Burma. It was delivered through 3 main mechanisms covering both government and non-state education providers:
(i)	Quality Basic Education Programme (QBEP) implemented by UNICEF (£7.2m). This was a joint partnership between Australia, Denmark, DFID, EU, Norway and UNICEF. The programme aims to expand the number and proportion of children who access and complete quality basic education in the 37 core townships (11% of townships in Burma), strengthen systems for education delivery and build the evidence base for national policy making through the Comprehensive Education Sector Review (CESR).
[note] The coverage of QBEP activities varies across township i.e. quality of teaching interventions are carried out in 25 townships, school based ECCD in 11 townships, community based ECCD in a further 14 townships and non-formal/second chance components (NFPE and EXCEL) operate in 45 and 41 townships respectively.
(ii)	Myanmar Education Consortium (MEC) managed by Save the Children (£4.1m). This was a partnership with Denmark and Australia to provide support to complementary (non-government) education systems, community and school based early childhood development and non-formal education programmes for youths outside the mainstream education system. The programme provides direct funding and extensive capacity development to local non-state education providers (Ethnic Education Departments, civil society and non-state organisations) through calls for grant proposals.
(iii)	Technical assistance (£500,000) added under the cost extension to enable DFID to respond to opportunities arising with new government

Achievements
      - Majority of logframe output targets met or exceeded.
- Increased access, including to early childhood education and non-formal/second chance education in addition to primary schooling. Through QBEP 103,480 children gained access to Early Childhood Development (ECD) centres and alternative learning was delivered to more than 98,000 10-17 year old children.
- Improvement in teaching and learning environments, including provision of learning materials to 1 million children, training of 44,000 primary teachers, and life skills training to 35,000 secondary teachers.
- Balance of engagement in both public and complementary education systems. Providing support through both formal and non-formal schools allowed BEP to reach some of the most vulnerable children living in conflict-affected areas. It also made sure that the programme was aligned with DFID Burma’s peace-building work, and wisely spread the risk of DFID’s investment.
- Contribution to policy dialogue, support to development of National Education Strategic Plan
- Provided a platform to move towards system strengthening approaches – building relationships with government, development partners and other stakeholders; and supporting development of coordination structures. Having a multi-donor approach permitted easier government engagement on both sides when capacity of government was low and the Ministry was adjusting to new ways of working with development partners.

The BEP operated in a rapidly changing context, in which education reform remained a contested priority among all major stakeholders (including current and new government, ethnic armed groups). The CESR provided a framework to analyse and approach education reform, culminating in the development of the National Education Strategic Plan that was launched in 2017. The operational and political contexts at the design and closure of BEP were radically different. The original design and delivery mechanisms was appropriate at the outset and provided a best fit solution working with key stakeholder through viable education delivery mechanisms. Channelling support through both QBEP and MEC allowed DFID to make a strategic initial investment in Burma’s education sector with measured levels of risk and return.

During the programme period QBEP and MEC adapted to the changing operational context to varying degrees. The mid-term reviews (MTR) conducted in 2014 were instrumental in reviewing and steering programme direction. Following the reviews UNICEF developed a Joint Performance Improvement Plan (JPIP) and MEC produced a revised strategy to respond to the findings. At this point both programmes made a shift away from direct service delivery (including provision of learning supplies) and move towards strengthening government systems and building government capacity. MEC chose to focus on ethnic and monastic education provision where it had a stronger comparative advantage.

A partial National Ceasefire Agreement was signed in October 2015 and peace talks have been on-going since. However ongoing conflicts continue to impact on children’s education opportunities and have impacted on MEC’s work in Kachin, Northern Shan State and Kayin State. MEC was able to utilise its Education in Emergencies fund to respond to short term interruptions to education in Shan, Wa and Karen areas.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Outcome assessment
The BEP has made significant progress in achieving its outcomes to support more children to remain in school and to improve the quality of teaching and learning in schools that the programme intervened in. Between 2012 and 2015 enrolment increased by 3.35% in QBEP townships compared to a 1.52 % increase nationally. Evidence drawn from stakeholder interviews, project reporting, evaluations and review of progress against output targets, indicates improvements in learning environments and school readiness through early childhood care and development (ECCD) provision. Evidence on learning outcomes is more mixed. A QBEP assessment of learning outcomes found significant improvements in Myanmar language, but smaller gains in maths.

BEP interventions have provided a platform for change at school, township, state and national policy level. The sustainability of progress and interventions going forward varies. This has been affected by the extent to which activities have been able to address some of the external barriers and embed changes in institutions and behaviours. This has been an increasing area of focus for both QBEP and MEC following their mid-term reviews and subsequent more intentional work on systems strengthening. .

Overall output score
The BEP has scored an A overall, with many outputs exceeding expectations. It has consistently performed well achieving annual performance targets - making improvements to the teaching and learning environments in supported schools, expanding pre-school opportunities to give young children a solid foundation for learning and providing learning opportunities for children who have dropped out of school or never attended through non formal primary education and life skills programmes. The programme has made progress on improving management and accountability, by intensifying capacity building at the school and township level, but continues to be limited by the pace of decentralisation within the Ministry of Education (MoE).

Output		Impact weighting	Score
1	Improved ECD service delivery and coverage, particularly in poorer, rural areas	25%	A
2	Improved access to quality teaching and learning in schools	35%	A
3	Improved access to quality non-formal, alternative and life skills education	20%	A
4	Improved management of schools and accountability to local communities.	20%	C

The scoring was based on an assessment of achievement of output targets plus a review of additional achievements under each output area. QBEP support was scheduled to finish in December 2015 so no targets for 2016 were included in the logframe. Therefore 2015 targets have been used to assess performance. The MEC annual report will not be received until June 2017 in line with the Steering Committee’s agreed reporting schedule and provisional logframe updates were not available in advance, so results reported below are based on the June 2016 report and correspond to 2015 targets.

Lessons learnt
- The importance of analysing and clarifying the organisational structures of consortia when looking at risks to delivery, then agreeing a clear terms of reference and statement of cooperation amongst members of a steering committee/between donor partners and implementing partners/programme managers, which sets out how and at which level decisions need to made, and each member’s role. A statement of cooperation for QBEP was drawn up, but unfortunately never signed. Using the UN pooled fund mechanism rather than bilateral MoUs could have reduced the administrative burden, and would have compelled all partners to agree a ToR setting out ways of working, decision-making and reporting to ensure comparable expectations from all parties from the outset.
- The importance of ensuring that programmes respond fully to changing political economies around education and operate in a conflict-sensitive approach going beyond the minimum of do no harm to consider education’s role in peace-building and state-building processes.
- The importance of agreeing clear value for money measures with implementers and how they are going to report on these, and of having robust financial reporting processes in place, with greater disaggregation of data.
- In what has been a closed society, not underestimating the challenges of building civil society capacity in new areas, and the tendency for bidding organisations to stay in their comfort zone, e.g. the prevalence of ECCD projects in MEC – reflects the existing supply for services, with stronger proposals received for established approaches. Stronger targeting on priority areas needed which should derive from a needs assessment/situational analysis. Because of this, MEC fell well short of its logframe targets on non-formal education (NFE).
- The importance of facilitating coordination between complementary projects – despite the division between QBEP and MEC in terms of state and non-state education respectively, there were still a number of areas of crossover where cooperation could have leveraged better results. More strategic coordination with Pyoe Pin could also have potentially added value to BEP delivery, drawing on their political economy analysis.
- The importance of building M&E and learning into the implementation of programmes, so that learning is more systematically captured and shared with feedback loops truly embedded in delivery. This was particularly important during the piloting stage and when working with multiple delivery partners.
- Agree a communications strategy (both internal and external) at the outset, and what each member’s responsibility should be. As noted by the MTR, opportunities for effectively communicating QBEP’s achievements were missed.
- When working with UN agencies on programmes, particular attention should be paid to how to separate out that programme activity from their core business – as noted by the MTR, “the work plan for QBEP is subsumed within the UNICEF multi-year work plan”. This made it difficult to identify progress on the programme against the logframe and sometimes led to blurred lines in delivery
- When involved in a programme such as this, it is important for the donor partners to have relevant technical expertise in-country. DFID Burma had a full-time education adviser in country for only one year during the programme – and had to rely on part-time support from an adviser in DFID-India for most of the time. This made it difficult to ensure sustained high-quality oversight. Other donor partners also lacked full-time in-country education experts. This potentially restricted strategic technical discussions. It is welcome that DFID has now appointed a full-time education adviser in its Burma Office.
- Non-formal education initiatives that DFID funds should always look at addressing opportunity costs of attendance and identifying and reaching the hardest-to-reach and “invisible” children, considering ways in which to mitigate these costs including cross-office coordination.
- To review and update the DFID logframe more frequently in order to reflect changes to the programme and ensure that revised targets are set for any extension periods.
- The sustainability of programme components needs to be considered carefully with regular review of assumptions and potential factors that may limit sustainability so that implementation approaches reviewed accordingly. For example the evaluation of the in-service teacher education (SITE) component of QBEP found that, without a critical mass of SITE teachers in a school, the model did not function well, with teachers losing motivation to continue their training. Similarly lack of funding to support Township Education Improvement Plans (TEIP) limited their impact and the incentives for township education officials to engage in future planning processes.
- In the development of the logframe in a programme with multiple interventions and delivery partners, consider, carefully consider if it is appropriate for multiple programme components to report with exactly the same indicators and outputs. Outputs and indicators should remain well mapped to each intervention’s delivery and expected results with consistent methodology to ensure effective programme management, flexibility and ease of monitoring results.
- Ensure that the elements of a programme are collectively coherent and share an overall vision with a consistent theory of change. The initial activities of QBEP and MEC were based on prior programmes that shaped how results and implementation were conceived e.g. MEC started as five separate programme elements (3 existing projects, support for civil society voice, education in emergencies), and then had a grants programme added to support non-state education in difficult-to-reach areas). The revised approach and strategy then provided clearer focus.
- Consider incentives to encourage working in hard-to-reach areas. With quantitative results the numbers will always be low relative to effort and cost. Better indicators would be the contribution the project makes to developing systems, establishing equivalence and convergence with government provision; or the extent to which pathways and opportunities have been opened up; or the creation of shared learning.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Improved Early Childhood Care and Development (ECCD) service delivery and coverage, particularly in poorer, rural areas.
Output number per LF		1	Output Score	A
Risk:		Moderate	Impact weighting (%):	25%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
No. of children who have benefited from ECCD services	Baseline: 11,000 / 2015 target: 95,488 QBEP: 85,000; / MEC: 10,488	Achieved. / 2015: 112,571 / QBEP : 103,480, MEC: 9091 / Figures are not cumulative. In earlier years ECD access reached higher numbers, peaking at 152,257 in 2014 but results and targets were revised in 2015 following mid-term review.
% of ECCD centres that meet minimum quality standards / (School and Community Based)	Baseline: 5% for school-based. 0 for community-based / 2015 target: 20% school-based, 60% community based	Exceeded. / 87% community-based ECCD centres met minimum standards
Multisector ECCD national action plan/policy in place	Baseline: No plan / 2015 target: Multi-sectoral five year ECD National Policy Designed	Achieved. / Policy completed and disseminated in 2014. Roll out supported through KG teacher training, provision of KG kits

Key Points
Over the duration of BEP the number of children accessing early childhood education increased, surpassing original targets. Double the final target number of QBEP-supported schools now have ECD facilities for 3-5-year-olds, from a baseline of 10% to 37%. The quality of community-based ECCD improved throughout the course of the programme. The mid-term review team were impressed by the visible impact of QBEP on improving the quality of ECD facilities.

With QBEP support the ECCD policy was finalised in 2015 and QBEP then continued to support implementation. With steer from DFID QBEP activities focused on rolling out the new Kindergarten (KG) year in 2016/17 in support of the government’s curriculum reform process. This responded to an Annual Review recommendation and leveraged on QBEP’s strong relationship with the MoE. QBEP support has ensured that teacher modules have been developed for ethnic language teachers and bilingual teaching materials developed in 65 local languages.

ECCD was a significant initial investment for MEC, at its peak accounting for 50% of expenditure. The predominance of ECCD built upon the activities of founding partners rather than a strategic decision on investment in ECCD. This focus was revised after the mid-term review to prioritise investment in basic education and move away from direct service provision towards a more strategic engagement that emphasised MEC’s “value-added” in supporting linkages and exploring points of convergence between different providers.

441 ECD caregivers were trained through MEC, of which two thirds were observed demonstrating minimum competencies. MEC also established 588 ECD township networks to support delivery of ECD and quality assurance of provision. Efforts have also been made to support sustainability of community-based ECD provisions. For example one MEC partner, Metta, facilitated the establishment of revolving funds with communities to finance salaries of caregivers.

Summary of responses to issues raised in previous annual reviews (where relevant)
As recommended in 2015 Annual Review QBEP focused attention on roll out of KG element of national policy and took a leadership role.

Recommendations for future programmes
When choosing implementing partners build upon their strengths and comparative advantage as partners to maximise results. UNICEF were able to leverage on their national and international expertise on ECD to influence policy development and roll out, whilst MEC was able to capitalise on the in-country experience of its founding members and consider more strategic ways to support the ECCD sector beyond immediate service delivery, freeing up resources to invest in results elsewhere.

Output Title	Improved access to quality teaching and learning in schools
Output number per LF		2	Output Score	A
Risk:		Moderate	Impact weighting (%):	35%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
% of primary teachers applying improved teaching methods as defined by classroom observation criteria	Baseline: 2% / QBEP 2015 target: 35% of sampled teachers. / MEC 2016 target: 30% of trained teachers.	Achieved / QBEP: 38% by end date of extension (June 2016) – as found by a University of York independent study. / MEC: 2016 target exceeded by mid-2016, with a score of 75.25%
No. of primary teachers receiving training	Baseline: QBEP 3,900; MEC 0 / QBEP cumulative target 2012-15: 20,500 (QBEP’s own logframe set a final cumulative target for 2016 of 27,500) / MEC cumulative target 2013-16: 5,715.	Achieved / QBEP: 44,000 / MEC: Cumulative target exceeded by mid-2016, having trained 14,603.

Key Points
The business case had set out as an expected output that “1.1 million primary school children will have improved access to quality teaching and learning in schools”. Although the DFID logframe does not map easily onto the business case or theory of change therein, teachers applying improved teaching methods could be taken as a proxy measure of this; if 38% of the 52,170 of the teachers trained who applied improved teaching methods each taught a class of 50 children, then approximately 1 million children would have experienced access to quality teaching.

QBEP
Although the DFID logframe was updated at the end of 2015 to take account of the mid-term reviews of both MEC and QBEP, it did not set any 2016 targets for QBEP, despite that programme being extended until June 2016. In addition to the two indicators above, QBEP’s own logframe had the following output indicator for 2015-16: “Proportion of Grade 3 and Grade 5 students, by sex, achieving the minimum (50%) competency in standardised math and Myanmar language tests”. On Myanmar language, there was a significant increase from the baseline of 10% at G3, and 14% at G5. However, on maths there was only an increase of 2% at G3 and 4% at G5. The University of York evaluation found that there was a great deal of variation in results, suggesting that the QBEP intervention had not been well-implemented in some townships and schools.

In terms of access, QBEP used enrolment as a proxy indicator – this increased in QBEP-supported townships by 3.35% against a national increase of 1.52%.

38% of primary classroom teachers applying improved teaching methods is a significant increase on the QBEP baseline of 4% child centred classroom practices and child-centred teaching only taking 2% of lesson time (from a survey of 229 schools in 25 targeted townships), and the programme should be praised for achieving such results in a schooling system where the exams still encourage rote learning. However, the University of York evaluation found that many teachers were still under-using pair/group work, critical questioning, and use of assessment for the learning and inclusion of children with special educational needs.

There are a number of other activities that QBEP undertook which are likely to have improved access to quality learning and teaching (or will do so in the future) but which are not captured by the DFID logframe: the provision of essential supplies and textbooks to 2.5m children; the building or renovation of 30 schools and 43 temporary learning spaces; the upstream work with government which helped to produce the National Education Sector Plan, the first costed strategic plan for the whole education sector in Myanmar (the MTR noted that QBEP support to the Comprehensive Education Sector Review had “a major influence on the direction of policy discussions”); and six evidence-generation research studies to make the case for quality education.

The MTR team were impressed by the visible impact of QBEP on schools, and stated that QBEP activities were generally regarded as meeting needs and having positive effect, with the in-service training in particular was “regarded as making a major contribution”.

MEC
MEC has clearly exceeded its targets in this area. Their higher percentage score in terms of applying improved teaching methods is possibly due to the fact that the complementary education system does not impose the same exam and inspection systems as in the state sector. The MTR found that monastic schools had benefited from teacher and manager training through the Burnet Institute project. The MEC’s own logframe has the following indicator: “percentage of children fully literate after completing NFE classes”, with a target of 70%. It is notable that they achieved 78%.

Summary of responses to issues raised in previous annual reviews (where relevant)
The 2014 Annual Review made the following recommendation: “Following the decision to shift away from providing essential supplies (based on the MTR recommendation) DFID will need to agree a new output indicator for quality of teaching and learning for the final year of the with UNICEF. The output should include a focus on system strengthening”. The QBEP logframe already had an output on “systems supporting quality basic education strengthening”, but no such indicator was added to the DFID logframe.

The 2015 annual review recommended that MEC should work with UNICEF on lesson learning around UNICEF’s approach in Mon and success in building linkages between government and non-state systems, and liaise on future plans to ensure coordination. It also recommended that QBEP should develop strong communication tools for teacher education evaluations, and ensure that any new programming in education builds M&E into its implementation.

Recommendations for future programmes
- To review and update the DFID logframe more frequently in order to reflect changes to the programme and ensure that revised targets are set for any extension periods.
- In order to assess the impact of a programme on quality of teaching and learning, a greater range of or different output indicators would be helpful – it is doubtful how effective “% of primary teachers applying improved teaching methods” is as a proxy measurement for quality education.
- The sustainability of in-service teacher training outputs needs to be considered carefully. The 2016 Montrose evaluation of QBEP’s SITE programme (School-based In-service Teacher Education) found that, without a critical mass of SITE teachers in a school, the model did not function well, with teachers losing motivation to continue their training.
- Programmes should analyse carefully where interventions may not be supported by government systems (e.g. child-centred learning with continuous assessment versus an exam and inspection system which favours rote learning), and look at ways to improve those government systems – otherwise the interventions are unlikely to be sustainable or have the intended impact.
- In a programme with multiple intervention areas to improve quality and access the theory of change and results chain need to indicate how the impact is greater than the sum of their parts, and programme activities should more intentionally foster linkages to achieve this. .

Output Title	Improved access to quality non-formal, alternative and life skills education
Output number per LF		3	Output Score	A
Risk:		Moderate	Impact weighting (%):	20%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
No. of children who have accessed non-formal, alternative or life skills education	Baseline: QBEP 19,000; MEC 0 / QBEP cumulative target 2012-15: 82,000 / MEC cumulative target 2013-16: 5,300 / MEC 2016 target: 375	Achieved / QBEP: By end date of extension (June 2016), 48,000+ children aged 10-14 were enrolled in non-formal primary education (NFPE), and 50,000+ children aged 10-17 received Extended and Continuous Education and Learning (EXCEL) training on life-skills development. / MEC: 428 reached by mid-2016, target exceeded.
Percentage of reached out of school adolescents completing EXCEL in targeted townships (QBEP only)	Baseline: 85% / Target: 85%	Achieved / 94.5%

Key Points
The business case had set out as an expected output that “81,000 children will have improved access to quality non-formal, alternative and life skills education” and this was comfortably exceeded, largely due to QBEP.

QBEP
An independent review of the NFPE initiative found that it was increasingly successful in facilitating re-entry to the formal system (a 20% rate from L1 to G6), and was a “much-needed initiative”. However, it also found that the NFPE was not sufficiently flexible to access the hardest-to-reach children (e.g. the MLRC required students to attend an NFE centre six days a week for 11 months – impossible for those involved in seasonal work etc.). Other areas where the evaluation felt the programme design could have been strengthened included: more adequately addressing the opportunity cost of attendance; putting in place mechanisms to map out-of-school children and strengthen community ownership. Anecdotal evidence is that the majority of NFE students in these programmes were boys, since girls were required to stay at home to take care of siblings.
These are all areas where more could have been done to share between MEC and QBEP on how they had tackled these issues. For example the Scholarships for Street Kids programme under MEC had a more flexible school timetable and calendar to recognise children’s other commitments.

As for Output 2, there are other activities that QBEP undertook which are likely to have improved access to quality non-formal, alternative and life skills education (or will do so in the future) but which are not captured by the DFID logframe: the development of a national framework for non-formal primary education equivalency, and the provision of life skills training to more than 35,000 teachers, compared to their own logframe target of 30,000.

MEC
MEC’s targets for NFE were initially higher, but they were revised in 2015 to reflect final grant allocations and that fewer grants than anticipated were allocated to NFE. Whilst this was only a small component of MEC the projects that were funded had a positive impact on the children and communities involved. The review team was impressed with the quality of teaching in the Scholarships for Street Kids centre they visited in Hlegu, and the inclusion of children with disabilities. Parents spoke highly of the project and the positive changes they had seen in their children’s learning. They also appreciated the supportive income generation element of the project. They felt that the financial sustainability of the project after MEC funding will require more attention.

Summary of responses to issues raised in previous annual reviews (where relevant)
The 2015 Annual Review recommended that MEC should consider how non-formal education activities could be included within any future work with complementary education systems in ethnic areas. In the latest grant application round, MEC have worked with successful Expression of Interest stage applicants to undertake a comprehensive analysis of the education context in which they operate including NFE and the role that this has in providing alternative learning opportunities. Full proposals are yet to be received so applicant’s inclusion of NFE work cannot be determined at present.

Recommendations for future programmes
- It is important to have indicators that can show whether an output has been achieved; the two above focus on improved access, but do not evidence the “quality” aspect of the output title.
- NFPE initiatives that DFID funds should always look at addressing opportunity costs of attendance and identifying and reaching the hardest-to-reach and “invisible” children.
- In programmes with multiple components and innovative pilots opportunities for sharing of lessons learnt and implementation experience should be built into programme delivery plans as an expected way of working.

Output Title	Improved management of schools and accountability to local communities.
Output number per LF		4	Output Score	C
Risk:		Moderate	Impact weighting (%):	20%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Proportion of schools with operationalized School Self-Assessment programme (SSA) / School Improvement Plans (SIP) in targeted townships	Baseline: 0% / Target: 35% by 2015	Not met. Achieved in 22% of schools. / In addition to school-level plans Township education improvement plans (TEIPs) were produced in all 34 target townships and second-draft TEIPs in 25 out of 34 target townships.
# of townships with Township Education Management Information Systems (TEMIS) fully operational	Baseline: TEMIS partially operationalised in 3 townships / Target: TEMIS fully operational in 15 townships by 2015	Not met. TEMIS partially operational in 15 townships

Key Points
Whilst some progress was made on delivering QBEP activities and achieving logframe targets, a majority of the impact of activities appear to be localised and short term rather than leading to more sustainable improvement in the management of schools. An independent evaluation of the Township Education Improvement Programme (TEIP) undertaken in 2016, concluded that “the current design of TEIP will not suitable for scale up at all unless significant changes are made to the design, implementation and monitoring of TEIP”.

Two key assumptions behind the theory of change for the TEIP work did not hold true. Firstly, it was assumed that there would be funding available to support implementation of the plans, but this did not materialise. Secondly it was assumed that the national ambitions and pace of change for decentralisation would provide a conducive operating environment for TEIP, but this was not the case. Without these pre-requisites the impact of the TEIP has been limited and is likely to be unsustainable.

In addition planned linkages between the TEIP and the TEMIS did not materialise due to operational issues with TEMIS. Concerns raised in the mid-term review around TEMIS and the risks of establishing a parallel data management system led to pause on new project activities under this area, with TEMIS activities being restricted to supporting data analysis of previously collected data. Lessons learnt have been incorporated into discussions with the MoE in development of a new EMIS strategic plan.

Whilst a majority of activities delivered under this output were intended to be delivered through QBEP, it should be noted that MEC has also supported activities to improve accountability and parental engagement in schools. This included the formation of 2980 parent teacher associations (PTA) more than double of their initial target of 1254. Of these PTAs 4 out of 5 were operating to agreed standards.

Achievements:
The School Self-Assessment programme (SSA) / School Improvement Plans (SIP) activities appeared to have assisted many schools in identifying their needs and in formulating plans. The TEIP evaluation school survey results found that a majority of respondents considered TEIP to be relevant to the needs of their school (95%) and township (97%). However despite these very positive results the evaluation noted “significant weaknesses” with regards to the integration of TEIP with other activities. One interviewee reported that “the SSA/SIP, school grant and TEIP were not integrated intentionally… Since TEMIS was halted, TEMIS could not feed analysis of data for development of TEIP” Without TEIP activities being coordinated and embedded in government processes the likelihood of sustainability is limited.
[note] QBEP no longer provides school grants. From 2014/15 these are being provided by the MoE through a World Bank/DFAT funded programme.

Education planning capacity has been strengthened through the training of over 2,300 education administrators and creation of a pool of TEIP workshop facilitators with skills to support future education planning work. The TEIP evaluation noted: “That capacity was developed through TEIP is clearly evident, and an important positive finding of effectiveness was that unintended stakeholders were able to benefit from participation in the TEIP process, such as Deputy TEOs, Assistant TEOs, and male and female head teachers.” The evaluation also observed an attitudinal change of MoE staff in recognising the importance of collecting and utilising data for planning at school and township level.

Lessons learnt
- A clear theory of change and project objectives are essential to ensure integration with other activities and strategic direction for adaptation if there is are changes in the operating environment and assumptions behind the theory of change.
- When working in a transitional operating environment, a comprehensive risk assessment that is regularly updated is essential to ensure that activities remain appropriate and relevant.
- A comprehensive assessment of resources, capacity and needs should be the basis of investment into planning systems to ensure that they are demand-driven and appropriate.

Summary of responses to issues raised in previous annual reviews (where relevant)
Based on these limitations no new TEMIS activities have been approved under QBEP since the Mid Term Review and will not be until the evaluation is complete. TEMIS activities are restricted to ongoing activities, including data analysis of previously collected data

Recommendations for future programmes
It is important that discussions of risk and delivery regularly reassess project assumptions and provide space for proactive discussions to adapt approaches accordingly.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

QBEP expenditure January to December 2014 USD				MEC expense July 2013 to June 2016 USD
	USD	%			USD	%
Output 1: Early Childhood Care and Development (ECCD)	441,555	3%		Ethnic Education Systems Strengthening	1,733,043	9%
Output 2: Quality Education	6,071,642	35%		Monastic Education Systems Strengthening	3,328,171	17%
Output 3: Second Chance Education	3,063,472	18%		Policy Engagement	247,602	1%
Output 4: Education Leadership and Management	1,359,517	8%		Early Childhood Education	7,773,940	39%
Support to special targeted townships (Rakhine)	769,607	4%		Non-Formal Education	611,406	3%
Staffing costs and technical support	1,893,636	11%		Education in Emergencies	185,911	1%
Local office costs	735,073	4%		Capacity Building	500,033	3%
Comprehensive Education Sector Review and National Planning	1,456,124	8%		Monitoring & Evaluation	1,198,024	6%
Indirect cost recovery	970,952	6%		Management Costs	2,316,083	12%
Monitoring and Evaluation	455,391	3%		Indirect Cost recovery	1,836,309	9%
Total	17,216,970	100%		Total	1,733,043

The relative costs of different programme components have changed over the course of the programme in response to needs, the evolving political context, change of government and the MTR recommendations. For example, QBEP expenditure on ECD reduced from 13% in 2013 to 3% in 2014, whilst Second Chance Education increased from 9% to 18%. Education Leadership and Management increased by 6% and CESR and national planning by 5%. For MEC, spend on ECD and Education in Emergencies decreased in line with the MTR recommendations. Correspondingly spend on Complementary Education, Alternative for out of school children, and policy dialogue increased significantly, showing MEC’s responsiveness to its new strategy.

The DFID business case set out the following range of unit costs to support assessments of value for money:
- Teaching and learning materials: $10 per child per year.
- ECCD Provision: $50-$89 per child per year or 8%-15% of per capita GDP.
However, due to the changing context, these quickly became outdated, see below.

Economy
The DFID business case set out a number of principles on procurement and overheads. On procurement, these principles appear to have been met by both QBEP and MEC, e.g. competitive tendering was used for technical expertise procurement. However, the QBEP MTR identified potential opportunities for greater efficiencies in the UNICEF procurement and sourcing strategy, e.g. use of umbrella contracts and more efficient methods of supply to townships.

The largest expenditure item for QBEP was the supply of provisions for schools and ECD centres. This was substituting for gaps in teaching and learning materials in government schools, but came with high transaction costs for procurement and logistics. QBEP was able to influence the government’s policy decision to take on the supply of textbooks to schools. This allowed QBEP to reallocate resources to higher value activities, for example assisting the transfer of provisions through researching capacity gaps and providing support in the form of technical advice.

On overheads, there were some concerns for QBEP, especially around TEMIS, which did not appear to complement or help strengthen the existing government systems, and missed opportunities for rationalisation and simplification. In addition, staff overheads for QBEP were high (QBEP directly funded 38 UNICEF posts) and the MTR commented that better use could have been made of the available human resources, e.g. senior staff spent too much of their time overseeing administrative matters.

On MEC a Joint Management Review conducted in 2016 sought to assess the appropriateness of the management, governance and implementation arrangements and provide further assessment of the value for money of overhead and indirect cost recovery. This was in response to follow up on the MTR recommendations on overhead costs. The review concluded that MEC had an appropriate staffing structure to enable it to effectively delivery on project objectives. It also undertook a limited benchmarking exercise to support VFM assessment of indirect cost recovery. This concluded that “private sector entities charging management fees in the range of 20-30% compared favourably” with the indirect cost recovery of Save the Children as managing contractor. They also noted the unique context in which MEC is operating and that it is difficult to quantify the added value that the Save the Children network and their quality assurance role brings. The Joint Management Review also recommended that the delegated cooperation arrangement between the UK and Australia should not be continued in a way that might result in disproportionate administrative overhead costs being applied to DFID’s contribution.

Efficiency
QBEP’s total expenditure over the lifetime of the programme was $63.57m of the planned $76.6m (an 86% expenditure implementation rate) – a large amount of money to channel through a government education system with limited absorption capacity... Improved monitoring and evaluation could have identified earlier which interventions were effective, and which needed to be amended or stopped. This could also have allowed for a more strategic discussion on use of underspend funds to increase impact, depth or coverage of activities.

Benchmarking of operational costs has been difficult due to the limited number of implementing partners involved in similar activities, especially in the early years of implementation. However where possible it has shown that MEC’s unit costs have been lower than comparable alternatives. For example the 2014 annual review set out the following for NFE: “MEC Non Formal Education costs $124 per child, with construction of centres driving costs. To assess value for money, the cost for 2 years of non formal provision is compared with 5 years of standard government schooling, as graduates from the accelerated non formal programme should reenter formal schooling at grade 6. At $248 the MEC non-formal programme compares favourably with the cost of $440 for a full cycle of primary education. The main complementary education programme under MEC, supporting monastic schools, has a unit cost of $65 per child per year. This is below the cost for 1 year of government schooling ($88).”

The MEC Joint Management Review noted that between 2013-16 and average of 67.8% of funds went to partner activities, with the remaining funds being spent on MEC management support, overhead costs, technical assistance, monitoring and evaluation and capacity building, It also noted concerns about indirect cost recovery costs of almost 10% for the programme, which is high compared to the UK’s usual benchmark of 7%. However, the review states that, without market testing, it is difficult to ascertain whether the strengths of the MEC model (e.g. the simple contracting of the impressive Save the Children network) justify the higher costs.

Effectiveness
QBEP completed a large range of activities, and a number of these probably had an important impact on the stated outcome of the programme in the DFID logframe, “200,000 children supported to remain in school with increase in survival rates during early years of primary school and to Grade 5”. The impact on beneficiaries will have varied according to their exposure to different programme interventions according to township. There were potential missed opportunities to leverage additional value from having this range of activities. More intentional planning connecting up the results chains and theories of change for each intervention could have increased the impact and sustainability of the programme. UNICEF attempted to address this after the mid-term review with the revision of their logframe and output areas to simplify and pull together activities.

Data quality and availability is an issue in Burma, and the MTR noted that there is little evidence of the effects of QBEP’s multiple activities beyond the self-reporting of service providers. However, the MTR did find that QBEP was making a positive difference to teaching methodologies, that the ECD centres were popular with considerable community involvement, and that the second-chance education was addressing a large and pressing need. The Joint Performance Improvement Plan recognised data constraints and invested in research activities to provide further quantitative and qualitative impact, including on learning.

Following the MTR, the QBEP logframe outcome was revised to “increased likelihood that an inclusive, informed and actionable NESP and supporting structures are developed and implemented”. Changing the focus to this earlier could perhaps have given greater direction to the programme activities, and helped to maximise the impact of the programme. However, it is notable that the progress made in the CESR would “not have been possible without the support and nurturing that QBEP has provided” (MTR).

MEC did not directly contribute a great deal to the DFID logframe outcome, given its focus on ECD provision, accounting for over 50% of expenditure (as the MTR pointed out in, a country where many children miss out on basic education, ECD is not the highest priority, and is already a relatively crowded field). Its own logframe was geared to the delivery of the Founding Partner service delivery projects, with indicators that disincentivised working in hard-to-reach areas. The small scale of projects also meant that impact on service delivery was localised, and the Founding Partner projects depended on development models that were weak on sustainability. The lack of consensus for the first couple of years of MEC around its core purpose led to a focus on activity rather than outcomes, and the lack of clarity in its management and governance arrangements had a serious impact on its effectiveness. However, MEC responded well to the MTR, and has re-written its logframe and strategy, which now focus on education for the hardest-to-reach children. It also achieved a number of outcomes beyond the DFID logframe, such as civil society strengthening. Nine of the 12 organisations funded through the 2014 grant allocation are likely to carry on their work when MEC funding to them ceases in May 2017.
.
The Joint Management Review of MEC observed that MEC had been able to mobilise “several sources of high quality technical advisory and quality assurance support” and that this diversity of sources of technical expertise was a strength of the programme. The review concluded that MEC had used technical assistance effectively and that this support had provided valuable, quality inputs to the programme.

Equity
The business case set out that the programme should focus on the most vulnerable groups, and QBEP targeting of townships was carefully done to include areas suffering from poverty and exclusion. However, the business case also set out that data should be disaggregated across girls, boys and children with special needs; the QBEP logframe did not disaggregate by either gender or disability. It does not appear that QBEP achieved its stated intention of raising awareness of disability issues, and inclusion of disabled children does not appear improved.

Due to political circumstances, MEC projects in the early years had to be located in accessible areas, rather than those of greatest need. The MEC MTR notes that this could have contributed to an increase in the inequity of provision. However, 15% of the grant projects agreed had a specific focus on children with disabilities. Eleven of the 12 projects funded through the MEC bidding round are in ethnic areas.

Assessment of whether the programme represented value for money
UNICEF’s financial systems and the reports it is able to generate have, at times, limited the level of independent interrogation that development partners have been able to conduct to ensure accountability and value for money. UNICEF has taken steps to address this for example generating donor-specific financial statements

It has been questioned as to whether the geographical spread of townships chosen for the QBEP programme led to higher transaction costs and limited economies of scale that could have been achieved through delivery in consolidated areas. Indeed some gains were seen in later years through the whole of state approach in Mon State. However there were a number of operational, needs-based, political and contextual factors that influenced the choice of townships, and potential economy savings have to be balanced against equity considerations (reaching the most vulnerable) and factors that could have influenced the effectiveness of the programme. For example if QBEP had operated in one state or region this is likely to have impinged upon its level of influence on national policy dialogue.

Across both projects there is a mixed picture on value for money. When considered solely with regards to the outcomes and outputs in the logframe, which reflects more if the service delivery components of the programme that were a focus of the early years of implementation, the project may not have represented value for money. With some activities such as TEMIS that did not turn out to be a good investment of money. As the programme shifted towards more capacity building and systems strengthening approaches following the mid-term reviews, greater effort could have been made to capture the added value of different approaches – for example leveraging government resources for textbook provision – and QBEP in particular could have pressed further to improve value for money of some activities. In addition the support to the development of the National Education Strategic Plan, improving donor coordination, and as platforms to move towards system-strengthening approaches have been a worthwhile investment. These were over and above what was in the logframe.

Quality of financial management during programme
The QBEP MTR noted that “the programme would be much easier to manage if its chart of accounts were aligned to the main project components and provided better, more disaggregated financial information on the costs of operation”. This complexity in financial management probably contributed to the final underspend.

Date of last narrative financial report	QBEP: 31/03/2016 / MEC: 30/06/2016
Date of last audited annual statement	2016, covering period 2013-2015

E: RISK (½ page)

Quality of risk management over the life of the programme

Risk	Probability/ / Impact	Comment
1. Fiduciary risk through loss or misuse of funds or supplies	Low/High	Moderately realised: MEC found evidence of fraud in one of the 13 projects it originally funded through its bidding round. It withdrew this funding.
2. Policy climate is unfavourable to change	Medium	Not realised: in fact, the policy climate changed so quickly that the programmes struggled to keep pace – QBEP was slow to reorientate to the new situation and opportunities it offered, and MEC’s bidding round was brought forward (perhaps with insufficient preparation, which brought its own risks).
3. Government seeks to restrict or control implementing partner activities	Medium	Not realised: due to the opening up of Burma, this was not really an issue.
4. Access to certain areas is restricted due to conflict or other reasons	High/Medium	Realised: the ongoing conflict in a number of states made it difficult to gather data and carry out M&E. It also increased the costs of reaching children in these areas.
5. Delays in establishing consortium mean that funds cannot be channelled flexibly to new partners	Medium	Moderately realised: both programmes started later than planned, and the lack of clear governance arrangements created issues around funding flows.

Given the changing context in Burma, the risk register in the business case (above) quickly became outdated, and each of the programmes drew up their own more detailed risk registers.

QBEP
Neither UNICEF nor its donor partners foresaw some of the risks that materialised in or affected this programme: the lack of English language translation capacity within MoE; the lack of absorption capacity in terms of funds by government ministries; the problems of retro-fitting a programme approach onto large areas of UNICEF’s core business in Burma; the lack of educational technical capacity amongst donor partners; the absence of clear governance arrangements; TEMIS creating a parallel system to the government’s own monitoring system, rather than helping to strengthen it; the cost and impact implications of target townships being geographically spread out and separated; and the absence of independent evaluation of pilot projects and feedback loops. However, following the MTR, QBEP updated its risk register, and risk management improved, with a greater focus on gathering evidence and evaluating implementation.

MEC
Given its focus on NFE, MEC is a risk-taking programme; the quality of the initial assessment of external risks to the programme was generally good, with sound mitigating actions. However, there was a failure to consider the internal risks of not having clear terms of reference, reporting structures, and organisational management. This had a negative impact on the programme, as detailed above. As the programme progressed, there was also a failure to identify the risks of the bidding round in terms of the local friction it would cause when some organisations received funding whilst others in the same area (but of different ethnicity, religion etc. did not); more input from DFID conflict advisers could have helped avoid these risks. In addition, the data requirements for the bidding round included information that posed security risks to the CSOs involved (these requirements were largely imposed by the donor partners. MEC reviewed their risk register every six months

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
Overall both programmes remained largely on track to deliver against milestones. However the political transition and nature of delivering in conflict-affected areas affected both QBEP and MEC. Consequently at times there were some delays, resulting in project underspends at points during programme delivery. Significantly for QBEP, the MoE’s departmental restructuring process left them without a designated focal department to deal with necessary fund flows between UNICEF and MoE for ongoing activity implementation. It took nearly six months to negotiate and establish fund flow processes with new departments during which delivery was delayed. The government changes delayed launching of the National Education Sector Plan (NESP) till end of 2016 and delayed some programme activities.
MEC’s financial expenditure and programme delivery largely progressed as expected, although there were delays in 2016 linked to revision of MEC’s strategy and delaying of grants to ensure that they reflected the revised strategic approach.

Performance of partnership (s)
As a multi-donor funded project QBEP provided coordination leadership amongst development partners, acting as one of the primary engagement points with government at a time when such partnership engagement was only beginning. This helped lay the foundation for subsequent bilateral engagement. However it was not always an easy partnership. The mid-term review concluding that “lack of transparency in sharing information and problems of communicating and reporting the programme have strained relations between UNICEF and partners”. The lack of established partnership principles from the outset resulted in different expectations amongst partners on leadership, decision-making, reporting and UNICEF’s role. This meant that Steering Committee meetings often focused on programme management and partnership issues rather than strategic or technical discussions. However UNICEF reported that they appreciated DFID’s inputs into the Steering Committee, our constructive voice and the technical expertise that we were able to bring, particularly on issues such as gender, inclusion and work with civil society.

A Joint Management Review of MEC in 2016 concluded that “MEC is well positioned to deliver the programme and to play an influential role in Myanmar’s education system”. The review commended MEC and Save the Children as the fund manager for their adaptation to the evolving context in Myanmar and response to the mid-term review. In addition feedback from their partners as part of this review identified MEC’s strong management and ability to develop positive relationships and trust with a range of partners as some of the project’s key strengths. This has been particularly critical for MEC in their role in supporting stronger partnerships and strengthening dialogue and points of engagement with ethnic education providers.

Asset disposal and value obtained by DFID
There is no issues have been identified with asset management practices. MEC have installed asset monitoring and control guidelines for all three asset types; MEC management team, founding partner projects and development fund partner projects. An assessment of partner’s financial policies and asset management practice was conducted prior to contracting. All partners are required to maintain asset registers and compliance is monitored through quarterly reporting and monitoring by the MEC management team.
UNICEF has a global asset monitoring and control policy which every country office mist be complaint with, and that policy is published on their website. UNICEF is responsible for due diligence and asset checks of downstream partners.
DFID conducted asset inventory spot checks and found no irregularities. Asset lists submitted in late 2016 for project closure.

G: CONDITIONALITY (½ page)

Partnership principles assessment

The DFID Burma partnership principles have been updated in October 2014 (Quest No: 4654477). In line with these principles the education programme does not provide any funds direct to government. QBEP provides funds to Township Education Office activities but all funds are channelled through QBEP Township bank accounts to ensure that partnership principles are not contravened.
BEP’s operation and ways of working have been consistent with the partner principles, particularly regarding support for commitments to achieve sustainable development goal 4 on ensuring equitable access to learning (principle 1). Both MEC and QBEP have proactively sought to support children’s right to education (principle 2) and create opportunities to improve accountability for education service delivery at school level and through national policy dialogue (principle 4).

H: MONITORING & EVALUATION (½ page)

Both programmes generated robust research and learning through the course of their delivery. Both mid-term reviews pointed to need for greater efforts to improve the emphasis on learning and sharing internally and externally and recommended improved efforts to more systematically capture learning and communicate this. Within QBEP as well as improved knowledge management and communication stronger feedback loops needed to be instituted to ensure that programme delivery was more intentionally learning from evidence and adapting in response. Following the mid-term review UNICEF recruited an evaluation specialist and undertook a series of research studies in response to recommendations. This included the evaluations of SITE and TEIP the findings of which have been discussed above. Reference groups were established for these studies, including government officials to build ownership for the studies and to support dissemination.
MEC made significant efforts at project outset to put a robust M&E framework in place. This was revised following the md-term review to allow for greater breadth. An end of programme evaluation was completed for the three founding partner projects and an evaluation is currently underway for the development fund partner projects. The endline findings are expected by June 2017.