  Programme Completion Review

Title: Accelerated Reform Facility (ARF)
Final Programme Spend £ (full life): £15 M	Review Date:	September 2022
Programme Code: [AMP ID#] 203601	Start Date: 04 Oct 2012 (AMP)	End Date: 30 June 2022

Summary of Programme Performance

Year	2013	2014	2015	2016	2017	2018	2019	2020	2021	2022
Programme Score	A	A	A	A	A	A	B	A	B	A
Residual Risk Exposure Rating	Low	Low	Medium	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case (and any addendum):	https://devtracker.FCDO.gov.uk/projects/GB-1-203601/documents
DevTracker Links to all logframes used during programme lifetime:	https://devtracker.FCDO.gov.uk/projects/GB-1-203601/documents

List of Abbreviations

3MDG Fund	Three Millennium Development Goal Fund		MESC	Mandalay Electric Supply Corporation
ADB	Asia Development Banks		MoEE	Ministry of Electricity and Energy
ARF	Accelerated Reform Facility		MPs	Member of Parliament
BIF	Business Innovation Facility		MSG	Multistakeholder Group
BSP	Business for shared Properties		MUPE	Myanmar UK Partnership of Education
CCW	Crowe Clark Whitehall		NECC	National Economic Coordination Committee
CPG	Cooperation Partner Group		NGO	Non- Government Organisation
CSO	Civil Society Organisation		NLD	Nation Ledge Democracy
DFAT	Department of Foreign Affairs and Trade		NPT	Nay Pyi Taw
DFID	Department for International Development		PCR	Project Completion Report
DIHR	Danish Institute for Human Rights		PFM	Public Financial Management
EfECT	English for Education College Trainer		PO	Programme Officer
EITI	Extractive Industries Transparency Initiative		PPA	Power Purchase Assessment
FCDO	Foreign Commonwealth and Development Office		PPPs	Public Private Partnerships
GoM	Government of Myanmar		PRO	Programme Responsible Owner
GP	General Practitioner		RWI	Revenue Watch Institute
HMG	Her Majesty Government		SLGV	Speaking Listening Grammar Vocabulary
ICJ	International Committee of Jurists		SOEEs	State Owned Economic Enterprises
ICU	Intensive Care Unit		SOEs	State Owned Enterprises
IDP	Internally Displaced Persons		SRO	Senior Responsible Owner
ILO	International Labour Organisation		SWIA	Sector Wide Impact Assessment
IPC	Infection Prevention and Control		TA	Travel Authorization
IPE	Irrawaddy Policy Exchange		TREE	Towards Result in Education and English
JICA	Japan International Cooperation Agency		UNICEF	United Nations International Children's Emergency Fund
KPIs	Key Performance Indicators		VFM	Value for Money
			YESC	Yangon Electric Supply Corporation
MDRI-CESD	Myanmar Development Resources Institute-Center for Economic and Central Development		YGHR	Yangon General Hospital Reinvigoration

A. Summary and Overview

Description of the programme and what it has achieved

The FCDO Myanmar’s Accelerated Reform Facility (ARF) was £15 million programme to respond quickly to opportunities, created by the reform process, to support interventions that catalyse, foster and deepen reform in Myanmar from September 2012 to June 2022.

The ARF was established to focus on six strategic pillars to create a better governed, more peaceful & prosperous Myanmar that uses its increased wealth to reduce poverty. The six strategic pillars of the ARF are:
1. Good governance and public financial management
2. Promoting responsible investment
3. Improving transparency, accountability, and the rule of law
4. Strengthening the work of Parliament
5. Helping the process of ethnic reconciliation
6. Better coordination and aid effectiveness

The military coup on 1 February 2021 brought to an end a period of ten years characterised by various reform efforts. At the outcome level, it is hard to judge what, if any, progress made by the reform processes supported by the ARF will be sustained though the political, economic and human crisis which has been created by the 2021 coup. In the period before the coup, some progress was made across several of the ARF strategic pillars. Myanmar improved public financial management, attracted more investment, grew rapidly, and reduced poverty. At the same time access to the internet increased massively, people in Myanmar became more connected with the outside world, and some social norms started to change. However, progress was inconsistent. Myanmar remained highly centralised, the rule of law remained weak, the armed forces retained a veto in Parliament and control of several key Ministries, citizenship laws continued to be exclusionary, and Buddhist extremism and Bamar nationalism became more powerful political forces. The Rohingya crisis of 2017 which led to hundreds of thousands of people fleeing to Bangladesh in the face of brutal attacks by the Myanmar military, forcefully highlighted the deep and complex challenges facing the country.

At the output level, there is good evidence that the ARF programme enabled the UK to respond quickly to opportunities to support core reform objectives in a complex and rapidly changing context. ARF Projects focused on strategy, policy, influencing and donor/aid effectiveness, complementing the wider UK Myanmar portfolio with the ability to respond swiftly to opportunities and challenges which were not duplicated wider FCDO programmes. The programme delivered value for money by ensuring each project focused on the key strategic pillars, supported change in Myanmar and worked with key reformers in piloting successful strategic and policy interventions that are low-cost but high impact.

Further Background

This programme was initiated in the context of President Thein Sein’s administration and the suite of reforms introduced after 2011. It continued through the period of NLD government from 2015 and its final components closed in the light of the 2021 attempted coup. This was an extremely fast-changing and complicated period in Myanmar’s history, and this programme sought to provide flexible support to processes of reform, openness, and democratisation.

Projects funded under the ARF were chosen based on them meeting the following criteria:
- The likelihood that the proposal will be transformational
- Complementarity with actions by other actors
- Delivery of tangible results within 18 months
- Key risks to UK
- The HMG programme management implications of the proposal (including the management of HMG financial resources)
- Where relevant, the likelihood that the proposal will create further opportunities to deliver against the six areas in future

Major lessons learned, evidence generated and recommendations

The programme enabled rapid responses in Myanmar’s highly fluid operating environment during a complex and unpredictable reform process. The results delivered both in areas directly covered by the projects and indirectly by supporting and influencing results in other areas. The ARF demonstrated success in piloting projects that could then be taken over by larger, sectoral focussed DFID Myanmar programmes, where they complement and reinforce other interventions. Overall, the ARF provided a valuable and necessary mechanism in enabling DFID to provide quick support to the reform process.

There were many projects funded under ARF programme. The programme management burden and frequent changes of ARF programme oversight posed risks to overall programme management. Management of small ARF projects were time consuming and resource intensive, although the benefits largely outweighed the costs.

The programme achieved value for money by having DFID directly engaged in critical areas where deeper understanding of context (e.g., Rakhine State which changes so rapidly) was needed, by creating platforms for larger scale work (e.g., work on health sector institutional linkages), and filling critical gaps.

FCDO should draw lessons from the ARF as a tool for supporting reform and look for appropriate ways to continue support its healthcare reform initiatives in particular. Critical lessons learned include:
- The importance of a timely and effective approach to respond to opportunities in a way which builds trust and creates opportunities for dialogue.
- The need to prioritise opportunities in order to avoid a portfolio of too many small projects that will increase complexity and programme management burden.
- The importance of an office wide discussion to help prioritise and understand linkages.

How this report was conducted

This report was led by the ARF oversight Programme Team SRO, PRO and PO. The review was given inputs by the thematic Lead Advisers and Programme Managers of the ARF projects including Economic Advisor, Governance Advisor and Conflict Advisor. Most findings and recommendations of this review are drawn from the ARF Annual Review documents and project reports. The documents referred to are the project documents of each of the projects supported under the ARF programme.

The “Foreign, Commonwealth & Development Office (FCDO)” was established on 2 September 2020 to merge DFID with the Foreign Office. The references to “Department for International Development (DFID)” in the review relate to events before September 2020. References to Foreign, Commonwealth & Development Office (“FCDO”) are for recommendations going forward or the things that happened since the merger.

All references to engagement with the Government of Myanmar in this review concern activity prior to February 2021; no element of this project has engaged with the regime since the attempted coup.

Actions following approval of this report

All projects funded under ARF programme have been completed and successfully closed. There are no outstanding actions with partners. Programme team will ensure the risk register on AMP and Delivery Plan are updated as necessary following this review and then archive the programme on the system for full closure. ARF programme oversight team will complete a sensitive information review of the PCR report before external publication.

FCDO should continue to think about how to maintain a strategic approach to reform opportunities. In the coming period many of these may be best addressed through the planned peace and local governance programme. Nonetheless a wider office discussion is required to ensure future interventions are strategic and appropriate.

## B: Theory of Change and Outcome Assessment

	Starting point	Final result
Budget	£15m	£11,788,326
Timeframe	September 2012 to April 2014	October 2012 to June 2022
Outcomes	Short term results that strengthen long term reform in the ARF focus areas.	There was no change to the outcome statement over the course of the programme. Table 1 below provided the details of achievements against each project.

Overall assessment of programme outcomes, sustainability and VfM

At the overall outcome level, it is hard to judge what, if any, progress made by the reform processes supported by the ARF will be sustained though the political, economic, and human crisis which has been created by the 2021 coup. The 2021 coup and the subsequent descent of Myanmar into an economic, political and security crisis, has set back expectations for sustainable progress towards the overall expected longer-term outcome.

The ARF was designed to enable DFID to move quickly to support the reform process in Myanmar. The impact that the ARF was expected to contribute to is: “a better governed, more prosperous Myanmar that uses its increased wealth to reduce poverty”.

To deliver this impact, it was always intended that the ARF would opportunistically finance interventions that arise in the fast-paced changing peace context to maximise the potential benefits opened up by political reform. It was accepted that it would do this by financing strategic and catalytic interventions, which are independent and discrete and so do not necessarily contribute to result in a single combined outcome.

The ARF was conceptualised and managed as a basket of interventions – allowing the UK to catalyse opportunities and manage risks - rather than as reform portfolio attempting to drive an impact greater than the sum of its parts. Again, this makes it difficult to assess overall outcome (especially as some of the reform processes it supported – especially EITI – achieved their greatest impacts after they had graduated from ARF support). However, it was a pragmatic approach given the contextual complexity and unpredictability.

At the same time, it is important to recognise that most individual ARF projects delivered outcomes in the short term against at least one of the ARF criteria. Individual projects played a critical role in influencing and catalysis in the areas of health, education, climate, infrastructure, aid effectiveness policies. Much of this progress has been undone by the post-coup crises, but some has been sustained.

Output level scoring

It was not expected that each project funded would deliver against all of the six outputs, nor necessarily to allocate equal weight to each of these areas. Instead, it was designed to support key reforms falling under a number of new priority areas identified by the Secretary of State. Therefore, it is not appropriate to judge it against whether it achieved outputs under all areas, but rather to judge whether the projects chosen were successful at achieving their goals and at least one of the criteria set out above. The scoring is therefore a qualitative assessment of whether this has been the case. We have also given weights to different outputs on the basis of the amount of total spend at the end of the projects contributed to each output.

The ARF swiftly adapted to a range of new challenges and contexts, including post 2015, post 2017, and the Covid crisis. This was done either by pivoting the project milestones or re channelling funds to areas of greatest emerging need while maintain focus on the original intended purpose. With the unpredictable and challenging context since 2017, the ARF approach evolved to include responding to both opportunities and challenges in the policy space. It demonstrated flexibility and identified areas of potentially high impact with low-cost interventions (e.g., climate change, durable solutions in Rakhine).

As a result of the COVID-19 crisis in Myanmar, there were understandable delays of some of the projects and the projects adapted to respond to Covid crisis. Summary of key achievements of each project under the ARF programme against the outputs are as below.

Output	Share of spend	Output Score	Foundation for further investment?	Strategic learning?	Strategic Impact?	Notes
1. Better Governance and Public Financial Management	32%	B		Yes – on how the health sector really works	Yes. supported COVID response.	Learning on health sector and strong UK- Myanmar linkages have been sustained post-coup.
2. More Responsible Investment	40%	A	Yes. Three projects scaled up	Yes – on opportunities to scale up business support.		Provided the basis for three important areas of UK funding covering responsible business, inclusive business and English language education.
3. Improving Transparency, Accountability, and the Rule of Law	9%	A+	Yes. Basis for World Bank Support	Yes – on EITI and civil society.	Yes. Supported EITI candidate status	Creating foundations for support to EITI was arguably key outcome for the ARF
4. Strengthen Parliament	1%	A	Yes. Basis for DFID Governance programme	Yes. On the challenges of working in NPT.		Help to build relationship between UK and Myanmar Parliaments
5. Helping the process of ethnic reconciliations:	14%	C		Yes. Learning about the challenges in the process		Both interventions highlight the risks around spoilers to complex peacebuilding processes.
6. Better donor coordination and aid effectiveness	4%	B		Yes. On the challenges of working in NPT.		Liaison office in NPT provided the basis for HMG platform planning (currently on hold)
Total	100%	A	Yes. At least 5 good examples of scale up.	Yes. Supported sectoral learning and insights		Challenges of managing a complex portfolio and the need to embed strategic objectives and monitoring

ARF’s contribution to gender and inclusions and how it meets the Gender Act

The support to Rakhine project worked on the needs of marginalised communities, including people in camps, the needs of girls who excluded with particular force from education, and the needs of volunteer and community teachers - mostly women - was central to this work, as well as the identification of ways in which child protection was embedded in safe learning. At the request of the Union Minister, a programme to ensure that the benefits of inclusive education were extended to children (girls and boys) with special education needs in and beyond Rakhine State. NPT office work with the Ministry of Social Welfare Relief also supported this objective.

Overall value for money

Myanmar’s reform process from 2012 to 2022 was complex and contradictory. Reform efforts were often driven by committed individuals within the system who required timely support and advice to build momentum. Some efforts quickly faltered; others made significant progress. To generate VFM in such a context, efforts to support reform need to be able to (i) accurately understand the reform context and identify the most promising opportunities; (ii) provide timely high-quality support in an economic and efficient way; and (iii) review progress and learn in order to inform decisions graduate/scale up or cancel the intervention.

Overall, the ARF generated a VFM by providing an appropriate, flexible, mechanism for small interventions, where separate full Business cases would have been disproportionate, allowing UK partners to engage rapidly in response to opportunities that appeared unpredictably across a broad range of potential areas. Management of small ARF projects is time consuming and resource intensive, but the benefits outweighed the cost when projects where carefully selected to open new opportunities for larger scale work (e.g., work on health sector institutional linkages or on sectoral infrastructure policy), and to support learning and deeper understanding of context (e.g., funding high visibility projects in Rakhine State) which benefited the broader UK portfolio.

Economy and Efficiency: Every drawdown submission for funding from the ARF was assessed against the criteria set out in the original ARF business case. These criteria were strengthened further during the £10m cost extension approved by the Minister of State in 2014 and by the addition of a requirement to demonstrate how projects would comply with the International Development Gender Equality Act 2014. Economy and efficiency were reviewed as part of this process. The majority of project funded under the ARF delivered against their objectives within or below the original costs set out in their financial plans. The cost drivers for each project were different but the predominant cost was consistently the recruitment of personnel to conduct the studies, the training or the convening and coordinating. The fee rates for these personnel were carefully considered as part of the project preparation. Further detail is provided in the output descriptions.

Effectiveness: It is hard to assess effectiveness of the ARF projects, because in many cases it is not possible to accurately attribute impact to ARF interventions. The ARF often helped to provide early support to help a process build momentum (e.g., the ARF supported Myanmar to join the EITI process and facilitated early CSO engagement). It was therefore one of a suite of interventions that supported outcome level impacts. However, it is true that most projects achieved outputs in areas that were key for reforms and provided DFID with a mechanism to respond quickly to reform opportunities. The completed projects delivered against some, or all of the criteria set for the ARF.

Equity. By working in a public hospital through RGHR project, the ARF programme ensured that women, men and children in need benefit from the changes. This included a focus on safe access to buildings, which is a neglected area of public health provision. Also, the work in the Rakhine state provided benefits for women in this remote area and in the IDP camps. NPT’s works with the government on disability agenda provided excellent value for money by influencing appropriate disability policies.

## C: Detailed Output Assessment

Output Number and Title		1. Better Governance and Public Financial Management
Output Score		A
Impact weighting (%)		32%	Impact weighting revised since last AR?	Yes (68%)

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score.

Two projects funded under this output. These complemented other work in the DFID Myanmar portfolio, in particular the Public Financial Management programme, infrastructure through InfraCo and the health sector through the 3MDG fund. This output is scored at ‘A’ as the achievement of components under this output met expectations.

1). Technical Assistance for Public Private Partnership (PPP) Framework Development (203601-114)
[£1,026,000, 01 May 2014 – 31 December 2017, Asian Development Bank]

Only 33% of households in Myanmar get access to electricity with a substantial variation of electrification rate in Yangon at almost 80% and the average rate in the rural areas was as low as 16%. The Government of Myanmar targeted 100% electrification by 2030. The government had a limited administrative and technical capacity, and budget to implement a full coverage of electricity access across the country. The Ministry of Electricity and Energy (MoEE) was a regulator as well as a service provider creating a challenging enabling environment for private investors.

DFID provided a technical assistance on Public Private Partnerships (PPPs) for the Ministry of Electric Power through this project. It was led by the Asian Development Bank, and it helped the Government negotiate better deals with the private sector in the area of electricity. It also helped them better understand the fiscal implications of PPPs for better manage public finances as they expanded access to electricity. This project was initially meant to run for 18 months. It ran for 3 years and 8 months mainly due to the change in government in 2015 and lack of cooperation of the Ministry of Electricity for a time.

Deloitte India was contracted by ADB to deliver the outputs of i) designing a framework for international competitive bidding for facilitating public-private partnership (PPP) investments in Myanmar targeting the electric power sector; ii) applying the framework to real business by proposing a list of potential projects and applying the international competitive bidding (ICB) methodology; iii) proposing an institutional design and management of PPPs; and iv) recommend the options for management of PPP projects at national level. Output number (ii) took time for the MOEE to realize the full usefulness of the draft framework and apply it. Due to this reason the output was modified with (i) Evaluation support for the Yangon 300 MW rental power plant (ii) Assistance in managing Power Purchase Agreements (PPA) by providing training of staff of the Electric Power Generating Enterprise in best practice of PPA management; and (iii) Conducting a study on infrastructure sharing which was to understand the use of public infrastructure for private business. One of the tasks was to analyse the use of existing rights-of-way of a transmission line for fiber optic cable for telecom business.

This project made significant achievement in the following areas: (a) Project selection, short – listing and profiling for PPP (b) Devising an International competitive bidding framework for power generation PPPs in Myanmar (c) Institutional Design and Management of PPPs (d) Public Finance Management for PPPs (e) Capacity building initiatives. The Ministry was not ready to provide ongoing project procurement support and as a result the project was not able to deliver overall national management of PPP projects.

Most of the outputs agreed with Asian Development Bank were delivered by 2017 including the corporatisation roadmap of Yangon and Mandalay Electricity Supply Corporation (YESC and MESC) during project extension period until end of 2017. Deloitte India, contracted by ADB, had extensive consultations with YESC and Mandalay for the final corporatisation roadmaps in November 2017 which was received well by respective management team from YESC and MESC. The final corporatisation roadmap was submitted to the Ministry of Electricity and Energy in December 2017. The corporation roadmap study was shared with National Economic Coordination Committee (NECC).

2). Funding Project Management of Restoration and Reinvigoration of Rangoon General Hospital (203601-116)
[£2,745,434, 05 December 2014 - 31 January 2021, Rangoon General Hospital Reinvigoration (RGHR) Charitable Trust]

DFID supported the Rangoon General Hospital Reinvigoration (RGHR) Charitable Trust to reinvigorate Yangon General Hospital (YGH) from 2014 to 2021. The project was first identified in a report prepared by Lord Darzi of Denham in 2013. It secured the support of Imperial College London’s world class team. The project helped the Government assess how to manage and prioritise public funds to revitalise health services (a major priority for public investment across the country).

Yangon General Hospital needed huge investment to rebuild the hospital and meet the expectations of people in Myanmar – to reflect modern ways of working and global best practice and technology. Under the project, three key outputs contributed to the overall ARF objectives:
- A detailed masterplan for the work required to support the reinvigoration of Yangon General Hospital.
- The comprehensive renewal of the medical curriculum and associated learning infrastructure.
- The quality improvement initiatives for General Practitioners (GP), through British expertise and professionals to deliver substantive and lasting change as a part of the wider health system reform.

These outputs contributed to the ARF outcome of better governance and public financial management. The masterplan set out a proposed governance structure and funding plans to drive more efficient use of growing government healthcare budgets. The most urgent items in the masterplan were implemented before the coup: fire safety as oxygen provision increased to meet the need for additional Intensive Care Unit facilities, renewal of essential utilities to improve patient safety across the YGH estate, installing new hand wash facilities for important wards and continuing work on sewage improvements. Before the coup, the medical curriculum reform project and GP quality improvement works engaged international experts including UK health professionals. RGHR were able to deploy the UK’s leading engineers (who also delivered the UK’s Nightingale Covid-19 hospitals) and medical experts to deliver substantive and lasting improvements in YGH and medical education sector.

In the context of the COVID-19 pandemic, RGHR prioritised activities that had the most immediate relevance to the crisis, and to pivot, where possible, towards activities that would support the resilience of the Myanmar healthcare system, especially at the Yangon General Hospital. RGHR reviewed the whole programme, adapted, or cancelled some programme’s activities if they relied too much on travel of experts into the country. RGHR diverted funding to COVID-19 mitigation project with particular focus on the Infection Prevention & Control (IPC) requested by the Ministry.

RGHR work in YGH paused following the coup in 2021, however, the established relationship and trust between UK and Myanmar health professionals through the RGHR programme was maintained to continue to improve clinical practices, skills and knowledge of medical professionals to improve quality of care and saving lives in the complex post-coup political environment. RGHR’s final audit report was submitted in July 2022.

Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme

PPP (203601-114)
As this was a technical assistance project, most expenditure was on consultants’ fees and capacity building activities. Economy was assured through the use of ADB tendering processes. The Ministry was not ready to provide ongoing project support to prepare profiles including the analysis required for competitive bidding. As a result, the project was not able to deliver objectives around overall national management of PPP projects. However, the project generated other important impacts, including broader understanding of the public financial management aspects of PPP, and greater interest from the Government of Myanmar (GoM) in how to develop the national level PPP management framework.

RGHR (203601-116)
The RGHR project prioritised COVID-19 responses in addition to its original plans and made savings across all projects to achieve this. Some activities had been cancelled, redesigned and cut to undertake new COVID-19 responses works. RGHR project supported well-informed decision making by the ministry which improved the efficiency of broader development funding. For example, the national ICU plan developed with the support of Cambridge Yangon Trauma Intervention Project informed the Ministry’s decisions to make the very best use of the funding. Building on the established professional relationships between different partners and donors included shaping the World Bank funding available for development of Intensive Care Unit (ICU) services.

Lessons learned through this output, and recommendations for future programming

PPP (203601-114)
Strong understanding of institutional politics, incentives and capacity is needed to inform project identification and design; and projects need to be designed to be able to adapt in order to respond to changes in the context. The expected outcome of Public Private Partnerships (PPPs) project (203601-114) was to improve institutional capacity to direct and manage public-private partnerships at the individual ministry level. The Ministry was not ready to provide ongoing project procurement support and as a result the project was not able to deliver overall national management of PPP projects. Some members of National Economic Coordination Committee (NECC) showed their interest to reform State Owned Economic Enterprises (SEEs) in the power sector.

RGHR (203601-116)
Under RGHR project (203601-116), the established relationship and trust between UK and Myanmar through RGHR program contributed to continued hospital improvements, medical education reform, improving clinical practices. FCDO should continue to draw on the relationship established through the ARF as a tool for supporting Myanmar health care actors to provide quality health care and life saving medical supports in the challenging political situation.

Output Number and Title	2. More Responsible Investment
Output Score	A
Impact weighting (%)	40%	Impact weighting revised since last AR?	Yes (0%)

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score.

Two projects contributed to increasing responsible investment in Myanmar. Two of these either helped to initiate or were absorbed into larger sectoral-focussed programmes. The responsible investment and inclusive growth study provided the basis for the successful BIF programme. EfECT was transferred to DFID Myanmar’s new education programme Myanmar UK Partnership of Education (MUPE) in mid-2017. The ARF therefore played a useful role in piloting work which was subsequently successfully scaled up. The output scored an A.

1) Promoting responsible investment and inclusive growth (203601-102)
[£93,224, 10 September 2012 – 31 March 2013, Price Waterhouse Coopers LLP]

The scoping study for the Business Innovation Facility (BIF) in Myanmar promoted inclusive business and led to the creation of a standalone multi-year project funded from the DFID Myanmar budget working in the garments and tourism sectors. The review concluded that the project clearly met the criteria set out by the ARF, most notably by creating an opportunity for DFID Myanmar to deliver strong results under this output in the future.

2). EfECT – English for Education College Trainers (203601-113)
[£2,950,749, 20 August 2014 – 31 October 2017, British Council Yangon]

Following a visit to London in September 2016, the Myanmar State Counsellor Daw Aung San Suu Kyi noted that English language training was vital, and she recognised the excellent work that the British Council was already undertaking in this area. She wanted to improve the language ability of civil servants, particularly those working in the trade and finance ministries. By improving English language skills, the project would support Myanmar people to engage more effectively in international trade and investment discussions conducted in English. Proficiency in English would allow Myanmar people to study international human rights law and trade regulations. It would also enable Myanmar to enter constructive dialogue on the conduct of businesses looking to invest in the country and would give future business leaders confidence in determining those investments beneficial to its long-term development.

Although the ultimate rationale for the project was focused on the impact on business, it quickly evolved a stronger proximate focus on supporting the NLD government’s education reform efforts. DFID Myanmar strengthened its partnership with the British Council to use EfECT to engage more effectively on strategic issues at the national policy level and it liaised with other DPs working in teacher education to streamline activities where possible. This was the first project with staff in all teacher colleges and EfECT trainers were therefore a valuable resource and used to strengthen design of future interventions, an example is EfECT trainers agreed to pilot the new English curriculum developed by JICA. DFID established a core donor group on teacher education issues to strengthen coordination in the absence of formal structures. This group were the first donors to be asked to feed into the design of the sub-sector law on Teacher Education by the team who led the process.

Key achievements of the project included: Over 2,200 Teacher Educators undertook a year of English Language teaching and methodology. In 2016, 50 EfECT trainers were working across al 24 education colleges in Myanmar. Teacher Educators’ confidence in using English improved (according to feedback from the monitoring in June 2017). Six out of ten key performance indicators (KPIs) were met. Over 80% of the core beneficiaries improved their English proficiency test score by at least one CEFR band and over 75% improved their overall confidence in their use of English and their teaching skills. Over 80% improved their theoretical knowledge of teaching methodology.

An independent evaluation of the EfECT project conducted in June/July 2016 (Vault no 5587242) reported positive impact such as:
- Without exception, the classes visited were characterized by a very positive learning environment and good rapport among teacher educators and between the trainers and the teacher educators.
- While differences in trainers’ individual teaching styles and strategies were evident, the quality of the teaching observed was always satisfactory (and in most cases very good).
- The training material had a positive experience for the teacher educators. It impacted on teacher educators’ knowledge, confidence and (to varying degrees) teaching.

Phase two of EfECT project from July 2017 was funded through DFID Myanmar new education programme Myanmar UK Partnership of Education (MUPE). However, phase two of EfECT project – Towards Results in Education and English (TREE) was terminated in March 2022 due to the contextual and political limitations after the coup.

Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme

EfECT (203601-113)
Negotiations on proposals considered economy, efficiency, and effectiveness. British Council Myanmar could drive the optimal use of available resources to achieve intended outcomes. Beneficiaries reported satisfaction with English classes, interactive classroom management, training activities, teaching practice sessions with FIT materials and pedagogy which was implemented by British Council Myanmar in education colleges across Myanmar.

Lessons learned through this output, and recommendations for future programming

EfECT (203601-113)
In EfECT project, there was a programme board, which DFID was not part of, responsible for setting direction. If there had been more DFID involvement, the extension of the project could have been planned differently laying the ground better for a smooth transition. DFID could have been stronger in managing the process in terms of regular discussions, monitoring on stakeholder management and outreach/impact of the programme. DFID should have encouraged the British Council to do more stakeholder engagement in planning the extension or involved the trainers more. Learning from this project, the Myanmar UK Partnership of Education (MUPE), project funded under the new education programme of DFID from 2017 to 2022 built upon the successful EfECT project and designed in a more sustainable approach, more integrated programme into the state’s system and more robust monitoring and evaluation.

Output Number and Title	3. Improving Transparency, Accountability, and the Rule of Law
Output Score	A+
Impact weighting (%)	9%	Impact weighting revised since last AR?	Yes (0%)

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score.

The three projects under this output contributed to achieving Myanmar’s candidacy status in the Extractive Industries Transparency Initiatives (EITI).
The UK facilitated two visits by the EITI Secretariat in 2012 – invited by the Myanmar Government on both occasions. The commitment to join EITI was reiterated by President Thein Sein at the United Nations General Assembly in September 2012 followed by a Presidential Decree of 14 December 2012 establishing a cabinet-level Leading Authority to oversee the implementation of the EITI. Myanmar made rapid progress in its bid to be an EITI compliant country by becoming a candidate country in July 2014, just 18 months after the President announced the country’s intentions and 13 months after our funding of these projects commenced.
Achieving EITI candidacy status had a transformational impact on budget transparency. There was a rapid and significant improvement in the transparency of questionable revenue from the Extractive Sectors (natural gas export accounts for 40% of total export in 2013), providing an opportunity for Myanmar to better ensure that natural resource revenues are used for the good of its people. This was vital in a country where these revenues already contributed 45% of the Government’s budget and were expected to grow. The project became a flagship for the Government of Myanmar and DFID Myanmar.
These projects complemented other work that DFID Myanmar undertook, particularly on civil society strengthening and public financial management. EITI successfully graduated from the ARF. Further funding to support EITI process (including through the World Bank EFO) were provided through the extractive component of Public Financial Management programme. This was good evidence of a successful ARF projects being mainstreamed into a larger business case.
Overall, this output exceeded expectations and scored an ‘A+’.

1). Coordinating the Extractive Industries Transparency Initiative (EITI) process in Myanmar (203601-109)
[£274,281, 01 May 2013 – 31 October 2014, Myanmar Development Resource Institute - Centre for Economic and Social Development (MDRI-CESD)]
Myanmar Development Resource Institute (MDRI) was nominated as a coordinator for EITI in the President’s December 2012 speech, and the project was to intend to equip MDRI to submit the EITI candidacy application. MDRI successfully implemented the formation of multi-stake holder group known as MSG and submitted the application of Myanmar to the EITI Board on May 2014. The application was considered by the EITI candidacy board meeting in Mexico in the first week of July 2014 and Myanmar was accepted as a candidate country. MDRI-CESD worked with Ministry of Finance to handover coordination responsibilities as national secretariat.

2). Support the Extractive Industries Transparency Initiative (EITI) application of Myanmar (203601-110)
[£413,000, 29 May 2013 – 28 May 2015, The World Bank EFO]
The ARF provided support through the World Bank to help MDRI to submit Myanmar’s application. This allowed MDRI to benefit from the World Bank’s technical expertise and constituted the core technical advisory support to the Myanmar EITI process. It delivered the EITI scoping study and legal review, the Political Economy Studies of Extractive Sector and a variety of trainings and workshops. Moreover, it contributed to World Bank engagement in essential EITI dialogue and coordination during the start-up-stage. These activities in large measure contributed to the achievements including constituency-building, the functioning of the Multi Stakeholder Group (MSG), and the successful candidacy application which was approved in July 2014.
3). Support local civil society to promote improvement in the governance of the extractive industries, including through participation in and implementation of the Extractive Industries Transparency Initiative (EITI) (203601-111)
[£323,838, 01 September 2013 – 30 April 2015, The Revenue Watch Institute (RWI) /Natural Resource Governance Institute – NRGI]

DFID funded the Revenue Watch Institute (RWI) to undertake (i) a scoping study of potential support to civil society on EITI and (ii) the delivery of a basic EITI training course to civil society. Revenue Watch Institute (RWI) was renamed to Natural Resource Governance Institute (NGRI) in mid-2014. The RWI team completed their two visits in–country including three training sessions on EITI in February 2013. The project resulted in a project proposal by RWI for a two-year project to support civil society engagement to the EITI process. DFID and DFAT jointly funded the follow-on project.

The NRGI Myanmar project played a key role in enhancing the capacity and coordination of key stakeholders in the EITI process. This project supported local civil society to pursue improvement of extractives governance, including through participation in and implementation of EITI. Activities were implemented directly by NRGI or in collaboration with civil society partners. These interventions formed part of a broader framework of civil society support for EITI. NGRI successfully delivered below against the agreed outputs which were assessed in the project evaluation report marked as impressive progress.
- NRGI and MDRI, worked closely with Pyoe Pin to support the first national civil society conference on EITI – bringing together 226 representatives from over 100 civil society organizations across the country in October 2013. MATA (Myanmar Alliance for Transparency and Accountability) was born there as a significant result. MATA was one of the main drivers of effective CSO representation on EITI.
- NRGI assisted the organization of the civil society constituency, including coalition building and selection of representatives. NRGI also facilitated numerous workshops with MATA and training for trainers to MATA members from 14 regions/states to enable them to deliver their own awareness-raising workshops. It facilitated CSO representatives from the region and delivered regional training on extractives.
- NRGI also delivered trainings to 20 representatives from Government side on EITI. The NRGI informed public debate, strong civil society coalition, skilled experts, improved enabling environment and local level participation.

Myanmar became an EITI candidate country during the project initial phase. The NRGI Myanmar project was continued and funded centrally beyond this project along with other 7 focus countries. The NRGI’s country strategy for Myanmar developed in close consultation of DFID Myanmar and other stakeholders in country.

Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme

This strand of ARF was highly successful and delivered good VFM. The intervention was highly effective: Myanmar joined EITI and catalysed significant improvements in transparency. Revenues shared with and flowing from the extractive sectors, the role of State-Owned Enterprises (SOEs) and ‘decision to extract’/licensing at the subnational level were all made to public as a result of the EITI process. The ARF programme created a very valuable space, that allowed the UK to provide coherent support to the EITI application and implementation process through different mechanisms and implementing partners. Based on the success of the ARF pilot phase, a new programme on Public Financial Management was developed – under which EITI projects were funded. This continued until February 2021 when the coup took place. Although the progress has been put back by the coup, the EITI process is likely to have formed a new benchmark for public expectations around effectiveness.

Lessons learned through this output, and recommendations for future programming

DFID continued to support the EITI implementation process for a further 5 years following the initial ARF start-up support. The dynamics around transparency changed: Myanmar made significant progress on budget transparency, shedding light on once-tig revenue and production data in oil and gas, mining, and forestry sectors. The coup in February 2021 put all EITI implementation to an end. This PCR recommends supporting and/or re-picking up EITI implementation not only for the transparency and accountability but also for contributing to tackling climate change once changes in the country context make it possible to re-engage.

Output Number and Title	4. Strengthened Parliament
Output Score	A
Impact weighting (%)	1%	Impact weighting revised since last AR?	Yes (0%)

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score.

There are three projects funded under this output. Overall, the activities under this output met expectations and concluded to score this output an A. The first two pieces of work helped to provide a foundation for furthermore sustained engagement with Parliament through the Democratic Governance Business Case. All engagement with Parliament was put on hold following the coup. We do not know how much of the progress supported in this area before the coup will have been sustained.

1). Strengthening the work of parliament (203601-104)
[£5,692, 2012 – 2013, DFID]

At the request of Aung San Suu Kyi, DFID supported three MPs from the Myanmar Parliament’s Draft Bill Committee, working on education legislation, to visit Westminster to learn how the UK process functions. The cross-party visit, which took place in the week of 17th December 2012, was endorsed by the Speaker of the UK House of Commons, and included sessions with him, Parliamentary Counsel, Parliamentary Committees, the FCO, Cabinet Office and DFID’s Minister of State. The visit was widely applauded by ASSK, the UK Parliamentary officials and the British Ambassador.

At the invitation of the British Secretary of State for Education, the Myanmar Minister of Education visited the UK in January 2013 to attend the Education World Forum. At the Minister’s request, DFID supported his travel expenses. This visit was an excellent opportunity for the Myanmar Minister of Education to be exposed to the latest debate on policies to extend the opportunities of learning to all students and we were able to organise useful meetings with the DFID Minister of State and the British Council in the margins.
2). Support to strengthen Myanmar Parliament by providing an international expert in drafting laws (203601-108)
[£53,424, 20 January 2014 – 28 February 2015, DFID]

Secondment of an experienced legal draftsman of a high international standard to Myanmar Parliament in Nay Pyi Taw from 10 July until 4 September 2013.

The draftsman, Michael Wright conducted legislative drafting training for members of the Bills Committee, other Parliamentarians, and private lawyers. This was requested by ASSK who was the chair of an informal committee that coordinates international support to Parliament. DFID received positive feedback on the training of Parliamentarians, including from Aung San Suu Kyi and her office.
Michael Wright completed a brief report on law drafting which set out practical recommendations on how to improve it in the short to medium term. The report showed a good understanding of the opportunities and challenges of law-making in relation to the Myanmar Parliament and made good recommendations for the way forward. It also influenced further the IPU and clerks from the UK Parliamentary support for the Myanmar Parliament.
A Research Service Development Plan was written setting out the actions required for establishing a research service over the following six months and beyond. MPs responded positively to the new services. Over 2000 copies of the Research Briefings were taken by members in the first two weeks. The Speaker, Daw Aung San Suu Kyi and other committee chairs praised the content and format of the Briefings and requested the Research Service to provide similar briefings on all major Bills to help members to scrutinise legislation.
The assignment achieved its specific objectives in terms of outputs and created stronger relationships within the Parliament than expected which gave a good platform for future work at that time. Overall, the assignment was a success and delivered results.

3). Local translator to support secondment of UK House of Commons research expert to the Myanmar Parliament (203601-112)
[£60, 2019]

In addition to the above-mentioned support, DFID also funded through the ARF, the translation and interpretation services for the House of Commons seconded Senior Library Clerk (a specialist in parliamentary research) to the Myanmar Parliament.

Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme

These interventions provided a strategic entry point for continuing UK work on Parliament. Building on the first two ARF funded interventions, DFID Myanmar continued to co-fund (with the UK House of Commons) the strengthening of the Parliament Library & Research Services (through a secondee) under the Democratic Governance Business Case.

The assignments helped us to understand the VFM context for working with Parliament. They delivered relatively good value for money in terms of economy (fee rates etc), but they also demonstrated the high coordination and support costs associated with working in Nay Pyi Taw - including accommodation and translation services.

Lessons learned through this output, and recommendations for future programming
Setting up these relatively small pieces of work took significant advisory and staff management time in DFID Myanmar, included arranging the contract, liaising with Parliament, arranging visa and accommodation, and translation services, the latter in particular took some time. It is important to recognise the impact of these costs on the office.
Whilst the request for support from Parliament appeared clear, in fact circumstances on the ground were more complex. This included the fact that other training for MPs was happening at the same time. This meant that Michael Wright had to be flexible and adapt his programme.

Output Number and Title	5. Helping the process of ethnic reconciliations: increased understanding of key actors in Myanmar on the strategic stakes and the mechanisms by which peace and reconciliation can be negotiated.
Output Score	C
Impact weighting (%)	14%	Impact weighting revised since last AR?	Yes (0%)

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score.

The three main projects contributing to this output aim to build trust and increase the understanding of key actors in Myanmar on the mechanisms by which peace and reconciliation can be negotiated. Although the projects under this output delivered significant pieces of work and there was early evidence of changing mindsets and increasing understanding, there were concerns about project management and challenges related to the results tracking systems and programme delivery. Over the period it became clearer that bringing people together and building mutual understanding would not be sufficient to provide a straightforward route to peace. The deep challenges, and the extent to which spoilers were prepared to go, were graphically illustrated by the horrendous murder of U Ko Ni as he returned from an ARF funded exposure trio. The output score of ‘C’ reflects the difficulties in delivering sustainable outputs in this context. It is consistent with the resurgence of widespread violence in Myanmar following the coup.

1). Establishment of a small fund for low-cost high visibility Projects in Sittwe (203601-118)
[£149,486, 2018-2019, DFID Myanmar]

The complex situation in Rakhine was exacerbated by the 2012 violence between Rakhine and Rohingya people. This further intensified in 2017 when over 700,000 Rohingya fled to Bangladesh in the face of a brutal operation by the Myanmar military. The remaining Rohingya population believed to be around 600,000 are now either living in camps in central Rakhine or confined to their villages across the central and northern part of the state.

This work was intended to engage with a range of stakeholders in Rakhine using visible, swift, low cost - quick impact projects. It aimed to counter the narrative that the international community was not listening to the requests of communities, and to build understanding of the situation and stakeholder perspectives. The interventions complemented DFID Myanmar’s support to all communities in Rakhine State through the longer-term sectoral programmes such as LIFT and the Access to Health Fund and the international humanitarian assistance provided by a number of UN and INGO agencies. The approach of the project was in line with the Principles of Engagement for Rakhine agreed by donors in Myanmar.

The project identified the gaps in support across a range of issues identified by communities. The fund identified small scale activities implemented directly by DFID. These included the funding of classroom spaces, and water and sanitation activities which did not cost more than £50,000 for each small activity. The project funded the production of a communications strategy which was subsequently implemented on behalf of the wider international community via the LIFT programme.

The project was closed in 2019. This decision reflected our recognition of the very high management costs associated with ensuring strong direct project management of a portfolio of small projects in a high-risk context and the need to have a stronger strategic framework to drive decision-making on small projects.

2). Supporting a more inclusive political settlement: Knowledge for Nation Building (203601-117)
[£1,326,113, 01 July 2015 – 31 June 2018, Proximity Designs]

This was an ambitious project funded through Proximity Designs on “Knowledge for Nation Building” to help influence the emerging political settlement. The purpose of the project was to equip Myanmar’s divided leaders and their constituencies with critical knowledge to make more informed decisions, seek consensus, compromises, and political settlements.

The following challenges and achievements of three outcome statements from their result framework contributed to the output 5.
- Proximity Designs developed good relationships with senior members of the Military, the new government and ethnic leaders. This had the potential to create a space for good relationships to be formed between these groups.
- Eight research papers, six essays/memos and three case studies were produced and presented to the target groups. These papers were overviews of themes or attempts to bring together multiple issues, rather than deep dives or serious academic research. Research around jade revenue sharing was not sufficiently robust and did not take sufficient account of one group’s likely position and so was met with a backlash on social media and there was some reputational damage to Proximity.
- This project organised a visit to Indonesia by senior Myanmar military generals to discuss the role of the Indonesian military in Indonesia’s transition to democratisation. During the trip a dispute between religious groups erupted in one of Myanmar’s states. Soon after the trip the activity underlying the dispute was ended. Sample stakeholder feedback reported by Proximity suggested that the participants in the visits developed increased understanding of opponents’ positions.

Human-resource constraints in the Proximity project team impacted on implementation, although the partner responded the majority of DFID AR recommendations. The dreadful murder of U Ko Ni had a huge impact on the project and the project team. The project closed in June 2018 without being able to achieve all the activities in the agreed workplan.

3). Creations and delivery of plan for sustainable change in Rakhine State (203601-124)
[£133,024, April 2020 – February 2021, The Irrawaddy Policy Exchange (IPE)]

The project to create and deliver a plan for sustainable change in Rakhine State was structured between DFID and IPE. Some of outputs and timings changed in response to the the COVID19 pandemic, but the overarching goals of work remained in place. IPE was in the process of supporting the Myanmar authorities to develop a new Roadmap for change (based on the duty to implement the Rakhine Advisory Commission (RAC) and Independent Commission of Enquiry recommendations); a Comprehensive Education Plan for Rakhine (draft was completed, and consultations were planned with Rakhine State partners); and work on camp closure and healthcare (meaningful next steps to improve access to services for displaced people in and around the camps at Kyauk Ta Lone and Mye Bone, co-created with CDNH and Professor Kaelin). The tensions around the 2020 election slowed the speed of delivery of the work, then the 2021 coup brought it to a full stop.

Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme

Overall, this strand of work has offered poor value for money. This assessment is largely based on the challenges in delivering effectiveness rather than problems with the economy or efficiency of project implementation (arguably we should have paid more for project management of the knowledge for nation building project to address the human resource constraints). The potential benefits from work on peace are huge, but so are the risks. Two of these three projects failed to deliver because these risks crystalised.

Knowledge for Nation Building (203601-117)

Lessons learned through this output, and recommendations for future programming

- Investments in peace are high reward/high risk bets. We need to be realistic about the potential for action by spoilers.
- Limited Human Resources in the partner project team for Knowledge for Nation Building directly affected implementation and made it difficult to deliver as planned. Skilled programme management is important to monitor project progress, respond to management matters and deliver activities effectively as planned.
- DFID Team should have regular informal meetings to provide the technical inputs to ensure frequent engagement with Implementing Partners on a mutually agreed workplan and more accurate financial forecast/management to achieve the planned activities of each project.
- Finding high quality technical translation was a key challenge in Myanmar in providing knowledge support and analysis provided to leaders of key stakeholder groups, to support decision making on critical issues.
- It was a challenge to measure impact when its outcomes are related to long term changes such as peace building which is hard to quantify.

Output Number and Title	6. Better donor coordination and aid effectiveness
Output Score	B
Impact weighting (%)	4%	Impact weighting revised since last AR?	Yes (32%)

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score.

There are four projects funded under this output. The output score of B reflects the contribution that the projects made to donor coordination fact that two of projects delivered according to expectations. The other two projects had more limited impact because of the reduced space for work on climate and environmental awareness following the coup.

1). Joint Liaison Office in Nay Pyi Taw (203601-106)
[£356,141, 2012 – 2021, DFID and DFAT]

The DFID-DFAT liaison office in Nay Pyi Taw was funded jointly by DFID Myanmar and the Australian embassy. The Launch of the office in 2012 attracted significant media attention with government Ministers warmly welcoming the move. The joint office was successfully set up as a steppingstone to a UK office which would allow the UK to gradually scale up staffing over the medium term in Nay Pyi Taw. This approach was consistent with enhancing overall HMG presence with a view to a future Embassy move eventually.

Other donors and development organizations used the space, and it also provided a platform for HMG staff to drive forward specific agendas with counterparts in the capital, the international community and the engagement with government officials, Parliamentarians and implementing partners/beneficiaries based in Nay Pyi Taw. Regular reports from the liaison office helped to improve UK engagement with government.

There were some key risks around the viability and sustainability of the approach, and the expectations of the Government of Myanmar which was pushing formal commitments to move Embassy. The process to move the office formally onto the HMG Platform was delayed due to the COVID-19 crisis. The office was then closed following the coup in February 2021 (we terminated the lease and kept the situation under review).

2). Additional Funding for the Cooperation Partners Group (CPG) Secretariat (203601-119)
[£60,000, 2019, UNDP]

The funding was to ensure the Cooperation Partners Group (CPG) Secretariat could continue its work to coordinate development donors and to ensure coherent information sharing. The following activities were completed.
- Produced materials for CPG monthly meetings, including agendas, talking points, pre-meeting briefs, meeting summaries, updates on sector coordination groups and work streams and action points.
- Facilitated bimonthly meetings with the CPG Facilitators to plan and track CPG work.
- CPG meetings with Government entities such as the Development Assistance Coordination Unit (DACU) and Foreign Economic Relations Department (FERD), as well as with other Government Ministries, coordination bodies
- Collated and shared aid and development cooperation information for the benefit of the CPG, including strategies/policies, studies, assessments, records of meetings and contact lists. In collaboration with MIMU shared knowledge on, and promoted understanding of, development cooperation with other stakeholders, including Government, parliament, INGOs, CSOs and the private sector.
- Supported and retained strategic overview to CPG Work Streams to ensure coherence across the work streams. Although work streams were self-managing, the CPG Secretariat helped ensure overall updates of strategic progress made under the work stream are regularly provided to all CPG members.
- Set up funding donor co-ordination mechanisms for effectively prioritise development needs and areas of cross-over.

3). Policy on Infrastructure and Climate Change (203601-120)
[£20,954, 2019-2021]

Key achievement under this component included the development of two short pieces of analysis on current status of coal in Myanmar and the Myanmar energy sector gaps analysis. The evidence collected was intended to shape the direction of the Hlan Chi programme energy pillar. However, following budget reductions, the energy sector was excluded from the GRD portfolio. A Policy Officer funded from this component contributed to UK engagement with decision makers to make the case for more inclusive and sustainable growth, working across 3 main technical areas: urban infrastructure/services and city administration, infrastructure investment and PPP, green and climate resilient infrastructure. The Policy Officer also strengthened linkages between existing DFID infrastructure projects and FCO and DIT Prosperity Fund work on Smart Cities.

Ultimately the impact of this work was limited as the UK made the decision to pull out of all work with the Myanmar authorities on infrastructure and smart cities following the coup.

4). Raising climate and environment awareness in Myanmar (203601-123)
[£24,283, 11 March 2020 – 31 March 2021, Acclimatise/Willis Towers Watson]

This project was a low value contract with Acclimatise ahead of COP26 to support awareness raising around climate change and its implications in Myanmar. Acclimatise was acquired by Willis Towers Watson in November 2020. The contract novation was signed formally by contract amendment between the relevant three parties.

The Acclimatise team supported U Thant House and the DFID Myanmar team to raise their capacity and knowledge of climate change and its impacts and to increase the potential for U Thant House to effectively communicate with a wide range of audiences in Myanmar. Work on Climate Change and public discussion around COP26 started but were impacted by COVID – and the delay to COP26 – and then the coup.

The benefits of taking action on climate as a result of raised awareness of climate and environment risks could be huge - particularly considering the high losses currently incurred due to climate threats (~3% GDP annually). However, again the impact of this work has been limited because of the coup. Some of the work done by acclimatise was reflected in our approach to COP26, but the public communications environment has not been right for broader information sharing on climate change since the February 2021 coup.

Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme

Overall, this output scored a B. However, the overall assessment of value for money moderate. The larger two component of the output, the joint office in Nay Pyi Taw and the support to the CPG both had a positive impact to donor coordination, including with the authorities.

The majority of spend in this output was on the Liaison Office. The principal costs of the Joint DFID-Australian Aid Liaison Office were the office lease agreement and contract staff salaries. The Australian Embassy managed the administration of Joint Liaison Office in the capital, which benefited DFID Myanmar through reduced commitment of DFID staff time. Staff salaries were benchmarked to local rates and a new, lower cost 2-year lease was signed in June 2016 which delivered anticipated savings of approximately 20% over previous years. DFID de-linked with the DFAT in November 2017 to have an independent office resulting in more savings from the rental as well as the staff costs. The new liaison office in Nay Pyi Taw relocated in 2018 presented value for money which reduced the rental cost while obtaining a larger office space. Prior to the coup there was a plan to bring the office onto the formal HMG platform. This was put on hold as a result of the coup.

The policy on infrastructure and climate change project funded technical assistance to government departments at policy, institutional and operational level. Rapid closure due to the military coup reduced VfM and limited the benefits and sustainability of the results achieved - although the projects were closed in responsible manner.

Lessons learned through this output, and recommendations for future programming
Ensure that the learning and communications products generated through the raising climate and environmental awareness work are recycled through planned post coup engagement with civil society on climate change.

D: Risk

Overview of programme risk during the past year and over the life of the programme, drawing on FCDO’s Risk Management Policy and Risk Appetite Statement and wider risk guidance.

The ARF programme overall risk rating is moderate. ARF programme delivered within risk appetite over the life of the programme. The following ARF risk appetite is set up on the system which is in line with country office level risk appetite.

The overall main risks identified for the ARF programme are external context, operational and programme delivery. The ARF programme risks in FCDO seven risk categories are as follows.

1). Strategy and Context: Backsliding of reforms closed opportunities for progress in ARF focus areas. Formal and informal political economy analysis underpinned interventions. In some cases, government was unable to manage all the different initiatives from development partners which led to failure of some initiatives; although ARF work to improve coordination helped to mitigate this risk. Objectives of ARF programme could only be delivered in politically favourable environment to influence reforms in critical areas or where there was robust risk mitigation approach. Ultimately the February 2021 coup closed all policy reform windows and led to massive backsliding across almost all agendas. It will not be clear for some time to what extent the progress made by initiatives supported by the ARF (such as EITI) has been completely eroded.

2). Policy and Programme Delivery: The withdrawal of international staff of the projects due to Covid-19 and the Coup disrupted ARF projects and delayed delivery. Alternative delivery approaches were discussed with project partners to ensure ARF responded emergency needs during Covid’19. As most ARF projects related to reforms and high-level technical assistance, and the UK cancelled all policy work with the authorities after the coup, the ARF was closed without spending its full budget allocation.

3). Public Service Delivery and Operations: Programme Management team from Delivery Effectiveness Team (DEFT) facilitated key compliance of ARF programme and supported across the office, but individual work was undertaken by the team across the ARF portfolio. Insufficient programme management could lead to the increased risk of fraud and failure of objectives and compliance due to the limited human resources capacity. In line with business continuity plans against priorities, protect and pivot strategy in the crisis, each ARF project was reviewed with thematic leads, assessed the impacts, and made timely decisions to slow down, suspend or prioritise implementation.

4). People: With increasing conflict nationwide, risks and challenges for partner staff increased. Development staff and their facilities were targeted. Partners had some difficulties in attracting and retaining staff in their field offices and concerned to their staff mental health, welfare and staff duty of care.

5). Safeguarding: There was a risk that potential ARF funding partners had low capacity to address safeguarding risks, along with weak control systems and policies. Due Diligence assessed organisations’ systems and policies to ensure the partners had safeguarding policies in place. FCDO Myanmar partners meetings promoted zero tolerance policy of FCDO, and safeguarding awareness champion sessions provided in partners meetings. For example, in response to FCDO’s letter to partners on safeguarding, RGHR highlighted their Anti-Bullying and Anti-Harassment Policy and reaffirmed their commitment to ensuring that all those who are employed by RGHR or act as consultants for RGHR to deliver a safe and trustworthy environment in which all can work without fear of exploitation or abuse.

6). Finance and Fiduciary: There was a risk that funds provided to project partners with weak systems and policies could lead to fraud and corruption or aid diversion especially during Covid-19. Due Diligence was conducted before any grants were disbursed with improvement actions undertaken by the partners. Ensured partners had awareness of UK’s zero tolerance approach.

7). Reputational: Any miss management of some ARF sensitive works or documents which need to be protected or redacted could lead to reputational risk especially during political sensitive and security risk increased. It is to ensure all the required published documents, including this PCR report, have sensitivity review before publication on the system.

Update on Partnership Principles

During its lifetime the ARF operated within the framework set out by the partnership principles. The partnerships principles were reviewed regularly. Throughout the life of the ARF, DFID did not provide direct financial aid to government and implementation of small projects were based on stakeholder consultation and engagement as appropriate. In February 2021 in response to the coup, the UK carried out an Aid Review for the Foreign Secretary which essentially reset the partnership principles. The review concluded that the UK should stop all work on policy reforms with the authorities and should not provide assistance through state systems unless there was an exceptional humanitarian justification. The decision to wind down and then close the ARF, with its focus on supporting reform processes, followed from the conclusions of the Aid Review.

E: Programme Management: Commercial and Financial Performance, Monitoring and Evaluation
Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including VfM measures of economy and efficiency.

FCDO Programme Performance

The DFID Myanmar Accelerated Reform Facility (ARF) was set up to provide up to £5 million between September 2012 and April 2014 for DFID Myanmar to be able to respond quickly to opportunities to support interventions that catalyse, foster, and deepen reform in Myanmar. The ARF programme was extended many times.
1. The programme was extended on a no-cost basis to the end of 2015 by the Head of Office in early 2013 on the basis that opportunities to support reform were continuing to present themselves and because opportunities were taking longer to operationalize because of the difficult and changing operational environment in Burma.
2. In 2014, the Minister of State (MoS) approved (Vault no 4322226) a further £10m and extended the ARF until the end of the December 2016 based on the success of the initiatives funded under the ARF and the further opening of reform space, particularly in relation to the peace process.
3. In 2016, the DFID Myanmar Head of the Office approved an extension of the project on a no-cost basis to the end of 2020. In July 2016, the MoS approved the reallocation of £5m earmarked in the 2014 extension for supporting the peace process for use under any of the ARF’s focus areas (Vault no 5514046).
4. In 2020, the Development Director approved a no-cost time extension of the ARF until June 2022, based on earlier agreement of the Senior Management Team that ARF was supporting useful works across a range of policy areas including climate change, improvement of Yangon General Hospital, strengthening donor coordination, and exploring potential ways forward in service delivery in Rakhine state. The extension was particularly intended to allow time to complete some activities which had been slowed as a result of the Covid-19 pandemic.

It was agreed in July 2016 that Ministers would approve the use of ARF fund for the projects initially. In November 2017, the new approval processes for the ARF projects were agreed which provided delegated authority back to the Country Director as decisions on small, opportunistic spending were best made at the country level.

The ARF risk matrix on the system was reviewed and updated to reflect the new FCDO risk management framework. There were no major changes to the original theory of change and outcome indicators. However, a refinement to the theory of change and results framework were needed. The projects funded under the ARF programme adapted to the four shifts in the overall portfolio, seek opportunities to focus more on inclusion, conflict areas and focused engagement on policy reform. The programme strengthened engagement on aid effectiveness to maximise ARF project support to reform process.

Performance of partners

The projects under the ARF mostly delivered their objectives within agreed timeframes. However, some projects were extended to compensate for delays caused by Myanmar government focus on the 2015 and 2020 elections and following the transition to the new government in 2016; delivery of the remaining project portfolio largely ground to a halt or pivoted away from the military authorities following the Coup. ARF projects adapted swiftly during Covid crisis due to its ability to respond to context and opportunities. Project risks were reviewed regularly by the ARF project teams with partners and mitigation actions updated.

All completed projects were closed properly with partners in line with the agreement end date and the Prof rule. There were no outstanding payments with partners. For the projects which had DFID funded assets, it was disposed of in a way that represents best value for money with approval from HoD or delegate. All the required project reports were received as per agreements with partners. FCDO recognised that there had been long delays in the submission of RGHR project (203601-116) audit report. This was received in July 2022. All the required audited accounts and financial statements covered the full duration of ARF funded projects had been received. Any unspent funds were transferred as agreed with partners in line with the Prof rule.

Financial performance

There are 24 components created under the ARF programme on the system. The total spend at the end of the programme is £11,788,326 from 22 ARF funded components which is 78.59% of £15m approved programme value.

Component no	Component/Project name	Project spend (£)	Total (£)	Absorption rate
ARF programme value			15,000,000
203601-101	Good governance and public financial management	5,893		0.05%
203601-102	Promoting responsible investment and inclusive growth	93,223		0.79%
203601-103	Improving transparency and rule of law	26,080		0.22%
203601-104	Strengthening the work of parliament	5,692		0.05%
203601-105	Unallocated budget under ARF BC	0		0.00%
203601-106	Joint Liaison Office in Nay Pyi Taw	356,141		3.02%
203601-107	Myanmar Centre for Responsible Business	1,786,308		15.15%
203601-108	Support to strengthen Myanmar Parliament by providing an international expert in drafting laws for two months	53,424		0.45%
203601-109	Coordinating the Extractive Industries Transparency Initiative (EITI) process in Myanmar	274,281		2.33%
203601-110	Support the Extractive Industries Transparency Initiative (EITI) application of Myanmar	413,000		3.50%
203601-111	Support local civil society to promote improvement in the governance of the extractive industries, including through participation in and implementation of the Extractive Industries Transparency Initiative (EITI)	323,838		2.75%
203601-112	Local translator to support secondment of UK House of Commons research expert to the Myanmar Parliament	60		0.00%
203601-113	English for Education College Trainers	2,950,749		25.03%
203601-114	Technical Assistance to Myanmar for Public Private Partnership Framework Development - Implementing by Asian Development Bank	1,026,000		8.70%
203601.-115	Support to Electoral Process in Burma	0		0.00%
203601-116	Funding project management of restoration and reinvigoration of Yangon General Hospital and transforming medical education	2,745,434		23.29%
203601-117	Supporting a more inclusive political settlement: Knowledge for Nation Building	1,326,113		11.25%
203601-118	Additional Funding for the Cooperation Partners Group (CPG) Secretariat	149,486		1.27%
203601-119	Additional Funding for the Cooperation Partners Group (CPG) Secretariat	60,000		0.51%
203601-120	Policy on Infrastructure and Climate Change	20,954		0.18%
203601-121	Strengthening Inclusion in Myanmar	845		0.01%
203601-122	Strategic support for education reform coordination	13,498		0.11%
203601-123	Raising climate and environment awareness in Myanmar	24,283		0.21%
203601-124	Creation and Delivery of Plan for sustainable change in Rakhine State	133,024		1.13%
Total projects spend			(11,788,326)	78.59%
	Balance		3,211,674	21.41%

Commercial

The ARF programme used a mix and balance funding instrument of Contracts/AGs/MoUs to the type of organisation and how the funding was initiated to procure goods and services for the projects that provided value for money and the best comparative advantage. As mentioned above, some ARF projects used the local market to procure locally available goods and services. Used of local organisation and local procurement in the supply chain provided low cost and speedy implementation under the delegated procurement threshold.

Overall VfM measures of economy and efficiency

Difficulty of measuring ARF impact makes demonstrating value for money challenging. Interventions were sometimes ad-hoc piecemeal rather than fitting into a clear strategic framework. The ARF did not deliver stand-alone strategic results. On the other hand, the ARF did make several significant contributions to helping catalyse longer term processes (for example support to EITI) and supporting UK learning and understanding (e.g., through the work with Yangon General Hospital). So, in some cases the ARF’s responsive approach also helped to generate value. In addition to VfM measures of Effectiveness and Equity above, there are some VfM examples achieved as follows.

Economy: DFID’s Liaison Office at Nay Pyi Taw represented positive value for money. The office underwent significant analysis by both FCO and DFID over the years, to ensure that it represented the most beneficial model for the UK moving forwards. RGHR’s international experts provided their world-class skills at less than 50% of commercial value, delivering the impact of UK expertise at the lowest possible cost, and where possible costs were shared across multiple projects with partner charities to achieve savings of scale. In addition, senior RGHR staff and consultants delivered their time way in excess of contracted hours. RGHR maintained few office staff, always seek to minimise administrative costs. The Sittwe Strategic Fund projects were implemented at low cost, with high visibility community improvement initiative. This supported the development of local services/environment in Sittwe, and its immediate surroundings benefited the urban population. Utilising delegated procurement for education support in Rakhine concluded on time in a complex area.

Efficiency: A key element of the ARF’s delivery of value for money is the significant amount of staff time saved by being able to write concise project proposals for small but effective interventions rather than full Business Cases. This addressed DFID’s objective to be able to rapidly respond to the opportunities that arise unpredictably in Burma’s development process to influence in a timely manner. Project proposals sit under the delegated authority of the Head of Office from November 2017 to speed up the approval process with clear criteria.

Programme-level approach to monitoring and evaluation

Programme Management and project approval governance approach was robust. There are clear designation of SRO and PRO in place with distinct thematic leads of each project funded under ARF. However, programme management of the ARF over-burdened programme team capacity. Although programme management effort and burden shared across the thematic leads, programme team and advisors, too many small components and frequent changes in ARF programme oversight team led to insufficient oversight and impact to overall programme management such as updating the ARF overall log frame and programme theory of change as recommended in the ARF ARs.

The logframe was reviewed in April 2018 following the Rakhine Crisis in late 2017. The update was intended to ensure that the use of the fund against the key strategic pillars and main outputs was still relevant. However, the overall logframe still needed to be updated regularly over the course of programme period to capture new activity indicators in a timely manner that enabled accurate measurement of achievements against the output indicators.

The key learning from this programme is that the ARF programme needed to embed a more effective and strategic approach to capture evidence and performance. Significant results were achieved, but indicators needed refinement to generate real evidence of impact for all the projects across the strategic fund. The approval of each of the project under the programme needs to outline key results indicators which contributed to overall ARF logframe prior to approval from the Country Director and SRO. This system will ensure that ARF continues to deliver value for money.

Date of last narrative financial report	The last ARF funded projects / RGHR (203601-116) - 04 June 2021 / Acclimatise/Willis Towers Watson (203601-123) - 26 March 2020 / The Irrawaddy Policy Exchange (203601-124) - 02 February 2021	Date of last audited annual statement	The last ARF funded projects / RGHR (203601-116) - 04 July 2022 / Acclimatise/Willis Towers Watson (203601-123) – Not required / The Irrawaddy Policy Exchange (203601-124) - 27 April 2021

Annex 1: Achievements by Components (projects) under the ARF

Component	Component (T)	Achievements
203601-101	Good governance and public financial management	Short-term support to Public Expenditure and Financial Accountability Review for PFM Reform Strategy by the Ministry of Finance
203601-102	Promoting responsible investment and inclusive growth / (Price Waterhouse Coopers LLP)	Promoted inclusive business and created a standalone multi-year project operated in the garments and tourism sectors.
203601-103	Improving transparency and rule of law	Scoping and Potential Engagement in Myanmar
203601-104	Strengthening the work of parliament	Supported the Westminster visit of three MPs from the Myanmar Parliament’s Draft Bill Committee on education legislation and how the UK process functions; and the Myanmar Minister of Education visit to Education World Forum in UK in January 2013.
203601-106	Joint Liaison Office in Nay Pyi Taw / (DFID and DFAT)	Expended UK’s understanding and fostered closer engagement with the Myanmar government departments; works on disability with the Ministry of Social Welfare Relief and resettlement; and co-ordinated high-level UK representatives to the capital NPT, including a Ministerial visit to Myanmar
203601-108	Support to strengthen Myanmar Parliament by providing an international expert in drafting laws for two months	Conducted legislative drafting training for members of the Bills Committee, other Parliamentarians, and private lawyers; and a brief report on law drafting with recommendations and a Research Service Development Plan.
203601-109	Coordinating the Extractive Industries Transparency Initiative (EITI) process in Myanmar / (MDRI-CESD)	Submitted the application of Myanmar to the EITI Board on May 2014 and Myanmar was accepted as a candidate country in July 2014.
203601-110	Support the Extractive Industries Transparency Initiative (EITI) application of Myanmar / (The World Bank)	Delivered EITI scoping study and legal review, the Political Economy Studies of Extractive Sector with a variety of trainings and workshops.
203601-111	Support local civil society to promote improvement in the governance of the extractive industries, including through participation in and implementation of the Extractive Industries Transparency Initiative (EITI) / (RWI/NRGI)	Supported the historic event of Myanmar on the first national civil society conference on the EITI; assisted the organization of the civil society constituency, training for trainers to MATA members from 14 regions/states; trainings to 20 representatives from Government side on EITI; and a major achievement on the revenue sharing, revenue flows on extractive sectors, the role of State-Owned Enterprises (SOEs) and ‘decision to extract’/licensing at the subnational level.
203601-112	Local translator to support secondment of UK House of Commons research expert to the Burmese Parliament	Provided the translation and interpretation services for the House of Commons seconded a Senior Library Clerk (a specialist in parliamentary research) to the Myanmar Parliament to establish an impartial parliamentary research service.
203601-113	English for Education College Trainers / (British Council)	1,977 Teacher education Colleges undertook a year of English Language teaching and methodology and 313 in Universities of Education; 50 EfECT trainers active in all 24 education colleges across Myanmar; and key performance indicators (KPIs) six points were met out of ten.
203601-114	Technical Assistance to Myanmar for Public Private Partnership Framework Development / (Asian Development Bank)	Yangon 300 MW rental power plant evaluation; training and Power Purchase Agreements (PPA) management of the Electric Power Generating Enterprise; a study on public infrastructure for private business; analyse a transmission line for fiber optic cable for telecom business; and final corporatisation roadmap submission to the Ministry of Electricity and Energy in December 2017.
203601-116	Funding project management of restoration and reinvigoration of Yangon General Hospital and transforming medical education / (RGHR)	Yangon General Hospital’s masterplan development and implementation; comprehensive renewal of the medical curriculum and associated learning infrastructure; and Quality improvement initiatives for General Practitioners (GP) through British expertise and professionals to deliver substantive and lasting change as a part of the wider health system reform.
203601-117	Supporting a more inclusive political settlement: Knowledge for Nation Building / (Proximity Designs)	Equipped the critical knowledge building and constituencies to senior leaders from Government, Military, Ethnic Group; research and analysis for dissemination at the ‘Reorienting Burma Convening’ with Harvard academics and major stakeholders; eight research papers, six essays/memos and three case studies; and organised a visit to Indonesia by senior Myanmar military generals, three study visits and a group of 21 Myanmar leaders visit to Indonesia to learn its democratic transition.
203601-118	Establishment of a small fund for low-cost high visibility Projects in Sittwe / (DFID)	Strengthened engagement with the ethnic Rakhine population; proactively engaged with a number of local political stakeholders to discuss mutual beneficial projects that demonstrably show the international community’s endeavours to provide assistance to all communities across Rakhine.
203601-119	Additional Funding for the Cooperation Partners Group (CPG) Secretariat / (UNDP)	Facilitated bimonthly meetings with the CPG Facilitators and Government entities; collated and shared aid and development cooperation information for the benefit of the CPG in collaboration with MIMU; strategic overview to CPG Work Streams; and set up donor co-ordination mechanisms.
203601-120	Policy on Infrastructure and Climate Change	Analysis on coal and energy sector gaps analysis in Myanmar which shape Hlan Chi programme energy pillar; and funded to B1 Policy Officer of DFID to support the Cities and Infrastructure for Growth Technical Assistance Programme.
203601-121	Strengthening Inclusion in Myanmar	Specialist technical support to strengthen the coherence and effectiveness of DFID Myanmar’s portfolio on inclusion.
203601-122	Strategic support for education reform coordination	Funded to DFID Education Adviser surge post
203601-123	Raising climate and environment awareness in Myanmar / (Acclimatise/Willis Towers Watson)	Review of Myanmar C&E evidence and developed a high-quality draft product; and capacity building activities to boost local capacity on C&E.
203601-124	Creation and Delivery of Plan for sustainable change in Rakhine State / (The Irrawaddy Policy Exchange)	Facilitated initial thinking on a comprehensive education plan for Rakhine; completed a Comprehensive Education Plan for Rakhine; established protocols and principles for safe study during lockdown; inclusive education in and beyond Rakhine State; and durable solutions for communities living in IDP camps and improve access to services for displaced people.