Programme Completion Review

Title: International support to encourage the implementation of SDG16 (previously Supporting SDG16 through advocacy, data management and country support)
Final Programme Spend £ (full life): £1,849,132	Review Date:	June 2024
Programme Code: 300377	Start Date: March 2019	End Date: / AMP closure March 2024

Summary of Programme Performance

Year	2020/21	2021/22	2022/23	2023/24
Programme Score	A	A	A	A
Residual Risk Exposure Rating	Minor	Minor	Minor	Minor

DevTracker Link to Business Case (and any addendum):	Business Case - https://iati.fcdo.gov.uk/iati_documents/46225357.odt / Business Case Addendum - https://iati.fcdo.gov.uk/iati_documents/54081858.odt
DevTracker Link to log frame:	https://iati.fcdo.gov.uk/iati_documents/60978944.xlsx

A. Summary and Overview

The ‘International support to encourage the implementation of SDG16’ programme began with support to UNDP which aimed to strengthen the global architecture for Sustainable Development Goal 16 (peace, justice, and inclusion) and to support the contribution that FCDO and HMG programmes make towards the achievement of SDG16.

It was piloted as the ‘Supporting SDG16 thorough advocacy, data management and country support’ programme which led to the follow-on SDG16 programme through a costed extension formalised in an Addendum in February 2020. Due to changes to ODA allocations in 2021 and 2022 during the Covid-19 pandemic, both the funding and the timelines for programme components altered significantly from those approved in the Addendum.

Under the SDG16 programme, three partners delivered components of varying size: UNDP for the Measurement and Monitoring of Governance workstream; the University of Birmingham for Thinking and Working Politically Community of Practice Secretariat (TWP CoP); and the Office of National Statistics Governance Results and Evidence (REX).

UNDP (final spend £1,461,678) was the original and principal partner. This component dwarfed the others. Its aim was to build the capacity of UNDP to deliver advocacy, data management and country support for the delivery of SDG16 in partnership with others. Funding stopped early (due to Covid-19 related constraints on ODA) with FCDO providing a final allocation to close the project responsibly in 2021/22.

University of Birmingham (final spend £342,454). After delay and reduced funding, this component started in late 2021/22 to provide funding for a Secretariat for the TWP CoP hosted at the University. Its aim was to expand and deepen knowledge of TWP practices to empower practitioners to use politically informed approaches in SDG16 workstreams and all other development sectors. A TWP lens helps maximise returns on UK investments in programmes as well as on diplomatic and advocacy efforts.

REX (final spend £45,000) was an early and small component. The SDG16 programme provided a one-off contribution and Research and Evidence Department (RED) designed and managed REX. Its aim was to set up a new governance results reporting system for HMG.

RED evaluated REX at its programme completion. Therefore, this final report covers primarily UNDP and TWP. As the UNDP component finished early, FCDO provided comprehensive reporting in the Annual Review following its closure. This report draws upon these findings to present an overview. It also gives a short update on REX and presents the lifecycle and final reporting in full for TWP.

Major lessons learned, evidence generated and recommendations

UNDP. FCDO support to UNDP to strengthen monitoring and reporting on SDG 16 was critical to enable work with different SDG16 stakeholders and to advocate for better target monitoring and implementation. It was important to begin to address the significant data gap many countries have in reporting progress on SDG16. However, the ambition and results of the programme were constrained by its premature end.

The absence of other funders meant UNDP was reliant on the UK: when funding ended, the programme itself was deprioritised which resulted in minimal staff time allocated to continue to support it. More efforts could have been made to secure other sources of finance for the work to continue (although all donors were facing the Covid-19 pandemic and funds were very limited everywhere.)

Similarly, with less staff time and a more hands-off approach, FCDO did not capitalise on the relationships and goodwill that the programme could have provided. The UK did not actively participate in the events and was not a visible leader or partner on SDG 16 despite being the main funder. Our technical input and participation could have improved the quality of the work and helped better shape how UNDP approached certain issues. This in turn could have been used for lesson learning within HMG.

SDG16 remains one of the most off-track SDGs, requiring vocal advocates to build partnerships with governments and beyond to protect and champion its importance. It also faces an extremely challenging international financing gap. The November 2023 White Paper re-centred the SDGs at the apex of the UK’s development efforts. Two years since this component closed and in the aftermath of Covid, there can be renewed ambition.

The UK’s future advocacy, support, and leadership for SDG16 and the principles of open societies, rule of law and good governance that underpin it, will continue to be important for delivery of the Integrated Review and the International Development Strategy and the White Paper.

REX. Since the SDG16 programme initially contributed to RED to help finance REX, its development continues as it aims to be the principal online platform FCDO uses for recording results data. REX enables data to be stored and shared, using a common framework which brings together information from across FCDO, other government departments and delivery partners into a single repository.

This helps the FCDO improve the efficiency of its reporting and better address questions around the impacts of programmes.  Technical development remains ongoing and delivered in partnership with the International and Digital Directorate who sponsor continued REX development as part of the Delivery Platform Business Case (2022-2025).  The service has been operationalised in smaller user communities, most notably in 2023 with the International Climate Fund which commissioned all its results using REX. It is yet to be more formally rolled out through the wider FCDO estate.

TWP. The CoP formed in 2013 as a loose global network bringing together individual experts and practitioners from donor organisations, development organisations, civil society, and the development research community. Its purpose remains to promote awareness of TWP approaches, encourage their adaptation, translate the insights of political-economy thinking into operationally relevant guidance, and provide evidence-based insights to stimulate innovation.

FCDO funding proved transformational albeit against a challenging background. The CoP grew considerably and became increasingly influential and diverse. UK funding made it possible for the CoP to have a more formal structure (through the Secretariat), and to be more proactive and propositional in engaging in debates about how international efforts to promote more peaceful, open, inclusive, and resilient states and societies (SDG16) can be more effective.

The CoP has evolved into more than simply a loose community to discuss new ideas around the theory of TWP. Practitioners share experiences regarding how ‘TWP’ or ‘adaptive management’ is applied in practice. It is a safe, open space to share evidence about what works as well as what does not, how, and why, and to discuss and debate the challenges faced by innovative approaches that are only just beginning to be tested in practice.

As a TWP lens becomes more thoroughly socialised among individuals and organisations (such as the FCDO) it helps to inform ways of planning and delivering. A strengthened TWP lens can “skill-up” organisations and harmonise a common approach. Ultimately, this can help practitioners support democratic governance and other programming in politically aware (and thus more effective) ways.

Predictable and stable funding is paramount with smaller partners with few staff. An environment where funding remains uncertain, and budgets cannot be determined in a timely manner, is extremely challenging and can profoundly undermine institutional capacity. This is even more the case if there are limited donors available and uncertainty continues for long. In addition to the inability to start planned programme activity, these challenges can lead to staff turnover and organisational memory loss.

The small and successful TWP CoP Secretariat programme currently continues with support in a subsequent grant (to the SDG16 programme) under one of the Development and Open Societies Department’s flagship programmes, the Democratic Resilience Platform, with funding until March 2025.

Programme Leadership and Management. The SDG16 programme began in the Global Strategy and Partnership team in the ex-DFID department Governance, Open Societies and Anti-Corruption (GOSAC). Post-merger, the programme moved to the newly created FCDO department Democratic Governance and Media Freedom (DGMF). After the UNDP element closed, the programme team had little choice but to continue the programme to support TWP, which had only recently started (after setbacks from budget uncertainty). This considerably lengthened the time lag from UNDP closure to formal programme end. Although a relatively quick way to mobilise funding for smaller projects, FCDO should exercise caution in incorporating small new projects inside older and larger programmes, particularly if the timing of projects does not match.

As a result of these issues, there were multiple generations of technical leads and programme staff throughout the course of the programme. Institutional knowledge was lost, frequent staff turnover hampered programme and financial management processes, and it inhibited a holistic understanding of the programme through its lifecycle. FCDO should be more mindful of staff capacity and change “moments” in programmes to ensure outgoing staff leave the programme in compliance with PrOF and incoming staff get full handovers and continued support on historical knowledge.

How this report was conducted
The DGMF final PRO for the programme prepared this report with input and evidence from the former PRO, the last UNDP relationship manager for the programme, the former DGMF Results Adviser who led technical input on REX, the first technical lead for the programme, and the current Director for the University of Birmingham. The report drew on significant volumes of written and saved records and all previous programme documentations (Business Case, Addendum, Annual Reviews, results information, workplans).

## B: Theory of Change and Outcome Assessment

	Starting point	Final Result
Budget	£0.8m (BC for one inception year)	The Addendum increased total budget to £5m. However, ODA reprioritisation during Covid-19 closed the UNDP programme early and reduced funds for TWP. / Final spend was £1.85m made up from: / UNDP = £1.46m (80% of total spent budget) / TWP = £0.34m (18%) / REX = £0.05m (2%)
Timeframe	January 2019 to February 2020	The Addendum extended four years to March 2024
Outcome	SDG 16 progress monitoring and reporting enhanced through capacity development, multi-stakeholder involvement, peer-learning and knowledge management, and advocacy.	Outcome level indicators were created in 2020 after the extension. The inception year did not have a full results framework with an outcome level. / Two indicators were created to measure the outcome. (Unforeseen and early closure meant neither final methodology nor targets were agreed.) / Number of countries where national capacities are strengthened to inclusively and systematically monitor and report on SDG 16 implementation. / Quality, comparable, and regular governance statistics and data are available to address national data gaps, establish baselines, and meet policy and reporting commitments under SDG 16.

Overall assessment of programme outcomes, sustainability and VfM

The problems affecting the UNDP workstream are comprehensively explained in the 2022 Annual Review which covers the year the component ended, providing reporting at closure. A proportionate overview is provided below.

Due to reprioritisation of the ODA budget, the programme’s UNDP results and vfm were reduced compared to earlier ambition and the original VfM proposition in the Business Case. The ability of UNDP to secure additional funding from other sources was severely limited as other donors faced the same challenges at the same time. Therefore, considerable parts of the future workstreams were unable to continue, which undermined the outcome and future impact of the deliverables.

Nonetheless, UNDP responded swiftly and adeptly and was able to continue delivery of some significant results despite the challenges of the pandemic, reduced timelines, and reduced funding.

UNDP’s expertise on SDG16 data through their Oslo Governance Centre meant they required minimal technical support and were able to deliver against agreed outputs independently.

UNDP continued delivering through online resources and events. Workshops took place virtually and written material was made available online that helped countries report on SDG16 in their Voluntary National Reviews.

Some products, like the Praia Handbook on SDG16 Statistics (Handbook on Governance Statistics), were finalised and are now supporting countries with SDG16 reporting.

The SDG16 Survey Initiative was promoted as part of UNDP, UNODC, OHCHR Regional Training on Measuring SDG16. For example, the Latin America and Caribbean training covered 44 countries (including countries outside the region). The Asia training had registered participants from over 80 countries.

The programme helped link up member states, international organisations, and civil society through the SDG 16 + Coalition. Although lack of funding limited future activity, the established relationships and community allowed the work on SDG16 evidence and monitoring to continue. This will prove important as we get closer to the end of the SDG period in 2030.

The SFG16 programme’s theory of change and results framework

Theory of Change. The strong focus on data and evidence and strengthening accountability for SDG16 delivery helps to position SDG16 as a catalyst among other SDGs in which governance is a central part of approaches to development. This is more likely to happen if:

an inclusive and well-coordinated policy environment is in place to ensure the effective implementation, monitoring and reporting on SDG16;

quality, inclusive, comparable, regular, and accessible governance statistics are available to address national data gaps and meet policy and reporting commitments under SDG 16 (and other governance related commitments and national priorities); and if,

all stakeholders including civil society are engaged in reporting and monitoring processes to promote accountability; then,

monitoring and reporting can contribute to evidence-based and responsive national policymaking and accountability for delivering better and more inclusive governance in society because;

awareness about progress in delivering on SDG16 will become widespread exerting pressure on member states to deliver; the conditions can be met for a participatory and rigorous assessment of the status of SDG16; and the steps that need to be taken to address existing gaps can be conducted, debated, and agreed amongst societal stakeholders.

The programme’s theory of change was updated in 2020/21 at the time the outcome and outcome indicators were developed. It did not change again.

Results Framework. After the 2020 extension, the programme team developed a log frame with three outputs covering UNDP. Later, they developed a fourth output to cover the contribution of the new TWP component. However, when TWP was added to the log frame it did not tie in at Outcome level and no Outcome level result (nor Outcome indicators) were subscribed to it. Therefore, this section does not discuss TWP’s contribution to overall outcome in detail although more embedded TWP analysis in an organisation can bolster the effectiveness of its SDG16 (and other) programming.

Assessment. The withdrawal of UK funding for UNDP’s work inhibited the full delivery of all outputs and undermined UK leadership on the SDG 16 agenda at the time. Therefore, the overall achievement of the programme to its outcome was significantly constrained. Some achievements had already been captured and some of the global advocacy activities were able to continue through the SDG 16+ Coalition beyond the end of UK funding. UNDP continued as custodian on many SDG 16 indicators, but the capacity to meet the demand on implementation of the SDG 16 Survey instruments or piloting of the Praia Group tools was left limited at closure (2021/22), with additional resource required to ensure that the benefits of several years of political, financial, and technical investment by the UK on governance measurement would not be lost.

Scoring.
[note] To recap on past performance, the UNDP outputs (weighted at 60%) all scored an “A” at first review. In the second (and final year), they scored an “A” and two “Bs”. The TWP output (weighted at 40%) scored an “A+” throughout previous reviews.
The programme team is satisfied with the final score of an “A” (the programme met expectations). This is not an assessment against the original expectations but rather it pragmatically reflects:
(1) the reduced time the UNDP programme had to deliver planned results;
(2) the progress and achievements that had been possible until closure;
(3) factors beyond UNDP’s control, which affected results and impact; and,
(4) the solid performance of the TWP CoP component.
The ambition and the expectations of the overall programme were significantly reduced by the early end of funding to the main partner, UNDP, and to a lesser effect by reduced funds to the CoP. Nonetheless, both partners were agile and swiftly adapted to these unforeseen circumstances. UNDP was able to deliver considerable elements of the programme such as the Praia Handbook, utilising the statistical survey, peer-to-peer exchange, as well as the creation of the SDG16+ Coalition out of what was the Alliance. And as detailed in Section A, TWP has been a solid success.

## C: Detailed Output Assessment

Output 1 (UNDP) – Strengthened multi-stakeholder and systemic approach to reporting and monitoring on SDG 16+. (Concluded in 2021/22.)

UK funding to UNDP facilitated the creation of the Global Alliance for Reporting Progress on Peaceful, Just and Inclusive Societies (SDG16 Global Alliance). It was a coordinating platform for Member States, private sector, civil society, and UN Agencies to promote and strengthen evidence-based reporting, monitoring, and measurement of SDG16.

Despite the early end to UK funding, the Global Alliance continued delivery through 2021 and in to early 2022. However, ambitions for its future work were curtailed. However, at that time, UNDP members set up and began actively engaging in the SDG 16+ Coalition, and some of its global advocacy activities continued past the end of UK funding although capacity was limited.

The programme team reported on Output 1 for activity in 2020/21 and in our final year of funding 2021/22 scoring an “A” and a “B” respectively.

Output 2 (UNDP) – Peer-exchange on experience and good practices on SDG 16+ reporting and implementation strengthened within countries from national to sub-national level, across countries, and regionally. (Concluded in 2021/22.)

UK funds helped connect partners and share knowledge and resources with an ever-increasing community of SDG16 practitioners. The Global Alliance delivered workshops and webinars to inform and share experiences on SDG16 monitoring and reporting with governments, civil society, and the UN, among others. One notable initiative was the SDG16 Hub. This online one–stop platform for knowledge, resources, and interaction on SDG16 became and remains a vibrant online community of practice. The Hub, hosted by the UNDP Oslo Governance Centre, increased in registered membership from 700 users in early 2021 to 3,196 users when UK funding stopped. It also provided a platform to showcase core learning resources and toolkits which it continues to host.

The programme team reported on Output 1 for activity in 2020/21 and in our final year of funding 2021/22. The scores were an “A” and a “A” respectively.

Output 3 (UNDP) – Data availability gaps addressed through implementation of SDG 16 survey; standards development addressing cross cutting priority areas highlighted in the Handbook advanced by the Praia City Group. (Concluded in 2021/22).

The “Praia” initiative aimed to develop a survey instrument that countries may use to measure progress on multiple SDG 16 survey-based indicators. The survey covers the thematic issues of governance, access to justice, corruption, violence, discrimination, and trafficking in persons. The Praia Group designed it specifically for national statistics offices (NSOs) to use, and it aims not only to further data collection on the SDG 16 indicators but also to contribute to strengthening national statistical capacities and ownership.

Headline result - the Praia Group in launching its seminal Handbook on Governance Statistics at the 51st UN Statistical Commission, which was the culmination of several years of collaboration between NSOs, international organizations, and civil society organizations. This Handbook takes stock of existing practices in governance data collection and proposes a way forward to implement international statistical standards for eight dimensions of governance.

The programme team reported on Output 1 for activity in 2020/21 and in our final year of funding 2021/22 scoring an “A” and a “B” respectively.

Overview of reporting on Outputs 1 – 3

Outputs 1-3 were introduced following programme extension in 2020. They were all weighted at one-third each. The inception year did not have a formal results framework, but rather, a set of early outputs. The 2022 Annual Review introduced Output 4 (TWP) at 40% and reweighted Outputs 1-3 to 20% each.

The 2021 Annual Review provides full reporting for Outputs 1-3 in 2020/21. The subsequent 2022 Annual Review reports on final year of UK funding 2021/22 and provides analysis of achievements at closure. It contains granular detail on what UNDP workstreams were and were not able to continue.
The programme team has used a pragmatic approach to scoring outputs for the PCR that considers scores across years of activity for UNDP, retains the weighting from the last review, (and considers TWP based on overall performance into 2023/24).

Output 4 (University of Birmingham) – Thinking and Working Political Community of Practice Secretariat (TWP CoP)

Uncertainty over ODA funding delayed the grant until late 2020/21. The programme team created and first reported on Output 4 in the Annual Review covering 2021/22 when it scored an A+. Given that it was by then the only remaining live Output, the team weighted it at 40% although in terms of funding it was small compared to UNDP. Reporting below covers the whole grant period.

Output Number and Title		4: Support and strengthen the use of Thinking and Working Politically practices
Output Score		A+
Impact weighting (%)		40	Impact weighting revised since last AR?	No

Output Indicator	Starting Target		Final Log frame Target	Final Result Achieved
(4) Knowledge of Thinking and Working Politically practices deepened and widened.	(4.1) Number of newsletter subscribers. (Baseline: 370 subscribers in March 2020). Target for was 600 subscribers. / (4.2) Click opening rate for newsletter (Baseline: unknown as data not captured before grant. Starting target was 25%). / (4.3) Number of events or webinars led by the TWP CoP Secretariat / (Baseline: zero and starting target was six events/webinars cumulative by grant end.		900 / 40% / 6	708 subscribers in March 2022 / 1,050 subscribers in March 2023 / (1258 subscribers in March 2024) / 38% click rate in March 2022 / 40% click rate in March 2023 / (48% in February 2024) / The TWP CoP launched its Global Webinar series organising seven webinars in collaboration with partners.
Notably outputs not captured in the results framework / Direct strategic support to FCDO. The grant funded six separate workstreams of direct support to teams in the FCDO. These were: / New FCDO guidance on political economy analysis and TWP / Seminar organised in conjunction with the Governance Head of Profession on what FCDO’s work on supporting “open societies” should prioritise and why (2021) / Ongoing work to support the development of an FCDO strategy on “open societies”/democracy support” (2021-2023) / Support to work on the political economy of illicit financial flows in Small Island Developing States / Provide strategic support on energy transition in the Pacific / Provided strategic advice to the FCDO Eastern Neighbourhood office on political settlements / Publications. From a baseline of zero, the grant supported nine publications (either published or co-published). Six were published online (often in collaboration with partner organisations including e.g. FCDO, ECDPM, The Policy Practice, etc). One publication was produced for an internal FCDO meeting on SIDS. There was also a research paper on governance and natural resource management and a blog published on ‘From Poverty to Power on TWP and localisation’. / Further events and seminars. In addition to the public webinars, the TWP CoP Secretariat: / Convened a follow up meeting with a sub-set of attendees on the challenges of democratic backsliding and how to work on supporting democracy more effectively through TWP (July 2022). / Co-led two hybrid events with FCDO staff to share and socialise the new FCDO-TWP guidance on political economy analysis (February 2023). / Joined a hybrid event with FCDO staff and selected external participants on the political economy of illicit financial flows in SIDS (March 2023) / Organised several seminars to discuss work from different actors involved in the TWP space (e.g. USAID-Chemonics paper by Jonathan Rose and others). / Hosted six informal “what’s up?” sessions to enable TWP CoP members to come together and discuss issues that they have been grappling with (October 2022-March 2023)
[note] On average, more than 120 people from across countries and regions signed up to each of the webinars, and attendance and participation from the audience was high quality.

FCDO funding enabled the establishment of a fully staffed Secretariat at the University of Birmingham to support the TWP CoP. The Secretariat launched a bi-monthly newsletter; redeveloped the website to include videos and publications and made it easier to navigate attracting increased usage; launched a global webinar series; organised further events; and published research and evidence papers. In direct support of FCDO, the CoP provided advice and analysis to FCDO teams on TWP approaches and worked with FCDO in updating PEA/TWP internal guidance.

The University of Birmingham has performed well over the course of the grant and activity in the final year exceeded log frame targets. Performance is therefore assessed at completion as A+ where “Outputs moderately exceeded expectation.” In particular, the number of subscribers to the newsletters increased significantly, the CoP was adept at directly supporting FCDO priorities with a TWP lens, and the CoP’s ability to generate thought, discussion and discourse exceeded expectations.

Lessons learned and recommendations

A key lesson that emerged from the work undertaken by the CoP is that there is a real hunger to engage with and learn from different actors on understanding how change happens and what that implies for how international actors can support such efforts more effectively. The CoP should continue to enhance its outreach and work with a broad spectrum of individual and organisations in the development space embedding a TWP lens, making linkages and increasing the effectiveness of results and impact.
The CoP has been widely valued for providing an essential public good anchored in synthesising and sharing evidence and lessons on TWP and providing an essential platform for engagement, discussion, debate, and learning. CoP members have consistently found the group deeply valuable and useful for reflecting on developmental challenges and pushing back on more traditional ways of working, and socialising and embedding TWP within their own organisations.

D: Value for Money

Due to reprioritisation of the ODA budget during the Covid pandemic, the programme’s vfm pertaining to delivering results and the longevity and impact of results was hampered (effectiveness). Section B assesses this top level VfM. This section focuses, instead, on internal vfm at programme level (economy, efficiency, equity, and cost-effectiveness).

Travel restrictions reduced the international community’s ability to attend conferences in support of SDG16, which may have reduced the efficacy and momentum of UNDP’s agenda and hampered efforts to deepened TWP reach. However, paradoxically, both partners made VFM saving with the move to online working and severely reduced travel (cost-effectiveness and efficiency).

The University of Birmingham worked closely with FCDO throughout the pandemic to try to manage funding uncertainty and to adjust workplans to fit the reduced support. University of Birmingham adapted quickly to the reduced budget to maintain VFM. The savings from online working/reduced travel meant for this small partner meant that the impact of the budget reduction was not as severe as first anticipated. The adaptive delivery, improved engagement in the CoP, and the TWP offer to wider FCDO all suggest the funding for this output delivered VfM.

UNDP’s key costs drivers were staff and the expert consultants. UNDP has a commitment to keeping bureaucratic overheads to a minimum (efficiency) and they ensured swift decision-making processes to adapt to changing circumstances and proved to be highly mobile and flexible. Technical and project leads from within UNDP, seconded staff and technical staff hired on consultancy contracts implemented the programme without the hiring of additional management roles making vfm savings (efficiency). Internal checks and balances ensured high quality standards and compliance with UNDP’s operating policies, and procurement processes followed UNDP’s guidelines with tenders held for all contracts to ensure best value for the lowest price (economy). Financial guidelines for all project beneficiaries followed UNDP’s rules for travel (economy class) as well as the per diem rates. UNDP has an efficient, well-tested financial system.

Similarly, the main cost drivers for the CoP are staff costs and expert costs. There are also costs associated with maintaining the website, publication of papers, and newsletters. Work was nearly always completed remotely, and seminars were virtual. TWP follow the University of Birmingham VFM rules on procurement, staff salaries and expenses which were vetted and considered up to standard in the due diligence exercise that preceded the grant (economy and efficiency).

The CoP Secretariat is committed to diversity and inclusion in all the work that it supports (equity). It ensures that women are actively integrated and lead/participate in all our activities and areas and engagement. The community also actively seek to capture and feature the voices of younger audiences.

E: Risk

The SDG16 programme risk level at approval was “minor” and fitted easily within ex-DFID’s risk appetite. A year later following good results with UNDP, the programme had a £4.2 million increase and an additional four years. The number of partners and workstreams also increased at extension. These changes happened in February 2020 one month before the first UK nationwide lockdown for Covid-19.

The risk rating remained “minor” and did not change at extension because UNDP was a trusted partner and its approach to fiduciary and safeguarding risks was well-established. Ex-DFID’s successive multilateral aid reviews confirmed this, although some of the initiatives in individual workstreams such as the work with the Praia Group to delivery regular monitoring of progress had “moderate” risk. The programme team judged that UNDP’s ability to mobilise stakeholders would mitigate these risks.

The identified risk with the highest residual impact after mitigation (“moderate”) was that stakeholders, including UN Member States, become less committed to SDG16. Other risks related to the level of support provided to UNDP being insufficient, and the complex nature of delivery across a wide range of stakeholders.

Covid-19 pandemic was an unforeseen risk. Its effect on the UK (and on potential donors and member states) was huge, in that it took resources away both in terms of actual funding and in terms of capacity as countries prioritised fighting the pandemic. FCDO had, at the time, limited capacity for engagement due to uncertainty around the ODA budget (and its ongoing transformation through the merger). Unfortunately, Covid precipitated what was already a risk of insufficient funds and had a severe impact on focus and capacity if not commitment.

Structural reorganisation of FCDO during the merger years also provided a direct risk to the programme management and its technical oversight. As discussed in Section A, this programme moved departments entirely in the new FCDO setup with a complete turnover of FCDO staffing and resources within the team resulting in a lack of consistency and loss of institutional memory of programme actions.

F: Programme Management: Commercial and Financial Performance, Monitoring and Evaluation

Under challenges circumstances from 2020 to 2022, partners had to navigate uncertainty. Underpinning this was a solid basis of programme management and partnership between teams. For FCDO, with limited staff capacity allocated to the UNDP programme and the recent move of the programme to a new department, this was challenging. However, the programme records show that invoices were received and paid on time as well as performance reports and financial statements. UNDP also had an efficient, well-tested financial system which minimised delays with funds transfers for third-party services.

For TWP, regular catch up and performance meetings were held and the FCDO continued to receive regular quarterly narrative and financial reporting. Invoices were received quarterly and paid in arrears. The University of Birmingham moved onto a new financial reporting system in 2023. This did delay invoicing for some time, but once the new system embedded that was rectified.

UNDP and TWP both ensured high compliance with their internal checks and balances and there were no significant programme or financial lags or issues. At all times, FCDO programme staff remained confident in the ability of partners to deliver results and manage FCDO funding. Although systems kept working, a holistic management and monitoring approach was hampered by frequent staff turnover. Previous sections have discussed these challenges as well as one of diminished staff capacity on programmes. Other sections of the report discuss both UNDP and TWP procurement policies, vfm and the issues of delayed financial uncertainty and staff turnover.

Monitoring and evaluation
At approval, support to the UNDP was limited to a year to allow reflection before extension. As such, the Business Case contained no evaluation plans. With promising first year results, the programme continued although the Addendum did not mention evaluation. Consequently, with UNDP funding finishing early and little overlap with TWP, a programme-level evaluation did not make sense.

With UoB the only remaining partner delivering a small magnitude (less than £350k from 2021/22 to 2023/24) project, an independent evaluation at that stage would have been disproportionate.

Date of last narrative financial report	UNDP – June 2022 / TWP – December 2023	Date of last audited annual statement	UNDP – January 2022 / TWP – December 2023