Project Completion Review - Top Sheet

This Top Sheet captures the headlines on the programmes performance over the course of its lifetime. Teams should attach summary sheets from each annual review over the life of the programme.

Review Date:	May 2017

Title: Monitoring and Evaluation of the UK’s Framework for Results for Malaria (“Breaking the Cycle: Saving lives and protecting the future”) and RMNH (“Choices for Women: Planned pregnancies, safe births and healthy newborns”)
Programme Code: 203368	Start Date: April 2012	End Date: July 2017
If programme was closed >1 month early please describe in a few words why.	N/A

Summary of Programme Performance

Year	Annual Review / Jan 2014	Annual Review / Jan 2015	Annual Review / Jan 2016	Project Completion Review / June 2017
Programme Score	B	A	B	B
Risk Rating	Medium	Medium	Major	Major

Financial Position

Original Programme Value	£4.5m
Extensions/ amendments
Log-frame revisions (with dates)	January 2013 - The logframe indicators were amended to improve their relevance and measurability. / January 2015 - The logframe was revised to reflect changes in approach since the programme was approved / December 2016 – Some milestones were updated.
Total programme spend	£713,133.

Follow up actions required following closure

Continued communication across DFID of key lessons arising from the lesson learning products, to ensure they are fed into future programming decisions: Action in hand by Head of Profession for Health and Human Development Department teams.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/3744994.odt
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/5289245.odt

Outline of programme and what it has achieved

This programme was set up to evaluate the implementation and outcome of strategy documents on malaria and women and children’s health, which were published by DFID in December 2010. These were known as Framworks for Results, fully titled:

- Breaking the cycle: Saving lives and protecting the future. The UK’s Framework for Results for malaria in the developing world
- Choices for women: Planned pregnancies, safe births and healthy newborns. The UK’s Framework for Results for improving reproductive, maternal and newborn health in the developing world.

Together the Frameworks for Results set out how the UK Government would deliver its commitments on malaria and reproductive, maternal and child health (RMNH) to:

   •	help halve deaths from malaria in at least ten high burden countries by 2015;
   •	provide access to modern methods of family planning for 10m additional women, including 1m young women aged 15 – 19 by 2015;
   •	prevent more than 5m unintended pregnancies by 2015;
   •	ensure at least 2m safe deliveries, particularly for the poorest 40% by 2015; and
   •	save the lives of at least 50,000 women during pregnancy and childbirth and 250,000 newborn lives.
The Mid Term Review and evaluation were planned to learn lessons from the Frameworks for Results to inform future programming and approaches. The Mid Term Review was a commitment under DFID’s Structural Reform Plan.

The ambition for the programme has been much reduced from the original intention and as a consequence, expenditure was much reduced. This followed external expert advice that an evaluation of the Frameworks for Results, while feasible, would not provide good value for money and that the learning could be generated at much lower cost and reduced risk through synthesising evidence and lessons learned across the RMNH and malaria themes. As a result the programme was scaled down. It was not closed because it was a valuable vehicle for carrying out lesson learning activities that were useful for Human Development Department policy teams.

Under the programme:
- An inception report (or evaluability assessment) covering both the MTR and evaluation of the Frameworks for Results was produced.
- A mid term review (MTR) of the Frameworks for Results was completed and published in 2013.
- A review of the progress DFID has made towards the commitments laid out in the 2011 HIV position paper Towards Zero Infections was completed and published in 2013.
- Lessons from DFID’s implementation of the Frameworks for Results have been collated and shared across DFID in 2017.

The programme has provided evidence on progress under the Frameworks for Results, recommendations to improve effectiveness, particularly on monitoring Value for Money, and lessons for future programming on malaria and reproductive, maternal and newborn health (RMNH).

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Overall Outcome Assessment

The intended outcome of this programme was improved effectiveness and value for money of malaria and reproductive, maternal and newborn health (RMNH) programmes funded by DFID and partners. While there is limited evidence that the activities under the programme have directly led to improved effectiveness, the products have been shared, discussed and used among DFID’s policy and country office health advisers and other DFID departments. In particular, there has been progress in the monitoring of Value for Money in malaria and RMNH programmes, one of the key recommendations in the mid term review of the Frameworks for Results. Other activities across DFID will also have contributed to this.

The indicator used to measure the outcome was ‘the number of DFID malaria and RMNH-related interventions adjusted to address the issues raised by the mid term review (MTR) including to improve the way Value for Money (VfM) is incorporated into logframes’. The MTR recommended that DFID should strengthen the analysis and monitoring of value for money in its health programming. While monitoring VfM does not necessarily lead to improved overall effectiveness of delivery, it is a necessary condition to ensure that programmes are managed effectively so that the impact of each pound spent is maximised.

A 2017 evidence gathering exercise on a sample of programmes showed that VfM monitoring has improved in DFID malaria and RMNH programmes. Although the number of VfM indicators in programme monitoring frameworks (logframes) has not increased, the VfM section of programme Annual Reviews are now more thorough and include quantitative indicators. The 2017 exercise found that overall two thirds of malaria and RMNH Annual Reviews in the sample had VfM indicators either in their logframes or the VfM section of the Annual Review. This compares with the MTR finding that VfM statements made in Annual Reviews tended to be very generic and use of VfM indicators was a rarity.

In addition, in 2017 there was a more even spread of indicators across the ‘4 Es’ of Vfm (economy, efficiency, effectiveness and equity) compared with the findings from the MTR. Monitoring across the whole VfM framework helps provide a comprehensive assessment of VfM taking impact and effectiveness into account, rather than a simple focus on cost. The table below shows that there are now more effectiveness and equity indicators in programme logframes compared with the MTR.

Table 1: The spread of VfM Indicators for existing programmes across the 4 Es
% of programmes with each type of indicator
	Economy	Efficiency	Effectiveness	Equity	% of programmes	Number of programmes
Mid term review (2014)	32%	52%	5%	11%	100%	23
PCR (2017)*	32%	37%	16%	16%	100%	21

* Excludes two process VfM indicators.

Indicator	Milestone	Progress 2017
Number of malaria and RMNH-related interventions adjusted to address the issues raised by the MTR including to improve the way VfM is incorporated into logframes.	15	Achieved: B / It is not possible to assess how many programmes were adjusted to address the issues raised by the MTR. On a proxy measure, an exercise from a sample of programmes shows that two thirds of programmes are using quantitative VfM indicators in Annual Reviews.

Output Score and Description

Overall this programme has scored a B: Outputs moderately did not meet expectation because although outputs were delivered as planned, they did not have the impact on DFID programming that was originally intended.
The programme delivered products to monitor progress and learn lessons from DFD’s delivery on malaria and reproductive, maternal and newborn health (RMNH) under the Frameworks for Results. The original ambition for the programme was much higher, including a full evaluation of the Frameworks for Results. This ambition was reduced following independent expert advice that while feasible, an evaluation would not provide good value for money. Reducing the scope provided considerable savings for DFID but means that the programme did not meet the original expectations.

Output 1: Availability of evidence on effectiveness and relevance of Frameworks for Results
B, performed just under expectations (weighting 80%)
The mid term review (MTR) was published along with DFID’s response in 2014. This contained recommendations, which were primarily focused on strengthening DFID’s analysis, monitoring and reporting of progress rather than policy lessons on malaria and RMNH. A review of the 2011 HIV position paper was also published, in 2013. More recently, lesson learning reviews have been conducted on both malaria and RMNH to identify lessons to inform future programming and broader policy and research agendas.
Output 2: Strengthened accountability for malaria and RMNH across DFID
B, performed just under expectations (weighting 20%).
The findings from the mid term review (MTR) and review of the HIV position paper were communicated within DFID and externally. Awareness of the MTR findings is not high in DFID’s country offices because many of the findings related to DFID corporate systems. Lessons learnt from two recent reviews have been shared with DFID advisers and will be disseminated further.

Lessons and how these have been shared

Evaluation of wide-ranging strategy documents is complex and challenging to do in a way that generates useful learning. One of the key findings from this programme is that learning can be generated at much lower cost and reduced risk through more tailored lesson learning activities, focused on issues of most use to decision-makers.

It was challenging to identify useful learning across the two large and complex policy areas of malaria and reproductive, maternal and newborn health (RMNH). While there were commonalities in the two Frameworks for Results documents, determining key areas of focus and ensuring staff engagement in the process was not straightforward. The final lesson learning products were separated and this helped to identify useful lessons and get staff buy-in to the process.

C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Availability of evidence on effectiveness and relevance of Frameworks for Results
Output number per LF		1	Output Score	B
Risk:		Moderate	Impact weighting (%):	80%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
1.1 Concise reports delivered as specified by TORs on the evaluation of the FfRs on time, with only 2 drafts needed before final version and with limited comments from external reviewers.	Delivery of final evaluation and communication products	Framework for Results products were delivered and the MTR published on time. The MTR needed substantial redraft before finalisation. The full evaluation was not delivered due to reduction in the programme scope, instead ‘lessons learnt’reports were produced to inform future programming. Partially achieved: B
1.2 Deliverables as specified by TORs for the review of the 2011 HIV Position Paper, complete on time to publish DFID review paper by World AIDS Day 2013	Review of results, facilitation of 3 workshops, report on findings and knowledge management system delivered.	Following information gathering and 3 stakeholder workshops, DFID published a review of the 2011 HIV position paper in time for World AIDS Day 2013. / Achieved: A
1.3 Number of products reviewed externally with comprehensive comments delivered within agreed deadlines.	2	The MTR was reviewed by external evaluation experts. The lessons learnt products were not reviewed externally. / Partially achieved: B

Key Points

Output 1.1 The external consortium ePACT delivered the inception report (or evaluability assessment) and the mid term review (MTR) in 2013. The consortium also produced two-page summaries of the report, one for malaria and one for RMNH. These which were used for communication to external stakeholders.

The MTR found that the Frameworks for Results had served an important and effective role. They strengthened DFID’s influence in international forums and contributed to sustaining or reinforcing international attention on malaria and RMNH. The evidence reviews supporting the Frameworks had been high quality and had an independent value in providing an authoritative assessment of the evidence on effective interventions. It also found that DFID was broadly on track against the spending and results commitments within the Frameworks. The MTR and the summaries were published in May 2014. At the same time DFID published its response.

The final evaluation was not conducted. On the basis of external expert advice it was decided that while feasible, an evaluation of the Frameworks for Results was unlikely to provide value for money. In addition, it would duplicate existing monitoring of DFID’s commitments through the DFID Results Framework. Instead, in line with expert advice, the programme was used to carry out focused lesson learning to inform future programming decisions.

The report Lessons learned from DFID Reproductive, Maternal and Newborn Health (RMNH) Programmes (2010-2015) was presented to DFID health advisers and finalised in April 2017. Its purpose was to identify lessons to inform future RMNH programming and broader policy and research agendas. It found that the most effective programmes were designed flexibly to respond to changing contexts. Programmes were less successful when they did not secure government ownership or build sustainability sufficiently into programme design. The Head of Profession for Health will promote the report with all health advisers and it has also been shared with DFID’s programme Quality Assurance Unit so they can use the lessons in their work.
The malaria lesson learning report Lessons from DFID malaria programming was also presented to health advisers in April 2017. It was split into two parts. Part 1 analysed the current malaria situation, especially in Southeast Asia. It highlighted the increased technical challenges for malaria control which will make it more difficult to build strategic and technical consensus between malaria control partners. Part 2 was focused on managing complex programmes, especially in uncertain environments. Lessons from effective and adaptive programmes included ensuring a clear theory of change, effective risk management and adequate staffing requirements. The report found that DFID has a good track record of engagement with partners, bringing together technical and institutional stakeholders to achieve effective outcomes. The report has been discussed with DFID’s Better Delivery Team and is informing Human Development Department’s approach to managing its programmes.

Output 1.2 Despite some challenges, a review of the 2011 HIV position paper “Towards Zero Infections-Two Years On” was published to time in November 2013.

Output 1.3 The MTR was reviewed by two external evaluation experts before finalisation.

Summary of responses to issues raised in previous annual reviews (where relevant)

1. Concrete plans for lesson learning on malaria and RMNH should be developed separately by the relevant teams, rather than being managed together. By end March 2016.

This recommendation was implemented: the lesson learning for malaria and RMNH was delinked. This meant that the respective policy teams could decide, in consultation with health advisers across DFID, which activities were of most value.

2. The logframe should be revised to reflect changes in approach since the programme was approved. By end April 2016.

This recommendation was implemented: some milestones in the logframe were updated in December 2016.

Recommendations for future programmes

Evaluation of wide-ranging strategy documents is unlikely to be good Value for Money. Learning can be generated at much lower cost and reduced risk through more tailored and demand-led activities, focused on issues of most use to decision-makers.

Output Title	Strengthened accountability for malaria and RMNH across DFID
Output number per LF		2	Output Score	B
Risk:		Minor	Impact weighting (%):	20%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
2.1 Number of DFID health advisers contributing to the gathering of evidence	16	Health advisers across DFID contributed to the gathering of evidence for the MTR and lesson learning products. / Achieved: A
2.2 Number of DFID Departments or country offices involved in discussions on implementing the recommendations from the MTR and evaluation.	10	10 DFID Departments were involved in discussions on implementation of the MTR recommendations. / Achieved: A
2.3 % of health advisers aware of MTR and evaluation findings.	100%	The findings from the MTR and lessons learnt reports were communicated internally. Further communication activity is planned but awareness among health advisers is unlikely to be universal. / Partially Achieved: B

Key Points
Output 2.1. As part of the MTR evidence gathering, the consultants conducted an e-survey of DFID’s country programmes. Responses were received fron 19 country offices. Key Informant Interviews were held with representatives from 12 DFID Departments and in depth case studies were conducted in three DFID priority countries (Ethiopia, India and Nigeria). The consultants producing the malaria lessons learnt study met 9 DFID staff.
Output 2.2. A wide range of departments were involved in discussions on the DFID response to the MTR and evaluation including Finance, Corporate and Performance Division, Research and Evidence Division, Africa Regional Department and Asia Regional Department.

Output 2.3. The milestone was ambitious and only partly achieved. The findings from the mid term review were communicated internally through Insight and a meeting with health advisers and externally to key stakeholders. There was also a follow-up meeting with health advisers on value for money in health programmes, focusing on experience in Mozambique and Zambia.

Summary of responses to issues raised in previous annual reviews (where relevant)

No recommendations in the previous annual review.

Recommendations for future programmes
To increase engagement in lesson learning, it is important to embed this into DFID processes, for example using regular adviser meetings, with the support of the Head of Profession.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

Costs for the programme were determined by fixed term agreements with suppliers. Cost drivers were salary costs, particularly the mix of personnel involved in the consortium and the number of days they were used. Some of the difficulties in the production of the mid term review were due to insufficient technical expertise. A lesson for the future is to ensure sufficient days from relevant health experts are built into contracts.

VfM performance compared to the original VfM proposition in the business case

The approach for the programme was driven by value for money considerations. Considerable savings were made by not proceeding with an evaluation of the Frameworks for Results. The initial estimate for the all activities under the programme, including the evaluation, was £4.5m. The total spend was £713,133. Following the reduction in scope, the planned activities were focused on issues that were important for the policy teams’ future decisions.

Assessment of whether the programme represented value for money

Due to the significantly reduced scope and spend, this programme represented value for money against the revised objectives despite performance against the outputs being slightly below expectations.The reduction in the ambition for the programme represented a cost saving for DFID of £3.7 million. For a significantly reduced spend, DFID still generated widespread learning through the MTR and the lessons learning products.

Quality of financial management during programme

There has been good quality financial management of this programme. The agreed products were delivered to time. Following production of the MTR and decisions to revise the programme approach, the contract with ePACT was terminated.

Date of last narrative financial report	n/a
Date of last audited annual statement	n/a

E: RISK (½ page)

Quality of risk management over the life of the programme

Following the reduced ambition for the programme, the key risks became a lack of commitment or capacity from stakeholders across DFID to participate in lesson learning. This risk was mitigated by involving the Heads of Profession for Health.

Over the life of the programme, the risk register has been kept updated to reflect changes and mitigating actions have been taken to minimise this risk.

Risk	Impact	Like-lihood	Direction / of travel	Action to mitigate risk
Insufficient expertise and capacity within HDD to maintain momentum over time.	Major	Minor	→	Deputy Head HDD to retain leadership to ensure lesson learning products are delivered and disseminated. Include responsibilities in job objectives of members of the IMG. Keep relevant team leaders in HDD up-to-date on progress.
Lack of capacity among DFID advisers to engage in lesson learning discussions.	Moderate	Moderate	↗	Organise a few high quality sessions and publicise well in advance.
Findings from lesson learning products not acted on.	Moderate	Minor	↗	Follow up if necessary and raise key issues with senior management.
Insufficient reliable DFID monitoring data available for the PCR.	Minor	Moderate	→	Being addressed through dedicated collection of evidence from DFID programmes.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

The mid term review, HIV position paper review and lesson learning products were completed on time.

Performance of partnership (s)

Not applicable.

Asset disposal and value obtained by DFID

Not applicable.

CONDITIONALITY (½ page)

Partnership principles assessment

Not applicable.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

Evidence of what works across the malaria and RMNH portfolios was gathered through the lesson learning exercise this year. The RMNH lesson learning product used evidence from a two stage methodology, The first stage consisted of a rapid review of 23 programmes from the development tracker site (of 41). The second stage consisted of 6 case studies, which involved a document review (DFID, web) and interviews with DFID staff and partners.

The malaria lesson learning products used evidence from a desk review which included: programme documents; strategy documents; DFID’s historic “How to Notes”, as well as the more recent “Smart Guides” and “Smart Rules”; and contextual documents from WHO, RBM and others. DFID staff also provided some draft documents and memos and a study, referred to below, on Adaptive Programming. It provided a framework for semi-structured interviews. Contextual interviews were conducted with a wide range of stakeholders in the wider global malaria community with which DFID interacted. Initial interviews took place at a meeting of senior officials of the Asia Pacific Leaders Malaria Alliance in May 2015. This provided opportunities to observe proceedings, to interact with a range of stakeholders, and to conduct interviews. Further interviews were conducted during a field visit to South East Asia by one of the consultants.

Four main types of data collection and analysis were carried out within the programme: document reviews, key informant interviews, quantitative data analysis, and questionnaire responses.

Monitoring progress throughout the programme

This PCR has been led by Penny Innes, deputy head Human Development Department, supported by Chloe Brooks. Input has been received from team leaders and advisers from the Health Services Team and Sexual and Reproductive Health and Rights Team and Scott Hardie and Paulina Paterson, project officers.

Smart Guide
The Programme Completion Review is the opportunity to reflect on the entire programme, its performance, achievements, lessons and how learning will be shared to inform future programming.

The Programme Completion Report assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with headline information on the programme and any follow up actions / Early closure is likely to be summed up by issues such as ‘poor performance by partners’ and/or ‘major changes in operating environment’
A: Introduction and Context
Briefly outline the programme, results achieved and contribution to the overall Operational Plan and DFID’s international development objectives. Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Outcome Assessment / Brief assessment of whether the programme achieved the Outcome
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Output Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on AMPas part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Minor/Moderate/Major/Severe / Enter: Minor, Moderate, Major or Severe / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Where the Risk for this Output has been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section E Risk
Key points
Summary of response to issues raised in previous annual reviews (where relevant)
Recommendations for future programmes
Repeat above for each Output.
D: Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case. Performance against vfm measures and any trigger points that were identified to track through the programme / If programme was closed >1 month early please describe in a few words why, what savings were made, as well as what money was spent.
Assessment of whether the programme represented value for money? / Overall view on whether the programme was good value for money
Quality of Financial Management during programme / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E: Risk
Quality of risk management over the life of the programme. / How were risks managed, the degree to which they were realised and/or mitigated? / Did any risks materialised throught the duration of the programme which were not forseen? What where they and how was this managed? / What lessons have been learned?
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / Could DFID be a more effective partner
Asset disposal and value obtained by DFID / How were assets managed throughout the programme? How have they been (or will they be) disposed to get maximum value?
G: Conditionality
Partnership principles assessment / For programmes where we have decided to use the PPs for management and monitoring, PCRs should generally include an assessment of commitment to the PPs, including any concerns that have occurred over the year, the partner government’s response, and details of any response by us. Teams should refer to the DFID guidance on reviewing projects.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the programme / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review and PCR process