## Annual Review Template

Title: Annual Review of the UK’s contribution to the Reserve Account of the IMF’s Resilience and Sustainability Trust
Programme Value £ (full life): £44,090,383.13		Review date: 30/06/2024
Programme Code: [AMP ID#] 400012	AMP start date: 04/05/2023	AMP end date: 20/04/2025

Summary of Programme Performance
Year	2024
Overall Output Score	A
Risk Rating	Moderate

DevTracker Link to Business Case:	DevTracker Programme GB-GOV-1-400012 Documents (fcdo.gov.uk)
DevTracker Link to results framework:	The results framework will be uploaded to Devtracker and will shortly be available online.

A. SUMMARY AND OVERVIEW

Description of programme

The Resilience and Sustainability Facility (RSF) is an IMF lending facility that provides loans to developing countries, including at concessional rates for the most vulnerable countries. It sits within the Resilience and Sustainability Trust (RST). The loans support countries to address long-term structural challenges that will improve their prospective Balance of Payments stability. To date, all RST loans granted have focused on addressing climate-change related challenges.

The UK’s £44mn ODA contribution facilitated Special Drawing Rights (SDR) loans by the UK to the RSF of SDR 1.8bn (circa £2bn), by providing the cash contribution needed to establish a satisfactory level of reserves. These reserves allow for the management of RSF credit risk and ensure that the reserve asset status of SDR contributions is maintained.

In August 2021 the IMF approved a historic SDR 456 billion ($650billion) allocation to boost global liquidity in response to the Covid-19 pandemic. The newly-created SDRs were allocated to IMF member countries in proportion to their quota. The UK’s SDR 2.5billion contribution to the RSF, along with the UK’s contribution to the PRGT, delivered the UK’s commitment to on-lend 20% of its 2021 SDR allocation, in line with the G20 commitment to support vulnerable countries.

Summary supporting narrative for the overall score in this review

The establishment of the RST – at a time of unprecedented shocks – was a breakthrough innovation in the Fund’s toolkit, and a clear signal of the Fund’s key role in supporting vulnerable countries to build resilience to ensure a strong and sustainable recovery. RSF arrangements have gotten off to a strong start. During the first 17 months of operation of the facility, 18 RSF arrangements with client countries were approved by the Executive Board, amounting to SDR 6.3 billion (about $8.4 billion). Demand for the facility is high - the IMF anticipates that between 30-35 countries could bring requests for Board consideration through 2026. Reserve levels are adequate across a range of scenarios.

The first RST programmes have generally been well-tailored to country needs and have been the product of good collaboration with other development finance partners. The IMF has played an important convening role in a sub-section of ‘pilot’ countries, which has helped borrower countries to identify and explore a broad range of solutions to their climate finance needs.

The IMF has recently completed an interim review of the RST. It has identified a number of design modifications that will improve the effectiveness of the facility which will be implemented in future programmes.

Major lessons and recommendations for the year ahead

We are strong supporters of the RST as a means to provide long-term catalytic policy reform and financing to support low-income countries, small (island) developing states and vulnerable middle-income countries to reduce risks to balance of payments stability, especially those stemming from climate change. The IMF should continue to clearly align the focus of its participation in climate finance mobilisation with its mandate in promoting macroeconomic stability. The IMF, through its RSF lending terms, should also continue to promote the policy and regulatory changes needed to attract climate finance at scale.
While there have been some very good examples of engagement with development partners, deepening collaboration with other financing institutions (in particular the World Bank and other multilateral development banks (MDBs)) is vital for coordinating and streamlining the policy requirements associated with different sources of climate lending and reducing the burden on borrower country administrations.
Engagement with external stakeholders, including civil society organisations in borrower countries, should be enhanced in future programmes to ensure that programme design draws on a range of expertise, provides additionality over and above other activities being undertaken in this area and fully accounts for downstream impacts of proposed reforms. It’s also vital that particular attention be given to the implications of the Fund’s thematic strategies for RST lending - including the Fund’s strategy on fragile and conflict-affected states, the Fund’s Strategy for IMF Engagement on Social Spending and the Strategy towards Mainstreaming Gender. Ensuring that the Fund’s work on governance informs the development of the RST programmes will also be essential.
More can be done to situate RST reform measures alongside countries’ Nationally Determined Contributions and National Adaptation Plans (documents that set out a country’s plans to contribute to the goals of the Paris Agreement treaty on climate change) to get a holistic view of financing needs. Specifically, we regard the Fund’s ability to use routine surveillance reports and diagnostic assessments to inform the design of relevant and high-quality reform measures as central to the effectiveness of RSF arrangements, reinforced by capacity development where needed. It is vital that modelling of different climate scenarios and the appropriate responses be incorporated into the Fund’s surveillance and programme activities more widely. With respect to the RST in particular, we would encourage the IMF to utilise these programmes to incorporate advice and planning for various climate shock scenarios, including risk insurance, into borrowers’ toolkits.
The Fund should think about more flexible models for donors to contribute to the RST’s fundraising needs without being too rigid on the division of financing between the reserve account and loan account for any individual contributor. A fundraising plan should also be established to identify how to meet the anticipated near-term shortfall in resourcing of SDR 5billion (~$6.6billion).

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The Theory of Change (ToC) set out in the business case in 2022 remains valid:

INPUT	ACTIVITY	OUTPUT	IMPACT/OUTCOME
UK makes contribution to the RST. The IMF disburse loans via the RST to vulnerable countries on concessional lending terms with long-term maturity.	IMF and country agree policy conditionality on loans, ensuring that the regular disbursals of RST finance are only delivered once programme benchmarks are completed by the borrowing country.	Strengthened public financial management related to climate change/pandemics. E.g., for climate - Identification of climate vulnerabilities and financing needs. Stronger country policies relating to renewable energy and transition. Stronger climate-based investment management.	Countries with RST programmes are more resilient to climate variability and pandemic risk, and thus capable of more sustainable patterns of economic growth, financial stability and resilience. Economic and human loss is reduced during crises including pandemic/epidemic disease and climate-related events.

While there have not yet been any programmes agreed related to pandemic preparedness, we anticipate that some such programmes will come on-stream in the coming months. We expect the UK, via the IMF Executive Board, to have sight of any framework for designing such programmes, to ensure they are focused on macro-critical reforms.

It is still very early to assess the impact and outcome levels of the theory of change. Reform Measure implementation performance in 2023 was 75%. This figure rises to 90% once the Niger RSF is removed from the calculation - there has been considerable political unrest in Niger that has impeded delivery. This suggests quite a strong level of early adherence to the RST programme plan by borrower countries.

One consideration not fully captured in this theory of change relates to the duration of RST programmes. The long-term nature of climate adaptation and mitigation measures and the potential for significant policy reversals outside of the life of the programme poses some challenge to the theory of change. In this respect, we encourage the IMF to consider how the long-term impacts of RST programmes may be monitored and evaluated, beyond the life of an individual programme. Systemic coverage of climate issues in the Fund’s surveillance activities (e.g. the IMF’s routine monitoring of the economic health and financial stability of individual economies) can help track the continued implementation of reform measures once an RSF programme concludes.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The programme is broadly on track to contribute to expected outcomes and impact, albeit it is quite early on to determine the programme’s contribution to the desired impact. A comprehensive review of the RST is planned for 2026.

The strong level of demand that has been demonstrated for RST programme does indicate that the programme may be delivering against an original ambition to destigmatise Fund lending. The reported pipeline of 30-35 countries indicates a strong willingness by prospective borrowers to engage in climate-related activities relevant to macroeconomic stability, as well as to undertake the broader economic reforms required by a parallel IMF programme that works to restore near-term Balance of Payments stability (an upper-credit tranche (UCT) quality program).

A constraint to the Fund’s ability to deliver against demand could come from a failure to meet the additional required fundraising target. However, commitments to further SDR channelling by some shareholders remain a distinct possibility. Another constraint to bear in mind is the human resource challenges that the IMF faces in delivering this volume of RST programmes to a high standard, and in a manner that is tailored to individual country circumstance. A strong forward-looking plan on how to resource this volume of RST programmes with the appropriate climate expertise, while simultaneously protecting other climate surveillance work, is crucial.

The IMF and World Bank have recently agreed an enhanced cooperation framework to help countries scale up action to confront the threat of climate change. The collaboration will provide support for countries’ climate strategies – through an integrated, country-led approach to policy reforms and climate investments – and should help make efforts less duplicative, and ensure reforms draw on the same analysis and evidence base.
[note] World Bank Group and IMF Deepen Joint Effort to Scale Up Climate Action-

The RST programmes are not yet contributing to outputs and impacts related to pandemic preparedness. This was a conscious decision by the IMF, supported by shareholders, based on the need to specialise in the initial stages of the programme and it reflected high demand and international appetite for lending related to progress against climate mitigation and adaptation. It is anticipated that some upcoming programmes will relate to pandemic preparedness. It has been clearly signalled to the IMF that these programmes should draw heavily on the expertise and established processes of the World Health Organization and the World Bank in these areas.

In order to ensure that RST programmes are appropriately tailored to the individual context of recipient countries and strengthen the consideration of the distributional impacts of the programmes, we would like to see further evidence that the Fund’s policies related to operating in fragile and conflict affected states, mainstreaming gender and strengthening social protection are all incorporated and embedded in RST programmes going forward. We would also like to see more consideration given, in line with the Operational Guidance Note, to the interaction between governance and climate ambitions - further consideration of how institutional constraints may disincentivise the type or volume of investment needed to meet climate ambitions is needed.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

The return-on-investment provided by unlocking billions of lending through Special Drawing Rights makes lending to the RST a uniquely strong value for money proposition. By contributing toward the establishment and implementation of key macro-critical climate-related policies and, in doing so, helping to potentially catalyse much larger volumes of climate finance, the contribution to the reserve account of the RST clearly fits within FCDO and HMG’s ambitions on tackling the global climate crisis.

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title	RST is operationalised in a timely manner and adequate lending resources secured.
Output number:		1	Output Score:	A
Impact weighting (%):		35%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
Sufficient volume of finance to meet initial demand is achieved	33bn SDR initial fundraising target	Met (within 10% of target). 31bn of SDR contributions were effective as at April 2024
Sufficient diversity of contributors achieved to maintain encashment function for contributions	Number and volume of contributions sufficient to meet encashment needs	Met. 21 countries had pledged contributions as at March 2024

Briefly describe the output’s activities and provide supporting narrative for the score.

After securing an initial contribution of SDR 15.3bn from six countries, which facilitated the operationalisation of the RST at the Annual meetings in October 2022, Fund staff have continued efforts to secure SDR contributions from a variety of countries that have strong reserves and are in a position of Balance of Payments stability.

As of mid-March 2024, 21 countries have pledged SDR 31.9 billion in total RST resources. Of this amount, SDR 26.3 billion pledged from 18 countries are contribution packages providing loan, deposit and reserve resources (about 80 percent of the initial target for loan resources), and SDR 5.6 billion are pledged standalone contributions to the reserve or deposit accounts from three countries. This has ensured that there has been an ample volume of finance available to deliver the 18 programmes delivered to date and to finance a pipeline of future programmes.

The wide number and regional diversity of the contributors have also allowed for a strong encashment regime to underpin the lending, which ensures that the reserve status of SDR loans is maintained for the lender. The liquidity buffer must be 20 percent of total loan resources or the largest loan account contribution if this exceeds it. Under the current assumption of usable loan resources being capped at SDR 16.7 billion, the liquidity buffer amounts to about 24 percent.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

As of mid-March 2024, around 30-35 countries have expressed interest in an RSF arrangement. This is somewhat above the demand anticipated last year. The baseline scenario modelled by the IMF anticipates that SDR 22bn would be committed through to 2026.

Design modifications for the RSF, to be introduced through the interim review process, including related to access policies, should make demand forecasting somewhat easier. At the same time, the initiation of programmes related to pandemic preparedness could add somewhat to the number of programmes being requested. Consideration should be given to the appropriate profile of fundraising targets under this output ahead of the next review.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

A key lesson learned was that the design of the RST, which requires simultaneous contributions to the Loan Account, the Reserve Account and the Deposit Account, might constrain the ability of potential contributors to provide resources. To support fundraising efforts, we support consideration of more flexible models for donors to work together to contribute to satisfy fundraising needs without being too rigid on the resources and ratio of resources being contributed.

Output Title	Reserve Adequacy is maintained in the Reserve Account
Output number:		2	Output Score:	A+
Impact weighting (%):		15%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
Reserve Coverage	10% reserve coverage benchmark	Exceeded. Under the central funding scenario,14% reserve coverage/ credit outstanding is achieved.

Briefly describe the output’s activities and provide supporting narrative for the score.

Maintaining adequate reserve coverage is a key safeguard measure to mitigate credit and liquidity risk for the RST. The Reserve Account primarily provides this function, although there is provision for the Deposit Account to act as a backstop to the reserve account in an extreme tail risk scenario.

At 14%, reserve adequacy remains sufficient in the central scenario. Even in a ‘downside’ scenario, where interest rates remains high, the number of the poorest countries borrowing at rates below the IMF’s interest rate increases and the return on investments is lower than expected, reserve adequacy sits at 11%.

The strong reserve levels result in part from high standalone contributions to the reserve and deposit accounts.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

While a strong level of reserves is strongly desirable, attention must be paid to ensure that the build-up in the RA is not excessive and that funds are being used for their intended purpose.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

N/A

Output Title	Number of RST programmes implemented
Output number:		3	Output Score:	A
Impact weighting (%):		15%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
Number of RST programmes implemented / related to climate change BoP stability	Function of demand. (Circa 10 per annum)	18 over 18 months
Number of RST programmes implemented related to pandemic preparedness BoP stability	Function of demand. (Circa 10 per annum)	0

Briefly describe the output’s activities and provide supporting narrative for the score.

In the early stages of the implementation of the RST, there was uncertainty about the level of demand that would exist for the programme. Time has proven that demand to be very high, with 30-35 programmes in the pipeline. The IMF has stepped up significantly to deliver a high volume of programmes in a relatively short period of time (18 at the point of the interim review). This has been resource intensive, and will continue to be, although there will be economies of experience and expertise achievable in the development of later programmes.

All RST programmes so far have focused on prospective Balance of Payments risks associated with climate change. The Fund has not yet commenced programmes related to pandemic preparedness, though we anticipate that some such programmes will come on board shortly. It is very important that those programmes draw very heavily on pre-existing frameworks of the World Bank and the World Health organisation, both to minimise the administrative burden for borrower countries, and to capitalise on the expertise that already exists in those organisations.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The postponement of programmes related to pandemic preparedness was justifiable, given the resource constraints that faced the Fund in delivering climate-change related programmes. The appropriate figure for pandemic related programmes in the output scoring should be reconsidered, taking account of demand.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

While a continued high ambition on RST delivery is needed, the associated risks should be given adequate consideration ahead of the next FCDO review. The RST interim review identifies the following human resources risk:

“These risks stem from inadequate resourcing that could strain overextended staff, including non-fungible experts and fungible staff trying to quickly gain climate expertise, in the face of strong RSF demand. Consequently, these staff could experience burnout…

Strong RSF demand also has implications for the Fund’s capacity development resources, and climate-related work could crowd out non-climate capacity development in regions with high numbers of RSF arrangements. However, the proposed modifications to the RST instrument are not expected to have an additional impact on HR risks.”

The risk that climate expertise could be diverted from other key work, like routine surveillance, is a risk that should be considered when setting the appropriate scale of ambition on this output going forward.

Output Title	Reforms that enhance Balance of Payments resilience implemented by borrower country
Output number:		4	Output Score:	B
Impact weighting (%):		25	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
Proportion of climate change- related reform measures that are implemented by borrower countries	85%	Moderately did not meet target. 75% (90% without Niger case)
Proportion of pandemic preparedness- related reform measures that are implemented by borrower countries	85%	N/A

Briefly describe the output’s activities and provide supporting narrative for the score.

A key metric of the success of RST programmes toward achieving their long-term ambitions of achieving prospective Balance of Payments stability against risks of climate change and pandemics is the success of implementation of the agreed reform measures within the programme.

While it is still relatively early in the process to measure implementation of reforms, and further to assess the durability and effectiveness of those reforms, some metric was needed.

The IMF report that the 18 climate change-related RSF arrangements that have been approved by the Board to date encompass 211 reform measures spanning various climate-related areas and issues. 75% of those reform measures comprise “green” public financial management, financial sector and fiscal policy reforms. The other 25% target the unique set of climate change challenges each country faces and a given sector’s macro criticality.

The IMF report notes that 75% of reform measures have been implemented. This figure rises to 90% when the Niger RST is excluded. The Fund suggests that 90% implementation reflects ownership by the authorities.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Going forward, some more nuance should be added to this output indicator, to take a measure of the depth, level of ambition and criticality of the reform measures associated with RST programmes.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

A lesson of the RST programmes implemented to date is that the duration of the programmes may be too short to facilitate the implementation of meaningful reforms on such long-term and, sometimes, politically difficult issues. The interim review of the RST suggests that consideration should be given to the scope to extend the duration of RST programmes a small bit beyond that of the associated upper-credit tranche macroeconomic programme (which is usually 3-5 years in the case of low-income countries) to account for that.

Output Title	Alignment of RST programmes with approaches of internal and external partners
Output number:		5	Output Score:	A
Impact weighting (%):		10	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
Consistent evidence of collaboration with the World Bank across programmes	References to CCDRs. Evidence of development of joint policy matrices and learning from one another.	Some examples of strong collaboration.
Alignment of RST programme ambitions with IMF Capacity Development work and climate diagnostics	Qualitative assessment + references to C-PIMA, CMAP	Reasonable reliance on existing diagnostics, though cessation/ reduction in CMAPs an issue for this indicator
Evidence of close working with development partners in relevant countries	Qualitative, based on feedback from overseas networks	Strong convening impact in pilot countries and generally good collaboration with development partners reported.
Evidence of alignment of RST programme with domestic plans of borrower governments	Qualitative, based on feedback from overseas networks. Evidence of alignment with published strategies/ NDC documentation etc	Again, mixed evidence, often depending on maturity of existing plans at country level. More required to align with national adaptation strategies and NDC plans.

Briefly describe the output’s activities and provide supporting narrative for the score.

From the outset, IMF shareholders were clear on the importance of RST programmes delivering activities that are complementary to national plans and to ongoing climate work of the World Bank and other IFIs. Engagement on issues related to climate mitigation and adaptation is a new area of work for the IMF, on which expertise had to be attained quickly. There is reasonably good evidence of the use by the Fund of existing diagnostics, such as the World Bank’s Country Climate and Development Reports. The Fund’s Climate Public Investment Management Assessments and Climate Policy Diagnostics have been drawn on, where available. Further models are being developed by the Fund. Capacity Development support has, in some instances, supported the implementation of the programme, though more clarity about how capacity development plans will be embedded into the RST programme design process would be welcome.

FCDO’s overseas network reported quite positively on the quality of engagement between IMF staff and development partners in-country. In a sub-section of countries - eg, Jamaica, Barbados and Kenya - FCDO staff praised particularly the convening role that the IMF had played and the rigour and accountability for delivering actions that came about from the disbursement-linked reform measures.

Ideally, a clearer link would be demonstrated between RST programmes and the pre-existing climate commitments that countries have already made.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Consideration should be given to incorporating a measure of success of collaboration with the World Health Organization in future reviews.

An output that specifically assesses the number and quality of joint policy matrices with the World Bank and other partners should be considered. Further feedback could also be gathered from the network of FCDO Missions about the appropriateness and complementarity of reform measures and reflected in the scoring process.

Future iterations of the results framework should look to incorporate quantitative metrics under this output.

Consideration should be given to incorporating an output metric that captures the extent of Fund engagement with Civil Society Organisations and domestic representative groups, to ensure a diversity of experiences and views are fed into the RST design process.

A greater weighting should be considered for the alignment with domestic priorities, as the IMF moves toward an ambition of more nationally-led processes around climate finance management.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

The IMF has been on a learning process since the initiation of the RST. While there has been a varied experience in the quality of IMF engagement with stakeholders at country level, there have been some examples of gold standard outreach. Staff should be encouraged to implement this element, as set out in the operational guidance for the RST, to ensure no duplication of conditionality and a holistic understanding of the climate-related Balance of Payments needs of the particular country.

## D: VALUE FOR MONEY (1 page)

Key cost drivers and performance

Administrative costs associated with the RST are financed primarily by investment income on the reserve account contributions. These costs will be in the range of SDR 12mn to SDR 25mn (~$16mn to $33mn), depending on the scenario presented.

VfM performance compared to the original VfM proposition in the business case

The case for mobilising finance for global climate adaptation and mitigation is as strong as ever. Estimates of global climate financing needs are inherently uncertain, but a recent OECD synthesis of evidence found that developing country climate investment needs lie between $0.5-$2.5tn per year by 2030.

Due to the relatively high rate of global interest rates over the life of the programme, returns on invested reserve assets were sufficient to facilitate a cap being placed on lending to the poorest countries, capping the interest rate at 2.25%. This has increased the concessionality that reserve account contributions have facilitated, relative to the lending terms initially established for the Trust.

Assessment of whether the programme continues to represent value for money
By providing the requisite 2% contribution to the RST’s reserve account, the UK’s £44mn ODA contribution facilitated on-lending of SDR worth in the region of 40 times that amount, the reserve account contribution to the RST represents excellent value for money. Through continuous iteration and adaptation of the approach to RST lending, drawing on the experience of initial ‘pilot’ countries and others, the performance and targeting of RST programmes and reform measures should continue to improve.

E: RISK

Overview of risk management

The overall risk level of the programme is moderate, which matches the risk appetite. See the programme risk register as at April 2024 in the Annex.

Risks related to policy and programme delivery are broadly common to all UK lending to the IMF and are mitigated through the IMF’s robust management frameworks. The UK Executive Director to the Fund and their office, as Board representatives, are responsible for working with a range of UK government departments, as well as IMF staff and management, to ensure that any risks are mitigated.

There is a risk that governing authorities of borrowing countries misuse the funds and do not abide by the conditionality associated with the programmes. This risk is mitigated considerably by RST design features. Under the RSF, disbursements are tied to the delivery of specific reform measures, the success of which are judged by the IMF Board through regular review processes. The risk is further mitigated by the requirement that an on-track upper credit tranche-quality programme (a macroeconomic programme designed to resolve Balance of Payments problems and provide adequate safeguards) must accompany an RSF programme. UCT programmes often contain conditions related to transparency, anti-corruption methods etc.

There are minor risks associated with the RST’s investment strategy. These include the risk that RST funds are invested in poor-performing assets that sustain losses over multiple years. There’s also a reputational risk involved, which would arise were RST funds invested in assets that aren’t managed in accordance with sound Environmental, Social and Governance principles. These risks are mitigated through close scrutiny by the Board of the Fund’s investment strategy, and by the liquid nature of the investments that the Fund invests in.

There is a moderate credit risk associated with the programme. This is the risk that RST loans perform badly (i.e. that countries are not able to repay funds that they have been lent) and there are numerous arrears and defaults that threaten the financial integrity of the Trust. This risk is mitigated by the Fund’s multi-layered safeguarding framework, the maintenance of a strong level of reserves and the established status of the IMF as a ‘preferred creditor’. It is also mitigated by the requirement that an applicant country’s debt position be sustainable, according to the Fund’s debt sustainability assessment.

There are also moderate risks associated with the strategy and context of the programme. Political risks include the risk that proposed programmes support countries who do not share UK values, development priorities, and respect for human rights or that programmes are approved for countries with UK sanctions regimes in place. These risks are strongly mitigated by the fact that programme approvals require a Board majority and there is alignment amongst many significant shareholders at the Board on the primacy of key values.

Other risks that were flagged in the RST interim review include “risks related to program design include the potential duplication of other International Financial Institutions’ (IFIs) work, delays in implementation of reforms under the concurrent UCT-quality program owing to large and frontloaded access to RST financing, and challenges associated with expanding structural conditionality to new areas, including designing and monitoring programs and mission creep”. Continued iteration of the approach to RST programmes and the introduction of design changes to eliminate dual-purpose reforms and deepening of reform measures to entrench commitment to the policy direction are amongst the mitigation approaches.

There is also a human resources risk - that the RST may have inadequate resourcing, or that staff with climate expertise are drawn away from other key functions at the IMF. This risk will need to be kept under constant review.

Another risk relates to resourcing of the Trust. On current estimates, about SDR 5 billion (~$6.6 billion) of near-term fundraising is required to meet demand. While countries with strong external positions are encouraged to contribute as generously as possible to the Fund’s facilities, there are prudent limits to each country’s ability to on-lend Special Drawing Rights. Ongoing monitoring of fundraising efforts and emerging demand levels will be required.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

The IMF provides a significant volume of reporting on its RST lending. Each individual RST programme is considered on its own merits by the IMF Board, informed by a detailed case, and the progress of the programmes and each associated disbursement is also considered by the Board. The recent interim review provided detailed figures on SDRs pledged and delivered and projected balances and reserve adequacy in an array of scenarios. This review is now publicly available. Providing this information in a format more amenable for analysis would help with external scrutiny.
[note] Interim Review of The Resilience and Sustainability Trust and Review of Adequacy of Resources (imf.org)

The IMF Board are frequently appraised of emerging and ongoing risks at programme and portfolio level. IMF finances are governed by strict auditing and transparency rules.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation

The interim review of the RST that was issued by the IMF provides a strong starting point on monitoring and evaluation of the programme. It includes a survey of senior IMF staff and feedback from those administrations that have availed of RST programmes.

In response to this feedback, the IMF proposed a number of design changes to address the operational challenges and peculiarities that have come to light through the implementation stage.

In parallel to the IMF’s own review, the network of UK staff working in the overseas network, situated in countries that received an RST programme, were consulted for their independent views of RST progress to date. This process will be repeated in a year’s time.

The FCDO has also worked closely with colleagues from HM Treasury and the Bank of England to ensure alignment of UK government perspectives on the operations of the RST to date and its strategy going forward.

With regards monitoring, an area that will require further thought by the Fund and shareholders is how the success of RST programmes can continue to be evaluated beyond the life of the programme. The inherently long-term nature of the climate reforms that are required, the challenges posed by quickly implementation of reform measures that require significant expertise and administrative burden and the relatively long repayment terms make a case for some level of ongoing monitoring of impacts after the completion of the programme.

A comprehensive review of the RST is expected to take place in 2026. This should include more extensive consultation and reporting on a wider array of dimensions of the RST implementation.

Date of last narrative financial report	Quarter ended / 31-01-1-2024	Date of last audited annual statement	30-04-2023

Annex: Programme Risk Register as at April 2024

Risk Description (cause, event, consequence)	Risk Category	Mitigation Strategy (including timescales)	Residual Risk Rating	Risk Appetite
Political risks: IMF and IMF Executive Board change the mandate of the Trust so it is no longer aligned to UK values and development objectives	Strategy and Context	A majority of the IMF Executive Board share the UK values and support for development objectives. The UK Executive Director to the Fund and their office, as Board representatives, are responsible for working with a range of UK government departments, as well as IMF staff and management, to ensure that any risks are mitigated.	Moderate	Receptive
Political Risk: RST programmes are approved by the Executive Board for countries with UK sanctions regimes in place against country authorities.	Strategy and Context	IMF is a trusted partner with strong alignment to UK democratic principles. The IMF Executive Board, which approves programmes on a majority basis, has voting power duly weighted in favour of key partners and allies that also share these principles. UK officials will ensure that the UK vote on any programmes brought before the IMF Board for RST lending are voted for/against in accordance with the UK sanction regimes.	Moderate	Receptive
Credit Risk: RST loans perform badly and multiple significant arrears/defaults arise. Reserve account contribution becomes depleted as it is used to absorb the RST’s losses on loans.	Strategy and Context	The IMF has a robust credit safeguarding framework in place for the RST. Countries with RST programmes must have an IMF Upper Credit Tranche Quality programme already in place to be able to access the RST; emphasising that countries’ commitment to sound governance and economic reform which is necessary to ensure capacity to repay. Any member country taking an RST programme must undergo a rigorous debt sustainability analysis carried out by the IMF analysts. If a country’s debt is judged as unsustainable, they are not eligible to access the RST. Substantial contributions have been made to the RST reserve account.	Moderate	Receptive
Governance Risk- RST programmes are disbursed to borrowing countries where governing authorities misuse funds and do not abide by conditionality prescribed by the IMF, diminishing the efficacy of the programme’s lending.	Policy and Programme Delivery	A pre-requisite for an RST programme is that an IMF Upper Credit Tranche Quality programme is already in place and on track. UCT programmes often come with governance, anti-corruption and anti-money laundering conditionality, which in turn ensures that IMF lending is used responsibly and transparently. IMF Executive Board will regularly monitor IMF RST programmes. Financing is disbursed over several tranches, with the Executive Board able to prohibit disbursement of tranches should the programme not be on track and reform measures not be successfully implemented.	Moderate	Receptive
Investment Strategy Reputational Risk: The IMF changes or doesn’t abide by its investment strategy, contributions to the RST are invested in assets that are not managed in accordance with sound ESG principles. Reputational risk for the Fund, as the custodian of the Trust, and the UK as a shareholder.	Policy and Programme Delivery	UK officials continuously monitor the IMF’s investment strategy at the IMF Executive Board to ensure that investments are conducted in accordance with the IMF’s investment principles and engage with other members at the Board to ensure the investment strategy continues to espouse highly professional standards and strong ESG considerations.	Minor	Receptive
Investment Strategy Risk: The IMF changes or doesn’t abide by its investment strategy, contributions to the RST reserve account are invested in poor-performing assets generate sustained losses over multiple years.	Policy and Programme Delivery	IMF Executive Board continues to scrutinise the investment strategy of the assets of the RST, ensuring that assets are liquid, high-quality and have a strong chance of generating modest returns over a long-term period; as envisioned within the terms of the RST. FCDO, HMT and UK Delegation to the IMF to input into this scrutiny.	Minor	Receptive

The overall risk for the programme is identified as moderate.

* The FCDO risk appetite refers to the risk level that FCDO is willing to operate at for specific risk categories. The FCDO risk appetite levels are presented in a 4-grade scale, labelled as “Minimal”, “Cautious”, “Receptive” and “Eager”. We have translated these FCDO level risk appetites into the same scale used to assess programme level risks for easier comparison. Programme level risks are again evaluated across 4 grades: “Minor”, “Moderate”, “Major” and “Severe”.

FCDO Risk Appetite	Equivalent Programme Level Risk Appetite
Minimal	Minor
Cautious	Moderate
Receptive	Major
Eager	Severe