Programme Completion Review

Title: Core support to UNAIDS 2021-26
Final Programme Spend £ (full life): £16 million	Review Date:	April 2024
Programme Code: 301256	Start Date: Dec 2022	End Date: Mar 2024

Summary of Programme Performance

Year	2024
Programme Score	A
Residual Risk Exposure Rating	Major

DevTracker Link to Business Case (and any addendum):	DevTracker Programme GB-GOV-1-301256 (fcdo.gov.uk)
DevTracker Links to all log frames used during programme lifetime:	DevTracker Programme GB-GOV-1-301256 (fcdo.gov.uk)

[GUIDANCE NOTES:

The Programme Completion Review is more than a final year Annual Review. It is the opportunity to reflect on the entire programme, its performance, achievements, lessons and how learning will be shared to inform future programming.

Text in brackets is included as a prompt, to guide staff completing each section. To reduce page count, this should be deleted before sending for approval. Section lengths are suggested maximums.

The PCR must be published in full on DevTracker (unless it meets transparency exemption criteria), so all text must be suitable for publication. You can use the Delivery Plan, Timeline and Risk Register on AMP (if applicable) to record more sensitive information. Bullets rather than full narrative may make sense for some sections.]

Scoring your programme:

The Programme Completion Review assesses and rates outputs using the following scale. The Aid Management Platform (AMP) and the programme scoring calculator will calculate the overall output score, taking account of the weightings and individual output scores.

Description	Score
Outputs substantially exceeded expectation	A++
Outputs moderately exceeded expectation	A+
Outputs met expectation	A
Outputs moderately did not meet expectation	B
Outputs substantially did not meet expectation	C

Ideally changes should not be made to any targets or indicators less than six months before review, unless agreed with the Head of Department.

In deciding how to score each output in a review, ask yourself: “are the results achieved to date those expected in the results framework, and if not, why not?” Provide sufficient justification of your score in the narrative].

A. Summary and Overview

Description of the programme

The Joint United Nations Programme on HIV/AIDS (UNAIDS) was established in 1996 in response to the global HIV/AIDS epidemic. The Joint Programme comprises the UNAIDS Secretariat (with Global Centres located in Bangkok, Bonn, Geneva, Johannesburg and Nairobi, 5 regional offices and 70 UNAIDS Country Offices) and the 11 UN Co-sponsors: UNHCR, UNICEF, WFP, UNDP, UNFPA, UNODC, UN Women, ILO, UNESCO, WHO and the World Bank. It is governed by the Programme Coordinating Board (PCB) which brings together the Cosponsors, member states and civil society to agree the strategy, budget and results framework for the Joint Programme. The Joint Programme is funded through a blend of core and non-core funding provided directly across the Secretariat and Cosponsors, all of which is managed and monitored by UNAIDS’ “United Budget, Results and Accountability Framework” (UBRAF). UNAIDS’ core budget sits between $187 and $210 million and is comprised primarily of Secretariat running costs, along with core funding allocations to Cosponsors – both to their Headquarters and Country Offices (the latter known as ‘country envelopes’). Cosponsors use these funds to embed HIV-specific resource into their offices and catalyse and leverage alternative funding across their organisations for HIV-related activities.

UNAIDS serves as the primary entity for catalysing and coordinating the global HIV response; it develops evidence-informed global strategies and supports the development of national strategies and interventions including treatment, care and support for those living with HIV/AIDS, as well working to optimise efforts to prevent new HIV infections.

The UK has provided £16 million over two years (£8 million each in 2022 and 2023) to UNAIDS to support its important role in the global response to end the AIDS epidemic by 2030. Funding was ring-fenced to the UNAIDS Secretariat to support its leadership, coordination and strengthening of the global response, and due to reporting at the time of programme inception giving limited sight of results beyond the Secretariat. Given the short length of this programme (15 months) an Annual Review exemption was granted, with only a Project Completion Report required.

Summary supporting narrative for overall score in the review

The past few years have seen some progress on UNAIDS’ core mandate, namely a global reduction in AIDS-related deaths and new infections as well as a record number of people living with HIV (PLHIV) on treatment. The programme has largely delivered on key outputs measured in the log frame, although with some mixed performance, which led to an overall score of A.

However, the choice of outputs and the exclusion of outcome and impact performance from the scoring has led to a score that does not reflect what was in practice a difficult period for UNAIDS, during which a number of fundamental concerns about its performance materialised and were highlighted by both FCDO and other partners to UNAIDS directly and via the Programme Coordinating Board (PCB).

Outcomes and impacts were not met during the programme’s lifecycle, and impact figures were the same between 2022 and 2023 based on current available data for 2023 – a worrying sign of a stalling global HIV response. Whilst UNAIDS cannot take sole attribution for outcomes, alongside this there emerged a number of wider governance concerns. These were particularly highlighted in the conclusions of the August 2023 MOPAN assessment of the Joint Programme, which concluded that there were serious concerns about co-ordination between the Secretariat and Cosponsors, and that the resource mobilisation strategy for the UBRAF has not kept up with the realities of global HIV funding. These concerns were echoed by several stakeholders at the December 2023 PCB. Additionally, MOPAN’s assessment also raised some concerns about UNAIDS approach to Protection from Sexual Exploitation, Abuse and Harassment (PSEAH), an issue that FCDO takes very seriously, and which is regularly discussed with UNAIDS. This has made conducting and scoring the final PCR difficult and has highlighted deficiencies with the current log frame and Theory of Change which are failing to provide adequate assessment of organisational effectiveness and value for money for the FCDO’s investment.

UNAIDS are making efforts to improve delivery and implementing changes which we expect to hear the outcome of in the coming year. Therefore, this PCR provides a valuable opportunity to take stock and learn lessons from the recent history of the Joint Programme’s effectiveness.

Output	Score
Leadership, advocacy and communication	A+
Partnerships, mobilization and innovation	A+
Strategic Information	B
Coordination, convening and country implementation support	B
Governance and mutual accountability	A

Programmatic progress

Achievements

UNAIDS remains the authoritative source of high-quality, disaggregated data on HIV used to inform local, national and regional HIV strategies and donors’ allocations.

UNAIDS Technical Support Mechanism has contributed to the successful submission of 47 Global Fund Grants Cycle 7 funding requests for a total value of US$ 5.9 billion.

UNAIDS has also continued to increase its focus on prevention. The Global HIV Prevention Coalition is catalysing tangible improvements in high-burden and high incidence countries, with new HIV infections in Coalition focus countries declining by 66% since 2010 – a steeper decline than in other countries. The number of focus countries increased from 28 to 38, and Coalition prevention scorecards enhanced granular tracking and accountability for results on HIV prevention

Many stakeholders including PCB Member and Observer States, civil society organisations including the NGO delegation, UNAIDS Co-Sponsors and other key implementing partners such as the Global Fund and PEPFAR - agree that UNAIDS plays an important role in the global response to HIV, especially in its role as a convenor and coordinator, as a source of authoritative data and technical expertise, and as a key driver for strong human rights and evidence-based advocacy work with key populations and marginalised groups. UNAIDS’ support for civil society and community-based organisations’ financing and leadership has been crucial in the context of the broader rollback on rights and civic space. The PCB remains a crucial platform within the UN system for advancing progressive, rights-based language, particularly on Sexual and Reproductive Health and Rights (SRHR). In 2023, UNAIDS was admitted as the only amicus curiae in the legal constitutional challenge to the Anti-Homosexuality Bill in Uganda, building on their reputation as an evidence-based, neutral UN organisation to bring a crucial public health lens and evidence of the impact of the bill on HIV epidemiology to judicial discussions.
[note] ’A “friend of the court,” or someone who is not a party to a case but who provides information or expertise to the court that can help clarify the issues in the case.’ Amicus Curiae - Definition, Examples, Cases, Processes (legaldictionary.net) ’

Due to the nature of the Joint Programme, decisions taken by the UNAIDS PCB require varying levels of follow-up and implementation by the Co-sponsors and have a valuable ripple effect across the UN system. Where needed, UNAIDS has pivoted its country work to respond to critical humanitarian and human-rights based emergencies, including providing humanitarian support and access to HIV-related health services in Ukraine following Russia’s illegal invasion.

Challenges

The world is off track for its 2025 and 2030 targets on HIV, and despite a record number of people on treatment (29.8 million) who are able to live long and healthy lives, there are also a record number (9.2 million) of people living with HIV are not receiving treatment, partly due to the rates of new infections and the disparities in accessing HIV services between countries and demographics. This figure represents 23% of people living with HIV – significantly off track against a target of just under 10% by 2025. The decline in new HIV infections and AIDS-related deaths is slowing and at risk of plateauing. New infections remain high and are increasing in some parts of the world (including Eastern Europe and Central Asia, the Middle East and North Africa, and Latin America), mainly driven by key and vulnerable populations. Gender inequalities, stigma and discrimination against some population groups, such as women, girls, and LGBT+ people, remain major factors that keep on driving the epidemic and the rising anti-rights movement threatens to exacerbate this.

- Under this programme, the outcome of this programme’s Theory of Change by March 2024 was that ‘UNAIDS contributes to sustained global and country level progress in reducing HIV infection rates, increasing access to treatment and addressing discrimination’. Progress has been made at the global level where new infections and deaths continue to fall, although more slowly than planned and not fast enough to meet the ambition to end AIDS as a public health threat by 2030. Progress at the country level is more variable, with rising infections in some regions, in part driven by broader socio-political factors such as the rollback on human rights.
- Over the course of this programme, UNAIDS has faced a range of organisational challenges, including the implementation of a formal ‘realignment process’ during the 2016-21 programme, as well as sustained and increasing financial shortfalls. UNAIDS have faced a shortfall of core funds since 2014, and this has grown to $50 million from its aspirational budget of $210 million in 2023. This has resulted in decisions such as targeted recruitment freezes, reductions in Co-Sponsor and country envelopes, and the closure of the UNAIDS MENA regional office.

In August 2023, a MOPAN assessment of UNAIDS’ fitness for purpose as a multilateral organisation concluded that the organisation was ‘in a worse situation than 2016’ and highlighted several areas for improvement, including on safeguarding, transparency, governance, mutual accountability, Secretariat-Cosponsor relationships, and budget prioritisation against its core mandate. Work on these areas, including clearer articulation of UNAIDS’ unique value add and core mandate and alignment of financial resources to these, should be sustained and increased to prevent a loss of progress and confidence and to ensure sustained programmatic effectiveness. The December 2023 paper ‘Agenda item 4: Follow-up actions to the 2024-2025 Workplan and Budget (UBRAF) | UNAIDS’ sets out UNAIDS response on these issues to the PCB and its plans to prioritise within a budget of USD 160 million.
[note] PCB53_Follow-up_2024-2025_Workplan_Budget_EN.pdf (unaids.org)

The assessment also flagged up questions on the future role of UNAIDS in the current and future phase of the HIV response, with concerns in the near-term about diversion of the Secretariat’s stretched resources away from its core mandate of HIV onto broader agendas within Cosponsors’ own core mandates. This is documented in the MOPAN assessment (2023):
‘Many global partners, donors, and Cosponsors express concern that the Secretariat seems to be expanding the advocacy agenda beyond HIV to include addressing wider inequalities. Many perceive the Secretariat as encroaching on their own roles as it has extended its advocacy and programming into, for example, girls’ education and pandemic preparedness and control.’

Despite increased resource mobilisation efforts, UNAIDS’ financial shortfall is sustained and growing, and a clear, agile approach to prioritisation and sustainability is required. The 2022-26 resource mobilisation strategy acknowledged a funding crisis. And the UBRAF has not been fully funded since 2014. Some Cosponsor and PCB members believe that decisions around resource mobilisation and prioritisation have not always sufficiently involved Co-Sponsors. This has contributed to increased tensions in relationships across the Joint Programme, as well as confusion over the levels of funding and resource assigned by the Secretariat to new activities and their contributions to the Secretariat’s core aims. The MOPAN assessment (2023) sets out that the Cosponsors interviewed argued that an honest and open review of the rebalancing of resource allocations across the Joint Programme is much needed and overdue.

Important lessons continued to be learned around safeguarding against sexual exploitation and abuse and sexual harassment, including the need for robust institutional mechanisms and an organisational culture which embeds preventing and reporting instances of SEAH. While positive progress has been made following the Independent Expert Panel and Management Action Plan in 2019, including the adoption of new organisational policies and development of new reporting mechanisms and awareness campaigns, UNAIDS staff confidence is not as high as hoped based on reports by the MOPAN and the UNAIDS Secretariat Staff Association, and resourcing for the Secretariat’s independent Ethics Office remains constrained. The MOPAN assessment (2023) highlighted these and other remaining gaps.

Major lessons learned, evidence generated and recommendations

The period under review has seen some progress despite some of the challenges. And there have been key lessons that have been learned over the period.

Major Lessons

The UK’s current programming mechanisms has limited its focus to UBRAF results indicators to focus on key programmatic priorities. However, for this review, it has made it more challenging to quantifiably assess progress on the organisational issues highlighted above, which are of heightened importance in the context of an increasingly strained fiscal, political and multilateral space. The Theory of Change in the current programming mechanism also has constraints between the overall achievement of outputs and the outcomes and indicators not being achieved, and attribution between these remains difficult due to the catalytic, technical nature of UNAIDS’ work within a large ecosystem and results chain.

The MOPAN assessment drew attention to concerns from Co-Sponsors regarding transparency of decision making across the PCB, the Cosponsoring Organisations (CCO) and the Secretariat. In its ‘management response to the MOPAN review’, UNAIDS Secretariat stresses its aim to continue to build and maintain Secretariat and Cosponsor relations. The High-Level panel on the sustainability of the HIV response could provide an opportunity to continue discussions on this.

Recommendations
Given the current fiscal context, with pressures on resources available for global health institutions and wider global health architecture reform efforts to harmonise, coordinate and align better, UNAIDS should ensure it clearly articulates - and effectively prioritises against- its core mandate in the global HIV response; UNAIDS should focus on addressing the most critical barriers to progress within its remit. Towards this, UNAIDS should play to its core strengths and its unique added value within the global health system. This includes expertise on multisectoral coordination (particularly civil society and community empowerment), addressing human rights issues, quality data generation/disaggregation, and evidence-based advocacy regarding key populations.

UNAIDS is encouraged to take a more agile and transparent approach to prioritisation across results areas and Secretariat functions, ensuring the core mandate and critical functions where UNAIDS provides unique value add compared to other organisations are protected. This should include efforts to identify ways to synergise activities across Joint Programme members as well as country and regional offices, in order to maximise the value for money of limited resources. The plans to revisit the operating model, alongside planned evaluations, will provide a key opportunity to achieve and embed this in the future Global AIDS Strategy. While financial management decisions sit firmly with the Secretariat, clearer communication around the rationale of said decision-making and any risk assessments conducted as part of this process is warranted with Joint Programme and Board membership.

While UNAIDS has set out its initial response to the MOPAN review, and updated the PCB with plans for a High-Level Panel on the sustainability of the HIV response, UNAIDS is encouraged to address any outstanding actions or recommendations from independent reviews in a timely manner, including the MOPAN review, and to continue to provide routine updates on their progress against established Action Plans in response to these review.
[note] MOPAN Management Response Annex1.pdf (unaids.org)

Further work on preventing sexual exploitation, abuse and harassment (PSEAH) must remain a critical priority; noting HMG's zero-tolerance policy on SEAH, including mishandling or inaction, UNAIDS is encouraged to further reform their mechanisms and increase transparency on PSEAH actions and improvements. Increased resource for the Ethics Office and sustained momentum for PSEAH activities is recommended, along with a potential revisiting of the MOU between WHO’s Office for Internal Oversight Services and UNAIDS’ Ethics Office, to ensure cases are investigated fully and follow-up actions are comprehensive.

A critical recommendation moving forwards is the need for a stocktake and potential reassessment of the role of the Co-Sponsors as part of the Joint Programme. The most prevalent opportunity for this is the High-Level Panel on the sustainability of the HIV response and a resilient and fit-for-purpose UNAIDS Joint Programme, a process due to be completed by June 2025. As part of this wide-reaching process, this High-Level Panel should provide an opportunity to further unpack any issues around resetting the relationship between the Secretariat and Co-Sponsors and agreeing processes for Co-sponsors to be more involved in decision-making as appropriate on key issues in the Joint Programme going forward. The outcomes of this process should be embedded into future decision making and planning for the Joint Programme, including the future Global AIDS Strategy and accompanying UBRAF, as well as UNAIDS’ vision to 2030 and beyond.

For any future FCDO programming with UNAIDS, we recommend having fewer UBRAF results indicators overall, and introducing more indicators around organisational sustainability and reform based on the issues highlighted above; management of the financial shortfall, sustainability planning, safeguarding, and efforts to improve the Secretariat’s relationship with Co-Sponsors. An increased focus on the demonstration of UNAIDS’ unique value-add, organisational efficiency and sustainability in a new Theory of Change with clear outputs to measure these will also hedge the high level of complexity in monitoring the whole Joint Programme ecosystem and ensure UNAIDS’ role and contributions to outcomes are more clearly elaborated. Finally, to reflect continuing improvements in UBRAF budgetary and results reporting to date, and to support UNAIDS in making the most effective decisions on resource allocation as possible against its financial shortfall, we recommend that future financing does not need to be ringfenced to the Secretariat.

## B: Theory of Change and Outcome Assessment

	Starting point	Final result
Budget	£16m over two years; £8m p/a	£16m over two years; £8m p/a
Timeframe	15 months; December 2022-March 2024	15 months; December 2022-March 2024
Outcomes	UNAIDS contributes to sustained global and country level progress in reducing HIV infection rates, increasing access to treatment and addressing discrimination.	B: Moderately did not meet expectations / At the global level new infections and deaths continue to fall, albeit considerably more slowly than planned. Progress at country level is more variable, with rising infections in some regions.

Overall assessment of programme outcomes and VfM

Impact Indicators	Baseline (2021)	Final Log frame Target (2023)	Final Result Achieved (2023)
Indicator 1: Estimated number of new infections total & among young women aged 15-24 (SDG, Global AIDS Monitoring (GAM)	1.4 million (total) / 230,000 (AGYW)	1 million / 160,000	1.3 million / 210,000
Indicator 2: Estimated annual number of AIDS-related deaths (GAM). Disaggregated by age and sex	660,000 (total) / 320,000 (men) / 240,000 (women) / 91,000 (children)	500,000 / 250,000 / 190,000 / 68,000	630,000 / 310,000 / 230,000 / 84,000

Outcome Indicators	Baseline (2021)	Final Log frame Target (2023)	Final Result Achieved (2023)
Indicator 1: Percentage of people living with HIV who know their status (GAM). Disaggregated by age and sex	84 (total) / 81 (men) / 88 (women) / 60 (children)	89 / 87 / 92 / 74	86 / 83 / 91 / 66
Indicator 2: Percentage of people living with HIV receiving antiretroviral (GAM) therapy. Disaggregated by age and sex	73 (total) / 68 (men) / 78 (women) / 55 (children)	81 / 78 / 85 / 68	77 / 72 / 83 / 57
Indicator 3: Percentage of people living with HIV with suppressed viral load. Disaggregated by age and sex	67 (total) / 63 (men) / 72 (women) / 43 (children)	76 / 73 / 79 / 59	72 / 67 / 78 / 48

UNAIDS supports countries and communities to make progress in the fight against HIV and AIDS. They do not themselves provide services at scale. It is therefore difficult to attribute progress (or the lack of it) to the programme alone. However given the role of UNAIDS overall, it is plausible to suggest that the programme has contributed to global progress.

While the impact and outcome indicators are all heading in the right direction across all groups, none of the milestones were achieved, and none are on track at current trajectories to achieve 2025 or 2030 global targets. Therefore, impacts and outcomes are ranked as ‘moderately did not meet expectations’. Likewise, progress is inconsistent between regions and countries. The most significant gains in absolute numbers and percentages on reducing new infections and deaths have been made in sub-Saharan Africa, due to their high burden share (20.8m of the estimated 39m living with HIV are located in this region). However, progress in regions such as Latin America, Middle East and North Africa, and Eastern Europe and Central Asia is beginning to reverse, with increases in new infections in all areas since 2010 and an increase in deaths in EECA in the same period.

Value for Money

Although the targets at impact and outcome levels were not met, there was progress across all areas at the global level. Overall, we judge that FCDO’s investment of £16 million over 2 years in UNAIDS has contributed to this and is good value. For example, UNAIDS’ support for National Strategic Plans on HIV and on scaling up combination prevention, as measured by the outputs, directly contribute to improving the quality and scale of HIV services in country, thereby improving access to Antiretroviral therapy (ARTs) and Pre-exposure prophylaxis (PREP). Technical support around improving epidemiology data allows implementing partners to better understand the nature of their HIV epidemics in local contexts, and therefore tailor their interventions to improve accessibility of services. UNAIDS also delivers vital work to support countries removing punitive laws removes barriers to key populations accessing HIV services, especially LGBT+ people and AGYW. These all contribute to a reduction in new infections and AIDS-related deaths. The focus on equity in the programme is particularly notable and is the framing of the whole End Inequalities. End AIDS. Global AIDS Strategy 2021–2026 (Global Aids Strategy 2021-26).

The Joint Programme disburses about a third of its expenditure to the 11 Co-sponsors; a drawback in the UBRAF reporting is the lack of a breakdown of information and details on results delivered by the Co-sponsors that is clearly linked to their budgets and their ‘leveraging’ of UNAIDS funds. This makes it difficult to cleanly distil the value for money on HMG’s investment. However, looking at some of the direct outputs and corresponding indicators described in the log frame, it is reasonable to conclude that the programme has contributed and a ‘good value’ for our investment.

In addition, the programme’s business case and its support for the Global AIDS Strategy 2021-26, was designed and delivered in an equitable fashion. One of the key strengths of the programme is it focus on key populations and other disadvantaged groups and channelling efforts and resources to populations and areas with the most needs. This equitable approach is demonstrated for example in the focus and emphasis over the period under review on differentiated and targeted services, the Global Prevention Coalition and the Fast-Track Cities, which were all initiatives and interventions with the aim to address ‘left behind’ groups and rightly putting resources in areas of the most need.

Within the outcome indicators 1, 2 and 3, the focus on women in addressing their particular disadvantages and vulnerabilities resulted in better outcomes compared to the men, and it is important to understand and therefore address the factors that are keeping men behind in the next period.

Summarise the programme’s theory of change and results framework, including any changes to outcome indicators.

The ToC is based on the logic that the provision of resources to UNAIDS (ringfenced to the Secretariat) will support its activities and ensure a coordinated strategic focus, effective functioning and accountability across the Joint Programme’s work. Secretariat-focused funding is designed to complement the activities of the cosponsors and therefore bring about the key shifts to accelerate progress on the HIV response. The realisation of the outputs and outcomes in the UBRAF in turn will contribute to delivery of the Global AIDS Strategy 2021-26 and the 2021 UN General Assembly Political Declaration on HIV and AIDS, to realise the 2025 targets towards the SDG 2030 goal to end AIDS as a public health threat. The ToC for the programme sits within the overall TOC and results chain for the UBRAF 2022-2026 and its contribution to the Global AIDS Strategy 2021-2016.

The design of the log frame continues the use of high-level impact and outcome indicators in line with our previous programming to continue tracking the overall progress of the global HIV response. Outputs focus on each of the 5 Secretariat Functions: Leadership, advocacy and communication; Partnerships, mobilization and innovation; Strategic information; Coordination, convening and country implementation support; and Governance and mutual accountability (including evaluation). Output indicators were selected from the UBRAF’s 10 Strategy Results Areas as well as the 5 Secretariat Functions to draw clearer links in our programme assessments of the Secretariat’s contribution to the Joint Programme outputs and operating model.

While attribution is difficult due to the operational model of the Joint Programme, these outputs achievements are judged to have fed into the positive trajectory of outcome results and contribution at the impact level. However, given the disconnect between outputs being achieved overall and outcomes and impacts missing their targets, attribution within the Theory of Change could be improved in future FCDO programming through exploring the development of outputs around organisational governance and sustainability. In a new programme, these supplements will highlight how the Joint Programme ecosystem and operating model is leveraged to drive cross-UN and cross-multilateral action, and to translate outputs into sustained outcomes through clear organisational mechanisms. Therefore, while the overall logic and steps described in the ToC are judged to be sound based on the outcome and output results described and achieved in the logical framework of the programme, further elaboration as described above would bolster a future ToC.

As with the previous programme, future UBRAF design and reporting, including strengthened robust agreements with the Co-Sponsors, should facilitate better-aligned objectives, clearer division of labour, and a stronger link between resource allocation and results. The next period of HMG’s programme with UNAIDS should consider this as a priority and engage the Secretariat and fellow Board members level to see this accomplished.
## C: Detailed Output Assessment

Output Number 1	Leadership, advocacy and communication:
Output Score	A+
Impact weighting (%)	20		Impact weighting revised since last AR?	N/A

Output Indicators		Starting Target	Final Log frame Target	Final Result Achieved
Output Indicator 1.1- Indicator S1.1.2. Number of countries where the Joint Programme operates, that are supported to review, assess and/or update the countries’ National Strategic Plan on HIV (or equivalent plans or frameworks)		37 countries where the Joint Programme operates, received support to review, assess and/or update the country’s NSP on HIV (or equivalent plans or frameworks) / (based on 37 reports from the Joint UN Teams on HIV and AIDS at country, Source: 2022 UBRAF Indicator Data Collection Survey).	40 countries per year where the Joint Programme operates, receive support to review, assess and/or update the country’s NSP on HIV (or equivalent plans or frameworks) by 2023.	Exceeded: In 2023, 81 countries, where the Joint Programme operated, were supported to review, assess and/or update their NSPs on HIV (or equivalent plans or frameworks).
Output Indicator 1.2 - Indicator S1.2.1. Number of countries that have received Secretariat support for meaningful engagement between people living with HIV, key populations, affected women and girls and young people etc. and government institutions for information sharing and decision making on HIV priorities.		In 2020-2021, the Secretariat operated in at least 91 countries. (Indicative baseline)	At least 90% of countries where the Secretariat operates, report having / advocated for and supported meaningful engagement between networks of people living with HIV, key populations, affected women and girls, and young people, and government institutions and other stakeholders as relevant in the country HIV epidemic context, in information-sharing and decision-making.	Exceeded: In 2023, 84 of 84 countries where the Secretariat operated (100%), received support for meaningful engagement between people living with HIV, key populations, affected women and girls and young people and government institutions for information-sharing and decision-making on HIV priorities.
Output Indicator 1.3 - 5.1.1. Number of countries supported by the Joint Programme in activities to remove or amend punitive and discriminatory laws and policies, and/or develop protective ones affecting the HIV response		28 countries were supported by the Joint Programme to remove punitive and discriminatory laws and policies and/or develop protective laws and policies affecting the HIV response in 2021.	At least 30 countries supported in activities to remove or amend punitive and discriminatory laws and policies and/or develop protective laws and policies affecting the HIV response.	Exceeded: In 2023, 69 countries were supported by the Joint Programme to amend or remove punitive and discriminatory laws and policies and/or to develop protective ones.
[note] All starting targets are 2021, unless stated.
[note] All final targets are 2023, unless stated.

Overall, output and corresponding indicators have been met and, in some instances, exceeded. An important value-add of UNAIDS is in its expertise to partner with and engage the relevant stakeholders, mobilise resources and coordinate partners at both global and country level geared towards the delivery of the Global AIDS Strategy 2016-21.

Output Indicator 1.1: The total number of countries (81) supported significantly surpassed the target milestone, and the range of support included new NSP development, modelling impact, monitoring and evaluation, costing, and mid-term reviews. This included support in over 30 countries for dedicated multidisciplinary technical expertise and peer review support.

Output Indicator 1.2: Exceeded. In 2023, those networks of populations include in almost all those countries people living with HIV (83 countries), as well as key populations (83 countries). Young people at risk of and affected by HIV were supported in 69 countries respectively; women and girls at risk of and affected by HIV in 67 countries; and people living with disabilities in 27 countries. Other groups were mentioned to be refugees, migrants, as well as people living in closed settings or indigenous people.

In 2023, most of the support was in the form of advocacy support (80 countries) and convening of stakeholders and/or facilitating dialogues (72 countries). Other support included organizing consultations or capacity building workshops or activities (68 countries) or financial support (58 countries). Such direct, in-country support was complemented by support to strengthen the meaningful engagement of community networks at global and regional levels.

Output Indicator 1.3: The Joint Programme supported the removal of the following laws and policies: criminalization of exposure and/or transmission to HIV and nondisclosure of HIV status (31 countries); criminalization of an aspect of sex work (20 countries); policies relating to the age of consent for health services (24 countries); criminalization of same-sex sexual activity (17 countries); criminalization of drug use (20 countries); criminal laws targeting trans-and other gender diverse persons (12 countries); and travel restrictions for people living with HIV (in 9 countries).

The types of support provided included: technical assistance (56 countries); advocacy and communications (57 countries); policy guidance (46 countries); capacity building (45 countries); strategic information generation and use (41 countries); financial support (28 countries); and sharing of good practices and facilitating cross-country cooperation (34 countries).

Lessons learned through this output, and recommendations for future programming

An important lesson of this output is that UNAIDS’ leadership remains crucial for the creation and development of enabling social, political and legal environments, and serves as one of UNAIDS’ strongest unique value adds within its core mandate, particularly in the face of the rising anti-rights movement. The variety of types of support provided by UNAIDS is a testament to their respected role as a technical, neutral political UN agency providing evidence-based public health lens to debates around human rights and SRHR. Additionally, technical support for countries’ own NSPs has effectively promoted a multi-sectoral approach in various country contexts. Continuing a focus on the importance of UNAIDS contributions to protecting human rights, particularly for positive HIV and health outcomes, is recommended for future programming.

Output Number 2	SF2: Partnerships, mobilization and innovation
Output Score	A+
Impact weighting (%)	20		Impact weighting revised since last AR?	No

Output Indicators		Starting Target	Final Log frame Target	Final Result Achieved
Output Indicator 2.1- Indicator S2.1.1. Number of countries in sub-Saharan Africa that join the Education Plus initiative and have an implementation plan		Five countries joined the Education Plus Initiative by the end of 2021.	At least 5 countries that joined Education Plus are implementing operational plans by end 2023.	Exceeded: By end 2023, the Education Plus initiative included 15 countries, including 2 new members in 2023 and 8 new members in 2022. 10 countries had an implementation plan in 2023.
Output Indicator 2.2- Indicator S2.1.3 Number of countries that join the Global Partnership for Action to Eliminate All Forms of HIV-Related Stigma and Discrimination (Global Partnership) and implement operational plans		By end 2021, 29 countries joined the Global Partnership for Action to Eliminate All Forms of HIV-Related Stigma and Discrimination (Global / Partnership) and implement operational plans	5 additional countries join the Global Partnership for Action to Eliminate All Forms of HIV-Related Stigma and / Discrimination and 16 countries have operational plans being implemented.	Reached: By end 2023, 20 countries have developed and are implementing costed action plans, while 4 are finalising their plans. The action plans are being operationalised with key interventions also integrated into Global Fund funding proposals and PEPFAR operational plans.
Output Indicator 2.3 - Indicator 1.2.1. Number of countries where the Joint Programme provided technical and/or implementation support to scale up combination HIV prevention programmes		36 out of 37 countries received technical and/or implementation for interventions or provide support to address barriers to implementation of HIV prevention programmes for key and other priority in 2021. / 28 focus countries joined the Global Prevention Coalition by end-2021.	30 countries supported by the Joint Programme adopt targets and key actions spelled out in the Global 2025 HIV Prevention Roadmap. 40 countries receive Joint Programme’s technical and/or implementation support to scale up combination HIV prevention programmes by 2023.	Exceeded: In 83 countries, the Joint Programme provided specific technical or implementation support to scale up combination HIV prevention programmes.

Overall, output 2 exceeded expectations.

Output Indicator 2.1: In 2023, the initiative supported 16 policy changes and 33 programmatic initiatives in 10 countries, including on SRHR, CSE and HIV in 4 countries, addressing various aspects of school-related gender-based violence in 3 countries. Meaningful engagement of adolescent girls and young women (AGYW) as well as young people in championing the initiative and participating in implementation as rights’ bearers took place in 9 countries, engaging over 240,000 young people, including AGYW. Advocacy campaigns on the Initiative’s multi-sectoral package and key “asks” through digital platforms, community radio and other media platforms in 2 countries reached a total of over 18.5 million people. Through the initiative, 9 countries developed Education Plus Investment Cases, further strengthened through a knowledge sharing workshop held in 2023, help build evidence and support resource mobilization.

Output Indicator 2.2: 5 countries joined the Partnership in 2023 and 6 in 2022, adding to the 28 members in 2021. They included Spain and Luxembourg, the first European Union countries to join. 20 countries have developed and are implementing costed action plans, while 4 are finalizing their plans. These are being operationalized with key interventions integrated into Global Fund funding proposals and PEPFAR operational plans.

Output Indicator 2.3: The technical and implementation support provided by UNAIDS on this indicator included support provided to community-based organizations for the promotion of access to or delivery of HIV prevention or testing services, development of standard operating procedures, mapping of prevention services and gaps, capacity building to better organize services delivery or their access for key populations or piloting of innovative prevention services.

This support was aimed at scaling up HIV prevention for the following population groups: gay men and other men who have sex with men (in 77 countries); sex workers (75 countries); adolescent girls and young women (68 countries); adolescent boys and young men (64 countries); transgender people (55 countries); people in prisons and other closed settings (58 countries); and people who inject drugs (48 countries).

Lessons learned through this output, and recommendations for future programming

Given the intersecting health, educational, and economic needs and vulnerabilities experienced by key and vulnerable populations at the heart of the HIV epidemic, a multi-sectoral approach is critical to sustaining and advancing the gains made on HIV to date. In order to achieve this integration effectively, partnerships with implementing countries and partners are key. UNAIDS is effective at convening these partners around issues and providing the technical support and guidance needed to effectively implement interventions which address these intersecting needs through an HIV lens.

Regarding global strategic initiatives such as those in indicators 2.1 and 2.2, further work could be done to further articulate and promote the impact of these initiatives in translating political will and convening into ground-level action. Given the catalytic nature of these initiatives, the Secretariat should also provide clearer narrative and reporting on how these initiatives are funded and resourced and contributing to the core UBRAF objectives, given the broader context of constrained fiscal and human resources in the organisation.

Output Number 3	SF3: Strategic Information
Output Score	B
Impact weighting (%)	20		Impact weighting revised since last AR?	No

Output Indicators		Starting Target	Final Log frame Target	Final Result Achieved
Output Indicator 3.1- Indicator S3.2.1 Number of countries supported by the Secretariat to provide quality and timely reporting against new GAM indicators and to complete the HIV estimates process		in 2021, the Secretariat supported 140 countries for developing HIV estimates (source: PMR 2020-2021). / Community-led monitoring supported in 10 countries (indicative reference).	150 countries supported for developing HIV estimates. / Community-led monitoring supported in 15 countries.	Moderately did not meet expectations: / The UNAIDS Secretariat, with support from its partners, provided direct support to 139 countries in 2022 and 124 countries in 2023 to develop their national HIV estimates. / In 74 countries, the Joint Programme provided support towards community-led monitoring (see indicator 4.1.1).
Output Indicator 3.2 - Indicator S3.3.1. Global AIDS Update reports, other flagship reports and annual updates to AIDSinfo produced and disseminated, highlighting progress and inequality gaps, and giving examples of data use by countries, communities and partners to improve programmes		Global AIDS Update reports and annual updates to AIDSinfo produced.	Global AIDS Update reports and annual updates to AIDSinfo produced.	Reached: annual updates to AIDSinfo being completed and UNAIDS’ annual Global AIDS Update, ‘The Path to End AIDS’, being published in July 2023

Output Indicator 3.1: This indicator was partially met regarding GAM reporting, with 124 supported further to develop their national HIV estimates in 2023. This is mainly because several countries, having been supported by UNAIDS previously, no longer need such support to produce HIV estimates while focus has shifted to more support to community-led monitoring for which needs are growing. However, this serves as a testament to UNAIDS’ unique value add on strategic information and their work on effective capacity building in country: HIV estimates were produced in 172 countries in 2022 and 174 countries in 2023, representing 99% of the world’s population.

However, work on community led monitoring exceeded expectations here. Among the 74 countries supported by UNAIDS on community-led monitoring, the Secretariat strengthened community-led monitoring in over 35 countries. This dedicated technical support included areas such as planning, data-collection, programme management and data-related queries, as well as coordination, tracking progress and problem-solving, all done with communities.

Output Indicator 3.2: This indictor was met, with annual updates to AIDSinfo being completed and UNAIDS’ annual Global AIDS Update, ‘The Path to End AIDS’, being published in July 2023. Comprehensive data books and analyses were also published and made available through the UNAIDS AIDSinfo platform. The sections of the platform include: Epidemic and Response, Inequalities, the Key Populations Atlas, the HIV Financial Dashboard, and Laws and Policies Analytics. These have been used widely globally, regionally and in countries for resource mobilization and advocacy, as well as for setting targets and monitoring progress.

Lessons learned through this output, and recommendations for future programming

Despite the output score of B, strategic information and data shines through as a clear strength of the Secretariat and a unique area of value add, with UNAIDS widely recognised as an authoritative data source and its data widely used by programme implementers and policy advocates alike. The Secretariat is urged to protect resourcing for this function and leverage their data capacity as part of its unique value add.

Output Number 4	SF4 Coordination, convening and country implementation support
Output Score	B
Impact weighting (%)	20		Impact weighting revised since last AR?	No

Output Indicators		Starting Target	Final Log frame Target	Final Result Achieved
Output Indicator 4.1- Indicator S4.1.2. Number of country-level UN Joint Teams on HIV and AIDS implementing a Joint UN Plan on HIV to support national HIV response as a part of and contributing to the UN Sustainable Development Cooperation Frameworks (UNSDCF) or equivalent.		91 country level UN Joint Teams on AIDS implement a Joint UN Plan on HIV to support national HIV response as a part of and contributing to the UNSDCF or equivalent (at start of 2022-2023 planning cycle).	At least 85 country level UN Joint Teams on AIDS implement a Joint UN Plan on HIV to support national HIV response as a part of and contributing to the UNSDCF or equivalent.	Reached: In 86 countries in 2023, UN Joint Teams on AIDS, led by the Secretariat with Cosponsors at the country level, developed and implemented a Joint UN Plan on HIV that effectively supports the national HIV response in a well-coordinated manner and as part of and contributing to the UNSDCF.
Output Indicator 4.2 - Indicator S4.2.1. Number of countries where Joint Programme support is provided to promote and apply an inequalities lens to the HIV response, including through a new HIV inequalities framework and toolkit and other available tools.		Baseline not available as this is a new area of work, including a new framework to be developed according to the 2021-2025 Global AIDS Strategy, and data prior to 2022 relating to this indicator are not available.	Normative guide to addressing Inequalities for ending AIDS (Framework and Toolkit on HIV / related inequalities) developed and / disseminated. / HIV-related Inequalities framework and toolkit piloted in 12 countries with lessons from gender assessments and Stigma Index which inform the refinement of the documents and are incorporated in the roll-out.	Moderately did not meet expectations: Framework and toolkit developed and piloted in 5 countries in 2022, which could not be expanded due to funding constraints. However, lessons learned from the pilot were incorporated into the refined framework and toolkit, which is available in 4 languages and mainstreamed for use in all countries. / Learning from the development of the framework and toolkit also led to the further development of the HIV/AIDS Inequality Visualization Platform on AIDSinfo as a key source of strategic information supporting framework and toolkit users.
4.3- 8.2.1 Number of countries having conducted studies to improve allocative efficiency, address implementation bottlenecks, or other analytical exercises to improve resource use efficiency, multi-sectorial financing, impact and equity; and/or with recent HIV Investment cases (in the past three years) that are being used		As per the 2022 UBRAF Indicator Data Collection Survey), 37 countries were supported to conduct studies to improve allocative efficiency, address implementation bottlenecks, or other analytical exercises to improve resource use efficiency, multi-sectorial financing, impact and equity; and/or reported using	45 countries supported by the Joint Programme to improve allocative efficiency, address implementation bottlenecks, or other analytical exercises to improve resource use efficiency, multisectoral financing, impact and equity and/or recent HIV Investment cases	Reached: In 2023, 49 countries were supported by the Joint Programme to conduct / develop studies to improve allocative efficiency (18 countries); address implementation bottlenecks (24 countries); or recent HIV investment cases (last 3 years) that are currently being used (24 countries).
4.4- 4.1.1. Number of countries where the Joint Programme provides technical support for community-led HIV responses		Baseline does not exist as though the Joint Programme has provided supported to community-led organization since its inception, the community-led response result area is new in terms of its more advanced framing and for more systematic monitoring.	At least 2 normative guidance documents developed and promoted, with focus on network strengthening, enhancing GIPA, community-led research and monitoring, community-led advocacy, or community-led service delivery by 2023.	Reached: Further to the approved definitions of community-led HIV responses and community-led organization, the following guidance was developed and promoted by 2023: / - a community-led monitoring (CLM) Progression Matrix to support the development of minimum standards and progress tracking for community-led monitoring of HIV services / - a draft guideline document on resource tracking for community-led responses informed by a pilot in 6 countries

The output and corresponding indicators have been met across all but one of the milestones. An ‘B’ rating for this output is justified as indicator 4.2 was not being fully met. All other indicators were met despite the pilot being smaller than planned, and the remaining substantive pieces of work in this indicator were still able to proceed, with products being refined and launched in 2023 alongside a supplemental AIDSinfo platform.

Output Indicator 4.1: This indicator was achieved. The slight decrease in 2023 is due to the impact of the UBRAF funding shortfall results which led to reduced presence in selected countries (closed country or multicounty offices).

Output Indicator 4.2: Although the pilot size had to be reduced, meaning the milestone was not fully met, this has not hindered the launch, refinement and roll-out of the Framework, Toolkit and other inequalities data tools from being mainstreamed into country and community work. Developed following the launch of the toolkit and a part of UNAIDS AIDSinfo platform, the HIV/AIDS Inequality Visualization Platform brings key data on HIV related inequalities such as on differentiate impact of HIV between populations groups arising from the social conditions in which people are born, grow, live, work and age to inform programmes, investments and research.

Output Indicator 4.3: This indicator was achieved.

Output Indicator 4.4: This indicator was achieved. Other technical fora supported included a meeting of CLM Technical Assistance Providers and support for the Global Fund-led global CLM convening with implementers, donors, technical agencies and others to consolidate learnings and prioritize strategic investments. In 86 countries, the Joint Programme also provided technical support to community-led organizations in the HIV responses. Among them, in 74 countries it provided support to 3 or more affected communities through community-led organizations.

Lessons learned through this output, and recommendations for future programming

UNAIDS demonstrated positive lesson-learning to respond to restrictions around the Inequalities Toolkit pilot size to maximise learning from a smaller sample size and reframe the final products to allow for effective mainstreaming of principles, particularly through the well-established AIDSinfo platform. The Secretariat may find lessons here in responding to their shortfall of core funding by synergising activities, reducing scales where the quality of evidence generated would not be significantly impacted, or utilising existing mechanisms or channels for rolling out new knowledge.

While the decrease in Joint UN Teams at country level was limited, it is important that these remain protected and continue to be established. Where UNAIDS Secretariat footprint has had to shift due to fiscal pressures, the Secretariat should consider working with Co-Sponsor offices in-country or the UN Resident Coordinator’s office to ensure joint cross-UN working is continued with the support of a Secretariat regional or global office.

Output Number 5	SF5 Governance and mutual accountability
Output Score	A
Impact weighting (%)	20		Impact weighting revised since last AR?	No

Output Indicators		Starting Target	Final Log frame Target	Final Result Achieved
Output Indicator 5.1- Indicator S5.3.1 Mandatory UNAIDS reporting relating to Quadrennial Comprehensive Policy Report (QCPR), UN Funding Compact and UN System-Wide Action Plan on gender equality and women empowerment, completed indicating progress towards compliance with recommendations and integration with UN system-wide tools		2021 UN SWAP report / 2021: QCPR and Funding Compact report	Annual QCPR, UN Funding Compact and UN / SWAP report completed	Reached: In 2022 and 2023, UNAIDS Secretariat submitted UN System-wide reports including QCPR, Funding Compact and SWAP reports, that showed a very high commitment and compliance with the SDG and UN Reform priorities, recommendations, and requirements, as well as integration with UN System-wide tools.
Output Indicator 5.2 - Indicator S5.4.1. Percentage of UNAIDS evaluations as per the PCB approved Evaluation Plan, implemented and tracking of the follow-up on related recommendations		2022-2023 evaluation plan approved by the December 2021 PCB. Annual report on 2021 evaluations	At least 80% of the evaluations (as per the evaluation plan for 2022-2023) implemented. / Follow up on recommendations from evaluations in 2021 and 2022 tracked. / Evaluation plan for 2024-2025 approved by the PCB	Reached: In 2022-2023, five comprehensive global Joint Programme evaluations were completed and externally assessed. / The implementation of evaluation recommendations was tracked and five meetings of the UNAIDS Expert Advisory Committee on evaluation were held with express focus on the evaluation function. / The evaluation plan for 2024-2025 was presented and approved by the PCB in December 2023.

Output 5.1: This indicator was achieved. Reports covered by this indicator included submission of annual survey for the UN QCPR (2021, 2022 and 2023), as well as progress reports against the QCPR, and the UN Funding Compact commitments to the PCB (conference room papers, 2021, 2022 and 2023). In 2023, this also included UNAIDS Secretariat report on the UN Checklist on oversight of the implementation of the repositioning of the United Nations development system. The UNAIDS Secretariat's 2022 and 2023 reports on UN SWAP 2.0 shows compliance with and ranking against the UN's ambitious targets for gender equality and women’s empowerment.

Output 5.2: This output was achieved. The Evaluation Office was commended for promoting accountability and evidence-based decision-making and for strengthening the evaluation culture and noted that evaluations were vital for demonstrating the impact of the Joint Programme's work and showing how resources and capacities could be used optimally. The MOPAN assessment (2023) of UNAIDS reaffirmed the important work of the Evaluation Office, but also found that feedback loops were lacking, meaning that opportunities for enable lesson-learning from the Evaluation Office’s work across the Joint Programme and in the design of new interventions may be being missed.

Lessons learned through this output, and recommendations for future programming

In the Secretariat’s role of coordinating and distributing evidenced-based technical guidance, more should be done to embed lessons from evaluations into the design or implementation of new interventions. This could include more explicit or formal mechanisms for tracking the implementation of evaluation recommendations (particularly where evaluations review UNAIDS’ organisational or structural mechanisms), and/or for tracking of the incorporation of evaluation recommendations into technical guidance or products.

It is also worth noting that, while the two indicators selected for assessment within this programme were achieved, the MOPAN assessment rated performance against this Secretariat Function as unsatisfactory, with only 2 of 9 relevant micro-indicators in the assessment being achieved, and noting the tensions raised previously regarding clarity of roles and comparative advantages of UN Agencies for activities, alignment of resources to protect key functions, and transparency on financial and resource decision-making. A new programme should take this context into account during its design.
D: Value for Money

VfM performance compared to the original VfM proposition in the business case

UNAIDS’s budget is allocated across the Secretariat (75%) (mainly for staff costs) and the Co-Sponsors (25%). While the UK’s funding to UNAIDS is ring-fenced to the Secretariat, Value for Money of UNAIDS depends on the performance of both the Secretariat and the Co-Sponsors, on the division of labour and interaction between them, and on their engagement with wider global partnerships including governments, civil society, multilateral agencies such as the Global Fund to Fight AIDS, TB and malaria and bilateral agencies such as PEPFAR. This fact underpins the recommendation to remove the ring-fencing of UK core contributions to the Secretariat.

Economy

The Secretariat has worked to maintain a focus on economy through the implementation of the realignment process, following its completion, as well as launching a new Resource Mobilisation Strategy and continuing work on prioritisation of core funding to offset its shortfall. The implementation of the realignment process is still in its early stages, so it is difficult to fully assess its impact at this stage, and the upcoming evaluations and revisiting of the Joint Programme’s operating model in 2025 will be a key point to take stock and learn lessons. Designed with cost-effectiveness in mind, the realignment process has gone some way to addressing the shortfall of core funding, but the gap has continued to widen further.

UNAIDS’ Resource Mobilisation strategy has focused on broadening and diversifying the donor base, including through outreach to new donors and private philanthropists, calls for existing donors to increase contributions, efforts to scale up domestic co-financing initiatives, and develop bespoke programmes for non-core donor funding and Global Strategic Initiatives. $16 million of the reserve budget was used in 2022 to supplement gaps between revenue and expenditure, and the reserve threshold is due to be revisited by the Secretariat soon; in 2023, a plan was presented to the PCB summarising the decisions taken to limit expenditure to projected revenue levels, utilising a ‘salami-slice’ model aligned to the UBRAF results areas and functions. The increase in non-core funding is consistent with trends across the UN system; however, caution is advised when designing bespoke projects or initiatives for additional and non-core funds. It is critical to ensure that the Secretariat adheres to its core mandate and that there is relevant participation of the whole Joint Programme ecosystem, including Cosponsors, in bespoke initiatives. This is an important consideration given the tensions across the Joint Programme Ecosystem around mandates and resource division as highlighted in the MOPAN assessment. Despite these efforts, a significant financial shortfall remains, and prioritisation is necessary to ensure maximum impact.

Prioritisation against this funding shortfall has been largely equal across the Strategy Results Areas and Secretariat Functions. However, tensions across the Joint Programme ecosystem have emerged due to the larger percentage of cuts to core Cosponsor funds and country envelopes and the perceived lack of transparency of decision making for Cosponsors and other partners as highlighted in the MOPAN assessment. Key recommendations of this report for the Secretariat include taking a more agile and focused approach to prioritisation over a ‘salami-slicing’ approach, increasing transparency with PCB members and collaboration with Co-sponsors on decision-making regarding resource allocations. The upcoming High-Level Panel represents a prime opportunity to address these issues.

Efficiency

Despite the negative impact of the increasing number of intersecting ‘polycrises’ and global fiscal context on the HIV response as well as UNAIDS’ budget and resources, the Secretariat were able to implement mitigation and adaptation strategies which minimised their impact. This was primarily through various efficiencies as part of its realignment and prioritisation processes and positive working relationships with its implementing partners, ensuring that UNAIDS was able achieve most of the outputs in the log frame as noted in Section C.

However, the increasingly strained political and fiscal context heightens the need for greater efficiency and sustainability planning at organisational level, especially where the Secretariat’s geographical footprint has reduced. This is crucial in the context of wider global health reform agendas, where the role, size and scope of UNAIDS- as with all global health multilateral institutions- has come under scrutiny; ensuring workstreams are streamlined and sustainable in the face of any changes UNAIDS may undergo in the global health reform process will be key. Several upcoming processes will provide opportunities to take stock for further efficiency across the Joint Programme through organisational and governance reform, particularly regarding the relationships between the Secretariat and the Co-sponsors, as well as synergising activities at country levels through HIV-competent Co-Sponsor and UNRC Office staff in country. These processes include multiple evaluations in the 2024-5 evaluation plan, the revisiting of the operating model in June 2025, and the development of UNAIDS’ strategies to 2030 and beyond. The current FCDO programme does not monitor these types of processes, and a key recommendation of this report will be to incorporate indicators around these processes’ outcomes into a future log frame.
Effectiveness

Despite some milestones not being met during this programme’s lifecycle, other milestones were exceeded, and the contribution of UNAIDS’ interventions towards the positive trends across all outcomes and goals, particularly for key populations, is clearly demonstrated through the targeted indicators for key population-specific work and the inequalities lens of the 2021-6 Global AIDS Strategy. Therefore, it is reasonable to conclude that the Secretariat and Co-sponsors’ contribution has been effective in contributing to the upwards trend across indicators, and therefore a ‘good value’ for our investment.

Progress in some programme areas and outcome progress is beginning to slow and face challenges, due to increasingly strained political and fiscal contexts in the face of the global anti-rights movements, as well as the expected nature of diminishing returns when approaching the ‘Last Mile’ as interventions increase and the remaining population size of people living with HIV not aware of their status or receiving treatment decrease (and often experience more vulnerabilities or are more marginalised). These populations need more targeted, bespoke support in order to ensure HIV services are safe and accessible, and UNAIDS’ role in data generation, community mobilisation and S&D will continue to be key for reaching these populations and preventing a reversal of progress on the epidemic.

Reporting on the Joint Programme’s budget and the UBRAF has continued to improve. The UBRAF now provides a comprehensive overview of activities undertaken, and the indicator matrix is well-aligned with the Global AIDS Strategy 2021-2026, which itself leverages four decades of experience and evidence from the HIV response. However, information on the links between budgets, activity and results continues to be limited, especially regarding the use of Co-Sponsor budgets for the Joint Programme. The MOPAN assessment (2023) notes that the evidence from UNAIDS reporting is not compelling for a donor audience seeking specific, measurable, and ‘results-based’ funding arrangements, and stresses the need for a clearer articulation of UNAIDS’ value add in the complex architecture of the global HIV response. The MOPAN and the Independent Evaluation of the UN Systems Report 2016-19 also found a lack of clear distinction of the roles of individual Co-Sponsors against specific results areas, although the MOPAN assessment (2023) noted some improvements in the 2022-6 UBRAF. Likewise, visibility on the Secretariat’s strategic prioritisation remains limited for Board members, and increasing this will be a priority for future UNAIDS programming- addressing this is a key recommendation of this report; this was echoed in the MOPAN assessment (2023).

Equity

The UNAIDS Global AIDS Strategy has a strong focus on the key and vulnerable populations most at risk from HIV, channelling efforts and resources to populations and areas of the most needs, and the Secretariat in particular works to reinforce community and civil society engagement in the AIDS response. During this period, a number of interventions were launched on differentiated and targeted services to address ‘left behind’ groups, including the Global Prevention Coalition, the Fast-Track Countries, and the Global Partnership to End All Forms of HIV Stigma and Discrimination.

Key populations continue to be particularly at risk from HIV, accounting for 70% of new infections in 2022, and progress is still too slow for other vulnerable populations such as children and adolescent girls and young women. An emphasis on equity and equality has been maintained in the Global AIDS Strategy 2021-26 and other UNAIDS flagship reports, focussing on the dismantling of the structural and systemic inequalities barring key and vulnerable populations from accessing HIV treatment/prevention services and SRHR. However, issues of stigma and discrimination continue to be a significant barrier to the global HIV response, so continued efforts on this will be critical in ongoing UNAIDS programming.

UNAIDS’ organisational operating model also has a strong focus on equity, with the staffing model comprised of a large majority of staff in country offices, a focus on recruiting locally based staff, and an emphasis on diversity and inclusion reflected in staff survey responses.

Assess VfM compared to the proposition in the Business Case, based on the past year and during the lifetime of the programme.

As a whole FCDO’s investment in UNAIDS has contributed to the upward trends and achievements on most of the indicators.

A particular strength of this programme and its value for money rests in its strong emphasis on equity, delivering significant impact for those poorest and most marginalised. UNAIDS’ value add in dismantling the structural inequalities underpinning the HIV response extends beyond the HIV epidemic alone, with secondary effects on gender equality, improved education curricula, and more resilient community health and social systems and organisations.

In addition to performance against outputs as outlined in the previous section of this PCR, UNAIDS is important in contributing impact and value for money across the FCDO’s wider global health portfolio. Alongside WHO it is the main technical partner on HIV for the Global Fund to Fight AIDS, TB and Malaria, which provides half of the world’s HIV financing and to which the UK has pledged to invest £1 billion between 2023 and 2025- one of our largest current multilateral investments. UNAIDS’ support for the Global Fund includes technical assistance to the application, design, and implementation of $1 billion’s worth of Global Fund grants, as well as acting as the leading source of HIV data for health institutions. This relationship remains a key tenet of UNAIDS’ approach, and its value add in the broader infrastructure of the global fight against HIV, and we will continue to evaluate this and seek continued evidence of its impact.

However, progress is still needed within UBRAF reporting on results delivered by the Co-sponsors through their Joint Programme core funding (comprising approximately 1/3 of Joint Programme expenditure). The MOPAN assessment highlighted lack of clarity around roles and individual organisations’ contributions to results in reporting, although noting improvements from the previous UBRAF, and the lack of a compelling narrative to attract donors seeking results-based funding arrangements for the Secretariat’s global coordination and convening role. And efforts to respond to the financial shortfall through intensified resource mobilisation efforts, while justified, have risked distracting from or deferring work on informed, risk-assessed prioritisation. A refreshed approach to prioritisation is recommended to ensure maintained economy and efficiency, with increased Co-Sponsor consultation and transparency of rationale of management decisions to PCB members, alongside a rethink of certain elements of the Joint Programme as is allowed within the Modus Operandi. For instance, as highlighted in the previous programme’s PCR, there is likely to be scope for reallocation of Joint Programme funds between the Secretariat and Cosponsors to improve Value for Money. A key priority for the FCDO in the upcoming 2022-26 programme cycle will therefore be to encourage a stronger focus on clearer reporting, especially an increased understanding of the role of Co-Sponsors as part of discussions on the sustainability of the HIV response and a fit-for-purpose Joint Programme.

E: Risk

Overview of programme risk during the past year and over the life of the programme, drawing on FCDO’s Risk Management Policy and Risk Appetite Statement and wider risk guidance.

The main risks identified in the original business case were:

1. Insufficient finance from donors undermines UNAIDS’ ability to deliver on contribution to Global AIDS Strategy 2021-2026
2. Global AIDS Strategy 2021-2026 is not implemented as planned
3. Changes in senior management team leads to reduced Secretariat performance and/or de-prioritisation of UK priorities
4. Weaknesses in accountability of Cosponsors reduces overall impact of Joint Programme
5. Non likeminded countries seek to limit UNAIDS ability to take an evidence based and comprehensive approach, particularly with reference to SRHR.

Our initial risk assessment was high (major), in line with our risk appetite for the programme, but further mitigations were identified during the business case development process to reduce the impact of these risks.

The inherent and residual risks of 1 and 2 remained high over the lifetime of the programme and were particularly heightened by the sustained and increasing shortfall of core funding. The rising opposition to the rights of women and girls and LGBT+ people seen globally has also kept alive the risk of the Global AIDS Strategy 2021-26 not being fully implemented, and contributed to risk 5; however, the vast majority of UBRAF outputs continue to be achieved, and outcomes and impacts continue a positive, albeit slowing, trajectory. As outlined in previous sections of this report, while UNAIDS’ approach to resource mobilisation and prioritisation have gone some way to addressing the financial shortfall, a more comprehensive and agile approach to sustainability planning and prioritisation with increased stakeholder engagement is recommended for future years. The UK will continue press for continued scenario planning and prioritisation for budget shortfalls, as well as sustainability planning, and encourage other donors to do the same as well as to increase or commence funding to UNAIDS.

Regarding risk 5, UNAIDS has continued to work through the Global AIDS Strategy 2021-26’s inequalities lens to protect and promote evidence-based and rights-based approaches, particularly regarding SRHR. Significant gains have been made in PCB negotiations for UNAIDS decisions, with landmark references to comprehensive sexuality education and transgender people secured without the need for a vote. UNAIDS will continue its efforts to advocate for human rights to achieve public health aims, within their respected role in various countries, and ensure key populations and community-led organisations remain at the heart of programmatic work.

Risk 3 did not materialise throughout the programme’s life cycle- two new Deputy Executive Directors were recruited in support of the implementation of the transformation and realignment process, adding further resilience to senior management through the additional staff as well as clearer reporting structures. The UK routinely and directly engages with UNAIDS at working, official and senior levels to ensure our shared priorities are followed through.

While transparency around Co-Sponsor expenditure and reporting remains an issue, there have been some improvements following the latest UBRAF iterations and evaluations. Earmarking of funds to the secretariat was also an effective mitigation again risk 4; however, given the importance of the Co-sponsors’ role in contributing to the Global AIDS Strategy 2021-2026 targets- and their unique contribution to UNAIDS as a Joint UN Programme- we recommend removing this earmarking in future programming to allow for more effective, flexible resource allocation across the Joint Programme. We will still continue to push for Co-sponsors accountability to be strengthened through updating the UBRAF to include results delivered through core Co-sponsor funding, in order to provide wider assurances around all areas of the programme and its implementers.

Additional risks around safeguarding remained high throughout the lifecycle of the programme, as highlighted by the MOPAN assessment (2023). The UK has been key in previous years. in building and maintaining PCB momentum on these issues in our capacity as Board Vice Chair (2017) and Chair (2018) and continues to discuss safeguarding matters with UNAIDS directly and routinely throughout the current and previous programmes’ lifecycles. We will continue to utilise our position as a Board Member to hold the Joint Programme to account against future evaluations and audits, and to encourage other donors to do the same. It is also recommended that future FCDO programme embeds metrics and indicators around safeguarding into its monitoring and evaluation framework.

F: Programme Management: Commercial and Financial Performance, Monitoring and Evaluation

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including VfM measures of economy and efficiency.

The UK provided £16 million over two years (£8 million each in 2022 and 2023) to UNAIDS to support its important role of leadership, coordination, strengthening and optimisation of the global response to achieve the ambition of ending the AIDS epidemic by 2030. The entirety of the UK’s support was unconditional for this period, following a reduction in funding from £15m p/a due to broader fiscal constraints as well as UNAIDS’s success in meeting annually agreed performance targets in the 2016-21 wave of programming. The UK’s funding to date has been ring-fenced to the UNAIDS Secretariat to support its leadership, coordination and strengthening of the global response. Given the short length of this programme (15 months) compared to previous programmes supporting UNAIDS (up to 5 years) due to longer-term fiscal uncertainty at the time of Business Case development, an Annual Review exemption was granted, with only a Project Completion Report required.
Supplementary to our performance agreement, the FCDO receives through the UK’s PCB membership annual reports from the Internal and External Auditors to support our programme monitoring and evaluation, including on risk, financial and asset management and partner management. In 2021, 2022 and 2023, UNAIDS were issued with an unqualified opinion on their financial statements by the External Auditors confirming that the financial statements were in accordance with international standards. Management has agreed to implement all 4 recommendations from the 2022 external audit, having a strong track record in doing so (as of 2022, all 11 previous external audit recommendations were in the process of implementation, had already been implemented, or were overtaken by events).
On points of economy and efficiency, the log frame effectively tracked programmatic achievements over the period under review against core UBRAF Strategy Results Areas and Secretariat Functions in a context of constrained funding and resources for the global HIV response. However, as noted previously, the log frame was not used to follow various streams of organisational reform, particularly on safeguarding, as well as work to improve efficiency and transparency via organisational transformation (including the implementation of the realignment process). These will be crucial workstreams in the leadup to the development of the 2026-30 Global AIDS Strategy against the backdrop of an increasingly strained fiscal and political landscape and the global health reform agenda.

Programme-level approach to monitoring and evaluation

Monitoring and evaluation of the programme has taken place in multiple ways and at multiple levels.
- FCDO used a logical framework to track and evaluate UNAIDS’ performance and progress during this PCR.
- FCDO officials also had regular monitoring check-ins with UNAIDS counterparts, designed to assist the identification of gaps and opportunities to address, particularly in relation to how the project is being managed and monitored.
- Membership of PCB: FCDO officials engage with UNAIDS staff through the bi-annual Programme Coordination Board and throughout the year to discuss specific areas relevant to strengthening UNAIDS and the wider HIV response, influencing the development of UBRAF indicator matrices and workplans and gaining access to regular audit reports from a range of agencies. These reports include those from the Internal Auditor, External Auditor, Independent Expert Oversight Advisory Committee, and as of 2021 the Ethics Office. Board discussions are also supported by UNAIDS’ ongoing monitoring through the Unified Budget, Reporting and Accounts Framework (UBRAF), comprised of a comprehensive set of planning and reporting tools.