## Template
Please refer to the PrOF Guide for advice on completing the various fields in the logframe.
Smart Guide
PROJECT TITLE | Core Funding to the UN Resident Coordinator System | [6 empty] | NOTES
IMPACT | Impact Indicator 1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
The desired impact of this programme is for the UN, with host countries, to accelerate action on priorities including the SDGs, human rights, humanitarian, peace and security. | % of programme country Governments reporting that, since the implementation of the new RC system in 2019, the resident coordinator has displayed increased or strengthened: 1. Authority 2. Leadership 3. Impartiality 4. Management skills 5. Capacity to coordinate UN activities in support to country priorities 6. Focus on common results 7. Coherence (reducing duplication of efforts) 8. Ability to serve as an entry point for easy access to UN expertise | Planned | 1. 59% (2019) 2. 65% (2019) 3. 59% (2019) 4. 75% (2021) 5. 66% (2019) 6. 60% (2019) 7. 56% (2019) 8. 78% (2020) | 1. 64% 2. 70% 3. 64% 4. 79% 5. 71% 6. 65% 7. 61% 8. 82% (2023) | 1. 88% 2. 90% 3. 85% 4. 82% 5. 88% 6. 89% 7. 85% 8. 92% (2024) | 1. 93% 2. 95% 3. 90% 4. 85% 5. 93% 6. 94% 7. 90% 8. 97% (2025)
|  | Achieved |  | 1. 83% 2. 85% 3. 80% 4. 79% 5. 83% 6. 84% 7. 80% 8. 87% | 1. 84% 2. 88% 3. 84% 4. 86% 5. 86% 6. 88% 7. 84% 8. 82%
Source
QCPR M&R
OUTCOME 1 | Outcome Indicator 1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumptions
Value for money – DCO sets direction and expectations to improve value for money across the UN Development System through greater coordination and One UN Delivery. | Savings accrued from system-wide and entity-specific reform initiatives (total) | Planned | $194m (2021) | $230m (2023) | $270m (2024) | $310m (2025)
|  | Achieved |  | $405m | $553m
Source
DCO Results Framework
OUTCOME 2 | Outcome Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
Effective leadership and integration – Empowered and impartial UN Resident Coordinators set strategic direction for, and lead coordination across, the UN Development System and with the UN’s humanitarian, human rights and peace/security pillars. | % of UNCTs in mission settings that have a joint mission-UNCT structure/mechanism in place | Planned | 56% (2021) | Not set | 88% (2024) | 95% (2025)
|  | Achieved |  | 84% | 87%
Source
DCO Results Framework
OUTCOME 3 | Outcome Indicator 3 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
A targeted approach that is aligned to UN mandates – RCs direct UN country teams (UNCTs), through planning cycles and country documents, to focus on delivering impact for the most in need, and delivering on their mandates, based on their comparative advantage. | % of programme country Governments that agree they received joint integrated policy advice from the UNDS that is tailored to national needs and priorities in the implementation of the 2030 Agenda. " | Planned | 79% (2017) | Not set | 95% | 100% (2025)
|  | Achieved |  | 85% | 88%
Source
QCPR M&R
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
5200000
INPUTS (HR) | FCDO (FTEs)
0
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumptions
Deliver well trained, experienced Resident Coordinators, who are deployed on time with fewer gaps between posts. | % of programme country governments agreeing the RC has the right profile and skillsets to support their country’s development | Planned | 78% (2019) | 85% (2023) | 93% (2024) | 95 % (2025)
|  | Achieved |  | 90% | 91%
Source
DCO Results Framework
| Output Indicator 1.2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| % of regular recruitments within RC System completed within the target time frame (120-days) | Planned | 70% (2021) | 82% (2023) | 88% (2024) | 95% (2025)
|  | Achieved |  | 62% | 52%
Source
DCO Results Framework
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
| 5200000 |  |  |  |  | 100
INPUTS (HR) | FCDO (FTEs)
0
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumptions
At country level, set clear guidance with benchmarks to UNCTs on value for money. | % of all UN premises that are Common Premises | Planned | 22% (2021) | 35% (2023) | 42% (2024) | 50% (2025)
|  | Achieved |  | 30% | 31%
Source
DCO Results Framework
| Output Indicator 2.2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| % of UNCTs with a Local Shared Services Centers (LSSC), formerly Common Back Offices, design business cases approved | Planned | 0% (2020) | 30% (2023) | 6 pilots launched and implications assessed for wider rollout (2024) | 50% (2025)
|  | Achieved |  | 0% | 1 complete in QCPR M&R period (Kenya) with 2 others launched May 2024
Source
QCPR M&R
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
| 5200000 |  |  |  |  | 100
INPUTS (HR) | FCDO (FTEs)
0
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumptions
Feeds into reform updates across a range of the UN Development System executive boards to engage with the agencies to support rollout, including setting guidance with benchmarks, to the UNDS on value for money and efficiencies. | % of UNDS entities that have updated the job descriptions of UNCT heads to recognize the role of the resident coordinator, as outlined in resolution 72/279 and the MAF | Planned | 36% (2019) | 80% (2023) | 90% (2024) | 100% (2025)
|  | Achieved |  | 68% | 89%
Source
QCPR M&R
| Output Indicator 3.2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| % of programme country Governments indicating that funds are “closely aligned” with the country’s development needs and priorities: 1. core 2. non-core | Planned | 1. 70% (2017) 2. 65% (2017) | 1. 75% 2. 70% (2023) | 1. 80% 2. 85% (2024) | 1. 85% 2. 90% (2025)
|  | Achieved |  | 1. 76% 2. 80% (2023) | 1. 76% 2. 70%
Source
QCPR M&R
| Output Indicator 3.3 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| % of relevant UNSDG members reporting that they complete the reform checklist and share with their governing body annually | Planned | 0 (new) | 0 (new) | 35% | 100%
|  | Achieved |  |  | 56%
Source
DCO Results Framework
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
| 5200000 |  |  |  |  | 100
INPUTS (HR) | FCDO (FTEs)
0
OUTPUT 4 | Output Indicator 4.1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumptions
Quality assure UN Sustainable Development and Cooperation Frameworks (UNSDCFs), and Common Country Analyses (CCAs) in a way that helps ensure that the content targets the most in need, is politically sensitive, brings together humanitarian actors where possible, integrates conflict sensitivity, identifies conflict drivers early on, improves structures to bring agencies together focuses on the UN’s comparative advantages and ensures implementation of the Management and Accountability Framework (MAF) - with consultation from donors. | % of Cooperation Framework Joint Workplans in UN INFO published on the UNSDG data portal | Planned | 66% (2021) | 74% (2023) | 85% (2024) | 90% (2025)
|  | Achieved |  | 81% | 82%
Source
DCO Results Framework
| Output Indicator 4.2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| % of UN Country Teams that undertake with humanitarian actors, as relevant: - Joint needs analysis - Complementary and joined-up planning | Planned | 56% (2020) 26% (2021) | 65% (2023) 35% | 75% (2024) 45% | 85% (2025) 60%
|  | Achieved |  | 61% 40% | 63% 60%
Source
DCO Results Framework
| Output Indicator 4.3 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| % of Common Country Analyses that were updated in the last year | Planned | 80% (2021) | 85% (2023) | 90% (2024) | 95% (2025)
|  | Achieved |  | 72% | 74%
Source
DCO Results Framework
| Output Indicator 4.4 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| % of Common Country Analysis that includes an assessment of barriers faced by those being left behind or at risk of being left behind | Planned | 60% (2021) | 80% (2023) | 94% (2024) | 100% (2025)
|  | Achieved |  | 89% | 89%
Source
QCPR M&R
| Output Indicator 4.5 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| % of UN Country Teams with results groups (chaired or co-chaired by UNCT heads of agencies) | Planned | 72% (2020) | N/A | 95% | 100% (2025)
|  | Achieved |  | 92% (2023) | 86%
Source
QCPR M&R
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
| 5200000 |  |  |  |  | 100
INPUTS (HR) | FCDO (FTEs)
0

## Change frame
Use this change log to record all changes to the logframe over the life of the project.
ID | LOGFRAME SECTION | DETAILS OF CHANGE | AUTHOR | DATE
E.g. | Output 1, Indictor 2 | Indicator amended from 'No of children enrolled in primary schools' to 'Number of children enrolled in UNICEF supported primary schools (disagregated by sex) | Joe Bloggs | 2018-01-01
1
2
3
4
5
6
7
8
9
10

## Guidance Notes
Smart Guide
Teams should use the guide below to complete the logframe template.
PROJECT TITLE
A meaningful, easily understood (plain English) Project Title.
IMPACT
Long term goal to which the project will contribute towards achieving. When drafting the impact statement, consider how your project fits with other efforts from FCDO and partners to achieve the impact, ie is your project nested within a broader undertaking?
OUTCOME
The outcome of your project identifies what will change, who will benefit and how it will contribute to reducing poverty, including contributions to the Millenium Development Goals (MDGs) or Climate Change.
An assessment of whether your project achieved the Outcome will be included in the Project Completion Review (PCR). Ongoing monitoring of progress against outcome milestones should still take place as an assessment of whether you expect to achieve the Outcome by the end of the programme will be included in Annual Reviews.
OUTPUTS
Outputs are the specific, direct deliverables of your project. These will provide the conditions necessary to achieve the Outcome. The logic of the chain from Output to Outcome therefore needs to be clear.
Progress against Output milestones and results achieved will be assessed and scored during Annual Reviews and the Project Completion Review.
IMPACT WEIGHTING
Once you have defined your Outputs, assign a percentage for the contribution each is likely to make towards the achievement of the overall Outcome.
The impact weights of all the Outputs will total 100% and each are rounded to the nearest 5%.
Impact weightings for Outputs are intended to:
l | Promote a more considered approach to the choice of Outputs at project design stage; and
l | Provide a clearer link to how Output performance relates to project Outcome performance.
INPUTS
Clarification of inputs is a key part of results-chain thinking. Inputs are specified at the country-level in country operational plans and the project information contained in logframes should feed up into these.
The input-level boxes show the amount of money provided by FCDO and any partners (£) including, where relevant, the government’s own contribution. This only relates to monetary (not in kind) contributions. At Outcome level this is equal to the sum of Inputs for all Outputs. The FCDO share at Outcome Level is a simple, pro rata calculation of DFID’s contribution in monetary terms for all outputs.
Information should also be provided for the total number of Annual DFID Full-Time Equivalents (FTEs) allocated to this project, based on the time individual staff members will spend on the project. It is understood that this may change through the project cycle, and is intended as a management tool.
INDICATORS
Indicators are performance measures, which tell us what will be measured not what is to be achieved. Avoid including elements of the baseline or target.
What makes a good indicator?
l | Specific – what will be measured? And how?
l | Measurable - data can be collected
l | Relevant - to the results chain
l | Useful – for management decision making
l | Does not include any element of the target
l | Can be disaggregated if relevant
l | Good mix of qualitative and quantitative
l | Already defined - if relevant include indicators which towards the DRF / OP / ICF KPIs / MDGs.
l | Consider using standard indicators / best practice indicators / learning from other projects
The basic principle is that “if you can measure it, you can manage it”.
Top Tip – select indicators based on relevance to the Results Chain and the availability of data.
Best Practice suggests a maximum of three Indicators per Output.
Some example indicators for a WASH project are shown below.
BASELINE
Baselines set the starting point and provide a measure of the situation before your project starts (could be zero if a new project).
The baseline is used to measure change and monitor progress.
Include a baseline for each of your indicators. The first 6 months of a project may exceptionally be used for assembling baseline data at output level if agreed by your PRO.
Use existing data where possible, but check reliability and seek assurances regarding the data quality eg use data from national statistical systems / MIS.
If you need to collect your own data - collect baseline data early – as soon as beneficiaries have been identified but before any results are expected.
MILESTONES
Milestones are the desired trajectory from baseline to target, helping you to track progress and make changes to underperforming areas.
Will depend on sequencing of activities and data availability.
Include REALISTIC milestones given resources and capacity.
At the output level include annual milestones for each year of the project (or monthly if short term). At outcome & impact level data may not be available annually.
TARGET (DATE)
Targets set the desired point, showing what is achievable within the timeframe available.
The target is often the last year of the project (or month if its short term).
Include realistic targets given resources and capacity, the baseline situation, funding available and country/operational context. Project targets might be informed by evidence about what has worked in the past and take into account lessons learned from other projects.
Include targets dissaggregated by sex/geography/income etc where appropriate.
Consider using government targets although if they are too ambitious then make a more realistic estimate.
Top Tip - A good Theory of Change will help you think about what is realistic and achievable as it will enable critical reflection of context, external influences & assumptions.
SOURCE
Each Indicator will have a data source to verify the results achieved.
List the specific data sources i.e. give the specific data collection e.g. named survey / report and avoid just naming the organisation.
State the frequency of the data source and ensure consistency with milestones and targets.
Check the source can provide disaggregated data as required.
Consider and specify the data collection and reporting responsibilities to ensure the results planned and forecast rows in the logframe are updated on a regular basis.
Top Tip - Before using a data source, assess its quality and seek assurances from data providers where needed ie consider its validity, reliability and availability.
ASSUMPTIONS
Define any assumptions which are linked to the realisation of your project's individual outputs, as well as those which are critical to the realisation of the outcome and impact: these will not all be the same.
VALUE FOR MONEY
Ensure the outputs and outcome projected represent good value for the invested resources, at the beginning of the project, and through its life.
Consider including VfM metrics in the logframe (or other documents such as the Delivery Plan) to allow VfM to be measured through the life of the project and to provide assurance at Annual Review.
VfM is achieved at different stages of the results chain. Thus for each result we seek to achieve we should aim to have metrics for each of the following:
Economy - Are we (or our agents) buying inputs of the appropriate quality at the right price?
Efficiency - How well are we (or our agents) converting inputs into outputs? (‘Spending well’)
Effectiveness - How well are the outputs produced by an intervention having the intended effect? (‘Spending wisely’)
Cost-effectiveness - What is the intervention’s ultimate impact on poverty reduction, relative to the inputs that we or our agents invest in it?
FCDO’s Approach to Value for Money (PrOF Guide) provides further advice on ensuring VfM.