## Annual Review

Title: Core Funding to the United Nations Special Purpose Trust Fund (UN SPTF) for the Resident Coordinator (RC) System
Programme Value £ (full life): £15,600,000		Review date: 09 August 2024
Programme Code: 301559	AMP start date: 30/10/2022	AMP end date: 30/03/2025

Summary of Programme Performance
Year	1	2
Overall Output Score	B	B
Risk Rating	Moderate	Moderate

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/D0004469.odt
DevTracker Link to results framework:

A. SUMMARY AND OVERVIEW

Description of programme

The UK supports efforts to reform the UN Development System, for which the Resident Coordinator System is a central part. The reform efforts are necessary to ensure that the Development System offers greater value for money, works as ‘One UN’, and has a more targeted approach to global development issues. The Resident Coordinator System (RC System) aims to help create a UN that is better aligned to the UN Charter systemwide and provides impartial, cohesive leadership in-country.

The most senior UN representative in-country, there are 130 Resident Coordinators (RCs), leading 132 Resident Coordinator’s Offices (RCOs) worldwide, overseeing development operations in 162 countries and territories. Given each RC’s leadership position, and with their oversight of all development activities in country, UK funding to the RC system is important in reinforcing the other streams of UK funding to the UN Development System (UNDS). Funding the RC system allows for the impact of wider UK UNDS funding to be enhanced and aims to provide a greater level of trust that the efficacy of this broader pool of funding is not being unduly hampered by inefficient processes or duplication of UN agency efforts in-country.

However, UK voluntary contributions make up only a small part of the overall funding for the RC system (£5.2m p/a), meaning it would be unrealistic to expect our level of funding to make substantial changes on its own in this area. The RC System currently has 3 funding streams and aims to collect $281 million in total in 2024: $154 million from voluntary contributions (VCs), $77.5 million from a UNSDG cost-sharing arrangement and $50 million from a 1% coordination levy.

There have been persistent issues caused to the RC system by a gap between desired and achieved funding levels, particularly in the amount raised through voluntary contributions from UN Member states. This has been evident since the reinvigoration of the RC system in 2019 and was still the case during the 2023 reporting period. The funding gap for 2023 was $54m, caused in large part by a lack of voluntary contributions. There are currently negotiations ongoing at the UN about potential changes that could be made to the funding streams of the RC System, with the UN Secretary General having published a report earlier this year proposing the conversion of the voluntary portion of the funding to assessed contributions from the UN Regular Budget.
[note] Note: the UK already bases its funding level on the amount it would contribute under an assessed UNRB funding model and has consistently called on other Member States to raise their funding level.

Summary supporting narrative for the overall score in this review

The programme has scored a B against the Output Indicators for the reporting period. This is to reflect the underperformance of the programme against targets in many Output Indicator areas, but also to account for the fact that target levels agreed with DCO are deliberately ambitious and that the system was operating against the backdrop of 5 consecutive years of funding gaps, despite the strong, consistent level of UK funding, which undoubtedly impacts each Output Indicator for the programme.

Further, given the short time the RC System has been operating in its current form, and the centrality of this reinvigorated system to the overall UN Development agenda, to have many areas across the logframe where a positive trajectory is visible year-on-year (even if in-year targets are missed) should represent encouragement that the programme is contributing to UN performance on the ground. It should also be emphasised on this point that the RC System is aimed at achieving long-term UNDS reforms and many of the indictor areas do not lend themselves neatly to yearly review, with the results of many indicators potentially impacted by subjective in-year events. For instance, emerging conflicts often require interim positions in RC offices to be extended rather than filled with a permanent appointment, which can negatively skew scoring on recruitment timelines in-year, despite it not necessarily being an example of the system underperforming.

Nevertheless, there have been some areas that have been more substantially off target and others where progress has either stalled or regressed. Among the most disappointing of these are specific areas such as establishment of Local Shared Services Centers (LSSCs) and on the broader point around recruitment timelines, where the programme has remained off target for a second year in succession.

It should also be mentioned, however, that the second year of the programme has seen some encouraging overachievements at the Impact and Outcome levels. This includes improved management skills displayed by Resident Coordinators at the Impact level, and substantial efficiency savings for a second year at the Outcome level.

Major lessons and recommendations for the year ahead

Lesson/recommendation	Owner/main implementer	Deadline
DCO to update FCDO on efforts to strengthen aspects of an RCs role related to accessing UN expertise / FCDO to explore this issue further internally through engagement with posts to understand where issues may have arisen from an in-country perspective	DCO/FCDO	November 2024 & ongoing
DCO to update FCDO on work that is ongoing to improve the status of recruitment timelines	DCO	Ongoing
DCO to update FCDO on the performance of the established LSSCs and the progress towards the establishment of the remaining pilot schemes already underway throughout the next reporting period / FCDO should use upcoming cross-department engagement to ensure that appropriate FCDO teams are aware of the efforts ongoing on these projects	DCO/FCDO	Ongoing
During the logframe refresh for the forthcoming reporting period, FCDO should communicate candidly with DCO to make sure that all final year Impact/Outcome/Output indicators have ambitious, but realistic targets and are representative of what the programme can achieve	FCDO	November 2024
DCO should update FCDO on the outcome of the review into the MAF and the continued applicability of Outcome Indicator 3.1 should be considered during the logframe refresh accordingly	DCO	Autumn 2024
DCO should use negotiations on the future of RC System funding as an opportunity to engage in discussions on how it can strengthen its governance model, in particular avenues through which more regular structured dialogue with member states can be facilitated / FCDO should engage closely with RC System funding negotiations and ensure governance models are considered as a central part of its contributions to the negotiations	DCO/FCDO	Ongoing

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

The desired impact of this programme is for the UN, with host countries, to accelerate action on priorities including the SDGs, human rights, humanitarian, peace and security.

Advancing reform in the UN Development System is key to achieving the desired impact and the UN RC system was reinvigorated in 2019 (having been made independent from UNDP) as a central feature of efforts to reform this space. As set out in UN documents, RC’s have various roles, including, but not limited to:

- Promoting fundamental values, standards and principles the of the UN Charter;
- Leading UN country teams in the development, monitoring and reporting on the UN Cooperation Framework;
- Coordinating UN system-wide support to Governments;
- Driving UN operational efficiencies and VFM;
- Ensuring effective UN support for disaster preparedness
  [note] UNSDG The Resident Coordinator. Available at: UNSDG | The Resident Coordinator

The UK is among the top voluntary contributors to the RC System, ranking 4th highest in the G7 in 2023 (behind the US, Germany and Japan) and, since 2019, ranks 5th in overall voluntary contributions (behind also Norway). Therefore, continued adequate funding of DCO from the UK is important if the RC system is to succeed in fulfilling its role within the UN Development System effectively and drive further reforms.
[note] UNSDG SPTF - Where the funds are coming from. Available at: UNSDG | Where the funds are coming from

The diagram below shows the Theory of Change (ToC) for this programme, as set out in the Business Case:

In relation to indicator alterations in this reporting period, Outcome Indicator 2 has changed from measuring the proportion of joint programmes in UNCTs with a dedicated focus on women’s empowerment, and poverty reduction and basic services, to instead measure the percentage of UN Country Teams (UNCT) in mission settings that have a joint mission-UNCT structure/mechanism in place. The annual milestones for Outcome Indicator 2 have also been amended to reflect the updated results framework.

Outcome Indicator 3 has also been changed in this reporting period. Formerly it measured the percentage of 8 different sub-groups of actors that UNCTs consulted during the Cooperation Framework design phase. Instead, it now measures the percentage of programme country Governments that agree they received joint integrated policy advice from the UNDS that is tailored to national needs and priorities in the implementation of the 2030 Agenda. This ensures that adequate focus is placed on the ability of the RC system to help implement to 2030 Agenda, a central tenet of the UNDS and the wider reform agenda.

Output Indicators 3.3 and 4.5 have been added to the logframe for this reporting period to provide a more rounded view of programme performance. They measure the percentage of relevant UNSDG members reporting that they complete the reform checklist and share with their governing body annually, and the percentage of UN Country Teams with results groups (chaired or co-chaired by UNCT heads of agencies) respectively.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

Impact

The impact of this programme is for the UN, with host countries, to accelerate action on priorities including the SDGs, human rights, humanitarian, peace and security. There is one Impact Indicator in this area.

Impact Indicator 1: Percentage of country Governments reporting that, since the implementation of the new RC system in 2019, the resident coordinator has displayed increased or strengthened:

- Authority (84% against a target of 88%)
- Leadership (88% against a target of 90%)
- Impartiality (84% against a target of 85%)
- Management skills (86% against a target of 82%)
- Capacity to coordinate UN activities in support to country priorities (88% against a target of 88%)
- Focus on common results (88% against a target of 89%)
- Coherence (reducing duplication of efforts) (84% against a target of 85%)
- Ability to serve as an entry point for easy access to UN expertise (82% against a target of 92%)
Although only two of the eight areas covered in this Impact Indicator have met or exceeded targets this year, given how close other areas are to achieving target and the fact that targets for this year were upgraded since the last annual review, overall progress against this indicator remains on a positive trajectory.

However, concern should be noted over the apparent regression in the RC System’s ability to serve as an entry point for easy access to UN expertise. FCDO should therefore liaise closely with DCO on where progress can be made on strengthening aspects of an RCs role related to accessing UN expertise and explore this issue further through engagement with posts to understand where issues may lie from an in-country perspective. Fluctuations in yearly scoring against this Impact Indicator can be expected due to changing country contexts, however it is welcome that DCO note the decline and will investigate it, undertaking course correction where possible.
[note] Report of the Chair of the United Nations Sustainable Development Group 2023; page 17

Outcomes

There are three Outcome Indicators, and the programme remains broadly on track to meet them. However, there are areas where the programme has underachieved in this reporting period:

Outcome Indicator 1: Savings accrued from system-wide and entity-specific reform initiatives (total)

Financial savings of $553m were accrued from system-wide reforms, against a target of $270m for both system-wide and entity-specific initiatives. For the second consecutive year, this represents a substantial overachievement in this area and shows that confidence can be felt in the ability of the RC System to drive reforms in a way that is beneficial to efforts to ensure value for money is achieved.

Outcome Indicator 2: Percentage of UNCTs in mission settings that have a joint mission-UNCT structure/mechanism in place

This Outcome Indicator has been substantially achieved in the second year of the programme, falling just 1% short of the target for this reporting period – 87% achieved against a target of 88%.

This Outcome Indicator has been changed since the previous annual review. The previous indicator was not considered to be providing enough of a holistic view of progress against the overarching aims of the programme in this area.

For this reporting period, the indicator better reflects the extent to which host Governments rate the effectiveness of the RC in leading the UNCT’s strategic support for national plans and priorities. While the target has not been reached for this reporting period, a score of 87% still represents a strong performance across the year.

Outcome Indicator 3: Percentage of programme country Governments that agree they received joint integrated policy advice from the UNDS that is tailored to national needs and priorities in the implementation of the 2030 Agenda.

This Outcome Indicator has not successfully reached the target level in the second year of the programme, scoring 88% achieved against a target of 95%.

This indicator is new for this reporting period, however the first result falls short of what was expected. Nevertheless, a score of 88% still represents an uplift from the previous reporting period and indicates a positive trajectory against the baseline of 79%, albeit with more work needed in order to reach target levels, so FCDO should continue engagement with DCO on this area.
[note] Note: The baseline level and previous year performance can both be found in the DCO Results Framework, even though this is the first year that this indicator has been included in the FCDO logframe.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

The programme has scored a B for this reporting period and has been considered to still offer good value for money in its second year, despite underachieving against many of the Output Indicators (detailed analysis below). The programme continues to demonstrate strong ability to drive system wide savings, which in turn ensure that more spectrum-wide UK development funding is spent efficiently and directly on development efforts. However, close cooperation will be needed between FCDO and DCO in the coming year to make sure results better meet expectations in number of areas in 2024-25, and both DCO and FCDO should work collaboratively to ensure RC System funding can be placed on a more sustainable footing to safeguard progress made to date and drive the system to make further improvements in future years.

## C. DETAILED OUTPUT SCORING

Output Title	Deliver well trained, experienced Resident Coordinators, who are deployed on time with fewer gaps between posts.
Output number:		1	Output Score:	B
Impact weighting (%):		25%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
% of programme country governments agreeing the RC has the right profile and skillsets to / support their country’s development	93%	91% (Underachieved)
% of regular recruitments within RC System completed within the target time frame (120-days)	88%	52% (Underachieved)

Briefly describe the output’s activities and provide supporting narrative for the score.

While Output Indicator 1.1 has fallen slightly short of the milestone for this review, a score of 91% of programme country governments agreeing the RC has the right profile and skillsets to support their country’s development is very encouraging and represents slight progress against last year’s score. Add to this the fact that only 3% of programme country governments answered ‘disagree’ on this measure, confidence can be derived from the continuing high percentage scores in this area.

Worth also noting is the fact that, ‘DCO now undertakes a robust analysis of the profile needed for each country, working closely with OCHA and DPPA/DPO when Resident Coordinators are expected to serve as Humanitarian Coordinators and Deputy Special Representatives of the Secretary-General, before a selection is made by the Secretary-General.’
[note] Report of the Chair of the United Nations Sustainable Development Group 2023, page 17

When considering the figures at face value, cause for continued and increased concern is Output Indicator 1.2. The percentage of regular recruitments within the RC System completed within the target time frame of 120-days is a long way from the target set for this year and has regressed since the previous reporting period. However, consideration must be given to the undoubted impact of the persistent funding shortfall on this indicator, with this reporting period having seen necessary recruitment being frozen for key roles in RC offices in the DRC, Mali, South Sudan, Sri Lanka, amongst others. Indeed, a UNSDG report notes that resourcing constraints have led to frozen recruitment for positions in 52 countries across the system.
[note] Id; page 10
[note] Id; page 12

There are also systemic challenges to recruitment within the target timeframe. As was noted in the previous annual review, there remain substantial hurdles facing DCO in their efforts to drive progress against this measure, which are difficult to overcome in a short timeframe. For fairness, it should also be noted that many of these lie outside of DCO direct control. For example, proposed RC candidates must be approved by country Governments, which, in certain instances, can cause significant delays to timelines for recruitment due to contextual and political factors.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No changes were made to the substance of these Output Indicators during the past year. As Output 1.1 had seen overachievement in the first year, the target milestone for this reporting period was raised to 93% from 90%.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Expanding the selection pool: In the last reporting year, DCO launched a National Officer Talent Pipeline – a highly competitive year-long career support programme, aimed at deepening professional development of the National Officer cadre. More broadly, DCO has continued pursue efforts to diversify overall Resident Coordinator system staffing, including the founding of a Women Talent Pipeline. The DCO note that the profile of Resident Coordinators has become more diverse, with RCs hailing from a wider range of UN and non-UN professional backgrounds, and in the past year the Resident Coordinator pool has included more women than men for the first time.
[note] Report of the Chair of the United Nations Sustainable Development Group 2023; page 20
[note] Id; page 17-18.

Recruitment Timelines: FCDO should liaise with DCO during the logframe refresh to ensure that this Output Indicator is providing a holistic view of ongoing priorities and issues around recruitment.

Output Title	At country level, set clear guidance with benchmarks to UNCTs on value for money.
Output number:		2	Output Score:	C
Impact weighting (%):		25%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 % of all UN premises that are Common Premises	42%	31% (Underachieved)
2.2 % of UNCTs with a Local Shared Services Centers (LSSCs), formerly Common Back Offices, design business cases approved	6 pilots launched and implications assessed for wider rollout	1 LSSC Complete, 2 Further Pilots Launched (Underachieved)

Briefly describe the output’s activities and provide supporting narrative for the score.

While progress towards targets for creating Local Shared Service Centres (LSSC) is not at the level initially envisaged, clear progress has been made in this reporting period towards the aims of this indicator area. There has been one LSSC that has been fully established in this reporting period, which is now operationalised (located in Nairobi, Kenya). The remaining 5 pilots are at different stages of Development. LSSCs in Brazil and Viet Nam were launched in May 2024, with the centre in Tanzania due for launch in the coming weeks. The initiative in Jordan has been put on hold due to conflict in the region, but is due for review before the end of 2024, with the hope of establishing the office in 2025. The initiative in Senegal has been delayed due to complexities related to the establishment of a large common premises and a prediction for the timescale of establishment is not currently possible.
[note] Id; page 16

The DCO also completed common premises projects in eight countries in during this reporting period. The projects that were completed were in Tanzania (prior to proposed launch of LSSC), Iraq, Morocco, Colombia, Bolivia, Mali, Ethiopia and Antigua and Barbuda. DCO also notes that 43 projects are underway – the largest one in Egypt hosting 2,700 staff from 36 UN entities.
[note] Report of the Chair of the United Nations Sustainable Development Group 2023; page 16

It is worth noting for contextual purposes that progress against these indicators cannot be driven only by DCO at UN level, as bringing in-country UN actors together in shared premises needs widespread buy-in. Indeed, DCO note that legal complexities often challenge efforts to secure common premises and agency efforts can often be complicated. For example, there is sometimes good reason from an efficiency standpoint for costs incurred by agencies breaking lease agreements early to be avoided, although clearly this will often mean a delay to creating common premises or LSSCs. Seed funding is also often required to initiate common premises projects or LSSCs and this is another aspect that has been negatively impacted by the continued funding shortfall.

While, of course, FCDO should still hold DCO to account for progress against this measure, FCDO can also work across the office to ensure that other UN agencies are responding to efforts to increase the number of LSSCs adequately and hold the entire UN accountable for realising the increased value for money that could be achieved by the greater success of this indicator.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No changes were made to the substance of the Outputs during the past year. As Output 2.2 underachieved in the previous reporting period, the target milestone for the output was revised to 6 pilots being launched and implications assessed for wider rollout for this reporting period. Targets for Output 2.1 have remained unchanged.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Common Premises: FCDO continues monitoring progress against the UN’s commitment to move to common premises in highest cost locations. While cognisant that progress continues to be made and that funding constraints are having an impact, FCDO will continue to monitor this indicator closely and use available avenues to raise this with DCO directly throughout the year ahead.

LSSCs Pilots: Early indications and feedback from DCO suggest that the fully operational LSSC in Nairobi has had a successful beginning, despite being very challenging to establish. Valuable lessons have been learned in the creation on the Nairobi office, but ongoing information sharing will be important. DCO should update FCDO on the performance of the established LSSC and those recently launched, as well as the progress towards the establishment of the remaining pilot schemes.

Output Title	Feeds into reform updates across a range of the UN Development System executive boards to engage with the agencies to support rollout, including setting guidance with benchmarks, to the UNDS on value for money and efficiencies.
Output number:		3	Output Score:	B
Impact weighting (%):		25%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1 % of UNDS entities that have updated the job descriptions of UNCT heads to recognise the role of the resident coordinator, as outlined in resolution 72/279 and the MAF	90%	89% (Underachieved - Note: Indicator is under review by DCO)
3.2 % of programme country Governments indicating that funds are “closely aligned” with the country’s development needs and priorities: / 1. core / 2. non-core	1. 80% / 2. 85%	1. 76% (Underachieved) / 2. 70% (Underachieved)
3.3 % of relevant UNSDG members reporting that they complete the reform checklist and / share with their governing body annually	35%	56% (Overachieved)

Briefly describe the output’s activities and provide supporting narrative for the score.

Output Indicator 3.1 has fallen marginally short of target in this reporting period, scoring just 1% short of target. Nevertheless, this represents a substantial uplift from the previous reporting period, when the indicator fell well below target. More broadly, it is worth noting that DCO have informed FCDO that the Management Accountability Framework (MAF) is going under review as DCO feel it needs to be strengthened.

Output Indicator 3.2 has underachieved against targets in the latest reporting period. The percentage of programme country Governments indicating that core funds are “closely aligned” with the country’s development needs and priorities has underachieved by four percentage points, with the non-core indicator falling short by a more substantial margin of 15% points versus target and regressing in comparison to last year. For context, DCO highlight that continued increases in levels of non-core funding will be impacting how “closely aligned” funds can be to priorities, as they feel earmarked funding increases fragmentation of efforts between agencies.

Output Indicator 3.3 has performed very strongly in this reporting period, overachieving by 21% percentage points versus target. However, FCDO will have to monitor progress against this indicator closely through the coming year, as the next target is 100% coverage for reform checklists.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Output indicator 3.3 has been added for this reporting period. This indicator measures the percentage of relevant UNSDG members reporting that they complete the reform checklist and share with their governing body annually. This indicator ensures that there is coverage in the logframe of oversight of and engagement with new DCO reform checklists, which are an important aspect of measuring UNDS executive board efforts and commitment to efficiencies across development work.

Output indicators 3.1 and 3.2 have remained unchanged.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Reform checklist: Last year’s recommendations stated that the FCDO should consider measuring this progress on reform checklists as part of Output 3, which has now been included in the logframe. For the coming year, FCDO should liaise closely and regularly with DCO to ensure that the ambitious target of 100% coverage for 2025 can be achieved.

Job descriptions: DCO should update FCDO on the outcome of the review into the MAF, as mentioned above, and the continued applicability of this indicator should then be considered during the logframe refresh.

Output Title	Quality assure UN Sustainable Development and Cooperation Frameworks (UNSDCFs), and Common Country Analyses (CCAs) in a way that helps ensure that the content targets the most in need, is politically sensitive, brings together humanitarian actors where possible, integrates conflict sensitivity, identifies conflict drivers early on, improves structures to bring agencies together focuses on the UN’s comparative advantages and ensures implementation of the Management and Accountability Framework (MAF) - with consultation from donors.
Output number:		4	Output Score:	B
Impact weighting (%):		25%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
4.1 % of Cooperation Framework Joint Workplans in UN INFO published on the UNSDG data portal	85%	82% (Underachieved)
4.2 % of UN Country Teams that undertake with humanitarian actors, as relevant: / 1. Joint needs analysis / 2. Complementary and joined-up planning	1. 75% / 2. 45%	1. 63% (Underachieved) / 2. 60% (Overachieved)
4.3 % of Common Country Analyses that were updated in the last year	90%	74% (Underachieved)
4.4 % of Common Country Analyses that includes an assessment of barriers faced by those being left behind or at risk of being left behind	94%	89% (Underachieved)
4.5 % of UN Country Teams with results groups (chaired or co-chaired by UNCT heads of agencies)	95%	86% (Underachieved)

Briefly describe the output’s activities and provide supporting narrative for the score.

Progress against Output Indicator 4.1 has been less encouraging than in the previous reporting period. Although positive progress year-on-year is still evident, the score for this year falls three percentage points short of the 85% target that was set.

For the second consecutive year, progress against the two sub-indicators in Output Indicator 4.2 has been mixed. The percentage of UN Country Teams that undertake a joint needs analysis with humanitarian actors is again the concerning aspect, underachieving by 12 percentage points versus target. As has been noted previously, concerns about this indicator are compounded by the fact that this area is very important for programme countries, given it underpins in-country development and humanitarian activity. However, strong encouragement can be taken from the percentage of UN Country Teams that undertake complementary and joined-up planning with humanitarian actors, which has significantly overachieved versus target in this reporting period. FCDO should work with DCO to learn lessons from why the latter sub-indicator is performing so strongly versus targets, and how this positive growth can be replicated in the former sub-indicator.

Output Indicators 4.3 and 4.4 both underachieved in this reporting year versus target. However, while the percentages showing underachievement appear concerning, important contextual points regarding Common Country Analyses (CCA) must be considered when evaluating these scores. For instance, as the CCA is an internal UN document, the CCA may not be publicly available in some sensitive contexts. It is also the case that CCAs in stable country circumstances will often not require yearly updates, as what is contained in them remains entirely valid given the stability of the context to which they apply.

Output Indicator 4.5 was not monitored in the previous reporting period, however it has disappointingly regressed from the level it had reached in the previous set of results published by DCO and has, therefore, underachieved against the ambitious opening target of 95% that was set in the logframe.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

As mentioned above, output indicator 4.5 is newly included in the logframe for this reporting period. It measures the percentage of UN Country Teams with results groups chaired or co-chaired by UNCT heads of agencies.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Joint needs analysis: FCDO raised the need to identify challenges in completing joint needs analyses with DCO in 2023 in response to the recommendations in the previous annual review. FCDO noted also that lessons learned from the success undertaking of complementary and joined-up planning should be applied, where possible, to the joint needs analysis. This aspect will continue to be raised with DCO in the forthcoming reporting period, in response to the repeated mixed results.

Results Groups: FCDO should work with DCO to establish the reason for regression in the percentage of UN Country Teams with results groups (chaired or co-chaired by UNCT heads of agencies) and encourage DCO to target efforts at communicating the need for these to UN Country Teams.
## D: VALUE FOR MONEY

Key cost drivers and performance

VfM performance compared to the original VfM proposition in the business case

Economy
The DCO aims to promote economic improvements by reforming the UN Development System through a range of different means, including operational efficiencies and sharing premises.
As was the case in previous years. the primary cost driver for the RC System in 2023 was the budget for post-related costs. According to DCO figures, 63% (or $177 million) of the $281 million budget was allocated for this purpose. In relation to the actual expenditure undertaken, $123.9 million went towards RCs and their office staff. At country level, there was a total of 1,149 core posts, which includes the total of 130 RCs. There was also expenditure at a regional level, where a total of 41 core posts in the DCO regional teams were funded, in addition to the 83 core ‘global’ posts funded in the New York-based DCO team.
[note] All figures from Annex 1, Report of the Chair of the United Nations Sustainable Development Group 2023
Expenditure on non-post costs accounted for the remaining 37% of the budget in 2023. Again, according to DCO Official figures, this included ‘operating expenses (12.3%), contractual services (9.7%), consultants (7.2%), other staff costs (1%), travel (4.1%), supplies (0.7%), hospitality (0.5%) furniture and equipment (1.6%)’.
[note] Ibid
Efficiency

Results for 2023 again saw a strong focus from the DCO on efficiency and the system-wide savings that were made demonstrate continued high performance in this area for the programme. As mentioned above, $553m was accrued in terms of system-wide savings against a target of $270m, which builds further on the positive figures reported in the previous annual report. Though greater progress on areas such as Local Shared Service Centres is needed, the FCDO will continue to work closely with DCO to continue these positive results and drive further efficiencies.
Effectiveness
The programme has scored relatively well at Impact level, especially in response to substantially upgraded targets given promising Year 1 performance. Although several Impact Indicator measures fell slightly short of targets, the overall picture shows the RC System demonstrating steady progress in a number of key priority areas. While there has been clear evidence of underperformance in some areas at Outcome and Output level, positive improvements continue to be visible in a year-on-year context. The areas where levels have dropped in 2023 are of course concerning and these have been an area of particular focus in this annual review and related discussions with the DCO, with a number of recommendations having been made to drive further progress against specific indicators in the year ahead.

Equity
An overarching objective of the work of the RC in-country is to advance efforts to ‘leave no one behind’, and their coordination efforts across the activities of UNDS actors in-country also directly enhances wider efforts supported by FCDO on this objective. Indeed, alongside their key role in ensuring development work is consistent with the integrated nature of the 2030 Agenda, DCO highlight that, “the 2023 OIOS evaluation found that Resident Coordinators supported the advancement of human rights and efforts to leave no-one behind for sustainable development in national policymaking dialogue.” Continued UK funding for the RC System underlines a commitment to equity across the entirety of the UN Development System.
[note] Report of the Chair of the United Nations Sustainable Development Group 2023; page 8

Assessment of whether the programme continues to represent value for money

While results against targets for this reporting year have been disappointing in many areas, there is still a strong case that the programme represents value for money for FCDO.

The Resident Coordinator System continues to sit at the heart of UN Reforms, underpinning much of the work that is done in the UN Development System and helps to ensure that the totality of UK spending on UN Agencies for development is better coordinated. As one of the key contributors to the RC System, strong levels of funding helps the UK stand steadfastly behind reform efforts and demonstrates UK commitment to improving key operational aspects of the UNDS, such as those covered in the Impact Indicators.

Performance against key financial indicators also continues to be positive and the considerable overachievement against savings targets in Outcome Indicator 1 stand as testament to the potential for the changes brought about by the system to greatly improve system-wide efficiency and value for money. Moreover, with over 80% of programme country Governments reporting that RCs have strengthened in each sub-indicator in Impact Indicator 1 since the implementation of the new RC system in 2019, we must consider UK funding to have been a significant enabler in each of these measures, with each being capable of delivering considerable value for money improvements across the UNDS.

E: RISK

The Risk Register covers the risks associated with the programme and each risk is regularly reviewed by the programme PRO on a quarterly basis, with a detailed discussion alongside the SRO and close colleagues on the Risk Register at each programme board (held twice a year). The most recent programme board was held in July 2024.

Of the nine identified risks that are currently covered by the Risk Register, only one lies outside the risk appetite set by FCDO for the programme. The outlying risk is the ‘risk of a critical mass of other Member States not providing funding to the SPTF’, which remains rated ‘severe’, as it was in the previous annual review. As discussed in the analysis of many indicators in this review, the impact of the funding gap for voluntary contributions continues to be felt by the DCO and is reflected in the performance of many areas of the programme.

The FCDO continues to be proactive in its attempts to mitigate this risk and has built on previous efforts of encouraging other donors to provide more funding by being strong supporters of the UN Secretary General’s proposal to reform the way the RC System is funded. Efforts are continuing across FCDO to advance this mitigation strategy and work is also ongoing with likeminded states, with whom thinking is shared on how best to ensure a positive outcome. In relation to the support of the UN Secretary General’s proposals, further formal submissions to this end are expected in the remainder of 2024 and efforts will continue to be focused on finding consensus to ensure future funding for the RC System is sustainable.

Of the other eight risks, three are under the ‘Policy & Programme Delivery’ risk category, two are ‘Strategy and Context’, with ‘Safeguarding’, ‘Financial & Fiduciary’ and ‘People’ making up the remaining three. As outlined above, each of these risks remains within FCDO risk appetite and all risks are reviewed by the PRO throughout the year, with wider oversight from SRO and colleagues undertaken at Programme Boards.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

Annual reporting on the performance of the RC system is primarily provided by DCO as part of the Operational Activities for Development Segment. This event, and the associated documentation that accompanies it, includes financial reporting. Though there have been informal sessions in this reporting year focused on funding for the RC System (which have also, at times, touched on system financial performance and oversight), the Operational Activities for Development Segment remains the only formal mechanism for donors like FCDO to discuss progress on the reforms and system performance.
[note] Annex I - Overview of resources of the Resident Coordinator system special purpose trust fund; Report of the Chair of the United Nations Sustainable Development Group 2023

Biannual Programme Board meetings are the primary avenue through which FCDO internally reviews progress, risk and priorities related to the DCO programme. Throughout the year, FCDO also liaises with DCO in formal and informal discussions (including during the annual review process and where opportunities arise) about progress on value for money, system effectiveness and other key priorities, including areas covered in the logframe. FCDO also has internal budgeting and financial forecasting processes, which are complete for this programme.

Following on from recommendations in the previous Annual Review, the FCDO have sought to ensure DCO make efforts to strengthen its governance model. It remains the case that, ideally, this would be achieved through more regular structured dialogue with the top donors to the SPTF, should the funding model remain as it is. However, FCDO has also made clear that the potential for a new funding model along the lines of the one proposed by the UN Secretary General can represent a great opportunity to implement a more structured dialogue with member states on key priorities.

FCDO should continue to press for improvements in RC System governance and oversight in the coming year, using all avenues available to push for increased opportunities for UN-Member State dialogue. This should also be a primary consideration in all FCDO efforts to support reform of the funding model for the RC System more broadly, as regular, structured dialogue is a crucial accompaniment to sustainable funding in ensuring the system is successful.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation

The annual review process has been completed by the PRO. Input has also been sought from DCO who have provided background information and reasoning for some of the scores, and comments have been collected from colleagues who have covered broad areas of engagement with DCO throughout the year. PRO also discussed areas of challenge with DCO, covering the breadth of the programme indicators and with particular focus on areas that have not met logframe targets for the reporting period.

In relation to in-year engagement and monitoring, FCDO engaged with Assistant Secretary-General for DCO, Oscar Fernandez-Taranco, to discuss progress on the reforms. The ECOSOC Operational Activities for Development Segment also provided an opportunity to have a more in-depth discussion on the reforms, including with RCs themselves and UNDS agency Executive Heads.

Evidence

The sources of evidence used to illustrate progress against the indicators in the logframe are from the DCO’s own Results Framework and the UN’s QCPR Monitoring and Reporting framework. These have not been changed from the previous annual review. The data that is gathered in compiling each of these is often based on reports from UN Country Teams and Governments that host a Resident Coordinator in-country, as well as objective statistics (eg. recruitment timelines, number of LSSCs, etc.). These sources of evidence are clearly important and represent the views of closely attuned stakeholders in the RC System. This also ensures that data is gathered from all areas globally where the RC System is operational. Nevertheless, as has been mentioned at points throughout the report, consideration must be given to the fact that year-on-year fluctuation can often be attributed to factors that are not captured in the data, so a focus on longer term trajectories remains important.
[note] Annex II – Resident Coordinator system Results Framework; Report of the Chair of the United Nations Sustainable Development Group 2023
[note] UN ECOSOC 2024 Secretary-General’s report on the implementation of the QCPR. Available at: 2024 Secretary-General’s report on the implementation of the QCPR | Economic and Social Council

Learning

Lessons learned from the operation of the programme in the past year include a deeper understanding of the breadth of impact that the continued funding gap has on a range of indicators; the complexities (both legal and political) involved in driving progress against indicators; and, from an internal FCDO viewpoint, the need to encourage relationship building between post teams and Resident Coordinators in-country, to help better inform our approach to pursuing changes to the RC System.

To build on the latter learning point, in the year ahead it is important that FCDO uses our global network to better understand the critical issues facing RC offices in programme countries (including issues not covered by logframe indicators) to construct a stronger knowledge base on areas within the system we should seek to strengthen or reform. This can also be used to provide a stronger understanding of individual cases where the RC system is not working as intended. Work in this area is underway and FCDO will use this to help inform positions in upcoming negotiations on RC System funding and UNDS mandate renewal. FCDO should also seek to share important information gained from such exercises with the DCO outside of these negotiations through the year ahead.

Date of last narrative financial report	May 2024	Date of last audited annual statement	May 2024