Programme Completion Review
Title: Support to establish an International Finance Facility for Education (IFFEd)
Final Programme Spend £ (full life): £745,000	Review Date:	November 2023
Programme Code: 301584	Start Date: 01/04/2022	End Date: / 31/03/2023

Summary of Programme Performance
Year	FY22/23
Programme Score	A
Residual Risk Exposure Rating	No residual risk

DevTracker Link to Business Case (and any addendum):	D0003257.odt (live.com)
DevTracker Links to all logframes used during programme lifetime:	D0003427.xlsx (live.com)

A. Summary and Overview

Description of the programme and what it has achieved

This programme supported the Foreign Secretary’s objective to deliver ambitious and innovative financing for girls’ education as a high UK and global priority. The programme helped set up the International Finance Facility for Education (IFFEd), an innovative financing mechanism that uses sovereign guarantees and grants to unlock seven times the scale of funding invested. This will then provide new and affordable education loans to Lower Middle-Income Countries (LMICs) through the Multilateral Development Banks (MDBs). The programme provided seed funding to enable IFFEd to establish itself as a new independent legal entity.

IFFEd will focus on LMICs because most of the world’s children in learning poverty live in LMICs. But LMICs are unable to access grant financing for education at the scale required. LMICs are not able to fund their significant education needs through domestic resources and are unwilling to borrow for education at the rates available to them through the Multilateral Development Banks. IFFEd will buy down the cost of loans, through the use of grant funding, making education loans more affordable to LMICs.

This programme provided £750,000 during the start-up phase of IFFEd to help establish the institutional and operational foundations for a successful launch in FY23/24. Out of £750,000, £720,000 was provided to the Education Commission to fund the following programme outputs (The remaining £30,000 was used for external legal advice):
- Establish IFFEd as an independent foundation.
- Support the development of IFFEd’s finance systems and legal framework.
- Secure additional sovereign donors.

The intended outcome of building IFFEd’s institutional foundations was largely achieved. Of the three outputs, one was completely achieved and two were largely achieved. This programme’s funding supported, drafting institutional and legal documents, establishing interim governance structure, starting engagement with the credit rating agencies with a view to obtaining the AAA rating, and establishing the internal financial, management and M&E systems.

The programme also supported IFFEd business development and resource mobilisation, including a new investment case to reflect the new, smaller start-up model preferred by donors and the Education Commission.

Finally, the programme supported branding and communications, to build IFFEd’s influence and brand, to encourage others to contribute. This includes website construction, public campaigning, and IFFEd participation at global fora.

The two top risks were insufficient support from other donors and donor grant and guarantee commitments that were too low. One medium risk was that IFFEd struggled to cover its operating costs. These risks were mitigated through the seed funding. The seed funding ensured that the governance structures and processes were appropriately designed, essential for attracting donors, and the legal advice was provided to seek the AAA rating. The funding covered 40% of IFFEd’s operating costs and unlocked matched funding from the philanthropic Atlassian Foundation and Jacobs Foundation.

Major lessons learned, evidence generated and recommendations

IFFEd benefited from lessons learned and evidence gathered from its inability to launch in 2019. This included reviewing IFFEd’s initial launch goals and reducing the level of ambition. The initial target was to unlock $5bn but this was reduced to $1bn. IFFEd decided to take a gradual approach to increasing the size of the instrument, with a goal to unlock $10bn by 2030.

The main lesson is that a relatively small amount of grant funding can catalyse the establishment of a major new financial instrument designed to address a major gap in the international education finance architecture. Without the FCDO’s seed funding (and the UK’s political commitment to IFFEd), it might have failed to launch again (or at all). The UK remains, the lead donor to making IFFEd a reality. This programme demonstrates how the UK is able to deploy small grants to good effect.

How this report was conducted

This report was conducted following a desk review of:
- The programme’s business case.
- Quarterly monitoring reports provided by IFFEd over the duration of the programme.
- IFFEd workplan.
- Progress updates from the IFFEd team.
- Other core programming documents including the programme logframe and risk mapping assessment.

Actions following approval of this report

It will be important to ensure continued support until IFFEd financing instrument becomes operational. This will be achieved by continued seed funding (an additional £250k has been allocated in December 2023). Close engagement with the IFFEd team and other contributors to ensure collaboration on governance arrangements including the Board nomination, results framework, and guidelines for operationalisation of the fund will be necessary. Continued UK political support will remain essential.

## B: Theory of Change and Outcome Assessment

	Starting point	Final result
Budget	£750,000	£745,000
Timeframe	April 2022 to March 2023	April 2022 to March 2023
Outcomes	Build IFFEd’s institutional foundations and business development to enable a successful launch in FY23/24.	The outcome was largely achieved. Of the three outputs, one was completely achieved and two were largely achieved (see section C on outputs).

Overall assessment of programme outcomes, sustainability and VfM

The outcome of building IFFEd’s institutional foundations and business development was largely achieved. The assessment of programme outputs is covered in section C.

This programme was essential to develop the institutional foundations of IFFEd. It focused on developing the required conditions of effectiveness for IFFEd to be able to launch in FY23/24. Conditions of effectiveness included:
Establishing IFFEd as an independent entity with an international organisation status.
Engagement with the credit rating agencies and obtaining an AAA rating.
Drafting the legal documents and establishing a robust financial model.
Securing a minimum of three donors.

The programme delivered those outcomes that were achievable within the timeframe of the programme. Some elements of the outcomes listed in the programme’s logframe will be delivered after the end of this programme. This will be part of the main IFFEd programme:

- Outreach and lobbying of donors and philanthropies.
- Obtaining the AAA credit rating (by the end of FY23/24).
- Setting up the permanent board and recruiting the new CEO and Board Chair.

This seed funding contribution, in combination with funding from philanthropies, delivered IFFEd's registration as a Swiss international organisation. This provided the IFFEd Secretariat with immunities and privileges, including tax-free status and staff visas.

This programme also ensured the smooth transition from the Education Commission (which itself was hosted by Rockefeller Philanthropy Advisors) to IFFEd as an independent legal entity, thus contributing to the programme’s sustainability.

Value for Money

The VfM of this programme is assessed as excellent. The programme largely delivered its outcome and outputs. A relatively small amount of grant money (£750,000) allowed IFFEd to undertake the fundamental work to ready itself to start operations by the end of FY23/24. Without this seed funding, IFFEd would have stalled until its operational cost needs had been addressed. This would have delayed set up and securing the minimum of three donors. IFFEd would have failed to launch yet again, jeopardising the credibility of the entire project and creating the risk that IFFEd would not be established at all. This in turn would have meant the failure of establishing an instrument designed to address a major gap in the education financing architecture (i.e. affordable education finance for LMICs). A lack of financial commitment by donors would also have made a bad impression with the credit rating agencies. In short, not providing the seed funding under this programme would have represented very poor potential VfM.

The £750,000 was a very small share of the UK’s bilateral expenditure on girls’ education. Given the Foreign Secretary’s steer to reinstate funding for Women and Girls to FY20/21 levels, funding IFFEd’s start-up costs delivered high value at a small cost. The seed funds provided by the FCDO represented 40% of IFFEd’s year 1 costs. The FCDO contribution also unlocked match-funding from the Atlassian Foundation and the Jacob’s Foundation.

Following the success of this programme, the FCDO was able to draft a business case for the main IFFEd programme, for up to £180m (including a guarantee of £100m and a grant contribution of up to £80m). The latter was approved by Ministers in September 2023.

Summarise the programme’s theory of change and results framework, including any changes to outcome indicators.

The programme did not have a separate theory of change because of its small size. However, it was designed to fit within the wider IFFEd theory of change.

IFFEd’s theory of change is summarised in table 1. This programme focused on the establishment of IFFEd input. This will pave the way for the delivery of the rest of the results chain: unlocking $1bn in new, additional, affordable education loans for LMICs (the IFFEd output); improving literacy and numeracy in LMICs (the IFFEd outcome); and contributing to progress on SDG4 (the IFFEd impact).

The delivery of the theory of change IFFEd input, is essential to disburse the UK £180m contribution, which in turn is essential to launch a start-up guarantee of $250m (with two other donors). These outcomes combined are required to unlock $1bn in affordable education finance for LMICs. Further, we expect the IFFEd launch to have a demonstration effect on other donors, thus unlocking further donor contributions, increasing the size of the IFFEd guarantee and unlocking up to $10bn in the next five years. This goal would make IFFEd the largest new financing instrument in the education finance architecture.

Table 1: Theory of Change and VfM measures
Theory of change		VFM level	VFM measures
Input	IFFEd establishment and activities	Economy	Operating costs and financial self-sufficiency / Cost to the UK of supporting the Contingent Financing Window
Output	Total volume of additional finance delivered and how this finance demonstrates additionality	Efficiency	Multiplier ratio on portfolio support delivered by the MDBs / Unlocking ratio on paid-in cash and grants / Range of grant element used in IFFEd-supported projects
Outcome	Expected education results of the additional financing supported by IFFEd	Effectiveness	Education results supported by IFFEd compared to the wider education portfolios of the MDBs / Targeting of IFFEd support / Co-ordination of education financing
Impact	Contribute internationally agreed indicators for SDG 4, with a particular emphasis on the indicators for 4.1.1 and 4.5.1.	Equity	Proportion of projects with an explicit focus on marginalised children and youth / Proportion of projects with disaggregated data, including by gender and disability

The IFFEd theory of change is underpinned by the following assumptions, which were either realised, or remain valid:
- Continued UK political support for IFFEd (realised: ministerial approval obtained for main £180m IFFEd programme).
- UK ODA budget for IFFEd's long-term operations is available (realised).
- Ongoing political support from other donors (realised).
- Support from UNSG through the Transforming Education Summit (realised).
- Continued engagement and willingness to participate in IFFEd from MDBs (Asian and African Development Banks) (realised).
- Assessment of continued appetite from LMICs to borrow for education at concessional rates (to be tested in FY24/25 when IFFEd starts extending guarantees).
- Seed funding from other sources is secured (partially realised but fundraising efforts continue).

## C: Detailed Output Assessment

Output Number and Title		Output 1: Establish IFFEd as a Swiss foundation / Output 2: Develop critical institutional foundations to operationalise IFFEd / Output 3: Secure additional donor partners to unlock UK commitment and proceed to full operationalisation of IFFED
Output Score		A
Impact weighting (%)		N/A	Impact weighting revised since last AR?	N/A
Table 2: Results Framework
Output Indicator	Starting Target		Final Logframe Target	Final Result Achieved
Objective	Baseline / (July 2022)		Endline: Output/Outcome / (end June 2023)	Objective
Output 1: establish IFFEd as a Swiss foundation	IFFEd is a project within the Education Commission		IFFEd completes registration as a Swiss Foundation / IFFEd has appointed a Founding CEO and initial team members / IFFEd’s Interim Governance structure (including IFFEd Interim Board) is fully operational. / IFFEd’s long-term governance structure has been designed and agreed by partners / IFFEd’s long term governance structure is being implemented / Application for International Institution Status is submitted/ under review	Output 1 MOSTLY ACHIEVED: / Achieved: IFFEd is registered as a Swiss Foundation. / In progress: CEO being recruited. / Achieved: interim governance structure fully operational. / In progress: long-term governance structure in process of being designed and agreed. / Achieved: application for international institution status under review.
Output 2: develop critical institutional foundations to operationalise IFFEd	Operational model per 2018-2019 negotiations / Draft legal documents and financial documents in place, based on 2018-2019 negotiations / IFFEd does not have a Trustee		Key parameters of IFFEd’s operational and financial model are agreed with partners (e.g. eligibility criteria, guarantee fees etc.) / IFFEd’s Legal documents and financial model are agreed by donor and MDB partners / Trustee model is agreed, and Trustee is finalised / IFFEd’s financial systems and processes are established to enable transfer of donor resources	Output 2 MOSTLY ACHIEVED: / Mostly achieved: most parameters of the operational and financial model agreed. Sub-sector allocation of resources yet to be achieved. / Achieved: legal documents and financial model agreed. / Almost achieved: selection process completed with clear recommendation / Achieved: financial systems and processes established.
Output 3: secure additional donor partners to unlock UK commitment and proceed to full operationalisation of IFFED	Two additional donors (Netherlands and Sweden) are progressing in approval process / Outreach to other donor countries and non-sovereign entities in process.		Approvals are complete and funding agreements are for 2 additional donors across the guarantee and grant windows (Canada and Sweden) / Additional sovereign donors reviewing IFFEd contribution / Evidence of outreach to philanthropic donors.	Output 3 ACHIEVED: / Achieved: two additional donors committed funding: Sweden a contingent guarantee (publicly announced and signed) and Canada paid-in capital (to be announced and disbursed in FY23/24). / Achieved: outreach to several philanthropies.

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score.

Output 1 – Establish IFFEd as a Swiss Foundation: MOSTLY ACHIEVED.

Registration of IFFEd as an independent organisation was completed on 7 March 2023. An interim governance structure was implemented through the development of an Interim Board which meets regularly to steer IFFEd’s through its establishment. The long-term governance structure was agreed by the Interim Board and fully approved just after the end of this programme.

Two activities were not fully achieved due to lengthy approval processes, but good progress has been achieved with targets expected to be completed by the end of FY23/24. This includes the appointment of an IFFEd CEO and establishment of the long-term board.

Output 2 – Develop IFFEd’s institutional foundations: MOSTLY ACHIEVED

Most parameters of the operational and financial model were agreed. The sub-sector allocation of resources is yet to be agreed.

The legal documents and financial model were agreed by donor and MDB partners.

The selection process for the commercial trustee was completed with a clear recommendation. ToRs drafted and discussions ongoing with three potential finance and back-office providers.

Financial systems and processes have been established.

Output 3 – Secure additional sovereign donors to unlock the UK’s contribution and allow IFFEd to operationalise with the required minimum of 3 donors: ACHIEVED

The UK obtained internal approval of IFFEd and announced its contribution at UNGA, together with Sweden.

Ongoing lobbying by IFFEd and the UK to bring more donors on board. Several countries are reviewing potential commitments.

By the end of this programme, IFFEd had two confirmed donors and was in a good position to attract a third donors, which was achieved by Canada joining after the end of this programme. The programme thus delivered the essential need to secure a minimum of three donors, one of its conditions of effectiveness.

Outreach to philanthropies was also successful, with additional seed funding provided by the Atlassian Foundation and Jacobs Foundation. Work is in progress to secure funding from additional philanthropies.

Lessons learned through outputs, and recommendations for future programming

Programme delivery was effective for the following reasons:
  - Effective collaboration between FCDO, IFFEd, MDBs and philanthropies was essential to the establishment of IFFEd.
  - Flexibility in programme design allowed IFFEd to respond to priorities as needed.
  - Building on activities delivered in previous years ensured realism and built a solid foundation for IFFEd, capturing lessons learned and delivering against an existing baseline.
  - Starting processes early, such as engaging credit rating agencies, was necessary and allowed for maximum use of the limited timeframe of the programme, ensuring targets were largely achieved by the end of the programme.

IFFEd is at an early stage and not yet operational. Therefore, it is difficult to provide recommendations at this stage. However, monitoring and evaluation is a core part of the main IFFEd programme, with a Results Framework being developed.

D: Value for Money

 VfM performance compared to the original VfM proposition in the business case.

This programme delivered excellent VfM by supporting the VfM of the main IFFEd programme:

Category	Performance indicator/example of best practice
Economy	IFFEd is a lean model, utilising the existing systems in place from other MDBs rather than setting up parallel structures. As such, its operating costs are limited to its trustee functions and those of a small secretariat. While £750,000 is a significant sum of money, this represents just 0.05% of the funds that IFFEd seeks to mobilise. Key cost drivers are staff and administrative costs, financial management costs, and incurring losses under the portfolio support to MDBs. The IFFEd financial model provides a preliminary set of benchmarks against which actual costs can be compared. Under business-as-usual assumptions, IFFEd would start to show positive net income in time for the first replenishment period (2022-2025), covering its costs.
Efficiency	IFFEd has already demonstrated its ability to raise additional finance beyond core donor resources. This has come about through grant-match funding from the Atlassian Foundation and pro bono support from TheirWorld on branding. This builds on existing in-kind contributions that have been received on legal advice, from Reed Smith, and on hosting from the Swiss government. The sunk costs that went into IFFEd’s previous launch attempts means that they can build upon existing outputs, rather than start from scratch, again lowering the input-to-output costs.
Effectiveness	Under current projections, IFFEd aims to mobilise $1bn of additional finance of ODA loans to LMICs. This is the current sum of all MDB lending to LMICs for education projects. This will go a significant way to addressing the problem set out in the Strategic Case and builds a demonstration effect for future ODA finance in the future.
Equity	Under the framework agreement, strong criteria will be developed for grant eligibility. For traditional MDB projects to benefit from additional grant resources they will need to demonstrate that there is an explicit focus on marginalised children and youth above and beyond what would have happened in the absence of grants.

E: Risk

Overview of programme risk during the past year and over the life of the programme, drawing on FCDO’s Risk Management Policy and Risk Appetite Statement and wider risk guidance.

When approved, the risk rating for the programme was assessed as moderate. There were no changes to the overall assessment of risks throughout the programme and it was delivered in line with its risk appetite. Risks were monitored in four areas through regular fortnightly meetings as well as technical working groups: legal, finance, education and philanthropic engagement.

The overall net programme risk is judged to have remained moderate, within FCDO’s risk appetite.

The principal risk was IFFEd failing to become operational despite seed funding support and insufficient donor finance. This risk was assessed as worth taking.

Financial risk was and remained minor throughout this programme.

F: Programme Management: Commercial and Financial Performance, Monitoring and Evaluation

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including VfM measures of economy and efficiency.

FCDO managed the IFFEd programme through several mechanisms; including tracking of the workplan, programme budget and disbursement tracking; quarterly programme meetings and reviews; quarterly spending utilisation reviews; and quarterly reviews of the Risk Register. Programme management on both sides (FCDO and IFFEd) was delivered smoothly. Internally the programme was managed by an experienced Grade 7 Economics Adviser and Grade 6 Senior Responsible Officer with substantial experience delivering programming addressing UK priorities on education. The IFFEd secretariat was managed by a small team of experienced staff with experience working on innovative financing structures, working with MDBs and other key stakeholders to deliver this.

Date of last narrative financial report	29/03/2023	Date of last audited annual statement	TBC

Financial management and Value for Money

The Accountable Grant Agreement with IFFEd was executed through sound professional and commercial management practice. Funds were always closely monitored by FCDO during programme implementation. By the end of the programme, FCDO funds disbursed to IFFEd, and external legal advisory services, were mostly used, with a marginal underspend of £5,000. IFFEd’s costs were primarily made up of administration costs (staff costs, travel, operational and administrative costs), payments for the services of the trustee, accounting, legal support and credit rating agency costs.

VfM of this programme was good as the outcome was delivered. This means that the seed funding provided under this programme was a sound financial investment (see section D on VfM). A relatively small grant contribution of £750,000 achieved the significant outcome of allowing the establishment of a large new international organisation. In the long term this will significantly contribute to progress towards SDG4 by allowing more children in LMICs to access quality education and stay in education for longer.

IFFEd’s efficiency over the programme’s lifecycle also improved, and it secured additional funding from philanthropies. This is a positive step for IFFEd in its early establishment phase and shows its ability to obtain funding on its own.

Programme-level approach to monitoring and evaluation

The programme was monitored through regular meetings with IFFEd. IFFEd remained on track in delivering the outcome and outputs of this programme. Overall the programme has been successful and delivered good VfM demonstrating excellent use of FCDO’s grant contribution.

Annex: Risk Register for IFFEd

	Risk	Probability	Impact	Mitigation
1	Insufficient support from other donors to make IFFEd fully operational	High	High	A minimum of three donors is needed for the facility to launch and these are not yet secured. FCDO’s engagement with donors at senior level will be a key mitigating action and seed funding will enable greater mobilisation efforts and strengthen the case for the mechanism.
2	Donor commitments to grants are too low	High	High	So far only the UK has signalled a contribution to the grant window at a level that is only enough to buy down $750m of loans, compared to IFFEd’s $2bn ambition. It is currently unclear where future grants will come from. Again, UK advocacy with other state and private donors will be a key mitigation of this risk.
3	Donor contributions to guarantee window are too low	Medium	High	Given the scaling ambitions of AsDB in the first few years, it appears that donors have already signalled sufficient commitments for these plans under current leverage ratios.
6	Significant and sustained increased non-accrual rates across the MDBs	Low	Medium	Proactively monitor the risk alongside the IFFEd Secretariat and MDBs. IFFEd’s strong capitalisation is designed to mitigate this risk but high interest rates and debt levels put us in uncertain territory.
7	IFFEd struggles to cover its own operational costs	Medium	Low	A high interest rate environment lowers the risk as IFFEd covers operational costs from interest on grants and guarantees held.
8	IFFEd becomes an Asia-only facility	High	Medium	Even if AfDB capacity issues were relieved, debt levels would prohibit many African countries from benefitting from non-concessional finance. World Bank engagement also appears unlikely in the short term.