Programme Completion Review

Title: Humanitarian Grain Shipments from Ukraine to Countries Suffering Famine
Final Programme Spend £ (full life): 8,000,000	Review Date: August 2024
Programme Code: [AMP ID#] 400010	AMP start date: 15 February 2023	AMP end date: / 14 May 2024

Summary of Programme Performance

Year	2024
Programme Score	A
Residual Risk Exposure Rating	Moderate

DevTracker Link to Business Case (and any addendum):	https://iati.fcdo.gov.uk/iati_documents/D0003465.odt
DevTracker Links to all log frames used during programme lifetime:	https://devtracker.fcdo.gov.uk/programme/GB-GOV-1-400010/documents

A. Summary and Overview

Summary
The Humanitarian Grain Shipments from Ukraine to Countries Suffering Famine programme was a multi-donor effort that facilitated humanitarian grain shipments from Ukraine to countries suffering food shortages and famine. It was delivered from February 2023 to May 2024. The programme was context driven, responding to a call from President Zelenskyy of Ukraine, in his speech to the G20 in November 2022, for the international community to mark the 90th anniversary of the Holodomor famine by supporting his “Grain from Ukraine” initiative and send Ukrainian grain to the poorest countries of the world. UK support for the programme contributed to the achievement of the FCDO’s goal of enhancing the UK’s position as a principled humanitarian donor, as well as delivering on the then Foreign Secretary’s priority of providing a show of support for Ukraine, through the humanitarian funding route.

The programme’s intended outcome was to allow refugees and asylum seekers living in camps and settlements, and populations affected by natural and human-caused disasters, access to adequate food to meet their food and nutrition needs throughout the year. Solid progress was made towards delivering this outcome and the programme had a positive humanitarian impact on vulnerable people in need in the targeted regions. Contributions from the UK and other donors enabled the United Nations’ World Food Programme (WFP) to procure 50,000 metric tons of wheat from Ukraine. This has provided life-saving food assistance to approximately 820,670 vulnerable people in Kenya and around 840,517 people in need in Nigeria (from May 2024 provisional results from WFP Nigeria).

Overview
In February 2023, the UK responded to a call from WFP and contributed £5m to the Grain from Ukraine initiative. Total contributions from the UK and other donors was $21.45m (approx. £16.76m). Kenya was selected because the 2023 Horn of Africa drought had significantly impacted Kenya, with 4.4 million individuals experiencing acute food insecurity and approximately 1.1 million women and children facing acute malnutrition. Refugee arrivals had increased by 13% compared to June 2022, pushing the national refugee population to above 700,000, further straining resources and elevating food security needs. To navigate this complex humanitarian landscape, WFP Kenya adapted its activities to enhance food security for 2.2 million people including through Grain from Ukraine. It scaled up its relief programme across 15 arid and semi-arid counties in Kenya, in response to the drought crisis. WFP procured an initial shipment of 25,000 metric tons of wheat from Ukraine with the contributions from donors which provided life-saving food assistance to approximately 820,670 vulnerable people in Kenya, including refugees in the arid and drought affected counties. The wheat also helped address food gaps and protect livelihoods. Lifesaving food assistance, including nutrition support, was provided to women and children to treat and prevent acute malnutrition and a safety net provided for drought-affected smallholder farmers. As part of their wider response, WFP provided cash transfers, in-kind food assistance, specialised and fortified nutrition commodities and capacity-building initiatives. This comprehensive response, supported by effective coordination, partnerships and rapid resource mobilisation, helped those most in need access minimum food and nutrition requirements.

In September 2023, the UK made a further £3m contribution, alongside Canada, Denmark, Finland, Republic of Korea, Luxembourg, Norway, and Sweden, raising $27.7m (circa £21.64m) which WFP used to procure an additional 25,000 metric tons of wheat to meet the needs of an estimated 613,000 people in need in Nigeria.

Northeast (NE) Nigeria was targeted because in early 2022, it faced a risk of famine with 8.4 million people needing humanitarian assistance. 4.1 million were estimated to be suffering from crisis and emergency levels of acute food insecurity, including 1.75 million children, who were expected to be malnourished. Delivery of humanitarian assistance in the Northeast was challenging as Internally Displaced Peoples camps (IDPs) in Borno State had been moved to rural areas, or elsewhere in Maiduguri, Borno’s capital. This had caused highly vulnerable people to move into more insecure locations, some of which were not accessible to humanitarian staff because of high levels of insecurity. It also risked exacerbating food insecurity and immune deficiencies that drive malnutrition, particularly for young children and pregnant/lactating women. This combined with rising food and fuel prices, meant millions had limited access to basic services and income generating opportunities, and were dependent on humanitarian assistance for lifesaving or sustaining sustenance.

The Humanitarian Grain Shipments from Ukraine to countries suffering famine programme has met the target for its outputs during its lifetime and scores an A.
This Programme Completion Review (PCR) scores the Grain from Ukraine Programme an A for delivering its key output in Kenya and Nigeria of ensuring that ‘Counties in drought-stricken areas have improved capacity to deliver food and nutritional services’. The total number of vulnerable people who benefitted from this programme that is attributable to UK funding are 275,580 in Kenya () and 98,016 in Nigeria based on provisional resultsby end of May 2024. Distribution operations in Nigeria are on-going with 13,893 metric tons distributed and an estimated 185,167 more beneficiaries expected to have been reached by October 2024.

The A score reflects the final results from Kenya and the provisional results from Nigeria. Reports and analysis of the distribution and impact on vulnerable people in Nigeria will be included in the WFP Nigeria’s 2024 Annual Country Report, when published. Lessons learnt to date are captured from the WFP Kenya’s Annual Report 2023.
[note] docs.wfp.org/api/documents/WFP-0000157727/download/

Major lessons learned, evidence generated and recommendations
UK support for this programme was provided because funding this initiative delivered against the then Foreign Secretary’s lead priority of supporting Ukraine as well as meeting urgent humanitarian needs. The initiative had a positive humanitarian impact in Kenya and Nigeria. Supporting the initiative increased UK funding to approximately £156m being provided for humanitarian crises in East Africa in financial year 22/23. The contribution in Nigeria adds to FCDO’s existing humanitarian programmes operating in that region, aligns with UK leadership on the development of the Famine Prevention Compact and highlights the increasing need to increase food production in vulnerable countries.

Summary of Recommendation captured in Section C
Recommendation: Design and implementation of any similar programme should set out and agree the operational expectations for both FCDO and any similar implementing partner, like WFP on, for example, how reporting on the distribution of grain will occur; how donor attribution will be done; how methods for calculation beneficiaries will be considered, to help promote clarity for audit and reporting purposes and help aid institutional memory.

How this report was conducted
This PCR was produced following a desk review of key project documents, including the business case, logical framework and annual reports on distribution from the programme’s implementer, the WFP. Additional inputs were provided by the Senior Programme Manager, PRO and Programme Management Team and Advisers in Kenya and Nigeria.

Actions following approval of this report
The approved Programme Completion Review (PCR) will be published. Lessons and learning from it will be shared with internal and external stakeholders to help inform the design and delivery of similar programmes.

## B: Theory of Change and Outcome Assessment

	Starting point	Final result
Budget	£5,000,000	£8,000,000
Timeframe	February 2023 to December 2023	February 2023 to May 2024
Outcome	Refugees and asylum seekers living in camps and settlements and populations affected by natural and human-caused disasters have access to adequate food to meet their food and nutrition needs throughout the year.	Grain distributed through this initiative by the UN WFP in both Nigeria and Kenya supported refugees and vulnerable people in crisis, and assisted food insecure local populations, including with livelihood and asset creation activities.

Overall assessment of programme outcomes, sustainability and VfM
The programme’s outcome reflected WFP’s established strategic plans and programmes in Kenya and Nigeria. Progress was measured through the output indicators listed in Section C below. The Log frame outcome has been achieved within the timeframe and allocated budget. WFP procured the grain from Ukraine and distributed it to food insecure local populations in Kenya and Nigeria. In Kenya, UK funding (approx. 32% of the total cost of shipment) is attributed to the procurement of 6,000 metric tons out of the total 25,000 metric tons procured. It is estimated to have reached 275,580 vulnerable Kenyan beneficiaries in the most food insecure, shock-affected populations with life-saving assistance and helped make certain daily food needs were met. It also provided a seasonal safety net to local communities in response to drought. In Nigeria, 25000 metric tons of wheat were received in February 2024. The UK contribution accounted for 14% of the overall costs. Reporting and analysis of the related impact of the distribution in Nigeria will be reported in the WFP Nigeria Annual Country Report for 2024, but provisional results are that 840,517 people in Nigeria had been reached by May 2024 of which 98,016 are attributable to UK funding.
[note] https://www.wfp.org/news/ukrainian-grain-donation-bolsters-wfps-response-northeast-nigeria-amidst-inflation-and-food

Value for money of the programme
Delivery through an established partner like WFP offered the best option to manage risks and Value for Money (VfM) considerations for this programme in both Kenya and Nigeria building on previous UK funded initiatives delivered and implemented by WFP. In Kenya, WFP also organised field missions with government representatives from donor nations that bolstered the programme’s visibility and helped to secure an additional USD$ 1m from six new private donors.

In Nigeria, the multi-donor effort helped procure grain before the impact of Nigeria’s lean season (July-October). The UK contribution covered 14% of the overall costs, met the needs of 98,016 beneficiaries to date, and is contributing to efforts to reduce death and hardship caused by food insecurity and malnutrition. It has also added to HMG’s ongoing delivery efforts in North East Nigeria’s humanitarian operations and is having attributable impact and influence in a conflict affected part of Nigeria where high levels of food insecurity and malnutrition are an imminent threat.

The specific contextual nature of the programme, which focused exclusively on procurement, delivery and distribution of grain purchased exclusively from Ukraine, and which has been delivered through the FCDO’s humanitarian funding route, meant that a more detailed and fully comprehensive business case that would have considered the ‘5 Es’ more comprehensively was not developed. A pragmatic approach was taken which, considering the programme’s outcome, has ensured the key objectives have been fully delivered within the constraints and limited programme timeframe.

Summarise the programme’s theory of change and results framework, including any changes to outcome indicators.
This programme was funded through the Humanitarian funding route and adopted WFP’s already developed strategic outcomes that had been designed to meet the needs of vulnerable people in Kenya and Nigeria. Assumptions made included: (i) that UK funding would deliver against the then Foreign Secretary’s lead priority of supporting Ukraine and would help garner support from the Global South for Ukraine in any future acceptable peace agreement; (ii) the initiative would have a positive humanitarian impact on refugees and drought affected counties in Kenya and Nigeria.

The anticipated results were that grain would be distributed to 820,670 beneficiaries (Outputs 1.1 and 1.2 cumulative) in Kenya with the UK funding providing support for up to 32% of these beneficiaries (i.e. 262,614 individuals). Results from WFP Kenya confirm 275,580 individuals were supported by the UK, which exceeds the 32% target.

There were no changes to the outcome, but a new Indicator for WFP activity in Nigeria was added to the output indicators following a further UK contribution of £3m in September 2023 to procure an additional 25,000 metric tons of grain for 613,000 vulnerable people in Nigeria.

## C: Detailed Output Assessment

Output Number and Title / Output 1		Counties in drought-stricken areas have improved capacity to deliver food and nutritional services
Output Score		A
Impact weighting (%)		100%	Impact weighting revised since last AR?	N/A

Output Indicator	Starting Target		Final Log frame Target	Final Result Achieved
Counties in drought-stricken areas have improved capacity to deliver food and nutritional services	Output indicator 1.1 / WFP Kenya - Country Strategic Plan (CSP) Strategic Outcome 1, WFP will target the most food insecure, shock-affected population with life-saving assistance to ensure their daily food needs are met and people recover from shocks.		Shipment total - 820,670 individuals (Outputs 1.1 and 1.2 cumulative) / FCDO portion 32% - 262,614 individuals	Kenya: / Procurement / 25,000 metric tons of grain procured (funded by UK and other donors). 6,000 metric tons (MT) of grain procured with UK £5m contribution (32% of overall costs of procurement, transportation and distribution). 4,788.39 MT received (due extraction losses after milling). / Distribution: / 1,493.30 MT distributed in October 2023. / 3,295.09 MT distributed in November and December 2023 (across 5 counties: Marsabit, Turkana, Garissa, Tana River and Turkana (Lodwar) with a seasonal safety net of food transfers to mitigate the immediate impacts of the current drought. / Beneficiaries: / 275,580 beneficiaries supported.
As Above	Output indicator 1.2 / WFP Kenya - supports communities in five arid counties (Garissa, Mandera, Marsabit, Tana River, and Turkana) with a seasonal safety net comprised of food transfers to mitigate the immediate impacts of the current drought.		Shipment total - 820,670 individuals (Outputs 1.1 and 1.2 cumulative) / FCDO portion 32% - 262,614 individuals	UK support contributed to the following WFP achievements: / Under Activity 1 (from Strategic Outcome 1): Provide food assistance and nutrient-rich commodities to refugees; / Under Activity 3 (from Strategic Outcome 2): Provide a seasonal safety net to local communities in response to drought in the Kenya’s CSP 2018 – 2023 (Kenya country strategic plan (2018 - 2023) World Food Programme (wfp.org)
As Above	Output indicator 1.3 / WFP Nigeria - Strategic Outcome 1, Food-insecure internally displaced persons, refugees and returnees in crisis-prone and crisis-affected areas, vulnerable to the impacts of climate change and conflict, receive food or cash assistance that meets their basic food and nutrition needs.		613,011 individuals	Nigeria (provisional results May 2024): / Procurement: / 25,000 metric tons of grain procured (funded by UK and other donors). UK £3m contribution funded 14 % of the overall costs of procurement, transportation and distribution. / Distribution / 13,893 metric tons distributed by May 2024. / 5,000 metric tons scheduled for distribution in Northwest Nigeria from August to October 2024. / Beneficiaries / 840,517 beneficiaries supported by May 2024. (98,016 attributed to UK funding) / 185,167 vulnerable people expected to be reached during August to November 2024.

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score.
The initial £5m contribution supported the delivery of the following WFP Kenya strategic outcomes (2018-2023):
- Activity 1 (from Strategic Outcome 1): Provide food assistance and nutrient-rich commodities to refugees;
- Activity 3 (from Strategic Outcome 2): Provide a seasonal safety net to local communities in response to drought.

Output activities included successful procurement, delivery and distribution of 50,000 metric tons of grain for Kenya and Nigeria. As part of WFP’s on-going humanitarian operations, the grain was combined with cash and other commodities to help meet the basic food and nutrition needs of crisis affected women, men, and children for a two-month period. The UK contribution in Kenya accounted for an estimated 32% of the overall costs and attributed to the procurement of 6,000 metric tons of wheat (and 14% of the overall costs in Nigeria). The tonnage in Kenya reduced slightly due to losses during the grain milling process and only 4,788 metric tons of milled wheat was available for distribution. This was distributed in two tranches between October and December 2023 (as set out in the final result achieved under Output indicator 1.1 and 1.2 above) with an estimated 275,580 people benefitting from the UK funded component of this distribution. The cumulative target for Outputs 1.1 and 1.2 of beneficiaries to be reached with UK funding was 32% (262,614 individuals) based on original estimates. WFP support was provided for 275,580 people, meaning slightly more people (12,966) were supported when compared to the programme target.
[note] https://www.wfp.org/news/ukrainian-grain-donation-bolsters-wfps-response-northeast-nigeria-amidst-inflation-and-food

Provisional results from WFP Nigeria confirm grain was received from Ukraine in February 2024. The transfer modality was hybrid using in-kind food (wheat grain) and e-vouchers to complement the ration. Of the 613,000-beneficiary target, 840,517 beneficiaries had been reached by May 2024 with 13,893 metric tons of grain distributed. WFP Nigeria has also earmarked an additional 5,000 metric tons for distribution in North west Nigeria during August, September, and October 2024. It is estimated that 185,167 vulnerable people in the most food insecure Local Government Areas (LGAs) of Katsina, Sokoto and Zamfara states will be reached during the peak of the 2024 lean season. Each beneficiary will receive 9kg of wheat per month covering an estimated 837kcal (40%) of the calorie requirement per individual per day. These LGAs are also being assisted under the nutrition prevention intervention (activity 2) and the grain distribution will ensure continuation and complementarity in interventions.

In North East Nigeria (Borno, Adamawa and Yobe States), WFP Nigeria specifically targeted camp populations and identified gaps in humanitarian assistance in host communities, which were not being reached by other Food Security Sector Partners providing support, to avoid duplication of effort.

This Output is scored an A for meeting and exceeding the beneficiaries target in Kenya and Nigeria (provisional) to ensure that ‘Counties in drought-stricken areas have improved capacity to deliver food and nutritional services.’ The additional 12,966 beneficiaries in Kenya and 227,506 (provisional) in Nigeria are noted. Final reports and analysis of the distribution to vulnerable people in Nigeria will be included in the WFP Nigeria’s Annual Country Report for 2024 (when published). Lessons learnt to date from Kenya are captured from the WFP Kenya Annual Report for 2023.

Lessons learned through this output, and recommendations for future programming
The process of compiling the information for this PCR has shown that whilst setting up the related documentation which led to the programme’s successful delivery, FCDO and WFP in both Kenya and Nigeria should have also established clear mutual expectations on sharing information on the timing of distribution planning, keeping FCDO updated on progress, agreed points for progress reports and updates, especially in relation to beneficiaries being helped. Any future, similar programmes should take this into account.

WFP’s broad approach to distributing this grain, by combining it with cash and other commodities to meet basic food and nutrition needs, is clearly value led. It also took account of gender-integrated assessments it had conducted, which helped WFP understand the specific needs and priorities of men, women, boys, and girls in meeting needs. WFP also found community dialogue and sensitisation useful, in helping to positively challenge identified negative social norms, behaviour and attitudes, and to raise the importance of women being heard and able to influence decision-making on various WFP food security and nutrition programmes.

From the experience, WFP Kenya has highlighted as valuable the importance of building resilience through livelihoods diversification to climate sensitive livelihood approaches. This can help the Agribusiness industry possibly increase yield and strengthen specific value chains to attract women to "women-friendly" nodes (e.g. processing and marketing and help them diversify their income and overcome cultural barriers in sectors traditionally perceived as male-dominated). WFP Kenya credits much of this to building productive relationships and working collaboratively with other partners (including NGOs, CSOs, UN agencies, State Departments for Health, Gender and other relevant government sectors).

In Nigeria, local partners were deployed to implement the distribution in North East Nigeria due to the fluid insecurity situation. WFP’s strategy of local engagement by embedding partners who possess deep local knowledge, particularly in security contexts helped it mitigate risks related to the loss of assets and commodities and to ensure the safety of staff. WFP Nigeria has also embedded PLAN International and the Grassroot Initiative for Strengthening Community Resilience (GISCOR) to do target verification through a plan to use the Government’s social registry for beneficiary targeting. Additionally, monitoring services in these locations will be provided by the Salient Humanitarian Organisation (SHO) and eHealth Africa. This approach is being adopted for the distribution in North West Nigeria where 75% of its Northwest Ukraine Grain Lean Season Response partnerships are local, reflecting WFP's commitment to localisation, capacity strengthening and sustainable solutions.

D: Value for Money

VfM performance compared to the original VfM proposition in the business case
The efficiency case set out in the business case remains valid. The programme was developed swiftly using the humanitarian funding route and successfully responded to and reduced the possible catastrophic effects of a humanitarian crisis, where an increasing number of vulnerable people had been identified as needing food and nutritional services in drought-stricken areas. It met this need, responded to the ask to the UK to support the ‘Grain from Ukraine Initiative’ and delivered against the then Foreign Secretary’s key priority of supporting Ukraine until it has won the war. Sourcing the grain on the world market could not have delivered on the latter two objectives although may arguably have been lower in cost.
The main costs drivers for the programme were grain procurement ($16.87m; 48.7% of total costs), logistics and transportation in Ukraine and Türkiye ($7.54m; 21.8% of total costs) and transportation and distribution costs in Nigeria ($2.81m; 7.3% of total cost). A higher procurement cost and increased logistics and transportation costs meant that the Nigeria shipment was more expensive than the Kenya shipment. Final total costs are not available for more detailed analysis and review at this time. However, as the business case set out, delivery through an established partner like WFP offered the best option to manage risks and Value for Money (VfM) considerations in both instances. WFP are a longstanding, trusted delivery partner of FCDO and have transparent and well tested governance and delivery structures. Alternative options were considered, but discounted as the political gains in supporting the initiative made the delivery route through WFP the most efficient and viable option at that time. For example, in Nigeria WFP was able to offload 11,000 metric tons of grain from the vessel and immediately dispatch directly to Maiduguri and Damaturu in North East Nigeria. This approach helped eliminate double handling costs associated with midstream stock prepositioning. Its consultations also revealed beneficiaries in North East Nigeria preferred to receive un-milled grain before distribution, which reduced the costs of milling and associated handling costs in Nigeria. In terms of outputs, equity was delivered by gender integrated assessments to identify the specific needs and priorities of women, girls, men and boys which informed the approach to distributing the grain. Sensitisation sessions were done to strengthen local stakeholders' grasp of gender equality and women's roles in this programme. These efforts bolstered the grain distribution efforts and WFP’s goals of community resilience and inclusive development. WFP plans to expand gender-equality initiatives by enhancing women's roles in community-based structures, increase capacity-building opportunities, and encourage male engagement in gender equality efforts. Additionally, combining the grain distribution with cash and other commodities to meet basic food and nutrition needs also demonstrated efficiency.

E: Risk

Overview of programme risk during the past year and over the life of the programme, drawing on FCDO’s Risk Management Policy and Risk Appetite Statement and wider risk guidance.
The overall programme risk at creation (and while the grain was in transit) was considered to be Major, this was revised down to Moderate after the grain had reached destination countries. FCDO has a receptive appetite (willing to take on major risks) for policy and programme delivery, and strategic and contextual risks. It has a cautious appetite (willing to take on moderate risks) for reputational, people, public service delivery and operational, safeguarding, and financial and fiduciary risks. Risk appetite statements were developed for each risk category.

The key identified risks were:
- (Feb 2023) Political and military tensions lead to suspension of the Black Sea Grain Initiative which would leave the WFP grain shipment stuck in the Black Sea corridor en route to Kenya.
- Grain spoils or is otherwise mishandled and is not in a fit state to be distributed to intended recipients.
- (Feb 2024) Although grain distribution is largely complete in Kenya - the weakness of the Kenyan shilling has the potential to reduce the impact of the WFP activities.
- "Fraud or aid diversion in the processing or delivery stages of WFP Kenya’s Country Strategic Plan means that grain does not reach intended beneficiaries.

WFP has long experience of managing complex logistics and it used this to successfully procure and move the grain from Ukraine to both Kenya and Nigeria. No storage or distribution challenges outside the norm, or reports of spoilt grain have been received. WFP also has extensive knowledge, experience and expertise of storing, processing and managing food stocks and there are no adverse reports of procured grain becoming spoilt, although, as noted above, there were some extraction losses after milling. Regular checks were done throughout the delivery process, liaising with both local and international partners to ensure delivery, milling (in Kenya) and distribution. Capacity strengthening activities, such as security training in safe and secure approaches in field environments; safety of distribution sites for beneficiaries; disease prevention following Health Ministries and World Health Organisation guidelines, were also done with all WFP partners to ensure safe, proper storage, management and tracking of the grain and of how it was being used.

F: Programme Management: Commercial and Financial Performance, Monitoring and Evaluation

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including VfM measures of economy and efficiency.

Component and project title	Name of Partner	Type of agreement	Start of agreement	End of agreement	Spend
400001-101: WFP – Humanitarian grain shipments from Ukraine to countries suffering famine (Kenya).	World Food Programme (WFP)	Memorandum of Understanding (MoU) – contribution to multi-donor/single entity funding mechanism	7 March 2023	30 December 2023	£5,000,000
400001-102: WFP – Humanitarian grain shipments from Ukraine to countries suffering famine (Nigeria).	World Food Programme (WFP)	Memorandum of Understanding (MoU) – contribution to multi-donor/single entity funding mechanism	27 November 2023	31 March 2024	£3,000,000
FCDO Aid Management Platform					£8,000,000

Financial management of this programme has been satisfactory and done in accordance with the terms and conditions of the Memorandum of Understanding between FCDO and WFP in Kenya and Nigeria. Payments were made in arrears. In terms of audit, WFP’s contributions are subject to the external and internal audit procedures provided for in the United Nations Financial Regulations and Rules. WFP activities are audited by WFP’s external auditors in accordance with WFP's Rules and Regulations. The External Auditor of WFP, which is appointed by WFP Executive Board and is the Auditor General (or official holding the equivalent title) of a State Member of United Nations or the Food and Agriculture Organizations of United Nations, conducts the audit of WFP’s financial statements. When done, the audit will be publicly available.

A strong working relationship with WFP teams in Kenya and Nigeria and with FCDO teams in London and at Posts was developed and maintained during the programme’s lifetime. Regular meetings were held and updates on progress with shipments, delivery and distribution provided. WFP reporting systems and processes were adopted for all donors, with no separate reporting system for the UK contribution. This was considered practical because of the crisis response approach being taken for programme delivery and the fluid context in relation to the Ukraine war with Russia, surrounding procurement and freight of grain from Ukraine. Regular updates on progress and performance were provided both at scheduled meetings, and on an ad hoc basis. Final reporting has been included in the WFP Kenya Annual Country Report for 2023 and will be included in the WFP Nigeria Annual Country Report for 2024.

Programme-level approach to monitoring and evaluation
WFP Kenya’s results-based management system tracked operational performance and fed back information on progress being made towards intended results into programme management and decision making. The Monitoring and Evaluation (M&E) Unit in the Kenya Country Office also tracked procurement, delivery, storage and distribution of the Grain from Ukraine. Activity 1 of the WFP Kenya Country Strategic Plan was monitored monthly. This included face-to-face meetings and/or remote monitoring through telephone calls in hard-to-reach areas (due to security challenges). Annual outcome monitoring is outsourced to an independent firm to strengthen impartiality, independence, and the credibility of findings. Monthly monitoring of the food distribution process was also done by WFP field staff, using standard checklists. Beneficiary contact monitoring was also done focusing on food utilisation, satisfaction with the implementation process, gender, protection, and accountability issues.

In Nigeria, provisional assessments of the impact of the Grain from Ukraine programme is that with current high food inflation and food security crisis, most beneficiaries are highly satisfied with the package received. They have noted significant improvements in the food value in terms of quantity compared to prices and quantities available at local retailer shops. Beneficiaries have also appreciated the flexibility of being able to process the grain into various meals of their choice (such as couscous and spaghetti).

Date of last narrative financial report	Feb 2024	Date of last audited annual statement	June 2024 / (for the year ending Dec 2023)