Programme Completion Review

Title: Programme for Strengthening State Capabilities in India - PSSC
Final Programme Spend £ (full life): £3,020,009	Review Date:	May 31, 2023.
Programme Code: AMP ID 300738	Start Date: 27.02.2019	End Date: / 31.03.2023

Summary of Programme Performance

Year	2020	2021	2022	2023
Programme Score	A	A	B	A
Residual Risk Exposure Rating	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case (and any addendum):	https://devtracker.fcdo.gov.uk/projects/GB-GOV-1-300738/documents
DevTracker Links to all logframes used during programme lifetime:	https://devtracker.fcdo.gov.uk/projects/GB-GOV-1-300738/documents

Description	Score
Outputs substantially exceeded expectation	A++
Outputs moderately exceeded expectation	A+
Outputs met expectation	A
Outputs moderately did not meet expectation	B
Outputs substantially did not meet expectation	C

Statement on ODA

A decision on early closure of the programme was based on the ODA prioritisation.

Recognising the significant and unanticipated costs incurred to support the people of Ukraine and Afghanistan escape oppression and conflict and find refuge in the UK, the government is providing additional resources of £1 billion in 2022-23 and £1.5 billion in 2023-24.

We will focus spend according to the priorities set out in the International Development Strategy, while maximising the best value for money and our flexibility to respond to new or emerging priority issues.

Experts on the ground will be empowered to determine with our partners which programmes to continue in line with our approach to prioritisation. The FCDO strives to ensure that every penny of ODA spend brings maximum strategic coherence, impact, and value for taxpayers’ money.

In due course, we intend to update ODA allocations, and the spending commitments set out in the International Development Strategy once we have worked through these decisions with our partners and suppliers.

The UK will remain a world leader in development, not just through the impact of our ODA spend but also through our business, trade, civil society, research and technology expertise.

This Programme Completion Review reflects that the programme has had limited time to deliver planned results, as well as reflecting the progress and achievements that have been possible. Where objectives have not been completed this does not necessarily reflect on the quality of programme design or delivery.

Abbreviations

AR	Annual Review
CBP	Country Business Plan
CPR	Centre for Policy Research
CEIP	Carnegie Endowment for International Peace
CBC	Capacity Building Commission
CTI	Central Training Institutions
DBTE	Direct Benefit Transfer of Electricity
DoPT	Department of Personnel and Training
EFO	Externally Financed Outputs
FOIR	Forum of Indian Regulators
FCDO	Foreign, Commonwealth and Development office
GoI	Government of India
GPI	UK’s Government Partnerships International
HM	His Majesty
IICA	Indian Institute of Corporate Affairs
IMF	International Monetary Fund
IUTF	India Umbrella Multi-Donor Trust Fund
LBSNAA	Lal Bahadur Shastri National Academy of Administration, Mussoorie, GoI.
NA	Not available
NSCTI	National Standards for Civil Service Training Institution
ODA	Official Development Assistance
PSSC	Programme for Strengthening State Capabilities in India
PFM	Public Finance Management
SARTTAC	IMF South Asia Regional Training and Technical Assistance Centre
TA	Technical Assistance
UK	United Kingdom
VFM	Value for Money

A. Summary and Overview

Description of the programme and what it has achieved.

The Programme for Strengthening State Capabilities (PSSC) worked with select government institutions, sectors, think tanks and states (mainly Odisha and Punjab) to improve policies, practices and systems to support governance, economic growth and development approaches. It did so through research and analysis, hands-on technical assistance, and facilitating learning from the UK experience.

The programme delivery slowed due to the covid pandemic, and reductions to the UK’s ODA budget. Some programme components - the secondment of a senior adviser to the World Bank; and contribution of £1.5 m to the World Bank Trust Fund – were dropped; no new states were added under any of the partnerships and the policy research was scaled back.

The programme closure date was brought forward from November 2023 to March 2023. This was in line with the ODA reprioritisation and the country business plan to design new initiatives, more closely aligned to the India network’s new Open Societies and Human Rights strategy.

Within these constraints, PSSC achieved significant results and is scored as an A. It met/exceeded the log frame indicators. More importantly, the programme helped i) build capability of Indian states and select institutions to be more citizen centric; ii) develop and test a peer learning approach, supporting top priorities of the government of India priorities – civil service reforms and streamlining court administration; and iii) produce and disseminate empirical research on institutions and centre-state relations to support India’s economic growth and democratic processes.

Through its briefing notes and learning sessions, PSSC also helped the FCDO to identify entry points for new areas such as internet governance, judicial reforms; and to better understand the political economy of India’s development trajectory.

Some of the significant results include:

New policies and processes on water management, urban planning, energy efficiency, agriculture reforms; and fiscal management adopted in Odisha and Punjab. These will help the states to provide more citizen focused services, improve financial planning and management, and respond to emerging areas such as data protection.

Through analysis, diagnostics and consultations, the TA facilitated the design of four new World Bank loans: two for Punjab, one for Odisha and one for civil service reforms. These will help respective states/agencies to implement the policies, reengineer processes and monitor impact over a longer period.

Capacity building frameworks now used by the national central training institutes to develop their courses.

New analysis, insights and policy recommendations on labour markets, apex institutions, federalism, and data systems, shared with the government but also with civil society, media, researchers, and development partners.

Forum of Indian Regulators (FOIR), at the Indian Institute of Corporate Affairs (IICA), GoI will continue with the “Know your Regulator” series to build the capacity of the regulatory authorities and to connect with the consumers.

Facilitated India-UK judicial partnership focused on digitisation to improve efficiency with a specific focus on culture change.

PSSC had the following partners:

Partner	Details
The World Bank	Test the Bank’s new “strategic state partnership approach” and diagnostic assessment of state capabilities in Punjab and Odisha; through policy dialogue, analysis and advise in key areas (urban, social protection, water, data systems). / Support GoI’s Mission Karamyogi on civil service modernisation and capacity building. / Assessment of institutional readiness, impact evaluation of innovative pilots for future scale up – in Energy Sector (Client governments: Punjab, West Bengal, National Ministry)
CEIP and CPR	Evidence-based policy approach to improve Indian states’ regulatory design and capacity to make markets work better, strengthen India’s apex institutions and enhance centre-state cooperation.
IMF SARTTAC	Strengthening Public Finance Management capabilities of Indian States. Provide key public financial, tax and revenue management trainings to government officials in key states (Odisha) and offer peer-to-peer learning at the national level.
LBSNAA	Training to senior officials on issues of governance, gender & inclusion.
GPI	Peer exchange on Civil Service reforms. Explored but decided not to move forward in 21/22
Ministry of Justice, UK and HMCTS	Formulate India-UK Judicial Cooperation peer learning programme.
[note] State Partnership approach: as part of its Country Programme Framework (2018-22), the World Bank introduced a new ‘whole-of-government’ approach and to break the departmental silos. WB will provide multi-year technical support to assist select states in addressing development challenges, support growth and shared prosperity. Several global practice teams in World Bank - Agriculture, Energy, Urban, Water, Governance, Social Protection - support the activities in Odisha and Punjab. This helps the state to strengthen its policies and institutions, gain new knowledge and develop new lending projects to implement reforms and improve service delivery. Bank is supporting Odisha, Punjab, Kerala, Meghalaya and Chennai (city partnership) under this approach.

In February 2023, the license of one of the implementing partners – the Centre for Policy Research (CPR) – to receive foreign money under India’s Foreign Contributions Regulations Act (FRCA)was suspended for 180 days initially and has been extended. However, CPR has delivered all reports as per the workplan.

Major lessons learned, evidence generated and recommendations:

1. There is genuine interest and appetite from Government of India in peer learning with the UK experience, particularly regarding judiciary and civil service learning and training. Exchange and expert cooperation underpin the UK’s approach to partnership with India on development issues. To ensure that the discussions are meaningful and mutually helpful for both the countries, a productive strategy is to identify two or three areas that the stakeholders in both the countries find challenging. For example, within the focus on digitisation of court processes, changing old patterns of behaviour and adoption of technology by different stakeholders – judges, lawyers, administrative staff and other was a common challenge.
2. Access to high quality robust analysis underpinned the reforms and capacity building initiatives. It also helped the programme team to identify the right entry points such as for court administration and internet governance.
3. From a programme management perspective, flexibility in our agreements with partners/suppliers have enabled the programme’s partnerships to respond to emerging policy and regulatory priorities. Future FCDO development partnerships should continue to focus on building flexibility into design of bespoke capacity building, technical assistance and evidence building interventions and partnership arrangements.
4. It was important to be adaptive given the changes in the operating context of the last three years. The scale, ambition and scope of the programme had to be revised a few times, making it difficult for the partners to finalise workplans. Strong relationships between the FCDO programme team and the partners/suppliers were critical to navigating this.
5. The COVID-19 pandemic made in-person gatherings, face to face interactions with key stakeholders and travel for the first year difficult. Virtual interactions were cost effective. well received and helped maintain the pace of work. But they were more difficult for discussions, peer learning and more informal/ice-breaking conversations. Face to face interactions is especially important to build a rapport with the state institutions.
6. Amendments to the FCRA rules have led to more compliance and scrutiny. As a result, the renewal process takes more time, and in some cases the license was suspended or cancelled. While we only work with organisations with valid FCRA, for any new programme, we need to be aware of the risks around compliance that may come up during the life of the project and affect project delivery.
Recommendations
1. PSSC demonstrated the value of targeted capacity building and evidence-based policies for specific UK-India objectives around institutions strengthening. It showed the UK can have impact by working in partnership with India on a smaller set of highly prioritised issues in a technical manner, an approach the UK should replicate for future work in this space. This work also provides a good foundation on understanding India’s political economy and key institutional drivers of reform. These are useful insights to inform the UK’s work in India.
2. Our justice partnership should continue via the institutional relationships that have now been established (Ministry-Ministry, judges and legal) to continue to grow this work. The justice partnership has the potential to support broader justice and home affairs objectives and improve services for UK nationals in India.
3. We should continue to maintain a partnership with the think tanks in India for an independent analysis of trends, political economy, institutions, and policy making processes. This is potentially useful resource for the entire network to deliver RoadMap 2030 priorities.
How this report was conducted

This report draws on interviews with the implementing partners, key stakeholders in the states and at the centre, past annual reviews, and review of products and documents produced.

Actions following approval of this report.

Audited Financial statements from CPR and CEIP have been received.

B: Theory of Change and Outcome Assessment (1-2 pages)
	Starting point	Final result
Budget	£4,995,000 / £4.5 million in Feb 2019. / Cost extension to £495,000 in Jan 2020	£3,020,009
Timeframe	Five years / December 2018- November 2023	Feb 2019-March 2023
Outcomes	Improved policies and systems to strengthen government capabilities	Achieved.

Overall assessment of programme outcomes, sustainability and VfM

The programme focused on strengthening capacity of select Indian states and institutions. It helped enhance their effectiveness in policy making and implementation to achieve inclusive growth and development outcomes by strategically collaborating with key development partners.

The programme outcomes were achieved though the number of states, sectors had to be scaled down. These results are embedded within the government systems and likely to sustain.

Summarise the programme’s theory of change and results framework, including any changes to outcome indicators.

The overall objective of strengthening state capacity was done through:
Engagement with states and sectors to understand drivers and barriers of inclusive growth, fiscal condition, governance readiness.
- Demand driven research and evaluation to inform policy and institutional and implementation capacity strengthening; and
- Capacity development trainings and associated activities to states and sector institutions.

Analytical and research work was underpinned by three components:
High-quality, rigorous research with the highest standards of academic integrity and independence.
- Papers published as a high-quality reference for key stakeholders; and
- Research findings made more accessible including through editorials, convenings, roundtables, and policy briefings.

The team had several discussions including with the partners to revise the log frame. However, given the budget uncertainties and early closure of the programme, the revision could not be carried out.

Input	Interventions	Output	Outcome	Impact
Up to / £4.95m TA (spend: £3,020,009 / FCDO: / SRO / Sr. Advisers / Programme Manager	Engagement with states and sectors to understand drivers and barriers of inclusive growth, fiscal condition, governance readiness (meetings, diagnostic analysis, research, seminars)	Strategic engagement with states leading to stronger partnerships	Strengthened institutional systems and capabilities (planning, management, policy-making, implementation capacity) in select states and sectors	Strengthened overall governance, enhanced income and livelihood outcomes and inclusive growth
		Identify key areas of governance, institutional and policy strengthening in states and across sectors
		Evidence driven and informed pipeline development for FCDO India
	Commission demand driven research and evaluation to inform policy and institutional and implementation capacity strengthening	Enhance FCDO’s ability to respond to demand driven governance, institutional and policy reforms to influence and enhance state capability. / Enhance FCDO India’s ability to influence key reforms
	Provide capacity development trainings and associated activities to states and sector institutions	Enhance capacity of state administration based on gaps identified from the diagnostics and research

Value for Money

As noted in the business case, it is difficult to quantify VFM for a policy engagement programme like PSSC. Programme impact and value for money were determined by the choice of interventions and the potential scale up and adoption of programme advice and outcomes.

The support to World Bank and IMF allows the FCDO to leverage its funds as part of a wider programme of support, and both organisations have built trusted and long-standing relationships with Punjab and Odisha state governments. Similarly, the Indian Institute of Corporate Affairs will continue with the knowledge outreach sessions with the regulatory authorities. The CBC will work with the central institutes, ministries and with the states to adopt the capacity building frameworks and training standards.

The research papers were used, to build an empirical record for researchers, policymakers, media, and civil society. Papers were also converted into shortform content – editorials, articles, podcasts, - accessible to policymakers and interested audiences.

For CPR and CEIP, costs were reduced and readjusted several times in line with FCDO budget uncertainties and priorities. The partners were able to accommodate through internal economies and providing pro-bono time.

VFM framework

Economy: The programme has achieved sufficient economy during its lifetime. The main cost drivers are for experts, technical assistance missions, training seminars and policy support to state governments.

Partnerships for civil service modernisation and rule of law have strong economic value, as they require limited financial investment. Effectiveness and ultimate value for money of these interventions will depend on activities in the coming year.

Efficiency: The programme’s overall budget was reduced by 40% from the approved amount to £3,020,009 and time frame brought forward by eight months. Costs were distributed across several themes and partners to support capacity building, research, policy analysis and knowledge products. Even with the scaling back and reprioritisation the programme met intended outputs/outcomes.

Effectiveness: States and centres have adopted the policy reforms, improved Public Finance Management; and government agencies are using the new capacity building frameworks.

Equity: PSSC integrated equity considerations within its interventions. Examples include gender budgeting in Punjab, social protection cell in Odisha, gender training with civil servants, new empirical evidence on women and work, and facilitating access to justice through judicial reforms.

Overall cost effectiveness: Within a revised budget and a tumultuous operating environment, the project helped to institutionalise many new reforms, policies, and practices within the systems of the project stakeholders. Overall, the programme was cost effective.
## C: Detailed Output Assessment

Output Number and Title	Strategic engagements with states leading to stronger partnerships
Output Score	A
Impact weighting (%)	60	Impact weighting revised since last AR?	NA

Output Indicator	Baseline	Endline	Status
Number of pilots supported with a pro-poor impact	NA	8 (cumulative) / Details in Annex 1	Achieved
% of engagements involving senior government officials.	NA	77%	Achieved

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score. [1/2 page]

PSSC provided TA to the World Bank to implement and test its new “whole of government” partnership approach in Punjab and Odisha including through policy dialogue, analytical studies, good practices. This allowed the states to introduce fiscal reforms, assess capabilities of state institutions in select sectors to improve service delivery.
1. The programme supported eight departments in Punjab and three in Odisha. This led to new policies, process reengineering, reforms, and knowledge sharing. For examples - data protection policy, groundwater management, gender budgeting in Punjab; social protection cell and agricultural markets in Odisha.
  [note] Punjab: Finance, Planning, Governance Reforms, Women and Child Development, Urban Development, Energy, Agriculture and Groundwater Management
  [note] Odisha: Finance, Agriculture and Information Technology Department
2. It also led to three new World Bank projects to support implementation of reforms: (i) Punjab Municipal Services Implementation Project, US $125 million approved in March 2021; (ii) Punjab Building Fiscal and Institutional Resilience, US $150 million, approved in July 2022, and (iii) Odisha State Capability and Resilient Growth Program, US $150 million.
3. The World Bank proactively shares lessons from Punjab and Odisha with other states and with Niti Aayog. for scale up adoption. The Fiscal Sustainability Analysis tool developed for Punjab, is now being transferred to Orisha, Kerala, Chhattisgarh.
  [note] Niti Aayog – Government of India’s Policy think tank.
4. Punjab Government’s Direct Benefit Transfer for Electricity (DBTE) -) which gives incentives to farmers to adopt water-saving technologies by providing financial incentives through direct cash transfers. The Bank assisted in providing proof-of-concept for the program which led to scaling-up of the program from six pilot feeders to 250 feeders across Punjab.
  [note] 'Paani Bachao Paise Kamao' (PBPK)

Building on the positive feedback of the first phase of training with the Government of Odisha on Public Finance Management (PFM), IMF/SARTTAC developed a new two-year capacity development program with the state. This will strengthen the medium-term fiscal framework, budget preparation, commitment control, and cash forecasting. This close collaboration with the state was also new for IMF and they plan to do similar intensive work with other states as well.

Lessons learned through this output, and recommendations for future programming.
1. The “whole of the government approach, underpinned by analysis and evidence brought together the highest political and bureaucratic to design and implement reforms and build state capabilities. There was an equal emphasis on helping the state bring the reforms to life through new projects. This is one reason that despite several changes in political leadership in Punjab, the policy reforms were introduced and followed through in the state.
2. IMF experts worked with and trained the government officers in Odisha to reform their financial management. The state was very appreciative of this approach as it helped them to apply the learning, make mistakes, and then operationalize the new financial management systems. Future programmes should aim to provide direct technical expertise and preferably not through third party agencies.

Output Title	Capability building mechanisms to influence key reforms in select states and sectors
Output number:		2	Output Score:	A
Impact weighting (%):		40	Weighting revised since last AR?	N

Output Indicator	Baseline	Endline	Status
Number of knowledge products/exchange programmes facilitated to inform policies - knowledge products, visits, policies informed	NA	10	Achieved. / Number of research papers published. / learning visits by GoP to Kerala on gender budgeting. / List given in Annex 2.
Number of capacity development training availed by national and state government (particularly low-income states) on governance, decentralisation, participation, responsiveness, transparency and accountability.	Nil	10	Achieved. / Workshops conducted by the Bank and IMF in the states and at the centre. / 10 Know Your Regulator events with chairpersons of statutory regulatory authorities, including 1 state-level regulator and 4 national regulators.

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score.

Government of India’s “Mission Karmayogi”, launched in September 2020, aims to build state capabilities and future ready civil servants. The Capacity Building Commission (CBC) was set up in April 2021, to catalyse, support and monitor various capacity building initiatives.
1. The UK supported the Mission and the CBC through the UK’s Government Partnerships International (GPI) and then through the World Bank. FCDO set up calls for CBC staff on the following topics.
  1. Online learning platforms and the UK People Survey with the UK Cabinet Office.
  2. results-based management frameworks with IM; and
  3. infrastructure project management training with the UK Infrastructure Projects Authority.
2. GPI facilitated a peer learning and exchange on civil service reforms with the Department of Personnel and Training (DoPT) in November 2020. The areas of focus were - capability, competency frameworks, learning and talent. Further support was channelled through the World Bank.
3. PSSC support to the CBC through the World Bank included:
Two e-learning Modules on public finance management and procurement reforms[[1]];
[[1]] For e-learning on “Public procurement Framework of GOI, 6073 officials have enrolled & 4610 officials have completed training. For e-learning on “Fundamental Rules and Supplementary Rules for Finance” 650 officials have enrolled and 192 have completed training.
Capacity Assessment Toolkit for Districts and Cities; based on the results from the pilot in Maharashtra, the tool kit will be scaled up to other districts and cities starting with Madhya Pradesh and Maharashtra that have an MoU with CBC; and subsequently in Assam, Goa, Himachal Pradesh and Gujarat that work closely with CBC);
Toolkit for assessment of capacity of Central Training Institutions (CTIs) and the accreditation framework - National Standards for Civil Service Training Institution (NSCTI). Various training institutes, such as the Central Bureau of Investigation, Institute of Secretariat Training and Management, National Academy of Direct Taxes, and National Academy of Defence Production - have used the tool kit to seek tailored support from CBC and have completed their accreditation as per the NSCTI.
A new lending project (US$ 47 million) to support DoPT and CBC in the implementation of Mission Karmayogi. The project focuses on (i) roll-out of the framework of roles, activities and competencies (FRAC) for all ministries, departments and agencies of government of India, (ii) development of the iGOT 2.0 platform for delivery of trainings, and (iii) strengthening the monitoring and evaluation framework for Mission Karmayogi.

IMF conducted training programmes at national level on revenue administration, public finance management, government finance statistics with relevant government departments. Sessions included peer experience sharing by officials from Odisha who had received technical support from IMF in this area. Building on its experience of targeted technical support to Odisha, IMF developed a partnership with Tamil Nadu for strengthening public finance management systems.

An independent evaluation of Punjab’s Direct Benefit Transfer for Electricity (DBTE) programme showed a reduction in water and electricity use (about 10-20%) by the farmers. The program design has been widely disseminated and promoted by the GOI (NITI Aayog, Ministry of Finance and the Ministry of Power).

Carnegie Endowment for International Peace (CEIP) and Centre for Policy Research (CPR) focused on evidence-based policy approach to regulatory design and capacity to make markets work better; apex institutions; and cooperative federalism. It conducted original, empirical research to fill policy and evidence gaps. Both CEIP and CPR developed many knowledge products including research papers, policy briefs, livestream and video seminars, roundtables and knowledge events and a forthcoming edited volume of papers.

Some of the examples include:
A new working paper series on cooperative federalism that will: document the shifts in the economic realities of states and the evolution of centre-state dynamics; analyse governmental institutions for managing federalism; and examine what institutional structures might be necessary for managing new or emerging priorities. The series will be published in June 2023.
- Regulatory governance through the ‘Know Your Regulator’ seminar series, papers and frameworks in collaboration with Indian Institute of Corporate Affairs, Government of India. Themes covered included energy, food, insurance and internet governance.
- Insights into labour markets and women’s work resulted in the publication of seven research papers published in a top, peer-reviewed journal accompanied by shorter, analytical commentaries for a policy audience. The research showed that for women safe mobility and proximity to work were two important considerations for joining the workforce.
- The work on apex institutions focused on analysing the institutional trajectories of critical federal institutions to highlight key vulnerabilities and offer recommendations for reform. Election Commission of India (ECI), the apex judiciary, referee institutions (such as the ECI, Supreme Court, and others), apex statistical agencies, as well as parliament. This work has helped shape the terms of the reform debate while also informing ongoing policy deliberations inside government.

1. Aside from the these, CEIP and CPR also provided real-time political economy analysis on relevant issues of politics and public policy, including on rule of law, and institutions. CEIP also worked with FCDO colleagues on understanding potential administrative reforms for the India’s judiciary.
2. FCDO has developed a partnership between the UK’s Ministry of Justice and His Majesty’s Courts and Tribunal Services (HMCTS) and Indian counterparts. This is in line with the MoU in 2018 to cooperate in the sphere of law and justice. It is also aligned to the India-UK 2030 Roadmap that commits to peer exchange including between judges and executive agencies to “strengthen our democratic and institutional partnership.”
  India-UK Judicial partnership: Key events
  May 2022: A UK delegation – MoJ, HMCTS and Judicial office visited India.
  July 2022: Justice Chandrachud (the current CJI) visit to the UK, held a round table on digital reforms.
   August 2022, the Joint Consultative Committee (JCC) set up under the 2018 MoU discussed the partnerships around court digitisation and judicial training.
  January 2023: the respective training academies held a seminar with senior judges on experiences with digital reforms.
  Jan – March 2023: 10-week placement of HMCTS expert to identify specific areas.
  March 2023 – India-UK Justice dialogue; led by 2nd Perm Sec, MoJ, UK; Justice Cheema Grubb; HMCTS, FCDO India; Secretary, Joint Secretary, Min of law and Justice; Vice Chair and members, of E-committee.
  June/July 2023 – proposed visit by the Indian delegation to the UK.

India’s e-courts project (£2bn; 2005 onwards) and UK’s HMCTS reform (£1.4 bn; 2016-2024) – both aim to modernise and digitise the courts, increase access to justice and improve court administration. The key Indian stakeholders are– Chief Justice of India (CJI) and the Supreme Court’s e-committee; Secretary, Department of Justice; and Director, the National Judicial Academy, Bhopal.

The partnership is focused on peer learning partnership on digitization and court administration to improve access and efficiency. Specific areas include – integrated digital systems and data flow; accessibility; behaviour and culture change amongst judiciary, administrative staff and lawyers.

Lessons learned through this output, and recommendations for future programming.

1. Government reforms such as Mission Karmayogi, or e-committee are ambitious agendas. While there may be interest, it takes time to identify tangible partnership activities. The UK should continue to deepen the relationships we have built during this programme and continue to be a supportive partner for the GoI’s agenda.
2. Regulatory authorities are critical to delivery of public services, and for open, fair, inclusive markets. But they often work in silos and are distant from the citizens. Evidence and training support to regulators is thus important to help them become more responsive; and aligned to the needs of a more digital economy.
3. Flexibility in framework agreements have enabled the programme’s partnerships to respond to emerging policy and regulatory priorities. Future partnerships should continue to focus on building flexibility into design of bespoke capacity building, technical assistance and evidence building interventions and partnership arrangements.
4. Primary research and analysis provided a lot of new insights such as on measurement of labour force, or lack of mobility as the biggest factor for low workforce participation of women. It requires sustained effort to take the findings to policy makers and inject them in popular narrative including via social media. Future programmes should build in sufficient resources – money, time and expertise – for a communication plan around policy analysis.

D: Value for Money

 VfM performance compared to the original VfM proposition in the business case.
  Section B includes an analysis of VFM performance.

E: Risks

Overview of programme risk during the past year and over the life of the programme, drawing on FCDO’s Risk Management Policy and Risk Appetite Statement and wider risk guidance. [1/2 page]

The Risk Rating of the programme remains Moderate. The programme has delivered well within its risk appetite. ODA budget cuts combined with a tough operating environment (mainly due to Covid) made it operationally challenging to deliver the programme at the scale envisaged.

Partners relied on digital platforms for outreach and moved to hybrid where possible. Though the response was positive, there were concerns that the virtual meetings may compromise retention, discussions, and rapport building.

Suspension of FCRA of a partner led to setback in some of the activities.

The programme was due to close in November 2023. However, it was decided to close the programme by March 2023 to develop a new programme in line with the Country Business Plan and the Open Societies strategy. There were no delivery or reputational risks associated with the early closure of the programme. The only two live accountable grants with Carnegie Endowment for International Peace (CEIP) and Centre of Policy Research (CPR) were scheduled to end in March 23.

Key Risks (And Residual Risk Rating Post Mitigation	Mitigation Measures
Reputational: There is a risk that in partnerships with multilaterals FCDO is not engaged with as an equal partner, adversely impacting the outcome and impact. (Moderate)	FCDO set up a clear governance structure for engagement with the World Bank. Working collaboratively across the spread of the partnership is non-negotiable.
Policy & Programme Delivery (Minor) / -Delay in programme implementation due to the ongoing pause.	FCDO streamlined/rescheduled/phased out deliverables in consultation with the partners.
Policy & Programme Delivery (Minor) / Programme interventions do not lead to envisaged impact.	By carefully screening sub-projects and through the governance arrangements, FCDO monitored progress and uptake of interventions and recommendations.
Financial & Fiduciary (Moderate) / Delay in partner organisations adhering to revised compliances under the Foreign Contribution Regulation (Amendment) Act, 2020 of India may result in FCDO not able to fund partner organisation.	Conducted due diligence of financial compliances of existing Indian partners for the revised compliances under the Government of India's Foreign Contribution Regulation Act, 2020.
Policy & Programme Delivery (Moderate) / There is a risk that the programme supports small scale/ad-hoc initiatives that are not subsequently scaled up.	The programme screened activities funded through it, supporting strategic interventions that are in line with to GoI and UK's priorities. / Payments were linked with agreed milestones.

F: Programme Management: Commercial and Financial Performance, Monitoring and Evaluation

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including VfM measures of economy and efficiency. [1 page]

The total spend under the project is £3,020,009. The table below gives a snapshot of all the partnerships.
Partner	Details	Spend
World Bank	Diagnostic assessment of state capabilities in 2 states. Punjab and Odisha	£1,526,000
	World Bank Trust Fund	£100,000
	Assessment of institutional readiness, impact evaluation of innovative pilots for future scale up – in Energy Sector (Client governments: Punjab, West Bengal, National Ministry)	£450,000
CEIP and CPR	Implementation of an evidence-based policy approach to improve Indian states’ regulatory design and capacity to make markets work better and strengthen India’s apex institutions.	£215,134 & £212,608
IMF SARTTAC	Strengthening PFM capabilities of Indian States. Provide key public financial, tax and revenue management trainings to government officials in key states as well as offer peer-to-peer learning	£480,000
LBSNAA	Training to batches of entry level and senior officials on issues of governance, gender & inclusion.	£23,905
GPI	Pilot exchange facility – explored but decided not to move forward with this in 21/22	£7,870
Ministry of Justice, UK	Scoping visit on court reform in India	£4,492

The FCDO programme team works closely with partners to monitor financial expenditure and ensure disbursements are made according to the terms and conditions of the AG/contract/MoU signed. Programme budget was closely monitored, and forecasts were regularly reviewed and uploaded on FCDO’s programme and financial management systems (ARIES/AMP / HERA). All payments were made only after submission of the agreed deliverables and mandatory quality assurance process by the SRO.

GOI suspended CPR’s FCRA registration on 27th February 2023, limiting CPR’s ability to receive any foreign contributions until the suspension is lifted. FCDO thus had to pause further implementation of deliverables from this date.

Programme-level approach to monitoring and evaluation

1. The performance and delivery of the programme was delayed during the pandemic. Considering the restrictions for monitoring visits the programme team took new approach for virtual monitoring of the programme during the pandemic period - progress updates, steering committee meetings and engagements with stakeholders.
2. FCDO tracked progress against the work plans, held review meetings held with implementing partners, participated in thematic discussions and government stakeholders to understand the status of the progress of the programme. Formal reporting by partners made mandatory through financial and progress reports in line with Accountable Grant/MoU requirements.

The FCDO team ensured adherence to all requirements, including risk, fraud, and safeguarding.

Date of last narrative financial report	April 18, 2023	Date of last audited annual statement	June 30, 2022

Annex 1: Details of the Pilot projects

The World Bank
Demonstration Farms’ programme in Punjab: new approaches for crop diversification and groundwater management/ conservation and technology applications.

State Data Policy of Punjab: one of the first states with a comprehensive framework, including on privacy and protection, to improve service delivery. World Bank lending project is supporting development of state-wide integrated data platform.

Design of standardised ICT architecture to support distribution companies (Discoms) to adopt the use of Smart Meters and improve efficiencies and reduce wastage.

Gender Responsive Budgeting in Punjab: will be implemented by 6-8 departments and a gender dashboard is also planned; and will be financed under the Bank’s new lending project.

Design of an integrated social protection delivery platform in Odisha. The integration and implementation will be undertaken through Bank funds in the lending operation approved for Odisha.

Agri tech challenge Fund in Odisha helped the state identify local agri tech solutions/companies.

Knowledge and Learning Hub with  CGIAR in Odisha.

Capacity Assessment Toolkit piloted in two districts and two cities in Maharashtra; will be scaled up to other districts and cities in Maharashtra. CBC will also share it with other interested states.
Others

1. TA on Public Financial Management (PFM) in Odisha (IMF): new processes and techniques scaled up and institutionalised.
2. LBSNAA Training curriculum on tackling gender-based violence for government officers including incoming batch of Indian Administrative Service (IAS) officers.