Business Case for Kenya’s Portfolio Monitoring, Evaluation and Learning (PMEL) Programme – December 2023

Summary Sheet

Portfolio/ Business/Country Plan Summary: The UK-Kenya Strategic Partnership, 2020-25, aims for a prosperous, safer, healthier Kenya which sees the UK as a partner of choice for peace, trade and economic development, is less reliant on aid and is more resilient to shocks and stresses.

Title: Kenya’s Portfolio Monitoring, Evaluation and Learning (PMEL) Programme.
Programme summary (100 words maximum): / This Portfolio Monitoring and Evaluation (PMEL) programme will provide assurance and evidence on what is working in our programmes and across all our goals and the portfolio. It will help us to verify that implementing partners are delivering what they say they are, achieving results and using the most effective and efficient approaches. It will provide a picture of what is happening within and beyond programmes, and across the portfolio as a whole, enabling us to understand and communicate our successes, and react and adapt to challenges or bottlenecks. It will improve assurance on value for money across the portfolio.
What is the rationale for UK Aid spending? (200 words maximum): / The British High Commission (BHC) Nairobi has a comprehensive Country Business Plan, outlining six key goals and our approach to achieving them. This pulls together programming, policy, diplomacy and influence work, as well as corporate, consulate and enabling functions. However, we have limited tools to outline or measure our results in many of these areas, or to pull together the aggregate effect of all our workstreams. Further, as the BHC Nairobi plans for an increased budget in official development assistance (ODA) programming in Financial Year (FY) 24/25, resource and skills to objectively verify results and assess progress are needed to ensure accurate reporting of activities, results or impacts of a programme. Some programmes are planning to expand into insecure areas where BHC staff cannot travel and need support to verify partners’ work. Others would benefit from being able to look at results in the longer term, beyond the life of the programme, or to compare different programmes over time or across approaches. / This PMEL programme will enable us to fill gaps in monitoring and evaluation across the Country Business Plan, within the portfolio of programmes and for individual programmes, reducing risks to future planning and delivery. This is aligned to the International Development strategy and the White Paper on International Development in terms of using evidence-based approaches.
Programme Value: / £4.8 million		Country/ Region or Sector: / Kenya, cross-sector
Department/Country Office confirmation of review processes		Director/HoM confirmation that Departmental processes for BC review have been followed prior to submission
Contact name		Sophie Tanner
Threshold for final approval of Business Case: / Head of Mission
Date of Approval of Concept Note:	06/10/2023	Name and role of Approver / Leigh Stubblefield, Development Director
Date of Approval of Business Case:	11/01/2024	Name and role of Approver / Leigh Stubblefield, Development Director
Programme Code: 400180	AMP Start Date: 03/11/2024	AMP End Date: / 31/12/2027
Overall programme risk rating:	Minor

## Strategic Case
#### Why is the intervention needed?
The British High Commission (BHC) Nairobi is proposing this intervention to fill gaps in evidence on delivery and results, within individual programmes and across the portfolio as a whole.

BHC Nairobi has a comprehensive Country Business Plan, which outlines how the mission works towards six key goals. This pulls together programming, policy, diplomacy and influence work, as well as corporate, consulate and enabling functions. However, we have limited tools to outline or measure our results in many of these areas, or to pull together the aggregate effect of all our workstreams.

The Internal Audit Department conducted a review of BHC Nairobi which was finalised in July 2023. The review highlighted gaps in monitoring and evaluation across the mission, expressing concerns that this would “further increase strategic level risks to future planning across the portfolio of programmes.” It recommended work be done to “ensure all activities at Post can adequately report progress against the in-country goals and individual programmes ODA and diplomatic activity.”

BHC Nairobi is expecting an uplift in budget for official development assistance (ODA) programming in FY24/25. With many monitoring, evaluation and/or learning (MEL) budgets cut during reduction in budgets in FY21/22, we currently have little resource to objectively verify our results and assess our progress, beyond implementing partners “marking their own homework”. There are risks around deliberate or unintentional misreporting of activities, results or impacts of a programme. Programme teams would benefit from additional technical skills on statistics, evaluation or economics in specific sectors, as well as the time and capacity to do thorough analysis and interpretation. Some teams are planning to expand activities into insecure areas where BHC staff cannot travel and need support to verify partners’ work. Others would benefit from be able to look at results in the longer term, beyond the life of the programme, or to compare different programmes over time or across approaches. Cross-HMG Outcome Delivery Plans frequently require inputs from country results (recent results commissions have requested data on our work in humanitarian, gender-based violence and education sectors), and teams can struggle with ensuring the quality of those results, including appropriate disaggregation.

This Portfolio Monitoring and Evaluation (PMEL) programme will provide an enabling function to BHC Nairobi, by providing assurance and evidence on what is working in FCDO programmes and across all our goals. The International Development Strategy (2022) highlights the importance of posts being able to take decisions on how to achieve goals in a way which is “grounded in evidence, relevant to the context in which we work, reflecting the new partnerships others want from us and harnessing all the benefits of our investment and expertise.” The White Paper on international Development (2023) emphasises the importance of accountability to taxpayers and ensuring we are tracking and sharing impact, as well as ensuring our partnerships are informed by a shared understanding of the context, objectives, and evidence of what works.

This programme will ensure we have more confidence in our actions and assurance on value for money across the portfolio. As a department, FCDO recognises the value of looking across multiple programmes and using existing evidence to generate new insights, as outlined in the FCDO Evaluation Strategy.
[note] FCDO Evaluation Strategy, 2022-2025, https://www.gov.uk/government/publications/fcdo-evaluation-strategy

The programme will provide a tool for accountability and learning. On accountability, it will help us to verify both that partners are delivering what they say they are, and that they are using the most effective and efficient approaches based on available evidence. It will ensure we achieve a minimum standard on monitoring and assurance across our programmes. On learning, it will provide a clearer picture of what is happening within programmes, workstreams and across the portfolio as a whole, enhancing our understanding and ability to communicate our successes, and our ability to react and adapt to challenges, bottlenecks or a lack of positive outcomes.
#### What will UK funds be spent on?
The programme will be divided into three key components:
- Programme monitoring support: providing technical and objective support through assurance visits in insecure regions, value for money assessments, data quality assessments, quality assurance of results frameworks / theories of change, option for programme funded audits.
- Independent, evaluative programme evidence: learning across and beyond the life of programmes, including drawing lessons on what works across a portfolio, measuring longer term impacts and sustainability, conducting rigorous evaluations of high risk or strategically important interventions, conducting bespoke, thematic learning on key topics.
- Strategic evidence and learning: evidence-based strategic insight, assessing the country plan goals and informing senior decision-making at the portfolio level, supporting measurement of diplomacy, influence and soft power, generating evidence on cross-cutting thematic areas (such as GESI, climate change, science and technology).
The programme will provide core services to the mission across all these components, estimated at £3.2million. In addition, programmes will have the option to ‘buy-in’ where they have specific demand for programme or portfolio specific evidence beyond the core capabilities, up to a value of £1.6m. Given the need to support non-ODA functions in BHC Nairobi (such as diplomacy and soft power), non-ODA funds will also be sought within this total.
The success of this programme will be demonstrated not only by producing data and results, but by how such evidence is used across the mission and with other stakeholders. The PMEL products and findings will therefore feed into existing BHC Nairobi structures, to ensure there is a direct line to decision making, including around the Country Business Plan (see Section E).
This programme will result in:
- Programme monitoring data that is more relevant, valid and reliable, increasing assurance and accountability to the taxpayer, and enabling learning and improvement on programme delivery.
- Independent, evaluative evidence, including beyond and across programmes, that allows us to spend in the most efficient, effective and impactful areas in current and future programming.
- Evidence and learning at the strategic and portfolio level, including in non-programme areas, which directly informs decision-making and adaptations to our approaches across BHC Nairobi.
Overall, individual programmes will deliver more and better for beneficiaries, and our portfolio of programmes, policy and influence will be more relevant, coherent, effective, efficient and impactful.
We have identified the following two outcomes for this programme:
- Compliance: Better accountability on use of our resources; better control, identification and management of risk.
- Learning: Insights inform programme and policy design and adaptation, strategic direction, country planning, forecasting and budgeting.
These outcomes will, by the end of the programme, lead to the following impact:
BHC Nairobi’s approach is grounded in evidence, ensuring our resources have a greater impact and accelerating our progress towards the goal outlined in the Country Business Plan of a prosperous, safer, healthier Kenya which sees the UK as a partner of choice for peace, trade and economic development, is less reliant on aid and is more resilient to shocks and stresses.
#### What is the evidence base?
In 2019, ICAI conducted a review on How Aid Learns. This review highlighted how external MEL providers can “increase the departments’ capacity to experiment and analyse the results” and can “help create space for discussion of what has not worked and why by providing an arms-length perspective.” However, ICAI also outlined concerns that “learning is often treated as a stand-alone activity or set of products produced to a predetermined timetable, without being properly integrated into the management of aid portfolios.”
[note] How UK aid learns - ICAI (independent.gov.uk)

A number of posts have adopted a portfolio approach to manage monitoring and/or evaluation to counter this challenge, ranging for third party monitoring to verify outputs in areas that FCDO staff cannot travel (such as Somalia and Yemen), to strategic research, evidence and learning to inform portfolio and country planning decisions (Nepal, Nigeria, Afghanistan).
[note] https://devtracker.fcdo.gov.uk/projects/GB-GOV-1-300858/summary
[note] https://devtracker.fcdo.gov.uk/projects/GB-GOV-1-300680/summary
[note] https://devtracker.fcdo.gov.uk/projects/GB-1-203385/summary
[note] Programme under design
[note] https://devtracker.fcdo.gov.uk/projects/GB-GOV-1-301019/summary

The portfolio MEL contract in Nepal (starting in 2019) sought to align outputs from programme level MEL activities, synthesise new evidence products and use these materials to help the British Embassy Kathmandu to develop and deliver strategic learning that will help the office answer a range of questions to help adapt, manage and plan the portfolio of programmes. The 2023 Annual Review found that the function provided good, synthesised evidence, tailored to priorities, and the embedded learning function added considerable value.

In Somalia, the third-party monitoring and learning component of the Somalia Monitoring Programme aims to verify activities and measure whether programmes deliver expected outcomes. Just one year into its implementation, the annual review in 2023 assessed that the TPML component was on track to contribute to the expected outcome to increase oversight and assurance of programme delivery and hold partners to account and mitigate risks. In year 1, the TPML team produced four learning summaries, including thematic and programme learning reports for different teams across the portfolio, and had completed M&E capacity assessments against four programmes.

In Nigeria, implementation of FCDO Nigeria Portfolio Monitoring, Evaluation and Learning Programme started in late 2023. The programme was designed to generate portfolio level evidence that is contextually relevant, and support adaptive and learning focussed approaches at the portfolio level. Its purpose is to directly support the more effective delivery of ODA in FCDO Nigeria and maximise impact, and generate learning which to inform all HMG activity at post. Similar to the proposed Kenya PMEL, activities will include improving monitoring, conducting analysis on existing data for new insights, and developing a learning agenda.

This programme will draw on experiences of similar programmes across FCDO, and will continue to benefit and adapt based on insights generated by different stages, contexts and expertise of the programmes.

In the past, BHC Nairobi has had mixed experiences with independent MEL partners. Some have provided comprehensive monitoring, evaluation and learning support, working closely with implementing partners and programme teams to deliver relevant and useful insights. Other programme teams have had harder experiences, with a mismatch in expectations around skills, approach or deliverables. This programme will build on those experiences, considering them through robust procurement, management, monitoring and learning processes, and adapting in response to emerging issues and evidence.
#### Gender equality and inclusion
Contribution to reducing gender inequality has been incorporated into the design of this programme, in compliance with the Gender Equality Act. Gender equality and social inclusion (GESI) is a cross-cutting priority for BHC Nairobi, as set out in the Business Country Plan. This contract will provide technical support to ensuring we are considering and assessing gender equality and social inclusion within our programmes, as well as providing us with the capacity to look across the portfolio at our progress on gender equality and inclusion as a whole. It will ensure results are disaggregated by gender, age and disability wherever possible, in line with the Inclusive Data Charter. In practice, this will mean that PMEL will:
[note] https://www.data4sdgs.org/initiatives/inclusive-data-charter

1. support teams and implementing partners to design theories of change and results frameworks in a way that considers and is inclusive to gender, disability and other protected characteristics, and enables data disaggregation as far as is possible;
2. ensures all evaluation and learning exercises include critical questions about gender and inclusion, in design, implementation and analysis; it is also possible that PMEL could provide specific and direct analysis on the effectiveness and impact of the BHC Gender Action Plan;
3. promote considerations of gender and inclusion in interpretation of evidence for decision-making, including consultation with relevant representatives of different groups.

In alignment with the theory of change for this programme, we hypothesis that such support will improve compliance and learning: this includes accountability to all beneficiaries, from all kinds of background, and learning to ensure we do no harm with our activities and that we maximise benefits for all groups.

Data collection and analysis will align to ethical principles which consider the impact of doing research on specific groups (see safeguarding section below).
#### Risk
The risk of this programme is considered minor, which is within the risk appetite of FCDO and BHC Nairobi. Further, this programme will act as control and assurance for risks across the portfolio. Risks will be identified for each component and suppliers will be required to respond to these in their proposals with appropriate mitigating actions.

The main risks identified for this programme are as follows (see Section E for details):
- Low levels of ownership, uptake and use of findings: There is a risk that programme teams and seniors are not fully engaged with the MEL process. This will be mitigated through careful, consultative design, demand driven products, and representative governance structures. The embedded MEL adviser will prioritise use of findings when considering MEL projects and activities.
- Demand outstrips supply: Conversely, there is a risk that staff have more requests for MEL support and products than the programme has resource to provide. We will assess the need during business case design, and ensure clear processes and criteria for meeting emerging demands.
- Replacing programme assurance: programme teams remain responsible and accountable for their programmes, but there is a risk programme teams assume this work is covered by the MEL programme and deprioritise it. This will be managed through careful communication and ongoing capacity building of teams on their roles around assurance and MEL (compared to the programme), as well as ongoing tracking of team-owned deliverables such as annual reviews, logframes and field visit reports.
- Quality of delivery partner: Having bulk of the MEL work for the mission into one contract concentrates the risk around poor delivery or negative relationships with implementing partners, particularly as that supplier will be required to cover a range of sectors, topics and evaluation approaches. We will draw on best practice for rigorous processes on procurement to mitigate this, including using the GEMFA for pre-qualified suppliers and including a range of expertise in the reviewing panel. We will also include a breakpoint in the contract, in the case of performance which does not meet our expectations.
- Programme management: challenges with forecasting due to demand driving contact, mitigated through careful management and ongoing contact with supplier to estimate pipeline.
In addition, safeguarding risks may emerge during this contract, if:
- the supplier or implementing partners commit safeguarding violations during contact with children or vulnerable people during data collection,
- the act of collecting data puts children or vulnerable people at risk of harm from others,
- data is not kept securely, creating risks of data breaches or other types of harm.

To mitigate the safeguarding risk, suppliers will be required to comply with the FCDO Ethical Guidance for Research, Evaluation and Monitoring Activities, including developing a clear ethical protocol for any primary data collection and getting ethical approvals where required. Spotchecks on activities will be carried out by the programme team to ensure compliance against this. FCDO will ensure that a safeguarding assessment is embedded within the due diligence processes, and that risk throughout the life of the programme is managed within the risk appetite approved in this Business Case.
[note] https://www.gov.uk/government/publications/dfid-ethical-guidance-for-research-evaluation-and-monitoring-activities
#### Other assurances
The following areas will be considered during design and implementation:

- Countering the Financing of Terrorism: PMEL will comply with FCDO’s approach to counter-terrorism financing as well as the UK’s legislation on counterterrorism. Kenya is currently ranked 20 on the Global Terrorism Index of 2023. However, given the nature of the programme, the risk of funds being misappropriated is deemed to be low. PMEL will implement safeguards to ensure financial aid is not diverted and rigorous due diligence is conducted on the partners that are delivering the programme. In addition, the programme will support strong governance arrangements, financial controls and risk management policies and procedures that provide proportionate safeguards.
  [note] Institute for Economics & Peace, (2020) Global Terrorism Index, accessed Feb 22 at https://www.economicsandpeace.org/wp-content/uploads/2020/11/GTI-2020-web-2.pdf
- Climate and Environment: Climate is a cross-cutting priority for BHC Nairobi, and the PMEL programme will support programmes and teams to integrate climate considerations in their design and results frameworks. Further, it will support more rigorous data collection and reporting against the ICF indicators. The principle of Do No Harm will be embedded within PMEL although the risk of any environmental impacts is low. Travel will be minimised.
- Partnership Principles: Activities will be delivered in line with the UK partnership principles. The immediate beneficiaries and direct stakeholders of the programme will be FCDO staff. Funds will not be directly or otherwise channelled through the national or state governments of Kenya.
  [note] DFID, FCDO & Treasury, (2005), UK Policy Paper - Partnership for Poverty reduction; re-thinking conditionality

## Appraisal Case

The appraisal case reviews three options for delivering monitoring and evaluation in BHC Nairobi and assesses them against a counterfactual of “do nothing”. The options are as follows:
- Option 1: Do nothing - £0
- Option 2: Programmes procure their own MEL contracts, under existing programme business cases – estimated cost £6.6m over 3 years
- Option 3: Teams procure portfolio level MEL support, by sector - £5.4m over 3 years
- Option 4: BHC Nairobi-wide Portfolio MEL - £4.8m over three years. Preferred option.

The appraisal of options will compare both the cost as well as how well each option meets the objectives set out in the Strategic Case. Key success criteria have been used as a framework for assessing these options. The options presented have been informed by consultations with BHC Nairobi programme teams, senior leadership and the Delivery Board in June-July 2023. Costs for options are calculated based on components offered, and prices are benchmarked on equivalent programmes delivering similar services.

Option 1 – Do nothing
Description: / No additional investment in MEL. Internal assurance processes are improved for programmes through more frequent programme-led spotchecks and field visits, which would include relevant internal experts. Implementing partners are primarily responsible for obtaining and quality assuring monitoring data. Two programmes currently have independent MEL/third party monitoring suppliers, which would continue. Learning at the strategic level is conducted by the internal MEL adviser. Bidding for central funds for cross-portfolio learning pieces (e.g. thematic/portfolio evaluations through the Evidence Fund).
Value	£0
Advantages	No additional costs to BHC, and funds could be used for other programme delivery. / High level of ownership and responsibility for monitoring and learning amongst BHC staff. / Maximises use of internal MEL staff. / Opportunities to upskill partners and programme staff on MEL.
Disadvantages / Risks	Risks around perceptions and actuality of not being able to subjectively assess our own progress, on programmes or portfolio wide, as highlighted by the FCDO Internal Audit Department. / Internally-lead learning pieces would not have the same level of rigour or quality as independent monitoring and evaluation, due to lack of resources and limited breadth of skillset (e.g. one MEL adviser cannot be an expert in all methodologies and themes). It may be necessary to increase MEL expertise at post to cover demand. / No resource to do evidence generation or learning beyond the basic requirements of programmes or central commissions, limiting BHC ability to become fully evidence based.

Option 2 – Increase to programmes procuring their own MEL contracts, under existing programme business cases
Description: / Individual programmes procure MEL contracts for the specific MEL need of ODA programme, as part of existing Business Case. This may include activities such as monitoring or verification of monitoring data, programme process or impact evaluations, learning reports and sessions, rapid MEL for adaptive approaches. Contracts would be held and managed by individual teams. There would not be any function for strategic level learning, cross-cutting evaluation and learning, or assessing impact beyond/ outside a programmes lifecycle. Learning at the strategic level would be conducted by the internal MEL adviser. Bidding for over-subscribed central funds for cross-portfolio learning pieces (e.g. thematic/portfolio evaluations through the Evidence Fund) and to EQUALS for ad-hoc evaluation and theory of change advice (again oversubscribed across FCDO).
Value	£6.6m over 3 years. Assumes 23 programmes, each with basic independent MEL function; likely to cost more if more rigorous and intensive approaches required on some programmes.
Advantages	This is the model that has been used in BHC in the past, and lessons/ expertise will be used to develop and manage delivery. / Would be incorporated into components of existing BCs, rather than designing and managing an additional programme. / Strong/ bespoke expertise for specific programme and sectoral need, and strong focus on individual programmes. / Spreads risk across multiple MEL partners and contracts, lowering net risks around poor performance. / High levels of ownership by programme teams, who will be managing the programmes directly, increasing the relevance and use of findings. / Potential to build strong relationships with individual implementing partners, government partners, and multilaterals for each programme.
Disadvantages / Risks	High transaction costs internally for managing multiple contracts, increasing the burden in terms of procurement and programme management. / Internally-lead learning pieces would not have the same level of rigour or quality as independent monitoring and evaluation, due to lack of resources and limited breadth of skillset (e.g. one MEL adviser cannot be an expert in all methodologies and themes). / No resource to do evidence generation or learning beyond the basic requirements of programmes or central commissions, limiting BHC ability to become fully evidence based. / Risk that not all programmes obtain sufficient MEL expertise, because they do not value it or do not have sufficient resources, or that MEL components are cut when budgets reduce (as happened in the past), or that the amount and quality of MEL varies considerably between programmes. / Tied to individual programme cycles, so no opportunities for measuring impacts beyond the lifetime of programme/s. / Programme teams see assurance as ‘outsourced’ to the MEL partner, and reduce their own field visits and monitoring of compliance. / Programme teams may have limited expertise to manage a MEL partner, and MEL adviser’s time/ability to support will be spread across multiple contracts. / Implementing partners see this as a policing tool – this is a higher risk with one MEL partner per programme as there will be a greater focus on one programme. / Programmes that had not considered this well during design may have to conduct Business Case addendums.

Option 3 – Teams procure portfolio level MEL support, by sector
Description: / Sectoral teams procure MEL contracts for the specific MEL need for their thematic portfolio, developing a new Business Case and separate contract. The MEL provider would be a sector expert, and could focus on programme or cross-programme monitoring and evaluation, technical support, ad hoc research or evidence generation, capacity building of implementing partners and in-depth learning. It would be possible to generate evidence across and beyond programme lifecycles. Contracts would be held and managed by individual teams with a programme budget, and would therefore focus on generating evidence in specific areas. There would not be any function for strategic level learning across the whole portfolio; learning at the strategic level would be conducted by the internal MEL adviser. Bidding for central funds for cross-portfolio learning pieces (e.g. thematic/portfolio evaluations through the Evidence Fund).
Value	£5.4m over 3 years / Assumes average 5 programmes per goal, across four goals (which currently have post-funded programmes)
Advantages	Strong learning across programmes within a pillar. / Supplier with a focused specialist / sectoral expertise, procurement and design tailored to teams’ need. / Opportunity to develop good relationships with implementing partners due to limited number. / High levels of ownership by programme teams, who will be managing the programmes directly, increasing the relevance and use of findings. / Only procuring / managing one contract per team (as opposed to one per programme in option 2), which should create efficiencies in cost and improve quality and management processes.
Disadvantages / Risks	High set-up and procurement burden, as each team would need to develop a Business Case for the MEL contract, and go through separate procurement processes. / High management burden: teams would have to manage each MEL programme separately, requiring dedicated SRO/PRO/PM resources. / Programme teams see assurance as ‘outsourced’ to the MEL partner, and reduce their own field visits and monitoring of compliance. / Programme teams may have limited expertise to manage a MEL partner, and MEL adviser’s time/ability to support will be spread across multiple contracts.

Option 4 – BHC Nairobi-wide Portfolio MEL
Description: / Accountability and Results Team procures and manages one MEL contract which provides a core service to all teams and programmes. Criteria will be developed for programme/ team use, but would include for all programmes: technical M&E support for theory of change/results framework development; data quality assessments; capacity building of staff and implementing partners; and direct third-party monitoring in insecure areas. At the portfolio level, it includes thematic / portfolio evaluations and learning, ad hoc contextual monitoring/research, assessment of country plan progress, cross-cutting priorities and support to measuring diplomacy. Direct dissemination through existing governance structures with senior leadership. Programmes would have the option to ‘buy-in’ to the MEL contract for specific programme evaluations. Where intensive MEL resource is required, such as for adaptive programmes or very rigorous quantitative impact evaluations, some programmes will still need to hire additional, bespoke MEL teams. Teams and leadership engaged to have strong oversight and direction of programme.
Value	£4.8m. £3.2m for core activities under this business case, £1.6m as optional ‘buy-in’ paid for by programme budgets.
Advantages	Ensures all programmes have access to basic monitoring and learning functions, adding rigour to implementing partner monitoring activities and providing challenge to internal bias / Supports implementing partners to improve their approaches and build capacity for the longer term. / Supports learning and development of BHC Nairobi staff on good monitoring and evaluation practice. / Opportunity for learning across programmes within and across pillars built in, including measuring results outside of a programmes’ lifecycle. / Enables strategic learning and assessment of progress within the country plan, to directly feed into BHC Nairobi decision-making processes. / Resource for supporting learning on influence and diplomacy. / Concentration of procurement and management burden on one team, saving programme management resource across the BHC and ensuring the right expertise (MEL adviser) is in position to manage. / Call down facility for ad hoc bits of research or learning to inform strategic or programme decisions.
Disadvantages / Risks	There is a risk that resources are not sufficient to meet needs of all programmes, and additional resource has to be purchased. / Provider will need to be able to cover all sectors and teams: risks of that they will not have sufficient specialisation in all topics, though this could be mitigated through good / careful procurement. / May need to consider how to complement, work with and build upon MEL providers supporting other government departments on platform or centrally managed programmes. / Risk of low levels of ownership of results by programme teams or implementing partners because they are not directly managing the MEL partner: this could be mitigated by ensuring its demand driven and tailored to the programmes/ team / need. / Programme teams see assurance as ‘outsourced’ to the MEL partner, and reduce their own field visits and monitoring of compliance.

#### Assessment of options
The table below provides a score against key criteria for each of the four options, from 1-5 where 1 is low and five is high.

Criteria	Option 1: Do Nothing:	Option 2: Programmes procure their own MEL contracts	Option 3: Teams procure portfolio level MEL support, by sector	Option 4: BHC Nairobi-wide Portfolio MEL
Accountability for HMG spend: ensuring we have objective and rigorous verification that taxpayer money is being spend wisely and well	No objective verification; relies on programme teams / internal expertise.	Programmes would have tailored and ongoing support. However, risk that not all programmes would procure the expertise or dedicate sufficient resources.	ODA programmes would have support. Limited ability to look across portfolio for how spend works in the wider context, though could do this on a sectoral level.	Ensures basic monitoring requirements are met for all programmes, and considers how spend works in the wider context / across portfolio rather than as stand alone.
Score (out of 5)	1	3	4	5
Learning, improving and adapting: making evidence-based decisions	Strategic learning is internal, with high ownership but limited rigour and scope. Programme level learning is possible but difficult due to IP led M&E.	High potential for programme level learning from results. Limited strategic level learning.	High potential for programme and sectoral level learning from results, which could feed in to BCP monitoring and strategic decisions. No cross-portfolio learning or support to non-ODA teams.	Programme level learning supported, plus potential for cross-portfolio and strategic learning and adaptation. Some evidence needs might require additional resource,
Score	2	3	4	4
Feasibility and coherence: provision of effective and high-quality deliverables.	Deliverables dependent on implementing partners and internal capacity, capability and resource – which is likely to be limited.	Challenging to implement in a uniform way, some contracts may lack the expertise required to steer high quality delivery. Some programmes may not allocate sufficient resources.	Potential for high levels of coherence and quality within sectors/ teams, but quality and approach will vary between teams. Limtied MEL expertise to support all contracts.	MEL expert leading the programme, coherence through having one supplier that understands BHC strategy and ways of working. Risks on sufficient sectoral expertise, which could be mitigated.
Score	2	2	3	4
Alignment with the BHC Nairobi’s priorities –ability to support achievement of BHC Nairobi’s goals	Some internal capacity to generate evidence against the Country Business Plan.	External capacity on assessing ODA programmes which support progress towards goals, can incorporate cross-cutting priorities.	External capacity on assessing ODA programmes which support progress towards goals, can incorporate cross-cutting priorities, plus look across individual goals where they have ODA spend.	Ability to assess cross-cutting priorities, non-ODA spending areas and country business plan as a whole.
Score	1	2	3	5
Total score	5	10	14	18

Option 4 provides the highest score against these criteria. We consider this proposed programme able to deliver this in an efficient way, with value added in evidence generation across and beyond programmes and on strategic goals. This is an option with good value for money, having just one procurement process and one contract, and quality and consistency through a service provider that has a strong knowledge of our portfolio objectives and ways of working. It will also provide different kinds of evidence compared to stand-alone programme MEL contracts, allowing learning to be generated across programmes and portfolios, gathering results over longer periods of time, and providing strategic insight on the country plan. The MEL programme will provide evidence which will help us to improve our work across economy, effectiveness, efficiency and equity measures, thereby creating amplifier effects in terms of the value and impact of all our work. We will design the MEL programme with uptake and use in mind, only carrying out data collection and analysis where we have a direct line of sight to what it will influence or change. We will also increase the value of implementing partner monitoring and assurance work, by maximising its quality and relevance, and developing capacity and capability amongst our partners.
#### Theory of change for the preferred option
Problem
The BHC Nairobi currently has no systematic, objective approach to monitoring, evaluation and learning, as picked up by the Internal Audit Department in March 2023. This means we have limited assurance on ODA programme spend, as well as limited resource to support evaluation and learning beyond and across programmes, portfolio and strategy.

Context
The current Country Business Plan covers 2023-2025, and will need ongoing review to adapt as well as make assessments for future planning from March 2025 onwards. The ODA budget will increase in FY24-25, requiring more tools for assurance and learning to maximise impact. Teams working on non-ODA or non-programme priorities have increased demand for establishing goals and assessing results.

Stakeholders: Critical to the success of this programme is BHC staff buy-in and engagement, to ensure relevance and ownership of deliverables and uptake of results and recommendations. This includes:
- Teams with ODA programming: monitoring and assurance on programmes, potential evaluation on programmes and /or themes and portfolios of programmes
- Teams working on non-ODA interventions: support to articulate theories of change or results frameworks, and to assess progress or results.
- Senior leadership / the Kenya Country Board / Pillar Leads: assessing progress against at the Country Plan; updates on programme results; evidence to inform strategic decision-making.

Outside of internal staff, the following stakeholders are important:
- Implementing partners: who may be the subject of PMEL enquiry; are expected to respond and adapt in line with results and recommendations; may engage in capacity building and technical assistance activities.
- The Government of Kenya: as strategic partners, should also be aware of programme results and feed into recommendations and decisions as well as wider strategic direction.
- The general public: Accountable to UK taxpayer in terms of ODA programme spend; accountable to Kenya citizens in terms of actions the UK takes in Kenya and ensuring do no harm.
- Other development, diplomatic and private partners working Kenya, where learning is relevant to their sector or their work, or where we are working in partnership on a programme or policy.

Causal chain and assumptions:
The programme is based on the following logic:
- If external expertise is provided to a) support/improve/ verify programme monitoring, b) generate new research and evaluative evidence on programmes and c) generate learning across our country plan and non-ODA work,
- Then we will have better evidence to ensure we are compliant in our activities, and learning on what is working or is not working. This will allow us to be accountable, to adapt and to improve.
- Then BHC Nairobi will have an approach that is grounded in evidence, maximising impact and value for money.

See figure 1 for a visual representation of the causal chain.

We assume that:
- There will be demand for and capacity to use evidence across all teams and senior leadership; seniors, teams and partners have capacity to absorb and act upon findings.
- It is possible to generate useful data on required topics (including e.g. diplomacy/influence), in a proportionate yet rigorous way.
- High staff turnover within implementing partners and BHC doesn’t negatively impact the programme, including reducing the benefits of capacity building for longer term change in monitoring and evaluation skills and culture.
- Budget is sufficient to meet demands of all programmes, or if not, programmes are able to identify additional MEL resource.
- Implementing partners comply and participate, including in using / implementing findings.
- Supplier has sufficient skills to cover a range of evaluation type and sector specialisms.

The supplier will be required to review and update the theory of change during the inception phase of the programme.

Figure 1: Visual representation of the PMEL causal chain
#### Value for money
The HMG Magenta Book on evaluation sets out the potential for evaluation to deliver high return on investment. It states that “high quality evaluation evidence can enable decision-makers to better target their intervention; reduce delivery risk; maximise the chance of achieving the desired objectives; and increase our understanding of what works.” Measuring the cost-benefit of evaluation and research is challenging since impact is often tenuous and difficult to quantify. As such there are very few examples of rigorous analysis on this. However, attempts which have been made do indicate a significant return on research. It is arguable that more specifically the return on evaluation, and applied, issue driven analysis for an already identified portfolio of work, will be much higher.
[note] HMG Treasury (2020), Magenta Book, Central Government Guidance on evaluation
[note] Evidence includes internal analysis by FCDO on the rate of return for our research portfolio. DFID’s How to Note on the Rates of Return for Research shares a conservative estimate from rigorous studies that would be around 10% although this varies across sectors.

Rigorous monitoring and evaluation of ODA programmes ensures taxpayer money is spent well, wisely and fairly: it can verify we are buying what we thought we were, and that what we are buying has the effects we expected. In non-ODA or diplomatic areas, it supports ongoing assessment of our human and financial inputs to ensure we are doing the right things in the right way. Having portfolio monitoring evaluation and learning pushes us to generate and use evidence that maximises our coherence, efficiency and impact. PMEL will assess activity across multiple departments, leveraging economies of scale for decisions on strategy. Evidence produced will benefit a broad range of stakeholders working across the portfolio. It will produce higher quality more rigorous evidence to improve decision making by engaging external expertise. Independent evaluation and external challenge will help BHC Nairobi look outside the internal system to identify issues and provide a different perspective to generate new insights and recommendations.

The PMEL programme will commit to spending £3.2m over the programme lifespan, equivalent to £1.1m per year. The remaining £1.6m will be paid for by other programmes on an on-demand basis, so will only be allocated and spent where it is really needed and where the evidence will be owned and used by teams. The total Business Case value is £4.8m, or approximately £1.6m per annum: this represents less than 2% of the total 24-25 bilateral ODA budget for Kenya (projected to be £81m). The PMEL represents a small proportion of the budget but is broadly aligned to other similar PMEL programmes in terms of cost: as the first such programme for BHC Nairobi, use and effectiveness will be carefully monitored, with costed extensions or future iterations of the programme possible if proven to be successful.
FCDO’s Value for Money (VFM) framework is based on the 4E’s measures of economy, efficiency, effectiveness and equity. The programme will employ a VFM framework nested within the wider delivery to inform VFM judgements and decision making and improve programme performance. A VFM framework will be developed alongside the logframe and risk framework to help steer PMEL and ensure it continues to be a good use of resources. The following paragraphs outline how VfM will be maximised and monitored within the programme.
Economy
The budget for the preferred option is lower than other options, and the human resource cost – in terms of procurement and management – is less than having multiple contracts. The supplier will be identified through a competitive process within the Global Evaluation and Monitoring Framework using VfM criteria. The contract will commit to spending on core activities, but additional functions will be used only if there is demand. The key cost drivers will be human resource of both BHC staff and the supplier, and the cost of field visits and data collection. Such costs will be monitored and field visits conducted only where necessary, with the supplier required to demonstrate how they keeping costs down.

Economy indicators may include:
- Average consultancy rates and fees
- Number of days per programme per year
- Average cost per field visit

Efficiency
Efficiency will be demonstrated by the quality and relevance of products delivered by PMEL. Products must stand up to technical scrutiny to ensure quality and reliability of results, but they must also be accessible and useful to senior leaders, programme teams, implementing partners and other stakeholders. The programme has been designed to meet the MEL requirements of all of these stakeholders, to ensure we have basic accountability and learning standardised across all BHC activities, with the option to bring in more as required. Teams will be part of the design of any assessments of their own programmes, interventions or workstreams to maximise relevance and usefulness. Evaluation and learning assessments will require some basic design documents, such as TORs and methodology documents, to ensure clear expectations on subject, approach and methods.

Efficiency indicators may include:
- Proportion of reports achieving ‘good’ or ‘excellent’ EQUALS rating.
  [note] Evaluation Quality Assurance and Learning Service: an independent provider with experts that quality assure evaluation products for FCDO.
- Feedback from users on the quality and usefulness of the reports.
- Products tailored to audience, according to study type/cost.
- Engagement of BHC staff in design and analysis processes.
- Engagement of partner or government staff in design and analysis.

Effectiveness
Effectiveness will be achieved through the use and uptake of lessons and recommendations generated by PMEL. Ownership by staff from the outset is essential to ensuring the relevance and usefulness of results, as well as their interest and ability to act upon the findings and make decisions based on the evidence generated. As well as engaging with staff directly involved, BHC governance structures will provide a high-level forum for discussion, for example:
- Kenya Country Board (KCB): strategic level analysis and information, results relevant to the Country Business Plan,
- Delivery Board: programme results, monitoring and verification,
- Pillar Boards (sector level working groups): programme and portfolio results and evidence.
A use and influence plan will be part of the design of any enquiry and analysis, from basic monitoring verification to strategic assessments.

In addition, support to implementing partners has been incorporated into the design: technical assistance on theories of change and results frameworks, capacity building workshops, and feedback from verification visits. These aspects will help amplify the effects of the PMEL, by developing skills both with partner and BHC programme staff, to improve our MEL work going forward.

Effectiveness indicators may include:
- Number of times PMEL content discussed at BHC Boards, against type/cost of study.
- Progress against use and influence plans.
- Evidence of PMEL results/ recommendations influencing decision-making (disaggregated by type/cost of study).
- Evidence PMEL results/ recommendations informing adaptations to programmes or programme design.

Equity
The PMEL programme will enable us to better monitor and measure our impacts on marginalised populations including women and girls. Equity within the PMEL will be monitored through deliverables and outputs – the extent to which data, findings and recommendations are disaggregated, and results are placed within the wider context of inequality or disadvantage. It is possible that inclusion or other cross-cutting priorities such as climate, disability and gender could be the subject of a thematic study. During procurement, the supplier will be required to demonstrate equity within the technical team, their commitment to social values and their technical experience and capabilities in assessing equity issues.

Equity indicators may include:
- Proportion of programme theories of change or logframes that provide results on equity (data disaggregated by groups, specific results for certain groups, etc.),
- Proportion of PMEL products which provide specific analysis on gender, disability or other marginalised groups,
- Results of inclusive approaches to monitoring for marginalised groups.

## Commercial Case
#### Delivery route
PMEL will be directly procured with one supplier who has the technical expertise to meet the needs of the programme, although the feasibility of this will be tested further during an Early Market Engagement. The relevant framework for procuring evaluations is the Global Monitoring and Evaluation Framework Agreement (GEMFA), lot 3: Monitoring, Evaluation and Learning, High Value Lot (>£600k) with mini-competition. This route will allow us to procure from a framework of pre-selected suppliers. The advantages of procuring through an existing agreement are shortened timescales, access to a selection of suppliers who have undergone assessment of capability in evaluation and due diligence. There are 10 suppliers eligible under Lot 3, each with a large number of sub-contractors, and they have proven expertise across sectors, methodologies and geographies.
Detailed terms of reference (ToR) will be developed to outline the full requirements of the programme, in consultation with key users and stakeholders of the PMEL. We will consider holding an Early Market Engagement as part of the design of the ToR. The ToR will be approved by EQUALS to ensure they hold clear and realistic requirements. The ToR will also be clear on our expectations around conflicts of interest to minimise any potential risks. We will ensure that all learning to date in similar such procurements is included in this process, seeking the support of the GEMFA procurement team and BHC Nairobi’s commercial specialists.
#### Requirements of the supplier
In order to support the realisation of the programme outputs there are overarching types of service to be provided under this contract:
- Providing programme monitoring and assurance support
- Generating independent, evaluative programme evidence
- Assessing strategic evidence and promoting learning
The elements of these services are outlined in the appraisal case. Design of these requirements has been developed in consultation with BHC Nairobi programme teams and the cross-cutting experts in FCDO, to gather views and expertise of what this service will provide, what is required and what works (and doesn’t work) in practice, as well as a clear idea of what is needed to ensure relevance to BHC’s current requirements. This learning will be applied to the procurement and management of this service. BHC staff will be consulted during the TOR design to ensure their diverse needs are considered.

Primarily, we are buying technical expertise and the collection of primary data. The supplier’s expertise, experience, knowledge and skills is therefore essential, and they will be required to demonstrate:
- Strong expertise in monitoring and evaluation approaches and methods covering a range of quantitative and qualitative approaches and across the full spectrum of assessment tools, from rigorous impact evaluations to process monitoring to light touch learning.
- Strong expertise in key sectors, including areas where we have programme spend (mutual prosperity; democracy, governance and politics; human and social development), cross-cutting priorities (gender and social inclusion, climate change, innovation and tech) and non-ODA areas (diplomacy, security and stability, people to people / soft power).
- Information management and sharing, to promote change, with expertise in packaging and sharing results to maximise relevance and use. This might include the ability developing user-friendly, targeted knowledge products, holding interactive workshops with key BHC and partner staff or participating in high level meetings and boards. The supplier would need to have good relationship management skills to ensure implementing partner staff are appraised of design and developments, and to keep teams engaged in their work.
- General administration and financial management, including keeping accurate management and financial information for each service and setting up efficient processes to manage and respond to requests.

The supplier is likely to be subject to high level strategic documents and forward-looking strategies, plans and design information. Conflict of Interest will need to be carefully managed in the contract and criteria will be outlined in the ToR.

The supplier will be required to sign confidentiality agreements and there will be protocols to ensure that sensitive information is sufficiently protected and destroyed when the work is completed. Guidance on FCDO’s data policies will be shared with supplier to disseminate. The procurement process will also include the best way to get some members of the supplier staff security cleared.

The programme has been designed to provide a core service costing £3.2m over the life of the programme, but will also have the option for other programmes to buy-in specialist services that they need, such as rigorous programme evaluations or audits on particular areas, up to a total of £1.6m. The supplier will need to have the capacity to absorb these demand-driven aspects, whilst recognising that they may not be needed and this additional budget may not used.
#### Performance Management
A 3-6 month inception period will be required for the set up of this programme, including establishing a programme monitoring support plan, criteria and processes for programme and portfolio evaluations, and proposals on strategic assessments and learning. The supplier’s contract will outline clear KPIs for delivery, against which performance will be assessed. This will include monitoring EQUALS ratings on written products. The supplier will be required to complete quarterly progress reports and discussion with the programme team.

There will be a breakpoint in the contract, following inception and some time for implementation. This will enable reflection on how the partnership is going and whether the supplier continues to represent the best value for money for this programme. It would allow for shifts in the contract in response to changing demand or need, and any changes in circumstances related to the Spending Review scheduled in 2025.

There will be a possibility for time extension, depending on the performance of the programme and the levels of spend. This is a demand driven programme with a buy-in provision, which is a new approach for BHC Nairobi, and the potential for extension allows some flexibility to respond to that. If demand is high and resources available, a costed extension could also be considered.

Value for money in the contract
Key cost drivers of PMEL will be the direct costs i.e. provision of technical services which are expected to be staff for the project management and specialist technical expertise, expenditure on data collection, and overheads and administration fees may also be included. Costs will be benchmarked with similar costs and programmes.
As detailed in the appraisal case, a single contract with a supplier is the chosen option. This arrangement will reduce transaction costs associated with delivering multiple contracts, and will provide additional value by allowing one supplier to have a few for capitalising on synergies across the outputs.
Risks
Key commercial risks include poor response from the market resulting in a low number of bids received; the right supplier with access to a sufficient range of expertise to meet all expectation of the terms of reference; and the quality of the bids, high fee rates and timeline pressures to deliver the full tender. The early market engagement will decrease the likelihood of the first risk which in turn will reduce the second and third risk. As noted above, a terms of reference will set out the expectations and requirements to ensure the supplier understands the requirements of the programme and delivers good quality bids.

## Financial Case
#### Affordability and funding sources
The PMEL programme will commit to spending £3.2m over the programme lifespan, equivalent to £1.1m per year. The remaining £1.6m will be paid for by other programmes on an on-demand basis, so will only be allocated and spent where it is really needed and where the evidence will be owned and used by teams. Annually, the maximum spend of the programme is £1.7m per annum. With BHC Nairobi’s ODA budget expected to increase to £81m in 24-25 and remain at similar levels going forward, the programme is highly affordable. A break clause will be included in the contract aligning to the new Spending Review period.

Funding will be RDEL as the bulk of the work is technical assistance and expertise, and the type of monitoring, evaluation and research proposed does not meet the criteria for CDEL Research and Development.

Non-ODA funding will also be applied for (within the stated amount), on an annual basis, to enable work on diplomatic or soft power areas, or BHC-wide strategy; the funding for the Business Case is hybrid.

Overview of costs
The programme will undergo inception and setup within the first 3-6 months of FY24/25, with full implementation expected from October 2024. The spend in the first year is likely to be slightly less than average as a result. The design will be flexible and responsive to the portfolio, ensuring VFM and the ability to scale or terminate funding if necessary. Annual work plans will be agreed on a six-monthly rolling basis. Payment points will be agreed as part of the contracting procedure, and will align key deliverables and the breakpoints outlined in section C.

Cost estimates for conducting the monitoring, evaluations and learning activities, plus administration costs have been provided in the below table. As this programme includes the ability for programmes to ‘buy-in’ extra support, the table outlines core costs against optional buy-in costs. It is expected that all core costs will be spent: buy-in costs will be used only if there is clear business need and demand from teams and seniors.

	FY24-25		FY25-26		FY26-27
Component	Core costs	Buy-in	Core costs	Buy-in	Core costs	Buy-in
Admin and overheads	20,000	0	20,000	0	20,000	0
Programme monitoring	300,000	100,000	450,000	150,000	450,000	150,000
Programme evaluation and learning	200,000	400,000	400,000	400,000	400,000	400,000
Portfolio evidence generation	250,000	0	350,000	0	350,000	0
TOTAL per year	770,000	500,000	1,220,000	550,000	1,220,000	550,000

Core costs total	3,210,000
Buy-in total	1,600,000
Contract total	4,810,000

 management and assurance of funds

The financial risk of this programme is moderate. The risk of funds not being used for their intended purpose or expenditure not being properly accounted for is minor after mitigating actions (see section E). The financial risk rating will be shaped further by the experience of the supplier. We will continually monitor and update the risk register, working with suppliers to mitigate financial risks. The supplier will be assessed on programme and financial management capabilities, including ensuring they have robust financial systems in place to maintain control and oversight of the programme and clear routes for managing risks with downstream partner. The selected supplier will also be required to undergo an annual audit and will share their annual audited statement with FCDO. For the ‘buy-in’ component of the programme, processes will be developed for transferring and accounting for funds, to avoid risks of double counting.

Monitoring, reporting & accounting for funds
The supplier will be required to submit 6-monthly budgeted work plans for FCDO approval containing detailed estimates for fees and other expenses. This will include ‘core funding’ and ‘buy-in’ costs, in line with the budget ceiling for the year. Suppliers will need to provide evidence on how they have utilised funding as part of invoicing and in line with the commercial agreements on costs. Payments will be made based on quarterly milestones signed off by FCDO staff through quarterly reports and a set of key performance indicators which will be developed and refined as part of the mobilisation phase. The funding type of the programme is “104 procurement of services” and the input sector codes will be allocated depending on the nature of the work undertaken, as work will cover the portfolio of BHC’s activities and sectors.

The main supplier will be required to submit an inception report following the inception period. The inception report should set out a detailed plan on how the supplier plans to deliver the expected outputs, contribute towards the programme outcomes, and deliver value for money.

It is not expected that there will be a need for assets. However, should assets be purchased then a full asset register will be generated to include the make, model, serial number and location of the asset along with lifespan, purchase price and date. These will be verified annually with potential spot checks. Asset disposal will be in accordance to the FCDO Programme Operating Framework rules with delegated authority approval.

## Management Case

Governance arrangements
The value in this programme rests in monitoring, evaluation and learning results being relevant and useful and informing adaptations and changes to our strategy, policy and delivery. Governance structures are therefore critical, to:
- Steer the PMEL to the most useful and relevant areas of enquiry,
- Provide a forum for sharing and decision-making based on the outputs of the PMEL,
- Provide feedback on what is or is not working within the PMEL processes or outputs.

We have decided to utilise existing BHC structures, rather than create parallel processes, as this is most likely to ensure the right people are present at the right discussions. Figure 2 outlines how the three components will feed into the relevant Board discussions and decisions, with overall oversight of the Development Director, who in turn reports into the High Commissioner. The SRO/PRO function will be merged, given the size of the programme, and will be accountable for day-to-day running of the programme as well as supplier performance management and tracking of results. This role will be filled by the post MEL Adviser to ensure sufficient oversight of all PMEL activities. The programme manager will support this, through ensuring that best practice and compliance are applied across the management of a programme, monitoring progress, managing risks and issues and overseeing financial compliance. The SRO/PRO will seek external expert support from the Evaluation Cadre, and through a PMEL community of practice, which will also help learn from others’ experience and keep up-to-date with the latest evidence.

Figure 2: Governance, use and oversight structures

Managing and monitoring supplier performance
A 3-6 month inception period will be required for the set-up of this programme, including establishing a programme monitoring support plan, criteria and processes for programme and portfolio evaluations, and proposals on strategic assessments and learning. This will include considerations of GESI and climate. The supplier will be required to develop rolling workplans, and to produce a quarterly progress report and monthly finance reports. Workplans will be informed by regular meetings between the supplier and the BHC management team, which will focus on delivery, compliance and programme management issues, as well as strategic reflections. The SRO/PRO will approve mini-TOR or methodology documents for evaluations or learning assessments, which will also go through EQUALS where appropriate. The supplier’s contract will outline clear KPIs for delivery, against which performance will be assessed.

Risk management
Overall residual programme risk is minor. PMEL will not directly be delivering ODA programmes, but instead will performing a support and enabling function. It is important to note also that PMEL will be integral to HMG delivery, helping us understand performance and how we can better manage risk across the portfolio by providing high quality evidence and analysis.

Risk will be discussed regularly with suppliers during monthly meetings and will be included in progress reports, monthly updates/meetings will discuss risks which are showing signs or have materialised. Risk escalation procedures will be agreed during the inception period. Key risks and mitigations are outlined in the table below.

Monitoring and evaluation
A logframe with clear targets will be developed during the inception phase, against the statements in the theory of change. This will include feasible but stretching indicators and targets at output, outcome and impact level, with a strong focus on evidence of uptake and use of results from the PMEL. The supplier will be expected to develop clear methodologies and data sources for these indicators and provide timely updates on progress against them. Further, they will develop a VfM matrix, which interfaces but goes beyond the logframe, and provides clear assessment of costs and progress against targets and benchmarks.

The SRO/PRO will conduct field visits to monitor verification exercises or other data collection in the field, and internal experts will conduct ad hoc spotchecks on finance, risk and safeguarding practices of the supplier. The SRO/PRO will lead an annual review of the programme, bringing in an external reviewer at least once during the programme’s lifetime.

At this time an independent evaluation of the programme is not envisaged due to its small size and low risk rating.

Risk Category	Summary of risks	Mitigation

Strategy and Context / FCDO appetite: Receptive / BHC appetite: Receptive	The supplier market does not have the required expertise to meet the demands of the programme (country context and thematic areas). / Likelihood: Unlikely / Risk rating: Minor	Clear terms of reference, developed in consultations with programme teams and quality assured by MEL experts. Strong panel for assessment. Use of GEMFA for pre-qualified experts / Net risk: Minor
	Access to insecure areas challenging for suppliers: verification or third party monitoring may be required in insecure areas for 1-2 programmes. Volatility may limit access at certain times. / Likelihood: Possible / Impact: Minor	Supplier selected based on their ability to work in insecure areas. Ongoing monitoring of situation and flexibility in approach to ensure supplier staff safety. / Net risk: Minor
Policy and Programme Delivery / FCDO appetite: Receptive / BHC appetite: Receptive	Low levels of ownership, uptake and use of findings: risk that implementing partners, programme teams and seniors are not fully engaged with the MEL process, due to lack of time, skills or interest, or due to an overwhelming amount of information produced. / Likelihood: Possible / Impact: Major	Careful, consultative design, demand driven products, and oversight and dissemination through governance structures. All activities will have a use and influence plan during design, and products will be tailored to audience. The embedded MEL adviser will prioritise use of findings when considering whether to move forward with MEL projects and activities. / Net risk: Moderate
	Demand outstrips supply: Risk that staff have more requests for MEL support and products than the programme has resource to provide, especially in terms of complex and rigorous evaluation. / Likelihood: Possible / Impact: Moderate	Teams sensitised to PMEL resources and services during programme design and on an ongoing basis. Clear processes and criteria for meeting emerging demands will be developed. Where teams need addition resource, there will be an option to ‘buy-in’. Where this still cannot meet need, teams may choose to have their own additional evaluation contracts, which complement and build upon the PMEL. / Net risk: Minor
	Replacing programme assurance: programme teams remain responsible and accountable for their programmes, but there is a risk programme teams assume this work is covered by the MEL programme and deprioritise it. / Likelihood: Possible / Impact: Moderate	This will be managed through careful communication and ongoing capacity building of teams on their roles around assurance and MEL (compared to the PMEL programme), as well as ongoing tracking of team-owned deliverables such as annual reviews, logframes and field visit reports. / Net risk: Minor
	Quality / performance of supplier: Having bulk of the MEL work for the mission into one contract concentrates the risk around poor delivery, particularly as that supplier will be required to cover a range of sectors, topics and evaluation approaches. There is also a risk that some qualified suppliers are not eligible because of conflict of interest, which will limit the pool. / Likelihood: Possible / Impact: Major	We will draw on best practice for rigorous processes on procurement to mitigate this, including using the GEMFA for pre-qualified suppliers and including a range of expertise in the reviewing panel. We will include a breakpoint in the contract, in the case of performance which does not meet our expectations. Conflict of Interest will be balanced carefully, working with procurement experts. / Net risk: Moderate
	Programme management: challenges with forecasting due to demand driving contact, results in delivery challenges or lack of ability to meet expectations. / Likelihood: Probable / Impact: Moderate	Careful management and ongoing contact with supplier to estimate pipeline. / Net risk: Minor
	Quality of data available/ or able to be generated at the programme level is poor/ insufficient to answer strategic questions, leading to poor quality outputs. / Likelihood: Possible / Impact: Severe	Monitoring support will improve data quality over the life of the programme. Evaluation and learning assessments will include consideration of evaluability (availability/ quality of data on which the evaluation will be based, feasibility of methods). Remains a risk that some areas cannot be assessed. / Net risk: Moderate
	There is a high turnover of BHC staff and implementing staff, which results in loss of knowledge and skills learnt during from the programme, and minimises the benefits to capacity development. This could also affect the quality of relationship with the PMEL supplier. / Likelihood: Likely / Impact: Moderate	Training events are held regularly through the life of the programme and documentation from such events will be stored for future use. The greatest benefits to developing capacity will be having the PMEL supplier work closely alongside teams: this will happen throughout the programme and a large number of staff will be exposed, increasing the chance that the capacity is maintained within BHC as a whole. / Net risk: Minor
Safeguarding / FCDO appetite: Cautious / BHC appetite: Cautious	Main supplier or any sub-contracted supplier does not have adequate safeguarding policies or practices in place increasing the risk of harms or abuse. / Likelihood: Possible / Impact: Severe	The supplier will have already completed due diligence as part of the framework, and this will be tested again during procurement. Partner will be required to provide due diligence and assurance of adequate safeguarding policies and practices of downstream partners. / Net risk: Minor
	During data collection or verification exercises, supplier undertakes unethical or exploitative actions. / Likelihood: Unlikely / Impact: Severe	Supplier and subcontractor required to demonstrate how methodology aligns to FCDO Ethical Guidance for Research, Evaluation and Monitoring Activities, and ensure processes in place for monitoring, reporting and acting on safeguarding concerns. They will be required to report numbers of safeguarding incidents to FCDO to help track risk and strengthen mitigation. SRO will conduct spotcheck visits to ensure ethical practices are being adhered to and to assess the levels of risk on an ongoing basis. / Net risk: Moderate
Financial and Fiduciary / FCDO appetite: Receptive / BHC appetite: Cautious	Funds are used for unintended purposes, by lead supplier or downstream partners, resulting in fewer deliverables/ reduced quality, as well as reputation and relationship damage. / Likelihood: Possible / Impact: Severe	The supplier will have already completed due diligence as part of the framework, and this will be tested again during procurement. Partner will be required to provide due diligence and assurance of adequate policies and practices of downstream partners. Suppliers will only be paid in arrears once work is signed off. The SRO will conduct spotchecks to assess how work is being carried out and whether there are any changes to the fraud risk levels. / Net risk: Moderate.
Reputational / FCDO appetite: Cautious / BHC appetite: Cautious	Evidence generated shows poor performance of programmes or interventions, resulting in criticism from media, peers, partners or government. Evaluations are required to be published by the FCDO Evaluation Policy. / Likelihood: Likely / Impact: Moderate	Having independent MEL is opening up programmes to necessary scrutiny: some programmes will not be performing or creating the results we had hoped. Our ability to respond to those results in a positive and proactive way will help mitigate the impact, but some risk remains. / Net risk: Moderate.
	There is a risk that published products are critical of our stakeholders – particularly the Government of Kenya, implementing partners and international peers – and that this has an impact on the BHC relationships with those stakeholders. / Likelihood: Possible / Impact: Moderate	Products will be peer reviewed to ensure language and framing is sensitive to our partnerships, whilst not diluting the findings. If material is very sensitive and threatens security or commercial interests, we will apply for an exemption to not publish. / Net risk: Minor
	Evidence generated by the programme is found to be of poor quality or the results falsified, which undermines its value, or suggests to externals that FCDO is masking its results because it has something to hide. / Likelihood: Unlikely / Impact: Moderate	All design and results documents will be quality assured by external evaluation professionals (EQUALS), as well as undergoing internal BHC scrutiny. The supplier’s performance will be carefully managed to ensure there is little opportunity for such instances. / Net risk: Minor
	Supplier has access to highly sensitive or confidential information: there is a risk of leakage or sharing such material by one or more supplier staff member. This could present a reputational or even a security risk to BHC Nairobi or wider FCDO. / Likelihood: Unlikely / Impact: Severe	Supplier will sign confidentiality agreements; protocols in place to ensure that sensitive information is sufficiently protected and destroyed when the work is completed. Guidance on FCDO’s data policies will be shared with supplier to disseminate. The procurement process will also include the best way to get some supplier staff security cleared, and suppliers will only have access to information at the security level for which they have been cleared. / Net risk: Moderate