Business Case Summary Sheet

Country Plan Summary: / Our vision is a broad and deep UK-Rwanda partnership that delivers UK priorities and supports ambitious goals of inclusive education and women’s empowerment; self-financed by cleaner, greener, inclusive growth and underpinned by free and democratic institutions. We want the UK to be seen as a reliable partner and ensure that Rwanda plays a positive regional and international role on priorities of interest to the UK, including on migration and as Commonwealth Chair.

Title: ACTION (Accelerating Climate Transition and Innovation) Rwanda
Programme summary (100 words maximum): / ACTION Rwanda will build the climate resilience of the most vulnerable to climate shocks, delivering UK International Climate Finance (ICF) commitments to support Rwanda’s Nationally Determined Contribution. It will use a multi-component approach that delivers technical assistance to support catalytic change, invests in Monitoring, Evidence, Research and Learning (MERL) to improve programming, and enhances a Rwandan public sector facility (Intego) to invest in sustainable infrastructure, agriculture, transport and other crucial sectors for adaptation to the worst impacts of climate change.
What is the rationale for UK Aid spending? (200 words maximum): / Rwanda is a Least Developed Country and is already heavily impacted by climate extremes. Future climate change will have large economic costs, estimated at 2.5% of GDP annually by 2050. These impacts will be largest for the poorest and most vulnerable. The cost of inaction on adapting to the realities of climate change in Rwanda are simply too high. / ACTION Rwanda builds on the UK’s previous engagement on climate programming in Rwanda, drawing on its comparative advantages, which are a trusted relationship with government, ability to programme directly through financial aid, and resilience expertise delivered through technical assistance. The programme aligns with Paris Agreement principles and will bolster Rwanda’s NDC delivery. Spend will be 100% ICF, reporting on relevant KPIs.
Programme Value: up to £15 million over 5 years (100% ICF contribution)		Country/ Region or Sector: Rwanda
Department/Country Office confirmation of review processes		HoM confirmation that Departmental processes for BC review have been followed prior to submission
Contact name		Anastasiya Kretova
Threshold for final approval of Business Case: HoM Kigali
Date of Approval of Concept Note:	13/06/2022	Name and role of Approver: / Minister for Africa, Minister Ford
Date of Approval of Business Case:	19/08/2024	Name and role of Approver / Anna Wilson, Development Director and Charge d’Affaires Kigali
Programme Code: 301524	AMP Start Date: 2024	AMP End Date:01/04/2029
Overall programme risk rating:	Moderate
Vault Number:

## Strategic Case
Context and Challenges

Extreme climate events like flooding and droughts are increasing in Rwanda. While such extreme events are often the result of natural climate variability, there is strong evidence that they are increasing in frequency and intensityvi:vi, and that climate change is driving this, as reported in recent attribution studies in East Africa for major droughts.

The country already experiences high levels of year-to-year rainfall variability. While this partially results from naturally occurring events like El Niño – Southern Oscillation (ENSO), the frequency of flooding and droughts is increasing, as indicated below.

Figure 1. Number of people affected by Hazards. 1980-2020. Source World Bank Climate Portal/EM-DAT.

There is a growing pattern of climate hazards affecting the country. Soil erosion is an increasing problem, floods happen almost annually, and there have been several droughts over the last decade. The geographical profile of these risks differs across the country, as shown in the risk maps below. Soil erosion and landslide risks are highest in the West and North of the country, while drought risks are highest in the East. River flood risks permeate the whole country in the main river catchments. Climate models project an increase in the intensity of heavy rainfall events (5-20% precipitation increases during East Africa’s rainy seasons by 2050), with the extent of the increase dependent on global emission pathways.
[note] Climate change impacts on East Africa: a review of scientific literature, WWF, 2006. https://www.wwf.or.jp/activities/lib/pdf_climate/environment/east_africa_climate_change_impacts_final.pdf

Figure 2. Hazard profiles for Rwanda. Left Landslide risk. Centre Flood risk. Right, Drought risk (Season B). Right Flood. Source: MIDIMAR/GFDRR, 2015.
[note] MIDIMAR/GFDRR (2015) Comprehensive Disaster Risk Profiles for Enhancing Disaster Management,

Rwanda is becoming a hotter place to live, with more heat events. Data shows that Rwanda’s average temperature has increased in recent decades, with Meteo Rwanda reporting increases of 1.25˚C in Kigali since the 1970s. There are robust projections that temperatures will continue to rise in Rwanda to between 1°C and 2.5°C of warming by the middle of this century compared to pre-industrial averages. The frequency of hot days and heatwaves is also projected to rise.

Least Developed Countries (LDCs) in Sub Saharan Africa including Rwanda are the most impacted by climate change despite being the least responsible for global greenhouse gas emissions. This is because of the climate-sensitive nature of their economies (e.g., with agriculture being an important sector), closeness to climate thresholds (e.g., for outdoor labour productivity efficiency and crop tolerance levels), and lower adaptive capacity.
[note] Tol R S. J. (2018). The Economic Impacts of Climate Change Review of Environmental Economics and Policy, volume 12, issue 1, Winter 2018, pp. 4–25. doi: 10.1093/reep/rex027

The economic costs of climate change in Rwanda are high, estimated at around 1% of annual GDP by 2030, increasing to 2.5% by 2050. Extreme climate events like flooding and droughts have already had significant macroeconomic consequences in Rwanda. For example:
[note] Kompas, T., V.H. Pham and T.N. Che. (2018). The Effects of Climate Change on GDP by Country and the Global Economic Gains from Complying with the Paris Climate Accord. Earths Future 6, 1153–1173. https://doi.org/10.1029/2018EF000922.
The Northern, Western and Southern provinces experience high levels of rainfall related soil erosion, estimated to cost 2% of agricultural GDP per year in lost productivity ii.
In 2012 the failure of the rainy seasons and a major drought led to a below-average harvest and a 4% decline in 2013 GDP growth due to lower agricultural output in Rwanda. Recovery from the 2023 floods and landslides cost Rwanda $415m.
- The World Bank Agricultural risk assessment for Rwanda iii estimated extreme weather years (floods and droughts) result in up to 10% loss in total agricultural production value.
- Major flood events now occur almost annually and there have been increases in flood related damage (fatalities and property) in Kigali and other major cities iv v.

In the longer-term, after 2050, economic costs will depend on global mitigation agreements, the progress towards the Paris Agreement of 2015, but could increase significantly. Climate change will also affect growth rates, meaning it will take longer for Rwanda to achieve upper middle-income status i.e. it will affect the achievability of Vision 2050. Studies estimate that impacts could be equivalent to almost a lost decade of economic growth by the middle of this century.
[note] Vivid Economics (2020). CLIMATE CHANGE & GROWTH. How will climate change affect South Asia’s economic future. Report prepared for DFID Action on Climate Today / Climate Proofing Growth and Development.

Climate change will disproportionally impact the poorest and affect Rwandan’s human development goals. World Bank analysis indicates that climate shocks disproportionately impact the poor due to overexposure to extreme weather events, higher vulnerability, lower adaptive capacity, permanent impact on education and health, and effects on savings and investment behaviour. The report estimates that Rwanda’s current risk from climate shocks is around $160 million or 1% of GDP ($100 million for risks to well-being and $61 million for risks to assets). Climate change is projected to increase the number of people living in extreme poverty in sub-Saharan Africa by 43 million by 2030 ). This will make it more challenging to achieve Rwanda’s National Strategy for Transformation and Vision 2050, rolling back on poverty reduction and development gains of the last few decades. This will have real-life impact on the lives of the most vulnerable in society and increase the likelihood of humanitarian needs increasing in Rwanda, putting additional strains on global development resources.
[note] Tol R S. J. (2018). The Economic Impacts of Climate Change Review of Environmental Economics and Policy, volume 12, issue 1, Winter 2018, pp. 4–25. doi: 10.1093/reep/rex027
[note] Hallegatte, S et al 2016. Shock Waves: Managing the Impacts of Climate Change on Poverty. Climate Change and Development Series. Washington, DC: World Bank. doi:10.1596/978-1-4648-0673-5. Commons Attribution CC BY 3.0 IGO

The need for FCDO intervention

Investing in climate adaptation and resilience can reduce the economic costs of climate change in Rwanda over the next 20 years. On a global level, mitigation policy is the only way to reduce GHG emissions and avoid the economic costs of warming pathways i.e., above 1.5°C higher than preindustrial levels. Mitigation policies while critical in the long term have relatively limited benefits in the short-term due to the inertia in the climate. The impacts of climate change in Rwanda are already severe, very likely to worsen in the next 20 years, and these can only be reduced through adaptation.
[note] Intergovernmental Panel on Climate Change (IPCC) Global Warming of 1.5 degrees Report, 2019. https://www.ipcc.ch/site/assets/uploads/sites/2/2022/06/SR15_Full_Report_HR.pdf

Figure 3. Estimates of the economic cost of climate change for Africa for different scenarios over time

Source: COACCH (2021). RCPs = Representative Concentration Pathways. RCP2.6 is broadly in line with the goals for the Paris Agreement, while RCP6.0 is a high warming projection. All values are presented for SSP2, a middle of the road Shard Socio-economic Pathway.

Rwanda’s ambitious Nationally Determined Contribution (NDC) sets out the need for significant international support to deliver adaptation priorities. The updated NDC builds on the first Rwandan NDC (2016) and is further expanded in the recently refreshed Green Growth and Climate Resilience Strategy (GGCRS) (2022). Significant international climate finance is needed to deliver the detailed list of actions set out in the NDC, with $5.4 billion needed for adaptation priorities by 2030. The Government of Rwanda has outlined that 40% of these costs will be met by domestic finance and 60% through international support. Substantial investment is therefore required for Rwanda to transition to a low carbon resilient economy.
[note] Republic of Rwanda (2020). Updated Nationally Determined Contribution. May 2020. https://www4.unfccc.int/sites/ndcstaging/PublishedDocuments/Rwanda%20First/Rwanda_Updated_NDC_May_2020.pdf

Climate finance plays a critical role in facilitating transformational adaptation among the poor and the vulnerable. A key objective of climate finance is to support adaptation solutions that improve the well-being of the poorest. However, at present less than 10% of finance from dedicated climate funds explicitly supports local climate action. A priority is to scale up direct access to finance for those who need it most.
[note] Soanes et al. 2017. Delivering real change: getting international climate finance to the local level. International Institute for Environment and Development. London.

Capacity building – including technical assistance and institutional strengthening – is a high potential adaptation ‘Best Buy’. Best Buy analyses have been developed by FCDO experts to compare the effectiveness, cost to benefit assessments and viability of different climate interventions. Delivering effective adaptation is challenging, and its efficiency and effectiveness can be enhanced by institutional strengthening, capacity building and technical assistance. Best Buy analysis identifies such actions as having high benefit to cost ratios (BCRs). For example, capacity building and training in climate sensitive sectors in India and Vietnam had BCRs ranging from 13:1 to 28:1. These are areas where FCDO has a strong comparative advantage having previously developed strong technical assistance facilities in Rwanda in agriculture and social protection.
[note] Sector Best Buys: Climate Change. Research and Evidence Division, FCDO, 2019. https://fcogovuk.sharepoint.com/teams/EADEEDLibraryOpen/Shared%20Documents/Forms/Alltems.aspx?id=%2Fteams%2FEADEEDLibraryOpen%2FShared%20Documents%2FGeneral%2FI%2E%20Best%20Buys%2F2019%2D05%20Best%20buys%20in%20climate%20mitigation%20and%20adaption%2Epdf&parent=%2Fteams%2FEADEEDLibraryOpen%2FShared%20Documents%2FGeneral%2FI%2E%20Best%20Buys
[note] Mullen, J., Gray D., de Meyer, J (2015), Evaluating the impact of capacity building by AICAR. Contributed paper prepared for presentation at the 59th AARES Annual Conference, Rotorua, New Zealand, February 10-13, 2015

There are clear benefits to integrating climate change within development planning (“mainstreaming”). Mainstreaming can ensure that climate is integrated in core development planning, including growth, governance and poverty reduction, and can also help delivery at scale. The evidence identifies critical factors for effective mainstreaming, including the presence of a high-level champion, the involvement of strong ministries, the availability of climate finance, and technical assistance and capacity building support. In many of these are areas FCDO has provided support and has a comparative advantage over other multi- and bilateral agencies.
[note] Economics of Adaptation and Climate-Resilient Development: Lessons from Projects for Key Adaptation Challenges. London School of Economics/ Grantham Research Institute. Watkiss and Cimato http://www.lse.ac.uk/GranthamInstitute/wp-content/uploads/2016/05/Working-Paper-235-Watkiss-and-Cimato.pdf
[note] This is evidenced by successful programmes, including the Rwanda Agriculture Technical Assistance Facility (which is mainstreaming climate change into agricultural development) and the Tanzanian Improving Rural Access in Tanzania programme, which is mainstreaming climate into national and regional government systems.

There is still a relatively low global evidence base on adaptation programming, and a need for better evidence and learning. There is an opportunity for FCDO to lead on analysing adaptation barriers (market, policy or information failures), providing a stronger justification for interventions (and the type of interventions), and on what works in addressing these barriers, noting these will vary for different sectors, risks and problems. This can include support on mainstreaming. Many of these cost-effective adaptation interventions are reliant on capacity and effective coordination at multiple levels of government due to the cross-cutting nature of climate change.

Targeting local climate finance to disaster risk reduction and community-based resilience can reduce the economic impact of climate change in Rwanda. Disaster risk reduction is a no-regret action. Investments that enhance preparedness to disasters, early warning systems , and disaster risk reduction, are all identified as ‘great’ Best Buys for adaptation. A systematic review of flood risk management appraisal (27 studies, mix ex-ante and ex-post) found a BCR of 5:1 for flood related risks. Interventions that target the most vulnerable are likely to have very positive distributional benefits, and community-based climate resilience projects can deliver high BCRs, (evidence from an ex-post analysis of 23 field tested pilots). Similar benefits are delivered by climate smart livelihoods investments, weather and climate services, climate smart extension services, capacity building, and climate smart agriculture, and these interventions have been found to have high benefit to cost ratios.,
[note] ECONADAPT. Assessing the economic case for adaptation to extreme events at different scales. Deliverable 5.1 https://econadapt.eu/sites/default/files/docs/Deliverable%205-1%20approved%20for%20publishing_1.pdf
[note] Shreve, C.M., & Kelman, I. (2014) ‘Does mitigation save? Reviewing cost-benefit analyses of disaster risk reduction’, International Journal of Disaster Risk Reduction, 10(A), 213–235. https://doi.org/10.1016/j.ijdrr.2014.08.004
[note] Mechler, R. 2016. Natural Hazards. 81: 2121. 2016. DOI: https://doi.org/10.1007/s11069-016-2170-y
[note] The Risk to Resilience Study Team. 2009. Catalyzing Climate and Disaster Resilience: Processes for Identifying Tangible and Economically Robust Strategies: Final Report of the Risk to Resilience Study, eds. Moench, M., Fajber, E., Dixit, A., Caspari, E., & Anil Pokhrel, ISET, ISET-Nepal, Kathmandu, Nepal, pp. 328.
[note] Eucker, D., P. Bolte & F. Rahmadana. 2012. The long road to resilience. Impact and cost-­‐ benefit analysis of community-­‐based disaster risk reduction in Bangladesh. Bangladesh Red Crescent Society(BDRCS).
[note] Venton, C.C., L. Coulter, & H. Schmuck. 2013. The Economics of Early Response and Resilience: Lessons from Mozambique Report to DFID.; Venton, C.C., S. Majumder. The Economics of Early Response and Resilience: Lessons from Bangladesh Report to DFID. 2013.
[note] International Fund for Agricultural Development (IFAD). 2016. The Economic Advantage Assessing the value of climate-change actions in agriculture. URL: https://cgspace.cgiar.org/bitstream/handle/10568/77628/Economic_Advantage.pdf?sequence=1
[note] Dehlavi, A., B. Groom, A. Grost, & F. Zaman. 2015. Climate Change Adaptation in the Indus Ecoregion: A Micro-econometric Study of the Determinants, Impact, and Cost Effectiveness of Adaptation Strategies. WWF-Pakistan. Karachi, Pakistan.

The Rwanda Green Fund (RGF) is one of Africa’s climate finance success stories. The RGF (formerly known as FONERWA) was established by the GoR in 2012 as the national fund for climate and environment, programming domestic funding and development partner finance. RGF was awarded the UN Global Climate Action award (Financing for Climate Friendly Investment category) and has high levels of fiduciary management. Since its inception, the RGF has used donor funding (including the UK’s initial £20m capitalisation) to mobilise over $250m in public and private climate finance.

FCDO has an established relationship with the RGF and a comparative advantage in its ability to provide financial aid directly to a Government of Rwanda agency. DFID funded the set-up of FONERWA through technical assistance and fund capitalisation. The project closure report for the DFID/FCDO programme (2020) shows consistent successful delivery. The RGF is now moving to a new phase, maturing to deliver through distinct public and private sector windows, to assist with the financing of the updated NDC. This will require a further evolution of finance and programming.
[note] Programme Completion Review – October 2020. Capitalisation of Rwanda Fund for Climate Change and Environment – FONERWA.

The ACTION Rwanda programme

ACTION Rwanda programme delivers on a key international development priority for the UK to tackle climate change and protect nature, as outlined in the refreshed 2022 Strategy. It responds directly to a vital pillar of FCDO’s 2022-25 Strategic Vision to build strategic partnerships with trusted partners to tackle climate change and delivers against a core part of the cross-party White Paper on UK’s International Development priorities. Following the 2024 UK elections, it is clear that global action on climate change, shared prosperity and growth, and investment in mutual partnership will be crucial for the newly elected UK government – ACTION responds to all those priorities. In Rwanda, taking action on climate change complements our existing priorities to provide social protection to the most vulnerable and alleviate humanitarian risks; strengthen governance of key Government of Rwanda institutions; and improve inclusion. Programme design has closely followed the recently refreshed BHC Kigali Gender Equality and Social Inclusion assessment which has identified groups with particular vulnerabilities.

ACTION aligns with HMG’s Rwanda current Country Plan. As FCDO’s flagship bilateral climate programme in Rwanda it will support the country’s ambition to tackle climate change. It is key to supporting Rwanda as a strategic partner to deliver on core shared COP commitments, for example on adaptation and resilience and climate financing for developing nations. ACTION will deliver UK International Climate Finance (ICF) commitments, support Paris Agreement principles and bolster Rwanda’s NDC delivery. Spend will be 100% ICF, reporting on relevant KPIs.

ACTION Rwanda complements the UK’s existing climate portfolio as well as the work of development partners. Extensive mapping and engagement with other development partners has shown that while areas such as clean energy, financial sector reform and climate-smart agriculture are already relatively well supported, a gap remains around sustainable adaptation and resilience building given the scale of climate change impacts in Rwanda. ACTION builds on the UK’s previous climate programming in Rwanda and draws on the UK’s comparative advantages: a trusted relationship with government, ability to programme directly through financial aid, and adaptation/resilience expertise delivered through technical assistance. We will therefore focus on building on previous successes and further bolstering the capacity of GoR to meet own climate ambitions through this programme.

We have drawn on the lessons learned from previous and existing programmes to design a new adaptation programme that helps address the challenges outlined above and supports the government to implement the NDC. Lessons include bolstering support for strong climate governance and leadership from Government of Rwanda institutions, better inclusion of climate-vulnerable community needs within government delivery and targeted technical assistance to support for better NDC implementation.

ACTION will address three key problems (barriers) to adaptation:

Policy and governance barriers in government, including coordination, that prevent effective adaptation. These barriers can be addressed with technical assistance support.

Information failures around what works, and how to deliver adaptation most effectively and efficiently. These barriers can be addressed through improved evidence and learning, the results of which will allow later programming at scale.

The need to channel adaptation finance to the most vulnerable. This is addressed through a component that provides direct financial aid to the RGF.

ACTION’s support for national-level capacity building and public sector delivery through Intego directly compliments a new East African regional adaptation programme currently under design, which will focus on local-level adaptation needs and nature priorities. ACTION will further complement a broad set of FCDO centrally managed programmes and a wider UK data and evidence offer: complementing Scottish Government-funded climate justice programming for vulnerable communities; utilising latest weather pattern data from the Met Office project; and crucially finding synergies between Intego and Ireme Invest – Rwanda’s private sector climate finance facility supported by the UK through its support for the Taskforce on Access to Climate Finance.

ACTION Rwanda is part of a coherent UK approach to improving access to climate finance in Rwanda. For instance, this programme’s support to Intego Facility will work with the UK’s support for Ireme Invest (funded by a CMP – Access to Climate Finance) to help establish a common platform for financing Rwanda’s climate priorities. This model enables coordinated funding of long-term investments aligned behind national climate plans - moving away from an inefficient project-by-project approach.

Rwanda’s adaptation gaps and ambitions are vast and close partnership working will be essential in order to achieve ACTION’s objectives, maximise UK’s investment and collaborate towards sustainable adaptation in Rwanda. Despite the fact that the programme will primarily provide support directly to the GoR and not via an interim partner (discussed within the Appraisal Case), we will work closely with other bilateral and multilateral partners through existing fora such as Sector Working Groups to capitalise on our joint approach towards Rwanda’s adaptation.

ACTION Rwanda will focus on targeted interventions that build the resilience of the most vulnerable to climate shocks, deliver UK’s climate agenda and COP commitments at scale, and leverage additional finance. It will use a multi-component approach to galvanise public action on climate change. This will include:
1. A technical assistance component to ensure further climate ambition is sustainable and inclusive.
2. A Monitoring, Evidence, Research and Learning (MERL) component to build evidence on what works and use Rwanda to showcase progress with transferable lessons.
3. A flexible component for direct financial aid providing adaptation finance accessible by local communities (through the Intego Facility) that builds on the capacity and evidence from components 1 and 2.

Component 1. Technical Assistance (TA)
In recent years, our technical assistance to the GoR (through bilateral governance programming and CMPs) has helped to strengthen Rwanda’s climate coordination, national planning and delivery towards NDCs. Through the previous programme supporting RGF, we have built the capacity of core functions such as Monitoring and Evaluation (M&E), compliance and inclusion expertise within the Fund. Recently we have provided TA at the request of MINECOFIN to integrate climate considerations throughout the planning of National Strategy for Transformation 2 (NST2). Additionally, we have leveraged CMP (the UK’s financial support for the Taskforce on Access to Climate Finance) funding to stand up Ireme Invest – a private sector investment facility also housed within RGF (complementing Intego’s public focus) – and strengthen its governance arrangements.

As a trusted partner providing recent TA for essential capacity building, we are well placed to add expertise to progress Rwanda’s climate ambitions. We will use a flexible and demand-led approach to target TA where it is most needed: whether to RGF, MINECOFIN or another GoR entity to improve the enabling environment and progress delivery towards Rwanda’s NDCs.

Component 2. Monitoring, Evidence, Research and Learning (MERL)
A dedicated MERL component will provide the evidence gathering and learning to help improve the programming for both components 1 and 3. This will strengthen the evidence base and improve the delivery of climate programming in FCDO and across government in Rwanda, and play a pro-active role in overseeing progress on projects mobilised with FCDO co-financing. Examples of activities under this demand-driven component will include: technical dialogues to unlock complex adaptation issues, research into what works and why in the public resilience space, and lesson sharing with others and deep-dives into unlocking financing within hard-to-reach sectors such as infrastructure and public transport. An early piece of research may also be centred around calculations on the cost of inaction, which would spur on further investment in adaptation. Given Rwanda’s regional and international convening power, this component could also be used for learning into what works in the relatively under-researched adaptation space for sharing with others through fora such as COP conventions, Africa-focused meetings or via existing networks such as the Taskforce on Access to Climate Finance.

Component 3. Direct Financial Aid for Adaptation
The final component provides direct financial aid for adaptation, aligned to key priorities in the NDC in the climate resilience space. This would include targeting adaptation to the most vulnerable and providing support to the RGF through the Intego (NDC) Facility. The Facility works through proposal rounds to provide public sector financing for key districts and public sector bodies to deliver on the adaptation priorities outlined within Rwanda’s NDCs. The Facility is a multi-partner fund, with a strong pipeline and ability to absorb much more donor funding than what is currently being offered. Working through this Facility will enable the increased domestic capability of the GoR to respond to the scale of the adaptation challenge whilst supporting the most vulnerable communities and areas.

Programme Impact and Outcomes

The programme will deliver the following high-level objectives:

Impact: “Rwandans are more resilient to climate change”.

Outcomes:
- ‘Strengthened institutional capacity and more effective adaptation programming within Government’
- ‘Improved evidence and learning leading to more effective, adaptation and resilience focused, FCDO programming in Rwanda’
- ‘Strengthened resilience of poor and vulnerable households to withstand current and future weather and climate related shocks and stresses’

Outputs:
- GoR technical assistance requests responded to in a timely and effective manner
- Intego facility replenished and functioning as an effective public sector financing facility, with links made to other donors and technical assistance offers to the extent possible
- Increased connections made to other HMG programming that demonstrates a cohesive UK approach to climate and environment priorities in Rwanda
- Effectiveness of Intego is maximised through UK and other partners support, for example through fulfilling recommendations from the Fiduciary Risk Assessments, targeted research and evidence and influencing
- Research published that informs policy on national planning and public sector

The expected ICF results will be reported against the relevant ICF KPIs such as:

- KPI1 Number of people supported to better adapt to the effects of climate change.
- KPI 11 (Amount of public finance mobilised)
- KPI 15 Extent to which ICF intervention is likely to have transformational impact (scorecard to be developed)

Theory of Change
Given the scale of the climate change impact on the most vulnerable communities in Rwanda, the cost of inaction is simply too high. If we invest in better data and evidence, strengthen the Rwanda Green Fund (RGF) and the Intego facility, and provide effective technical assistance and capacity building to enable the Government of Rwanda (GoR) to adapt to climate impacts, then the most vulnerable communities in Rwanda will become more resilient to climate change. This will contribute to Rwanda achieving its poverty reduction and development goals, thereby meeting Official Development Assistance (ODA) eligibility objectives.

The assumptions underpinning this Theory of Change include:
Political will to meet Rwanda’s climate commitments remains strong, particularly in light of additional challenges around poverty reduction, youth employment and economic growth which could be seen as competitive to climate goals.
- Rwanda’s governance and institutions responsible for carrying out their environmental obligations remain strong
- Sound fiscal management and budgetary distribution means that an appropriate level of domestic funding is maintained on climate and environment commitments
- Policy decisions and funding levels of other Development Partners are maintained to supplement Rwanda’s journey towards achievement of its NDCs
- Rwanda’s NDCs are revised in line with future UNFCCC milestones (for example the 2025 revision) and goals/indicators are aligned to Rwanda’s growth and capacity
- Rwanda maintains a steady green growth towards becoming a Net Zero economy by 2050
- Rwanda continues to strengthen its Monitoring, Results and Verification (MRV) systems

Simple example pathways of the Theory of Change include:
- The Intego facility collects household data to verify outcome indicators, providing evidence of increased resilience among vulnerable communities. This evidence supports the continuation and improvement of adaptation solutions.
- RGF evaluates the effectiveness of adaptation solutions, generating lessons and recommendations for future initiatives. This leads to better decision-making and informs policy recommendations.
- Technical assistance and capacity-building efforts enhance the GoR's ability to plan, react, and adapt to climate impacts. This results in improved resilience and evidence-based decision-making.
- The Intego facility and UK programming assess how well climate considerations are integrated into development activities. This provides evidence of alignment with strategic climate objectives and supports the justification for continuing or improving these activities.

We will measure our results through a range of existing data including:

- Rwanda’s reporting against Sustainable Development Goals (SDGs) progress
- Rwanda’s reporting to UNFCCC and other international bodies, including against its NDC delivery (towards 2030 and beyond)
- Other national strategy reporting including against the National Strategy for Transformation 2 (NST2, towards 2029), Green Growth and Climate Resilience Strategy (GGCRS, towards 2050) and Imihigo indicators where appropriate (for example when Intego funding is allocated to districts)
- Reporting from Rwanda Green Fund through its formal structures, including Auditor General reporting, Board of Directors reporting and specific partner reporting on the impact of the Intego facility
- Aligning our reporting requirements with other Development Partners as much as possible to ease the administrative burden on GoR and avoid duplication

We will carry out independent monitoring using the MERL component to verify results on a periodic basis, aligning reviews with independent audits of other development partners to the extent possible.

Gender Equality and Social Inclusion

The British High Commission in Kigali is an Africa Equality and Inclusion Trailblazer within FCDO, mainstreaming vulnerability impact considerations throughout our operations. We have committed to conduct consultations with vulnerable groups as part of each new programme design. As part of design for ACTION, we have participated in consultations with civil society organisations (CSOs) working in the climate change and environment space through numerous fora:
- In partnership with the Swedish development agency (SIDA) during the conclusion of SIDA-supported CSO project with the RGF in March 2023.
- During the launch of the Scottish Government-supported climate justice project delivering through SCIAF and Trocaire in partnership with multiple umbrella and local CSOs in February 2024. The project will be working with climate vulnerable communities in three districts across the Western Province.
- Engagement with civil society representatives at British High Commission hosted events such as the Social Inclusion Day in January 2023, and Inclusion Bazaar in March 2023. Similar engagement at wider fora such as preparation workshops for COP28 and COP29.
- Learning from consultations conducted during other programme development at the British High Commission, for example for the new GIRL education programme and Twiyubakire governance programme.

Additional consultation with vulnerable groups representatives were not conducted due to ACTION’s focus on strengthening national level systems and working through the Government of Rwanda to deliver on climate priorities, and the risk that this might set undue expectations of direct support to the CSOs.

The British High Commission in Kigali’s GESI analysis points to individual and community vulnerabilities in Rwanda based on six characteristics: gender, age, disability, LGBTQI+, refugee status and historically marginalised persons. These characteristics often intersect to multiply vulnerability to shocks, including those driven by climate change (for example, research shows that experiences of climate change are highly gendered (Daoud, 2021) Women are particularly affected by climate change in Rwanda because the majority of smallholder farmers are female, the majority of women rely on farming as their primary source of income, and women are primarily responsible for water availability and food security at the household level).

We will continue to use our understanding of vulnerabilities to press the Government of Rwanda to be more inclusive, open to a diverse range of needs based on distinct vulnerabilities and respond to the varying needs of vulnerable communities. We have already identified a number of gaps within RGF’s operations and governance arrangements (for example, needing a greater level of gender, social inclusion and safeguarding expertise) through our latest fiduciary risk assessment (2023) and made recommendations for improvements. These largely echo recommendations from other partners including SIDA and Danida. We will use a united development partner voice to steer Government of Rwanda’s operations to be more considerate of GESI. Within ACTION specifically, we will develop concrete GESI goals for each of the 3 components within the first year of the programme.

Compliance

As discussed above, our strong emphasis on GESI inclusion and pushing GoR to be more responsive to vulnerable community needs would ensure that ACTION is able to feed into the annual Public Sector Equality Duty assessments and is compliant with the Disability PrOF Guide. We will go above and beyond essential compliance on equality where possible, capitalising on the existing strong partnerships with GoR to push for greater focus on vulnerable groups and provision for the communities most impacted by climate change. We will collaborate with centrally managed programmed on data and evidence where possible, and link to programmes such as AT2030 (using technology to increase disability inclusion, including for example during disasters and sending alerts in accessible formats) to ensure the whole of UK offer on climate and environment is coherent and progressive on inclusion issues.

ACTION Rwanda will be fully compliant with FCDO’s Partnership Principles and respond directly to the new UK Government’s priorities around respectful partnerships and close collaboration on development objectives. We will ensure that all ACTION Rwanda partners (including our internal teams) are fully aware of our Safeguarding procedures, risks around Sexual Exploitation, Abuse and Harassment (SEAH) and actively monitor and mitigate these risks. Our insistence on compliance, close monitoring and reporting will help to ensure that we remain compliant with our legal Safeguarding obligations. Further discussion on our risk management processes is set out in the Management Case.

## Appraisal Case
Intervention versus ‘do nothing’

The ‘do nothing’ option was rejected at concept note stage as it will result in a reversal of previous gains made through the multiple FCDO climate interventions outlined in the Strategic Case. It will moreover undermine the UK’s current position as a key partner to GoR on the agenda, diminishing our ability to influence GoR and development partners’ climate investments. It would increase the resource gap for financing Rwanda’s NDC, slowing growth and lessening progress towards poverty reduction, as well as reduce the ability of the GoR to deliver on its existing climate commitments.

Under the ‘do nothing’ scenario, the economic costs of current climate variability and climate change in Rwanda increase, as shown in Figure 3 above. Rwanda will continue to experience major climate shocks, particularly floods and droughts, with high economic costs. These are estimated to be approximately an additional 0.5 to 1% of GDP loss each year on average by 2030. This will lead to a continued pattern of disaster and humanitarian response. Further, these losses fall disproportionately on the poorest and most vulnerable. Without intervening, the current pattern of climate shocks will undermine development gains achieved to date – including through previous UK programming.

The options for FCDO intervention

As part of business case development, five possible programme components have been identified and appraised. These are not mutually exclusive. In appraising them, we consider their potential impact, value for money, FCDO comparative advantage, and synergies/overlap with other HMG programmes.

- Component 1: Technical assistance to government agencies to improve climate outcomes. One example may be TA to integrate climate change in development planning and budgeting (mainstreaming), which would help integrate climate into core public financial management and align the NDC to national development pathways.
- Component 2: Research, evidence, and technical assistance support for Cross Cutting NDC development and delivery, or a thematic cross government focus (e.g. on pathways for mobilising further private sector investment). This would involve strengthening public sector incentives through MoE, RGF, REMA or other agencies.
- Component 3: Programming to support climate adaptation in the public sector. This would build on previous catalytic support from FCDO, such as to the RGF, and would allow a scale-up of adaptation delivery and results.
- Component 4: Support to the Rwanda Green Investment Facility (“Ireme Invest”) (a combination of a project preparation facility led by RGF and a credit facility led by Development Bank of Rwanda (BRD)). This seeks to leverage private sector climate finance in Rwanda.
- Component 5: Support to develop a carbon market and carbon credit facility (with the Rwanda Environmental Management Agency (REMA) and transaction hub (with the RGF). This would use Rwanda’s strong governance and track record of delivery to deliver an exemplar for a national carbon market facility.

An initial appraisal of these five components was undertaken. Two components have been discounted from consideration:

Component 4 is being taken forward through other FCDO initiatives. The Taskforce on Access to Climate Finance – which the UK co-chairs with Rwanda - includes Rwanda as a pilot country. The Rwanda country trial focuses on mobilising and aligning private sector financing behind national climate priorities. The UK’s support for the trial already supports the new Rwanda Green Investment Facility (now named Ireme Invest) through a £7m investment (2023 – 2027) to prepare project pipelines and attract private sector climate funding. Therefore, the ACTION programme will not work on component 4.

For Component 5, FCDO has limited comparative advantage on carbon markets in Rwanda (despite CMPs including Ci-Dev working regionally), with other development partners possessing greater technical expertise and seeking to provide funding.

Having consulted with GoR, analysed other development partners’ activities, and assessed FCDO’s comparative programming advantages, it is recommended that the ACTION programme will work on a combination of Components 1, 2 and 3 from the list above:
- Component 1 provides technical assistance to support the direct financial support.
- Component 2 (“MERL”) delivers research and evidence to ensure lessons are documented and shared.
- Component 3 provides direct adaptation support to public sector institutions and builds on the UK’s strong previous track record.

Assessment of the three ACTION components

We now look at the three components to assess the evidence for their inclusion in the ACTION programme.

Component 1 – technical assistance
A review of the literature on capacity building TA in the area of climate change was conducted and is summarised in the box below.

Capacity building and development for cross-sector NDC implementation	Capacity building and institutional strengthening is generally reported as being extremely effective but is very challenging for valuation. Some international reviews have identified high economic benefits and a number of context-specific studies have estimated benefit-cost ratios (BCRs), reporting results of >10:1, though these are not specific to Africa. One study from South Africa, where institutional options were compared against hard options in Durban in the context of adaptation and found institutional support had among the highest BCRs. / Information dissemination and capacity building have high economic benefits and these ‘soft’ options increase significantly under higher climate change. Furthermore, a number of studies report that capacity building and institutional strengthening lead to higher benefits for outcome-based options (e.g. farm-level interventions) as they enhance the effectiveness and efficiency of these interventions. / A number of studies report higher BCRs when capacity building/institutional strengthening are combined with outcome orientated adaptation options. A portfolio of improved seeds, soil and water conservation, better extension services and improved climate information, was most effective in enhancing agricultural production in climate vulnerable areas in countries studied.
[note] Economics of Adaptation and Climate-Resilient Development: Lessons from Projects for Key Adaptation Challenges. London School of Economics/ Grantham Research Institute. Watkiss and Cimato http://www.lse.ac.uk/GranthamInstitute/wp-content/uploads/2016/05/Working-Paper-235-Watkiss-and-Cimato.pdf
[note] Mullen, J., Gray D., de Meyer, J (2015), Evaluating the impact of capacity building by AICAR. Contributed paper prepared for presentation at the 59th AARES Annual Conference, Rotorua, New Zealand, February 10-13, 2015
[note] Cartwright, A., Blignaut,J., De Wit, M.,, Goldberg, K., Mander, M., O'Donoghue, S., and Debra Roberts, D (2013). Economics of climate change adaptation at the local scale under conditions of uncertainty and resource constraints: the case of Durban, South Africa. Environment and Urbanization 2013 25: 139. DOI: 10.1177/0956247813477814
[note] Anton Cartwright, James Blignaut, Martin De Wit, Karen Goldberg, Myles Mander, Sean O'Donoghue and Debra Roberts (2013). Economics of climate change adaptation at the local scale under conditions of uncertainty and resource constraints: the case of Durban, South Africa. Environment and Urbanization 2013 25: 139. DOI: 10.1177/0956247813477814
[note] The Risk to Resilience Study Team (2009): Catalyzing Climate and Disaster Resilience: Processes for Identifying Tangible and Economically Robust Strategies: Final Report of the Risk to Resilience Study, eds. Moench, M., Fajber, E., Dixit, A., Caspari, E., & Anil Pokhrel, ISET, ISET-Nepal, Kathmandu, Nepal, 328 pp. Anton Cartwright, James Blignaut, Martin De Wit, Karen Goldberg, Myles Mander, Sean O'Donoghue and Debra Roberts (2013). Economics of climate change adaptation at the local scale under conditions of uncertainty and resource constraints: the case of Durban, South Africa. Environment and Urbanization 2013 25: 139. DOI: 10.1177/0956247813477814
[note] Di Falco S. and M. Veronesi (2012) How African Agriculture Can Adapt to Climate Change? A Counterfactual Analysis from Ethiopia. University of Geneva, Mimeo

Component 2 – monitoring research and learning
Monitoring of results and evaluation is a key part of the success of this programme, ensuring value for UK taxpayers’ money in delivering TA and direct financial aid. This component will go beyond evaluation however and provide crucial evidence for strengthening Rwanda’s climate governance further and sharing lessons with others. Rwanda has ambitions to be a regional climate exemplar and given its market size and typography, it is an excellent testing ground for innovative adaptation approaches to replicate globally. Initiatives trialled out here have already been shared with others, for example Uganda is setting up a climate finance vehicle following the example of Rwanda’s Green Fund (and replicating the success of UK’s early investment into the Fund). This component will remain flexible and fund studies, research and technical events to further enhance UK’s position as a trusted partner on climate and environment for Rwanda and ensure Rwanda’s approach to adaptation and resilience remains innovative and coherent.

Component 3 – direct support
Direct financial support would support Rwanda’s NDC priorities. A review of the economic benefits of such a wide range of issues would be unfeasible. However, it is possible to review some specific priorities which the direct support could target, especially as Rwanda becomes more frequently affected by extreme weather events. The box below summarises the evidence in relation to two likely uses (as these are of high priority to Rwanda) of UK direct support: disaster risk monitoring, and early warning systems. This is followed by an economic analysis of the direct support.

Disaster risk monitoring (DRR) and management	Disaster risk reduction (DRR) and management. There is robust international literature on the economic benefits of disaster risk reduction and management. General reviews find high BCRs, e.g. such as studies by World Bank (2012),and in systematic review by Mechler (2016): the latter (based ex ante and ex post) found average BCRs of 5:1 for flood related risks, and 4:1 for windstorms, but none of these were for Africa. Shreve and Kelman (2014)undertook a review of the cost-benefit ratios for disaster risk reduction, which highlighted the potentially high benefits, but also the challenges and limitations of such analysis. It found an extremely wide range of BCRs for DRR, with maximum values from 3:1 to 60:1 (with one outlier above this). However, this only included one study in Africa, with the study of Venton et al. (2010) for drought in Malawi (maximum BCR 24:1) and one outlier with a very high BCR in Sudan. / Cabot Venton et al. (2013) reviewed benefit cost ratios for 23 field tested community-based adaptation DRR pilots in terms of humanitarian aid avoided from social protection and early intervention worldwide, finding BCRs of 1.8-2.7:1. Incorporating the value of avoided losses increases these BCR estimates to 2.3-3.3:1. This includes interventions in Africa for Kenya and Sudan (not quantified), for Malawi for drought with crop diversification, soil and water conservation, and drought-resilient livestock (BCRs of 24:1) and Gambia for drought ex post finding BCRs of seeds and fertilizer (3.3); fire belts (38.7); and tree-planting (2.6), and Kenya for drought of 1.5 – 3:1.
Weather and climate information services, including early warning systems.	This includes a range of services including hourly, daily and short-term weather forecasts (e.g. up to 10 days) through to climate services (e.g. seasonal forecasts). There are a number of international reviews of the benefit to cost ratios of these services that show high BCRs (Clements et al. (2013), WMO (2015), ECONADAPT (2017) which generally report average values around 10:1 and a range from 2:1 up to 36:1. Economic benefits arise from the use of services to improve decisions (the value of information). These provide immediate benefits, and these usually increase with climate change, though there is an increasing focus on extending W&CIS to adaptation services. Values vary with site and location, and benefits depend critically on the delivery of climate information along the value chain (forecast accuracy, communication and reach, uptake and use, effectiveness). While historically the focus has been on agriculture, W&CIS can provide important benefits for multiple sectors, e.g. energy, water, tourism, health and others. / Early warning systems can include short-term (hourly to weekly) forecasts of major extreme events, such as floods, as well as longer term seasonal early warning, e.g. for droughts. These are generally reported as having high BCRs, e.g. with the GCA (2019) reporting a value of 9:1. Law (2012), cited in WMO (2015) estimated BCRs of 3:1 to 6:1 for the Benefits of Ethiopia’s Livelihoods, Early Assessment and Protection (LEAP) drought early warning and response system. Watkiss et al., (2021) undertook a CBA for marine early warning information on Lake Victoria, and found a BCR of 16:1, driven by the combination of avoided deaths and fuel savings. Benefits of EWS are projected to increase under future climate change, because of increasing events, although costs and residual damage will increase as well. These EWS have focused on flood and windstorm related hazards. In the OECD, there is a greater focus on heat alert warnings, which have been found to have high BCRs (greater than 10:1) (Ebi et al., 2004: Hunt et al., 2016: Chiabai et al., 2018 ) and there may be some potential for similar system in major African cities. / Strong evidence exists on the benefits of investing in Early Warning Systems (EWS) for enhancing food security in. In Ethiopia, investing in a drought EWS, which would reduce livelihood losses and dependence on assistance, has a BCR of between 3:1 and 6:1. The study found that the BCR of improving national hydrometeorological services in developing countries range from 4:1 to 36:1. In terms of cost-benefit analysis, disaster risk reduction has been estimated to amount in savings of $7 (sometimes $4-7) for every $1 invested. / A study by NEF Consulting (NEF, 2016) for Meteo Rwanda estimated a benefit to cost ratio of weather services strengthening of 4:1, though this was dominated by EWS and reduced fatalities. There has also been a major USAID-funded project – Rwanda Climate Services for Agriculture (RCSA) - that has improved weather forecasts for farmers. This four-year project ran from 2016 to 2019. The CGIAR Research Program on Climate Change, Agriculture and Food Security (CCAFS) funded an evaluation of RCSA project, published in 2020 (Birachi et al., 2020). / A socio-economic benefit assessment of the WISER Enhancing Climate information Services for Agriculture and Disaster Risk Reduction in Rwanda (Iteganyagihe Ryacu) project was undertaken (WISER, 2021). The total estimated benefits (undiscounted) of the Rwanda national project were estimated at £19.2 million, with annualised benefits of £3.4 million/year. The cost- benefit analysis estimated a benefit to cost ratio of 23:1, although did not include farmer action.
[note] World Bank (2012). A Cost Effective Solution to Reduce Disaster Losses in Developing Countries: Hydro-Meteorological Services, Early Warning, and Evacuation. Stéphane Hallegatte. Policy Research Working Paper 6058.
[note] Mechler, R. Nat Hazards (2016) 81: 2121. https://doi.org/10.1007/s11069-016-2170-y
[note] Shreve, C.M., & Kelman, I. (2014) ‘Does mitigation save? Reviewing cost-benefit analyses of disaster risk reduction’, International Journal of Disaster Risk Reduction, 10(A), 213–235. https://doi.org/10.1016/j.ijdrr.2014.08.004
[note] Courtenay Cabot Venton, Lorraine Coulter, Hanna Schmuck (2013). The Economics of Early Response and Resilience: Lessons from Mozambique Report to DFID. Courtenay Cabot Venton, Shuman Majumder (2013). The Economics of Early Response and Resilience: Lessons from Bangladesh. Report to DFID. Courtenay Cabot Venton, Lorraine Coulter (2013). The Economics of Early Response and Resilience: Lessons from Niger. Report to DFID.
[note] Clements, J et al (2013). The Value of Climate Services Across Economic and Public Sectors. Report to the United States Agency for International Development (USAID). Available at http://www.climate-services.org/sites/default/files/CCRD-Climate-Services-Value-Report_FINAL.pdf
[note] WMO (2015). Valuing Weather and Climate: Economic Assessment of Meteorological and Hydrological Services. World Meteorological Organization, Geneva.
[note] ECONADAPT (2017). “The Costs and Benefits of Adaptationˮ, results from the ECONADAPT Project, ECONADAPT consortium, http://econadapt.eu/.
[note] Law, A., 2012: Evaluating the cost-effectiveness of drought early warning early response systems for food security: A cost-benefit analysis of Ethiopia’s Livelihoods, Early Assessment, and Protection (LEAP) system. Submitted in partial fulfilment of the requirements for the degree of Master of Science in Environmental Change and Management. Environmental Change Institute, University of Oxford
[note] Ebi, K.L., Teisberg, T.J., Kalkstein, L.S., Robinson, L., and R.F. Weiher (2004), “Heat Watch/Warning Systems Save Lives: Estimated Cost and Benefits for Philadelphia 1995-98”, Bulletin of the American Meteorological Society, August, 1-7.
[note] Hunt, A., Ferguson, J., Baccini, M., Watkiss, P., Kendrovski, V. (2016). Climate and Weather Service Provision: Economic Appraisal of Adaptation to Health Impacts. Climate Services. DOI: 10.1016/j.cliser.2016.10.004
[note] Chiabai, A., Spadaro, J.V., Neumann, M.B., 2018. Valuing deaths or years of life lost? Economic benefits of avoided mortality from early heat warning systems. Mitigation and Adaptation Strategies for Global Change. https://doi.org/10.1007/s11027-017-9778-4
[note] World Bank (2017). Assessment of Food Security Early Warning Systems for East and Southern Africa. https://documents1.worldbank.org/curated/en/195261520889090479/pdf/Assessment-of-food-security-early-warning-systems-for-East-and-Southern-Africa-final-report.pdf
[note] Building Flood Resilience Capacities in Rwanda. GGI & GCF Report. (2020). https://www.greenclimate.fund/sites/default/files/document/rwanda-nap-gggi.pdf
[note] NEF (2016). Forecastive Cost Benefit Analysis of the ‘Strengthening Meteo Rwanda’s Weather and Climate Services to Support Development’ Project. Report by New Economics Foundation (NEF) Consulting for Meteo Rwanda.

Based on the above, the business case assumes Benefit Cost Ratios (BCRs) of 4.1, with a range of 2:1-6:1 and Economic Internal Rates of Return (EIRR) in excess of 20%.

Decisions within ACTION programme components

The detailed analysis of the programme options has considered a number of alternative options within the three components of the ACTION programme. These decisions are:
- Decision A: Within component 1 should the TA be delivered to RGF or MINECOFIN?
- Decision B: Within components 1 & 2 should the TA and MERL (a) have a medium term (2- or 3-year plan) set out in advance, or (b) be more flexible with short-term (e.g., 6 month) priorities agreed and then delivered?
- Decision C: Within component 1 should the TA be delivered through (a) an intermediary (such as DAI), (b) directly by GoR, or (c) some combination?
- Decision D: Within component 3 should the direct support for public sector be through (a) the RGF’s Intego facility, or (b) the World Bank’s Strategic Programme on Climate Resilience in Rwanda (SPCR) route?

Each of these four decisions (A, B, C, D) is taken in turn.

Decision A – TA to RGF or MINECOFIN?
If the technical assistance was provided to RGF, it would support key areas tha have previously been identified as priorities, notably around improving value for money, further resource mobilisation, increasing inclusion and sustainability and MEL (as identified in the project closure report for the previous support to RGF by DFID/FCDO). TA and institutional strengthening in these areas would improve the efficiency and effectiveness of RGF programming, leading to additional economic benefits. Investing in resource mobilisation and financing would improve the capacity of GoR to access international climate funds. The current pipeline for RGF is assumed to be $150 million over the near future. This is comprised of Intego (which has considerable funding from KFW, but with an increasingly strong project pipeline requiring further donor funds) and Ireme Invest which partners RGF with BRD to increase private sector finance flows.

If the technical assistance was provided to MINECOFIN, it would provide support for mainstreaming climate considerations across national planning. Recent environmental and climate budget tagging has identified that the Government of Rwanda budget currently involves expenditures of 2.6% on climate and environment (INDP PEAS, 2020). TA and institutional strengthening in these areas would therefore improve the efficiency and effectiveness of this existing expenditure, improving the delivery of economic benefits from climate integration. This would be done by increasing outcomes per £ spent in climate relevant sectors through better programme design, coordination and delivery.

In either case, it is assumed that the TA would improve the efficiency and effectiveness of climate spend by GoR. The economic analysis is shown below. This table shows that TA to either RGF or MINECOFIN delivers a substantially positive BCR. Therefore, the choice of where to provide TA, which may vary through the lifetime of the ACTION programme, can be driven by other factors (e.g., the location of other DP support, or how best to support other ACTION components) with confidence that it will provide positive returns.

TA assumptions:
Business and proposal development for resource mobilisation (to deliver the $0.25 billion of potential climate finance). This will include building capacity of the team for in-house resource mobilisation to ensure the sustainability of the fund.
Support to the fund for the management of these funds in early years (to support its role as the lead entity for fund management and reporting). Ensure function at a level to ensure get the finance.
Targeted positions (including risk management (legal and safeguards), private finance expert, financial forecasting, economic and financial, safeguards), to improve the strategic delivery and fund delivery
Call-down technical experts (including sector specialist), to provide targeted TA to develop the key strategic priorities (Design and support) through the strategic process and for proposal development
Value for money, to ensure inputs are minimised (economy) and outputs and outcomes deliver efficiency and effectiveness. Key focus on internal capacity

Decision B – timeframe of MERL plans
There is a choice around setting a concrete plan for the MERL component during the development of this Business Case or maintaining flexibility and agreeing plans on a rolling 6-month basis.
1. An established 5-year MERL plan at the outset of the programme would provide certainty and continuity on supporting the other two programme components. Budget planning and spend forecasting would be much easier operationally. However, given the low global evidence base on what works in adaptation, innovation within Rwanda and the unpredictable nature of future climate and environment tools (global climate finance initiatives such as Loss and Damage, cooperation between different regional players and future priorities for international commitments around COP meetings for example) means it is difficult to say at this time which research or learning products will support Rwanda’s adaptation and resilience over the next 5 years.
2. A flexible approach to addressing monitoring, research and learning needs would result in much less budgetary and spend certainty. It would also require ongoing engagement between UK teams and GoR on the latest research priorities and to agree workplans. However, this option would provide the flexibility needed to respond to the latest data and evidence developments, provide timely research in a fast-paced adaptation space in Rwanda and share learning with the global community on topics which are still relatively under-researched. We already have experience in working this way by utilising the BHC governance programme (SPARC) to respond to research and learning requests from GoR, most recently on pathways for offering green financing through community-level savings banks (SACCOS) in early 2024. This model will be preferable to deliver on ACTION’s objectives to be a flexible and agile programme in an ever-evolving space of climate adaptation.

Decision C – who should deliver TA?

As discussed in earlier sections, the technical assistance component will need to be agile and responsive to the needs of GoR and the climate and environment context at any given point – for example sometimes more focused on disaster responsiveness and at other times building up GoR’s capacity to mainstream climate considerations within line ministries. We have options for delivering the technical assistance through a number of vehicles:
1. A technical assistance provider (private sector or otherwise)
2. As direct financial aid to the GoR (most likely RGF) to enable own hiring of TA consultants
3. A combination of the approaches above

Before the development of ACTION as a standalone programme, we have delivered on our UK-Rwanda climate objectives through the governance (SPARC) programme’s demand-driven TA facility on a number of standalone capacity building requests, for example to include climate considerations into national planning. This was delivered through a commercial contract with DAI and ensured that timely support was delivered to meet GoR’s expectations. This also ensured that as the donors, we had greater oversight around decisions such as timelines and expertise of appointed consultants. Securing a standalone commercial contract can be expensive however and may not provide the best value for money if it is not utilised regularly, particularly as the demand-led TA requests may be infrequent and unpredictable in nature.

We have the option to provide funding for technical assistance directly to the GoR to enable own recruitment of expertise as needed. Rwanda Green Fund for example already have an extensive roster of consultants to support different thematic needs as required, and there is a similar consultant roster available to MINECOFIN. As the UK, we have extensive experience of enabling GoR to procure own expertise, for example through the governance and PFM programme, although some delays in procurement processes mean that this may not always be the most efficient route. This enables targeted support to be delivered in a timely manner and empowers GoR entities to make own decisions over their capacity needs, thus strengthening government institutions. However, providing direct funding for GoR to recruit for own technical experts means that the UK would have less visibility and influence over the details of assistance offered.

Ultimately, the nature of capacity and technical needs will likely change over the lifetime of this programme, requiring different approaches at different times. Therefore, a combination of the two approaches is recommended to ensure flexibility. In practice, this would likely mean using an existing call-down FCDO facility for year or two year-long assignments, potentially combining TA needs with other programmes within our portfolio (for example the governance and social protection programming) and for distinct pieces of work providing funds for consultants directly to GoR to procure for own needs. Further modalities are discussed within the Commercial Case. Whichever delivery modality is chosen during a given year, an annual TA workplan would be agreed based on UK-Rwanda Partnership Principles in consultation with the Development Director and relevant teams across the office such as the governance and social development colleagues to ensure that capacity building for GoR is complementary to other efforts. The annual workplans would also be agreed with the chosen provider, either appointment by FCDO or via GoR.

Decision D – how should direct support be delivered?
This component of the ACTION programme will provide around £12 million of core funds. This funding would either provide direct financial aid to RGF, or to the World Bank as part of the Strategic Programme for Climate Resilience (SPCR).

The first option is to programme this funding through RGF. RGF already manages a significant portfolio of climate finance and is well equipped to implement. It has a track record of value for money delivery. Funding would build on previous UK investments (into FONERWA as RGF was known then), safeguarding previous investment and enabling the fund to strategically use new finance to deliver even greater impact. In order to deliver direct support to the public sector the ACTION funds would be provided to Intego Facility – RGF’s public sector climate finance vehicle. Intego (and its private sector twin – Ireme Invest) follow the 10-year expansion and maturity of Rwanda Green Fund’s operations and now deliver as separate, but closely related, funding windows. Intego provides funding to public sector institutions (and PPPs where appropriate) to deliver against key NDC priorities. It is an adaptable window, able to respond to the most pressing adaptation needs in Rwanda – from disaster preparedness for districts and communities to resilient public transport expansion. Intego works through regular bidding windows where public sector entities can access funding for their projects. Intego is replenished through a range of domestic and international funding (mirroring NDC commitments), with KfW being the biggest international donor since 2022.

Channelling funds through RGF would mean that there is significant potential to scale up, replicate and sustain results. By funding RGF’s Intego facility, ACTION could create linkages with other (existing and planned) adaptation priorities, for example link to the latest data and evidence or complement private sector initiatives. Supporting an existing facility would also build institutional ownership and have the potential for multiplier effects, for example by investing in PPPs or scaling up programming through global (GCF, CIF and the like) investments and co-funding. Funding through this channel would align to Rwanda’s NDC and the development of resilience in national economic growth strategy. This will create high country ownership.

Use of a government fund and support of public-sector interventions will transfer and mainstream the knowledge generated and lessons learned and ensure that the necessary capacity is developed within local and national institutions. This will strengthen the technical capacity of key government agencies, local NGOs, cooperatives and other key stakeholders to support new climate-resilient approaches and technologies and respond to climate change.

The risks of the RGF approach are low. Rwanda has established strong institutional frameworks and RGF has a reliable track record for implementing climate change projects. All the necessary policies and legal frameworks are in place including a fund that can absorb and disburse funds and monitor interventions. The UK has supported the organisation (as FONERWA) for many years and there is an existing MoU between a central FCDO programme and RGF (to fund Ireme Invest – the private sector window). There is high-level ownership and commitment from Rwandan institutions. In terms of mitigation, the Government has enshrined low carbon growth in its legal and policy frameworks and has made significant efforts to build awareness at the local level.

The alternative route would be to fund the World Bank for the implementation and operationalisation of SPCR priorities. The main advantage of this option is that the World Bank manages the Climate Investment Funds which finance the SPCR projects. Thus, the Bank can direct the funding towards Rwanda’s SPCR projects, and leverage IDA funding and other climate funding at scale. In terms of management and fiduciary risk, this modality would benefit from the World Bank carrying out these functions and, by transferring resources through the World Bank Trust Fund, FCDO is transferring some risk to the World Bank. Moreover, through setting up and managing a Trust Fund the World Bank may be able to attract more concessional finance for the sector than the national climate fund may do by itself.

This option would deliver similar benefits (in economic terms) to Rwanda but would lose the substantial benefit of programming through government, notably in terms of the transformative effects of aligning to sector and economic development planning, as well as country ownership and capacity building. It is also likely that any of ACTION’s TA and MERL would be less effective if the bulk of the programme money (the direct support) went through the World Bank, rather than directly to RGF, as the direct influencing relationship by the UK would be lost. Multi-donor trust facilities can be more opaque and as we have the option to support the GoR directly in Rwanda, we will provide the financial aid directly to the GoR instead of using an intermediary. However, close partnerships with DPs including multilateral partners will remain crucial to the success of this programme and value for UK investment. Therefore we will continue to collaborate closely with partners including the World Bank to ensure a coherent approach towards Rwanda’s adaptation is followed.

Conclusion
In conclusion, this appraisal case has ruled out “do nothing”, working on private sector financing and looking at carbon markets, and appraised a number of possible components for the ACTION programme. It has concluded that there is a strong case for the ACTION programme to provide direct support for public sector climate priorities, supported by TA, and a MERL component. It has set out evidence from literature reviews that these will provide positive returns. The appraisal has also examined some choices within the programme components and found that (i) TA to either RGF or MINECOFIN would provide strong returns, (ii) MERL model should work on short-term timelines to maximise flexibility; (iii) TA and MERL can be done through a contract initially but moving to through GoR later in the programme, and (iv) direct support should be provided as Financial Aid through RGF’s Intego facility.
## Commercial Case
The intervention will be composed of the following components:
1. Technical assistance to Government of Rwanda (£1.8m)
2. Monitoring, research, evaluation, analysis and learning (£1.2m)
3. Financial aid to Government of Rwanda (for climate adaptation programming) (£12m)

Delivering climate impact in Rwanda can be done through a number of partners and contractual options. Rwanda is able to receive direct financial aid from the UK and therefore deliver results directly through its government ministries and agencies. We have previous experience of a direct financial aid arrangement , partnering with RGF to deliver adaptive climate programming at scale, which has proven to be a successful approach with strong VfM. We currently also deliver social protection and governance programming through direct financial aid. A fiduciary risk assessment is conducted every three years to provide assurance for UK taxpayers and ensure effective delivery, including proper public financial management, through Government of Rwanda institutions. The latest fiduciary risk assessment was completed in February 2023 and included a separate annex on RGF operations in addition to a wider analysis of GoR institutional capacities. The assessment has made a number of recommendations for institutional strengthening of RGF, some of which will be delivered through the TA component of ACTION. The assessment found that direct financial aid remains an effective delivery mechanism for UK Aid via GoR institutions and sound financial management is practiced by the GoR to deliver results using UK funding.

In addition to direct delivery through government institutions, there is a wide landscape of climate expertise within multilateral organisations, not-for-profit organisations, consultancy firms and civil society partners. Rwanda has achieved impressive results against its high climate ambitions over the last few decades and the delivery partner market for continuing with this progress is well developed.

Key cost drivers are likely to be:
- Salaries, travel and administrative costs for technical assistance and capacity building
- Research fees, salaries, travel, technical discussions, learning events and administrative costs for the MERL component
- For the financial aid component, investments into Rwanda’s adaptation to climate change will be the cost drivers – these could be improvements to agricultural practices, better irrigation, green infrastructure and expansion of green public transport networks. These will be delivered through projects approved by the Intego Facility.

Technical assistance component

As discussed in the appraisal case, the best VfM approach would be a combination of direct financial aid to RGF or MINECOFIN, or TA sourced via a commercial provider, based on Government of Rwanda (GoR) needs at the time. The proposed approach is for this assistance to be flexible and iterative, with particular needs agreed between GoR Ministries/agencies and Post, informed by wider development partner offers on a regular basis, for example 6-monthly. There are GoR plans for improved coordination and allocation of climate technical assistance based on ongoing needs analyses, therefore our support would be well aligned to broader plans.

If technical assistance is delivered directly to GoR, the support would be governed by an MoU. This would make provision for an action plan which would be updated on a 6 monthly basis detailing the areas of focus for the technical assistance during any given upcoming period. RGF or MINECOFIN would be responsible for hiring their own consultants based on needs and the action plan agreed with FCDO, with clear deliverables and milestones developed for the length of the consultants’ assignments. The MoU would cover GoR responsibilities in relation to spend of UK Aid, including fiduciary risk recommendations in line with our assessment. The payment schedule would be stipulated within the MoU. Disbursements would be made by the UK to GoR according to an agreed schedule within the MoU, and GoR would be responsible for any contracting with a TA provider or consultants (depending on the modality selected). Our MoU would govern the monitoring and evaluation of results or policy objectives as agreed in advance, and further payments would only be made upon satisfactory delivery against previous milestones.

We will ensure ACTION maintains the flexibility to use a commercial TA provider if required to deliver on ever-evolving adaptation priorities in Rwanda. We will likely use an existing draw-down framework such as the Global Development Delivery (GDD) framework to procure technical expertise (consultants, studies etc as required), likely on a short-term basis to meet demands at any given point.

We will explore creative ways of delivery against this programme’s objectives whist demonstrating the best value for money for the UK taxpayer. This might include partnering with existing programming and delivery partners, such as DAI who are already delivering the ambitious governance programme for the UK in Rwanda and have an ongoing relationship with MINECOFIN. Pursuing this route would mean achieving economies of scale as a number of UK priorities would be achieved through the same existing contract. In practice, this would mean combining budget lines and delivering governance (SPARC) and climate (ACTION) programmes through one existing contract, with regular input from FCDO colleagues to streamline objectives and focus of technical assistance. Consultants would be recruited by DAI to deliver against climate priorities within MINECOFIN as agreed between GoR and FCDO. Specific goals and objectives would be agreed through a terms of reference process ahead of each consultancy offer period, and for example could include climate budget tagging and other greening of the budget policy objectives.

ACTION will have to adapt its approach towards contracting and delivering technical assistance during the programme years based on availability of UK ODA , GoR priorities, development partners’ work, and the fast changing climate landscape. Flexibility will be essential in order to keep up with the high climate change adaptation ambitions.

MERL component

Similarly to the technical assistance component, there is a need for a high degree of flexibility for contracting under the MERL component to respond to the changing ODA allocations throughout the programme delivery years, evolving GoR climate adaptation needs and priorities and ability of other development partners to meet those needs.

To achieve better efficiencies, research and analysis elements could be combined under the same component and contractual arrangement as technical assistance. In practice, this could for example mean MINECOFIN agreeing technical assistance needs and policy questions in partnership with FCDO on a regular basis and the existing pool of consultants and expertise at a commercial provider being used to address those needs under the existing SPARC programme contract. This could be a flexible arrangement for the first year or two of the programme while budgets remain extremely tight and a compromise is needed. When more flexibility is possible, research and analytical work could again be offered together with technical assistance, but through an MoU directly with RGF or MINECOFIN, allowing the government entities the flexibility to procure own consultants with the required expertise based on needs assessments agreed with FCDO.

Policy questions and technical research answers to them will inform future needs assessments and therefore dictate what further research and technical assistance is needed. All this learning will continuously feed into the understanding of adaptation needs to address climate crisis impacts in Rwanda and therefore capacity needs of GoR to address these. Flexibility is integral to this iterative approach, therefore we will use a range of options during the programme cycle to deliver this component.

Monitoring and evaluation of ACTION will take place against agreed results set out in a logframe which will be revised on a regular basis due to the flexible nature of the programme. Regular field visits and meetings with GoR and consultants delivering technical assistance and MERL will complement the formal evaluation cycle in line with relevant ProF guidance.

Financial aid component

Analysis shows that best at scale results are achieved when GoR’s climate finance instrument, RGF is fully empowered to carry out its mandate and deliver at-scale adaptation programming. RGF’s public sector window, now known as the Intego Facility, has an ambitious pipeline of public sector adaptation programming to address wide ranging needs from environmental protection to clean energy to better irrigation for agricultural purposes. We will either provide general support to Intego Facility (public sector window) to carry out wide ranging adaptation projects to a wide cross section of the population, or – if ODA budgets are tighter or earmarked for certain thematic areas in future years – we could earmark our funding for specific priorities, for example disaster preparedness and humanitarian risk prevention which would include flood and landslide preparedness works. We will ensure that the MoU with the GoR for support to Intego has specific GESI indicators, and require RGF to improve its approach to diversity, inclusion and safeguarding.

As outlined in the appraisal case, alternatives to financial aid were not assessed due to Rwanda’s track record of delivering structural reforms through financial aid. Financial Aid (FA) has been a key mechanism for the UK deliver support to Rwanda for twenty years. Evidence from previous programmes shows that Rwanda uses FA effectively, compared to other aid instruments in terms of development impact per £ spent. Additionally, the use of FA reduces transaction costs and, by aligning ACTION (and other UK programming) directly to GoR strategic objectives, FA offers a key opportunity to directly support GoR implement its reforms.

Commercial risks

Policy influencing outcomes cannot be pre-defined in the terms of reference for the commercial supplier if this route is used for TA and MERL provision. This creates additional risk around holding the supplier to account for their impact, although input and delivery will be easier to measure. The initial mitigation strategies to these risks include (1) getting the supplier to prepare a detailed, fact-based, realistic plan of activities, milestone and KPI targets for a short time, for example 12 months and (2) a more flexible outline plan for the long term/ outer years. The same approach would be used to deliver TA or MERL outputs directly through GoR, and any key milestones would be outlined within the MoU and regularly reviewed workplans. As the TA and MERL outputs are difficult to define at this stage of programme development, we will agree annual workplans with a high degree of complementarity with other UK programming and high GESI returns.

## Financial Case
Overview of costs

The proposed disbursement profile is as follows (subject to change):

Component	FY24/25	FY25/26	FY26/27	FY27/28	FY28/29	TOTAL
Technical Assistance	£0.2m	£0.4m	£0.3m	£0.3m	£0.6m	£1.8m
MERL	-	£0.1m	£0.2m	£0.4m	£0.5m	£1.2m
Financial Aid	£1.3m	£1.8m	£2.9m	£3m	£3m	£12m
TOTAL	£1.5m	£2.3m	£3.4m	£3.7m	£4.1m	£15m

The strength and flexibility of Intego’s project pipeline means that we would have the ability to flex spend up or down depending on yearly budget allocations.

Fund Flows and Delivery Chain

The major cost drivers for this programme are likely to be:
- Component 1: procurement of technical consultants to mainstream climate considerations across the Government of Rwanda;
- Component 2: procurement of expertise to carry out research projects, hold events or technical discussions and prepare policy recommendation papers;
- Component 3: procurement of goods and services related to the delivery of public sector climate adaptation projects.

All cost drivers will be tendered competitively in line with Government of Rwanda policy where procured directly by GoR agencies. As discussed above, the option to combine budgets with governance team’s SPARC programme and deliver technical assistance and research (components 1 & 2) through the existing contract will also be explored, particularly during the first two years of delivery.

Spend through Rwanda’s Intego Facility will be via grants to public entities and public-private-partnerships distributed through a regular pace of funding rounds. These will be spent on projects in key thematic sectors, all contributing to the achievement of Rwanda’s climate ambitions (NDCs):

The MoU with the Government of Rwanda to provide direct financial aid for Intego will make provision for spend on both RDEL and CDEL, with funds earmarked for infrastructure or capital investment for example when budgetary realities mandate a greater proportion of CDEL spend. The variety of thematic areas will provide further flexibility and earmarking for certain sectors if HMG’s policy direction should shift or budget requirements change. This could mean that focus shifts to spend on additional areas such as disaster risk improvements, particularly if future rainy seasons continue to be as catastrophic as they were in 2023.

Financial and Fraud Risk Assessment

Government of Rwanda’s overall fiduciary risk is rated as moderate (2023 Fiduciary Risk Assessment). This is largely because of residual gaps in financial management capacity in service and local government, with improvements noted since the previous Fiduciary Risk Assessment in 2019. Corruption risk is rated as moderate. Commitment to improve PFM remains very high in Rwanda and strong progress is being made continually.

FCDO will retain the ability to pull, re-direct or recover financial aid in the event of mismanagement or weak value for money. The use of agreed delivery and payment plans allows FCDO to avoid paying for changes that are not delivered. The MoU will have provision for the recovery of any advance payments made. For MINECOFIN, RGF and any other GoR disbursements are made against detailed work plans and only advanced when needed. The GoR – FCDO MoU contains a provision for Government to repay any funds not used for the intended process. The MoU will give FCDO the flexibility to redirect funds where necessary, including to other programme components.

To maintain the financial, fiduciary and fraud risk at a minimum, FCDO will ensure that:

· Annual work plans and budgets, procurement plans and progress reports are rigorously scrutinised prior to releasing FCDO’s funding tranches.

· Independent audits and annual reviews continue to focus on procurement, financial risks, fraud, making appropriate recommendations to mitigate risks and improve the project governance.

· Recommendations from annual reviews and audits are tracked for timely and effective implementation of remedial measures.

International Climate Finance

ACTION Rwanda will contribute 100% of its spend towards UK’s legal International Climate Finance (ICF) commitments. ICF3 is at a target of £11.6bn by 2026, therefore ACTION Rwanda will be contributing towards this and towards any future ICF4 targets as when they are committed. Given the scale of the climate emergency, it is imperative that climate considerations are included throughout our work. We will use learning from ACTION Rwanda, particularly the MERL component to inform climate understanding and inclusion in our other bilateral and centrally managed programmes. We will track the results according to the relevant ICF KPIs.

## Management Case

Management arrangements in place for implementing the intervention

FCDO’s support to Rwanda Green Fund (RGF) Intego facility will be managed through a MoU with GoR, that sets out all the guiding principles and procedures of the RGF funding. As RGF’s Intego facility programme, the facility has in place its own in-country governance and accountability structures. Governance arrangements have been designed to ensure efficient decision making and review mechanisms, while maximising the flexibility of the facility to respond to evolving circumstances within the agreed upon strategic scope, allowing for clear accountability to the donor and government. These will be described first before moving on to FCDO’s internal arrangements.

RGF’s organisational structure, including the Board of Directors, the Board Committees and the Green Fund’s Secretariat, will support the functioning of Intego facility. The Board will be the principal decision-making body regarding which projects to fund and will provide strategic oversight of Rwanda Green Fund. The Board will meet at least once a quarter and whenever deemed necessary. The Board will be supported by Rwanda Green Fund’s Board Committees which includes Audit Committee for audit compliance and assurance function, Investment Committee that provides technical advice and oversight of project screening and makes recommendations to the board for approval. The Human Resources and Governance committee will oversee rules, transparency and accountability within the Rwanda Green Fund, oversee the implementation of resolutions adopted by the board and assess the performance of the Fund’s organs and advise the board of appropriate and necessary actions.

The RGF’s secretariat will be responsible for day-to-day management of the Fund, including mobilisation and management of resources used in financing activities for protecting and preserving environment and natural resources. If the Fund is not delivering the intended results, it will be the responsibility of the Investment Committee to take remedial action, under the overall guidance of the Board and DPs forum. The Secretariat will be supported by the Facility Management Consultant (FMC), ensuring efficient projects implementation of approved projects and supporting projects that did not initially meet viability criteria.

There is an ongoing regular (at least 6-monthly) Rwanda Green Fund Development Partners Forum, which will continue to be a consultative and advisory forum. DPs will be represented at the DPs forum which will be an opportunity to monitor progress and for accountability toward achieving RGF’s development objectives. The DPs forum discussions will inform Investment Committee and Board meetings and will be Chaired by the CEO RGF and Co-chaired by DPs on a rational basis.

FCDO internal oversight arrangement

Within BHC Kigali, the programme will be managed by the Climate Adviser, in their capacity as Senior Responsible Owner, with oversight and quality assurance of the programme provided by the Green Growth and Trade Team Leader. The Senior Programme Manager/Programme Responsible Owner (PRO) will manage the administrative arrangements of the programme including oversight of the programme delivery plan on AMP and HERA finances. Regular engagement with a range of other teams and advisers, including governance, social development, commercial and M&E advisers will ensure close integration of ACTION Rwanda into the wider country priorities. As the sole bilateral climate programme, ACTION will be a useful link to wider climate and environment priorities for the UK in Rwanda, including leveraging closer relationships for the regional adaptation programme and key CMPs including the UK’s support for the Taskforce on Access to Climate Finance.

Majority of the funding via the programme will be provided as Non-Budget Support Financial Aid. As such, continued support is subject to consideration of the Partnership Principles that underpin the provision of UK aid. The Rwandan government’s commitment to these principles was reviewed most recently in 2021 with the following conclusions:

“Overall, we assess that the Government of Rwanda remains committed to the underlying principles of our aid partnership sufficient to continue financial aid. Rwanda continues to demonstrate strong commitment to poverty reduction, economic and social rights, anti-corruption and sound public financial management. Commitment to civil and political rights and domestic accountability is limited and we remain particularly concerned about civil and political rights.”

No significant new concerns have emerged since the last assessment. On this basis, it is considered possible to continue to give Non-Budget Support Financial Aid in the Rwandan context.

Due to the flexible nature of the TA and MERL components, an annual workplan will be required to ensure that capacity building is responding to the current GoR needs, outputs are clearly defined and support to GoR complements wider UK offers, for example through governance or social protection programming. Therefore, the SRO and PRO will work closely with other teams across Post on a yearly basis to develop a concrete workplan for the two components and seek agreement from GoR or direct implementing partner as necessary. We will ensure that most marginalised communities are prioritised within any capacity building initiatives by engaging the social development adviser early in the annual planning process and ensuring that the latest GESI strategy is included within the annual workplans.

As the MERL component will likely produce learning for regional and international audiences, close engagement with relevant policy teams and regional partners will be essential. The SRO will work through others to ensure that learning on what works within the adaptation space is gathered, remains relevant and is shared with others, while empowering GoR to add to the global evidence base at appropriate opportunities.

Monitoring and Evaluation

The principal tool for FCDO’s internal project monitoring will be the logframe, which will also be the basis for FCDO annual reviews. The annual review will draw on the inputs described in the sections above, reporting from the Intego Facility and on beneficiary feedback. The logframe outputs will be drawn directly from the RGF’s Intego facility results framework (draft included in Annex B). To reduce the administrative burden on the Rwanda Green Fund, we will aim to align annual review cycles with other Intego facility funders (currently KfW) where possible.

Approved projects with funding from Intego are required to prepare and submit Quarterly Progress Reports to RGF to ensure continuous monitoring of project activities and allow for timeous corrective action. These reports provide an update on output delivery, expenditure and forecast spend as well as a workplan for the next quarter.

M&E of the Intego Facility is a key responsibility of the RGF M&E analyst, with the Technical Committee providing additional guidance and oversight. A monitoring framework has already been established as part of the RGF’s Intego facility design work and will be taken forward by the Research and evidence supplier to be procured by FCDO. The framework proposes indicators covering impact, outcome and output levels which are directly aligned to the Nationally Determined Contributions (NDCs) targets and climate action plan as well as Rwanda National Strategy for Transformation (NST 2) and other national strategies. The M&E function will include conduct regular field visits and ‘spot-checks’, with a particular focus on ‘at risk’ projects; and are also responsible for updating the Fund’s log-frame based on the results achieved by the individual districts or public sector bodies.

Monitoring of the FCDO contribution to the Fund will be carried out using the draft logframe attached at Annex B. All indicators are taken from the full monitoring framework described above. The logframe will be regularly updated using information provided in quarterly progress reports prepared by the RGF M&E Analyst. This will help in identifying opportunities and gaps as well as areas where progress is off-track to ensure action is taken in a timely manner.

We will use learning from other programmes including the CMP CLARE which is calculating the costs of adaptation to households to ensure that ACTION implements the latest GESI strategy and commitments. We will include specific GESI outputs and goals within the Intego results framework (draft in Annex B) and annual workplans of the MERL and TA components. In recognising that climate change impacts are the harshest on the most vulnerable communities, we will flex the MERL component as needed to support other UK programmes to ensure strong climate adaptation and GESI complementarity.

Risk management

The table at Annex A identifies the main programme context, delivery, operational, fiduciary, reputational, people and safeguarding risks that may affect the successful delivery of the ACTION’s RGF support and looks at the likelihood of occurrence, the potential impact on the programme and mitigating strategies. Risks will be monitored and updated regularly - every quarter, in addition to the annual risk assessment during the annual review.

Overall, the risk is judged as moderate and judged to be within the risk appetite for the broader FCDO Rwanda programme portfolio risk appetite statement. This moderate risk level is consistent with the recent fiduciary risk assessment of Rwanda Green fund (Jan 2023) which gave overall rating of moderate due the fact that GoR systems continue to undergo strengthening, with recent improvements in public financial management (PFM) system; an enhanced and cohesive integrated financial management information system (IFMIS), with real-time linkages with other government databases, and capacity and experience in managing climate finance from multiple sources. The level of risk is judged acceptable given the clear and robust risk mitigation strategies that have been included in the draft risk register set out in Annex A. The SRO and PRO will supervise the programme and will monitor and provide quarterly updates on risks. Risks will be monitored through the risk register in the project’s delivery plan on AMP.

Annex A: Indicative Risk Matrix
Risk Area	Risk Owner	Before mitigating action		Overall rating	Mitigation Strategy	Residual Risk		Overall rating
		Probability	Impact			Probability	Impact
Strategy and context
The Fund fails to mobilise sufficient resources to deliver entirety of fund objectives due to difficult operating context due to budget cut/fall in GNI/economic downturn. Resources spread too thinly across funding windows to have a meaningful transformational effect	SRO	Possible	Major	Major	Use policy dialogue to encourage Government of Rwanda to increase domestic resources available for the Fund / TA to work with RGF and MINECOFIN to design new ways of raising revenue in the longer term (e.g. environmental taxes)	Possible	Major	Major
Policy and programme delivery
Financial sustainability and future scale-up remains a high priority for Rwanda Green Fund (RGF) and securing replenishment funding is key for continued operations and for meeting goals and objectives. Unpredictable levels of replenishment therefore pose a risk.	SRO	likely	Major	major	FCDO support to enhance resource mobilisation, including capacity building on resource mobilisation through technical assistance, and support to the new RGF division for resource mobilisation, including strengthening domestic resource mobilisation.	Possible	Moderate	Moderate
Over-reliance of the Fund’s operations on a few key staff members’ abilities and institutional knowledge	SRO	Possible	Major	Major	FCDO should review RGF’s Staff Capacity Development Plans, to help employees increase their capacity and achieve their personal and strategic goals. / FCDO should regularly monitor staffing levels in RGF, especially for key positions, such as in grant management, finance, and internal audit, and should enquire about any delays in filling any vacancies that arise in key positions.	Possible	Moderate	Moderate
The capacity of districts to manage multiple complex programmes and initiatives, such as those relating to climate change, may pose a risk to the overall success of these programmes	SRO	Possible	Major	Major	Technical assistance to work with fund committees and build required capacity and systems across RGF, affiliated agencies and districts	Possible	Major	Major
Lack of stringent monitoring and reporting - The Fund’s Result and Information Monitoring resourcing levels may not match the scale up of the Intego and Ireme facilities.	SRO	Likely	Major	Major	The Fund’s Result and Information Monitoring System (FRIMS) has been strengthened with the support of GGGI, and a new ICT Plan developed as part of the previous joint-TA / The Programme will have a M&E system that is embedded in RGF’s Management Information System and the new digital platforms. It will facilitate the regular monitoring of project progress and results. The TA to support strengthening of M&E and review the work to date on the ICT strategy to ensure that RGF information systems are fit for purpose.	likely	Moderate	Moderate
Public Service Delivery & Operations
The complexity of the multi-sectoral and multi-donor RGF creates difficulty to properly monitor spending and results for FCDO.	SRO	Possible	Major	Major	Rationalisation of implementation channels has meant the majority of resources flow through the basket fund basket fund MoU the specific reporting (technical and financial) requirements to be met by RGF. / In addition, BHC Kigali Climate Adviser, as the SRO, and the senior programme manager as the PRO will manage the programme.	possible	Moderate	Moderate
Financial and Fiduciary
Fiduciary and corruption risk as a result of misuse of funds by project implementers, or non-compliance with laws and procedures. And funds not used for intended purpose	SRO	Possible	Moderate	Moderate	Support to GRF to ensure that grant management procedures are documented and shared with implementing partners and that M&E and fiduciary oversight is consistently applied to all grants throughout their lifetime. / Ensure agreed financial management procedures (as set out in the Fund operational manual) are followed / Detailed budget and budgetary controls in place, including rigorous and regular audit by OAG / Technical assistance to support comprehensive improvement on procurement and financial management issues	Unlikely	Moderate	Minor
The risk of RGF reporting transfers to grantees as actual expenditure, rather than as advances, which would be misleading.	SRO	Likely	Major	Major	FCDO should follow up to ensure that expenditures are accurately captured by RGF’s financial management information system (the GoR IFMIS) and are reported accurately to development partners / The treatment of advances should be discussed with RGF, the OAG, and MINECOFIN, to agree a standard accounting approach.	Possible	Moderate	Moderate
Variability in the financial management capacity of districts, reflected in the weak PEFA scores assigned by recent district assessments, may undermine the effective management of climate change activities.	SRO	Likely	Major	Major	Rwanda Green Fund and its development partners, if providing funding to districts, should continue to work with districts to gauge levels of risk, identify the key weak points for each district vis-à-vis financial management, review available evidence (such as the recent PEFA assessments), and provide capacity building and training accordingly.	Possible	Moderate	Moderate
Pressure to disburse funds results in RGF overlooking minor project risks and shortfalls on project outputs.	SRO	Likely	Moderate	Moderate	FCDO should ensure that grant management standards are maintained throughout the life of FCDO’s financial aid.	Unlikely	Moderate	Minor
Rwanda Green Fund’s reporting to funding agents and the complexities of meeting multiple demands for different financial statements and templates.	SRO	Likey	Moderate	Moderate	FCDO, along with other funding agencies should agree a basket fund MoU the specific reporting (technical and financial) requirements to be met by RGF. Consolidated comprehensive financial management reports could be developed with RGF to meet multiple reporting demands	Unlikely	Moderate	Minor
Reputational
As a non-budget support financial aid to GoR, there a risk that failure to adhere to partnership principles assessment (PPA) may threaten FCDO reputation.	SRO	Possible	Major	Major	A MoU include a clause on commitment to PPA, which will be annually reviewed	Possible	Moderate	Moderate
Safeguarding
The risk that RGF’s safeguards do not meet high standards in key areas, including safeguarding, human resources, whistleblowing, risk management, codes of conduct, and governance.	SRO	Possible	Major	Major	RGF, with support from technical assistance, should develop policy documents on, and training for, safeguarding, whistleblowing, risk management, and anti-fraud/ corruption/money laundering, and should strengthen the staff code of conduct, human resources, and governance manuals. It is essential for there to be a comprehensive RGF risk management framework covering all environmental, social, governance, organisational, and fiduciary risks facing the entity. / RGF with support from TA undertaken a comprehensive organisation-wide risk assessment in recent years, covering all environmental, social, governance, organisational, and fiduciary risks facing the entity.	Possible	Moderate	Moderate
Fund supports proposals with negative Climate & Environment (C&E) impacts	SRO	Possible	Moderate	Moderate	Work through Fund Technical Committee to ensure that robust C&E screening procedures are developed and rigorously applied	Unlikely	Moderate	Minor
People
The on-going budget cuts reduces staff affecting programme management.	SRO	Possible	Major	Major	Ensure timely discussion on prioritisation to balance ambition with resourcing now that SR outcomes are known (and Strategic Workforce Plan no longer an issue) and operational budget cut temporary	possible	Moderate	Moderate

Appendix B: Draft results framework for Intego Facility / Project Name / Support for the NDC implementation (NDC facility) Phases I and II	BMZ-No. / 2020 68 203, 2021 6933 2
Country/Region / Rwanda	Impact matrix created on / 29.07.2022

Objectives	Indicators	Means of verification	Assumptions
Overall Objective of Rwandan-German cooperation on climate change (still indicative): / The resilience of the Rwandan population towards the impacts of climate change has increased and greenhouse gas emissions have been reduced or avoided.	Reduction of national greenhouse gas emissions (in t CO2e) compared to the BAU Scenario / Base value: 5.3 MtCO2e / Target value (2035): 10 (MtCO2e) incl. interventions (16.13 MtCO2e- BAU according to Vision 2050 / The national climate vulnerability index shows reduced level of climate vulnerability, or at least no overall increase / Base value (2019): out of 37 assessed indicators, 17 indicators show reduced vulnerability, 11 an increase in vulnerability and 5 show no change in comparison to the baseline study in 2015. 5 indicators could not be assessed / Target value (2025): out of the 37 indicators, at least 20 show reduced vulnerability and a maximum of 10 indicators show increased vulnerability with regards to a certain aspect, compared to the baseline study of 2015 / Percentage of urban households living in a smart green city/district accessing sustainable and modern municipal services / Base value: 10% of the population / Target value (2025): 25% of the population / Mechanisms for climate finance in Rwanda enhanced / Base value: a measurable base value shall be defined on the basis of the findings of the Access to Climate Finance Task Force. / Target value (2025): an increased budget for climate finance shall be achieved. Measurable target value shall be defined on the basis of the findings of the Access to Climate Finance Task Force.	Rwandan NDC, Rwandan National Communication under the United Nations Framework Convention on Climate Change (UNFCCC ) (done by REMA, four-year reporting cycle) / „Assessment of climate change vulnerability in Rwanda“) issued by REMA, every third year / Revised Green Growth and Climate Resilience Strategy (GGCRS) (2021/22) of Ministry of Environment, Joint forward looking annual sector review report / Annual reports of the Access to Climate Finance Task Force and Joint forward looking annual sector review report	not to be filled!
Project Objective / Contribute to strengthened climate resilience of the Rwandan population and to mitigation of greenhouse gas emissions through FONERWA's sustainable NDC financing mechanism.	Number of people whose resilience to extreme weather events and the effects of climate change has been strengthened through FONERWA. / Base value (2021): 117,829 people / Target value (2026): tbd / Target value (2024): 531,465 people / Actual value (202x): / Expected to be achievable in term: yes	Annual Reports of FONERWA	Continued commitment of the Government of Rwanda to the Rwandan NDC. / Continued commitment of the Government of Rwanda to maintain FONERWA as key Rwandan organization for climate change adaptation and mitigation, and to establish the NDC Facility. / Continued commitment of Germany and other donors to fund climate projects through FONERWA
	Greenhouse gas emissions avoided through FONERWA / Base value (2021): 93,604 t CO2e / Target value (2026)1: tbd CO2 e / Target value (2024): 292,606 t CO2 / Actual value (202x): / Expected to be achievable in term: yes	Annual Report of FONERWA
	Project implementation will be monitored by FONERWA in line with the standards agreed between FONERWA and KfW / Base value (2021): n.a. / Target value (2026): fulfilled / Actual value (202x): / Expected to be achievable in term: yes	Reports of FONERWA and of the Implementation Consultant
	Percentage of female beneficiaries reached through the NDC Facility / Base value (2022): n.a. / Target value (2026): at least 60% / Actual value (202x):	Reports of FONERWA and of the Implementation Consultant
Outputs / Output A: NDC projects are realized	Number of people whose resilience to extreme weather events and climate change was strengthened through the Project	Project reports of FONERWA, or of the Implementing Consultant, respectively	Continued commitment of FONERWA to further develop and improve its standards and procedures as a learning organization. / NDC Facility meets sufficient demand of the IPs / Continuous support by Germany to the NDC Facility / Other donors express interest in co-financing the NDC-Facility
	Base value (2021): 0 / Target value (2026): at least14,300( 5.700 male and 8.600 female)Actual value (202x): / Expected to be achievable in term: yes/no / Percentage of IP Projects with regular disaggregated gender data reported, including setting targets on IP level, and monitoring their achievement / Base value (2022): n.a. / Target value (2026): all / Actual value (202x):
	Greenhouse gas emissions saved through the Project compared to the NDC baseline scenario / Base value: 0 t CO2 e / Target value (2026): 11,200 t CO2 e / Actual value (202x): / Expected to be achievable in term: yes	Project reports of FONERWA, or of the Implementing Consultant, respectively
Output B: institutional capacities of FONERWA are strengthened	The Specific Procedures for the NDC Facility have been approved. / Base value (2021): not applicable / Target value (2026): fulfilled / Actual value (202x): / Expected to be achievable in term: yes / Specific Procedures have been improved continuously over time / Base value (2022): not applicable / Target value (2026): yes / Actual value (202x): / Expected to be achievable in term: yes / FONERWA implements the NDC Facility in accordance with its Grant Management Manual and guidelines and in line with the Specific Procedures for the NDC Facility / Base value (2021): not applicable / Target value (2026): fulfilled / Actual value (202x): / Expected to be achievable in term: yes	Reports of FONERWA or of the consultants, respectively; audit reports, no-objection from KfW
Activities	not to be filled!	not to be filled!	IPs prepare the IP Projects up to the needed design standards within acceptable time / Sufficient number of qualified staff available at FONERWA as well as at the level of the Implementing Partners. / Continuous refinement of FONERWA's procedures such that the agreed standards are met in an efficient and effective manner / Decisions are taken within FONERWA without delay / KfW issues no-objection to well-prepared documents without delay
Activities regarding Output A / Select NDC relevant IP Projects with high impact potential / Select consulting firm as Implementation Consultantby international competitive bidding / assess the availability of good feasibility studies for the IP Projects, support completion of the studies if needed and carry out pre-grant award survey / conclude IP Project grant agreements / Monitor the award of contracts for supplies and services carried out by IPs / Monitor IP Project progress / obtain and consolidate reports from IPs / Release payments to IPs / Carry out audit of the use of funds / Provide training for IPs (e.g. regarding sustainable operation) / Monitor commissioning and defects liability period
Activities regarding Output B / Define Specific Procedures of the NDC Facility / Continuously refine the FONERWA grant management manual as part of the institutional knowledge management and learning processes / Maintain the staff and competences needed at FONERWA in order to implement the NDC Facility / Train and further develop FONERWA staff, ensure the needed decision-making power on all levels and practice newly established procedures / Monitor cost-coverage of grant management activities for the NDC Facility / Report to KfW on the development of the NDC Facility and the IP Projects / Ensure Audits and involvement of KfW by no-objection for quality assurance / Market the Facility and acquire additional donors
[note] The target values currently available from FONERWA cover the time horizon up to 2024, which is before the end of the Project. FONERWA will therefore initially report based on the value for 2024 and report on the value for 2026 as soon as it has been defined.
[note] Here, the avoided CO2 equivalents (CO2e) are determined in comparison to the so-called “Business as Usual” (BAU) scenario presented in the Rwandan NDC, where the calculation methodology defined in the Rwandan NDC is applied.
[note] The reference value for 2024 refers only to avoided CO2 emissions. Emissions include not only CO2 but also other greenhouse gases such as methane. The avoided CO2 equivalents (CO2e) represent a conversion of all greenhouse gases to the reference value CO2. The avoided CO2e are therefore systemically higher than the avoided CO2.
[note] For future funding commitments, projects may be selected according to specific, thematic priorities, if applicable.
[note] Estimate, determined based on information provided by FONERA about the cumulative number of people it has reached as well as the funding volume it has provided from its establishment up to now., compared to the Grant amount.
[note] Estimate, determined based on information provided by FONERWA about the CO2e savings it has achieved and the funding volume it has provided up to now, compared to the Grant amount.