Business Case – February 2022

Summary Sheet

Country Plan Summary: / The British Embassy Kinshasa’s (BEK) Country Plan intends to achieve ‘a more resilient and stable DRC that sees the UK as a key partner on stability, climate change, health and education’ and that ‘DRC increasingly becomes a place of opportunity for British businesses and an ally in the region and in the African Union’. Underpinning this statement are 5 core campaign goals. This programme will help deliver the third campaign goal: ‘DRC more able to contain global health security threats’.

Title: Supporting Health Emergency Response in DRC (SHER)
Programme summary (100 words maximum): / This programme will enable the UK to offer rapid support to government-led efforts to prepare for and manage high-risk communicable disease outbreaks in the DRC, a global hotspot for such events. Despite DRC’s growing capacity to respond to health emergencies, there remain key weaknesses that affect mobilisation of an effective public health response. The programme provides a £12 million contingency vehicle to support an early and effective response to high-risk outbreaks of infectious disease with up to £4m to enhance preparedness for outbreaks, should funding be allocated. Key activities would include: communication of health risks and measures to reduce disease transmission; increasing access to safe water, personal protective equipment and disinfection materials, especially in health facilities; and supporting health system capacity for treatment and prevention. By supporting the early containment of health threats, the programme will avert costly socioeconomic impacts and reduce risks to regional and global health security.
What is the rationale for UK Aid spending? (200 words maximum): / DRC has experienced the highest frequency of epidemics within the WHO Africa region since 1970 and has a high burden of communicable disease. The 10th outbreak of Ebola between 2018 and 2020 was the second most severe on record, claiming 2887 lives. The world’s largest measles outbreak, a vaccine preventable disease, occurred in DRC from June 2019 to 2020, causing over 7000 deaths. Supporting national preparedness and early response to outbreaks in DRC is essential to safeguarding global health security and achieving our global health goals. / The programme is closely aligned to the UK’s strategic goals and contributes to the UK government’s manifesto commitment to ‘lead the world in tackling Ebola’. Global health is identified as a major shift of the Integrated Review: ‘we will work to strengthen global health security, including through the Prime Minister’s five-point plan to bolster international pandemic preparedness […] and we will prioritise supporting health systems and access to new health technologies using our Official Development Assistance (ODA)’. / The programme will help deliver on the Minister for Africa’s vision (as set out in FCDO’s December 2021 position paper on health system strengthening) to ‘renew our partnerships […] to build stronger and more inclusive health systems […] that are better prepared to deal with pandemics and infectious diseases’. The programme also contributes towards the FCDO campaign goal on ‘Improving Global Health Security (GHS)’ and its related KPI ‘number of countries demonstrating an improvement in their capacity to prevent, detect and respond to health threats, following UK support’.
Programme Value: £12,000,000		Country/ Region or Sector: Democratic Republic of Congo
Department/Country Office confirmation of review processes		HoM confirmation that Departmental processes for BC review have been followed prior to submission
Contact name
Threshold for final approval of Business Case: / Head of Mission delegated limit.
Date of Approval of Concept Note:	23/09/2021	Name and role of Approver
Date of Approval of Business Case:	26/04/2022	Name and role of Approver
Programme Code: 31152	AMP Start Date:27/11/2023	AMP End Date: 01/08/2025
Overall programme risk rating:	Major
Vault Number:	Save this document in Vault with the correct metadata (‘Business Case’) to allow for publication to Devtracker. Note that FCDO programme teams that do not use Vault (i.e. legacy FCO), should follow existing processes for saving information.

List of Acronyms

ADF: Allied Democratic Forces
BEK: British Embassy Kinshasa
CERF: Central Emergency Response Fund
CFE: Contingency Fund for Emergencies
CNC: National Coordinating Committee
DDA: Due Diligence Assessment
DD: Development Director
DGLM: Direction de la Lutte contre la Maladie
DRC: Democratic Republic of the Congo
DREF: Disaster Relief Emergency Fund
FCDO: Foreign Commonwealth & Development Office
GIBS: Groupe International de Bailleurs en Santé
HMG: Her Majesty’s Government
ICF: International Climate Finance
IDSR: Integrated Disease Surveillance and Response
IFRC: International Federation of the Red Cross and Red Crescent Societies
IHR: International Health Regulations
IHRMEF: International Health Regulations Monitoring and Evaluating Framework
JICA: Japan International Cooperation Agency
MoU: Memorandum of Understanding
NGO: Non-governmental organisation
PHEIC: Public Health Emergency of International Concern
PNASS: Plan National d'Action pour la Sécurité Sanitaire
PPE: Personal protective equipment
PRO: Programme Responsible Officer
PrOF: FCDO Programme Operating Framework
PSED: Public Sector Equality Duty
REDISSE: Regional Disease Surveillance Systems Enhancement
SEMI: Essential Services for Maternal and Child Health programme
SRO: Senior Responsible Owner
SSA: Sub-Saharan Africa
UHC: Universal Health Coverage
USAID: US Agency for International Development
USCDC: US Centres for Disease Control
VfM: Value for Money
WASH: Water, sanitation and hygiene
WHO: World Health Organization
WHO AFRO: World Health Organization Africa Regional Office

Figures

Figure 1: Epidemic events by disease in the countries of WHO African Region (1970-2016)
Figure 2: DRC score per International Health Regulations core capacity (2020)

## Strategic Case

The Democratic Republic of Congo (DRC) is the largest country in Sub-Saharan Africa (SSA). It is the fourth most populated country in Africa, with an estimated 92.3m people in 2021, which will double within 30 years. DRC is also one of the most fragile and poorest countries in the world: 9% of the world’s extreme poor live in DRC, which will grow to a sixth by 2030.

DRC has the potential to be a major ally and contributor to UK interests in Africa if it can maintain a path towards greater stability, prosperity, and democracy. It matters to the UK because of its long-running conflict which destabilises the region; deep humanitarian and poverty needs; and as home to the second largest rainforest in the world. DRC has the ingredients to move away from a reliance on aid and build a thriving green economy with $24 trillion estimated mineral resources (including key strategic minerals like copper and cobalt), 80 million hectares of arable land, and multiple renewable energy sources.

Despite having this natural wealth, the average per capita income in 2020 in DRC was £409 ($557), just over a third of the Sub-Saharan Africa average of £1084 (US$ 1483). Without a healthy, educated and employed working-age population, DRC will struggle to realise this potential. The situation is particularly acute for women and girls, with 62% of Congolese women beneath the poverty threshold and social norms, cultural practices, and informal institutions which reinforce inequality, economic and social exclusion, and widespread violence against women and girls. The UK is a major development partner of the DRC and we have worked with DRC for 20 years to improve stability, prosperity and development for millions of Congolese.

CONTEXT – HEALTH SECURITY AND PREPAREDNESS FOR HEALTH EMERGENCIES

Since the onset of the COVID-19 pandemic, DRC has seen more than 86,000 confirmed cases and over 1300 deaths. Although the actual number of cases and deaths is likely to be much higher, due to limitations in disease surveillance and death registration, there is growing evidence that suggests excess mortality associated with COVID-19 in DRC (and much of Africa) is lower than in other regions such as the Americas, South Asia and Europe. The causes of this difference are still being explored but a younger population, lower prevalence of non-communicable diseases and differences in exposure to, and natural immunity from, a range of infectious diseases may be factors.

Whilst the direct and indirect impacts of the COVID-19 pandemic are not yet fully understood, it is clear that the pandemic has had a devastating socioeconomic impact, triggering a 3.6% reduction in DRC’s economic growth and forcing an estimated 4 million Congolese into extreme poverty in 2020. The pandemic highlighted both strengths and weaknesses within DRC’s national capacity for preparedness and response to health emergencies. DRC’s response benefited from quick action to scale capacity for confirmatory molecular diagnostics (notably for PCR testing), the rapid implementation of public health controls at points of entry and a core of well-practiced responders with significant experience in responding to health emergencies.
[note] World Bank Group estimates of C-19 impact, 2021

However, as in many other countries, the DRC government has struggled to balance effective public health action in suppressing the virus with wider socioeconomic needs. The implementation of non-pharmaceutical interventions (such as mask wearing, physical distancing, school closures etc.) broadly responded to the changes in the context of the pandemic. However, limited communication of the risks of COVID-19 and the rationale for measures resulted in limited behavioural change and implementation. Surveillance for COVID-19, whilst expanded at pace initially, has generally covered only some segments of the population (e.g. travellers and major urban centres) leaving significant blind spots. Limitations in infrastructure, supply chain management, capacity for treatment and management of the health workforce also posed a challenge to a delivering a comprehensive national response.

A context of multiple threats to public health; limited communication on the risks of COVID-19 and benefits of vaccination; and widespread online disinformation have moderated individual perceptions of risk (only 22% of people believe that their personal risk of being infected with COVID-19 is high) and potentially dampened demand for vaccines. In addition, fundamental challenges affecting the delivery of basic services (including governance, public financial management and human resource management challenges) have constrained the efficient deployment of COVID-19 vaccines, with DRC immunising ~1% of its population (as of April 2022), amongst the lowest coverage in Africa.

Beyond COVID-19, DRC remains uniquely vulnerable to health emergencies and experiences a high frequency of communicable disease outbreaks: low immunisation coverage (~53% childhood immunisation coverage); high population growth that poses a challenge to the provision of basic services (+3 million per year); low governmental health expenditure (covering only 16% of actual healthcare costs); and limited preparedness to prevent, detect and respond to health emergencies constrains DRC’s ability to contain disease outbreaks and mitigate future threats to global health security.
[note] Survey of childhood vaccination coverage, ages 6 – 23 months in Democratic Republic of the Congo; Kinshasa School of Public Health, 2021.
[note] Global Health Expenditure database; World Health Organization, 2018.

Figure 1: A graph of epidemic events by disease in the countries of WHO African Region (1970-2016). Adapted from WHO AFRO technical report3, DRC highlighted in red boxing:

There is evidence that Ebola virus disease is naturally present in certain bat populations. Animal to human transmission (or resurgence from survivors of earlier outbreaks) has led to 13 outbreaks across different parts of the country since 1976. The 10th outbreak of Ebola in the conflict-affected and densely populated North Kivu and Ituri provinces was the second largest outbreak on record and lasted for 2 years from August 2018. The outbreak claimed 2287 lives, and the response cost several times the national annual health budget.

In 2019 and 2020, the DRC experienced the largest measles epidemic on record. It was exacerbated by delays and coordination issues with vaccination campaigns and led to more than 7000 deaths, mostly children. Additionally, there has been a surge in plague cases in Ituri province: 43 cases of bubonic plague and two of septicaemic plague, with nine deaths, occurred between June 12, and July 15, 2020. Cholera outbreaks are a regular occurrence, especially amongst displaced populations with poor access to safe water and sanitation.

Insecurity, conflict and humanitarian crisis are a significant driver of morbidity and mortality in DRC’s populous eastern provinces, undermining access to basic services such as health care and limiting the functionality of the health system in detecting and responding to disease outbreaks. Elections, due in 2023, may further exacerbate instability in some regions.

Health security and the achievement of Universal Health Coverage rely upon the development of strong and resilient health systems with capabilities to prevent, detect and respond to health emergencies. A weak health system and the wider determinants of health (such as nutrition, education and access to safe water) underpin vulnerability to health emergencies in DRC. Only 35% of the population have access to primary health care, 43% of children under five (5.3 million children) suffer from chronic malnutrition; and only 49% of the population have access to clean water. Fundamental challenges to the building blocks of the health system affect the accessibility, resilience and quality of healthcare and capacity for the prevention, detection and response to health emergencies. Low governmental expenditure on health (4.4% of general expenditure in 2019, well below the 2001 Abuja Declaration target of 15%) and low disbursement of allocated budgets preclude sustained investment in public health capacity, especially at district and health facility level.
[note] DRC National Health Development Plan 2016-20
[note] Multiple Indicator Cluster Survey, Unicef, National Institute of Statistics, DRC, 2017-18
[note] i) service delivery; (ii) health workforce; (iii) health information systems; (iv) access to essential medicines; (v) financing; and (vi) leadership/governance
[note] World Bank data [https://data.worldbank.org/indicator/SH.XPD.GHED.GE.ZS?locations=CD]

The health workforce is undersized with just 6 health care workers per 10,000 population, far lower than the critical threshold set by WHO of 23 per 10,000 population. Specialist public health skillsets (e.g. epidemiology; microbiology; social science analysis and behaviour change communication) are scarce and unevenly distributed. Stockouts of drugs, including preventative vaccinations, are common at all levels of the system, impacting on the availability and quality of care, and preparedness for health emergencies. Routine health information is captured through the District Health Information System (DHIS2) which covers all areas of DRC, but with varied implementation and data quality. Surveillance of communicable disease and implementation of WHO’s integrated Disease Surveillance and Response framework is piecemeal; as a result, epidemics are often identified only once significant community transmission has occurred.
[note] WHO Global Atlas of Health Workforce [https://www.who.int/hrh/fig_density.pdf?ua=1]
[note] Rapport d’évaluation: Évaluation de la mise à échelle nationale du DHIS2 en RDC. Epiconcept; June 2017

DRC performs below average against key indices of preparedness for health emergencies in comparison with the wider African region, for example the International Health Regulations monitoring and evaluation framework (IHRMEF). WHO identify 13 ‘core capacities’ required to prevent, detect and respond to public health events; DRC performs below average for Africa on 10 out of 13 (figure 2).

Figure 2: IHR Score per Capacity, DRC (adapted from WHO e-SPAR platform):

DRC has made significant progress in recent years. A concerted focus on strengthening childhood immunisation has delivered a 15% increase in childhood immunisation coverage in target provinces and the country now has an agreed, albeit underfunded, National Action Plan for Health Security (PNASS). The national response to recent outbreaks has contributed to growing expertise in the management of outbreaks within the health workforce and within the National Institute for Biomedical Research (INRB). Prospects for the management of Ebola have also been transformed through the development of effective vaccines (for the most prevalent species), establishment of a global vaccine stockpile, and advances in diagnostics and therapeutics.

There is growing evidence that the frequency of epidemic events in Africa is increasing. This is thought to be due to complex interplay between factors which increase the risk of epidemics, including:
- Inequitable access to quality primary health care and the wider determinants of health such as water, sanitation and hygiene, nutrition.
- Population growth and increased human encroachment into natural environments, increasing contact with wild animal populations and the risk of zoonotic spillover events (i.e. transmission of disease from an animal to human population). 60% of emerging infectious diseases reported globally are zoonotic, or animal in origin.
- The ecological implications of climate change and environmental degradation including disease ‘vector’ (i.e. mosquito) density and the conditions for increased prevalence of water-borne disease;
- Large scale population displacement, which can alter herd immunity and see large numbers of people living in temporary settlements with poor access to water and sanitation;
- Cultural norms and relative levels of food insecurity that impact on the consumption of ‘bushmeat’ increasing the risk of human-animal transmission;
- Increasing population mobility and trade which has the potential to accelerate outbreaks.
Despite progress in strengthening the health system and significantly better health outcomes, much of the population remains acutely vulnerable to communicable disease outbreaks. Inputs to strengthen health systems (including integrated public health capabilities to prevent, detect and respond to future outbreaks) remain necessary in working towards Universal Health Coverage and to mitigate the emergence and spread of epidemics, including pathogens pandemic potential.

RATIONALE FOR UK INTERVENTION AND UK COMPARATIVE ADVANTAGE

Strengthening global health security (GHS) through supporting stronger, better prepared, and more inclusive health systems has been consistently identified as a key HMG objective. The importance of GHS and development of health systems is referenced within the government’s manifesto; the Prime Minister’s five-point plan for international pandemic preparedness; HMG’s Integrated Review of Security, Defence, Development and Foreign Policy; and FCDO’s December 2021 position paper on health system strengthening.

If required, this programme will be the UK’s main vehicle to respond to future outbreaks in DRC, with the aim of supporting DRC’s early and effective response to high-risk outbreaks, minimising risks to regional and global health security. By helping to enable a comprehensive and rapid response to health emergencies, the programme will help stop outbreaks before they develop into significant crises, saving lives and averting socioeconomic costs.

The UK continues to play a leadership role in global health. Our support to strengthen regional and national public health capacity, develop new vaccines and diagnostics and a long-term commitment to strengthening DRC’s health system have been key in addressing recent threats to health security (including Ebola and COVID-19) and make us a well-positioned and respected partner.

The UK has historically played a leadership role in enabling a rapid and effective response to health emergencies in low- and middle-income countries, particularly through our contribution to multilateral emergency response mechanisms. In 2021 the UK was the 2nd largest donor to the United Nations Central Emergency Response Fund (CERF), providing $88m; the 2nd largest donor to the WHO Contingency Fund for Emergencies (CFE), providing $5.5m; and a major donor to the International Federation of the Red Cross/Crescent’s (IFRC) Disaster Relief Emergency Fund (DREF).

These mechanisms have frequently been mobilised in support of DRC’s response to health emergencies. For example, the UN CERF was mobilised in 2020 in response to DRC’s 10th Ebola virus disease (EVD) outbreak and in 2021 to mitigate the risk of cholera outbreaks following the Nyiragongo volcanic eruption. WHO’s CFE was mobilised in 2021 to support DRC’s response to an outbreak of meningitis in Tshopo province, whilst both the CFE and IFRC DREF were activated in response to DRC’s most recent (13th) EVD outbreak.

However, multilateral response mechanisms support a limited range of actors, operate on a replenishment basis and are not designed to act alone in supporting a national response or to provide longer-term support in the event of a protracted emergency. Recent outbreaks have demonstrated that, in the DRC context, greater international support of government-led action is necessary to address health emergencies that threaten wider developmental gains and global health security. In 2018, a measles outbreak in DRC saw a need for significant financing in support of a reactive vaccination effort, whilst Ebola outbreaks (2018-21) underscored the importance of adequately resourcing a multi-disciplinary response centred on strong community engagement and mobilisation.

For this reason, the UK played a leading role in the international community’s support of DRC’s response to the three EVD outbreaks that occurred between 2018 and 2020. FCDO support to DRC’s 10th, 11th and 12th outbreaks totalled £113m, including £93m for the public health and humanitarian response within DRC and £24m for regional preparedness in neighbouring countries. The UK Department of Health and Social Care’s Public Health Rapid Support Team also previously supported DRC’s response to these crises through the deployment of skilled epidemiologists and data analysts.

In addition to our historical support and leadership in responding to health emergencies, the UK is a global leader in science, research, innovation including the development of new tools such as vaccines to prevent epidemics and improve response. Since 2016 the FCDO has invested more than £280m in an Epidemics and Global Health Research Programme. This included funding through the Joint Initiative on Research in Epidemic Preparedness and Response (with the Wellcome Trust) that enabled the development of the ERVEBO vaccine against Ebola (Zaire species) virus. In the context of COVID-19, the UK has pledged up to £160m to CEPI, the Coalition for Epidemic Preparedness Innovations (CEPI) to speed up vaccine development.

LESSONS LEARNED TO DATE

The proposed programme builds on lessons from our support to earlier outbreaks, including:

  1. The importance of prioritising proportionate but early intervention with a “no regrets” approach, recognising that even modest inputs have the potential to shorten an outbreak.
  2. Placing risk communication and community engagement at the centre of a response from the outset, building community trust and ownership of a response and ensuring individuals and communities are empowered to protect themselves and others.
    [note] Risk communication is the dissemination of information to the public, through a range of channels, about health risks and events, such as outbreaks of disease, and instructions on how to change behaviour to mitigate those risks. Effective risk communication reduces fear and empowers individuals and communities with the knowledge of how to protect themselves and others.
  3. Supporting sustainable gains in preparedness for health emergencies by avoiding parallel systems for response: supporting local leadership, coordination and delivery of a public health response through the existing health system.
  4. Implementing a robust zero tolerance approach to corruption and sexual exploitation and abuse.

Having a purpose-built bilateral programme to respond to health emergencies in DRC is also important to safeguard our ability to deliver wider UK objectives in DRC, protect the gains from past humanitarian and development investments, and to avoid diverting longer-term development programmes to short-term emergency response.

IMPACT AND OUTCOME

The SHER programme is a ‘contingency’ programme and would only be activated following an agreed recommendation to respond to a health emergency, or if funding becomes available to support preparedness during the lifetime of the business case. The specific outcomes towards which the programme will contribute, indicators and a log frame would be fully defined at the point of programme activation and when specific inputs are clear. The expected programme impact and indicative outcomes are set out below.

IMPACT: the intended impact of the programme is to help contain high-risk communicable disease outbreaks in DRC earlier, reducing risks to national, regional and global health security. The primary beneficiaries of the programme will be those living in an affected area and susceptible to communicable disease.

OUTCOME(S): At outcome level, interventions will support an effective and government-led response to health emergencies that is proportionate to the level of risk encountered and reduces mortality, morbidity and socioeconomic costs associated with outbreaks. Programme interventions will have a sustained positive outcome for systems and populations including:

  1. a health system that is more resilient and better prepared to respond to health emergencies;
  2. communities that are empowered with knowledge and tools to identify, escalate and minimise the risks of the emergence and spread of endemic diseases;
  3. increased capacity of response partners to manage programmes transparently, accountably and efficiently;
  4. better evidence and analysis to inform preparedness for future outbreaks.

WORKING WITH EXTERNAL PARTNERS

British Embassy Kinshasa (BEK) Policy Engagement in the Health Sector

We will support the delivery of the SHER’s objectives through policy engagement delivered through our human development programmes and engagement with the health sector. Working in support of the government’s health objectives, BEK seeks to enhance global health security by supporting DRC’s progress towards Universal Health Coverage (UHC) and Sustainable Development Goal 3. Our policy priorities in support of these objectives include:

- The development of a more equitable and resilient health system with integrated public health capabilities for the prevention, detection and response to health emergencies.
- The adoption of a One Health approach to health security and preparedness for health emergencies, that recognises the interconnectedness of human, animal and environmental health and the need for interdisciplinary action for health security.
- Maximising the contribution (and synergies) of UK supported multilateral investments (e.g. through the Global Health Initiatives) in the development of a stronger, more equitable health system.
- Supporting clear and effective national governance of the health sector, including the effective coordination of international partners and efforts to strengthen health security and preparedness.
- Supporting a proportionate national focus on action to address the wider determinants of health that underpin health security, including immunisation, nutrition and access to safe water, hygiene and sanitation.

Government of DRC

Whether for a health emergency or longer-term preparedness, the Government of DRC is the principle external stakeholder for the programme. In the event of health emergency where a UK contribution was recommended, programme activities would support the delivery of a government-owned strategic response plan. Should funding become available to support community-based surveillance and preparedness, programme activities would be aligned with and contribute to, the delivery of the National Action Plan for Health Security and implementation of WHO’s Integrated Disease Surveillance and Response Framework which has been adapted and approved by the Government of DRC.

The proposal envisages that implementing partners for both response and preparedness activities would, to the fullest extent possible, work with and through local health systems, contributing to the sustained strengthening of provincial and sub-provincial capacity for the early detection and effective response to health emergencies. At the national level, key government stakeholders include the Ministry of Health and specifically the Direction Generale de Lutte contre la Maladie (DGLM). DRC’s National Institute for Biomedical Research (INRB), whose remit includes laboratory and diagnostic capacity, could also be a key stakeholder should the programme have the resources to support catalytic inputs for preparedness at the national level.

The DGLM chaired National Coordination Committee, convened in response to health emergencies, would be a key mechanism through which the programme’s contribution to a response is coordinated. At the provincial level, the programme will work in coordination with the relevant Division Provinciale de la Santé (DPS) and coordination mechanisms established at the operational level including, where applicable, the UN cluster system.

Health Donors Group

The Groupe Inter Bailleurs Santé (GIBs) is one of the key mechanisms through which the SHER programme will coordinate with other health actors. In particular, BEK participation in the GIBS sub-group on infectious disease will support coordination with other partners and inform programme inputs through the exchange of information on respective programme portfolios, health emergencies and response priorities.

Bilateral donors

A number of bilateral partners (e.g. USAID, ECHO) seek to strengthen the health system’s preparedness for health emergencies through their contribution to health systems strengthening. However, the most targeted and significant support for the development of integrated public health capacities (for prevention, detection and response to disease outbreaks) is delivered through multilateral channels.

The United States, through USAID and US Centres for Disease Control (USCDC), is a key bilateral donor in the DRC health sector. USAID has significant investments to strengthen health systems nationally and in select provinces and US CDC provides technical assistance on public health. Historically the US has supported DRC’s response to health emergencies. The US has also invested in the development of integrated public health capacities through its multi-phase global ‘Emerging Pandemic Threats Programme’. We will remain actively engaged with counterparts on future US investments in DRC’s preparedness and response capacity, ensuring complementarity with any UK intervention through the SHER programme.

The Japan International Cooperation Agency (JICA) has a portfolio of programmes supporting the health sector, including technical cooperation with INRB on diagnostic laboratory strengthening centrally and epidemiological analysis in Kongo Central.

Civil society

A range of national and international NGOs have relevant interests, experience and activities in outbreak response and preparedness, with several organisations having played an active role in response to EVD outbreaks 9 – 13. NGOs may be included as SHER delivery partners, recognised for the specific contextual and technical knowledge they can bring to outbreak response, especially regarding risk communication and community engagement. In determining any inputs by the SHER programme (on response or preparedness), relevant NGO activity and insight would be included as part of the contextual analysis underpinning a recommendation for programme activation and inputs. NGO’s already known to BEK with relevant expertise and experience include Alima; AFENET; MSF; FHI360; IFRC/RC; VillageReach; PATH.

WORKING WITH OTHER UK FUNDED PROGRAMMES

Bilateral – at the country level, the SHER programme will complement our new bilateral health system strengthening programme: Essential Services for Maternal and Child Health programme in DRC (SEMI). Whilst SEMI’s delivery will primarily focus on Kasai province, we will ensure that the programme’s policy engagement at the national level is informed by SHER’s learning on preparedness and response, which are fundamental capabilities of a resilient health system.

Regional – at the regional level the SHER programme will work in close coordination with FCDO Pan-Africa Department’s planned successor to the Tackling Deadly Diseases in Africa Programme. The new programme is expected to operate on a regional basis, providing technical assistance and working with African Public health actors to address key gaps in capacities to prevent, detect and respond to health emergencies at both the regional and national level. Where activated, the programme and team will also engage with relevant capabilities owned by other UK government departments, for example the Department of Health and Social Care’s UK Public Health Rapid Support Team.

Multilateral – at the multilateral level the programme will coordinate with UK investments of relevance to preparedness and response. These include our investments in the major global health initiatives, for example GAVI – the vaccine alliance (£330m per year 2021-25) and our core voluntary contribution to WHO (£340m 2020-24), which supports delivery of WHO’s Health Emergencies Programme. The WHO Health Emergencies Programme works with countries and partners to prepare for, prevent, respond to and recover from all hazards that create health emergencies.

The Global Fund for AIDs, TB and Malaria is the largest multilateral investor in health systems, providing grants to strengthen the key pillars of the health system that also underpin effective preparedness for health emergencies. In particular, the Global Fund’s focus on supporting laboratory and diagnostic capacity and supply chain management are critical in building effective capacity for the detection and response to epidemics.

The World Bank’s Regional Disease Surveillance Systems Enhancement Programme (REDISSE) is investing $75m (IDA) in DRC to strengthen disease surveillance, laboratory (diagnostic) capacity and the public health workforce. Whilst the REDISSE programme has flexibility to support response to health emergencies, it is primarily focussed on supporting surveillance infrastructure upstream from the community level. SHER’s contribution to outbreak response and disease surveillance will complement REDISSE’s inputs by working at the community level in outbreak affected (or high risk) regions.

COMPLIANCE WITH UK LAWS AND POLICY PRIORITIES

Partnership Principles

Overall, the peaceful transfer of power in 2018 marked a step forward for DRC, despite significant and well publicised irregularities which undermined the credibility of the result. DRC continues to experience violent conflict in parts of the country and has a predatory state with endemic corruption. Public financial management reforms have failed to move forward, particularly since 2018. A 2020 Public Expenditure and Financial Accountability assessment (covering data from 2017-2019) found the DRC PFM system to be performing below satisfactory levels across almost all aspects and an overall deterioration in performance compared with the last assessment in 2012. There has been some small progress towards establishing a Directorate for National Treasury and Public Accounting, a necessary action to access World Bank budget support. However critical reforms in public sector and public financial management remain undelivered. Presently, legal frameworks remain often in place without the accompanying action; the political economy does not incentivise rapid change and improvements; and progress is slow and erratic.

The SHER programme will not use the Partnership Principles as a formal mechanism for programming as no UK aid money will flow directly (or indirectly) to the Government of DRC. UK funding must not displace DRC government funding and activation of this programme will be dependent on appropriate prioritisation of the health emergency by the government. Only where the health security of the UK is threatened would we consider investing in a response that the government had not prioritised.

Gender Equality and Inclusion

DRC is ranked 150 out of 162 countries on 2019 Gender Inequality Index. Gender inequality and social exclusion is widespread in DRC. Women’s opportunities are curtailed by high birth rates, early and forced marriages, sexual and gender-based violence, as well as entrenched views about a women’s role in society supported by legal frameworks positioning the man as head of the household.

Gender can be a factor in people’s exposure to, and the subsequent incidence of, communicable diseases. For example, power dynamics can affect a person’s risk of contracting a sexually transmitted infection. Gender inequalities can also impact morbidity, for example through the additional socio-economic barriers that women and girls face in accessing healthcare, such as negotiating caring responsibilities that may traditionally be allocated to women and girls. This programme will support partners and activities that include a strong consideration of gender dynamics as part of the development and implementation of activities, including consideration of mitigating measures to counter negative effects.

Disability

Disability and underlying health conditions are an important determinant in people’s vulnerability to infectious disease. Data on disability in DRC is limited; however, based on global figures, up to 15m (18%) of people could be living with disabilities. Under this programme, we will consider the ability of potential partners and interventions to identify vulnerable participants and design effective measures to prioritise and protect them in the event of a health emergency.

Public Sector Equality Duty

1. This programme will be consistent with the Public Sector Equality Duty (PSED). The protected characteristics that we evaluate will be most likely to be affected by this programme are sex, disability and pregnancy and maternity. As outlined above, the programme will have a strong consideration of both gender and disability in evaluating both partners and interventions and partners will be expected to explicitly outline how they will ensure they meet needs relating to these characteristics.
2. The first element of the PSED around prohibited conduct will be addressed at the due diligence assessment stage. We will ensure that we only work with partners who have strong rules and codes of conduct in place to prevent against discrimination, harassment and victimisation, in line with our wider safeguarding commitments and in light of the difficult safeguarding context in DRC. The second and third elements of the PSED will be considered at intervention design stage: for instance, a community awareness programme around infectious disease might include a component addressing stigma around survivors to fulfil our duty.

Climate and Environment

In line with our Paris Agreement commitments, a climate risk assessment was undertaken as part of the business case development process, identifying the level of risk as moderate. The ecological implications of climate change are thought to be affecting patterns of infectious disease emergence and prevalence. Whilst the programme is not intended to address the root causes of these changes, it will help address some of the direct health impacts.

The business case will need to consider environmental risks, in particular around pollution and waste, such as the disposal of medical waste following any infection prevention and control activities. These risks will be addressed in intervention design with partners and covered in due diligence and direct monitoring processes.

This programme will not undertake shadow carbon pricing and does not invest in fossil fuels. We do not anticipate that this programme will be ICF eligible.

Conflict and Fragility

This programme will adopt a ‘do no harm’ approach and may, due to its national focus, end up working in conflict affected or highly fragile areas of DRC. We will work to understand the context, conflict dynamics and how the programme impacts on the local population. We will ensure the programme does not contribute to worsening conflict. We will work closely with the Politics & Governance and Humanitarian, Peace and Security teams and the Goma office, partner organisations, other UK programmes and wider HMG stakeholders to undertake and share conflict analysis and information. We will work with established delivery partners and screen at due diligence stage for their track record on conflict sensitivity, as well as offer programme and resource – including Conflict and Governance advisors - where necessary to help partners strengthen their approach to conflict sensitivity.
Counter Terrorist Financing

The Allied Democratic Forces (ADF) in the northeast of North Kivu province have been domestically proscribed as terrorist groups by the government of the USA and Canada, but there are no proscribed groups under UN terrorist sanctions, there are groups and inviduals sanctioned for armed activity under UNSCR 1533 as well as UK sanctions. The programme will meet FCDO’s obligation to ensure UK aid is not used to support terrorist activity under the Terrorism Act 2000 (TACT). Use of FCDO’s standard MoU, Accountable Grant and contract templates, Due Diligence Assessments and ongoing risk management will ensure partners understand and comply with their legal obligations; that the Embassy understands partner capacity to monitor and mitigate against aid diversion; and that the risk of diversion by proscribed or listed groups or individuals is proactively monitored over time.

Risk

DRC is a high-risk operating environment and we assess the overall programme risk as Major. The most significant risks associated with this programme are likely to relate to strategy and context (in particular the challenges posed by insecurity and conflict in parts of the country); financial and fiduciary (given the high level of risk relating to fraud and aid diversion); and safeguarding. Safeguarding risks in the DRC context are high, especially in relation to violence against women and girls and sexual violence. Safeguarding risks are considered the highest priority risk area under the new programme. A full assessment of programme risk can be found in the management case and attached risk register. Programme risks will be escalated in line with both the Embassy and FCDO risk policies and monitored via quarterly meetings with partners and, in the event of the programme’s activation, through field visits.

Safeguarding

In a complex operating context such as DRC, sexual exploitation and abuse is a major risk across the lifetime of the programme. The pace and complexity of crises, including health emergencies, demand the proper consideration and resourcing of safeguarding measures to prevent sexual exploitation and abuse. Processes and mechanisms to protect vulnerable populations; identify and mitigate risks; and to swiftly escalate and address safeguarding incidents must be embedded in the response to health emergencies from the outset.

The historical context of serious instances of sexual exploitation and abuse in the response to the 10th Ebola outbreak in eastern DRC 2018-2020 highlight the need for a robust approach to safeguarding. The serious wrongdoings exposed by the New Humanitarian and detailed in WHO’s Independent Commission into sexual exploitation and abuse demonstrated shocking inadequacies in the design and implementation of safeguarding processes and mechanisms. The findings of the Independent Commission primarily highlighted failings within the UN World Health Organization, but also UNICEF, Save the Children, Oxfam and the Government of DRC. All actors responding to health emergencies have an obligation to ensure the prevention of sexual exploitation and abuse.

The UK is committed to improving safeguarding standards. We submitted evidence to WHO’s Independent Commission call for evidence in August 2020 and have worked with allied member states in Geneva to champion WHO reform. Under the SHER programme, we will ensure that safeguarding due diligence checks are in place across each partner and will only work with partners that have sufficiently robust policies and practices in place to mitigate risks and ensure the prevention of sexual exploitation and abuse. Safeguarding risks will be closely monitored through quarterly meetings and direct monitoring visits.

Community engagement and mobilisation forms an important part of any public health response and is likely to be central to the type of activities the SHER programme may support. Asymmetric power relations between response actors and communities in crisis introduces the risk of sexual exploitation and abuse. However, prioritising community participation and building genuine community ownership of activities, alongside adequate safeguarding measures, is central to an effective public health response and to minimising safeguarding risks. We will prioritise partners with the contextual knowledge and relationships to deliver a community-led response that demonstrates strong accountability to local leaders.

## Appraisal Case

OPTIONS SUMMARY

The appraisal case explores 4 potential options:

1. A ‘Do Nothing’ counterfactual
2. Rapid response capability through a partner with national reach
3. Rapid response capability through a partner with national reach and targeted support through other actors
4. [Recommended option] Rapid response through a partner with national reach, additional targeted support through other actors and investment in longer-term preparedness

OPTION 1: DO NOTHING / COUNTERFACTUAL

One option would be to do nothing. In the past we have supported DRC’s response to health emergencies without new funding but through technical inputs, lobbying key actors to shape a more effective response and contributing through existing streams of FCDO funding, including our core contributions towards multilateral response mechanisms. The UK’s future bilateral health programme, SEMI, will support better preparedness for health emergencies, but only through limited technical support at the national level and in Kasai province. FCDO’s wider investments in multilateral actors (e.g. the World Bank, WHO) and global health initiatives (e.g. GAVI - the vaccine alliance) also contribute to building DRC’s capacity to prevent, detect and respond to communicable disease outbreaks. However, as demonstrated by recent outbreaks (measles, 2018; Ebola 2018-21; COVID-19), multilateral inputs can be insufficient to enable DRC to mount a rapid and comprehensive public health response to a major health emergency.

Whilst other donors are likely to continue to support DRC’s response to future health emergencies, the absence of UK funding could leave a significant gap, especially if other donors do not prioritise the response, or react quickly to an emerging threat. Not only could inaction directly threaten the UK or UK interests on the continent, an inability to financially support future responses could also limit the influence of FCDO’s technical and policy inputs. This would reduce our ability to influence key issues such as the effective leadership and coordination of a future response.

In some cases, protracted or large outbreaks of communicable disease (with no option for UK support) could risk significant mortality and morbidity; place strain on DRC’s already fragile health and broader governance system; limit access to essential services; incur significant socioeconomic and political impacts that undermine our wider development and bilateral investments in DRC; and potentially present a risk to the health security of the wider region and UK.

This option would also run counter to our major campaign goal in the DRC Country Plan of ‘DRC more able to contain global health security threats’ and commitments in the Integrated Review. Proceeding with this programme requires no resource allocation at this time: the programme is a vehicle for future funding should an outbreak of sufficient risk profile take place or funds be allocated to support preparedness. This model is based on lessons learned from previous responses and the associated difficulties in identifying an appropriate vehicle to enable rapid UK response without a pre-approved mechanism.

OPTION 2: RAPID RESPONSE CAPABILITY THROUGH A PARTNER WITH NATIONAL REACH

This option would include partnering with one or two large organisations who demonstrate an ability to support the main pillars of a future response to a health emergency (especially risk communication, community engagement and infection prevention and control activities). This approach would prioritise geographical coverage and speed. Suitable partners would be able to leverage an existing presence, established relationships with government, and contextual knowledge to launch and scale operations in any region of the country.

To enable an effective response to the variety of a) communicable disease threats and b) different contexts in which an outbreak could occur, the scope of activities the programme could support (listed below) is intentionally broad. Activities in bold reflect those activities where we assess that the UK is likely to have a comparative advantage and where we have previously prioritised UK support to address critical needs.

1. Risk communication and community engagement
2. Infection prevention and control (including community and health facility water, sanitation, and hygiene)
3. Surveillance and case finding
4. Laboratory capacity for confirmatory diagnosis
5. Case management, therapeutics & capacity for isolation
6. Coordination and implementation of reactive vaccination strategies
7. Safe & dignified burial
8. Mental health and psychosocial care
9. Protection, gender & inclusion
10. Conflict sensitivity analysis
11. Response coordination
12. Social sciences analysis & behaviour change insights
13. Mitigating secondary impacts, supporting continuity of essential services

This option would draw on partners who have existing standing capacity to initiate a response at short notice. Timelines to the implementation of activities would be short and there would be no need for the UK to financially contribute to maintaining standing capacity, as might be the case with smaller organisations. With a small number of partners and a pre-agreed Memorandum of Understanding, this arrangement would be comparatively simple to manage, freeing up Embassy resource for policy engagement and influencing. It is likely that other donors might partner with the same actors as the UK, streamlining donor support.

There are also several risks with this option. Given the limited number of organisations that meet these criteria, we would likely have reduced choice over the range of interventions that we could fund, potentially limiting our ability to address more specific gaps that require specialist input or that are underfunded by other donors. Given the size and breadth of potential actors in this field, UK funding and priorities would need to be managed alongside other donors’ priorities. UK influence and oversight of programming could still be strong, but it would not be at the same level as a bilateral partnership with an NGO for instance. In some contexts, large multilateral actors might struggle to deliver a sufficiently localised response. Earlier outbreaks have demonstrated that successful community mobilisation can depend on strong and localised leadership. If we only had the option to work with a larger organisation (as an intermediary with smaller, more localised partners), it could reduce our ability to support a strongly localised and context-specific response.

OPTION 3: RAPID RESPONSE THROUGH A PARTNER WITH NATIONAL REACH AND TARGETED SUPPORT THROUGH OTHER ACTORS

This option balances geographical coverage and speed (option 2) with an ability to more closely shape an effective response by providing scope for BEK to partner with a wider range of actors who can provide more specialised technical inputs (e.g. protection, gender and inclusion) or leverage specific contextual expertise (e.g. experience and an understanding of local political economy built through a history of working in a given area).

In addition to the strengths of option 2, the additional targeted support possible under this option would enable the UK to partner with the best placed actors to support specific aspects of the government’s response. In contrast with the rapid response only option, we would retain the flexibility to work with a greater number of partners. This option would equip the UK with a greater ability to meet critical gaps in a response and to access partners who may only have regional or local reach, and to fill any gaps left by other donors.

There are risks with this option. A targeted partnership with smaller organisation(s) would likely take longer to negotiate and mobilise. This risk would be partially mitigated by taking forward targeted support alongside a pre-arranged rapid response capability (as outlined in option 2), as well as by using FCDO humanitarian funding rules where rapid lifesaving intervention is needed to allow expedited funding and intervention. This option, with scope for a greater number of partners, is likely to place greater demands on the Embassy from a management perspective. However, this risk could be partly mitigated by using a limited range of organisations or a consortium of partners.

OPTION 4: [RECOMMENDED] RAPID RESPONSE THROUGH A PARTNER WITH NATIONAL REACH, ADDITIONAL TARGETED SUPPORT THROUGH OTHER ACTORS AND INVESTMENT IN LONGER TERM PREPAREDNESS

This recommended option builds on option 3 and would enable the UK to go beyond supporting DRC’s response to health emergencies to include investments that would strengthen community-based surveillance and preparedness for health emergencies, ultimately reducing the risk of major health emergencies and the need for external support of DRC’s response to health emergencies.

In outer years (subject to the allocation of funding), the programme would support a small number of activities to implement WHO’s technical guidelines for Integrated Disease Surveillance and Response (IDSR) in the African Region8, with a focus on building capacity for the prevention and earlier detection of communicable disease outbreaks at the community level. Potential inputs would include:

Supporting catalytic inputs at the strategic level for better preparedness

1. Supporting discrete, short-term pieces of research or analysis with the potential to inform and accelerate a ‘One Health’ approach to preparedness for health emergencies at the strategic level e.g. identifying disease emergence ‘hotspots’ by supporting the consolidation and mapping of data sets covering risk drivers of disease emergence.
2. Supporting discrete, short-term programmes of technical exchange & peer support between external academic/public health institutions and the DRC National Institute of Biomedical Research and/or DGLM. Such programmes would include a focus on specialist competencies of relevance to the prevention, detection and response to health emergencies e.g. genomic surveillance and bioinformatics.

Community based-surveillance in regions at higher risk of disease (re)-emergence

1. Working with local health and agricultural authorities (extension workers), community and religious leaders to establish community-based surveillance structures and identify focal points at the community level.
2. Mapping, identifying and monitoring relevant sources of information for community-based surveillance.
3. Equipping focal points (and communities) with knowledge and resources to identify suspected priority animal and human diseases / public health events (unexpected mortality / morbidity).

Wider community-level preparedness

1. Supporting community groups and local health and agricultural authorities to establish standard operating procedures and lines of communication to escalate alerts for investigation.
2. Providing pre-positioned resources to enable early community-based response, to allow for safe isolation; community level-infection prevention and control measures, including basic water, sanitation and hygiene measures.
3. Supporting provincial level planning and pre-positioning of essential infection prevention and control materials for health facilities (e.g. PPE; hand-washing and disinfection materials).

Ebola survivor care and monitoring

Supporting the strengthening, integration and evaluation of Ebola survivor care and monitoring programmes to support long-term access to care and the management of survivor-associated viral re-emergence.

We consider that option 4 (with scope to invest in preparedness for health emergencies, as well as supporting DRC’s response to such events) represents the best value for money. This is because investing in preparedness for health emergencies is considered vastly more cost effective than resourcing continued responses to recurrent crises. For example, the independent Global Preparedness Monitoring Board has determined that effective, multisectoral, preparedness for health emergencies would cost $5 per person annually. It notes that the cost of responding to the COVID-19 pandemic to date, estimated to exceed $11 trillion, is already equivalent to 500 years of global spending to ensure adequate preparedness. By supporting DRC’s preparedness for health emergencies, we would help strengthen the development of nationally owned capabilities that, in the longer term, would reduce the requirement for UK support to future responses and help mitigate risks to regional and global health security. The costs of infectious disease outbreaks and the relative cost-effectiveness of investing in preparedness are explored in greater detail under ‘Value for Money’ section of the business case, p. 21.
[note] A world in disorder: Global Preparedness Monitoring Board annual report 2020 [https://www.gpmb.org/annual-reports/annual-report-2020]

Preparedness for health emergencies requires governments, development banks and partners to commit resources to strengthen systems upfront, in advance of an emergency. The key implication of this option, compared with options 1-3, is therefore cost. This intervention would require funding allocated to the programme outside of an outbreak, which may not be fiscally possible within the lifetime of the programme. However, by electing to pursue option 4, BEK would have the flexibility and scope to support the best value for money interventions should funding become available. The delivery of community level interventions across multiple working areas may require multiple implementing partners, increasing management costs. Should BEK be able to access and allocated additional funding for preparedness, a risk-based prioritisation would be undertaken with longer-term preparedness activities incorporated within an existing SHER partner agreement.

SUMMARY TABLE OF OPTIONS, ADVANTAGES AND DISADVANTAGES

	Summary of option:	Advantages:	Disadvantages:
Option 1: / Do nothing / counterfactual	No dedicated programme to enable BEK response to future health emergencies or investment in preparedness should funds become available. / BEK investment in health systems strengthening & preparedness in Kasai province only through SEMI health programme / Limited national level policy inputs on preparedness through SEMI and regular BEK policy engagement / Existing FCDO multilateral investments to strengthen health security and progress towards UHC through WHO, World Bank and Global Health Initiatives (e.g. GAVI, CEPI)	No additional cost, enables BEK resources (staff capacity, funds) to be spent on other priorities / Absence of BEK support could lead government or other donors to prioritise their own resources for preparedness and health security	BEK has no ability to respond at pace to a future health emergency and diminished ability to influence an effective response / Absence of BEK funding could prolong future crises, increase risk to global health security and result in greater direct and indirect impacts that may negatively impact UK interests. / Poor alignment with UK strategic priorities that include development of resilient health systems that can prevent, detect and respond to outbreaks
Option 2: / Rapid response capability through a partner with national reach	Scope to support DRC’s rapid response to a future health emergency in any province. / Likely focus on supporting core pillars of an emergency response, including: / Risk communication and community engagement / Infection prevention and control (including community and health facility water, sanitation, and hygiene) / Coordination and implementation of reactive vaccination strategies / Protection, gender & inclusion / Mitigating secondary impacts, supporting continuity of essential services	Enables BEK to support key pillars of government-led response to future health emergencies nationwide and at scale / 1-2 large strategic partners minimises management burden for BEK and enables BEK to avoid management costs between crises	Working with 1-2 large strategic partners limits avenues for BEK support, reducing our ability to shape a nuanced international response that fully addresses critical gaps / Inability to access and deploy certain types of specific technical or contextual expertise outside main strategic partners / Inability to work with smaller CSOs, or those with specialist contextual knowledge, may limit BEK’s ability to support a strongly localised response to a future emergency
Option 3: / Rapid response capability through a partner with national reach + targeted support through other actors	As for ‘option 2’ (above) but with scope to support a more diverse range of civil society actors who bring specialised technical or contextual knowledge. Ability to fund new partners at pace under emergency humanitarian funding rules (where this is appropriate and would meet urgent lifesaving needs)	Provides greater flexibility for BEK to access a wider range of partners and support a more diverse portfolio of response partners / Enables a more nuanced BEK response with agility to further scale-up and respond to gaps by leveraging relevant contextual and technical expertise / Provides greater scope for BEK to shape an effective response that meets government needs / Allows BEK to support a more localised response delivered through CSOs with an established presence in affected region	A larger number of partners would place a greater management burden on BEK, potentially beyond current BEK capacity without additional staffing inputs / A competitive process to solicit, select and implement grants may be slow to mobilise in an emergency context, unless administered under humanitarian spending rules / Disbursements under humanitarian spending rules would lead to a higher level of fiduciary and reputational risk for FCDO
Option 4: [recommended]: / Rapid response capability through a partner with national reach + targeted support through other actors + scope for investment in longer term preparedness	As for ‘option 3’ (above) but with scope for investment, outside of an emergency response context, in longer-term preparedness for health emergencies. / BEK investment (subject to the availability of funds) in activities that would strengthen the implementation of WHO’s technical guidelines for Integrated Disease Surveillance and Response (IDSR) including: / Catalytic inputs at the strategic level for improved preparedness to health emergencies e.g. discrete, short-term pieces of research, analysis or technical exchange / Establish or strengthen community based-surveillance in regions at higher risk of disease (re)-emergence / Support community-level preparedness including the pre-positioning of resources for community-based response	Would enable more sustainable and better value-for-money investment in preparedness for health emergencies (rather than a response only model of support) / Investing in preparedness would support earlier detection of future emergencies, enabling early intervention and reducing the risk of epidemics becoming large crises that pose a risk to regional and global health security	Requires BEK to identify and allocate funds for investment which is not currently affordable and may not be within the lifetime of the programme / A larger number of partners would place a greater management burden on BEK / Even if feasible, BEK investments in preparedness unlikely to be of a sufficient scale to needs

How would a rapid response capability be triggered?

We propose that activation of the programme would be considered either by Ministerial request or for ‘high-risk’ outbreaks that meet at least one trigger criteria from either category A or category B:

Category A: specific priority diseases:

1. An outbreak of a disease considered by the UK Health Security Agency to be a ‘high consequence infectious disease’ or by WHO as an epidemic-prone disease, as set out in their Integrated Disease Surveillance and Response framework.
  [note] https://www.gov.uk/guidance/high-consequence-infectious-diseases-hcid
  [note] https://www.afro.who.int/publications/technical-guidelines-integrated-disease-surveillance-and-response-african-region-third
2. Outbreaks which are assessed by WHO as a Grade 3 Public Health Emergency or declared a Public Health Emergency of International Concern (PHEIC).
3. An outbreak of a high-mortality vaccine-preventable childhood disease e.g. measles, polio.

Category B: outbreak characteristics:

1. An outbreak which is unusual in terms of scale, rate of expansion (basic reproductive value - R0) or virulence (case fatality ratio / morbidity), including outbreaks of unknown cause.
2. An outbreak where epidemiological analysis suggests existing national and/or international response is insufficient to control the outbreak.

Meeting trigger criteria would not automatically result in a recommendation of programme activation. For each outbreak, BEK would undertake a rapid contextual analysis, working with government and partners to understand the nature of the outbreak, determine priority gaps and FCDO’s comparative advantage in supporting the response. If programme activation is recommended, advice, including proposed activities, would be submitted to the Development Director and Head of Mission for review and approval. Either a submission or an information update on programme activation would be provided to Regional Directors and Ministers.

THEORY OF CHANGE

The SHER programme is a ‘contingency’ programme and would only be activated following an agreed recommendation to respond to a health emergency, or should funding become available to support preparedness, during the lifetime of the business case. The programme theory of change (specific inputs, expected outputs and outcomes) would be refined at the point of activation. An overarching theory of change and narrative is outlined here.

By providing inputs that support a comprehensive and government-led response to health emergencies, alongside evidence-based policy advice, the SHER programme will help address consistent resource constraints that could prevent the effective management of future high-risk outbreaks. The programme will leverage FCDO’s strong relationships with government, established through our long-term commitment to the development of the health sector, and our track record of supporting effective response and management of health emergencies.

Targeted inputs decided on the basis of a rapid contextual analysis and lessons from earlier health emergencies will complement those of other health sector partners to deliver a comprehensive national response to health emergencies. A flexible and agile programme design will allow FCDO to support inputs that address gaps in any of the critical pillars of a future response.

Programme inputs grounded in a wealth of evidence, including best practice in communicable disease control and lessons from reviews of our previous Ebola interventions, will ensure intended outputs are delivered. Programme inputs will also align with FCDO’s own analysis of health ‘best buys’, which consider: ‘preparedness and strong early responses to major, potentially cross-border disease outbreaks as a global public good’ and best buy.

Whether activated to support a future response, or to support longer-term preparedness, we expect the programme will contribute to achieving the impact level objective: earlier containment of high-risk communicable disease outbreaks in DRC, reducing risks to national, regional and global health security. However, the delivery of specific intermediate outputs and outcomes will rest upon the availability and mobilisation of FCDO funding for different inputs. Whilst we expect to be able to mobilise funding for response activities from within the FCDO country budget (or other contingency sources), funding for longer-term preparedness activities is less certain and will depend on BEK’s country budget and portfolio in the outer years of the current spending review period (2022-2025).

A focus on delivering outputs that strengthen the core pillars of a multisectoral public health response, placing community engagement and ownership front and centre, will support the delivery of outcomes. Target outcomes include: a more effective response to future health emergencies; more empowered local communities who are better able to identify and address disease risks; more capable partner organisations; continued refinement of the evidence base underpinning response to health emergencies in DRC; and reduced mortality and morbidity associated with outbreaks.

The realisation of programme outcomes and a more effective response to future health emergencies in DRC stands, at impact level, to benefit regional neighbours and other countries. The programme will help safeguard regional and global health security, protecting other populations from health threats that present a cross-border epidemic, or pandemic threat.

THEORY OF CHANGE ASSUMPTIONS

We expect that, where activated, the programme will contribute towards the realisation of outputs in the affected geographical area, with some evidence of sustained improvement in capacity (achievement of outcomes). However, we also recognise that the sustainability of outputs and full realisation of benefits at outcome level (as depicted in the theory of change) rests upon a.) continued government and donor commitment to the development of equitable and resilient health systems with integrated public health capacities to prevent, detect and respond to health emergencies and b.) a security environment that does not lead to widescale reversals in either governance or development. If permitted within the country budget, UK investment in longer-term preparedness and capacity for earlier detection (appraisal case, option 4) would strengthen the likelihood that outcomes are achieved and sustained.

Other key assumptions that underpin the theory of change include:

- Sufficiently granular information is available, and coordinating mechanisms are in place, to enable a swift contextual analysis and identification of key gaps and priorities;
- UK and selected partners are able to mobilise funding and programme at pace to support early response;
- Government of DRC and local communities are mostly receptive to programme support;
- Response governance and coordination is established early and is sufficiently clear and effective;
- National, UK and international response works with and through the existing health system, leveraging our existing relationships via our health programme SEMI and its predecessors, to deliver sustainable improvements in response capacity;
- Partners have access to affected location: logistical constraints can be overcome /security environment is sufficiently permissive;
- Partners coordinate and share information effectively; and,
- Relevant vaccines and therapeutics are available in country.

Outcomes:
GoDRC led response to health emergencies delivers an effective response to health emergencies that is proportionate to risk

Interventions have a sustained positive impact on systems and populations:
- health system better prepared;
- communities empowered to minimise ongoing risks;
- increased partner capacity to manage programmes in a transparent, accountable, and efficient way;
- better evidence and analysis to inform preparedness for future outbreaks.

Reduced mortality, morbidity and socioeconomic costs associated with communicable disease outbreaks in DRC

Inputs:
Up to £12m in the event of a recommended UK response, deployable through a choice of partners, depending on context and key gaps

Targeted inputs to understand and address outbreak drivers; empower individuals and communities to reduce and interrupt disease transmission; protect health care workers

Technical and policy inputs from British Embassy Kinshasa and British Embassy Office Goma and HQ

Problem: DRC is a global hotspot for communicable disease outbreaks with improving, but stretched, capacity for early detection & response to costly outbreaks.
UK response: provide a framework to offer rapid support towards DRC’s future response to high-risk communicable disease outbreaks, and enhance earlier detection, helping to protect regional and global health security.

RESPONSE ACTIVATED
Processes:
- Develop and maintain productive relations with GoDRC response architecture
- Identify and analyse emerging health threats, informing recommendation for programme activation to HOM & DD
- Liaise with GoDRC, WHO, other donors and response partners to identify needs and determine appropriate UK response
- Identify and explore opportunities for longer term investment in preparedness
- Lessons learned are shared across the health sector and partners in DRC and HQ

Foster systems strengthening approach in any health emergency response

Outputs:
Well resourced, government led response to high-risk health emergencies, delivered through existing health systems

More effective surveillance, case-finding and diagnosis enables identification and interruption of chains of transmission

Communities understand risks of outbreak and have knowledge and resources to prevent and reduce transmission (behaviours, WASH)

Health care workers are equipped with knowledge and resources (e.g., PPE, IPC materials) to protect themselves, prevent nosocomial transmission, maintain essential services and public confidence in health system

Commitment and measures to ensure the prevention of sexual exploitation and abuse and effective public financial management is embedded across emergency response

Vaccines, therapeutics, and diagnostics are effectively deployed to manage the outbreak and reduce morbidity / mortality

Assumptions:
- FCDO able to mobilise sufficient funding where response recommended
- UK / partners able to mobilise programme at pace
- Government of DRC / communities invite support.
- Response coordination is clear and effective
- Partners have access to affected location
- Vaccines, diagnostics and therapeutics are available in country
Impact:
High-risk outbreaks in DRC are contained, reducing risks to national, regional and global health security.

VALUE FOR MONEY

The costs of infectious disease epidemics

As well as the deep human costs (over 5 million deaths globally as of February 2022), COVID-19 has made the potentially catastrophic socioeconomic costs of communicable disease outbreaks abundantly clear, triggering a 5.2% contraction in global GDP (3.6% reduction in growth in DRC) and pushing 97 million more people (at least 4 million of whom are in DRC) into extreme poverty in 2020. Costs associated with outbreaks of communicable disease arise from the direct (health) and indirect (socioeconomic) impacts they cause.
[note] World Bank Group estimates of C-19 impact, 2021

The impacts of communicable disease outbreaks are often disproportionate to the number of people directly affected: for example, the 2013-16 West Africa Ebola outbreak saw ~28,000 cases and 11,000 deaths – a tragic human toll; yet an outbreak that directly impacted ~0.1% of the overall population (of Guinea, Liberia and Sierra Leone) led to an estimated economic loss of 16% of regional income. This loss was driven by the direct (health) costs of the response, and indirect costs resulting from lower productivity and economic disruption driven by changes in consumer behaviour and border restrictions.
[note] The Economic Impact of the 2014 Ebola Epidemic, 2014, World Bank Group.

The social costs of the West Africa Ebola outbreak were also profound. Liberia lost 8% of its doctors and nurses to Ebola, materially impacting the health system’s capacity to provide essential services; immunisation coverage for children in the region dropped by 30% and school children lost between 33 and 39 weeks of schooling.
[note] Cost of the Ebola Epidemic 2014-16, US CDC

Increasing connectivity across geographies, facilitated by enhanced travel and trade will amplify the human and socioeconomic impact of future outbreaks, underscoring the vital importance of preparedness to effectively prevent, detect and respond to outbreaks.
[note] A Framework to Counter Infectious Disease Crises. The Case for Investing in Pandemic Preparedness. Commission on a Global Health Risk Framework for the Future; National Academy of Medicine (US); 2016

Cost-effectiveness of investments for enhanced preparedness

Preparedness for epidemics refers to ‘a range of health and non-health interventions, capabilities and systems at the community and national levels. Their purpose is to prevent, detect, and respond to the spread of disease and other hazards, mitigating social, economic and financial disruptions’. The proposed programme will primarily support the rapid and comprehensive response to outbreaks, reducing transmission and mitigating direct and indirect impacts.
[note] Why preparedness is a smart investment, Resolve to Save Lives

Further investment in national capacity for rapid response, especially at the community level, remains crucial to support the early containment of infectious disease outbreaks in DRC. This is because outbreaks become exponentially harder to contain when case numbers and transmission increase. Such investments, whilst less cost-effective than upstream investments in prevention and detection, remain necessary to mitigate the impacts of outbreaks and can be considered cost-effective: one study of response to meningitis outbreaks demonstrated that faster response (accelerating the timeframe for reactive vaccination) could avoid a 218% increase in cases and reduce associated costs13.

Subject to the availability of funding, the programme will also support longer term preparedness for health emergencies, with a particular focus on community-based surveillance, which would support the earlier detection of outbreaks. FCDO’s own analysis identifies preparedness and strong early responses to major, potentially cross-border disease outbreaks as a ‘best buy’ and global public good because countries and regions stand to benefit from the reduction in risk of a cross-border epidemic (or pandemic) that local investments in preparedness, elsewhere, can deliver.

Because of the disproportionate socio-economic impact of outbreaks, investments in preparedness that mitigate or avert the impacts of disease outbreaks on lives, livelihoods, health system resilience and economies are considered by the World Bank to offer an extraordinarily high potential return on investment. Returns on investment that enhance the preparedness of animal and human health systems are estimated to be as high as 10:112.
[note] Financing Pandemic Preparedness at a National Level, International Working Group on Financing Preparedness

There is good evidence - for example, comparing the response of comparatively well-prepared Nigeria to other, lesser prepared nations during the 2014 West Africa Ebola crisis - that responding to outbreaks is more costly than investing in prevention and earlier detection. In other words, preventing an outbreak is more cost effective than resourcing recurrent responses to outbreaks. This is why FCDO continues to prioritise investments in country capacity for the prevention and detection of outbreaks, including investments to: strengthen childhood immunisation, improve access to quality health care and address the wider determinants of health such as nutrition and WASH.

Expected benefits of the programme:

The proposed benefits of the programme include:

  - A faster and better resourced, government-led response to major health emergencies leading to reduced morbidity and mortality associated with communicable disease outbreaks;
  - A more effective response to health emergencies that adopts a localised approach to delivering a public health response characterised by strong community engagement and ownership;
  - Communities better empowered to minimise the risks of outbreaks and to play an active role in mitigating outbreaks when they do occur
  - A better prepared health system with integrated public health capabilities for the prevention, detection and response to outbreaks of communicable disease
  - Better evidence and analysis to inform preparedness for future outbreaks

The programme’s contribution towards the realisation of proposed benefits is contingent on FCDO being able to rapidly mobilise resources in response to an approved recommendation for programme activation. The Embassy’s policy engagement at the national level will help to create an enabling environment for programme delivery and contribute to the realisation of these benefits. However, it is expected that benefits will primarily be accrued in the geographical region(s) in which the programme is activated.

It is important to note that the proposed programme budget (£12m), alongside government and partner investment, is sufficient to contribute towards the realisation of proposed benefits but is not sufficient to ensure these benefits are delivered within the programme lifetime. The 2019-2023 National Action Plan for Health Security, developed on the basis of a WHO facilitated Joint External Evaluation, included a financing requirement for $717m, but is significantly underfunded. In the absence of additional domestic and international financing, DRC’s significant needs in building integrated public health capabilities for the prevention, detection and response to health emergencies will remain partially unmet.

Outcome Level Monitoring (effectiveness)

Monitoring the delivery of benefits (outcomes), and defining the programme’s contribution in achieving these benefits, offers one route to assess the overall value for money of the programme. However, quantifying the programme’s expected contribution to reduced morbidity and mortality associated with communicable disease outbreaks is challenging. Firstly, because a reduced burden of communicable disease is expected over time and consistent with long-term developmental trends, underpinned by drivers including vaccination coverage and improvements in the wider determinants of health (e.g. access to water, sanitation and hygiene, nutrition). Secondly, because the counterfactual impact of a future health emergency, without UK support, is unknown.

Benefits (outcomes) related to the overall efficacy of outbreak response could be quantified and monitored by monitoring the median time to outbreak detection, notification and control over the duration of the programme. A methodology and analysis has previously been undertaken (2017-19) to help quantify the contribution of earlier efforts to strengthen preparedness. However, this would require significant resources for evaluation which are not available. We will engage WHO and other stakeholders to determine whether continued monitoring of these metrics is planned or feasible.
[note] Impouma B, Measuring Timeliness of Outbreak Response in the World Health Organization African Region, 2017–2019 (https://www.ncbi.nlm.nih.gov/pmc/articles/PMC7588517/pdf/19-1766.pdf)

The programme’s contribution towards the realisation of benefits related to preparedness (e.g. capacity for surveillance, emergency preparedness, emergency response operations and risk communication) is likely to be difficult to disaggregate from other contributors, without a full contribution analysis, which is not envisaged for reasons of affordability. However, monitoring the overall delivery of such benefits is possible through the International Health Regulations (IHR) Monitoring and Evaluation Framework and progress against IHR benchmarks, which are self-assessed by states annually.
[note] IHR Monitoring and Evaluation Framework; https://extranet.who.int/sph/ihr-monitoring-evaluation
[note] IHR benchmarks; https://apps.who.int/iris/handle/10665/311158

Delivering value for money (VfM) through the design and implementation of the programme

The programme will drive VfM through the selection of appropriate partners, including those most able to:

  - Work effectively in support of a Government of DRC led response to health emergencies, delivered where possible through the existing health system;
  - Facilitate and build strong community ownership of responses, through effective community engagement;
  - Respond at pace, saving lives and minimising cross-border risk;
  - Offer economies of scale through an ability to scale response operations nationally, according to need.

Sustainability is a key consideration. By selecting partners and interventions that operate in support of existing health systems, the programme will seek to strengthen durable capacity for response, rather than deliver a siloed approach to addressing health emergencies.

Priority interventions the programme will support (including risk communication & community engagement; emergency provision of water, sanitation and hygiene and; infection prevention and control) represent strong value for money because they are: effective – based on robust evidence of a public health approach that interrupts and minimises disease transmission; economical – requiring relatively inexpensive commodities; efficient – because such activities when delivered through a localised partner and with communities, have a short delivery chain; equitable – these interventions will prioritise the mobilisation of entire affected communities. Empowering community members to lead actions that minimise risk to themselves and others, including vulnerable groups.

Key cost areas and drivers related to the programme’s expected activities are outlined below:

Cost area	Cost drivers
Development, production and distribution of context appropriate risk communication materials.	Public health & behaviour change communication expertise (labour market) / Graphic design & printing services / Raw materials (flip-charts, poster paper etc.)
Salary, transport, accommodation and telecommunications costs for non-government response workers.	NGO / multilateral salary costs / Market pricing for accommodation / hotels / Market pricing for telecommunications (calls / data)
Planning and implementation of training events for response workers, local government and community members.	NGO / multilateral salary costs / Venue costs / Agreed rate of appropriate and standardised Per diem payments
Procurement, transportation and distribution of key commodities including infection prevention and control materials (e.g. personal protective equipment, cleaning and disinfection materials, hand washing equipment)	Effectiveness of procurement practices / Market cost of commodities / Transportation costs

Whilst undertaking due diligence of potential partners, we will seek to understand and assess partners’ approach to monitoring value for money and managing costs, focusing on major cost areas. In agreeing MoUs / grants for specific activities, we will work with partners to identify relevant VfM metrics that can be monitored and reported during implementation.

Where possible we will seek to strengthen VfM by requiring partners to benchmark costs. For example, infection prevention and control commodities (including PPE) could be benchmarked against publicly available reference information following the COVID-19 pandemic (e.g. pricing through WAMBO, the Global Fund’s online procurement platform). Costs relating to NGO worker salaries, accommodation and transport will be benchmarked against comparable humanitarian (emergency response) or relevant previous health emergency response programmes.
[note] https://www.theglobalfund.org/media/10161/covid19_personalprotectiveequipmentoxygentproducts_list_en.pdf

Wider factors that may impact VfM

A wide range of contextual factors have the potential to impact the VfM of the programme. The intended approach to risk management is outlined in the ‘Management Case’. The risks with the most potential to impact the VfM of the programme are:

  1. Fragility and conflict. DRC is a one of the world’s most conflict affected countries. The ability of government and partners to mount an effective public health response in areas subject to insecurity, violence and conflict has previously been limited, as demonstrated by the protracted 10th outbreak of Ebola in eastern DRC. More recent outbreaks (#12, #13) affecting the region have, however, been contained more rapidly, in part due to the availability of vaccines and therapeutics which were still in the early testing phase during outbreak 10. We will mitigate this risk by ensuring that, where appropriate, we learn lessons from previous outbreaks and ensuring conflict sensitivity analysis informs the development of response strategy, and by working with actors who have relevant expertise and experience operating in fragile environments.

  1. Health system capacity. Weaknesses across the core pillars of the health system (both systemic and localised) have the potential to affect the VfM of programme interventions. This is because an effective public health response to health emergencies (and longer-term preparedness for health emergencies) is contingent upon a resilient and accessible health system, able to deliver equitable and quality health care.

In the DRC context, health system challenges (including those affecting the health workforce; service delivery; public financial management; leadership & governance; and health management information systems) impact the functionality of the health system and may affect the VfM of programme interventions. We will mitigate this risk through our wider bilateral and multilateral investments in health systems strengthening, governance and public financial management and our policy engagement on health sector development.

  1. Leadership, governance, and coordination of an emergency response. Effective local leadership and coordination is essential to delivering an effective response to health emergencies. This requires the clear devolution of operational leadership to the local level and effective coordinating mechanisms between government, response partners and community actors. Weak leadership of a response, or poor coordination, could negatively impact the VfM of programme interventions. We will manage this risk by advocating for a localised and effective approach to response coordination and leadership, with strong government ownership and appropriate mechanisms for response coordination.

## Commercial Case

DELIVERY OPTIONS

SHER will be delivered through third parties, likely a mix of multilateral organisations and NGOs depending on the circumstances in which the business case is activated. We have considered procurement of services from the private sector through a competitive tender. However, we assess that this route would be unsuitable for three reasons. Firstly, the time needed for a competitive procurement process in DRC would not allow the programme to rapidly mobilise in an emergency context. Secondly, the ‘dormant’ nature of the programme would not generate a guaranteed return for the supplier (in a best-case scenario the programme would never be activated). Thirdly, for a private sector supplier, maintaining a standing response capacity would likely incur a management fee and other operational costs - even if no response were launched - which is unaffordable and could undermine the value for money of the programme.

In partnering with a mix of multilateral organisations and NGOs, we expect that unaffordable recurrent management and/or operational costs can be avoided by only entering into a partnership agreement at the point of intervention design and delivery. In the case of multilateral partners and some NGOs, some receive core funding from the UK which enables them to maintain standing capacity or ongoing programming. Early engagement with potential partners, due diligence and the pre-agreement of MoUs or accountable grants with key strategic partners and potential application of emergency humanitarian funding rules (where appropriate) would enable us to expedite programme mobilisation, if required.

The recommended option will be delivered in three components, set out in the table below:

Components	Delivery Channel	Type of agreement
1. Rapid Response in a health emergency	This component would require partner(s) with national reach and existing standing capacity to respond to an outbreak. We assess the best candidates to be a United Nations Agency or the International Federation of the Red Cross. / Depending on the scale of UK response and emergency context, delivery of the rapid response component may require BEK to supplement its own technical (advisory) capacity. The programme would support this by leveraging FCDO’s established HSOT programme enabling, for example, the draw-down of humanitarian expertise.	Memorandum of Understanding or Accountable Grant / CHASE-owned HSOT contract.
2. Targeted, specialised support in a health emergency	There are a variety of NGOs operating in DRC who may be well positioned to deliver this component. The relative competitiveness of potential partner NGOs will be dependent on the geographical location of the relevant outbreak, the type of outbreak (pathogen), and priority activities required. This will be the route to engage suppliers who are well placed to respond (with specific technical or contextual expertise) but may lack the existing standing capacity to provide an immediate rapid response.	Accountable Grant
3. Investment in preparedness for prevention and early detection of health emergencies	If this component was activated and affordable within the BEK country budget in outer years, we assess the majority of activities (paragraph 74; c-i) would be best delivered by one of the partners under components 1 or 2. / Discrete, short-term research, analysis or programmes of technical advice, exchange & peer support (paragraph 74; a-b) would be best delivered by an academic institution or commercial supplier with relevant experience and expertise. BEK has access to several established FCDO contractual framework agreements for the provision of these types of service. Alternatively, a contract could be tendered or agreed with an appropriate supplier.	Memorandum of Understanding or Accountable Grant / FCDO framework agreements for the provision of services or dedicated contract

COMPONENT 1: RAPID RESPONSE IN A HEALTH EMERGENCY

In surveying the supplier market, three partners were identified as broadly suitable to deliver interventions under this programme to FCDO standards, each with the geographic coverage, thematic expertise and standing capacity required. Potential partners to be considered under this component are:

  1. UNICEF: have frequently supported key aspects of outbreak response in DRC, particularly those of priority to the UK. Well placed to deliver infection prevention and control measures (such as community and health facility water, sanitation and hygiene); risk communication and community engagement activities; reactive vaccination campaigns; safe and dignified burial and integrated outbreak analytics (for example, incorporating social science and behavioural insights into emergency responses).
  2. IFRC: are experienced and well placed to deliver risk communication and community engagement activities, as well as safe and dignified burial, mental health and psychosocial care. IFRC work with and through the Congolese Red Cross’ extensive association of local brigades, with unique reach to community level.
  3. WHO: has the mandate to lead support to government on health emergencies response and preparedness. The organisation has a well-established Incident Management System for response leadership and coordination (in partnership with government). WHO also possess the technical capacity to support surveillance and case finding; laboratory capacity for confirmatory diagnosis; case management, therapeutics and isolation capacity; and infection prevention and control measures. However, we have serious concerns about WHO DRC’s programme management and financial management capability in DRC and the robustness of its safeguarding procedures. These concerns would need to be fully resolved before we can recommence direct funding.

Under the SHER programme, BEK would perform due diligence assessments and seek to pre-agree a Memorandum of Understanding in readiness for programme activation. MoUs will draw on pre-negotiated templates agreed between FCDO and respective agency HQs. If programme activation is recommended, partner selection for component 1 would be informed by a rapid contextual analysis (paragraph 44) specifying key gaps, response needs, the UK’s comparative advantage and any Ministerial steers. Partners would be selected based on criteria including suitability to deliver in the affected location and technical capacity to deliver the activities required.

All three partners have previously received funding from the UK government and any proposed collaboration would be informed by earlier partnerships. Whilst these organisations have varied expertise, all are in theory well placed to support a range of core activities as described in the appraisal case. Funding would be subject to the successful completion of a due diligence assessment and, where applicable, satisfactory implementation of earlier due diligence recommendations.

There are outstanding actions from a previous due diligence assessment of WHO DRC, as well as the serious findings of The Independent Commission on Allegations of Sexual Exploitation and Abuse in the Democratic Republic of the Congo (DRC) following the response to DRC’s 10th Ebola Outbreak. Any future funding to WHO DRC specifically will be contingent on the WHO Country Office demonstrating progress on the necessary reforms and passing a robust due diligence assessment, including on measures and systems to ensure the prevention of sexual exploitation and abuse. The due diligence assessments for eligible rapid response partners under component 1 will be completed in advance of programme activation.

All three organisations are core delivery partners for FCDO globally and have central assurance agreements in place. FCDO also has institutional leads for each, enabling us to influence programme effectiveness at both country and HQ level to drive best practice and greater efficiency.

Depending on the context of an outbreak and the range of interventions selected, a wide range of commodities could be purchased under this programme including risk communication and IPC materials; vehicles, IT and other equipment. With each partner we would be buying a mix of technical expertise, logistical capacity, commodities and a contribution to the partner’s overheads. Each partner has access to both a core level of staffing and recruitable pools of technical expertise which could be called on to support the interventions proposed under the programme. Given their size and global operations, as well as our organisation- wide partnerships, we have good confidence in each organisation’s procurement ability, including delivering value for money through economies of scale.

COMPONENT 2: TARGETED, SPECIALISED SUPPORT IN A HEALTH EMERGENCY

Procurement of a commercial partner to provide additional targeted support (in a given geography, or in a specific technical domain) is not considered a feasible option because of the likely limitations in working with a commercial supplier (at paragraph 109) and because the unknown nature of an event that triggers programme activation means that required inputs would not be sufficiently clear to enable procurement of services in advance of a crisis. Timely procurement of a commercial partner is also not possible within an emergency timeframe in the DRC context. We therefore assess that delivery via an NGO would be the best approach. For more targeted inputs, a direct relationship with an NGO could also offer BEK greater oversight and influence than with a multilateral partner. There are a range of potential delivery partners under this component and their comparative advantage will be dependent on the nature and location of an outbreak as well as the specific inputs required.

If targeted or specialised programme support was agreed in addition to (or instead of) rapid response (component 1), partners under component 2 would be selected through a call for proposals administered by the Embassy or review of readily available proposals / appeals. Where the PRO, SRO and Development Director agree that emergency intervention is required to deliver life-saving activities, funding for selected proposals could be classified as ‘emergency humanitarian funding’ under FCDO’s Programme Operating Framework (PrOF). Classification of funding as emergency humanitarian funding would enable the rapid disbursement of funding to selected partners upon signing of an accountable grant, with full due diligence and delivery chain mapping taking place following the initial disbursement of funds. In all other circumstances normal PrOF rules would apply and due diligence assessments and delivery chain mapping would take place prior to the signing of an accountable grant.

We expect that potential partners under this component would likely include a mix of organisations with whom BEK has collaborated previously and potentially new partner organisations. It is feasible therefore, that under this component we are less likely to have visibility of previous performance or the effectiveness of organisations’ fraud and fiduciary controls. For routine programme funding specific attention will be paid to this during due diligence assessments, including an assessment of any evidence from partnerships between FCDO and the relevant organisations in other countries. However, a decision to disburse funding under humanitarian emergency funding rules would expose BEK to great fiduciary and reputation risk, this would need to be carefully considered by the PRO, SRO and Development Director and balanced against humanitarian need when making a decision on the most appropriate funding modality.

As in component 1, we would be buying a mix of technical expertise, logistical capacity, commodities and a contribution to the partner’s overheads. It is likely that both non-project attributable costs (overheads) and the price of commodities and equipment will be higher than under component 1, due to smaller operations and smaller economies of scale. From a value for money perspective, this would be justified as this component will be activated to provide specialist expertise (contextual or technical) that is not available under component 1. We judge that the higher costs would be offset by BEK’s greater control and influence of activities in meeting our objectives.

Procurement capability will be a specific focus of the call for proposals and tested further at due diligence stage. Given that access to specific technical expertise (for example in risk communication or infection prevention and control) is likely to be a fundamental part of any response, this will be rigorously evaluated during the selection process.

BEK have other programmes with NGOs operating across DRC, including in difficult to reach areas. These will provide important benchmarks on staff, logistics and overhead cost drivers. We can benchmark commodity costs against the rapid response component, as well as previous and current health security interventions in DRC and worldwide, such as our new health programme SEMI and previous Ebola interventions, taking in to account varying economic contexts of different geographies in DRC, as well as e.g. local needs such as language.

Results will be agreed in advance and measured at quarterly progress meetings where overall performance will be assessed. The Accountable Grant arrangement allows for the termination of the agreement in the event of poor performance and payment to be staggered, most likely in arrears, to ensure BEK can withdraw if the programme performs below agreed expectations.

COMPONENT 3: INVESTMENT IN PREPAREDNESS FOR PREVENTION AND EARLY DETECTION

1. Component 3 includes scope (paragraph 74, a-i) to support two categories of activities:
  1. Activities to support short term research, analysis and programmes of technical exchange (paragraph 74, a-b)
  2. Activities to strengthen community-based surveillance and preparedness in regions at higher risk of disease outbreaks (paragraph 74, c-i)

We consider that activities under ‘category A’ (short term research, analysis and programmes of technical exchange) would be best delivered by an academic institution or commercial supplier with relevant experience and expertise. We consider that the simplest route to procuring these (comparatively low-cost) inputs is through an established FCDO framework agreement with pre-approved suppliers. If a suitable supplier is unavailable within an existing framework contract, we would launch a competitive tender for services or (given the likely low financial value of these inputs) award a single source contract to a suitable supplier where appropriate and permissible.

Should budget become available (and be allocated) to support activities under ‘category B’, we would undertake a call for proposals open to existing (or pre-approved) NGO and multilateral partners under components 1 and 2. We consider that the delivery partner for activities under category B would ideally be an established partner under either component 1 or 2, or pre-approved partner under component 1. This is because a partner engaged at the community level in supporting preparedness under component 3 would be best placed to support a subsequent response, drawing on an established community presence and credibility with local authorities to support government’s response to a health emergency. Minimising the number of partners would also reduce the associated burden on FCDO in terms of programme management, where our capacity to administer this programme is finite.

Partners under component 3 would be subject to the same commercial considerations around due diligence, results and wider supplier management as other components.

## Financial Case

BUDGET
This business case is designed to activate should a significant outbreak of disease occur, in line with the triggers set out in the appraisal case. The budget ceiling is set at £12 million, which we consider would provide sufficient funding to cover the UK’s share of an emergency response and potentially, if additional budget were to become available in outer years, small scale preparedness and surveillance activities.

An indicative budget split, between proposed components, is outlined below. However, as the programme is primarily designed to support emergency response and the availability of future budget is not confirmed, this allocation will remain subject to amendment.

Component	Description	Indicative budgetary allocation
Rapid Response	Supporting the main pillars of a government-led response to a future health emergency, anywhere in DRC, through a partnership with 1-2 large organisations with significant standing capacity for response.	£8m
Targeted, specialised support	Supporting the deployment of specialised technical inputs or specific contextual expertise, through a partnership with smaller NGOs
Investment in preparedness for prevention and early detection	Investments that support longer-term preparedness for, and earlier detection of, health emergencies.	£4m

1. As this business case will, in the first instance, only be activated in an emergency, it is not possible to profile the spend across the lifetime of the programme. Spend will be dependent on the timing and nature of the response required or defined preparedness activities, should funds be available within the UK’s portfolio budget for DRC or the region. Ministers would, however, be advised of any decision to activate the programme via a submission or an information note.
2. Should a recommendation to activate the programme be approved by the Development Director and HMA, funding for an emergency of up to £500,000 would be reprioritised from the BEK budget to enable a response. Funding for a response in excess of £500,000 would require additional resources, potentially from the FCDO crisis reserve or wider Africa Directorate reallocation. The source of funding would also be set out to Ministers as part of advice to activate the programme. Funding for component 3 (investment in preparedness for prevention and early detection) will depend on an increased budgetary allocation to the UK’s ODA portfolio for the DRC or the region in the outer years of the current HMG spending review period (2022-2025).

1. As has been seen in previous infectious disease outbreaks in DRC, the UK may decide to intervene at a level that exceeds the £12 million budget ceiling. In this event, the budget ceiling allows for a significant initial contribution to a response. Additional funds / inputs, if required, could be channelled through SHER following a business case addendum and necessary approvals.
2. Spending planned through this programme would count against the Resource Departmental Expenditure Limit (RDEL). There will be no spending against the Capital Departmental Expenditure Limit (CDEL). All spend within this programme will meet the criteria for Official Development Assistance, as defined by the Organisation for Economic Co-operation and Development's (OECD) Development Assistance Committee (DAC). Spend within the programme is not expected to contribute to international climate finance (ICF) as the planned activities are ineligible.

DELIVERY CHAIN
Multilateral implementing partners will likely deliver their activities through downstream partners, mostly at tier 2. If NGOs are engaged under the response, we would fund them to respond directly at tier 1 or in a consortium where one responds at tier 1 and the other consortium partners become tier 2 partners. It is possible that government health centres or hospitals may be a tier 2 or 3 partner in a response but this would be limited to the supply of response inputs and no funding will be channelled via government systems.

FUNDING INSTRUMENTS
Programme funds could be disbursed through three instruments:
i. Memorandum(s) of Understanding (MoU) with multilateral partners setting out a disbursement, with annexed performance indicators if not provided in a linked appeal. Financial performance will be discussed at quarterly progress meetings.

ii. Accountable Grant(s) with any NGO partners. Budgets for grants will be agreed before implementation and progress monitored on a quarterly basis. Variances within agreed budgets will be investigated and appropriate actions agreed.

iii. Contract(s) awarded via an FCDO framework agreement, tender or single source. Agreed budgets for a contract awarded via a framework agreement or other route would be monitored on a quarterly basis. Variances within agreed budgets will be investigated and appropriate actions agreed.

With multilateral partners, payment will be made in advance (but not in advance of need) in line with our institutional arrangements. This is to ensure that these partners have committed funds to plan their activities against appeals or specific concept notes agreed with FCDO.

EXPENDITURE MONITORING AND REPORTING
The Human Development Team Leader has overall responsibility and accountable for the financial management of this programme as the Senior Responsible Owner (SRO). The Health Security Adviser and Response Manager (PRO) will oversee the accurate forecasting of the programme, scrutinise reports/invoices, monitor partners’ performance on value for money and overall compliance with the Programme Operating Framework.

In the event of programme activation, multilaterals will be required to present an appeal or concept note ahead of any agreement being signed in line with our institutional arrangements. If NGO partners are used, a full budget will be required in advance of a grant agreement. The implementing partners will be responsible for providing regular financial and narrative reports (six monthly in the case of multilaterals and quarterly in the case of NGOs) alongside updated forecasts. The narrative reports will clearly outline the activities undertaken and results achieved, which will be assessed against the agreed workplan.

Assets acquired under this programme will be carefully monitored. Any assets procured under the MoU agreements with multilaterals will be owned by the partner organisation. It is their responsibility to keep a record to track the programme assets and they should do so using an inventory. Any assets procured by an NGO partner will be owned by the FCDO. An asset register will be maintained for all items over £500 and ‘attractive items’ e.g. mobile phones will be grouped to ensure they are captured. An annual check of the assets will be completed and BEK staff will also undertake spot checks during monitoring visits. At the end of the programme, asset disposal will be agreed based on value for money and in line with the FCDO’s Programme Operating Framework. A depreciation schedule will also be set out at the start of any agreement to ensure mutual understanding and reduce fraud risks.

At due diligence stage we will assess the audit arrangements for each organisation. For large multilateral partners, this will involve an understanding of the internal audit function and the recommendations of recent country office reviews, including progress on actions. With an NGO partner, we will seek to understand what existing arrangements they have in place for auditing, likely including auditing by an external partner. Given that both of these audit arrangements will only be able to identify issues retrospectively, this will be a last line of defence in our monitoring arrangements, and will be supported by wider assurance arrangements, including financial spot checks on monitoring visits and fiduciary risk assessments across the delivery chain.

FINANCIAL RISK
We have a receptive appetite for financial and fiduciary risk in DRC. High levels of corruption and a lack of accountability mean that we cannot eliminate these risks, especially if an outbreak were to take place in a volatile or hard to reach area – or should a humanitarian imperative to act outweigh residual risks. This would be clearly flagged to the Development Director, HMA and Ministers. We take a zero-tolerance approach to fraud and communicate this expectation to partners, who are in turn expected to communicate this to downstream partners and, in some cases, build their capacity to manage risks better. We will work only with well-known partners able to demonstrate they have policies and processes which adequately mitigate these risks, and who will act quickly to report and act on any cases of aid diversion if they arise. Monitoring visits will include a focus on evidence of fraud and financial management processes to proactively identify any issues with their implementation.

Our Due Diligence Assessments (DDAs) of partners, routinely conducted before agreements are signed, will examine the capacity and capability of partners to deliver the programme at the local level in the areas of: governance, financial stability, ability to deliver, downstream partner management, and safeguarding. This assessment will provide a good indication of their fraud management processes and an opportunity to communicate expectations and actions to meet FCDO standards. In addition, alongside the delivery chain mapping exercise in the DDA, we will undertake a fraud risk assessment across the delivery chain. In the event the programme was used to disburse emergency humanitarian funding, DDAs (under component 2) would take place after the disbursement of initial funding. This would create additional fiduciary and reputational risk for BEK. The programme’s SRO, PRO and Development Director would need to be satisfied that immediate humanitarian need justified this additional risk in electing to disburse funds under emergency humanitarian funding rules.

We do not anticipate any exchange rate issues under this programme. Partners operate in dollars which has a relatively stable relationship with the pound.

## Management Case

FCDO GOVERNANCE STRUCTURE AND ARRANGEMENTS
Following identification of a public health event that meets the programme triggers (see appraisal case, thresholds for programme activation), a rapid contextual analysis, including consultation with government, WHO and partners, would inform a decision by the BEK Human Development Team on whether to recommend programme activation.

A standard rapid contextual analysis will include consideration of outbreak epidemiology and trajectory, risk to regional and global health security, resource mobilisation to date and a review of existing / planned response by other national and international actors to identify key gaps. A recommendation for programme implementation (including partners, budget, and activities) would be submitted to the Development Director and Head of Mission for review and approval, and Ministers if required. Where necessary, additional technical inputs will be solicited from the FCDO Chief Scientific Officer and Conflict Humanitarian and Security Department chaired Epidemic Threats (EpiThreats) group. Notification of programme activation will be provided for decision or information to Africa Directors and the Minister for Africa, and, if required, wider cross-HMG structures.

The BEK Human Development Team will have oversight of the activation and delivery of SHER. Lesson-learning from previous Ebola outbreaks in DRC has highlighted the importance of the UK promoting a proportionate response to health emergencies. A proportionate response reflects the level of risk presented by an emerging threat and is calibrated against national capacity to manage outbreaks including availability and access to tools (e.g. human resources, vaccines, therapeutics and diagnostics) for the management of an outbreak. The internal resourcing of this programme compared to earlier UK responses to Ebola outbreaks adopts a BEK-led model of HMG response, resourced by a core team drawn from within existing human resources:

  1. 1 x UKB Human Development Team Leader and SHER Senior Responsible Owner (Grade 6) with overall accountability for the leadership and strategic oversight of the programme and response.
  2. 1 x UKB Health Security Adviser and Response Manager and SHER Programme Responsible Officer (Grade 7) who would provide technical leadership on programme activation and response management. They would be responsible for liaison with partners on technical aspects; for coordinating the response with other donors and the Government of DRC; and leading engagement with FCDO’s EpiThreats group.
  3. 1 x UKB Health Security Policy and Response Officer (HEO) who would support the health security adviser in their responsibilities, as well as leading on information management and outbreak monitoring, coordination with HQ / across HMG, engagement with in-country partners and donors, and supporting on the day-to-day programme management of the response.
  4. 1 x UKB Senior Programme Manager (G7) who will dedicate a portion of their time to supporting quality programme management of the response by the Health Security Adviser and Policy Officer. This role will have strategic oversight of the programme finance, risk, monitoring and safeguarding but the day-to-day management will fall to the staff primarily responsible for the programme.
  5. 1 x CBS Deputy Programme Manager (EO) to support programme administration and management.

Additional Embassy and cross-FCDO resources will be available to draw on as required throughout the lifetime of the programme as below:

  1. Ambassador (SCS1): targeted diplomacy with senior stakeholders in government, UN system, Ambassadors and heads of agencies. Overall responsibility for delivery of Country Plan.
  2. Development Director (SCS1): targeted diplomacy with senior stakeholders in government, UN system, Ambassadors and heads of agencies. Responsible for oversight of all ODA spend, compliance with FCDO rules and escalating risk to HQ when outside of risk appetite.
  3. Health Adviser (Grade 7) to support exchange and application of learning between BEK’s health programme (SEMI), with a focus on health system strengthening, and the SHER programme, if activated
  4. Conflict, Peace and Security Adviser (Grade 7): technical advice on conflict sensitivity analysis, peace and security issues in relation to the activation and management of a response.
  5. Political Counsellor (Grade 7) to support political and contextual analysis in the event of a health emergency.
  6. Governance Adviser (Grade 7) to support political economy and contextual analysis in the event of programme activation in response to a health emergency.
  7. Social Development Adviser (Grade 7): technical advice on gender equality, safeguarding, monitoring and evaluation.
  8. Humanitarian Adviser (Grade 7): liaison with the Humanitarian Country Team, advice on the complementarity of emergency intervention with existing and new humanitarian response.
  9. Economist (Grade 7): technical advice on value for money during programme activation and monitoring.
  10. Results Adviser (Grade 7): technical advice on results, monitoring and evaluation
  11. Head of Goma Office (Grade 7): political and contextual advice should the programme be activated to respond in or near the eastern provinces.
  12. Conflict & Humanitarian Rep, Goma Office (Grade 7): contextual advice, advice on synergies across programmes, and relationship management in Goma and eastern provinces, should the programme be activated to respond there.
  13. Finance Manager (Grade 7): technical advice on financial management of the programme.
  14. Risk Manager (Grade 7): technical advice on the risk management of the programme and escalation processes.

The above resources will be sufficient for managing a small-scale response, but staff capacity will be monitored depending on Ministerial expectations for UK engagement, the extent of UK policy and programming (e.g. number of partners / fields of intervention), and the context of the outbreak. Surge staffing may need to be considered if a later decision were made to increase the budget ceiling, or if the emergency was located in a complex, fragile and/or conflict setting. In this situation we would consider drawing on the FCDO’s central advisory and generalist surge capacity (e.g. through HSOT) including possibly funding an additional surge adviser (health or humanitarian) under the programme. We would flag additional HR needs and cost implications early to Africa Directorate and FCDO HR.

The team will directly manage implementing partners with whom BEK enters into a programme arrangement with, but the Government of DRC will also be a key programme stakeholder. Although the government will not be formally included in the BEK’s management or governance of the programme, BEK will ensure that inputs directly respond to, and align with, government-led response plans and relevant national strategic frameworks, (for example the Plan d'Action National pour la Sécurité Sanitaire - PNASS).

We will support strong accountability between the SHER programme and national priorities through active participation in relevant national coordination mechanisms including relevant National Coordinating Committee (CNC) meetings and the GIBS. The programme and partners will also transparently engage in relevant government owned operational coordination structures, (including at the sub-national level) and UN-convened coordination meetings and humanitarian cluster system.

The programme will work closely with other health and humanitarian programmes within the BEK portfolio to ensure coherence and interlinkages are maximised to deliver on the overall DRC Country Plan. The programme will be closely aligned to the planned SEMI programme, focused on supporting health systems strengthening at a national level and health services in the province of Kasai. In the event of a health emergency in Kasai SEMI would take the lead and SHER would likely not be activated. Where relevant, the programme would also be aligned with centrally managed FCDO programmes, for example Pan-Africa Department’s Tackling Deadly Diseases in Africa Programme which supports regional public health actors (such as the Africa Centres for Disease Control) to strengthen preparedness for health emergencies.

MONITORING PROGRESS AND RESULTS

Programme performance will primarily be monitored through a logical framework which will function as the primary management tool. A template logframe will be developed during inception and adapted at programme activation to account for the exact response that the UK has initiated. The programme logframe will be reviewed annually during the Annual Review process following programme activation.

Once activated, BEK will receive reporting from partners to assess progress against targets, risk and financial performance. BEK will hold quarterly meetings with partners to review progress against work plans and assess key challenges to delivery covering at minimum:

1. Progress against milestones and targets and operational issues that affect these.
2. Integration of the programme into the wider response to a health emergency.
3. Assessment the financial situation of the programme, including updates on expenditure and forecasting.
4. Updates of the programme risk register.
5. Updates on aid diversion and safeguarding matters.

For all partners, BEK will underpin conversations on performance, risk and results with regular field monitoring visits to verify information provided in formal reporting and test the quality of interventions. BEK will take a risk-based approach to monitoring, prioritising visits for partners deemed most ‘at risk’. Partners will also be expected to share their own monitoring plans and the outcomes of their own monitoring visits.

RISK MANAGEMENT

The risk management approach for this programme is informed by previous health responses in DRC, including our health systems strengthening programming and in particular our 5 previous interventions to respond to outbreaks of Ebola, which has given BEK a good understanding of the risk environment this programme faces. Given the similarities between this programme and previous Ebola response programming, our risk approach has been based on lessons learned from those responses. Our risk appetite overall for SHER is receptive and the overall risk for this programme at the time of design is assessed as ‘Major’.

As outlined in the Programme Completion Review of the previous Ebola outbreaks, the highest risks in this programme are likely to be around strategy and context, financial and fiduciary and safeguarding. During the previous interventions these risks were outside of the risk appetite of the Embassy but we think that they can be brought within appetite on this programme, due to the mitigations outlined in the risk appetite statement below. This will be kept under review.

Our key risk management tools will be partner selection and effective monitoring and assurance. As outlined elsewhere, all partners will be subject to a robust due diligence process and partners with whom we have historically worked effectively will be prioritised. Whilst there is a relatively limited pool of partners for the primary rapid response component, this risk is minimised by an effective record of previous BEK projects by some. Field monitoring by BEK staff, where security and physical accessibility allows, will further corroborate information received by partners and test that partner policies are being implemented as designed and accountability mechanisms are in place, supported by wider regular engagement with partners and mapping in advance of key assurance risks.

Internal reviews of the programme risk register will take place quarterly and the outcomes recorded on the Aid Management Platform, where a live version of the risk register will be kept. This risk management approach will include clear risk owners, identification of stakeholders and escalation routes up and down the delivery chain. This review will reflect on the written records of field reports and partner meetings during the quarter and include the full programme team. Where risks are found to have increased beyond our appetite, these will be escalated to BEK senior management.

Our overall risk appetite, compared to the corporate and BEK risk appetites is represented below:
Risk Category	FCDO Corporate	BEK	SHER	Alignment
Strategy and Context	Receptive	Receptive	Receptive	Yes
Reputational	Cautious	Cautious	Cautious	Yes
Financial and Fiduciary	Cautious	Receptive	Receptive	Yes
Policy and Programme Delivery	Receptive	Receptive	Receptive	Yes
Safeguarding	Cautious	Cautious	Cautious	Yes
Public Service Delivery and Operations	Cautious	Cautious	Cautious	Yes
People	Cautious	Cautious	Cautious	Yes

We have a receptive appetite for strategy and context risk. DRC is a fragile and conflict-affected state with high levels of corruption and poor infrastructure. An outbreak of a qualifying illness could happen anywhere in the country, including areas which are subject to active conflict or which are very hard to reach. Previous responses to Ebola in conflict-affected areas saw violence directed towards the response and response workers killed, necessitating the pausing of the response at times which was then followed by a surge in cases. We will seek to mitigate this by ensuring that partners have an effective plan for analysing local conflict dynamics and community perceptions of any response, selecting partners that already have experience in these areas with robust security and operational protocols and with sufficient reach and logistics capability to overcome poor infrastructure. We also mitigate these ‘securitisation’ risks through our strategic engagement and lobbying with the wider response and all response elements (not just our implementing partners) to prioritise and strengthen community engagement and contextual humanitarian analysis.

We have a cautious appetite for reputational risks. This reflects that many of the greatest risks to the FCDO’s reputation come from poor management of other risk categories, especially safeguarding, financial and fiduciary and strategy and context risks. Effective mitigation of these wider risks should in turn reduce reputational risks and keep them within risk appetite.

We have a receptive appetite for financial and fiduciary risk in light of the high existing risk of aid diversion and lack of accountability, especially if an outbreak were to occur in a conflict-affected or hard to reach area. We have a zero-tolerance approach to fraud and corruption, and demand high standards from all partners and in the delivery chain to manage these risks robustly, and to reimburse us for any losses. All partners are required to immediately report any suspected cases, which are then managed and investigated in line with central FCDO policy. This programme will also take into account lessons learned during previous interventions against Ebola, including drawing on the PCR and best practice document created by the outgoing team. Whilst this risk could be further mitigated, for instance via the use of a third-party monitoring system, this would increase the cost of an already highly budget constrained intervention and it is unlikely that the increased assurance that this would provide would offset the cost.

Our appetite for policy and programme delivery risk is receptive, because work under this business case will be lifesaving and seeking to end a disease outbreak before it expands more widely. We will work with partners with strong evidence of relevant previous delivery, assessing this as part of the due diligence process, and dedicating time for policy influencing of the response to ensure that it is well coordinated, including utilising the UK’s HQ relationships with response partners where relevant.

There is a high degree of operational risk in DRC and previous interventions have highlighted risks around our ability to monitor programmes where insecurity prevents field visits or there is a lack of staff capacity to manage a response within BEK. These risks can be partially mitigated through effective planning, including workforce planning, planning with partners on monitoring and through effective ‘travel risk assessments’ to enable travel for FCDO staff monitoring. Information security is also a risk that needs to be considered and the due diligence process will need to consider how beneficiary data is managed securely and monitoring visits will need to ensure these processes are being implemented correctly.

1. For safeguarding, we have a cautious risk appetite. The UK has a zero tolerance towards sexual exploitation, abuse and sexual harassment and requires all partners commit to ensuring that UK funded programmes do no harm. Safeguarding risks in the DRC context are high, in particular in relation to violence against women and girls and sexual violence. Safeguarding risks will therefore be the highest priority risk area under the new programme. We will seek to mitigate through effective due diligence on all partners to ensure they have robust policies and systems in place to prevent, identify and effectively respond to all suspicions or reports of safeguarding breaches – including through participant reporting mechanisms such as hotlines or complaints boxes – and ensure that these reports are also communicated to the FCDO. This will be monitored throughout the lifetime of the programme in monitoring meetings, and we will also seek to influence the overall safeguarding agenda in DRC through our policy and influencing work, including the UN’s Prevention of Sexual Exploitation and Abuse Country network. We will also ensure that interventions do no harm by including both conflict sensitivity and climate and environment risks prior to implementation.
2. On people risk, we also have a cautious risk appetite. We currently have the people resources required to implement this programme and regularly review our plans across the embassy to ensure that this remains the case. Nonetheless, resource constraints or competing international priorities could affect this in the future so the risk cannot be eliminated. We will therefore also prioritise the activities that add the most value in terms of programme delivery and risk management.