## Supporting Health Emergency Response in the Democratic Republic of Congo (SHER)

Title: Supporting Health Emergency Response in the Democratic Republic of Congo (SHER)
Programme Value £ (full life): £12 million		Review date: Year 1
Programme Code: 301552	AMP start date: 27/11/2023 / (Business case approved April 2022).	AMP end date: 01/08/2025

Summary of Programme Performance
Year	Year 1 / 2024/2025
Overall Output Score	A
Risk Rating	Major

DevTracker Link to Business Case:	DevTracker Programme GB-GOV-1-301552 Documents
DevTracker Link to results framework:	DevTracker Programme GB-GOV-1-301552 Documents

AR	Annual Review
BEK	British Embassy in Kinshasa
CAC	Community Action Committee
CATI	Case-Area Targeted Interventions
CTC	Cholera Treatment Centre
DD	Development Director
DPS	Division Provinciale de Santé (Provincial Directorate of Health)
DRC	Democratic Republic of Congo
FCDO	Foreign, Commonwealth and Development Office
GoDRC	Government of DRC
HMA	His Majesty’s Ambassador
HOM	Head of Mission
IDSR	Integrated Disease Surveillance and Response
IDP	Internally Displaced People
IOM	United Nations International Organisation for Migration
IPC	Infection, Prevention and Control
M&E	Monitoring & Evaluation
MTC	Mpox Treatment Centre
ODA	Official Development Assistance
PHEIC	Public Health Emergency of International Concern
PHECS	Public Health Emergency of Continental Security
PoE	Point of Entry
PRSEAH	Prevention and Response to Sexual Exploitation, Abuse & Harassment
PRO	Programme Responsible Officer
RCCE	Risk, Communication and Community Engagement
SGBV	Sexual and Gender-Based Violence
SHER	Supporting Health Emergency Response in DRC
SRO	Senior Responsible Owner
TOC	Theory of Change
UNICEF	United Nations Child Emergency Fund
UK	United Kingdom of Great Britain and Northern Ireland
VFM	Value for Money
VHFs	Viral Haemorrhagic Fevers
WASH	Water, Sanitation and Hygiene
WHO	United Nations World Health Organisation

A. SUMMARY AND OVERVIEW

Description of programme

The Supporting Health Emergency Response in DRC (SHER) programme was designed to enable the United Kingdom (UK) to offer rapid support to government-led efforts to prepare for and manage high-risk communicable disease outbreaks in the Democratic Republic of Congo (DRC). With a current business case ceiling of £12m, it is a contingency vehicle to support early and effective response to high-risk communicable disease outbreaks in DRC. DRC is highly vulnerable to health emergencies and experiences a high frequency of communicable disease outbreaks, low immunisation coverage, and limited preparedness to prevent, detect and respond to disease outbreaks. Insecurity, conflict and humanitarian crisis are a significant driver of morbidity and mortality in DRC’s populous eastern provinces, undermining access to basic services such as health care and limiting the functionality of the health system in detecting and responding to disease outbreaks. The country has experienced the two largest recorded measles outbreaks in history (in 2019 and 2023) and 14 of the 34 recognised outbreaks of Ebola have originated from DRC.

Cholera outbreaks in humanitarian settings in Eastern DRC have been occurring alongside the conflict in the Great Lakes region in DRC for decades, with 2023 representing a particularly bad year in North Kivu as displacement from the conflict increased. 2023 also saw massive increase in mpox across DRC, with increased rates of and geographic expansion of clade Ia and the emergence of a new clade (Ib) in eastern DRC. This has spread rapidly across eastern DRC and into neighbouring countries with novel sexual transmission demonstrated in clade Ib accelerating the spread. As of November 2024, there has been over 40,000 notified cases of mpox clade Ib in DRC, and over 1,000 deaths, with mortality highest in children. In this context, the SHER programme was activated in May 2024, with approval at HMA level, based on the triggers set out in the business case.

Programming began with an allocation to UNICEF in August 2024, to respond to concurrent outbreaks of mpox and cholera. Response activities were initially focused in 3 provinces for mpox and 2 provinces for cholera. Support to UNICEF has since been extended to cover national digitisation of disease surveillance and mpox response in North Kivu. WHO has also since been selected as a partner, to support mpox response activities nationally and in the provinces of South Kivu, North Kivu and Kinshasa. In total, £9m has been programmed in the reporting period, with £4.6m for UNICEF and £4.4m for WHO. This funding is aligned with the Government of DRC’s national response plans and, through SHER, the UK aims to support the country-wide efforts to arrest the spread of mpox and to reduce morbidity and mortality of mpox and cholera.

This Annual Review covers the period up to November 2024. Therefore, it will review the initial 4 months of activities delivered by UNICEF for mpox in South Kivu, South Ubangi and Sankuru, and cholera response in North and South Kivu. It does not cover in detail the expanded UNICEF activities on digitisation of surveillance or mpox response in North Kivu, nor the WHO mpox responses including in North and South Kivu and Kinshasa, as these components are commencing outside of the review period and will be covered in the next Annual Review.

Summary supporting narrative for the overall score in this review

Output	Score	Weighting
Through UNICEF, reduce the morbidity and mortality related to mpox and cholera in affected communities in targeted provinces (Sankuru, South Ubangi, South Kivu for mpox; North and South Kivu for cholera)	A	90%
Establish additional mpox response support via WHO	A	10%
Overall Programme Annual Review Score	A	100%

This programme is assessed as achieving a score of A. It is worth noting that activities under this programme have been ongoing for just a short period of time, but to date delivery has been effective across the two output indicators. The milestones agreed with UNICEF were set for 31 March 2025 and in many areas they are already exceeding or are on course to reach them by March. This is an achievement given the highly difficult operating context, with a significant proportion of activities taking place in hard-to-reach, conflict-affected health zones in South Kivu and North Kivu.

Major lessons and recommendations for the year ahead

Top-line recommendations are given below, which are not repeated throughout the document. Recommendations against specific outputs are recorded in Section C:

Recommendation 1: FCDO to work with UNICEF to ensure that all learning and recommendations for the first four months of the programme are reflected in the plans for the remaining four months of programming, to ensure all milestones are met.

Recommendation 2: FCDO should produce a complete logframe for full reporting year ahead, encompassing UNICEF and WHO components.

Recommendation 3: FCDO should develop a VfM framework for SHER to allow a full analysis in next year’s Annual Review.

Recommendation 4: British Embassy Kinshasa should feed into the planned FCDO regional lessons learned exercise, which will look into outbreak responses from across the region, including cholera, mpox and Marburg.

Recommendation 5: FCDO should consider how the UK can better help, over the medium to long term, to prevent and mitigate future outbreaks to high consequence infectious diseases in DRC through health systems strengthening and other preparedness activities.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The theory of change (TOC) for this programme aims to contain outbreaks and reduce risks to national, regional and global health security. The TOC outlines that for a given outbreak targeted inputs should bolster a government led response to be delivered through existing health systems across multiple response pillars including;

1. Surveillance
2. Risk, Communication and Community Engagement (RCCE)
3. Infection Prevention and Control (IPC) & Water, Sanitation and Hygiene (WASH)
4. Vaccination and therapeutics
5. Prevention of Sexual Exploitation, Abuse and Harassment (PSEAH) embedded within the response
The TOC remains relevant through this reporting period, with our contributions to UNICEF supporting multiple pillars of the national response to mpox, including directly (i – iv) or indirectly (v). Moreover, the future programmed work through WHO will similarly support these response pillars.

It is worth noting that, given the scale of the mpox outbreak, the contributions made to the national response through this programme, cannot of themselves contain the outbreak, as outlined in the IMPACT section of the TOC. However, it is likely that they will contribute successfully to mitigating regional, national and global health security risks of this outbreak, and in particular within the regions and health zones in which the programme is operable.

Likewise, the cholera outbreaks in Eastern DRC have been recurrent for decades and are exacerbated by iterative displacements in the region, driven by the conflict. The design of the cholera intervention cannot fully impact the root causes of cholera outbreaks (displacement, poor sanitation, cramped living conditions, water access) and is instead designed to reduce chains of transmission and mitigate the scale of outbreaks of cholera and improve prognosis of cases.

Outcomes:
GoDRC led response to health emergencies delivers an effective response to health emergencies that is proportionate to risk

Interventions have a sustained positive impact on systems and populations:
- health system better prepared;
- communities empowered to minimise ongoing risks;
- increased partner capacity to manage programmes in a transparent, accountable, and efficient way;
- better evidence and analysis to inform preparedness for future outbreaks.

Reduced mortality, morbidity and socioeconomic costs associated with communicable disease outbreaks in DRC

Inputs:
Up to £12m in the event of a recommended UK response, deployable through a choice of partners, depending on context and key gaps

Targeted inputs to understand and address outbreak drivers; empower individuals and communities to reduce and interrupt disease transmission; protect health care workers

Technical and policy inputs from British Embassy Kinshasa and British Embassy Office Goma and HQ

Problem: DRC is a global hotspot for communicable disease outbreaks with improving, but stretched, capacity for early detection & response to costly outbreaks.
UK response: provide a framework to offer rapid support towards DRC’s future response to high-risk communicable disease outbreaks, and enhance earlier detection, helping to protect regional and global health security.

RESPONSE ACTIVATED
Outputs:
Well resourced, government led response to high-risk health emergencies, delivered through existing health systems

More effective surveillance, case-finding and diagnosis enables identification and interruption of chains of transmission

Communities understand risks of outbreak and have knowledge and resources to prevent and reduce transmission (behaviours, WASH)

Health care workers are equipped with knowledge and resources (e.g., PPE, IPC materials) to protect themselves, prevent nosocomial transmission, maintain essential services and public confidence in health system

Commitment and measures to ensure the prevention of sexual exploitation and abuse and effective public financial management is embedded across emergency response

Vaccines, therapeutics, and diagnostics are effectively deployed to manage the outbreak and reduce morbidity / mortality

Processes:
- Develop and maintain productive relations with GoDRC response architecture
- Identify and analyse emerging health threats, informing recommendation for programme activation to Head of Mission (HOM) & Development Director (DD)
- Liaise with GoDRC, WHO, other donors and response partners to identify needs and determine appropriate UK response
- Identify and explore opportunities for longer term investment in preparedness
- Lessons learned are shared across the health sector and partners in DRC and HQ

Foster systems strengthening approach in any health emergency response

Assumptions:
- FCDO able to mobilise sufficient funding where response recommended
- UK / partners able to mobilise programme at pace
- Government of DRC / communities invite support.
- Response coordination is clear and effective
- Partners have access to affected location
- Vaccines, diagnostics and therapeutics are available in country
Impact:
High-risk outbreaks in DRC are contained, reducing risks to national, regional and global health security.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

As stated above, given their scale, it is not conceivable that SHER in and of itself can contain the regional mpox outbreak or the chronic cholera outbreaks in North and South Kivu. Mpox is quite likely to become newly endemic in some areas, and SHER itself currently covers only 5 provinces in DRC, and does not exhaustively cover all the health zones within these provinces. This is in line with the expected benefits of the programme outlined in the business case, where it is noted that “it is expected that benefits will primarily be accrued in the geographical region(s) in which the programme is activated” and that this programme [will be] “sufficient to contribute towards the realisation of the proposed benefits but not sufficient to ensure these benefits are delivered within the programme lifetime”.

Indeed, the programme is operating in some of the most important health zones with respect to the outbreak (e.g. 10 priority hotspot health zones in South Kivu, the epicentre of the 1b mpox outbreak). Therefore, the performance against the output indicators detailed below indicate that the programme is on track to deliver against the impact objective of reducing risks to national, regional and global health security.

A key outcome envisaged by the TOC is that the government-led response is able to respond proportionately and effectively to health emergencies. The activation of SHER has enabled FCDO to play an important role in supporting the GoDRC in the mpox outbreak. FCDO has been clear throughout, through public communications and policy engagement in country, that the response must be led by GoDRC. The British Embassy Kinshasa (BEK)’s engagement in country on the mpox response has seen the development of a collaborative partnership with the Public Health Emergency Operations Centre (PHEOC) and the Ministry of Health, and with other key donors - particularly the US. BEK’s Health Security Adviser has participated in the National Mpox Strategy review and weekly meetings with the Ministry of Health, where donors and partners coordinate with GoDRC to shape the response and engage on critical policies imperative for effective response. BEK’s Humanitarian, Peace and Stability Team have also been engaged in the response, to reinforce messages through humanitarian coordination mechanisms where relevant, and ensure a joined-up UK approach.

FCDO has ensured that all activity programmed through its implementing partners is designed in concert with and then validated by the DRC’s PHEOC, which is a relatively new function of the Ministry of Health and is managing its first significant outbreak in DRC. Through this, the intention is to strengthen domestic institutions, leadership and response capacity for disease control and emergency response.

After USAID, FCDO is the second largest bilateral donor of financial support to DRC’s mpox response. BEK has worked closely with USAID to ensure that contributions are non-duplicative and targeted at the unfunded priority response areas, to maximise our collective impact.

Since the announcement of the Public Health Emergency of International Concern (PHEIC) by WHO, GoDRC has announced the allocation of US$10m to mpox response. In the year ahead, through ongoing engagements with GoDRC. FCDO will continue to advocate for more domestic financing of response to enhance the autonomy and leadership of the PHEOC to respond to the outbreak.

Once the acute phased of mpox response is over, greater consideration should be given towards how FCDO can support preparedness for future disease outbreaks to achieve greater, sustainable impact at lower cost.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

Based on the analysis in this Annual Review and the continued PHEIC for mpox, this programme should continue. The importance of SHER as an effective vehicle for health security has been also demonstrated by the outbreak of Marburg this year in neighbouring Rwanda. Had there been confirmation of community transmission in Western Rwanda, close to the DRC border, SHER could have enabled rapid, early and effective response in Eastern DRC in anticipation of, or in reaction to, confirmed cases. Moreover, bolstering African national and regional capabilities to safeguard health security is critical to protecting the world, including the UK, from health threats.

This programme is viable and has allowed the FCDO to respond flexibly and with agility to an emerging infectious disease (clade 1b mpox) ahead of most international donors, supporting an underfunded national response to a PHEIC. It has simultaneously allowed FCDO to address overlapping cholera outbreaks. The programme activities are performing well in a highly difficult context

Looking at the wider portfolio, SHER has been able to build on previous support to cholera outbreaks by the UK in DRC. SHER is complementary to BEK’s £114m humanitarian programme in the East of DRC which includes the provision of improved water and sanitation, helping affected communities to protect themselves from disease. SHER is therefore judged to be an effective standalone programme that should continue.

## C. DETAILED OUTPUT SCORING

Output Title	Through UNICEF, reduce the morbidity and mortality related to mpox and cholera in affected communities in targeted provinces (Sankuru, South Ubangi, South Kivu for mpox; North and South Kivu for cholera)
Output number:		1	Output Score:	A
Impact weighting (%):		90%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
1.1 Mpox surveillance/ Community based surveillance: / Percentage of suspected case alerts reported by RECO, investigated and referred for management in the appropriate structures	100%	Achieved. All alerts (1,422/1,422) reported by the communities were investigated to be validated by the care providers and then referred.
1.2 Mpox medical care / Number of Mpox treatment centres (MTCs) set up and functional in the 10 targeted HZs	10	Moderately exceeded. 11 have been set-up in the review period. / The Treatment Centres are in 7 Health Zones and have 412 beds. There are 4 in Miti-Murhesa, 2 in Nyangezi, 1 in Kitutu, 1 in KimbiLulenge, 1 in Kadutu, 1 in Walungu and 1 in Kalehe. The Shabunda HZ does not yet have Mpox TCs due to difficult accessibility conditions.
1.3 Mpox patient food and nutritional support / Percentage of targeted mpox patients, children separated from their mothers or orphans, and their companions, who received food support	100%	Exceeded. 3,610 mpox patients received food support against target of 3,489; 103% of target achieved.
1.4 Mpox risk communication and community engagement. / Percentage of targeted Community Action Committees (CACs) strengthened and involved in household home visits and Mpox awareness.	100%	Moderately not achieved, but likely to achieve by March 2025. 59.5% (1,115 /1,872) CACs trained benefited from monthly operating support. Due to higher-than-expected cost of activities, the others do not benefit from it. However, the planned activities that the CACs are being carried out as programmed. / People were reached through different communication strategies such as community engagement and face-to-face communication (home visits, community dialogues, focus groups etc.), communication media and public displays, media and influencers. / This was done through CAC members, local leaders and influencers.
1.5 Safeguarding / Percentage of planned number of women, girls and boys benefiting from risk mitigation, prevention and/or response to gender-based violence interventions	100%	Moderately not achieved, but likely to achieve by March 2025. 43% achieved (902 women, girls and boys) were reached with information on available GBV and Child Protection services in their areas as well as information on how to access them. / In addition, nearly 5,800 children, family members of those affected, and at-risk community members participated in community-based activities. These activities included group discussions and awareness-raising sessions organised by para-social workers, psychologists, and psychosocial support assistants. The focus was on addressing concerns related to the disease, discussing strategies for de-stigmatisation, coping with stress and fear, and preventing and responding to violence.
1.6 Mpox coordination and monitoring / Number of health zones that have established their local response coordination	100%	Achieved. Support was provided from the national level for this coordination in the 10 HZs in this programme (Miti-Murhesa, Ibanda, Kadutu, Nyangezi, Uvira, Walungu, Kalehe, Shabunda, Kimbi-Lulenge et Kitutu) with various committees established.
1.7 Cholera: Targeted rapid response to suspected cases using the CATI (Case Area Targeted Interventions) approach to break the chain of transmission.	95% of responses within 48 hours.	Exceeded. 99.7% of responses were carried out within 48 hours after notification of the suspected case. The responses have included awareness sessions amongst 206,553 persons, 4,131 households received household water treatment items, 475 cholera kits were distributed, and 21,538 houses were disinfected.
1.8 IPC/WASH for mpox and cholera in affected areas. / PCI/WASH activities established in 10 Mpox Treatment Centres	10	Moderately not achieved, but likely to achieve by March 2025. IPC/WASH activities have been fully implemented in 9 Mpox Treatment Centres (of the originally planned 10). 7 other at-risk health facilities in the targeted health zones have also been provided with WASH materials, and 300 health care providers have been equipped with IPC/WASH. / Oral Rehydration Points for cholera have also been established in 19 priority locations in North and South Kivu.

Briefly describe the output’s activities and provide supporting narrative for the score.

It is worth noting that these output indicator milestones cover the expected deliverables through UNICEF between August 2024 and March 2025. As such, the gap between the target and progress to date are in some cases explicable by the fact that there are 4 months left in the reporting period for the target to be achieved. UNICEF and their downstream partners have been able to, with FCDO support, respond to an increase in mpox patients, compared to what had been originally been anticipated – their ability to meet the increased demand has contributed to their achievement or exceeding of milestones in some areas.

It is also worth noting that UNICEF report to FCDO on a broader set of indicators than the above, but the milestones above are chosen as lead indicators to report performance against each thematic area.

This output covers the full range of activities delivered by UNICEF to date on mpox and cholera outbreaks. This includes outbreak mpox coordination, community-based surveillance, medical care and nutritional support, WASH and infection prevention and control, psychosocial support, Risk Communication and Community Engagement, and cholera Case Area Targeted Interventions (CATI). Some highlights so far, in addition to the indicator activities described above, include:

- The coordination of the Mpox response in South Kivu is now functional (with the different pillars) and 100 per cent of the weekly meetings held. The meetings are occasionally chaired by the provincial Minister of Health.
- UNICEF’s partner REMED delivered training to community outreach units (CACs) to reinforce their capacity, so that they can increase awareness raising in households/the communities, and the identification of mpox alerts and reporting them.
- UNICEF has been able to support provincial authorities’ training of healthcare workers, and UNICEF report that more than 90 per cent of cases admitted to Mpox Treatment Centres have been cured.
- Over 1.5million people have been reached so far with risk communications (via media campaigns, face-to-face outreach, community awareness raising, etc.) on mpox and over 200,000 have been reached by awareness campaigns for cholera. Communications activities for mpox have been linked with ongoing vaccination campaign outreach. Messages on the prevention of sexual exploitation and abuse have been integrated.
- FCDO funds are being used for all of the CATI responses taking place in North and South Kivu during the review period. This activity is being conducted in partnership with “Croix Rouge NK (CRNK)” in North Kivu, involving 18 CATI teams, and the Croix Rouge Sud Kivu (CRSK) in the southern axe of South Kivu involving seven CATI teams.

While progress to date has been strong, it is worth highlighting that the project was initially delayed slightly, with activities originally planned to commence in July but activities not beginning until August. This was primarily due to the need for all response activities to be aligned across partners and with the Government of DRCs Public Health Emergency Operations Centre (PHEOC), and some delay in finalising agreements with downstream partners in South Kivu. FCDO at the time fed back to UNICEF that proactive communications about these kinds of delays were essential and communications have since improved.

The key aims for the coming months of the UNICEF component will be to ensure that the milestones for Safeguarding, IPC/WASH and RCCE are achieved while continuing to manage the larger than expected number of mpox patients. As outlined in the recommendations below, it is also critical that emerging evidence regarding the importance of nutritional support for isolating patients needs to be appropriately incorporated into the planned activities in the rest of the programme.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

This is a new output following the activation of SHER in May 2024. In the coming year, with the further scaling up activities through UNICEF and WHO, a full revision to the SHER logframe will be conducted.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

This is the first AR completed for SHER. The following lessons learned and recommendations are made for the year ahead:

Lessons learned

- The multisectoral response requires good coordination and complementarity between different actors. For example, there is a need to coordinate with partners in the education sector for the effectiveness of actions carried out in schools, which will be important to land as we look to implement IPC/WASH activities in schools following school strikes at the start of the programme.
- UNICEF has identified some learning already which can improve their ability (and the sector’s) to respond and achieve success in patient management. For example: dietary support for Mpox patients reduces the dropout rate and improves response to treatment; food support helps contain the epidemic by limiting the contact of patients and caregivers with the community; and a human-centred design approach in the identification of causes and solutions related to the spread of mpox produces better results.
- For CATI interventions for cholera, access remains one of the inhibiting factors in several areas. In South Kivu, most cases are in areas that are very difficult to access, for security and/or logistical reasons. One mitigating measure is the training of ‘Pre-CATI’ teams, consisting of small teams of people originating from remote areas, who remain on standby until suspected cases are declared.

Recommendations

- FCDO to work with UNICEF on ensuring that nutrition support is offered to all patients in UNICEF facilities supported by FCDO in mpox response.
- UNICEF to support the improvement of the coordination of the response by establishing provincial meetings for the food and nutrition support pillar.
- UNICEF to strengthen IPC/WASH actions in currently underserved communities including schools and health facilities at risk.
- UNICEF to scale up the training of Pre-CATI teams to strengthen readiness and response, especially in hard-to-reach areas.
- FCDO to consider options for longer term capacity building and system strengthening, to build on gains made and to support sustainable interventions for the post-epidemic health system in the most affected health zones.

Output Title	Establish additional mpox response support via WHO
Output number:		2	Output Score:	A
Impact weighting (%):		10%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
Establish additional mpox response support via WHO	FCDO to finalise agreement with WHO for additional mpox response support activities by November 2024.	Achieved. The British Embassy Kinshasa has conducted a full proposal review, due diligence assessment and established a Contribution Arrangement with the WHO DRC Country Office as of 22 November 2024.

Briefly describe the output’s activities and provide supporting narrative for the score.

This is a basic process output indicator, to capture a second key area of activity in the reporting period. Following the announcement of the mpox PHEIC in mid-August 2024, WHO rapidly scaled up its global, regional and national response plans and called for additional resources to support their implementation. The British Embassy Kinshasa had Official Development Assistance (ODA) available to support the response and, once the WHO’s strategic response plan was finalised, was able to work with the WHO DRC Country Office to agree a project proposal. The Contribution Arrangement has been finalised in November 2024.

The new £4.4m of planned funding for WHO DRC will support the mpox response, covering the Government of DRC’s national response pillars (surveillance, laboratories, case management, IPC/WASH etc.) in 14 Health Zones in 3 Provinces: North Kivu, South Kivu and Kinshasa. IOM are a key implementing partner covering work with Internally Displaced People) (IDP) and at Points of Entry in North Kivu.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

This is a new output area. As a process indicator which has been achieved, the planned work through WHO will be integrated into a fully updated logframe for the coming year.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

A full due diligence assessment of the WHO DRC Country Office was conducted before the British Embassy Kinshasa signed the Contribution Arrangement. This was in part due to historical issues weaknesses in the prevention and response to sexual exploitation and abuse during the 10th Ebola outbreak response in DRC. For the year ahead, close attention must continue to be paid to safeguarding across all SHER-supported activities, including by WHO.
## D: VALUE FOR MONEY

Key cost drivers and performance

The primary driver of costs to date has been transfers to implementing partners for mpox response £450,000 and cholera response £680,000. WASH activities £150,000, community outreach £235,000, child protection £100,000 and nutritional support £130,000, represent other large drivers of total expenditure to date of £2.2 million through UNICEF.

As noted in the business case, operating in fragile and conflict affected areas, such as those found in Eastern DRC is also a significant driver of costs.

VfM performance compared to the original VfM proposition in the business case

The business case for this programme notes that responding to outbreaks is more costly than investing in prevention and early detection. Investments in preparedness that mitigate or avert the impacts of disease outbreaks on lives, livelihoods, health system resilience and economies are considered by the World Bank to offer an extraordinarily high potential return on investment. The business case also notes that VfM is driven through allowing the embassy to respond at pace and through the selection of partners which operate in the support of existing health systems. This thinking has underlined our choice of partners in country.
[note] Financing Pandemic Preparedness at a National Level, International Working Group on Financing Preparedness

The interventions chosen with UNICEF and WHO are as outlined in the business case:
- effective – based on robust evidence of public health approach that minimises disease transmission
- economical – those which require relatively inexpensive commodities
- efficient – delivered through localised implementing partners and downstream partners
- equitable – prioritise the mobilisation of entire affected communities and vulnerable groups.
A fuller VfM analysis of the SHER interventions via UNICEF and WHO over the coming year is necessary and should be reviewed in the next Annual Review.

Assessment of whether the programme continues to represent value for money

This programme represents good value for money as a response vehicle to mitigate the impacts of outbreaks of high-consequence infectious disease. More consideration should be given however to future investments in preparedness to reduce the incidence or shorten the outbreak extent and length of emerging infectious diseases, which represent more cost-effective interventions.

E: RISK

Overview of risk management

The overall risk remains Major, which is within FCDO DRC’s risk appetite. The DRC context remains particularly challenging, particularly in eastern DRC with the ongoing conflict and insecurity. UNICEF, the implementing partner in the first year of the programme, has capacity and experience in working in conflict-affected areas and humanitarian settings. They have strong security protocols and logistics capability, as well as strategic engagement and lobbying with government, civil society and community in the response to the mpox outbreak. There was no interruption of response due to conflict as UNICEF has an early warning system used to evaluate situations and work with key stakeholders for a humanitarian access to beneficiaries.

The safeguarding context is difficult in DRC and a major risk for the programme. Both implementing partners, UNICEF and WHO (implementer in the second year of the programme), have systematic approaches to address any risk related to sexual exploitation and abuse, gender issues, and gender-based violence. They focus on raising awareness, improving reporting mechanisms, providing rapid responses, and assisting survivors. Training is also provided to staff, partners, and community leaders on prevention and reporting protocols. FCDO has conducted country level due diligence assessments for both multilaterals, with a particular focus on safeguarding and was satisfied with the mitigation measures to prevent risks and respond to potential issues.

A full risk register has been agreed between UNICEF and FCDO covering the initial £3.1m of activities initiated in August. This is being reviewed to ensure that any necessary adaptations stemming from the new activities initiated by the £1.5m uplift in funding are reflected in the updated programme risk register. A risk register covering the WHO activities is being developed and all these products will be consolidated into a single programme-wide risk register for the SHER programme.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

The SHER programme had been dormant until mid-2024, with a Contribution Arrangement with UNICEF signed in August 2024. Despite some initial delays, UNICEF’s management of mpox and cholera response seems well planned and organised. UNICEF received £1.9 million as the first instalment of the total initial funding of £3.1 million at the signature of the MoU, of which 88% has been spent to date. UNICEF has submitted a quality mid-term report and a financial donor statement report for the first three months of implementation. The agreement with UNICEF has since been uplifted by an additional £1.5 million, bringing total support under this programme to £4.6 million.

A Contribution Arrangement with WHO has been agreed in November 2024 for an additional £4.4 million response to mpox outbreak with activities currently due to be delivered by the end of March 2025.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation

A complete logframe has not yet been developed since SHER was activated this year, nor is there a template logframe to draw on (the business case refers to a template logframe being developed at the inception point for the programme, but this was not completed). Therefore, two simple output indicators were established for this reporting year and a full logframe will be prioritised for the second reporting year (from Nov 2024). This logframe will draw together all elements of the multiple elements of the programme.

Since the activities were initiated with UNICEF in August the Senior Responsible Owner (SRO) has made two programme visits to oversee the initiation and rollout of activities in 2 of the 4 provinces involved in the initial programme with UNICEF: North and South Kivu. These visits took place in August and November, and both involved 5 days of observations, with August’s visit more targeted towards South Kivu and November’s more targeted towards North Kivu, although both provinces were visited in each visit. These visits have directly informed programming decisions.

In August, in visits to health clinics and displacement sites and in discussions with health care workers in North Kivu, the SHER SRO surfaced multiple incidences of mpox patients being treated in Cholera Treatment Centres often alongside patients with active cholera infections. This informed a decision to allocate over £1m of the £1.5m uplift for UNICEF towards mpox response in North Kivu specifically.

From August to October weekly sessions were held between UNICEF, USAID and FCDO covering the totality of UNICEF’s interventions for mpox. As of November, a decision was taken to have a more in-depth monthly meetings focusing on just FCDO-funded activities, in line with data collation timelines in UNICEF.

There is not currently an external Third-Party Monitor covering SHER, but the British Embassy Kinshasa are assessing options for a mechanism like this to support results verification and ongoing risk monitoring.

Evidence

The interventions being delivered through UNICEF and WHO are based on best-practice, evidence and medical protocols for cholera and mpox response and are aligned with the Government of DRCs national response plans. FCDO will ensure that ongoing changes in the data and emerging evidence into cholera and mpox responses and best practice feed into any necessary adaptations for delivery.

For the next review the intention is to have data delineated at the provincial level, to disaggregate between Sankuru, South Ubangi, North and South Kivu. It is also the intention to ensure that provincial level data is derived from WHO activities. Having disaggregated data is FCDO best practice and will inform more accurate mpox and cholera responses in DRC.

Learning

The main vehicle for sharing lessons from SHER so far has been with the FCDO health cadre and in particular the Africa Health Advisors group. There are plans for a wider lesson learned exercise into FCDO’s responses to outbreaks in the region, a range of recent outbreaks in Africa, including multiple outbreaks of cholera, regional outbreaks of 1a and 1b mpox and the outbreak of Marburg in Rwanda. British Embassy in Kinshasa will feed experiences from outbreak response to cholera and mpox into this exercise.

Date of last narrative financial report	5 November 2024	Date of last audited annual statement	n/a