## Annual Review Template

Title: Building Debt Management Capacity in Low-Income Countries
Programme Value £ (full life): 5,000,000		Review date: 13/01/2021
Programme Code: 300861	AMP start date: 01/02/2020	AMP end date: / 01/02/2026

Summary of Programme Performance
Year	2021	2022
Overall Output Score	B	A
Risk Rating	Minor	Minor

DevTracker Link to Business Case:
DevTracker Link to results framework:

A. SUMMARY AND OVERVIEW

Description of programme

The “Building Debt Management Capacity in Low-Income Countries” project works through international experts to provide high-quality technical advice and support to developing countries to boost their debt management capacity, tackle debt vulnerabilities and engage with their creditors. Initially the programme worked solely on debt management capacity building through the IMF/World Bank Debt Management Facility (DMF). Following the onset of the Covid-19 pandemic and the increase in debt vulnerabilities which this contributed to, this project added a component working with the African Legal Support Facility (ALSF). ALSF specialises in supporting African countries to engage with their creditors on a level playing field, providing expert legal and financial advice and advisers.

Summary supporting narrative for the overall score in this review

Over 2021, Building Debt Management Capacity in Low-Income Countries adapted delivery as best it could to cope with the problems posed by COVID-19. The programme delivers technical assistance (TA) in response to demand from countries across a wide geographical range. Travel restrictions, local lockdown rules and quarantine requirements have severely impacted the two programmes’ ability to deliver. The DMF has adapted its training and TA to a virtual setting - constructing online courses, shared virtual learning forums and online peer to peer lesson sharing. There has been a concerted effort to replicate in-person training and TA using online platforms. Training, such as on how to conduct a debt management performance assessment, have been piloted and refined as an online course and are now being delivered. The ALSF has also strongly developed its online training and knowledge sharing – in 2021 ALSF held three seminars on debt management and produced over twenty knowledge sharing products. However, not all of the products and services that the two programmes provide adopt well to virtual delivery and this has constrained the programmes as well as the diversion of effort into developing online delivery.

Despite the best efforts of the teams to adapt the programme to the new realities of COVID, delivery has remained below expectations. The project overall did not meet targets for four of the seven indicators. A likely reason for this is that the programmes are demand-driven. Both ALSF and DMF can only respond to requests from country governments for assistance. Beneficiaries may value in-person assistance more than online training, resulting in lower than expected demand. General IT and connectivity issues have also contributed to lower demand. DMF over the year invested time and resources into creating new digital products. It has taken time to pilot and develop these products but now many are ready for virtual delivery – subject to demand. Some potential easing of travel restrictions will hopefully also allow for greater delivery in 2022 in a return to in-person TA, but this is very uncertain.

Major lessons and recommendations for the year ahead

A critical lesson from 2021 (building on 2020) has been in how to adapt in-person assistance to virtual delivery. DMF has worked hard to adjust, where possible, its training to online. This has been done through an iterative and adaptive process, including piloting and integrating users’ and providers’ feedback. Despite the progress on virtual products and delivery methods, demand has been lower than hoped. Users seem to continue to value in-person technical assistance over virtual, and IT connectivity issues dampen the uptake of training offers.

The key recommendations for the year ahead are
1. To track and monitor the implementation of the new virtual assistance programmes from DMF.
2. Mitigate as much as is possible the impacts of further travel restrictions on the delivery and effectiveness of the programme.
3. To further ensure coordination between the work done by the ALSF and DMF so that they form one cohesive and complementary offer to partner governments.
4. For the FCDO to ensure that relevant Posts and country teams are aware of ALSF and DMF so that they can promote them to contacts and counterparts in national host authorities.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case. [1/2 page]

The DMF and ALSF will reduce debt vulnerabilities in low-income countries by improving conditions in five causal pathways; governance and institutions, improved strategy and policy, developed debt markets and debt crisis management. By enhancing various debt institutions' legal framework and roles and responsibilities, low-income countries will be better equipped to deal with debt management. To complement this, a coherent debt management strategy will allow debt intuitions to work together in sustainable debt management. Improved transparency will allow for a sound and cohesive fiscal policy. Improving domestic debt will provide the government with another tool to raise debt sensibly and sustainably. Improved debt crises management will allow countries to engage effectively with creditors to find quick and best solutions to problems.

Several exogenous factors can prevent the Theory of Change (ToC) from being implemented. Political will is listed in the ToC as a risk. This refers to situations where incentives for key actors are aligned with increasing the debt burden unsustainable. The FDCO's wider engagement in-country and other interventions mitigate this scenario. A second critical risk is a worsening of global economic factors. This includes commodity price crashes, global economic recessions and further covid restrictions causing severe economic harm. These factors are beyond the control of this or other interventions. The work done by the ALSF and DMF will equip countries to manage better and navigate these crises if they occur.

A critical risk to the programme is from the Activities to Outputs stage. Both ALSF and DMF are demand-driven – while they can advertise and encourage uptake, they have to be asked to help by partner country governments. This reflects that cooperation and ownership are essential ingredients in the impact and success of both TA and training in improving debt management capabilities. FCDO will support the advertising and demand-generation of the programmes themselves by seeking to promote use of ALSF and DMF through its Posts and country teams. Any easing of covid restrictions in 2022 will likely boost demand for services but both programmes need to plan for both a hybrid of in-person and online, and fully virtual delivery.

Describe where the programme is on/off-track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

At this stage in the programme's life, it is expected to deliver on outcomes to some extent. DMF is slightly behind revised logframe targets. This has been primarily due to adapting its services to virtual delivery and reduced demand. Adapting to online delivery has been labour intensive and challenging; each intervention or training has had to be assessed to understand which component can be translated to a virtual setting, what has to be removed and several new additions built that are suitable for online provision. Several critical training programmes have been piloted in 2021 and are now underway. It is hoped that this will allow for effective delivery in 2022.

The ALSF is a well-established and valued institution that delivers quality legal service to recipients. There is a low risk to overall under-delivery due to the strong reputation and impartiality of the institution. The key objective for the FCDOs contribution is to encourage the ALSF to work more on debt-related issues.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

The programme is behind on several outputs in this annual review. There has been a longer than expected adjustment to working under the constraints and restrictions of COVID. However, significant work has been done and most virtual training is now ready to roll out where possible. In 2022 risks to delivery remain in particular from COVID restrictions reducing the expected demand for services and assistance. Both ALSF and DMF have strong reputations and are well placed to deliver. Debt will become an even more critical issue over the next year. With rising debt levels in low income and middle-income countries, the need for support and assistance on debt-related topics are likely to continue to rise. Given the rising need and higher probability of debt crises, this programme providing debt capacity support will generate greater returns and represent stronger value for money.

## C. DETAILED OUTPUT SCORING

Output Title	DMF TA missions, trainings and knowledge products are taking place and being developed in priority areas relating to debt transparency and governance
Output number:		1	Output Score:	B
Impact weighting (%):		30	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review (for 6 months)	Progress
Output 1.1 TA missions and trainings to boost debt transparency (includes debt reporting and monitoring, debt-related contingent liabilities, DSA)	Target: 13	Slightly missed: delivered 11
Output 1.2 TA missions and trainings under Improving Governance & Institutions (includes DEMPA, Debt Reform Plan and Institutional set up)	Target: 14	Missed: delivered 8

Briefly describe the output's activities, and provide supporting narrative for the score.

Overall progress on Output 1.1 is below target. This annual review's target has been revised from 19 to 13 due to covid impacts. However, the revised target has also been missed, initiating 11 training missions. As above, demand seems to be dampened by recipients preferring in-person elements of the assistance; many may have postponed support in the hope of getting it in-person later.

Progress has however been made on TA for debt transparency. Building on the Debt Management Performance Assessment, a Debt Transparency tool has been constructed. The tool identifies the reason reporting standards are lacking and identifies actions to improve reporting. The tool was piloted in Armenia by the World Bank this year and has had two follow up runs in Sierra Leone and the DRC.

Output 1.2 fell short of the 2021 milestone of 14 missions, achieving only eight missions. Work under this output is still managing the transition to a primarily virtual forum. The methodology for the DMF’s key tool the Debt Management Performance Assessment (DeMPA) was reviewed and has been revised. The DeMPA training is a now in a virtual peer-to-peer format designed to work effectively under the challenges posed by COVID. The revised DeMP methodology was piloted in Honduras and then rolled out in two TA sessions for Somalia and Kenya. The DMF also delivered several other virtual training sessions. This included a session with an auditor, training on subnational debt performance assessment and a facilitated online course.

The DMF introduced new TA streams on the debt management legal framework, which were delivered (Georgia) as well as on institutional frameworks (Vietnam and Nepal)

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

This output has delivered below target for a second year running. However, the DMF has just completed the adaptation of its training to an online forum. As explained above, the training in the DeMPA has been piloted and implemented during 2021, which will hopefully enable a higher volume of delivery in 2022.

Describe any changes to this output during the past year, and any planned changes resulting from this review.

Output 1.1 was revised down from 19 to 13, and Output 1.2 was revised down from 16 to 14. The reasons for this were the adaptation to COVID and adapting the interventions to a virtual setting. COVID has had a significant effect on the DMF’s ability to deliver through travelling in-region and internationally to provide expert TA and training. The DMF has agreed grant arrangements with five implementing partners (IP) with expertise in debt management. No disbursements have been made in this AR period, but all agreements have been finalised with delivery expected to begin in 2022. Two of the IPs, have a large global coverage. Three of the IPs are regional and based in their respective developing regions. The use of regionally-based partners will might slightly reduce the difficulties that COVID places on access and travel, as well as providing well-tailored and region-specific support. The DMF has established a coordination and lesson sharing forum between all IP to improve results and delivery.
[note] the DMFAS – United Nations Conference on Trade and Development (UNCTAD) and the Development Finance International Group - Debt Relief International (DRI).
[note] Macroeconomic and Financial Management Institute of Eastern and Southern Africa (MEFMI), West African Institute for Financial and Economic Management (WAIFEM) & Agence UMOA-Titres (AUT)

Progress on recommendations from the previous AR, lessons learned this year and recommendations for the year ahead

There were no substantive recommendations related to this output from the previous annual review.

Lesson Learned: The DMF remains a relevant programme fulfilling a useful output and addressing a key constraint in debt management and development planning. Addressing capacity constraints is a process that takes time to embed institutionally but will provide a lasting and sustainable impact once achieved. The activities of the DMF have remained relevant in the context of rising debt issues amongst low-income countries.

Recommendation: For the DMF to continue developing its portfolio of virtual interventions but remain active in assessing opportunities for in person interventions. Once the grants have been disbursed to the regional implementing partners the DMF should explore opportunities to use their expertise and staff to maximise in-person training opportunities.

Output Title	DMF TA missions, trainings and knowledge products are taking place and being developed in priority areas relating to strategy and domestic debt
Output number:		2	Output Score:	A
Impact weighting (%):		30	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review (for 6 months)	Progress
Output 2.1 TA missions and trainings under Enhancing Strategy and Policy (Includes MTDS design, MTDS implementation, and cash management)	Target: 13	Exceeded: / Delivered 15
Output 2.2 TA missions and trainings to develop domestic and international debt markets	Target: 10	Missed: delivered 7

Briefly describe the output’s activities, and provide supporting narrative for the score.
Output 2.1 exceeded its target of 13 by delivering 15 TA missions. There was a relatively high demand for support on medium-term debt strategies (MTDS) and on cash management. A MTDS TA mission to Cameroon supports implementing an annual borrowing plan focused on the design of debt management strategy and touched upon how to manage Treasury bill issuance including the introduction of FX indexation.
Under output 2.2 seven missions were delivered against a target of 10. DMF has made considerable progress in domestic and international debt markets this year despite the slight underperformance. A mission to the DRC assisted in managing Treasury bill issuances, including the introduction of FX indexation. In Cambodia, technical advisory provided to design Policy Framework on Development of Government Securities is a critical step for the country in creating a medium-term approach to this. The IMF released a guidance note on developing local government currency bond markets. The note focuses on addressing key bottlenecks and barriers and delivering currency markets resilient to shocks that can provide multiple economic benefits. Future DMF TA in this area will follow the principles from this note.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

This continues to represent good value for money. This TA aims to provide a lasting impact by establishing medium-term strategies and developing local currency debt markets.

Describe any changes to this output during the past year, and any planned changes resulting from this review.

Output 2.1 was revised down from 17 to 13, and output 2.2 was revised down from 11 to 10. This was to reflect the difficulties of implementing TA during COVID restrictions on international travel but was still overly optimistic. It has taken time to adapt the TA and training to online delivery.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

There were no substantive recommendations related to this output from the previous annual review.

Lessons Learned: The lessons learned under output 1 apply to output 2. The DMF will continue to develop its virtual offer while remaining active to the possibilities for in-person assistance.

Recommendation: The development of domestic currency markets has been an active space for the DMF this AR period. With several individual TA missions conducted and concluding the year with a webinar. Next year the DMF should look to assess the sustainability of its efforts in domestic currency markets and the possibility for lesson sharing across countries, as multiple countries venture into the space for the first time.

Output Title	African Legal Support Facility delivers high quality technical advice and generates useful knowledge products
Output number:		3	Output Score:	A
Impact weighting (%):		40	Weighting revised since last AR?	no

Indicator(s)	Milestone(s) for this review (for 6 months)	Progress
Output 3.1 Number of government officials and lawyers trained in sovereign debt management	Target: 8	Narrowly missed: delivered 6
Output 3.2 Number of contracts negotiated by trained lawyers and government negotiators	Target: 3	Met: delivered 3
Output 3.3 Number of knowledge products and/or model agreements and templates related to debt management or negotiation developed	Target: 17	Exceeded: delivered 22

Briefly describe the output's activities and provide supporting narrative for the score.

The UK's support to the ALSF has a primary objective of providing support and building capacity for countries dealing with debt issues. The ALSF achieves this by providing free legal support to countries. The ALSF is demand-driven, so it can only respond to requests from countries. Over the last year, debt issues represented 9% of the ALSF’s operations.

Output 3.1 was slightly missed, with six government officials and lawyers trained in sovereign debt management. Demand is expected to rise in 2022 as debt issues are expected to become more prominent. In anticipation of this, the ALSF recruited six (6) new legal counsels and a Senior Finance and Budget Officer to ensure practical project and financial management to strengthen ALSF's performance further.

The Government of The Gambia sought capacity-building assistance from the ALSF concerning (i) negotiations with The Gambia's creditors to obtain debt relief and (ii) development of a prudent and sustainable restructuring strategy, in each case to assist it in meeting a precondition to an IMF financing programme. ALSF's assistance resulted in confirmation from creditors of their commitment to restructuring The Gambia's debt and to the extent possible restructuring agreements and similar arrangements between the Government and its creditors.

In 2021, ALSF delivered knowledge products and learning events under output 3.3. ALSF intensified its support to African countries, including providing immediate and short-term solutions such as emergency review of contracts, financing arrangements and restructuring options, review of debt relief programmes, debt sustainability and communications strategies, negotiations and restructuring of various agreements and transactions; and long-term solutions such as institutional capacity building, training programmes, and relevant systems and toolkits.

The ALSF provided information on debt transactions and sovereign debt negotiations to more than 300 participants through its flagship e-learning platform - the ALSF Virtual Academy. It held three massive online open training sessions (MOOCs) on debt with a combined total of 745 participants.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

This is the first year the ALSF contribution has been included in the annual review. The initial delivery has been good. The ALSF has an established reputation for impartial solid legal support. Output 3 represents good vfm.

Describe any changes to this output during the past year, and any planned changes resulting from this review.

This is the first year this output has been included in the annual review. We do not recommend any specific changes as a result of this review.

Progress on recommendations from the previous AR, lessons learned this year and recommendations for the year ahead

This component was not reviewed in the previous annual review as it was too new.

Lesson Learnt: Client and donor countries continue to look to the ALSF as a reliable and impartial provider of legal advice.

Recommendation: The ALSF has a moderate level of requests for work on debt specific issues. It is expected that demand for these services will increase over the next year so ALSF should ensure that it is prepared to deal with higher levels of requests. The FCDO team should advertise ALSF’s services to the FCDO country network and encourage them to share with partners in country where relevant.

D: RISK

Overview of risk management

The Business Case assessed that DMF had low fiduciary, safeguarding and reputational risks due to its reliance on strong IMF/World Bank systems. Operational risks were also assessed as low given that the DMF Secretariat is well established with strong experience. These assessments remain accurate despite the changing circumstances. The DMF has an Implementing Partners Council which provides a forum for regular engagement with DMF partners and an opportunity to share learnings, including about how to manage risk.

The Business Case identified external context and delivery risks as the most serious for the DMF. This remains true with in particular the Covid-19 pandemic. The pandemic has triggered a significant increase in debt vulnerabilities across DMF’s countries of operation. This has altered the demand for DMF support, with planned programmes in areas such as Medium-Term Debt Management Strategy Development being delayed or cancelled. The pandemic has also affected the ability of DMF staff to travel. The impact of this on the overall delivery of DMF projects is twofold:

Firstly, there has been a reduction in the number of missions and trainings which have been delivered in 2021. DMF has responded by adapting its offer in terms of content, introducing a new framework for crisis response, and in terms of delivery, moving an increasing number of trainings online. The relative effectiveness of this delivery approach will be closely monitored in client feedback.

The shift to trainings online have made it easier for DMF staff based in Washington DC to oversee and monitor delivery. This limits any increase in the risks of aid diversion or safeguarding breaches as a result of DMF staff’s inability to travel.

The Building Debt Management Capacity in Low-Income Countries project remains low risk.

Current level of fiduciary risk and direction of travel since last ASP	Minor/ Stable
Specific assessment of corruption risk and direction of travel since last ASP	Minor / Stable
Is a full FRA update required?	No

E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including consideration of VfM measures of economy and efficiency.

The two programmes are discussed in turn.

DMF: DMF’s overall programme budget was revised down in January 2021 by approximately USD 2m. This was to reflect the pause on staff travel and resulting savings. Overall DMF utilisation rates are 61%, broadly in line with DMF 11 utilisation rates.

Disbursements for FY21 totalled USD 4.6 million, with 43% on TA and 42% on knowledge management. Within TA, activities that supported enhancing strategy and policy constituted 37% of TA expenditures, followed by 29% on boosting debt transparency TA, then developing debt markets TA (18%), and improving governance and institutions TA (17%).

Programme Administration costs in FY21 amounted to USD 373,109 which was slightly above the budget of USD 320,000 due to the one-off cost of producing the DMF II multidonor Trust Fund Closure Report. This budget also covered the processing and setup of new grant agreements with five implementing partners under DMF III with new features. Support to Grant Agreements alone amounted to 29% of Programme Administration expenditure.

Seventy percent of project-related spending was on staff costs, followed by 21% on consultant fees (for delivery of TA and training). Under the previous phase of DMT, pre-covid, around one-fifth of spending was on travel and in-person visits; we anticipate a return to this when conditions allow.

ALSF: The total 2021 budget for the ALSF was USD 27m. The majority was planned to finance advisory services and the UK contribution of £0.5m in 2021 was part of this. The subset of project-related funding disbursements at end-September (the last financial report) was just over USD 5m. Most of this was to finance ALSF advisory services, which is its key focus, while capacity building accounted for USD 0.7m of the spending.

The overall Value for Money of the project remains strong, as per the business case

Date of last narrative financial report	DMF: / September 2021 / ALSF: / September 2021	Date of last audited annual statement	DMF: September 2021 / ASLF: June 2021