## Template
Please refer to the Guidance Notes tab for advice on completing the various fields in the logframe.
Please refer to the Results Framework Prof Guide for broader information on the logframe approach
PROJECT TITLE :Ghana Governance Programme (GGP)
IMPACT | Impact Indicator 1 |  | Baseline (2022) | Milestone 1 (May 25) | Milestone 2 (May 26) | Milestone 3 (May 27) | Milestone 4(May 28) | Milestone (May 29) | Target (May 25- 29)
Effective governance system that is transparent and accountable and protects civil and political rights. | Extent of and satisfaction with democracy (%) | Planned | 43 |  | 50 |  | 55 |  | 60
Achieved
Source : Afrobarometer Survey/ Corruption Perception Index 2023
| Impact Indicator 2 |  | Baseline (2023) | Milestone 1 (April 25) | Milestone 2 (April 26) | Milestone 3 (April 27) | Milestone 4(April 28) | Milestone(April 29) | Target (April 29)
| Ghana score on Corruption Perception Index Score (xx/100) | Planned | 47 | 49 | 51 | 53 | 55 | 57 | 57
Achieved
Source : 2022 /Afrobarometer
OUTCOME 1 | Outcome Indicator 1 |  | Baseline (2021) | Milestone 1 (May 25) | Milestone 2 (April 26) | Milestone 3 (April 27) | Milestone 4(April 28) | Milestone (April 29) | Target (April 29) | Assumptions
| Level of influence of CSOs supported by GGP to impact elections in 2024 & 2028. | Planned | CSOs influenced credible elections in 2020 through citizens engagement, election observation and anti-vigilantism initiatives (STAR-Ghana PCR, 2021) | CSOs funded by GGP have influenced credible elections through stakeholder engagement and election observation. | CSOs funded by GGP have successfully influenced stakeholders to agree on electoral reforms based on lessons from 2024 elections. | CSOs actively engaged in electoral reform processes. | Reformed electoral processes being implemented towards improved December 2028 elections with CSOs activeky engaged in the processes. | CSOs have infleunced credible elections in 2028 | CSOs have enhanced capacity and regulalry engaging stakeholders on electoral issues and reforms leading to improved electoral processes and outcomes. | • Peaceful electoral processes before during and after the elections. • Peace transition of power from the outcoming to the incoming government • Political parties and Electoral Commission willing to engage on electoral reforms
Achieved
Reforms and improved practices strengthen elections in 2024 and 2028. |  |  | Source | STAR-Ghana PCR (2021); Partners Reports, Media Reports, Annual Reviews and Programme Completion Reports.
| Outcome Indicator 2 |  | Baseline (2020) | Milestone 1 (April 25) | Milestone 2 (April 26) | Milestone 3 (April 27) | Milestone 4(April 28) | Milestone (April 29) | Target (April 29)
| Level of Electoral Management Bodies capacity and preparedness to conduct the elections. | Planned | The National Peace Council and the National Commission for Civic Education have limited capacity to effectively play their roles to promote credible elections. | EMBs have enhanced capacity and organised credible elections | EMBs agree on areas of electoral reforms based on lessons learnt from 2024 elections. | EMBs implement agreed electoral reforms. | EMBs have enhanced capacity to implement strategies for a credible elections in 2028. | EMBs successfully organise 2024 and 2028 elections with outcome acceptable to most stakeholders. | EMBs successfully organise 2024 and 2028 elections with outcome acceptable to most stakeholders.
Achieved
Source : Surveys conducted during Annual Reviews; Parliamentary Hazards
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | Total (£) | Total (£) |  | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTCOME 2 | Outcome Indicator 1 |  | Baseline (2023) | Milestone 1 (April 25) | Milestone 2 (April 26) | Milestone 3 (April 27) | Milestone 4(April 28) | Milestone (April 29) | Target (April 29) | Assumptions
| Number of CSOs supported by GGP that have able to infleunce reforms and improved practices to strengthen strengthened transparency and accountability | Planned | CDD has developed a model Bill for campaign financing; ACEP has launched the Pledge Against Corruption Campaign and IMANI had engaged political parties to infleunce commitments to reform governance structures. | Two (2) of CSOs supported by GGP have been able to build consensus on their reform agenda or policy proposals to strengthen transparency and accountability. | Two (2) of CSOs funded by GGP have been able to sustain the the buy-in of their stakeholders and one (1) CSO secures the needed support of stakeholders to initiate reforms or introduce policies that strengthens transparency and accountability | All three (3) CSOs funded by GGP are effectivley engaging in processes leading to reform of policies and practices that strengthen transparency and accountability | All three (3) CSOs funded by GGP have made significant progress towards completion of proccesses to reform policies/priactices to strengthen transparency and accountability | All three (3) CSOs have achieved progress to infleunce reforms in policies and practices that strengthen transparency and accountbaility. | All three (3) CSOs have achieved progress to infleunce reforms in policies and practices that strengthen transparency and accountbaility. | • Legal framework remains • No/limited intimidation and self-censorship • Political space remains stable • Political will of Stakeholders (including political parties) to engage with citizen groups/CSOs, in particular marginalised and excluded groups • Citizens, including marginalised and vulnerable groups, have the potential to effect change • CSOs are able to collaborate and work together for collective action. • FCDO ensures effective coordination of the demand and supply sides interventions • Parliament has the appetite (political will) to effectively play its legislative and oversight role
Reforms and improved practices strengthen transparency, accountability and human right and reduce corruption. |  | Achieved
Source : Project proposals of implementing partners; partners reports, Annual Reviews.
| Outcome Indicator 2 |  | Baseline (2023) | Milestone 1 (April 25) | Milestone 2 (April 26) | Milestone 3 (April 27) | Milestone 4(April 28) | Milestone (April 29) | Target (April 29)
| Number of asset recovery cases investigated and successfully prosecuted. | Planned | The OSP has only made one asset recovery in relation to its investigation into Labianca Group of Companies and Customs Division of Ghana Revenue Authority | The scope of ICAR support to OSP defined and agreed between FCDO,OSP and ICAR. | TBC | TBC | TBC | TBC | TBC
Achieved
Source : OSPs Report of Investigation into Labianca Group of Companies, August 2022 https://osp.gov.gh/media/attachments/2022/08/07/osp_investigation_report_labianca.pdf
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | Total (£) | Total (£) |  | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTCOME 3 | Outcome Indicator 1 |  | Baseline (2023) | Milestone 1 (April 25) | Milestone 2 (April 26) | Milestone 3 (April 27) | Milestone 4(April 28) | Milestone (April 29) | Target (April 29) | Assumptions
| TBC | Planned | TBC | TBC | TBC | TBC | TBC | TBC | TBC | • LBGT Act is not assented or implemented • Ghana remains stable • A good number of media organisations remains non-partisan. • Diaspora groups willing to engage on domestic issues.
Achieved
Increased protection (in principle and practice) of the political and civil rights of all persons in Ghana (e.g. PWDs, LGBT+, journalists). |  |  | Source: Partners Reports; Amnesty Rights Reports, Media reports , Annual Reviews and Programme Completion Report
| Outcome Indicator 2 |  | Baseline (2023) | Milestone 1 (April 25) | Milestone 2 (April 26) | Milestone 3 (April 27) | Milestone 4(April 28) | Milestone (April 29) | Target (April 29)
| TBC | Planned
Achieved
Source: Partners Reports; Media reports , Annual Reviews and Programme Completion Report
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | Total (£) | Total (£) |  | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline (2023) | Milestone 1 (April 25) | Milestone 2 (April 26) | Milestone 3 (April 27) | Milestone 4(April 28) | Milestone (April 29) | Target (April 29) | Assumptions
| Level of CSOs engagement to promote credible elections | Planned | CSOs influenced credible elections in 2020 through election observation, fact-checking of mis/disinformation, inclusive citizens engagement and anti-vigilante initiatives | 1193 CODEO Observers provide independent assessment of th electoral processes; IMANI influences voters choices through analysis and sharing of information on the credibility of political parties manifestos and ACEP,GACC &GII influence political parties' anti-corruption committments | Stakeholder consensus achieved on the roapmap for enacting a Campaign and Political Financing law | Draft Campaign and Political Financing Bill undergoing scrutiny. | Draft Campaign and Political Financing Bill approved by Cabinet | Campaing and Political Financing law enacted and enforced during the 2028 elections. | Campaing and Political Financing law enacted and enforced during the 2028 elections.
Strengthened capacity and motivation of CSOs and EMBs to promote credible and peaceful elections. |  | Achieved
Source: STAR-Ghana PCR, 2021; Partners reports, Media Reports, Draft Bills etc
| Output Indicator 1.2 |  | Baseline (2023) | Milestone 1 (April 25) | Milestone 2 (April 26) | Milestone 3 (April 27) | Milestone 4(April 28) | Milestone (April 29) | Target (April 29)
| Number of engagement platforms created by (i)National Peace Council (NPC) to increase dialogue to mitigate the risk of electoral violence ; (ii) National Commission for Civic Education (NCCE) to increase voter education among women and youn people. | Planned | Adhoc public call for a peaceful elections. | (i)Six(6) regional and one (1) national dialogues to build consensus among political parties for a peace elections ;(ii) Four (4) voter education engagement involving women and young people to increase their participation in the 2024 elections | TBC | TBC | TBC | TBC | (i)Six(6) regional and one (1) national dialogues to build consensus among political parties for a peace elections ;(ii) Four (4) voter education engagement involving women and young people to increase their participation in the 2024 elections
Achieved
Source
IMPACT WEIGHTING (%)- 25% | Output Indicator 1.3 |  | Baseline (2024) | Milestone 1 (April 25) | Milestone 2 (April 26) | Milestone 2 (April 27) | Milestone 2 (April 28) | Milestone (29) | Target (29)
| Level of National Peace Council's strategic communication capacity to address salient issues during 2024 elections. | Planned | Limited strategic communication capacity to handle potential crisis. | Increased NPC's responsiveness to crisis situations before, during and after the election | TBC | TBC | TBC | TBC | Increased NPC's responsiveness to crisis situations before, during and after the election
Achieved
Source
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | Total (£) | Total (£) |  | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline (2023) | Milestone 1 (April 25) | Milestone 2 (April 26) | Milestone 3 (April 27) | Milestone 4(April 28) | Milestone 5 (April 29) | Target (April 25- 29) | Assumptions
| Number of strategic partners created and sustained by CSOs funded by GGP to promote citizens engagement with state instittions and processess. | Planned | Adhoc engagements between and among CSOs and state actors on issues they're aligned. | Three (3) strategic partnerships established to facilitate citizens engagement with state instutitions and processes. | Three (3) new strategic partnerships established and three maintained to facilitate citizens engagement with state instutitions and processes. | Two new strategic partnerships established and five sustained to facilitate citizens engagement with state instutitions and processes. | Ten (10)strategic partnerships established to facilitate citizens engagement with state instutitions and processes. | Ten (10) strategic partnerships sustained and enabling citizens to influence policies and processes for greater transparency and accountability . | Ten (10) strategic partnerships established and sustained and enabling citizens to influence policies and processes for greater transparency and accountability . | • CSOs political neutrality, consistency and credibility • Capacity and willingness of citizens/citizens groups to engage on key issues
Achieved
Enhanced citizens engagement with state institutions and processes. |  | Source
| Output Indicator 2.2 |  | Baseline (2023) | Milestone 1 (April 25) | Milestone 2 (April 26) | Milestone 3 (April 27) | Milestone 4(April 28) | Milestone (April 29) | Target (April 29)
| Level of quality engagements between CSOs funded by GGP and state institutions and in state processes | Planned | CSOs funded by GGP have some level of access to state instutions and are engaged in some public policy discussions. | CSOs funded by GGP have engaged with political parties, EMBs and other stakeholders on key electoral issues such as manifesto building, voting processes, electoral intergrity and election security among others to infleunce credible elections. | CSOs have generated evidence with recommendations to duty bearers and have mobilised citizens to use the evidence to hold government to account on their manifesto promises, commitments to public sector reforms and corruption in the public sector | CSOs have secured commitments from state actors and are engaging on with them to implement these commitmments | CSOs/citizenshave institutionalised engagements with state actors and are effectively engaging publicin policy making and implementation and regularly challenging the status quo to to improve transprency and accountability. | CSOs/citizenshave institutionalised engagements with state actors and are effectively engaging publicin policy making and implementation and regularly challenging the status quo to to improve transprency and accountability. | CSOs/citizenshave institutionalised engagements with state actors and are effectively engaging publicin policy making and implementation and regularly challenging the status quo to to improve transprency and accountability.
Achieved
Source:CSOs proposals
IMPACT WEIGHTING (%)-30% | Output Indicator 2.3 |  | Baseline (2023) | Milestone 1 (April 25) | Milestone 2 (April 26) | Milestone 3 (April 27) | Milestone 4(April 28) | Milesotne 5 (April 29) | Target (April 29)
| % of CSOs/citizens -state actors engagement that have resulted in commitment to reform policies and practices | Planned: | 0 | 2 CSO and state actors engagement have resulted in commitments to reform policies and practices | 5 commitments from CSO and state actors engagement have progressed to reform policies and practices | Processes for reforming the 5 commitments from CSO and state actors engagement have been concluded | Improved practices in five areas of committment as a result of reforms | CSOs actions have reformed policies and practices leading to inmprovement in governance outcomes in five areas | CSOs actions have reformed policies and practices leading to inmprovement in governance outcomes in five areas.
Achieved
Source :Partners report, media reports, (This will be measured by the % of CSOs recommendations that have been actioned by state institutions)
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | Total (£) | Total (£) |  | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 3 | Output Indicator 2.1 |  | Baseline (2023) | Milestone 1 (April 25) | Milestone 2 (April 26) | Milestone 3 (April 27) | Milestone 4(April 28) | Milestone (April 29) | Target (April 29) | Assumptions
| Number of cases involving asset tracing, freezing or seizure from investigations by OSP supported by ICAR | Planned | TBC | TBC | TBC | TBC | TBC | TBC | TBC | • State institutions would be persuaded to adopt reforms. • Political and administrative ownership of interventions
Achieved
Enhanced state capacity and motivation to strengthen legislative and institutional frameworks and improve transparency, accountability and human rights as well as reduce corruption |  | Source
| Output Indicator 2.2 |  | Baseline (2023) | Milestone 1 (April 25) | Milestone 2 (April 26) | Milestone 3 (April 27) | Milestone 4(April 28) | Milestone (April 29) | Target (April 29)
| % change in cases received throug the Citizens Eye and investigated by Ghana Audit Services as a result of CSOs advocacy | Planned | TBC | TBC | TBC | TBC | TBC | TBC | TBC
Achieved
Source
IMPACT WEIGHTING (%)-30% | Output Indicator 2.3 |  | Baseline (2023) | Milestone 1 (April 25) | Milestone 2 (April 26) | Milestone 3 (April 27) | Milestone 4(April 28) | Milestone (April 29) | Target (April 29)
| Number of cases investigated and prosecuted by the OSP as a result of CSOs/media investigations/reports funded by GGP | Planned | TBC | TBC | TBC | TBC | TBC | TBC | TBC
Achieved
Source
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | Total (£) | Total (£) |  | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 4 | Output Indicator 2.1 |  | Baseline (2023) | Milestone 1 (April 25) | Milestone 2 (April 26) | Milestone 3 (April 27) | Milestone 4(April 28) | Milestone (April 29) | Target (April 29) | Assumptions
| Level of preparedness of partners to implement interventions | Planned | TBC | Partner identified and agreement signed | TBC | TBC | TBC | TBC | TBC | • Partners have capacity to deliver on projects/programmes (including GESI mainstreaming) • CSO and citizen-based groups, including marginalised and vulnerable groups, can be mobilized for collective action • Target service providers have the capacity (e.g. MEL) to provide quality services. • Citizens, including the marginalised and vulnerable, are willing and able to engage with CSOs • CSOs are interested in driving citizen-led agendas forward that reflect the agendas/needs and priorities of marginalised and vulnerable groups • • Risks identified by partners are within their control to manage, including risks to marginalised and vulnerable groups (to Do No Harm) • Diaspora community willing to engage
Achieved
Increased domestic and diaspora voices/actions for protection of rights of all persons in Ghana. |  | Source
| Output Indicator 2.2 |  | Baseline (2023) | Milestone 1 (April 25) | Milestone 2 (April 26) | Milestone 3 (April 27) | Milestone 4(April 28) | Milestone (April 29) | Target (April 29)
Planned
Achieved
Source
IMPACT WEIGHTING (%)- 15% | Output Indicator 2.3 |  | Baseline (2023) | Milestone 1 (April 25) | Milestone 2 (April 26) | Milestone 3 (April 27) | Milestone 4(April 28) | Milestone (April 29) | Target (April 29)
Planned
Achieved
Source
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | Total (£) | Total (£) |  | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
Note on B93: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Best to use numbers rather than %

## Change frame
Use this change log to record all changes to the logframe over the life of the project.
ID | LOGFRAME SECTION | DETAILS OF CHANGE | AUTHOR | DATE
E.g. | Output 1, Indictor 2 | Indicator amended from 'No of children enrolled in primary schools' to 'Number of children enrolled in UNICEF supported primary schools (disagregated by sex) | Joe Bloggs | 2022-01-01
1
2
3
4
5
6
7
8
9
10

## Guidance Notes
Logframe Template Guide
Teams should use the guide below to complete the logframe template.
PROJECT TITLE
The name of the programme to which this logframe applies, from the business case
IMPACT
Long term goal to which the project will contribute towards achieving. When drafting the impact statement, consider how your project fits with other efforts from FCDO and partners to achieve the impact, ie is your project nested within a broader undertaking? This will often be the Impact indicator from the Theory of Change in the Business Case.
OUTCOME
The outcome should link through to the outcome level in the programme Theory of Change as stated in the Business Case. The outcome of your project identifies what will change, who will benefit and how it will contribute to reducing poverty, including contributions to the Sustainable Development Goals (SDGs) or Climate Change.
Ongoing monitoring of progress against outcome milestones takes place as an assessment of whether you expect to achieve the Outcome by the end of the programme in the programme Annual Reviews. An assessment of whether your project achieved the Outcome will be included in the Project Completion Review (PCR) based on the target milestone for the programme completion.
OUTPUTS
Outputs are the specific, direct deliverables of your project. These will provide the conditions necessary to achieve the Outcome. The logic of the chain from Output to Outcome therefore needs to be clear. Outputs should reflect the Theory of Change as set out in the Business Case for the programme.
Progress towards the outputs will be assessed and scored at the Annual Review, using output indicators and milestones. Achievement of the outputs will be assessed at project completion, using output indicators and targets.
IMPACT WEIGHTING
Once you have defined your Outputs, assign a percentage for the contribution each is likely to make towards the achievement of the overall Outcome.
The impact weights of all the Outputs will total 100% and each are rounded to the nearest 5%.
Impact weightings for Outputs are intended to:
1. Promote a more considered approach to the choice of Outputs at project design stage; and
2. Provide a clearer link to how Output performance relates to project Outcome performance.
INPUTS
Clarification of inputs is a key part of results-chain thinking. Inputs are specified at the country-level in country operational plans and the project information contained in logframes should feed up into these.
The input-level boxes show the amount of money provided by FCDO and any partners (£) including, where relevant, the government’s own contribution. This only relates to monetary (not in kind) contributions. At Outcome level this is equal to the sum of Inputs for all Outputs. The FCDO share at Outcome Level is a simple, pro rata calculation of FCDO’s contribution in monetary terms for all outputs.
Information should also be provided for the total number of Annual FCDO Full-Time Equivalents (FTEs) allocated to this project, based on the time individual staff members will spend on the project. It is understood that this may change through the project cycle, and is intended as a management tool.
INDICATORS
Indicators are performance measures, which tell us what will be measured not what is to be achieved. Avoid including elements of the baseline or target.
What makes a good indicator?
Specific – what will be measured? And how?
Measurable - data can be collected
Relevant - to the results chain
Useful – for management decision making
Does not include any element of the target
Can be disaggregated if relevant (especially when the indicator relates to number of beneficiaries reached with an intervention)
A mix of qualitative and quantitative
Already defined - if relevant include indicators which towards the FCDO Outcome Delivery Plan / ICF KPIs / SDGs.
Consider using standard indicators / best practice indicators / learning from other projects
The basic principle is that “if you can measure it, you can manage it”.
Top Tip – select indicators based on relevance to the Theory of Change and the availability of data.
Best Practice suggests a maximum of three Indicators per Output.
Some example indicators for a WASH project are shown below.
BASELINE
Baselines set the starting point and provide a measure of the situation before your project starts (could be zero if a new project).
The baseline is used to measure change and monitor progress.
Include a baseline for each of your indicators. The first 6 months of a project may exceptionally be used for assembling baseline data at output level if agreed by your PRO.
Use existing data where possible, but check reliability and seek assurances regarding the data quality eg use data from national statistical systems / Management Information Systems.
If you need to collect your own data - collect baseline data early – as soon as beneficiaries have been identified but before any results are expected.
MILESTONES
Milestones are the desired trajectory from baseline to target, helping you to track progress and make changes to underperforming areas.
Will depend on sequencing of activities and data availability.
Include REALISTIC milestones given resources and capacity.
At the output level include annual milestones for each year of the project (or monthly if short term). At outcome & impact level data may not be available annually and you should record the expected frequency of data availability.
TARGET (DATE)
Targets set the desired point, showing what is achievable within the timeframe available.
The target is often the last year of the project (or month if its short term).
Include realistic targets given resources and capacity, the baseline situation, funding available and country/operational context. Project targets might be informed by evidence about what has worked in the past and take into account lessons learned from other projects.
Include targets dissaggregated by sex/geography/income etc where appropriate.
Consider using government targets although if they are too ambitious then make a more realistic estimate.
Top Tip - A good Theory of Change will help you think about what is realistic and achievable as it will enable critical reflection of context, external influences & assumptions.
SOURCE
Each Indicator will have a data source to verify the results achieved.
List the specific data sources i.e. give the specific data collection e.g. named survey / report and avoid just naming the organisation.
State the frequency of the data source and ensure consistency with milestones and targets.
Check the source can provide disaggregated data as required.
Consider and specify the data collection and reporting responsibilities to ensure the results planned and forecast rows in the logframe are updated on a regular basis.
Top Tip - Before using a data source, assess its quality and seek assurances from data providers where needed ie consider its validity, reliability and availability. Use the Data Quality Prof Guide to help you consider the quality of your data.
ASSUMPTIONS
Define any assumptions which are linked to the realisation of your project's individual outputs, as well as those which are critical to the realisation of the outcome and impact: these will not all be the same. If you are carrying out any evidence gathering to check your assumptions then make reference to this as part of this section.
VALUE FOR MONEY
Ensure the outputs and outcome projected represent good value for the invested resources, at the beginning of the project, and through its life.
Consider including VfM metrics in the logframe (or other documents such as the Delivery Plan) to allow VfM to be measured through the life of the project and to provide assurance at Annual Review.
VfM is achieved at different stages of the results chain. Thus for each result we seek to achieve we should aim to have metrics for each of the following:
Economy - Are we (or our agents) buying inputs of the appropriate quality at the right price?
Efficiency - How well are we (or our agents) converting inputs into outputs? (‘Spending well’)
Effectiveness - How well are the outputs produced by an intervention having the intended effect? (‘Spending wisely’)
Cost-effectiveness - What is the intervention’s ultimate impact on poverty reduction, relative to the inputs that we or our agents invest in it?
Equity - Is the intervention meeting the needs of all beneficiaries?
FCDO’s Approach to Value for Money (PrOF Guide) provides further advice on ensuring VfM.