Annual Review

Summary of Programme Performance
Year	2023/24
Overall Output Score	A+
Risk Rating	Moderate	Choose a risk rating	Choose a risk rating

Programme title: UK – Rwanda Trade and Investment Partnership Programme
Programme Value £ (full life):	£4,500,000 (of which £174,751 allocated for first year-2023/24)	Review Date: / November 2024
Programme AMP Code: 400150	AMP start date: / November 2023	AMP end date: / October 2028

DevTracker Link to Business Case:	Issues with the link but being rectified
DevTracker Link to results framework:	Developed as part of the initial BC – to be uploaded

## SUMMARY AND OVERVIEW

Programme description: / The UK-Rwanda Trade and Investment Partnership programme is a £4.5m programme (of which £174,751 was allocated for the first year: 2023/24 to support primarily the convening of the first UK-Rwanda Business Forum). The programme aims to strengthen the bilateral relationship between the UK and Rwanda and as such, promote mutual prosperity and inclusive economic development. The planned portfolio of interventions is designed to be both proactive and responsive to the market and priorities of the UK and Rwanda in the areas of trade and investment. The interventions leverage on the UK’s high-level convening power, and strategic relationship, as well as draw on the good political will of the Rwandan government. / The UK and Rwandan governments have a strong strategic partnership, which supports Rwanda's growth journey through work on reforms aimed at improving the investment and business climate, green transition, tax policy and administration, land reform, and public administration in Rwanda. Rwanda's positive economic trends have been influenced by its strong governance and institutions, as well as progressive bilateral relationships with other countries, including with the United Kingdom. / The economy of Rwanda grew by 8.2% in 2023, primarily due to increased agricultural production, government investment in infrastructure, foreign capital investment in tourism and hospitality, and an increase in private sector credit. Total trade in goods and services (exports plus imports) between the UK and Rwanda was £35 million in the four quarters to the end of Q2 2023, an increase of 9.4% or £3 million in current prices from the four quarters to the end of Q2 2022. However, Africa, accounts for just 2.5% of the UK’s trade, with 60% of this accounted for by South Africa and Nigeria. / The appetite of UK firms to invest and establish businesses in Rwanda is promising, but a concerted strategy for boosting trade and investment between the two countries is required to make significant progress. Rwanda serves as a critical strategic partner to the UK, with significant convening power and influence across Africa (in particular, within the East Africa region). In addition, the Rwandan government sets high ambition on objectives important to the UK such as climate, green growth, and the rights and empowerment of women and girls. / The two countries went through election cycles during the year under review, with the ruling party in Rwanda retaining control, while a new (Labour) Government has been constituted in the UK. The former provides continuity – with sustained ambition on economic transition as contained in the new National Strategy for Transformation (NST) 2, while the objectives of the programme in terms of promoting growth and inclusive economic development align with the priorities of the new UK Government. / The funding mechanism for this programme is through ODA and non-ODA budgets, allowing post the flexibility to deliver on a more inclusive economic development ambition, encompassing both UK commercial interests and development priorities.
Intended policy objective(s) of the interventions within this programme. / The programme serves as a vehicle to support Rwanda in actualising its long-term strategic plan to become an upper middle-income country by 2035 as well as actualising the trade and investment goals set out in the revised National Strategy for Transformation (NST 2) – leveraging on UK’s strong convening power, robust and diverse investment toolkit as well as targeted technical assistance, policy influencing and enhanced UK-Rwanda partnerships. / Rwanda has a good investment climate, with a pro-business government, a growing economy, and access to the East African markets, with several FDI opportunities in sectors including manufacturing, infrastructure, energy distribution and transmission, financial services, fintech, off-grid energy, health services; education, electric vehicles, agriculture and agro-processing, tourism, services, mining, and information and communications technology (ICT). However, there is need for concerted efforts in attracting substantial capital, facilitate technology transfer, create jobs, promote competition, and reinforce Rwanda’s integration into the global economy. This programme, through its interventions supports Rwanda’s priority policy areas, in particular attracting investments that generate decent jobs and enhancing the country’s export base to increase foreign revenue. / The policy objectives of the programme include: / Through the convening power of the UK Government, the programme would deliver series of trade and investment events e.g., high-level UK-Rwanda Business Forum; trade and investment roundtables and missions; capacity building sessions with both government and the private sector; and support the UK-Africa Investment Summit. The aim of these convenings is an anchored on the following objectives: i) showcasing Rwanda as a preferred investment destination leveraging its favourable business climate, and strategic position within the EAC region; ii) building sustainable commercial relationships that drive trade and investment growth in Rwanda. / Leverage the robust and diverse investment toolkit (in particular, the British Investment Partnerships, BIP vehicles) such as UK Export Finance, British International Investment (BII), Private Infrastructure Development Group (PIDG), and Manufacturing Africa (MA) to support Rwanda in delivering on its policy priorities – creating decent and productive jobs as well as boosting exports. This policy objectives align with the Post’s bilateral programmes that are leveraging private investments in the tea sector (one of Rwanda’s top exports) and supporting crucial infrastructure projects to boost trade. This portfolio of interventions aims to contribute to inclusive economic growth, increase the flow of Foreign Direct Investments (FDIs) and enhance Rwanda's business climate. In addition, they support Rwanda's private sector development in areas such as manufacturing, green economy, infrastructure, agriculture, research, and innovation. / Curate and deliver capacity building and market research interventions, including acting as a source of knowledge sharing and capacity building channel for both the Government of Rwanda and the private sector on trade and investment opportunities, e.g., trade preferential agreements – including the Developing Country Trading Scheme (DCTS), which could promote adoption and enhance trade flows between the two countries; support to the Rwanda Development Board and MINICOM on investment facilitation and promotion, as well as identifying new growth/emerging sectors of investments. In addition, build capacity around investment opportunities and partnerships that could support an increased flow of FDI.
Overall Programme Score / Programme score is A+.
Summary supporting narrative for the overall programme score in this review. / Over the last year, building on the strong bilateral relationship between the UK and Rwanda, the UK-Rwanda Trade and Investment Partnerships programme has leveraged diverse levers – including the economic diplomacy of the UK, its convening power, as well as vast investment toolkit and trade facilitation capability. / At the Output level: The programme met one and exceeded two of the output targets across the three output areas – i) Record high attendance of registered participants at the UK–Rwanda Business Forum, ii) Facilitation of Trade and Investment Missions (to the UK and Rwanda) and iii) Production of high impact knowledge products. / Record high attendance of registered participants at the UK–Rwanda Business Forum: The programme exceeded the Log Frame target in terms of attendance at the Business Forum. The total number of attendees was over 1,000, compared with the 750 projected in the Log Frame. Beyond the attendance, the Business Forum recorded successes in a number of areas including: i) the identification of trade and investment opportunities, including specific deal sourcing support, as well as commercial relationships between the UK and Rwanda companies, ii) creation of opportunities for a wide range of businesses, including those that are women- and youth-run, to display and exhibit their products and services; iii) dissemination of high-impact knowledge products focused on emerging and green investments in Rwanda; iv) provision of networking opportunities to supply chain partners, farmers, exporters, buyers, coffee roasters, baristas, among others, yielding commercial deal announcements during and after the event; v) provided opportunities for delegates to join fourteen industry site visits; vi) curation of post-event trade and investment missions to the UK. / Facilitation of Trade and Investment Missions (to the UK and Rwanda): The programme successfully organised two trade and investment missions to the UK. The events led to an increased visibility of the trade and investments opportunities in Rwanda, facilitated matchmaking between the Rwanda firms and UK investors, as well as strengthen the strategic partnership between the UK and Rwanda (through the close collaboration between the BHC Kigali, National Agricultural Export Development Board NAEB, Rwanda Development Board RDB, and Invest Africa). / Production of high impact knowledge products: The programme supported the production of over twenty impact knowledge products including sectoral pitch decks/fact sheets, investment vignettes and insightful research reports on new and emerging sectoral opportunities. This exceeds Log Frame targets of five high impact knowledge products. The knowledge products provided currency in terms of trade and investment opportunities in Rwanda and have been used by government counterparts in trade and investment roadshows – including at international events and mission in the UK. / Impact / Outcomes / At least twenty Rwanda businesses and government counterparts attending trade and investment missions to the UK to increase access to market and strengthen partnerships / Increased number of UK and Rwanda businesses registered in Rwanda, and initiating trade and investment deals and expanding business network. / Organise trade and investment missions, roundtables, deal rooms, exhibitions, where Small and Medium-sized businesses (including women- and youth-owned SMEs) can connect with investors access markets. / Activities / Facilitate the convening high-level bilateral trade and investments events, such as the UK-Rwanda Business Forum and the UK-AIS that brings together key stakeholders in the UK, Rwanda and SSA. / Increased insights on the investment opportunities for Rwanda as well as visibility for the Government of Rwanda’s effort in positioning Rwanda as an investment destination. / Commission market research and disseminate of high impact knowledge products, as well as build capacity and capability of the Rwandan market – including private/public. / Outputs / 750 registered participants at the UK-Rwanda Business Forum / (50 UK Companies) / At least two Trade and Investment Missions (to the UK and Rwanda). / Five high impact knowledge products produced. / At the Outcome Level: The results at the outcome level reflects the attitudinal changes and practices expected from businesses and investors, particularly with regards to the former’s ability to leverage knowledge products such as investment vignettes and pitch decks to pitch at the Business Forum and other trade and investment missions as well as an increase in investors’ appetite to invest in Rwanda as a result of attending the Business Forum. / Through the Business Forum, six companies within the green economy and manufacturing sectors delivered investment pitches, using the vignettes and pitch decks produced as part of the event. In addition, to the successful pitch session, some of the business that pitched such the Biomassters, Proud Holding Rwanda, and Pink Mango received investment facilitation support from the UK through the Manufacturing Africa programme after the Business Forum, enhancing their investment readiness to attract FDIs. Furthermore, at the Business Forum, there were three high-level Public-Private Dialogue PPD (involving government counterparts such as RDB, MINIINFRA, MINIAGRI) to unlock investment bottleneck, with positive outcomes for project pipelines such as the Ruzizi III project, Power Resources International, Del Agua, Ampersand, Trinity Metals. / Through the Business Forum and subsequent trade and investment missions to the UK, there has been at least one investment support through the UK British Investment Partnership, i.e. the securing of a $7.5 million debt facility from the British International Investment (BII) to scale BasiGo’s E-bus deployments in Rwanda. / At the Impact Level: The impact level result that the programme aims to achieve is an increase in trade and investment flows between the UK and Rwanda. Following the Business Forum in January, the programme commissioned Invest Africa to conduct a post-event evaluation assessment of the event with a view to gathering feedback from participants, as well as consolidating evidence on indicative impact level results. The Business Forum addressed several aspects of the trade and investment facilitation and promotion – including, / Facilitating high-level government-private sector dialogues (e.g., on the Ruzizi III project) – which has helped unlocked some of the policy bottlenecks hindering the progress on the project with an expected investment capital of $450 million. / Showcasing UK’s diverse investment toolkits (e.g., through plenary sessions on UK’s British Investment Partnerships) – which allowed institutions such as TheCityUK to set out scoping work to support the Kigali International Financial Centre, KIFC; provided deal sourcing platform for Manufacturing Africa programme, which has gone ahead to deploy its transaction facilitation instrument to support manufacturing companies such as Biomassters, Proud Holding Rwanda and Pink Mango, to become investment ready. The support through the Manufacturing Africa programme could help these companies secure over $50 million in FDIs over the next year. / In addition to the Business Forum, the impact level results also flow from the other two components including trade and investment missions as well as insightful high-impact knowledge publications (in particular on the green economy, including “green” investment vignettes). / There is a recognition that actual trade and investment flows do take time to materialise, and the full picture in terms of immediate and longer-term impact of spend £174,751 may not be evident for a while. It is therefore imperative that the programme puts in place a proportionate monitoring and evaluation mechanism over Year 2 to support evidence and data gathering that could help track these flows and assess attributions. In addition, in order to deliver on a more transformative ambition that would help deliver on the planned impact, the programme would benefit from a detailed workplan that signals the strategic intent and ambition, aligned with the overall appropriate budgetary allocation reflective of this ambition. The programme, in structuring this plan could take into consideration: the growth objective of the new UK Government, alignment with the Country Business Plan and the emerging opportunities to support Rwanda’s National Strategy for Transformation 2 (NST2) priorities as well as leveraging on the British Investment Partnerships toolkit – and then set out an approval process.
Major lessons and recommendations for the year ahead / There were several lessons and recommendations drawn from the interventions delivered on the UK-Rwanda Trade and Investment Partnership. The lessons are clustered across the following key thematic areas: Planning, Partnership and Resources. / Planning / Internally, the BHC, Kigali Green Growth and Trade Team commenced planning for the curation and design of the programme relatively early, with wide consultation with both Rwandan stakeholders (government counterparts and the private sector), as well as both regional and UK based partners. This reflected in the wide-ranging thematic areas of the UK-Rwanda Business Forum – including high attendance, insightful contents, and seamless delivery. However, there was a progressively higher than expected interest and demand for the Business Forum, both from the Government of Rwanda and the private sector. This has significant implications for the scope of the event and budgetary resources. / Recommendations: / Early Planning: For the delivery of a successful major trade and investment event such the UK-Rwanda Business Forum, it is recommended that planning should start early, ideally at least 9 months before the start date of the event to manage expectations. In addition, a well-defined scope of work with defined with boundaries and clear objectives should be set out as this would help in managing allocated budget. / Logistics: The timing of the next UK-Rwanda Business Forum should take into consideration, holiday periods (such as summer and Christmas) to maximise attendance and ensure effective engagements and smooth delivery of the event. Organising the Business Forum straight after the Christmas period meant that the event planning lost momentum over the Christmas break and thus put considerable pressure on the team in January, with negative implication for team wellbeing. In addition, logistics areas such of onboarding of a Professional Conference Organiser PCO, design and development of promotional and conference materials, website and registration links should be prioritised. / Safeguarding: An area that was flagged during the post-event feedback sessions was safeguarding around public facing events, such as the Business Forum. It is recommended that safeguarding training and guidance be incorporated into the planning process and this made to both internal and external stakeholders to ensure increased awareness and compliance. / Workplan: The programme should develop a detailed workplan over the next one year to capture its ambition and set out interventions that aligns with the expected impact, considering the budgetary provisions. / Partnerships / There is a recognition that having strategic partnerships in place, in particular with key government counterparts such as RDB, Rwanda Convention Bureau (RCB), thematic ministries, media, Private Sector Federation (PSF), HMG and UK partners in the curation of the event ensure effective delivery and leveraging of the support. In addition, this reinforces the commitments of these stakeholders and for HMG partners such as the Department for Business and Trade DBT, ensure access to trade and investment networks beyond which the programme could access. / Recommendations: / Formalised Collaboration: To ensure commitment, ownership and effectiveness of the planning and delivery of international events such as the UK-Rwanda Business Forum, it is highly recommended that an MoU be signed with the GoR (including key partners such as RDB, RCB and Rwanda High Commission, London) and other key partners such PSF and the British Chambers of Commerce. This would ensure shared responsibility, promoting collaborative culture and effective management of workload and key activities. In addition, DBT should be brought on board early, as they could act as champions and provide staff resource, and support on the commercial priorities. / Resources / The programme (with a small core team) delivered a significant amount of work, which was complimented by a few volunteers in the final weeks (nearly all BHC staff member was involved at some point, and it became a whole-of-mission effort). The planning and delivery also benefitted from having a Professional Conference Organiser in place, which lessened the burden on the FCDO programme implementing team. There was a steep learning curve with the PCO – including on registration and badge production, website launch and management of contents as well as the delivery the main event day. In terms of funding, the programme successfully secured a total of £20,300 in sponsorship, which complimented the available (ODA and non-ODA) funding. However, the increasing scope of the event, driven by high expectations of the Business Forum impact (particularly, by GoR), resulted in additional budget lines (and initially unanticipated costs). Overall though the event was delivered within budget, with the sponsorship generating a modest return which offset overspend. / Recommendation: / It is recommended that the development and delivery of such an event be well resourced early – leveraging on external partners such as RDB, with clear role and responsibilities, clarity on key contacts, delegation of power on key activities and decisions. In addition, leverage DBT (UK & Africa), British Chambers and UK media in championing the event and providing visibility. / To ensure effective coordination on the planning and delivery of the next Business Forum, it is recommended that the programme appoint or delegate a relationship focal person(s) with counterparts including GoR and HMG and UK Partners for engagements on support and partnership. These focal partners should be familiar with how to navigate the systems. / The programme should aim for more clarity on roles and responsibility of onboarded event organiser to ensure that expectations are aligned. This could include having a well-articulated provisions and contract clauses that holds both parties accountable and ensure adept deliver. Such clauses could also tie performance/delivery effectiveness on milestone to payments. / In addition, it is recommended that the programme should articulate a well-thought-out sponsorship plan well in advance of future events.

## PROGRAMME STRATEGY OR THEORY OF CHANGE

Impact
Increased Trade and Investments between the UK and Rwanda

Number of new and additional UK investments attracted into Rwanda and increased UK-Rwanda trade flows
Number of businesses supported to pitch investment / trade opportunities and forge partnerships with their counterparts from the UK
Outcomes

Production of high impact knowledge products.
Facilitate Trade and Investment Missions to the UK

Record high attendance of the UK-Rwanda Business Forum

Outputs

Organise trade and investment missions, roundtables, deal rooms, exhibitions, where Small and Medium-sized businesses (including women- and youth-owned SMEs) can connect with investors access markets.

Commission market research and disseminate of high impact knowledge products, as well as build capacity and capability of the Rwandan market – including private/public.
Activities
Facilitate the convening high-level bilateral trade and investments events, such as the UK-Rwanda Business Forum and the UK-AIS that brings together key stakeholders in the UK, Rwanda and SSA.

Capacity Building & Market Research
Trade & Investment Missions
High-Level Trade and Investment Convenings

Components

Figure 1: Theory of Change

Figure 1 represents the Theory of Change (ToC) of the UK-Rwanda Trade and Investment Partnership. The ToC is anchored on three components, i) Delivery of high-level Trade and Investment Convenings, ii) Organising of Trade and Investment Missions, and iii) Delivering impactful Capacity Building and Market Research Interventions. It brings together the logical flow of inputs across these components into the delivery of Outputs, Outcomes and Impact.

This therefore means that,

- As the programme organises Trade and Investment events and missions – including the Business Forum, opportunities are created for businesses to showcase investment prospects, increase visibility, initiate trade and investment deals and expanding business networks, as well as increase access to market and strengthen commercial/investment partnerships.
- In addition, the government is able to leverage on the knowledge products to drive its Trade and Investment action plans, as well as provide current and up-to-date information on current and emerging opportunities in Rwanda.
- These then translate to - more confident and informed investors; improved products, services and processes; an improved business environment, all of which increases the trade and investment flow between Rwanda and the UK.

## DETAILED OUTPUT OR PERFORMANCE AREA SCORING

Delivery of Programme
Output:	Registered participants at the UK-Rwanda Business Forum
Target Number:		750	Score:	A+
Weighting (%):		70%	Weighting revised since last AR?	No

Briefly summarise the projects that have been delivered and provide supporting narrative for the score.

This programme has delivered substantially better than expected because of this is scored an A+ under this output.

This performance area is linked primarily to the curation, design and delivery of the first UK-Rwanda Business Forum which took place in Kigali, Rwanda in late January 2024. The Business Forum served as a premier platform for the Government of Rwanda and businesses to showcase investment and trade opportunities, fostering partnerships with their UK counterparts. Its overarching goal as contained the Business Case was to spotlight Rwanda’s investment potential, favourable business climate, and strategic position within the EAC region to UK investors.

The Forum facilitated dialogue and collaboration among policymakers, business leaders, and investors from both the UK and Rwanda. Discussions were held to address existing trade and investment barriers, with the ultimate aim of fostering a conducive environment for bilateral economic cooperation.

Its objectives included
- identifying opportunities, devising strategies, and fostering sustainable commercial relationships to drive trade and investment growth in Rwanda.
- Bringing together UK and Rwanda policy makers, business operators and investors to engage, discover opportunities, strategize, and further trade and investment prospects.
- Pitching Rwandan business opportunities and lay the groundwork for building sustainable commercial relationships, to drive trade and investment growth in Rwanda, including in the run-up to the UK-African Investment Summit 2024 (UK-AIS 2024).
- Discussing and developing recommendations to address the existing trade and investment barriers.

The Business Forum was a huge success with over 1,000 registered delegates in attendance at the three-day event – including over 400 women and 300 youths, nationals from over 52 countries, over 100 UK investors, a further 150 from across the region, and about 575 Rwandans joining the event. The event leveraged the insights provided by research that were commissioned, such as the Rwanda Green Economy and Lithium-ion Battery Precursor in highlighting investment opportunities in emerging areas, whilst supporting Government of Rwanda trade and investment policy thrusts on attracting investments and promoting export.

A contributory aspect of the Business Forum to the scoring for this performance area is the series of sessions (plenary and breakouts) where delegates benefitted from insights into the pivotal role of the BIP in channelling UK-backed finance, aligning with the $600 billion G7 Partnership for Global Infrastructure and Investment, as well as emphasising the UK’s commitment to mobilise up to $40 billion through BIP by 2027. In addition, the six breakout sessions (agriculture, infrastructure, critical minerals, manufacturing, green economy and financial services) provided compelling engagements on Rwanda’s investment landscape, drawing insights from industry experts, as well as key opportunities and dynamic interactions through investment pitches.

Feedback from the UK-Rwanda Business Forum

- “Thank you once again for your support last week and congratulations on a highly professional and productive inaugural forum. It was a great event for us; we made lots of important contacts.”
- “The congress was a testament to the unwavering commitment of the British High Commission in Rwanda to excellence and innovation, and we are grateful to have been a part of this memorable experience.”
- “I can safely say from a regional perspective, you have set the bar extremely high. I know how hard these events are to put on; the time, commitment, attention to detail and management required - you pulled it off seamlessly!”
- “My thanks to you and the team for organising a brilliant event – I received really positive feedback about the panel session and thought the moderation of the panel (and the event as a whole) was superb. Plenty of action to build on!”
- “I also heard the UK-Rwanda Investment Conference was a huge success. Congratulations! I spoke to partners here who loved it. I think we might consider something similar in Nairobi. I’d love to pick your brains on how you organised it and any tips etc.”
- “Top marks for the organisation and hospitality I really enjoyed it.”
- ”It was very uplifting event that was well structured and well organised. I had a great deal of positive feedback from the businesses attending.”
- “The exposure and engagement we experienced was remarkable and exceeded our expected targets. This has been a great platform for us to achieve maximum visibility, engage and contribute to the agenda of highlighting Rwanda’s potential and get the needed traction among UK Investors, as well as local businesses.”
- “Congratulations to the High Commission for an excellent event.”
- “Thank you and your team for delivering a great experience of UK-Rwanda business forum.”
- “Thanks again for the great organisation. Now starts the real business and the follow ups we need together to work on to create new leads in Rwanda...”

As part of the leveraging an important export focused sector, a coffee-cupping ceremony which was the first event of its kind was also organised by the British High Commission as part of the event to raise the profile of Rwanda’s specialty coffee amongst UK buyers. This further provided networking opportunities to supply chain partners, farmers, exporters, buyers, roasters, baristas, among others, yielding commercial deal announcements during and after the event. With UK buyers, the ceremony increased knowledge about Rwandan coffee, and local farmers, producers and exporters expanded their knowledge and experience on the quality of coffee needed to access the UK market. The event created a one-on-one positive feedback loop amongst participants, increasing coffee export revenues for Rwanda in the future.

To bring a practical element to the Business Forum, delegates attended fourteen industry site visits to better understand the investment opportunities and ease of doing business in Rwanda. These sites included Kigali International Financial Centre (KIFC), Norrsken Foundation, Trinity Metals, Bugesera SEZ, Proud Holding Rwanda, Kigali Water Limited, Bella Flowers, Pink Mango, Kigali SEZ, Champion Humanity, Zipline Drone Delivery and Logistics, Ampersand, Basigo and Biomassters Limited.

In addition, there were also opportunities for a wide range of businesses, including those that are women- and youth-run, to display and exhibit their products and services. On the policy side, there were several bilateral meetings on the side of the event and the Post was able to facilitate government-private sector dialogues aimed at unlocking investment flows into Rwanda.

A total of 118 respondents to the post-event feedback report was gotten, with the respondents’ feedback summary presented below:

- 96% of attendees felt the content meet your expectations in terms of its relevance and the quality of presentations.
- 79% of attendees feel they are more likely to invest in and/or open a business in Rwanda increased since attending the UK-Rwanda Business Forum.
- 94% of attendees felt that the UK-Rwanda Business Forum was inclusive.

Programme-level recommendations for the year ahead, and progress on recommendations from previous AR (if completed).
N/A
Output:	Facilitation of Trade and Investment Missions to the UK
Number:		2	Score:	A
Weighting (%):		20%	Weighting revised since last AR?	No

Briefly summarise the programme that have been delivered and provide supporting narrative for the score.

The programme curated and organised, successfully, two trade and investment missions to the UK – i) Invest in Rwanda: The Green investment opportunities (on the sides of the Africa Debate 2024) and ii) Taste of Rwanda event.

The score of A+ is attributed to the success and impact of the event in terms of visibility of the trade and investments opportunities in Rwanda, the matchmaking between the Rwanda firms and UK investors, as well as the strengthening of the strategic partnership between the UK and Rwanda (through the close collaboration between the BHC Kigali, National Agricultural Export Development Board, Rwanda Development Board, and Invest Africa).

As a follow on from the first-ever UK-Rwanda Business Forum that took place January 2024 (captured in Output 1), which provided unrivalled opportunities for high-level dialogue and networking, bringing together UK and Rwandan business leaders, investors and senior government officials, the BHC, Kigali through this programme, and its collaboration with the aforementioned partners, organised a follow-up engagement on the sidelines of the Africa Debate 2024 edition. This event was tagged Invest in Rwanda: The Green investment opportunities and leveraged on one of the knowledge products produced and disseminated as part of the Business Forum.

The Invest in Rwanda event provided an opportunity to further strengthen business and investment cooperation between the two countries, through an investor-facing roundtable focusing on key business opportunities within the green economy and green finance space in Rwanda. This enabled the facilitation of match-matching prospects in several already identified investment opportunities in industry such as, e-mobility, off-grind solutions and manufacturing. Moreover, the Roundtable brought together green finance vehicles in Rwanda as well as leading green economy companies developing groundbreaking solutions tackling some of the most pressing issues and challenges in Rwanda and the region.

Leveraging the strong partnerships with the UK British Investments Partnerships’ Growth Gateway and BCG’s Green economy research, which identified equity and debt finance needs worth over $430m in the Rwanda Green Economy, as well as the identified pipelines, the event (which attracted over 20 Rwandan delegates – both government counterparts and private sector players in the green economy) exceeded its expected outcomes of:

- Directly supporting and impact the fundraising efforts of the Rwandan companies looking to raise capital (e.g., BasiGO, which was subsequently supported by the UK’s British International Investment (BII) to the tune of $7.5 million debt facility, to scale the company’s E-bus deployments in Rwanda).
- Supporting Rwandan public financial institutions (e.g., Ireme Invest, Rwanda Development Bank) to directly connect with institutional investors and asset managers looking to gain exposure to the Rwandan economy.
- Promoting Rwanda as the foremost green finance and green economy destination in Africa.
- Engaging and building commercial relationship with British Investors who have the appetite of expanding their business to Rwanda.

The second trade and investment mission to the UK, the Taste of Rwanda, which builds on the success of the UK-Rwanda Business Forum aimed at further strengthening the UK-Rwanda bilateral trade and investment relationship through business promotion. The event’s focus was to connect export-ready Rwanda exporters in the coffee, tea, and horticulture space with UK buyers.

With a total of 75 participants in attendance, including 22 Rwanda exporters, 33 UK based buyers and 20 officials representing their respective institutions, the attendees including UK buyers and roasters had the chance to smell, taste and identify the unique flavours of Rwanda coffee. Later, Rwanda coffee exporters directly engaged with UK buyers. The event also afforded Philip Schulter, Managing Director COVOYA Speciality Coffee and Suzy Garraghan a Tea Buyer, from Bettys & Taylors of Harrogate to deliver pitches on doing business with Rwanda.

The key outcomes of the event included:

1. Identified new business opportunities, secured partnerships and 12 business deals (sales orders) between Rwanda exporters and UK buyers. The total amount for the initial signed contracts at the time of this Annual Review was $2,538,200.
2. An increased appetite for Rwanda agricultural products in the UK market.
3. Valuable market insights and networking opportunities for Rwandan companies.
4. Provided guidance and insights on the UK regulatory framework to help Rwanda businesses navigate market entry.
5. Enhanced brand visibility for Rwandan products in the UK.

Feedback from Taste of Africa Mission to the UK

- 97% of Rwanda exporters asked the Taste of Rwanda event to be a continuous or annually planned event in the UK.
- To mobilise more UK buyers to attend the next event.
- Rwanda exporters advised to scale up the event to other parts of the UK (Manchester, Bristol, Cardiff, Birmingham, Leeds, Edinburg, Newcastle, Coventry, Sheffield, Southampton, Bradford, Derby, Plymouth and Belfast) through Road shows.
- Rwanda exporters asked BHC Kigali to cover their travel and accommodation costs in the next event. (We covered for few delegates due to the budget constraint).
- Rwanda exporters asked BHC Kigali, if possible, to be involved in the planning process for the next event.
- Johnson Busingye and Claude Bizimana were very positive about the event and recognized the continuous BHC Kigali support in strengthening UK-Rwanda trade ties.
- Johnson and Claude are keen to see the next UK-Rwanda Business Forum. (They pledged their future support).
- UK buyers were happy with the selection of the Rwanda exporters.
- Rwanda exporters asked BHC Kigali to organise a follow-up trade mission in Kigali to further build their commercial relationship with UK buyers met at the Taste of Rwanda event.

Output:	Production of High impact knowledge products
Number		5	Score:	A+
Weighting (%):		10%	Weighting revised since last AR?	No

Briefly summarise the projects that have been delivered and provide supporting narrative for the score.

This performance area was assigned an A+ rating.

The programme supported the production of over twenty impact knowledge products including sectoral pitch decks/fact sheets, investment vignettes and insightful research reports on new and emerging sectoral opportunities.

These report not only provided currency in terms of the trade and investment opportunities in Rwanda, but it also allowed for the dissemination of the research outputs through Fora such as the UK-Rwanda Business Forum, and on the Trade and Investment missions to the UK. In addition, the Investment Promotion Agency in Rwanda, the Rwanda Development Board, was able to use the sectoral pitch decks/fact sheets on its investment roadshows – and the impact could be seen in the additional deal sources opportunities created through the Manufacturing Africa – including for companies such as Biomassters, Proud Holdings Rwanda and Pink Mango. This is in addition to the investment vignettes produces specifically for companies within the green economy that detailed specific investment opportunities in Rwanda.

Examples of knowledge products produced and their usage

Pitch Decks:
- RDB’s Sectoral Pitch Decks/Fact Sheets (Agriculture, Infrastructure, Green Economy, Mining, Horticulture, Global Business Outsourcing).
  - This knowledge products have been used by RDB on investment road shows, as part of their investment promotional materials to attract investors as well as during trade and investment missions.
- Investment Vignettes – this helped to address the lack of visibility, as well as consolidate the repository of business opportunities. The Vignettes consisted of all opportunities for investment or partnership with Rwanda stakeholders in key sub-sectors of the Green Economy
  - This knowledge produced were extensive used by investors at during the Business Forum, in particular, those that attended the Green Economy Breakout Session. In addition, the vignettes are available for reuse by opportunity owners who requested them at the Forum.
- Commissioned research – this focused on Green Economy opportunities as well as the emerging opportunities in the critical minerals/manufacturing sector – focused on Lithium-Ion Battery Precursor Production in Rwanda
  - Both outputs and recommendations of these reports were disseminated to participants at the Business Forum as well as at trade and investment missions on the UK. The research were well received and also part of the knowledge products being used by RDB to facilitate trade and investment flows into the country.

Programme-level progress on recommendations from previous AR (if completed).
N/A

D: RISK

Overall risk rating: Moderate

Overview of programme risk

The Business Case outlines expected context, reputational, fiduciary, delivery, operational, people and safeguarding risks, which have been captured in the programme risk register. This is updated on quarterly basis following review of the programme risk register. The programme’s risk in the business case was assessed overall as low/moderate with a ‘good’ development return.

Key risks for this first year review were around delivery of UK-Rwanda Business Forum and included:
- Lack of adequate budget to deliver the Business Forum, due budgetary cuts in FCDO programmes
- Capacity of the team to successfully deliver all the requirement of the business forum in short time frame
- The risk that individuals and businesses that register do not attend the UK-Rwanda Business Forum affecting the success and objectives of the forum,
- The risk that UK-Rwanda Business Forum is not inclusive and some marginalised groups including women and youth are left behind, and
- key agencies such as Rwanda Development Board (RDB) have witnessed several changes to their leadership team which had significant implication for the implementation of FCDO’s programmes.

The above risks were addressed and mitigated as summarised in the table below and residual risk impacts are either minor or moderate.

Key risks are how they were addressed

Risk Description	Mitigation Strategy	Risk Assessment
lack of adequate budget to delivery the Business Forum, due budgetary cuts in FCDO programmes	The programme team was able to bid for funding from the Growth Gateway programme and in sponsorship	The risk reduced to Minor/Moderate
Capacity of the programme team to successfully deliver all the requirement of the business forum	A professional service provider was procured to support deliver the business forum. In addition, BHC Kigali core team was formed with volunteers across the mission, including support from Trade and prosperity officer from Kampala	The residual risk reduced to Moderate, as the BHC core team together with the service provider delivered a successful business forum
The risk that individuals and businesses that register do not attend the UK-Rwanda Business Forum affecting the success and objectives of the forum	The programme team worked with Professional service providers to promote, and the communications team to create awareness, promote and advertise for the forum including working on sponsorship scheme and Business Forum was a huge success with over 1,000 registered delegates in attendance at the three-day event – including over 400 women and 300 youths, nationals from over 52 countries, over 100 UK investors, over 150 from elsewhere, and about 575 Rwandans joining the event	The residual risk reduced to Moderate
The risk that UK-Rwanda Business Forum is not inclusive and some marginalised groups including women and youth are left behind	Strategies to deliver inclusive business forum were designed with support inclusion experts from Human Development and resilience team including creation of opportunities for a wide range of businesses, including those that are women- and youth-run, to display and exhibit their products and services. As a result, registered delegates in attendance at the three-day event – including over 400 women and 300 youths, nationals from over 52 countries, over 100 UK investors, and about 575 Rwandans joining the event	Residual risk judged as Moderate
The risk that key agencies such as Rwanda Development Board (RDB) have witnessed several changes to their leadership team which had significant implication for the implementation of FCDO’s programmes	The team strengthened the strategic partnership through joint planning and collaboration with both with Rwandan stakeholders (government counterparts and the private sector), as well as both regional and UK based partners. / Reassurance of UK’s support to Rwanda in strengthening institutional capacity and / capability to deliver effectively irrespective of the cycle of leadership, and / Continued support on facilitating effective coordination between Ministries Departments and Agencies.	Residual risk judged as Moderate

E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

Delivery performance
Delivery for the first year of the programme focused on the business forum and facilitation of trade and investment missions in UK. Delivery was improved due to joint planning and collaboration with both Rwandan stakeholders (government counterparts and the private sector), as well as both regional and UK based partners. The BHC Kigali also formed a core team to support a professional service provider deliver the business forum. As a results, all milestone targets for 2023/24 were achieved and some targets exceeded milestone. Having an event organiser lessened the burden on the programme implementing team.  There was a steep learning curve with the PCO – including on registration and badge production, website launch and management of contents as well as the delivery the main event day.
Commercial consideration
British High Commission Kigali contracted a Service Provider (Planitswiss Africa Ltd) in a competitive tender process through local procurement, to deliver on the UK-Rwanda Business Forum. The SP was from a credible Professional Conference Organiser company with extensive experience in preparing, managing and delivering business fora including the design of post forum follow-up process. The contract for Planitswiss Africa Ltd was 100% output based with payment linked to delivery of key milestones linked to Business forum such forum registration and promotion, and preparation for forum delivery. Despite the challenging timing of the business forum (summer and Christmas holidays which put considerable pressure on the BHC Kigali team and the service provider), and the scale of the event exceeding initial expectations, the supplier managed to meet the milestone targets.

Financial Performance
Planitswiss Africa Ltd designed a tailored budget management tool, which helped to forecast for business forum and improve the quality of financial management. The total budget for the business forum was £174,751 (of which £121,043 was managed by Planitswiss Africa Ltd for business forum and £53,708 by Radisson Blue and convention Centre for venue, accommodation and meals). There was a negligible variance as most of the payments were milestone based.
F: Monitoring and Evaluation

The programme does not have a monitoring and evaluation process in place now. Considering the nature of in trade and investment deals – which in most cases do not materialise immediately, the programme would benefit from a monitoring systems / mechanisms that allows for the tracking deals, ensuring attributions, as well as updating of LogFrame appropriately.