Business Case
Summary Sheet

Portfolio/ Business/Country Plan Summary: The International Finance Division Business Plan sets out that more climate finance needs to flow to developing countries to meet urgent mitigation and adaptation challenges, and that MDBs must play their part by scaling their climate finance. We plan to innovate, engage, and reform accordingly. A $300m UK guarantee to the Asian Development Bank will increase its climate lending by over $1.8bn to the region, as part of a broader guarantee unlocking up to $15bn.

Title: / UK guarantee support to The Asian Development Bank’s Innovative Financing Facility for Climate in Asia and the Pacific.
Programme summary / The Innovative Financing Facility for Climate in Asia and the Pacific (IFCAP) is a new multi-donor financing mechanism being established by the Asian Development Bank (ADB). Through IFCAP, development partners will be able to contribute a combination of grants and guarantees to the ADB, which will unlock new climate-focused lending from the Bank. The proposed $300m UK guarantee to support IFCAP would unlock up to $1.8bn of additional, affordable climate finance from the ADB for middle-income countries in Asia and the Pacific.
What is the rationale for UK Aid spending? / Multilateral Development Bank (MDB) Guarantees have become an increasingly important part of the FCDO’s toolkit for supporting middle-income countries. No Official Development Assistance (ODA) is scored up front when a guarantee is issued. ODA is only scored if a guarantee is called, meaning that guarantees can mobilise large volumes of financial assistance without immediate trade-offs with the UK’s grant support for the poorest countries. The Preferred Creditor Treatment (PCT) of the MDBs reduces the risk associated with MDB guarantees. / The proposed $300m guarantee to support ADB’s new IFCAP initiative is closely aligned with the FCDO/UK policy priorities and wider HMG programmatic work within the region. It will mobilise a large volume of climate finance, focused on both adaptation and mitigation, for countries in the Indo-Pacific region. These countries are home to large numbers of poor people and face large financing gaps to address the challenges caused by climate change.
Programme Value: A guarantee worth up to $300m. The guarantee has no DEL cost unless called. The expected loss from the guarantee is approximately £136m. This Business Case also requests up to £100,000 of RDEL expenditure for legal costs of setting up the guarantee.		Country/ Region or Sector: / Indo-Pacific Region; approximately 20 middle-income countries in the region will be eligible to benefit.
Department/Country Office confirmation of review processes		Phil Stevens, Director International Finance
Contact name		Josiah Littlehales, Dan Jollans
Threshold for final approval of Business Case: / FCDO Minister for Development and Africa, HM Treasury.
Date of Approval of Concept Note:	23 Jan 2023	Name and role of Approver: Andrew Mitchell, Minister of State for Development and Africa
Date of Approval of Business Case:	14 Sept 2023	Name and role of Approver: Andrew Mitchell, Minister of State for Development and Africa
Programme Code: 400072	AMP Start Date: Early 2024	AMP End Date: Approximately 2049.
Overall programme risk rating:	Moderate

## Strategic Case

The Problem Statement

The Indo-Pacific Region, which is home to many of the UK’s close partner countries, needs support to address the causes and consequences of climate change. Countries in the region face large financing gaps in their efforts on both mitigation and adaptation, which has significant implications for poverty in the region, the global fight against climate change, and other UK strategic priorities.

Climate change and environmental degradation acutely threaten development gains in the Indo-Pacific region. Estimates suggest that in East Asia and the Pacific, 7.5 million more people could fall below the extreme poverty line due to climate change by 2030, while the equivalent figure for South Asia is 35.7 million. This in a region which is already vulnerable; although poverty rates in many parts of the region have significantly reduced over the last two decades, compounding shocks of Covid-19, natural disasters, and elevated food prices means that poverty will not fall as fast as previously expected. In South Asia, the number of poor in the region at the low-income threshold (US$2.15/day, 2017PPP) is only expected to fall below 2019 levels by 2024.
[note] World Bank (2020), Revised Estimates of the Impact of Climate Change on Extreme Poverty by 2030.
[note] World Bank (2023), World Bank: East Asia and the Pacific Economic Update April 2023.
[note] World Bank (2023), World Bank: South Asia Economic focus, Spring 2023.

At the same time, Asia is the world’s largest emitter. Over half of global emissions come from Asia – and 44% of global emissions come from developing Asia –, and economic development and emissions reductions have often been considered competing priorities.
[note] CO2 emissions - Our World in Data
[note] Asia’s net-zero transition: Opportunity and risk amid climate action | McKinsey

Governments across Asia and the Pacific are stepping up commitments on climate and it is increasingly recognised as a priority for many in the region. Following the Paris Agreement, all parties in developing Asia and the Pacific have submitted National Determined Contributions (NDCs), in most cases these have either been updated or countries have submitted a second NDC. Equally many in the region are either considering or have announced net zero pledges.
[note] Asian Development Bank (2023), Asia in the Global Transition to Net Zero: Asian Development Outlook 2023 Thematic Report.
[note] Climate Analytics and NewClimate Institute: Climate Action Tracker.

However, there are still significant gaps between committed NDCs and tangible policies. UNESCAP estimates suggest that 65% of economies in developing Asia have yet to update existing strategies to support NDC implementation. This gap is often clearest in the power sector and the region accounts for 94% of the global coal-fired plants under construction, planned, or announced.
[note] UNESCAP (2022), 2022 review of climate ambition in Asia and the Pacific.
[note] Asian Development Bank (2023), Asia in the Global Transition to Net Zero: Asian Development Outlook 2023 Thematic Report.

The UK is already working closely with partners in the region…

The UK is strongly invested in the prosperity and resilience of the Indo-Pacific region; it is critical to our security, and our ambition to work with likeminded partners to promote democracy, human rights, and freedom. The Integrated Review Refresh confirms UK support for “a free and open Indo-Pacific” and that the UK will continue to “deepen relationships, support sustainable development and poverty alleviation, and tackle shared challenges including climate change”. It is imperative that the UK continues to focus on poverty reduction and responding to climate change in the region. As set out in Box 1, support to the Indo-Pacific Region and the importance of addressing climate change are at the heart of several key FCDO strategies.

Box 1: Alignment with existing FCDO strategies.
The International Development Strategy sets out key international objectives of the UK as a Patient Development Partner. These objectives include tackling climate change; supporting energy transition (including away from dependency on Russian fossil fuels); expanding infrastructure investment; and providing UK guarantees to unlock more affordable finance for partner countries. / The Integrated Review Refresh, which identifies the Indo-Pacific as a geographic priority region, notes that development reversals and climate change in the Asia Pacific region undermine HMG’s objectives for an open and stable international order. Its objectives include: promoting sustainable economic development, reforming and greening multilateral development banks to meet the needs of developing countries in dealing with the economic, debt, climate and nature crises; and delivering clean, green infrastructure and investment. / The FCDO’s SIDS Strategy, envisages that SIDS will be resilient to climate and economic shocks, with a sustainable pathway to graduate from ODA by 2030. Our strategic approach is to use both policy engagement and programmes to support sustainable economic diversification and improve climate and economic resilience, while showcasing how the rules-based international system can deliver for SIDS. / The FCDO’s Pacific Strategy sets out that the UK will step up our engagement as a long-term, honest, and reliable partner for Pacific Island Countries (PICs). Its objectives include strengthening climate resilience and the UK’s soft power offer. / The Strategic Framework for International Climate and Nature Action 2030 sets out our approach to tackling climate change and protecting nature globally. Its objectives include: taking urgent and ambitious measures to address climate change and biodiversity loss; accelerating the transition to clean energy; and highlighting the need for international cooperation, finance, and innovation to support the transition to a low-carbon economy. / The ASEAN-UK Plan of Action guides the implementation of the ASEAN-UK dialogue partnership. Its objectives include: cooperation to promote just energy transition; collaboration on just transition policies to ensure that workers and communities are not left behind; and promoting an increased flow of high-quality sustainable finance to support resilient infrastructure.
[note] HMG(2023), Integrated Review Refresh 2023: Responding to a more contested and volatile world.

The UK has a significant portfolio of programmes, investments, and initiatives in the region to address poverty and the interplay with both climate adaptation and mitigation. Key programmes include:

- The £274m Climate for a Resilient Asia (CARA) programme. This is a seven-year (2022-2029), £274m programme to help build the resilience of economies and vulnerable communities to climate change, improve the natural environment, and promote low carbon growth, across South Asia, South-East Asia, and the Pacific.
- The ASEAN Catalytic Green Finance Facility is a blended finance vehicle financing green infrastructure in the ASEAN region, and provides concessional loans (0% interest rate), alongside Asian Development Bank lending, to stimulate green infrastructure investment.
- Just Energy Transition Partnerships (JETPs) for which the UK – alongside other development partners – are providing financial and technical assistance to support decarbonisation in large developing economies with significant emissions. For the Indo-Pacific region, we have provided $1bn guarantee to a World Bank project in Indonesia, and are working with partners and the Government of Vietnam to establish a package of support there.
- The £20m ‘Pacific Clean Energy Programme’ (PCEP) which aims to increase access to affordable and reliable electricity.
- The £38.5m ‘Asia Regional Trade and Connectivity Programme’ (ARTP) which aims to promote regional connectivity and trade, including energy trade, in South Asia.
- A (forthcoming) Indo Pacific Connectivity Programme, which is currently under development (concept note stage), will aim to regional economic connectivity and trade, including in renewable energy.

In addition, we are progressing key bilateral policy initiatives and innovations to help generate climate impacts on the continent. This includes:

- A Bangladesh-UK Accord on Climate Change which aims to work bilaterally to deliver the outcomes of COP26 and COP27.
- The 2030 Roadmap for India-UK Future Relations which aims to mobilise investment and channel climate finance towards the implementation of United Nations Framework for the Convention on Climate Change (UNFCC) and the Paris Agreement.
- A UK-Malaysia MOU aims to strengthen cooperation on climate action through the promotion of private sector involvement to accelerate a transition to a low carbon development path.

We also work centrally and through key institutions to deliver on our climate and development ambitions in the region. This includes through the multilateral agencies, including the multilateral development banks (MDBs), the vertical climate funds (including the Green Climate Fund, the Climate Investment Funds, and the Global Environmental Facility), as well as through British International Investment (BII), the Private Infrastructure Development Group (PIDG), and many others.

There is, however, a lot more to be done…

Globally, we have fallen behind on commitments to provide climate finance to developing countries. In 2009, at COP15 in Copenhagen, advanced economies agreed to pledge $100bn of climate finance per year by 2020. This target was unmet, and at COP21 in Paris, advanced economies agreed to extend this commitment to an average of $100bn climate finance p.a. to between 2020 and 2025. We are now playing catch up; At COP26 in Glasgow, the $100bn average target over 2020-2025 was reaffirmed, and a Delivery Plan was established to ensure this target will be met. We currently believe that the $100bn target will be met for 2022, and exceeded thereafter, meaning the average goal will be met and likely exceeded.

Recognising this, the UK is continuing to expand its offer of climate finance to help meet international targets, but there is catching up to be done. The UK has been a top-5 donor on International Climate Finance over 2016-2020, providing £5.8bn climate commitments over the 5-year period. We have since doubled our own International Climate Finance (ICF) commitments, to £11.6bn over 2021-2026. This latest commitment, which equals circa $3bn p.a. climate finance from the UK, further solidifies the UK as a key provider of climate finance. We are strongly engaging in negotiations on a New Quantified Goal on Climate Finance. The financing needs, however, remain huge.
[note] See OECD analysis – Workbook: Climate-Related Development Finance Recipient 2020 (tableau.com)

Even more ambition is needed, however, as the risks associated with global warming continue to accelerate. According to the latest Intergovernmental Panel on Climate Change (IPCC), the world will face severe climate risks before the end of this century, even under a low emission scenario. However, the financing gap for developing countries is large. Estimates suggest that annual financing needs for both adaptation and mitigation are $1.2 - $1.7 trillion dollars for 2030.
[note] IPCC (2022), Climate Change 2022L Impacts, Adaptation, and Vulnerability.
[note] There are several estimates of global climate financing needs. LSE estimates that the financing gaps are $1.2 - $1.7 trillion for 2030 and estimates from Beyond the Gap are $1.5 trillion for 2030, while World Bank’s CCDR’s estimate annual climate-related investments are $783bn per year, albeit with differences in scope and ambition of the scenarios which don’t make it directly comparable.

Asia and the Pacific is critical to the prospects of meeting the temperature goals of the Paris Agreement (1.5°C) and accounts for an increasing share of global greenhouse gas (GHG) emissions. Developing Asia’s share of GHG emissions has risen to 44% in 2019, from 22% in 1990. Estimates suggest that the region by itself would exhaust the remaining carbon budget consistent with a warming to 1.5°C by 2040. Significant additional investment in areas such as energy transition and nature-based emission capture solutions is therefore required.
[note] Asian Development Bank (2023), Asia in the Global Transition to Net Zero: Asian Development Outlook 2023 Thematic Report.
[note] UN ESCAP (2021), Is 1.5°C within Reach for the Asia-Pacific Region? Ambition and Potential of NDC Commitments of the Asia-Pacific Countries?

The majority of the above investment needs in the region are for mitigation investments, in order to reduce emissions in line with the Paris Agreement. This amounts to an additional c. $200bn per annum primarily needed in the power sector (investments in renewable energy, smart grids, and energy efficiency) as well as the transport sector (through shifts to less carbon-intensive modes of travel).

The cost of meeting the Indo-Pacific region’s infrastructure needs is estimated to be around $1.7tn annually through to 2030. This is up from $1.5tn annually for consideration without climate adaptation and mitigation considered (i.e. a pre-Paris Agreement business-as-usual). This equates to annual investments of around 5.9% of GDP, although this increases to around 9% in the Pacific and South Asia, and is about double current levels of investment. This highlights the scale of additional climate finance needs, to address both mitigation and adaptation, which are considered in turn.
[note] Meeting Asia's Infrastructure Needs | Asian Development Bank (adb.org)

Asian and Pacific countries are vulnerable to the risks and socioeconomic impacts of climate change. Alongside mitigation, the region requires investment in adaptation; its large populations, many of which are concentrated in coastal zones, are vulnerable to the impacts of climate change. According to the 2021 Climate Risk Index (Figure 1), six out of the top ten countries most affected by weather-loss events (floods, heat waves, storms etc) between 2000 – 2019 were in Asia. The main source of loss in the region is caused by flooding and the frequency of extreme rainfall is rising in Asia. Of the top 30 cities in the world with the poorest air quality in 2020, 26 are in South Asia. Of the top five most polluted countries in the world (by Particulate Matter (PM2.5)) in 2020, four are in South Asia – Bangladesh, Pakistan, India, and Afghanistan.
[note] Germanwatch (2021), Global Climate Risk Index 2021.
[note] WMO (2022), State of the Global Climate in 2022.
[note] IQAir (2022), World's Most Polluted Cities in 2020 - PM2.5 Ranking, https://www.iqair.com/world-most-polluted-cities.
[note] IQAir (2022), World's Most Polluted Countries in 2020 - PM2.5 Ranking, https://www.iqair.com/world-most-polluted-countries.
[note] PM2.5 is used when describing pollutant levels both outdoor and indoor, where health impact from exposure considers amount of PM2.5 over a 24-hour period.

Figure 1: Map of the Global Climate Risk Index 2000 – 2019
Source: Germanwatch (2021)

We know that investments in addressing climate change are money well spent...

Evidence shows that the returns to investing in adaptation can be much larger than avoided losses. Commonly referred to as the ‘triple dividends’, investment in adaptation can result in avoided losses (first dividend), induced economic or development benefits (second dividend), and additional social and environmental benefits (third dividend). Using this approach can yield returns to adaptation investment with much higher cost-benefit ratios. Despite this, there is a significant shortfall in adaptation financing for developing countries, at approximately 5 to 10 times greater than the current international adaptation flows. This is forecast to widen further, to be in between $79bn to $612bn across developing countries to 2030; of which South Asia and East Asia and the Pacific have the highest median estimates of $59bn and $69bn, respectively.
[note] World Resources Institute (2022), The Triple Dividend of Building Climate Resilience: Taking Stock, Moving Forward.
[note] UNEP (2022), Adaptation Gap Report 2022: Too Little, Too Slow – Climate Adaptation Failure Puts World at Risk.

The economic costs of environmental damage in the region are severe. One estimate suggests that GDP losses would be 24% across developing Asia by 2100, 35% in India, 30% in Southeast Asia, and 24% in the rest of South Asia in a high emission scenario. World Bank analysis suggests that in the absence of major adaptation efforts GDP losses could range from 5-20% by 2100 across the region. These are most severe in the Pacific Island Countries (PICs) with annual losses estimated to be 2% of GDP as rising sea levels threatens the existence of entire low-lying atoll island nations, such as Kiribati, Marshall Islands, and Tuvalu. These are likely underestimates, particularly given the methodological challenge of capturing losses from extreme events and non-linear impacts as "tipping points" are reached.
[note] Another study by Guo et al (2021) project GDP losses between 11-14% relative to a scenario without climate change. These are far greater in developing countries vis-à-vis developed and large across Asia (For Example, 33-36% in Thailand, Malaysia, and the Philippines).
[note] Asian Development Bank (2023), Asia in the Global Transition to Net Zero: Asian Development Outlook 2023 Thematic Report.
[note] World Bank (2023), World Bank: East Asia and the Pacific Economic Update April 2023.
[note] World Bank (2023), World Bank: South Asia Economic focus, Spring 2023.
[note] World Resources Institute (2022), The Triple Dividend of Building Climate Resilience: Taking Stock, Moving Forward.

In poverty terms, the potential impacts of climate change in the region are severe – risking over 40 million additional people (or a doubling in total headcount) in poverty by 2030 as a result of unabated climate change. This number justifies filling the significant investment gap (c. $40bn p.a.) in climate adaptation, to minimise the potential poverty costs of climate change in the region. In parallel, the case for climate mitigation investment also goes hand-in-hand with poverty reduction: the infrastructure needs explored above are compatible with full decarbonization need not cost more than more-polluting alternatives, while they can achieve key Sustainable Development Goals in-country —universal access to water, sanitation, and electricity; greater mobility; improved food security; better protection from floods; and so on.
[note] World Bank Document
[note] Beyond the Gap: How Countries Can Afford the Infrastructure They Need while Protecting the Planet (worldbank.org)

…and that the Multilateral Development Banks have a critical role to play in addressing these challenges.

The Multilateral Development Banks (MDBs) are the largest providers of climate finance to developing countries. The MDB’s operate by leveraging the capital contributions of their shareholders to invest 4-5 times shareholders’ initial investments. They are owned by their member countries, have AAA credit ratings, and have high standards of governance. Their high capacity and large size (the Asian Development Bank lends over $20bn to the region each year) make the MDBs an essential part of the international climate finance system.

As a shareholder at seven of the major MDBs, the UK has been consistently working to support a dramatic scale up in the quality and quantity of MDB climate finance. The UK’s leadership on climate finance in the MDB system goes beyond our own direct contributions to the Bank. We have long championed greater climate ambition through our delivery partners and on engaging the private sector to support decarbonisation, clean growth, and investing in adaptation and resilience. We have utilised our position on the Boards of the MDBs to drive the system to deliver more climate finance. This was a particular push during the UK’s COP Presidency, and we successfully worked with other partners to update ambition and goals for climate finance from the International Financial Institutions. In 2021 (latest data), the MDBs collectively delivered over $50bn to low- and middle-income countries.

The Asian Development Bank (ADB) is the largest MDB across Asia and the Pacific. In 2021, it committed $22.8 billion in loans, grants, equity investments, private sector programs, and technical assistance both to the public and private sectors of its borrowing members. Its largest five borrowers in 2021 were Pakistan, the Philippines, Bangladesh, India, and Indonesia. It provides predictable and substantial long-term financing to support low- and middle-income countries. ADB provides a unique regional perspective combined with a strong country presence and client relationships built over many years of engagement.

ADB is a significant provider of climate finance. It provided over $7bn of climate finance commitments in 2022, and over $25bn over the last four years. Around three-quarters of this was for mitigation, and one-quarter adaptation. At COP26, ADB announced its ambition to commit $100bn in climate finance projects between 2019-2030 (an increase on its previous target of $80bn). This will require a doubling of its climate finance commitments in the second half of this decade, vis-à-vis what it achieved between 2019 and 2023.

There is scope for the ADB to strengthen its offer on climate finance further. The ADB has pledged to become the “climate bank of Asia”. We are supportive of this, though we believe that there is much more that it should be doing. Primary areas to strengthen ADB’s quality of finance include: reviewing its climate co-benefits methodology to incentivise highest-impact, mainstreaming nature in line with the COP26 Nature Joint Statement and creating a nature/biodiversity mainstreaming strategy, full Paris Alignment of its operations by 2025, updating approach to vulnerability, provision of climate resilient debt clauses in its financing, and phasing-out coal in the region. Given its clientele (typically wealthier than the African Development Bank’s or World Bank’s typical borrower, more populous and higher emitting), we feel that ADB needs to push to become more ambitious on its climate finance offer.

The UK is pushing for the reforms of the international financial architecture, including the MDBs, which are needed to deliver the SDGs and unlock the financing needed to address climate change. Box 2 sets out key UK priorities, which fit well with similar reform agendas such as the Bridgetown Initiative, the World Bank Evolution Roadmap, the UN’s SDG Stimulus Plan. Progress made so far, such as initial MDB commitments to unlock approximately $200bn over the next ten years through implementing the recommendations for the G20 Review of Capital Adequacy Frameworks (CAF review), is a promising start but much more is needed.

Box 2: UK Priorities on International Financial Institution (IFI) reform)
The UK’s efforts on IFI reform are focused on delivering a bigger and better international financial system. The UK’s top priorities for IFI Reforms are: / Stretching MDB balance sheets to increase their scale and financing volumes across the spectrum. This can be achieved by: implementing CAF review reforms, increasing the size of IDA, and channelling Special Drawing Rights (SDRs) to vulnerable countries. / Reforming the IMF’s toolkit, especially for the poorest countries. This can be achieved by, amongst other actions, raising IMF access limits under the Poverty Reduction Growth Trust (PRGT) – the IMF’s fund for the poorest countries - and raising new PRGT funds. / Building a shock responsive international financial system. This could be delivered by encouraging faster uptake of Climate Resilient Debt Clauses (CRDCs) and strengthening Disaster Risk Financing to help countries better prepare for and pay for disasters, including by implementing and scaling up a new Global Shield against climate risks. / Mobilising more private capital. We want MDBs to develop more ambitious strategies for countries to mobilise more private investment - especially for climate transitions - by developing innovative new vehicles, transferring more risk to the private sector, and building the pipeline of bankable deals.

The Capital Adequacy Framework Review is a key element of our reform priorities, and the ADB are engaging and responding positively with its findings. Its proposals to remove its Sustainable Lending Limit (SLL) policy and changing its capital adequacy framework could unlock around $11bn additional annual finance to support climate and development projects in the region. Further measures, including donor-backed guarantees, would increase this further. The World Bank is also including donor guarantees as part of a package of measures in their response to the CAF, and we expect that other MDBs will take a similar approach.

The UK is also supporting the MDBs bilaterally to scale up their commitments on climate finance. At COP26, the UK announced support for the $2bn Room to Run guarantee, which is supporting the African Development Bank (AfDB) to deliver an additional $2bn of climate finance to Africa. In the last two years the UK has also committed loan guarantees to support $1bn of additional climate-focused lending to each of South Africa (via the AfDB), India (via the World Bank) and Indonesia (via the World Bank). The UK has also committed $5bn in loan guarantees to scale up MDB lending to Ukraine.

We are encouraging other donors use guarantees to further increase MDB lending. Increased use of guarantees was a recommendation of the CAF review and, if taken up by a range of donors, has the potential to mobilise tens of billions of additional MDB climate finance. Japan has recently committed guarantees to support the World Bank in Ukraine and the US has committed a $1bn guarantee to support the World Bank’s support for Indonesia’s Just Energy Transition Partnership (JETP).

The proposed intervention aims to address the financing needs of partner countries in the Indo-Pacific through a UK portfolio guarantee.

This Business Case proposes a $300m UK guarantee contribution to the ADB’s new Innovative Financing Facility for Climate in Asia and the Pacific (IFCAP). Through IFCAP, which the ADB launched at its May 2023 Annual Meeting, development partners can provide grants and/or guarantees to the ADB to enhance the Bank’s climate finance capacity. Contributions to IFCAP will partially protect the ADB against losses on a Reference Portfolio of loans for the next 20 years; by protecting the ADB against these risks, IFCAP will enable the Bank to make new climate-focused loans.

Through the IFCAP mechanism development Partners will provide first loss portfolio credit protection to the ADB. In the event of a default to ADB by a country in the reference portfolio (i.e. a non-payment lasting over 180 days), IFCAP partners will cover 100% of losses up to an overall pre-defined cap (for which losses will be shared pro-rata, so if the UK provides 10% of the total guarantee, we would bear 10% of the losses up to the cap). Once the cap is reached, all losses will be absorbed by the ADB.

This first loss structure will provide powerful credit relief to the ADB, allowing them to increase climate finance by around $4 for every $1 guaranteed through IFCAP. This high leverage is achieved by guarantors – with strong AAA-AA credit ratings – significantly reducing ADB’s risk exposure to some of its riskiest borrowers (more detail in the Financial Case). IFCAP will protect ADB against short-term losses on a large section of its portfolio, unlocking its resources to be used elsewhere.

The current Reference Portfolio for IFCAP is shown in Table 1. The mechanism will protect the ADB against losses in 29 countries. For example, the mechanism will cover ADB for up the first $888m of losses on its lending to India (or approximately 5% to the ADB’s total India loan portfolio). The Reference Portfolio describes the risks that the IFCAP will take off the ADB balance sheet, it does not dictate where the new climate finance unlocked by IFCAP will be targeted. It is likely that the exact composition of the Reference Portfolio will change before the final IFCAP structure is finalised.

Although the total volume of lending covered by the IFCAP guarantee will be approximately $9bn, the maximum pay-out under the guarantee will be determined by Development Partner (guarantor) contributions and will be significantly less than $9bn. The reference portfolio sets out a series of country caps (e.g., $888m for India, $951m for Bangladesh) but IFCAP will also have a maximum payout cap determined by the value of guarantees provided by Development Partners. For example, if Development Partners provide $2.5bn in guarantees, then payouts will not exceed $2.5bn. If the UK provides a $300m guarantee, the most the UK could be required to pay out is $300m. The Financial Case sets out the workings of the guarantee in detail.

The ADB aims to generate $10bn - $15bn of new climate finance through the IFCAP mechanism. The structure of the guarantee (which means $4 of new finance can be unlocked for every $1 guaranteed) and the involvement of multiple donors means that IFCAP can drive a very significant scale-up on ADB climate lending. As set out in the Appraisal Case, the final volume of ADB climate finance mobilised will depend on the structure of the mechanism and the scale of development partners’ contributions. We judge that UK technical and financial support to the development of IFCAP is the best available way for the UK to deliver the scale of climate finance needed in the Indo-Pacific region.

Table 1: The IFCAP Reference Portfolio
Country	Exposure / $m	% of total ADB Exposure to Country	Credit Rating			Region
			S&P	Moody's	Fitch
India	888.1	5%	BBB-	Baa3	BBB-	South Asia
Pakistan	1,311.5	7%	CCC+	Caa3	CCC-	South Asia
Bangladesh	951.0	8%	BB-	Ba3	BB-	South Asia
Indonesia	419.2	8%	BBB	Baa2	BBB	South-East Asia
Philippines	1,383.3	8%	BBB+	Baa2	BBB	South-East Asia
Uzbekistan	1,142.3	19%	BB-	B1	BB-	Central Asia
Nepal	527.7	29%	CCC			South Asia
Georgia	373.9	28%	BB	Ba2	BB	Central Asia
Vietnam	139.8	12%	BB+	Ba2	BB	South-East Asia
Cambodia	396.2	29%		B2		South-East Asia
Mongolia	403.6	26%	B	B3	B	Central Asia
Papua New Guinea	446.2	29%	B-	B2		Pacific
Thailand	82.5	2%	BBB+	Baa1	BBB+	South-East Asia
Turkmenistan	81.3	41%			B+	Central Asia
Azerbaijan	66.8	18%	BB+	Ba1	BB+	Central Asia
Timor-Leste	39.0	42%	CCC			South-East Asia
Kyrgyz Republic	127.8	28%		B3		Central Asia
Kazakhstan	26.7	18%	BBB-	Baa2	BBB	Central Asia
Armenia	26.6	15%	B+	Ba3	B+	Central Asia
Bhutan	29.6	28%	CCC			South Asia
Lao, PDR	90.0	20%		Caa3	CCC-	South-East Asia
Solomon Islands	12.6	31%		Caa1		Pacific
Maldives	17.7	14%		Caa1	B-	South Asia
Fiji	6.5	19%	B+	B1		Pacific
Palau	7.7	31%	CCC			Pacific
Cook Islands	1.5	28%	B+			Pacific
Vanuatu	0.4	26%	CCC			Pacific
Tonga	0.4	4%	CCC			Pacific
Samoa	0.3	2%	CCC			Pacific
Total	9,000.0

The Founding Partners of IFCAP are expected to be the US, Japan, Korea, Sweden, Denmark, Italy, and the UK. The US and Japan are expected to be the largest guarantors of IFCAP. Japan has also committed some grant funding (which will be used for activities such as project development). Korea has already committed a $100m guarantee to support IFCAP. Sweden and Denmark are smaller partners but have been important partners in discussion. Italy is expected to make a commitment from their new climate fund. Overall, including the proposed $300m contribution from the UK, we expect the Founding Partners of IFCAP to provide guarantees worth between $2bn-$3bn in total.
[note] Sweden are experienced guarantors, albeit usually providing smaller scale project-focused guarantees. Denmark is just opening their guarantee agency.

A UK guarantee contribution to IFCAP will deliver high-quality climate finance to the Indo-Pacific Region at scale…

Figure 1 shows the ADB’s expected climate finance commitments with and without IFCAP over the proposed investment period (2024-2028) in best- and worst-case scenarios. The variance in the forecasts under these scenarios is explained primarily by anticipating the amount of financing capacity that may have to be directed towards large and unforeseen future shocks, such as another global pandemic. Under each scenario, IFCAP unlocks c. $12bn additional climate finance.

This additional climate finance will enable the ADB to significantly exceed its ambition of $100bn climate finance between 2019-2030 in the best case scenario, and meet its ambition under the worst case scenario. Estimates of total climate finance form 2019-2030 range from $100bn to $113bn (Figure 2).

Figure 1: Estimated impact of IFCAP on ADB climate finance commitments, USDbn
Source: ADB
Best Case Scenario
Worst Case Scenario
Figure 2: ADB Cumulative Climate Finance 2019-2030, USDbn
Source: ADB
Best Case Scenario
Worst Case Scenario

Countries across the Indo-Pacific will benefit from the unlocked lending. The countries which we expect to benefit are set out in Table 2. The cost at which additional lending will be provided depends on which lending group a country is in. Group B countries have access to blend financing terms (25-year loans, 5-year grace periods, interest rate of base rate+2%) whereas Group C countries face more expensive (but still very affordable relative to capital markets) terms (up to 19-year loans, no grace periods, base rate+1-2% interest).

Table 2: Countries benefiting from IFCAP
Country	ADB Lending Group	High Risk of Debt Distress	Income Classification
Bangladesh	B	No	LMIC
Mongolia	B	No	LMIC
Pakistan	B	Yes	LMIC
Palau (S)	B	No	LMIC
Papua New Guinea (F)(S)	B	No	UMIC
Timor-Leste (F)(S)	B	No	LMIC
Uzbekistan	B	No	LMIC
Fiji (S)	C0	No	UMIC
Sri Lanka	C0	Yes	LMIC
Vietnam	C0	No	LMIC
Cook Islands (S)	C1	No	n/a
Georgia	C1	No	UMIC
India	C1	No	LMIC
Indonesia	C1	No	UMIC
Philippines	C1	No	LMIC
Armenia	C2	No	UMIC
Azerbaijan	C2	No	UMIC
Thailand	C2	No	UMIC
Turkmenistan	C2	No	UMIC

(S) Small Island Developing State, (F) Fragile Conflict Affected State

IFCAP will primarily deliver additional adaptation finance, complementing the mitigation finance which ADB already provides. In addition to the scale of additional financing, a key objective for the UK was to secure significant increases in climate finance directed towards adaptation and resilience. Under best- and worst-case scenarios, around two-thirds of IFCAP climate finance will be used for adaptation and resilience investments, which will also imply a greater focus of funding to the more climate-vulnerable countries in the region. This will substantially support, although not yet fully deliver, the UK ask for a 40% climate adaptation target from the ADB.

ADB Climate Finance has achieved significant results over recent years. Its headline targets – covering mitigation, adaptation, and nature – have been met or exceeded, and include over 12 megatonnes of CO2 reduced in 2021, nearly $2.5bn additional climate finance mobilised, over 750,000 supported with resilience to climate and natural disasters, and nearly half a million hectares of terrestrial, coastal, or marine areas restored or enhanced (Table 3). These results are just the tip of the iceberg with regards total impact needed in the region (as explored above); however, the ADB plays an important standard-setting role and one that can mobilise the private sector to enable much more climate finance and impact.

Table 3: ADB’s Climate Targets and Results, 2021
Measure	2021
Mitigation
Total annual greenhouse gas emissions reduction (tCO2e/year)	12,742,648
Additional climate finance mobilized ($)	$2,405,255,000
People with increased capacity in implementing mitigation and low-carbon development actions (number)	3032
Low-carbon infrastructure assets established or improved (number)	19
Installed renewable energy capacity (megawatts)	678.28
Low-carbon solutions promoted and implemented (number)	7
Resilience
People with strengthened climate and disaster resilience (number)	762,580
Area with reduced flood risk (hectares)	2,941
Gender-inclusive climate and disaster resilience capacity development initiatives implemented (number)	4
Financial preparedness instruments provided (number)	2
National and subnational disaster risk reduction and/or management plans supported in implementation (number)	15
New and existing infrastructure assets made climate and disaster resilient (number)	71
Environment
People benefiting from strengthened environmental sustainability (number)	3,421,768
Pollution control enhancing infrastructure assets established or improved (number)	135
Solutions to enhance pollution control and resource efficiency implemented (number)	17
Terrestrial, coastal, and marine areas conserved, restored, and/or enhanced (hectares)	495,198
Solutions to conserve, restore, and/or enhance terrestrial, coastal, and marine areas implemented (number)	13
Sustainable water–food–energy security nexus solutions implemented (number)	7

A UK contribution to IFCAP is an opportunity to magnify UK impact in the Indo-Pacific by working with the ADB and other Development Partners…

Working with other donors significantly increases the size and impact of this climate-focused guarantee. Previous UK MDB guarantees have mobilised $1bn-2bn; the combination of Development Partners supporting IFCAP means that there is potential to mobilise up to $15bn through a single mechanism. The UK has provided more MDB guarantees than any other Development Partner (see Box 3) and FCDO expertise has played a leading role in shaping the final structure of the IFCAP mechanism. As set out in the Appraisal Case, UK involvement in IFCAP is a very good value way to deliver the climate finance needed to the Indo-Pacific region, as well as some broader climate finance targets (e.g. $100bn pledge and doubling adaptation finance) at an affordable cost to the UK.

Box 3: UK Experience using MDB guarantees
Over the last 2 years, FCDO has scaled up its MDB guarantee portfolio from less than $1bn of exposure to over $10bn of potential exposure. The UK has committed $4.6bn in new MDB guarantees to support African and Asian Countries as well as up to $5bn in new guarantees to support World Bank lending to Ukraine. / The FCDO guarantee portfolio includes a diverse mix of guarantees. In 2021, the UK announced its first portfolio guarantee; the $2bn Room to Run portfolio guarantee protects the African Development Bank against losses on a portfolio of 11 African Countries. In 2021 and 2022, the FCDO announced new guarantees to support World Bank lending to India under the India Green Guarantee and to Indonesia and South Africa under the Just Energy Transition Partnerships (JETPs). / The UK’s leadership on providing guarantees to the MDBs has had a demonstration effect. Other guarantors, including Japan and the US are now committing MDB guarantees for the first time. The FCDO’s experience designing and negotiating guarantee agreements with the MDBs has already been valuable in the case of IFCAP.

The other Development Partners involved in IFCAP are all close partners of the UK. IFCAP offers an opportunity to work with traditional UK Development Partners such as the US, Italy, and Sweden, but also newer partners such as South Korea. The UK Indo-Pacific Strategy notes that increasing UK’s international and development engagement with Korea and Japan are two key areas for the UK to strengthen.

The close alignment between IFCAP partners makes it straightforward to address geopolitical considerations. We have ensured that the lending unlocked by the UK (as well as all other Founding Partners) will be directed to ADB’s less wealthy and most vulnerable countries (by excluding ADB’s wealthier borrowers – China, Kazakhstan, and Malaysia – from any of the unlocked lending). A significant share of the mitigation lending unlocked will go to emerging economies with large populations and growing emissions (such as Pakistan, Bangladesh, Vietnam, the Philippines, India, and Indonesia) which will complement our existing work on JETPs and Middle Ground Powers. We are also working to ensure that the poorest and most vulnerable countries in the region (such as Small Island Developing States (SIDS) and vulnerable countries in South Asia also benefit from IFCAP: ensuring that a high proportion of the unlocked lending will be directed towards adaptation investments is a key mechanism through which this will be delivered.

Through IFCAP, the UK is also engaging closely with the ADB on the design and implementation of its Climate Change Action Plan (CCAP) and wider programmatic work. The CCAP, which will be put to the ADB’s Board in September 2023, is the Bank’s central climate change strategy. The UK’s early support for IFCAP has already provided a valuable opportunity to work with the Bank on its CCAP, which will have wide-reaching consequences for the ADB’s climate finance (i.e. beyond the $15bn unlocked by IFCAP). IFCAP is proving a useful reason for the UK’s voice to be heard. UK priorities for the CCAP are that the Bank should: (1) review its climate co-benefits methodology to incentivise highest-impact, mainstreaming nature in line with the COP26 Nature Joint Statement and creating a nature/biodiversity mainstreaming strategy, (2) ensure full Paris Alignment of its operations by 2025, (3) update its approach to vulnerability including by allocating and pricing its finance to reflect it, providing climate resilient debt clauses in its financing, and (4) supporting coal phase-out in the region. Ensuring that these objectives are met will be factored into our decision on when and how to commit UK support to IFCAP. Additionally, the UK is mindful of wider UK programmatic and research work within the region and aims to maximise impact and lessons learnt into IFCAP.

Compliance with UK legislation: standards, safeguards and equalities

As an ADB shareholder, the UK has regular discussions with the ADB about governance standards, the quality and inclusiveness of programmes, and risk. This includes at the Board – where we are permanently represented by a UK Official – and through year-round engagement between the UK and ADB management, as well as other shareholders. Following the Programme Operating Framework’s guidance, IFCAP meets and exceeds minimum legislative criteria:

  1. Counter-terrorist Financing and Anti-money Laundering: Recognising the obligations of ADB’s member countries under various United Nations Security Council Resolutions to take measures to prevent the financing of terrorism, ADB undertakes to use reasonable efforts, consistent with the Agreement Establishing the Asian Development Bank (the ADB Charter) and policies, including those pertaining to combating the financing of terrorism, to ensure that funds provided under any arrangement are used for their intended purposes and are not diverted to financing of terrorism; nor are they used directly or indirectly, to provide support to individuals or entities associated with terrorism.

  1. Public Sector Equality Duty: Our ADB shareholding role and responsibilities, our potential contribution to IFCAP, and the UK’s contribution to ADF is also in line with UK’s guidelines on “Overseas Security and Justice” and the Public Sector Equality Act, as the Bank has policies and procedures that follow international best practice and obligations in respect of race, disability and gender. We use the ADB Board to voice concerns about human rights, alleged discrimination, social and economic inclusion and environmental concerns as part of the broader social and environmental safeguards for programmes and projects over the full project cycles. The ADB is currently reviewing its safeguards policy. The have particular expertise to share on tackling SEAH, which is overall the top UK safeguarding priority, with a UK SEAH 2020 Safeguarding Strategy that outlines our approach and principles, as well as a dedicated FCDO team to lead on SEAH safeguarding across UK programs and at international organisations.

  1. Climate and Environment: ADB is currently developing its approach to Paris Alignment, drafting its first ever Climate Change Action Plan (CCAP) and reviewing its safeguards policy which will provide operational guidance for implementing climate change projects. ADB has already committed to being and in full compliance with it by end-2023 (for sovereign lending) and end-2025 (for non-sovereign operations). IFCAP goes beyond ADB’s Paris Alignment, though, as it will specifically target ambitious climate projects and policies in the region to reduce emissions (focused on renewable energy and coal decommissioning) and scaled-up investments in adaptation to strengthen resilience.

  1. Partnership Principles: ADB is a key delivery partner for the UK and the UK’s ODA budget. We have long partnered with the bank to deliver development programmes. In addition, the Founding Partners of IFCAP are likeminded countries seeking to deliver climate and development programmes together. New governance structures and reporting mechanisms will be established under IFCAP, which are detailed in the Management Case.

  1. Gender and Disability: Climate change will fall disproportionately on women, poor and marginalised people, including people with disabilities. FCDO has committed to making social inclusion and leaving no one behind at the centre of what we do, notably through the international women and girls strategy (March 2023) and the Disability Inclusion and rights Strategy (February 2022). The ADB’s Corporate Results Framework incentivises the Bank to focus on disability in its projects, which IFCAP will also abide by, and we are lobbying for a target to be set. The ADB includes gender equality as one of its Strategy 2030 operational priorities, with its own operational plan for 2019-2024 under the strategy. ADB recognises the need “to strengthen assessment and management of gender risks in projects, and ensure meaningful consultation”. ADB has committed to further “support inclusiveness and do more to expand equitable opportunities for the most vulnerable groups, which include the poor, women, indigenous peoples, ethnic minorities, persons with disabilities, hard-to-reach and remote populations, migrants, and displaced and conflict-affected people” including though its infrastructure projects which will “improve access of the poor, women, and the vulnerable (including older persons and people with disabilities)”.

  1. Safeguarding: ADB core policies which have been found to be sound by DFID’s Central Assurance Assessment Enhanced Safeguarding Assessment of ADB. ADB’s existing safeguards statement was approved by the Board in 2009. The Bank decided to undertake a review of the policy following a May 2020 report by its Independent Evaluation Department. The review will be finalised in 2024 and the UK will play a leading role in shaping the new standards. FCDO will press for clear and transparent accountability processes for monitoring the implementation of the safeguards, with regular reporting to the Board including where breaches have occurred.

  1. Procurement: To ensure that ADB financing is used for its intended purpose and delivers successful development outcomes, the bank follows a set of core principles, including fairness, economy, efficiency, transparency, quality, and value for money. The ADB publishes an annual procurement report and reviews its procurement policy intermittently. The FCDO monitor any issues around procurement and work with other likemindeds on concerns raised in client countries.

  1. Risk: See Management Case for a full list of the risks for IFCAP.

## Appraisal Case

Options Appraisal

This appraisal case is structured around three questions:

  1. Is a guarantee through IFCAP an appropriate way to provide high quality climate finance at scale to middle-income countries in the Indo-Pacific region?
  2. How should IFCAP be designed to maximise value for money?
  3. How big should the UK guarantee contribution to IFCAP be?

Appraisal Question 1: Is a guarantee through IFCAP an appropriate way to provide high quality climate finance to the Indo-Pacific region at scale?

To answer this question, we worked through a range of potential options:

  1. Do nothing. As set out in the strategic case, there is a strong rationale for supporting climate action in the Indo-Pacific, for showing leadership in the UK support for the CAF review recommendations and to help further strengthen the ADB’s offer. It is likely that the IFCAP mechanism would be established without UK participation, partly due to the UK’s close engagement with the ADB on it to date, though withdrawing at this stage would marginally damage the UK’s credibility. On balance, we discount the option of doing nothing because the needs are so high and the opportunity cost of providing a guarantee (which does not require up-front DEL budget beyond legal fees) is affordable (see appraisal summary in table 5 below).

  1. Support a bilateral (or multi-donor) International Climate Finance project in the region. This option was quickly discounted due to the limited availability of UK ODA resources. UK ODA resources, where available, are typically being targeted at the World’s poorest countries. There is not budget available for the FCDO to use bilateral programming to directly provide the large-scale financial support needed by middle-income countries in the Indo-Pacific region. Furthermore, the UK does not have a sovereign lending instrument, and hence can only provide funding on grant terms which is not appropriate given these countries’ ability to repay this sort of finance. Alternative instruments, explored below, are more appropriate in this regard, and allow us to leverage and provide much more funding than we can provide directly through grants.

  1. General Capital Increase (GCI) at the ADB. MDB capital increases are a very efficient but resource intensive way to support more lending to partner countries. GCIs require all shareholders to contribute funds and typically happen every 5-10 years. A GCI is not currently being discussed at the ADB Board, and there is little appetite amongst shareholders. Capital Increase negotiations also tend to last several years, meaning that any agreement would delay new climate finance towards the second half of this decade. A GCI would support an increase in lending across ADB’s portfolio, not just its climate-focused operations. Furthermore, The UK is a 2% shareholder of ADB and as such our influence is limited; both Japan and the US are much larger shareholders, and we would typically need to follow their lead on anything as significant as opening a capital increase discussion. A GCI would also require a significant up-front investment of scarce ODA resources from the UK. This option was also discounted as unfeasible at this time.

  1. Multiple Single-Country MDBs Guarantees. At COP26 in 2021, the UK committed to guarantee $1bn of climate-focused World Bank lending to India. At COP27 in 2022, the UK committed to guarantee $1bn of climate-focused World Bank lending to Indonesia. One way to support the Indo-Pacific regions response to climate change would have been to support further single-country guarantees. Individual country guarantees could be closely targeted towards UK priority sectors and there would be a clear, strong narrative about UK attribution.

  1. IFCAP, the ADB’s proposed portfolio guarantee. At COP26 in 2021, the UK announced its first portfolio guarantee, the Room to Run initiative with the African Development Bank (AfDB). Portfolio guarantees support the MDBs to expand lending by protecting them against losses on a diverse portfolio of loans. For example, the Room to Run guarantee enables the AfDB to increase its climate finance by offering (partial) protection against losses on an 11-country portfolio of loans. Portfolio guarantees are an efficient tool for supporting the MDBs to increase lending at scale; rather than targeting constraints on a country-by-country basis, they support an MDB’s core balance sheet and allow a fast scale-up in lending.

On balance, we conclude that IFCAP is the best way to unlock additional high quality climate finance for the Indo-Pacific region at scale. Single-country guarantees are a useful tool for supporting specific sectors and partner countries – such as our experience with supporting high emitting countries’ transitions to clean energy through JETPs (see paragraph A7 and Box 3). A portfolio guarantee mechanism, such as IFCAP, is better suited to deliver greater scale and leverage across multiple countries and multiple sectors. It also enables contributions from multiple donors and is lower cost to administer. We judge it is the most effective instrument to bring in other donors and deliver affordable climate finance to a large set of countries at the large scale needed. It would complement our existing country- and sector-specific guarantees. A portfolio guarantee also presents an opportunity to strengthen the ADB’s climate policies centrally.

Appraisal Question 2: How should IFCAP be designed to maximise value for money?

There are a wide range of factors which determine the effectiveness of a mechanism like IFCAP. It is, for example, necessary to decide exactly what should be guaranteed, how long for and what commitments the ADB should make in return for donor contributions to IFCAP. In January 2023 we submitted a Concept Note for a UK guarantee contribution to IFCAP, which noted six areas where we wanted to see progress if a UK contribution to IFCAP was to offer value for money. Table 4 sets out progress made in each of these areas.

Table 4 – Progress on six design considerations highlighted in the Concept Note
Issue	Progress to-date
Governance. To design a governance structure which balances administrative simplicity (to reduce costs) with the need for UK influence over the unlocked funds and get credit for this with partner countries.	Achieved. Simple administrative structure obtained: guarantors will meet once, annually, to oversee IFCAP and provide strategic steers. No project-by-project approval, not lots of new overhead burdens or carve-outs. We proposed strong alignment to CCAP, which other guarantors have got behind.
Additionality. To ensure IFCAP expands additional Climate Finance beyond $100bn (or meets that target in a worst-case scenario).	Achieved. Latest IFCAP proposals are to expand climate finance to between $100bn-$115bn dependent on scenario. The UK has been recognised as the key voice in pushing for this.
Risk sharing. Important mechanisms for risk mitigation were diversification of the IFCAP loan portfolio (i.e. ensuring cover is split between at least 10 countries) and risk sharing with other partners, including other donors, the ADB itself (to mitigate moral hazard), and the private sector (where appropriate).	Partially Achieved. We have ensured that the IFCAP portfolio covers 29 countries, and 5-6 other guarantors (for now). The ADB remains involved as second-loss (so not taking as much risk as we had hoped) in return for greater leverage. We pushed for private sector participation but were informed we would also lose significant leverage if they were to be involved.
Country coverage. To ensure that the UK does not unlock additional finance is offered to ADB’s wealthier borrowers.	Achieved. We have ensured that no UK guarantee would provide new lending for ADB’s wealthiest borrowers. We have also ensured that we would not bear exposure to countries with key political or financial risk (i.e. in default) in the IFCAP portfolio.
Pipeline and capacity. To ensure that the Bank has sufficient capacity to deliver $10-15bn of high quality ADB climate finance, without risking debt sustainability or reduced quality of investments.	Partially Achieved, work in progress. ADB is setting out its CCAP which includes significant scaling of financial, political, and technical capacity to scale its climate operations. We believe this will ensure the capacity and pipeline for IFCAP to deliver quantity and quality of new climate lending. The recently-agreed partnership between ADB and the Private Infrastructure Development Group (PIDG – a specialist group of companies that provides upstream TA, investment, and credit solutions on infrastructure projects in developing countries, co-founded and co-funded by the UK) should help in this regard. We will continue to review pipeline, ADB capacity, and project quality as IFCAP is disbursed.
ADB reform. To secure commitment from ADB to implement other recommendations of the G20 MDB Capital Adequacy Frameworks Review, alongside UK support for IFCAP.	Partially achieved, work in progress. ADB have identified the potential for a substantial increase in total annual financing in response to the CAF Review – in the region f $10bn to $15bn. This will have significant impacts on ADB’s total climate financing and should enable the Bank to significantly exceed its $100bn ambition. IFCAP is a key element of the ADB’s response to the CAF review. There is room for the ADB to go further in its response to the CAF Review and this will remain a key priority for UK engagement with the Bank.

The other key design consideration referenced in the IFCAP Concept Note is the composition of the reference portfolio. The design of the IFCAP reference portfolio (current portfolio shown in Table 1) involves trade-offs. A higher-risk reference portfolio (e.g. a portfolio with significant exposure to Pakistan) creates a high expected loss for the UK and other Partners but generates high leverage (e.g. $6 of new lending unlocked for every $1 guaranteed). A lower-risk portfolio (e.g. a portfolio with less exposure to Pakistan) creates a lower expected loss but will have lower leverage (e.g. $4 of unlocked for each $1 guarantee). At the time of finalising this Business Case, the portfolio is still under negotiation.

The current IFCAP design is significantly riskier than previous guarantees the UK has provided. This is because of both the high-risk reference portfolio and first-loss structure of the guarantee. As set out in the Financial Case, the risks associated with IFCAP are considerable. For example, under the proposed $300m IFCAP guarantee, there is a 42% chance that over £100m will be demanded from the UK over the duration of IFCAP support, and a 72% chance of a demand of more than £50m. This high-risk structure is partly driven by the preferences of other IFCAP partners, who have a relatively high-risk appetite. It is not in the UK’s interest to significantly reduce the riskiness of the IFCAP structure as this would likely reduce the overall impact of the mechanism once other Development Partners’ preferences are considered.

The current IFCAP design also delivers higher leverage than any other guarantee the UK has provided. We expect the final IFCAP structure to mobilise around $4 for every $1 of guarantee committed by Development Partners. Most UK MDB guarantees mobilise $1 for each $1 guaranteed. The only other UK MDB guarantee providing leverage at this scale is the International Finance Facility for Education (IFFEd) which leverages approximately $4 for each $1 guaranteed. This high level of leverage, in part, is what allows the IFCAP mechanism to deliver such scale for the Indo-Pacific region. It does, however, mean that the set-up of the guarantee is riskier, and so will use up more of our risk appetite for $1 guaranteed than other guarantees, which is explored below.

We will continue to negotiate the IFCAP structure with ADB and other Development Partners based on a set of key principles. As set out in the Management Case, we expect to finalise the precise design of IFCAP with the ADB and other Development Partners over the next 6 months. This is normal practice on FCDO guarantees and the final structure will be agreed with the FCDO Finance Director. The key principles we will follow when finalising these negotiations are set out in the Management Case.

Appraisal Question 3: How big should the UK contribution to IFCAP be?

1. We base the appraisal of how large a UK contribution to IFCAP should be on three criteria. These are:
  1. The level of risk. While guarantees do not create an up-front DEL cost to the FCDO (beyond legal fees), they do create a contingent liability. The FCDO has a risk appetite for new guarantees, which is defined by the FCDO Guarantee Risk Management Framework (RMF). Where possible, FCDO’s preference is to avoid large, single year demands on our guarantees requiring urgent and costly reprioritisation of resources. A larger UK contribution to IFCAP will add more to risk. Key terms for assessing the level of risk are set out in Box 4.

  1. The volume of climate finance unlocked. A larger UK contribution to IFCAP will unlock proportionally more climate finance from the ADB. For example, a contribution which is twice as big will unlock twice as much climate finance for the Indo-Pacific region.

  1. The UK’s relative position amongst other Development Partners supporting IFCAP. The size of the UK’s contribution to IFCAP relative to other partners’ contributions matters because losses under the IFCAP guarantee are shared pro-rata; if the UK provides 10% of the total guarantee to IFCAP then the UK will bear 10% of losses (up to the pay-out cap). The UK’s burden share of IFCAP may also impact the UK’s relative influence in discussions with the ADB, though we do not expect this to be a major factor.

Box 4: Level of risk, key terms
Expected Loss or Risk-adjusted Exposure is calculated as the cost of a guarantee being called multiplied by the probability of that guarantee being called. For IFCAP, where there are many different possible outcomes (e.g. it could be called for $50m or $100m) we commissioned the UK Government Actuary’s Department to support FCDO with calculations of expected loss/risk-adjusted exposure. / Average In-year Risk-adjusted Exposure (AIRE) is calculated as the annual expected loss from a guarantee over the next 20 years. This is used in the FCDO Guarantee RMF as a key metric for comparing guarantees and setting risk tolerance. / Maximum In-year Risk-adjusted Exposure (MIRE) is calculated as the maximum expected loss in a single year from a given guarantee. This is used in the FCDO Guarantee RMF as a key metric for comparing guarantees and setting risk tolerance.

Although the January 2023 concept note proposed a UK contribution to IFCAP of $500m to $1.5bn, this Business Case considers a more conservative set of options. Since January, we have analysed the (evolving) IFCAP structure in more detail and judge that a more appropriate set of options to consider are a guarantee of $100m (£77m) (matching the contribution of Korea), $300m (£232m), or $500m (£386m). The UK guarantee would be denominated in US dollars, as explained in the Financial Case.

Table 5: UK guarantee size options appraisal
Option	Appraisal Summary
$100m (£77m) guarantee	The level of risk associated with a $100m guarantee would be low relative to the other options presented below. We estimate that the maximum pay-out from a single country defaulting in this scenario would be approximately $60m (£46m) if the Philippines defaulted. The maximum total payout would be $100m (£77m). On a risk-adjusted basis, the estimated AIRE is £2m. The estimated MIRE is £3m in 2031/32. This level of risk could be added to the FCDO guarantee portfolio without a significant impact of FCDO’s guarantee risk levels, it would be less than the initial risk appetite ‘budgeted’ for IFCAP at the Concept Note stage. / The volume of climate finance unlocked with a $100m guarantee would also be low, relative to other options presented below. We estimate that this would mobilise $400m-$600m of new climate finance from ADB. / In relative terms, a $100m guarantee would place the UK at the lower end of IFCAP contributors with a share of approximately 5%. It is likely that our guarantee would be a similar size to Sweden and Korea in this scenario. A low share would improve the risk profile of IFCAP from a UK perspective (making it more likely that payment demands would be spread over multiple years).

$300m (£232m) guarantee	The level of risk associated with a $300m guarantee would be high. We estimate that the maximum pay-out from a single country defaulting in this scenario would be approximately $166m (£128m). The maximum total payout would be $300m (£232m). On a risk-adjusted basis, the estimated AIRE is £6m. The estimated MIRE is £8m in 2031/32. / This level of AIRE/MIRE could be absorbed within the FCDO Guarantee RMF (and would be roughly consistent with the risk ‘budgeted for’ at the Concept Note stage) but would breach the FCDO’s internal requirement that the maximum possible payout from a single country defaulting in a single year should not exceed £100m. On balance, we judge that a $300m contribution would be affordable with some changes to the reference portfolio (which ADB have indicated they are open to). / The volume of climate finance unlocked with a $300m guarantee would be approximately $1.2bn-$1.8bn. This is significant and would be amongst the largest volumes of finance mobilised by a single UK MDB guarantee to date (the Room to Run guarantee mobilised $1.6bn-$2bn. / In relative terms, a $300m guarantee would place the UK in the middle of IFCAP contributors with a share of approximately 12%. It is likely that a $300m would be larger than the contribution of Korea, Sweden, Denmark and Italy, but smaller than that of the US ($1bn) or Japan.

$500m (£386m) guarantee	The level of risk associated with a $500m guarantee would very high. We estimate that the maximum pay-out from a single country defaulting in this scenario would be approximately $256m (£198m). The maximum total payout would be $500m (£386m). On a risk-adjusted basis, the estimated AIRE is £9m. The estimated MIRE is £13m in 2031/32. This level of AIRE/MIRE would take up approximately one third of the remaining space within FCDO’s guarantee risk appetite (i.e. have a significant opportunity cost) and would breach the FCDO’s internal requirement that the maximum possible payout from a single country defaulting in a single year should not exceed £100m. On balance, we judge that a $500m contribution would not be appropriate given the additional risk it would add to the guarantee portfolio. / The volume of climate finance unlocked with a $500m guarantee would be approximately $2bn-$2.4bn. This is very significant and would be the largest volumes of finance mobilised by a single UK MDB guarantee by a considerable margin. / In relative terms, a $500m guarantee would place the UK in the middle of IFCAP contributors with a share of approximately 19%. It is likely that a $500m would be larger than the contribution of Korea, Sweden, Denmark, and Italy, but smaller than that of the US ($1bn) or Japan.

We conclude that the best option is a $300m guarantee, which will unlock $1.8bn of climate lending for IFCAP, subject to agreement with ADB that the maximum UK payout for single country in a single year should remain below £100m. This condition could be achieved by agreeing to adjust the IFCAP reference portfolio, setting a UK-specific cap (that the UK won’t pay out more than £100m in a single year) or by making the UK guarantee conditional on the UK’s relative share being 10% or less (which would reduce the maximum single year payout to <£100m). If necessary, we will scale down the size of the UK guarantee to ensure this condition is met. A $300m UK guarantee will mobilise significant volumes of climate finance, and situate the UK as a large, but not the largest IFCAP guarantor.

Value for Money

1. We judge that that a $300m contribution to IFCAP would deliver value for money against each of the ‘4Es’:
  1. The proposed guarantee is judged to be economical because it will increase ADB lending to the Indo-Pacific at low up-front cost to the FCDO; the Financial Case sets out the expected guarantee call to FCDO: an Average In-Year Risk-Adjusted Exposure of around £6m, in line with the Concept Note and the UK’s appetite. We have also ensured that running costs of IFCAP are minimised (see Management Case for more information). There will only be an individual facility manager plus existing ADB resource to run the secretariat, there will be limited resources dedicated to IFCAP day-to-day management. Guarantor oversight will largely take place at annual Development Committee meetings which themselves will take place in the margins of the ADB Annual Meetings, so at little marginal cost. The overall cost of IFCAP is also relatively low; the expected loss of £136m offers good value relative to the approximately $1.8bn which will be unlocked.

  1. The efficiency of the proposed guarantee is determined by how much additional ADB lending capacity is unlocked by the guarantee. Overall, we judge that the proposed guarantee is an efficient transaction. The $1.2bn-$1.8bn of affordable climate finance which will be mobilised is significantly more than the UK could mobilise using grant finance alone. This efficiency is partly driven by the first-loss structure of the guarantee, and partly by ADB’s AAA credit rating (which allows ADB to borrow cheaply from capital markets and lend to countries on very affordable terms (base rate, plus 1-2% points of interest, with c. 20-year maturities). Providing the same guarantee to an institution without AAA status would be less efficient in generating new lending.

  1. The effectiveness of the proposed guarantee in driving sustainable investments in mitigation and adaptation depends on the extent to which the additional ADB lending capacity unlocked by the guarantee leads to (i) an updated ambition on climate finance over 2019-2030, and (ii) an affordable, climate-focused lending to Indo-Pacific countries. On (i) we continue to work with ADB and partners to update the target, with some success as explored above. On (ii), we judge that this will be effective on the basis that the ADB has scored well in recent reviews; for example:
    1. The UK’s Multilateral Development Review scored the ADB in the top quartile of all institutions review, with having a “good” match with the UK’s development objectives, and “very good” organisational strength.
    2. An output score of A for the Asian Development Fund 2021 Annual Review and on track for a similar score for 2022’s Review.
    3. A recent Centre for Global Development analysis of the ‘Quality of ODA’ spending, ranked the ADB in the top quarter of aid spending institutions.
    4. The ADB was top-ranked in the DFI transparency index 2023 for sovereign lending and second for non-sovereign lending.
    5. We judge there will be strong demand for the finance unlocked by IFCAP. ADB are working closely with client countries to establish climate priorities and expansion of projects under CCAP. The lending rates of the finance unlocked by IFCAP are – for most borrowers – significantly below what they could otherwise access.
    6. IFCAP poses a good demonstration effect for other donors and MDBs to learn from. While IFCAP has certainly sought inspiration from the UK-only-supported Room 2 Run guarantee at the African Development Bank, it has successfully attracted interest from a range of likeminded guarantors.

  1. The equity of the proposed guarantee will be determined by ADB’s lending policies, which are assessed regularly in FCDO annual reviews of the UK core capital contributions to the Bank. Further to this, by ensuring that lending unlocked by IFCAP will two-thirds be directed to adaptation and resilience programmes and policy, we have further assurances that IFCAP will be supporting poorer and more vulnerable populations in the region.

Overall, we conclude that a portfolio guarantee to support IFCAP is an effective way to increase affordable finance to middle-income countries. The proposed guarantee will increase ADB lending to countries across the Indo-Pacific – which has a track record of positive development impact – at zero up-front cost to the UK.

Theory of Change

The proposed Theory of Change for the UK contribution to IFCAP is illustrated below. This will be updated in due course.
Figure 3: Theory of Change for the proposed IFCAP portfolio guarantee
Inputs		Outputs		Outcomes		Impacts

UK support for AfDB IFCAP transaction through: / Guarantee on ADB existing loan portfolio. / Policy engagement with the ADB, participation on IFCAP donor committee, and performance monitoring.		A successful IFCAP transaction: / Other donors contribute. / ADB lower their exposure to risk, increasing capacity for new lending operations.		Increased climate finance for Asia and the Pacific / $10-15bn in additional ADB lending to eligible members for development projects aligned with ADB’s Climate Change Action Plan.		Accelerated progress towards Climate Targets in Asia and the Pacific / Indo-Pacific countries reduce greenhouse gas emissions, their negative exposure to the impact of climate change is reduced, and progress towards Climate Action SDG 13 is accelerated.

		Assumptions: / Other donors interested. Korea have already announced their support to IFCAP, the US have made $1bn allowance in their budget. Other donors engage actively in design, albeit with slightly longer clearance timelines than us and the above. / ADB’s lending capacity is increased. This will depend on Credit Rating Agencies (CRA) assessment of whether the guarantee substantially reduces the ADB’s exposure to default risk. This will be confirmed with CRAs before finalising the IFCAP transaction.		Assumptions: / ADB pipeline and capacity increases. ADB must have institutional capacity and pipeline of projects to utilise additional lending headroom (focussing on adaptation and mitigation activities). / IFCAP finance is additional and non-fungible. ADB must provide monitoring and evidence to provide all assurances that lending unlocked through IFCAP is additional to lending plans – including those unlocked by other CAF measures – and not substitutional thereof. / Demand from partner countries for climate-change related investment increases in-line with IFCAP modelling.		Assumptions: / Projects deliver expected results. ADB is capable of sustained impact on the sectors and policies of its programmes. / Effective allocation. We assume that ADB systems are in place to allocate new lending effectively to projects which will have a positive impact. / There is political will and capacity in partner countries to make commitment and reforms to reduce GHG emissions and to ensure that ADB projects have a sustained impact.

## Commercial Case
The delivery partner for this programme is the ADB. The ADB is not a delivery partner in the typical sense for this programme (in fact, the ADB is paying the UK a fee for providing the guarantee); however, the strengths of ADB as an institution are essential for ensuring that the funding unlocked by IFCAP is deployed effectively, and that the risks of default across ADB’s portfolio are managed responsibly. The UK will continue to provide oversight of the ADB’s activity and ensure the guarantee delivers value for money to the UK whilst staying joined up on wider HMG objectives and programmatic work within the region.

The ADB is a long-standing, trusted partner for UK International Development work. The UK has a 2% shareholding (14th largest) in ADB but is influential within the Bank due to our development expertise and our major contribution to the Bank’s grant financing arm, the Asian Development Fund (ADF). The UK is the 4th largest donor to the ADF with a 5.4% burden share (£117.6m over the 4 years from 2021-24). The ADB consistently scores well in independent evaluations and is delivering several other FCDO programmes effectively.

IFCAP will be established as a Financing Partnership Facility (FPF) within the ADB. The FPF will have two trust funds (which the UK will not contribute to as part of this Business Case, but will consider contributing to through a separate programme) and will accept bilateral guarantees from donors (which the UK will contribute). Grants provided to IFCAP, which will be administered through the two trust funds, will be used for project preparation activities to ensure that there is a strong pipeline for the up to $15bn of new lending unlocked by Development Partners’ guarantees (including the UK’s). The IFCAP FPF will be governed by a single Donor Committee, which the FCDO will sit on (see management case for details).
[note] The Indo Pacific Connectivity Programme is currently under development by the Indo Pacific Regional Department (at concept note stage). It will consider the option of making a trust fund contribution, which would be to support feasibility studies and other technical assistance to promote cross border renewable energy trade.

Contractual details and type of agreement

The UK contribution to IFCAP will be formalised through two inter-linked legal agreements. It is envisioned that the UK will enter into two agreements: (i) a Common Terms Agreement, to be entered into between ADB and all guarantee partners, which will set out the key governance and operational framework among the guarantors and ADB’s administration the IFCAP facility , and (ii) a Deed of Guarantee which will be entered into between ADB and the UK, which will contain the UK’s guarantee commitment. These two agreements, which will be legally binding, taken together will provide ADB with effective credit protection and the UK with certainty of the terms of our guarantee and the governance and operation of IFCAP by ADB.

A further non-binding agreement will be signed with ADB setting out the development objectives and reporting requirements of IFCAP. An MoU (or similar arrangement) will set out the programme objectives and monitoring requirements of IFCAP with ADB. A similar structure has been used for other UK-MDB guarantees.

Once executed, the IFCAP agreements will commit the UK as primary obligor to a guarantee. This will be a demand guarantee protecting the ADB against losses on the reference portfolio of countries (Table 1) in the event of default. Full details are set out in the Financial Case. In the event of a demand on the guarantee, the UK will have up to 30 days to make the required payment to ADB and will not be able to challenge the demand.

The guarantee will provide a Synthetic Risk Transfer for ADB. The ADB will remain the Lender of Record for all loans and will remain fully responsible for managing all the loans in its portfolio, but a portion of the risk associated with its portfolio will, in effect, be transferred to the UK.

The exact terms of the guarantee agreements will be negotiated to fit the FCDO’s risk appetite and share risk appropriately with the ADB and other Development Partners. FCDO’s risk appetite on challenging issues will be agreed with the FCDO’s Finance Director and/or Legal Team, where appropriate. As set out in the Financial Case, the UK guarantee agreement will be structured to diversify risk, share risk appropriately with the ADB and other guarantors, and provide strong incentives for responsible risk management. Internal and external legal expertise will be involved when negotiating the final guarantee agreement to ensure that the terms agreed are appropriate for the UK. The Government Actuary’s Department (GAD) and Contingent Liabilities Central Capability (CLCC) will also be consulted.

ADB’s capability and systems
1. The ADB’s strong governance processes and operations systems make it an appropriate partner for the IFCAP initiative. The ADB has appropriate safeguarding, fiduciary risk, and key policy decisions (gender, debt sustainability). For example:
  1. ADB has sound processes for risk management. ADB has a risk framework built on three pillars: governance, policies, and processes. The Bank’s risk management process is led by the Office of Risk Management (ORM) and various management committees, e.g. the Audit and Risk Committee, that are responsible for overseeing Bank-wide risk issues. The Board of Directors plays an oversight role. Independent review of ADB’s Risk Management comes from the ratings agencies, such as Moody’s which in August 2021 highlighted the Bank’s strong risk management culture as having provided a buffer against Coronavirus shock. Fitch in its July 2022 report notes ADB’s high governance standards as contributing to its low-risk business profile.
  2. ADB has strong policies for preventing aid diversion and conflicts of interest. Details of the ADB’s Anticorruption and Integrity Policies and Strategies can be found here. The FCDO’s Central Assurance Assessment of the ADB reviews its systems in depth on a regular basis.
  3. The ADB is well aligned with the FCDO on policy priorities. In addition to the ADB’s increasing focus on climate action set out in the Strategic Case, ADB has policies on gender and debt sustainability which the FCDO supports. For example, ADB’s Strategy 2030 includes ‘Accelerating Progress in Gender Equality’ as one of its five operational priorities. ADB has committed to a target that by 2030, at least 75% of the number of ADB’s committed operations will promote gender equality.
2. If the ADB stops performing on its climate finance commitments under IFCAP, or there is evidence that it is mismanaging the portfolio of loans covered by the UK guarantee, the UK will use the IFCAP Donor Committee and its position as a shareholder to hold ADB to account. The UK will not be able to terminate the guarantee except in cases where the ADB fails to pay any IFCAP fee due to the UK. In the event of under-performance, our main recourse will be to pressure the ADB to improve performance alongside other IFCAP Partners in the Donor Committee and ADB Board meetings.

Overall, we judge that the commercial risks are minimal because of the ADB’s strong track record and governance procedures. The guarantee agreement will have appropriate legal protections for the UK, such as provisions for arbitration and – subject to negotiation - for FCDO to challenge ADB calculations of loss.
The Guarantee Fee
FCDO’s current Policy on guarantee fees is to assess the case for charging a guarantee fee on a case-by-case basis. Where the FCDO does charge a fee, this is not included in ODA scoring calculations.

The FCDO does expect to charge a fee to ADB for this guarantee. The starting point for setting the UK guarantee fee will be the estimate of expected loss. The UK team will, however, be open to reducing this fee if required to make the transaction financially viable for the ADB (i.e. to ensure ADB retains a sufficient share of net income from loans in the reference portfolio to cover its operating expenses) and if necessary to ensure consistency with other guarantors (on the basis that it could be reputationally damaging for the FCDO to charge a lower/higher fee for the same service as other Partners). The team will also consider waiving the fee if doing so could lead to a transfer to the Asian Development Fund, though this possibility needs to be explored further. The final decision on the FCDO’s IFCAP fee will be agreed with the FCDO Finance Director.

The fees paid to the FCDO will be returned to the Department’s central budget. The fees will not be provision for future calls, they will be used for ordinary non-ODA eligible FCDO expenses.

Guarantee Recoveries
If there is a default under the reference portfolio and ADB makes a demand on the UK’s guarantee, it is likely that the UK will have to deal with the issue of recoveries. The ADB has never written off a loan. Recoveries are always made, even if years later. If/when recoveries are received, the ADB will refund a pro-rata portion of the net amount received (after deduction of any reasonable costs or expenses related to the recovery of the guaranteed amount) to relevant Financing Partners. Pro-rata recoveries will be made at reasonable intervals taking into account the administrative burden of processing recoveries. Following a recovery, the FCDO will have the option to:

  1. Return the recovered/refunded amount to the UK budget. This is not a preferred option. The DAC Secretariat has indicated that payments resulting from a guarantee being triggered would score 100% as ODA under the current rules if the guarantor forgoes the right to recoveries. FCDO only has ODA budget available to meet demands on MDB guarantees, so it would not be appropriate for the UK to receive recoveries directly.

  1. Return such funds to the IFCAP FPF until the end of the 20-year IFCAP period. This may be a preferred option in the short-term. We may wish for recoveries to be held by ADB in case further calls are made on the guarantee. This is still to be negotiated with the ADB.

  1. Reallocate such funds to another trust fund or a Special Fund of ADB. This is our preferred option in the medium-term, and potentially in the short-term too. If recoveries can be quickly re-allocated to another trust fund within ADB this will achieve strong development impact. Depending on negotiations with ADB, we may wish for recoveries to be held within IFCAP until the 20-year term expires (option b) then transferred to a trust fund.

A decision on treatment of recoveries will be made (and communicated to ADB) by the FCDO, in consultation with HMT, at the point of a default occurring.

Moral Hazard
Moral hazard occurs when a person/institution is disincentivised from guarding against risk because they are protected from the consequences. Moral hazard is an important concern on any guarantee. In the case of IFCAP, moral hazard could arise both before and after the point of default as a result of Development Partner guarantees. Before default, the ADB may take fewer precautions to prevent defaults because they know that IFCAP will pay-out in the event of a default. This problem could be worsened if ADB is allowed to keep guarantee pay-outs even after seeking recoveries (para C11.b.) as in this scenario ADB has the potential to gain financially following a default. After a default, ADB may be slower to pursue recoveries because a large share of any recoveries may need to be shared with guarantors who have paid out. This problem could be worsened by the first-loss structure of the guarantee, which means that guarantors meet 100% of the costs of default (until the relevant IFCAP pay-out cap is reached). Furthermore, Borrowers may also be disincentivised to repay ADB if they know payments are covered by IFCAP.

On balance, we recommend accepting this moral hazard risk (while continuing to monitor it closely) because the following mitigating factors are in place:

  1. The IFCAP guarantee cannot be called until a non-payment has lasted for 180 days. This means that ADB is incentivised to avoid payment being missed.

  1. The Preferred Creditor Status of the ADB is essential to the ADB’s business model. The ADB’s PCS underpins the Bank’s AAA credit rating and allows it to borrow cheaply from capital markets. Any defaults to ADB risk damaging the perception of ADB’s PCS, and the perception of PCS is essential given it is, after all, a customary practice. The ADB therefore has a strong incentive to prevent defaults.
    [note] Preferred Creditor Status is a customary practice whereby loans issued by the ADB (and other Multilateral Development Banks) are prioritised ahead of bilateral and private debt for purposes of sovereign debt service by borrower countries.

  1. The Founding Members of IFCAP (US, UK, JPN, KOR, DNK, SWE, ITA) have a combined shareholding at the Bank of approximately 35%. This gives the Founding Members a direct means to influence how ADB conducts itself (through the ADB board). It also creates a strong incentive for the Bank to act in the Founding Members interests and diligently protect itself against risks.

  1. IFCAP will never cover more than 50% of ADB’s exposure to a given country. This means that once IFCAP cover is exhausted the ADB will always face further losses on its own balance sheet, creating a further incentive to avoid default.

  1. Borrowers will not be incentivised to default because IFCAP will not clear their arrears with ADB. Even if IFCAP partners make a payment to ADB under the guarantee, the defaulting borrower’s obligations will be unchanged and ADB will continue to seek recoveries.

Finalising Negotiations with ADB
At the point that this Business Case is being finalised, not all details of the guarantee have been agreed. We are, for example, still negotiating the UK fee for the guarantee. Subject to approval of this Business Case, we will work with ADB and other IFCAP partners to finalise the guarantee structure in a way which is consistent with the principals and objects set out in the Strategic and Appraisal sections of the Business Case. The financial terms on previous FCDO guarantees will be used as a guide. We will agree the final structure of the guarantee with the FCDO Finance Director before signing.

When finalising the guarantee agreement, legal fees of up to £100,000 may be required. Legal advice will be procured through the current FCDO legal panel to support the negotiation of both the Common Terms Agreement and Deed of Guarantee. Based on the advice of FCDO’s internal legal team, and experience with a previous portfolio guarantee, legal expertise of up to £100,000 may be procured to review the agreement once drafted. This cost will be programme RDEL. Once the Business Case is approved, the exact scope and cost of the legal work needed to finalise the guarantee will be agreed with the SRO based on advice from FCDO Legal Team. If additional budget is required, this will be agreed with the International Finance Director.

## Financial Case

IFCAP will be the third large MDB portfolio guarantee which the UK has supported. The FCDO signed the Room to Run portfolio guarantee with the African Development Bank (AfDB) in October 2022. The FCDO has also been closely involved with developing the International Finance Facility for Education (IFFEd) with the ADB and AfDB. IFCAP will, however, have several differences with these other portfolio guarantees. It will be the first MDB guarantee provided by the UK using a first-loss structure and will be the first time the UK has joined more than two other financing partners on a single portfolio guarantee.

This Financial Case sets out the structure of the proposed guarantee and evaluates the risk. This section draws heavily on analysis provided by the Government Actuary’s Department. The Financial Case concludes that, subject to certain conditions being met, the proposed guarantee contribution of $300m (£232m) is within the FCDO’s MDB guarantee risk appetite.
Structure of the Guarantee and Budgetary Implications for FCDO
1. The UK guarantee to IFCAP will provide the ADB with first-loss credit protection worth up to $300m. The UK guarantee will cover part of the 29-country $9bn reference portfolio set out in Table 1 the Strategic Case. The guarantee will pay out if any of the 29 countries included in the IFCAP portfolio misses a payment to ADB by more than 180 days. A default to ADB is unlikely due to the ADB’s Preferred Creditor Status, but would not be unprecedented (see risk section, below).
2. The amount paid out in the event of a call will depend on the nature of the default. For example, which country defaults, how much they owe to the ADB when they default, and how long the default lasts.
  [note] It will be possible to forecast relatively accurately how much borrowers owe to the ADB each year (subject to variation in exchange rates/interest rates) once the final reference portfolio is agreed. The UK guarantee will include a non-acceleration clause to ensure that multiple repayments cannot be called simultaneously.
3. It will also depend on the level of risk-sharing with other participants. Risk will be shared pro-rata between the five guarantors to IFCAP. At inception, we expect the UK guarantee will be 12% of the total IFCAP guarantee, making the UK responsible for 12% of any demand on the guarantee. This share could then fall if other donors provide guarantees in future. If the UK share is expected to be significantly above 12% at the point of signing, the risk (and scale of UK contribution) will be re-assessed.
4. As an example, in the unlikely event that the Philippines missed a $1bn payment to the ADB by than 180 days, the UK would be required to pay out approximately $120m. This is because more than $1bn of exposure to the Philippines in included in the reference portfolio (Table 1) and so the UK would be required to meet 12% of the cost of the missed payment.
5. There are two caps on the amount the UK could be required to pay-out in the event of default. There is an aggregate $300m cap on payouts set by the total size of the UK guarantee; for example, if the UK has already paid out $300m to cover one default to ADB and a second country in the IFCAP portfolio defaults, then no further pay-out will be required. There is also a cap on single country exposure; for example, there is an $82.5m cap on exposure to Thailand, so once the UK and other guarantors (combined) have paid out $82.5m to compensate the ADB for losses in Thailand, there will be no further pay-outs (even if Thailand continues to miss payments). The UK’s IFCAP guarantee could be called multiple times, but these caps cannot be breached at any point. These country caps will be included in the Common Terms Agreement, the final set of caps (i.e. the reference portfolio) will be agreed by all six Founding Partners of IFCAP. Figure 3 below illustrates the process of a demand on the UK’s IFCAP guarantee in detail.
6. The ADB will remain the Lender of Record on all loans covered by the guarantee. The IFCAP guarantee is an example of synthetic risk transfer. Even in the event of a default, the ADB will continue to administer the loans and seek recoveries. The UK guarantee would not repay loans on behalf of defaulting borrowers, it would compensate the ADB temporarily for losses sustained as the result of a default (i.e. ‘make the ADB whole again’).
  [note] A subrogation clause may be included in the guarantee agreement, though is unlikely to be utilised.
7. In addition to the risk sharing with other guarantors, and the exposure limits mentioned above, the UK guarantee to IFCAP will have several design features to ensure the UK guarantee is acceptable within the FCDO’s guarantee risk appetite:
  1. Diversification. The reference portfolio will include 29 countries. This will diversify the risk of providing a UK guarantee to IFCAP and limit UK exposure to any single country.

  1. Phased-in guarantee cover. The size of the UK guarantee (i.e. the caps outlined in Table 1) will be scaled up as new climate lending is unlocked by the ADB. For example, if the ADB has only unlocked half of the agreed volume of climate lending by 2028, then the UK guarantee will remain at $150m (i.e. half of the planned amount). This protects the UK against a key value for money risk; if the ADB does not deliver additional financing then the full UK guarantee will not be provided.

  1. ADB to hold 50% risk. The ADB will be required to hold at least 50% of the risk on all countries in the IFCAP reference portfolio, providing a strong incentive to manage loans responsibly.

  1. Early notification of a call. Consistent with other UK guarantees, the ADB will only be able to make a demand on the UK guarantee 180 days after a payment has been missed by a country covered by the IFCAP reference portfolio. The ADB will be required to notify the UK of any missed payments within 30 days. As a result, the FCDO will have at least 150 days to plan for a potential call on the guarantee.

1. The guarantee will be recorded as a contingent liability and will have no immediate budgetary impact on the FCDO’s Department Expenditure Limit (DEL) budget. It will be disclosed as a financial guarantee (contingent liability) in FCDO’s Annual Report and Accounts and Annual Estimates when the agreement(s) is/are entered into. In line with the UK Government Financial Reporting Manual, an initial provision will be recognised using non-cash Resource Annually Managed Expenditure (RAME) budget, to reflect the fair value of the guarantee. This will be the equivalent of the lifetime expected credit loss of the guarantee. If an outflow of resources from FCDO becomes probable – i.e. there becomes a greater than 50% likelihood of a country in the reference portfolio defaulting on a loan repayment(s) and therefore triggering the guarantee – FCDO will increase the provision to the likely amount of the default in its Non-Cash Resource Annual Managed Expenditure budget (RAME). FCDO will make an assessment whether to fully provide for the remainder of the guarantee in RAME. If the probability of default rises above 50%, the FCDO team may include budget for this guarantee directly in spending plans, which can then be re-prioritised if a call on the guarantee doesn’t materialise.
2. The guarantee will have a DEL impact at the point at which the guarantee is triggered, and a payment request is made by the ADB. This is agreed with HMT. The cash impact and ODA impact will be at time of payment (we currently expect this to be within 30 days after a payment request is made). The flow of funds will be direct to ADB.
Country	IFCAP Exposure	Annual Repayments
Country A	$300m	$250m
Country B	$500m	$300m
Country C	$400m	$250m
Country D	$100m	$20m

- If any country in the IFCAP portfolio misses a payment to ADB by more than 180 days, ADB can trigger the IFCAP guarantee.
- If ADB has not reached the IFCAP exposure cap for that country (e.g. $500m for Country B in the example portfolio illustrated here) nor the overall pay-out cap for IFCAP (i.e. $300m), then a pay-out will be required.
- The UK pay-out is proportional to the UK’s share of IFCAP guarantee coverage.
- Following a default, calls on the IFCAP guarantee will continue until the default is resolved or one of the two pay-out caps are reached.
Figure 3: The structure of the IFCAP Guarantee, a worked example
Financial Risk and Affordability Analysis
1. FCDO has set a level of risk appetite for holding contingent liabilities based on the potential affordability of any calls. This has been agreed with the FCDO Accounting Officer. The Government Actuary’s Department (GAD) advises FCDO on our contingent liability risk modelling. The FCDO’s guarantee risk appetite is set out in a Guarantee Risk Management Framework (RMF) which considers metrics including the Average In-year Risk-adjusted Exposure (AIRE) of FCDO’s guarantee portfolio. The RMF also considers metrics for Maximum In-year Risk-adjusted Exposure (MIRE), the level of concentration risk in any single country/region, and the maximum possible pay-out to a single country in a single year.
  [note] This average is calculated over a 20-year period.
2. The Financial Transactions Steering Board (FTSB), which oversees FCDO’s work on guarantees, has agreed that the proposed guarantee is good fit for FCDO’s guarantee portfolio. The FTSB tracks FCDO’s total guarantee exposure and reviews scenario analysis to assess the possibility and impact of tail risks (e.g., low-likelihood but potentially high-impact events). Through scrutiny of the FCDO guarantee pipeline, the FTSB aims to spread FCDO’s guarantee exposure over time and reduce the likelihood of large pay-outs being required in a single year from the (fixed in-year) ODA budget. Based on the analysis from the Government Actuary’s Department below, FTSB members agree that the proposed contribution to IFCAP is a good value for money use of the FCDO’s guarantee risk appetite.
3. The affordability assessment for this guarantee is based on analysis from the Government Actuary’s Department (GAD). GAD regularly supports the FCDO with risk analysis of new guarantees. Given the complexity of the IFCAP guarantee structure, officials judged that dedicated GAD stochastic modelling of the IFCAP guarantee using the R programming software was needed to understand the risks in detail. The GAD analysis which underpins this financial case is available on request.

1. Key elements of the GAD analysis of the IFCAP guarantee are presented below. Core assumptions underpinning this analysis are that: the UK provides a $300m (£232m) guarantee; other donors provide $2.2bn in guarantees; the USD:GDP exchange rate is fixed at 1.26; The probabilities of default for countries covered by the guarantee are accurately represented by Moody’s data on default probabilities, with a 4-notch credit rating uplift to reflect the ADB’s Preferred Creditor Status; Loss Given Default is 100%; there is some, but not full, correlation between countries’ macroeconomic situations; the structure of IFCAP is as described at the time of Business Case drafting.
  [note] This reflects the fact that FCDO would likely waive its right to any recoveries following a pay-out (para C13).
  1. The UK guarantee to IFCAP will increase FCDO’s total guarantee exposure by approximately £232m for the next 25 years. As illustrated in Figure 4, the proposed $300m UK guarantee will cover a relatively small share of the total portfolio guaranteed by IFCAP. The IFCAP platform will cover $9bn of ADB loans (the green bars), donors will cover losses up to approximately $2.5bn (the yellow line) and – within that $2.5bn – the UK will cover up to $300m of losses. Exposure will increase steadily in years 1-5 as new climate loans are made and the IFCAP guarantee is deployed, then will fall back to zero after 20 years as the guarantee is phased out.

  1. The expected loss from the proposed $300m guarantee in any given year is estimated to be between approximately £3m and £8m. As illustrated in Figure 5, which shows the risk-adjusted exposure profile for the proposed UK contribution to IFCAP, risk-adjusted exposure rises quickly to approximately £8m before falling. This means that in the riskiest year (year 7) the UK could – on average - expect to lose approximately £8m. Average In-year Risk-adjusted Exposure (AIRE) for the UK guarantee would be £6m, Maximum In-year Risk-adjusted Exposure (MIRE) for the UK guarantee would be £8m.

Figure 4: IFCAP Exposure Profile, £m
Source: GAD modelling

Figure 5: IFCAP Risk-adjusted Exposure Profile, £m
Source: GAD modelling

  1. Despite relatively low expected loss figures, it is important to note that possible calls on the UK guarantee could be very large. Figure 6 shows the 95th percentile of estimated demands on the UK portion of the IFCAP guarantee over time (i.e., in 5% of cases, demands will be higher than this amount). The 95th percentile line illustrates that for the first 13 years, there is a roughly 5% chance of a UK payout of ~£50m or more.

  1. Over the lifetime of the arrangement, there is a high likelihood that a large annual payment will be required. For example, there is a 72% probability that over the lifetime of the arrangement, in at least one year, IFCAP donors (combined) will have a payout of over $500m (i.e. a ~£50m pay-out by the UK). There is a 42% probability of a pay-out of over $1,000m (i.e. a ~£100m pay-out by the UK) in at least one year (this would likely require multiple countries to default). As the guarantee is currently structured, if Pakistan (which has a Caa credit rating) defaulted, then the $1.3bn country limit would be quickly met resulting in payments of $160m (~£125m) from FCDO. FCDO’s International Financial Institutions Division (IFID) are continuing to negotiate with ADB on this point. The options to deal with this are: (i) adjusting the reference portfolio to avoid this constraint becoming binding, (ii) agreeing a payment plan with ADB to spread payments over numerous years in case of default, (iii) reducing FCDO guarantee to IFCAP. There is an estimated 14% chance that the full $300m UK guarantee would be ‘used up’ over the lifetime of the arrangement.

Figure 6: Potential IFCAP pay-outs by year, £m
Source: GAD modelling

  1. The first-loss structure of the IFCAP guarantee is what drives the potential for large demands in a single year. For 24/29 countries in the IFCAP reference portfolio, annual repayments to the ADB are larger than the volume of exposure included in the reference portfolio. This means that for 24/29 countries, the full amount of IFCAP cover could be called in a single year. While this is not a significant concern for defaults by smaller countries (e.g. a default by Fiji would require a total IFCAP payout by all donors combined of $6.5m); it is a concern for larger countries, such as Pakistan, the Philippines, and India, where a default could lead to single-year demands on IFCAP worth up to $1,383m (£1,072m) in the case of the Philippines

  1. A UK guarantee to IFCAP will add to existing FCDO guarantee exposure to India and Indonesia. In 2021 and 2022, the FCDO announced commitments to guarantee $1bn of World Bank lending to India and Indonesia respectively. If India or Indonesia defaults to the ADB, it is likely that they are in such financial distress that they also default to the World Bank; these guarantee exposures are likely to be highly correlated. If India defaulted, the maximum pay-out in a single year from both UK guarantees could be up to £160m. If Indonesia defaulted, the maximum pay-out in a single year could be up to £120m. India and Indonesia both currently have investment grade credit ratings.

  1. Key risks in the IFCAP reference portfolio are exposure to Nepal and Pakistan. These countries are significant exposures in the portfolio ($528m and $1,312m respectively) and amongst the highest risk. Where appropriate, officials will aim to limit the size of these two countries in the final IFCAP portfolio, their credit risk will also be closely monitored (Box 5).
    [note] Credit protection for $1 of CCC-rated Pakistan risk is more effective for ADB than $1 of B-rated India risk, as a result it will unlock a greater volume of additional climate finance. This trade-off is a focus of the negotiations to finalise IFCAP.

Box 5: Default risk in Pakistan
Pakistan is currently the most important risk in the IFCAP reference portfolio. If Pakistan missed a payment to ADB and did not resolve its arrears within 180 days (i.e. entered default), it is likely that the full $1,312m IFCAP cover for Pakistan would be called at once by ADB. This would result in a demand on the UK guarantee of approximately £157m (though as set out above we are aiming to make adjustments to the structure to reduce this). / Pakistan has been on the cusp of external default for many months and has endured years of balance of payments crises and ballooning external debt repayments. $12bn in debt repayments are currently due before December 2023. Economic and political instability make a default by Pakistan to at least some of its creditors likely in the medium-term. / In June, Pakistan managed to secure a last-minute $3bn IMF deal which reduced the risk of imminent default. The IMF deal promotes progress towards fiscal discipline, a market determined exchange rate, and business climate reforms. The deal brings temporary respite, but strong political leadership will be required to address the long-term causes of macroeconomic crisis. / ADB’s Preferred Creditor Status reduces but does not remove the risk of a default by Pakistan; PCS will count for little if Pakistan has no funds left to pay creditors. Pakistan’s recent brush with default highlights the high risk associated with the IFCAP guarantee.

Overall, the financial risk associated with a $300m UK guarantee to IFCAP is significant but affordable if some adjustments can be made to the reference portfolio. The increase in risk-adjusted exposure (both AIRE and MIRE) generated by the guarantee is affordable within current FCDO guarantee RMF. The most challenging aspect of IFCAP is the first-loss structure, which creates the possibility of large payouts in a single year. Officials will work with the ADB to agree a structure that minimises single year payouts.
Foreign exchange and interest rate risk
1. Foreign exchange risk: FCDO will provide a US dollar-denominated guarantee to the ADB. This maximises the positive impact of the guarantee (as ADB will not be required to account for exchange rate risk) but does create an exchange rate risk for the FCDO. If the guarantee is triggered at a time when GBP is weaker against the dollar than its current level, UK payments to the ADB would cost more than the initial estimate. Conversely, should the guarantee be triggered at a time when the pound is stronger than its current level, the UK payments would be cheaper. The exchange rate risk will be monitored regularly as part of the management of the guarantee. Previous FCDO guarantees have also been denominated in foreign currency (Euros or US Dollars).
2. Interest rate risk: unlike some other UK MDB guarantees where the level of exposure rises as interest rates rise, the UK’s total exposure from its guarantee to IFCAP will not be directly affected by changes in interest rates (because exposure will be capped at $300m). Less directly, though, increases in interest rates could (i) increase the size of individual calls on the UK guarantee: as a high interest rate increases the size of countries’ repayments to the ADB (although this would only be for those 5/29 countries whose annual repayments are expected to be below their capped exposure), and (ii) increase the risk of individual calls on the UK guarantee: as the risk of default increases with interest rates. We propose that the FCDO accepts and monitors this risk. We advise against hedging the risk, as this would be against HMT’s advice in Managing Public Money guide, and we advise against requiring ADB to hold this risk as that would reduce the development impact of the IFCAP guarantee.
Managing and Monitoring Financial Risk
1. Financial risk will be monitored and managed through both FCDO’s internal processes and external engagement with ADB. Internally, the FCDO will complete annual Default Risk Assessments and regularly track default risks across the IFCAP portfolio through coordination with FCDO’s country office network. Externally, FCDO will engage closely with ADB through our Executive Director/Advisor seconded to the Bank and our regular engagement with ADB management on Board decisions. Fraud/Fiduciary risk are tracked through Central Assurance Assessments of the ADB carried out by the FCDO team.
2. The up to £100,000 of programme RDEL for legal fees will be managed by the SRO. Based on advice from Legal Team colleagues, the SRO will commission legal support to get the final structure of the guarantee agreed.

## Management Case

Management arrangements
International Financial Institutions Department (IFID) will be responsible for financial, delivery and risk management of the FCDO’s IFCAP guarantee. The Senior Responsible Owner (SRO) will be the Head of IFID. The Programme Responsible Owner (PRO), advisory capacity, and programme management capacity will also be provided by IFID. IFID will liaise closely with the UK Delegation at the ADB, Finance Directorate, and the FCDO regional team in management of the guarantee.

Oversight of all FCDO guarantees is provided by the Financial Transactions Steering Board (FTSB). The FTSB, which is a sub-committee of FCDO’s Investment and Delivery Committee, meets quarterly to review the FCDO’s guarantee portfolio and take decisions on new guarantees.

The UK will be a participant in the IFCAP Donor Committee, which will be chaired by the ADB. The Donor Committee will review the pipeline of IFCAP-supported projects, and on a consensus basis, take decisions on issues such as electing a co-chair, introducing new guarantors, setting the eligibility criteria for IFCAP projects, and specifying the reporting required from ADB. Key decisions on, e.g. changing the terms of donor guarantees, will require unanimity. The Donor Committee will be the main forum for the FCDO to influence the implementation of the IFCAP guarantee. The donor committee will have a limited ability to influence the terms/design of individual projects (that is the role of the ADB Board, of which the UK is also a member) but it will have an important role in influencing the ADB’s pipeline of climate finance projects by setting out the criteria for which projects will/won’t be acceptable for IFCAP approval.

Internally, FCDO’s contributions to the Donor Committee will be agreed between officials in IFID, Indo-Pacific Regional Department (IPRD) and relevant country teams. This cross-term working will be important to ensure a joined-up approach with the wide range of complementary FCDO support to the Indo-Pacific outlined in the Strategic Case. The FCDO representative at Donor Committee Meetings will be the International Finance Director or Executive Director to the ADB.
Business case approvals
This Business Case has been approved by the relevant FCDO management committees. It has been reviewed by both the FCDO’s Investment and Delivery Committee (IADC) and Financial Transactions Steering Board (FTSB). The FTSB is a sub-committee of the FCDO’s Investment Committee that provides oversight on guarantees and non-fiscal CDEL. There is explicit statutory authority under the 2002 International Development Act for the FCDO to issue guarantees.

Before the UK guarantee to IFCAP can be signed, approval is required from Ministers at FCDO and HMT. Approval by FCDO Minsters has been delegated to the Minister for Development and Africa.

Parliament also scrutinises all FCDO guarantee commitments before they are signed. MPs have 14 sitting days to scrutinise the guarantee, and unless anyone objects, then Parliament’s approval has been obtained. Officials will prepare the documentation for the Minister to notify the House and relevant Parliamentary committees of UK guarantees to support IFCAP. A Departmental Minute will also be laid (highlighted by a Written Ministerial Statement).

Risks
Our risk appetite statement follows FCDO’s central guidance on Risk Appetite. This means, for IFCAP, that FCDO will take a receptive appetite (i.e. willing to accept major residual risks) to risks around Strategy and Context, and Policy and Programme Delivery, and a cautious appetite (willing to accept a moderate degree of residual risk) for Public Service Delivery and Operations, People, Safeguarding, Financial and Fiduciary, and Reputational risks. The overall risk rating for this project is moderate. In additional to the moral hazard risks set out in the Commercial Case and the financial risks set out in the Financial Case, there are a range of further risks associated with this guarantee set out in Table 5.

Risks will be escalated by the SRO. The first point of escalation for most risks will be the UK’s Delegation at the ADB in Manila. If a challenge cannot be resolved with the support of the UK Delegation, FCDO’s International Finance Director will likely be asked to escalate the issue further with ADB management. Failing this, the FCDO Minister for Development and Africa, as UK Governor at ADB will be advised and asked to support.
Table 5: Risk Management

Risk Description	Risk Category	Gross Likelihood	Gross Impact	Gross Risk Rating	Mitigation Strategy	Residual Likelihood	Residual Impact	Residual Risk Rating
Poor projects designed by ADB, or cherry picking of best projects for IFCAP (at detriment to the rest of the portfolio).	Policy and Programme Delivery	Likely	Major	Major	Mitigate through proactive FCDO engagement in design phase (next 6 months), on the Donor Committee (annually and online), and collaboration with FCDO’s UK Delegation in Manila.	Possible	Major	Major
Limited understanding and/or oversight of financial risks leads to larger calls on UK ODA than modelled	Financial and Fiduciary	Possible	Major	Major	Continuing to strengthen FCDO’s internal capacity for risk management and providing regular (at least bi-annual) updates to the FTSB on guarantee portfolio risk which include scenario analysis. This mitigation strategy will reduce the overall residual risk rating to moderate by reducing the likelihood.	Unlikely	Major	Moderate
Lending ‘unlocked’ by IFCAP is not truly additional to what ADB would have done without IFCAP support.	Strategy and Context	Possible	Major	Major	Mitigate through a scenarios approach to measuring additionality (during design phase). The counterfactual scenario to estimate what ADB would lend without IFCAP should be updated annually through this approach. Ensure credit ratings agency reviews IFCAP and provides assurance.	Unlikely	Major	Moderate
ADB unable to scale up sufficiently given its increased lending capacity	Policy and Programme Delivery	Possible	Major	Major	Mitigate through proactive FCDO engagement on the ADB's Climate Change Action Plan (this quarter), at the Donor Committee (annually) and at the ADB Board (meet frequently).	Unlikely	Major	Moderate
Only UK and Korea finance IFCAP	Reputational	Possible	Moderate	Moderate	Continue engagement with Founding Partners to establish an IFCAP that works for all.	Possible	Moderate	Moderate
IFCAP projects are inconsistent with UK ODA rules, including on safeguarding.	Safeguarding	Unlikely	Major	Moderate	ADB already scores highly here, but further to this, the UK influencing ADB's updated safeguarding strategy (over next 3 months), to ensure strengthened approach.	Unlikely	Major	Moderate
Crowding out of programmes focused on extreme poverty	Policy and Programme Delivery	Possible	Moderate	Moderate	Ensure mitigations for Risk 2 are working i.e. an approach to additionality to ensure other programmes aren’t being squeezed out (over next 3 months). Use the donor committee (annually, and ad hoc as needed) to ensure strong focus on poverty from IFCAP finance.	Unlikely	Moderate	Minor
ADB lending unlocked or guaranteed by IFCAP conflicts with UK sanctions.	Financial and Fiduciary	Unlikely	Moderate	Minor	ADB meets UK legislation (see Strategic Case). In case of extreme event, UK can engage at political levels to mitigate.	Unlikely	Moderate	Minor
Non-cooperative countries seek to join or benefit from IFCAP	Strategy and Context	Possible	Minor	Minor	UK (and other Founding Partners) has a veto on new members joining IFCAP.	Unlikely	Insignificant	Minor
Deterioration of UK relations with ADB, or over-estimation of UK influence.	Reputational	Unlikely	Minor	Minor	Mitigate by addressing any difficulties in the ADB-UK relationship quickly. Can raise to highest levels where necessary.	Unlikely	Minor	Minor

Monitoring and Evaluation
Financial, delivery and risk oversight will be provided by IFID. This will include Annual Reviews of the UK guarantee which monitor value for money, an annual Default Risk Assessment (developed in consultation with country teams), and development of a detailed Theory of Change, Logframe, and Delivery Plan to guid day-to-day management of the programme. Where possible we will aim to align reporting requirements with other donors to reduce the administrative burden on ADB.
Approach to finalising negotiations with ADB
1. As on other MDB guarantees, the final IFCAP structure will be negotiated with the ADB and IFCAP Partners over several months then confirmed with the FCDO Finance Director before signing. As part of this process, we will ensure that the UK contribution to IFCAP:
  1. Remains within the boundaries of the FCDO’s Guarantee Risk Management Framework.
  2. Leads to strong commitments from the ADB on climate finance unlocked and the details of its Climate Change Action Plan.
  3. Has a clear framework for governance which allows the UK a voice in decision making going forward.