English in Action (2008 – 2018)
Project Completion Review
February 2018

Review Date: November 2017
Title: English In Action
Programme Code: 107480	Start Date: May 2008	End Date: March 2018

Summary of Programme Performance
Year	2009	2011	2012	2013	2014	2015	2016	2017
Programme Score	2	2	A+	A+	A+	A+	A+	A+
Risk Rating	Low	Low	Medium	Medium	Medium	Medium	Moderate	Moderate

Financial Position
Original Programme Value	£49,787,096
Extensions/ amendments	£959,500 (May 2016)
Log-frame revisions (with dates)	June 2009, June 2011, June 2016
Total programme spend	£50,746,596

Follow up actions required following closure

The following captures key lessons learned that can be taken into account when designing future education programme. DFID can continue to disseminate across the international education community and use the lessons learned and the knowledge products from the project to inform future education interventions.
- Evidence generated from project strongly suggests Teacher Professional Development (TPD) through school-based intervention is more effective than cascade, center based or one off training models. This enables learning inside the classroom; contributes to early successes for teacher motivation and confidence; and increases effectiveness of TPD training.
- Ensure that any TPD inputs follow a staged model of delivery, development and follow-up in order to facilitate change, rather than a block one-off training.
- Work through and build the capacity of district and sub-district teams of local Government Education Officers and teacher trainers as co-implementers. Work with them to adapt their local structures to improve effectiveness and sustainability.
- Secondary schools operate in a less-structured system and with higher levels of autonomy when compared with primary schools in Bangladesh. This requires greater levels of direct engagement and use of alternative mechanisms, e.g. community-led mechanisms like School Management Committees (SMCs) and Parents Teachers Associations (PTAs).
- Advocate for teachers inclusion in the design and delivery of national pre-service and in-service teacher education programmes.
- Ensure that from the outset of the project, strategies associated with institutionalisation and sustainability are featured as a key component of the design framework, together with appropriate resources and capacity.
- Use of evidence to support advocacy for programme institutionalisation i.e. credible research showing improved learning outcomes; demonstrated affordability and cost-effectiveness of any innovation compared to existing government programmes.
- Use the strategic advantage and role of DFID and other donors to facilitate engagement with government through formal platforms.
List of Acronyms
CLT	Communicative Language Teaching
CPD	Continuous Professional Development
CSO	Civil Society Organization
CWG	Core Working Group, DPE & EIA
DEO	District Education Office/Officer
DFID	Department for International Development
DPE	Directorate of Primary Education
DPEd	Diploma in Primary Education
DPEO	District Primary Education Office/Officer
DSHE	Directorate of Secondary and Higher Education
EIA	English in Action
ELT	English Language Teaching
FIVDB	Friends in Village Development for Bangladesh
GOB	Government of Bangladesh
HT	Head Teacher
I&S	Institutionalisation and Sustainability
ICT	Information and Communication Technologies
IER	Institute of Education and Research
M&E	Monitoring and Evaluation
MEW	Monitoring and Evaluation Wing
MoE	Ministry of Education
MoPME	Ministry of Primary and Mass Education
NAEM	National Academy for Educational Management
NAPE	National Academy for Primary Education
NCTB	National Curriculum and Textbook Board
NGO	Non-governmental Organization
OU	Open University-UK
PCR	Project Completion Review
PEDP III	Third Primary Education Development Programme
PMIS	Project Management Information System
PMU	Project Management Unit
PTA	Parents Teachers Association
PTI	Primary Teachers’ Training Institute
QWG	Quality Working Group, PEDP III
RME	Research, Monitoring and Evaluation
SARH	South Asia Research Hub
SBT	Subject Based Training
SESIP	Secondary Education Sector Improvement Programme
SMCs	School Management Committees
TDP	Teacher Development Programme
TF	Teacher Facilitator
TPD	Teachers Professional Development
UEO	Upazila Education Office/Officer
USEO	Upazila Secondary Education Officer
ZEST	Zambian Education School-based Training

A. Introduction and Context (1 page)
DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/countries/BD/
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/countries/BD/

Outline of programme and what it has achieved
English in Action (EIA) was a 10 year English language education programme, running from 2008 to 2018 with UK funding of £51 million. BMB Mott McDonald as the lead managing agent implemented the project in partnership with the Open University and BBC Media Action. It is a discrete project under a multi donor funded and Government of Bangladesh (GoB) led Third Primary Education Development Programme (PEDP3).

EIA worked to improve the English language skills of 25 million Bangladeshis, with an aim to contribute to economic growth. This has been implemented through two main components:
- a school-based programme to improve English teaching and learning in primary and secondary schools
- an adult (15+) learning programme that used electronic and print media e.g. television, website, mobile and newspapers to teach communicative English.

Under the school based component, teachers were trained, through both face to face methods and content loaded in mobile phones, to improve the English language teaching and learning process in their classroom and to createa more interactive classroom. This helped to improve the quality of English language learning of students.

The adult learning component raised interest in and motivation for learning communicative English language of youth/adults reaching them through electronic and print media.

EIA research found that, for individuals across the country and in a wide variety of employment types, there is a small but significant association between tested and self-assessed level of English and income.  Whilst the benefit is greater for those in skilled occupations who had acquired intermediate English, benefit was still found for those in unskilled occupations and who had acquired basic English. In the 2017 Employers survey, 41.3% of those interviewed stated that it is very likely for those with higher levels of English language skills to be employed over those who do not have such skills but otherwise have similar qualifications and experience.
[note] EIA 2014 Synthesis Report: Evidence of the Relationship between English and Economic Gain in Bangladesh
The project met or exceeded all output targets. EIA has reached far beyond the original scope of the programme both in terms of quantity and quality e.g. 44 million people reached against a target of 25 million, 56% of the adults (those who tested) have shown measurable improvement in their English language competency score for speaking and listening against a target of 49%. Throughout the life of the project, it continued to innovate and adapt to maximise its impact, increase effectiveness and efficiency e.g. teacher training contents have been institutionalised into the government education system reaching all teachers; EIA technical team worked with GoB to produce design notes on teacher development and ICT for the new primary sector-wide programme; provided input in the secondary sector programme design; developed local Upazila level facilitators as resource pools that will continue to contribute to future teacher development; in a research led by teachers (2017) showed that teachers now have  increased confidence to speak English and use it in the course of their work. Training cost of primary teachers came down to £94 in the final phase from £496 during scale up phase
In the adult learning component, lower socio-economic groups and female learners, previously regarded as beyond project reach, have been engaged significantly. Under Output 4 i.e. increased knowledge available around improving English language competency and teacher practice, the project added an innovative school-based research initiative led by teachers, which assisted the teachers to have an in-sight into their own teaching practices based on feedback from students. This initiative also contributed significantly to raise the profile of the project among national-level stakeholders in its final phase.
The project has also faced challenges that have potentially impacted on the level and extent of programme achievements. These challenges include:

Institutionalisation of secondary school component within GoB mechanisms was a challenging task. Secondary sector teacher professional development did not have one comprehensive platform, instead it included several large donor funded projects. Working through these multiple platforms resulted in some challenge around coordination, ownership and building an effective relationship. This was however better tackled during the final institutionalisation phase of the project by appointing dedicated staff and resource focused on the secondary sector only.

The overall integration and learning across the first three components i.e. the primary sector, the secondary sector, and the adult learning component is an area that is considered a missed opportunity. The education and research approaches that were common across all three areas could have been integrated through a more streamlined project management and a comprehensive oversight.

The project needed to adjust its implementation strategies and respond to external risks at different stages of its lifetime e.g. political unrest throughout the country; decrease in the value of the pound against the taka during the final phase.

These are discussed in more detail under ‘Lessons learned’ in the section below.
## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Overall Outcome Assessment
Overall achievement against outcome indicators is a mixed picture. In majority of the areas EIA has achieved and, for several sub-indicators, exceeded the outcome indicators, with the following to be noted.

Indicator	Milestone	Progress (final project outcome)
1a. Increases in English language competence (ELC) among the population of Bangladesh (teachers & students) at Trinity Graded Examination in Spoken English (GESE) level:	Primary students / 5 percentage point (ppt) increase in GESE level 1 or above / 5 ppt increase in GESE level 2 or above / Secondary students / 10 ppt increase in GESE level 2 or above / 5 ppt increase in GESE level 3 or above	Primary students (compared to baseline) / 19 percentage point increase in GESE level 1 or above (increase from 39% to 58%) / 2 ppt increase in GESE level 2 or above (increase from 9% to 11%) / Secondary students / 12 ppt increase in GESE level 2 or above (increase from 40% to 52%) / 2 ppt increase GESE level 3 or above (increase from 26% to 28%)
1b. Proportion of adults with improved communicative language ability measured by: / a) self-assessment of English speaking and understanding with a score of 4/10 or higher / b) increase in competence measured through speaking and listening tests	a) Self-assessment / 49% of users rate their speaking at 4/10 or higher. / 59% of users rate their understanding at 4/10 or higher. / b) Testing / Increased competence: 49% of users show measurable improvement in their English language competency	a) Self-assessment / Speaking: 21% of all respondents rate their English language speaking skills at a rate of 4/10 or higher; in addition 35% for those highly exposed achieved this rate / Understanding: 40% users rated their English language understanding skills at 4/10 or higher / b) Testing / 56% of those tested have shown measurable improvement in their English language competency score for speaking and listening.
2. Employer satisfaction (with applicants’ / employees’ communicative English)	Applicants not having necessary EL skills: 35% / Employees having necessary EL skills: 92%	Applicants not having necessary EL skills: 31% / Employees having necessary EL skills: 93%
3. Motivation for learning and using English among school population of Bangladesh	English is very important: / Students: 60%; Teachers: 75% / English is difficult to learn: / Students: 55%; Teachers: 40%	English is very important: / Students: 95%; Teachers: 94% / English is difficult to learn: / Students: 33%; Teachers: 7%
4. Use of English Language news and media: online; broadcast or print based	35% improvement from baseline of estimated under 5% of population regular users	10% of population regular users (i.e. estimated 100% improvement on baseline of 5% regular users)
[note] Following 2014 Annual Review, logframe was revised and it was agreed not to measure this indicator for teachers in future.
[note] Trinity Grade Scale is developed based on the common European framework of language testing, developed to assess students’ English Language ability objectively. It is a 12-grade scale. Attainment levels for the first four grades on the scale is as follows: - Grade Level 1 – requires knowledge of greetings and some basic personal information - Grade Level 2 – speakers can offer and respond to short, simple questions, requests and statements relating to personal details and situations - Grade Level 3 – speakers can exchange basic everyday information, asking and answering questions using simple sentence patterns - Grade Level 4 – speakers can talk about a prepared topic, asking and answering questions about it
[note] Following 2014 Annual Review, logframe was revised and agreed not to measure this indicator. The indicator was valid for the initial part of the project and already achieved and reported in previous annual review reports. The milestone and progress figures are therefore from March 2014.
[note] As adult learning component closed in 2015, the evidence of achievement is from March 2014.

In the case of Outcome Indicator 1a (student English language competence), for the final phase at GESE level 2 criteria, primary students achieved 14% above target and secondary students achieved 2% above target. However, at the GESE level 3 criteria, while both Primary and Secondary improved by 2%, both sectors are 3% below the target. In general the project has done better in improving students at the lower grades. It is to be noted that the final outcome targets were set for achievement at the end of a full academic year of intervention. Nationwide unrest in 2016-2017 resulted in delays to start the intervention. Schools were only halfway through the intervention when the GESE assessment was conducted.
In the case of Outcome Indicator 1b (adult learner English language competence), the 2014 survey results show that tested language competencies exceeded target by 7%. On self-assessment of speaking and understanding achievement was below the target. In the case of Outcome Indicator 2 (Employer satisfaction with applicants’ / employees’ communicative English), the 2015 survey results show that the target has been achieved. In the case of Outcome Indicators 3 (Motivation for learning and using English) and 4 (Use of English Language news and media), the March 2014 survey results shows success in mobilising a change in attitude towards English language learning across the population as a whole. This was the last survey during the life of the project as it was deemed, and also evident from the results, that further intervention and study on motivation and use of English is not required.
In summary, the project’s overall achievements at outcome level have been broadly positive. In 2008 when the project commenced, many of the key features were regarded as either emerging and innovative approaches to teacher professional development and English language learning in a development context. In particular, this includes elements such as: the use of mobile technology for teacher development, use of mobile, web, electronic and print media for self-directed language learning; the use of peer-to-peer professional support for teachers.

Over the course of EiA these approaches have become recognised as models of international best practice and are increasingly integrated into the educational mainstream. The EIA project has largely contributed to this process. This is evident through the 12 international awards the project has received in its lifetime.

Within the adult learning component the project has been successful in designing cutting edge technology based learning platforms, reaching out to and engaging with more than its targeted population. It has supported the Bangladeshi youth and adults to engage with English language learning through courses available on a non-formal and self-directed basis. Based on learning from this project similar mobile and electronic media based platforms have been used by BBC Media action in DFID funded health programmes in Bangladesh.
[note] http://www.bbc.co.uk/mediaaction/publications-and-resources/research/summaries/asia/bangladesh/maternal-nutrition

Under the institutionalisation and sustainability component, the project operated at national and local levels within the government education system in a comprehensive manner. Key success factors have been building a trusted relationship backed up by evidence and strong technical knowledge. Achievements in terms of Institutionalisation & Sustainability (I&S) have prioritised the school component, and within that, the primary sector in particular. More detailed analysis on the above are under the relevant section for each output.

The project was strongly committed to the promotion of social inclusion through its activities. The methodology of implementation was ‘inclusive’ in itself e.g. availability of the trainer in the hands of the teacher (in mobile phones), peer support at school meant that training was easily accessible for female teachers without them having to travel long distances. Contents of teacher training materials included socially inclusive approaches and were socially and culturally sensitive, research and monitoring has been done taking into account a balanced sampling (gender, inclusion), communication materials reflected social inclusion practices for teachers.
Output Score and Description
The overall output is scored A+ at project closure. Results have exceeded targets in all outputs.
Lessons learned and how these have been shared
This section highlights the range of factors that have contributed to the overall achievements and challenges of the project across its lifetime.

Project design factors
- The extended (10 year) project duration: Enabled the project to design innovations, pilot interventions to test assumptions, scale-up based on lessons learned and to test what works at large scale, respond to emerging priorities, finally build up the trust and relationship with relevant counterparts for a successful handover. The time allowed the project to undertake extensive research to gain a thorough and detailed knowledge of context and learners and facilitated a continuous process of review and revision.
- The focus on research and funding flexibility: Allowed investment in audience research; development of high quality products with contextual relevance; development of a broad range of multi-platform media, which reached a broad section of the target audience; and deliver services at scale.
- The flexibility of project and logframe design: The project amended and updated the logframe to address some of the changing context and new priorities i.e. adding a new output, revision of the target from ‘reach’ to ‘learning outcome’. This was a result of flexibility and an adaptive management approach taken by DFID and the project consortium.
- The independence as a ‘project’ versus ‘government programme’: The project’s independent status gave it the autonomy to proceed with the innovations and timely implementation of key activities allowed EIA to work closely with local level stakeholders closely i.e. schools, upazila education officials.

Some of the challenges that have emerged from elements within the project design include:
According to the design, the Project Management Unit (PMU) was located within the Directorate of Primary Education (DPE). While this greatly benefited the institutionalisation process in primary, the secondary ministry perceived it as a Primary education programme rather than a sector-wide programme. As a result it was particularly difficult to gain traction in securing engagement, ownership and participation from secondary education institutions.
According to the project design the adult learning component (Output 2), implemented by BBC Media Action, had separate research and English language learning cells which were not included under Output 4 (research). As a result it was difficult to comprehensively co-ordinate and gain the full benefits of cross learning between the research and language learning activities of output 2 and 4.
Project delivery factors
Key factors that have contributed to the successful delivery of the programme include:
- Professional team: A committed project team with national and international staff with strong technical and administrative capacity and high levels of motivation.
- Commitment and approach: A project-wide commitment to foster a rigorous and context-specific approach to address needs at all levels. There was an emphasis to engage with local-level stakeholders to influence change at school and community level. A mature approach to institutionalisation and sustainability was used to focus on the integration of educational approaches and evidence-based principles rather than specific activities and delivery mechanisms.
- Flexibility: A flexible and adaptive approach to project delivery was used that enabled the project to respond to external factors, to pursue further contextual information and understanding when required, and to roll out new and additional interventions when there was evidence of their effectiveness in influencing change.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Greater access to and use of EIA English classroom methods for primary school teachers and students
Output number per LF		1	Output Score	A+
Risk:		Minor	Impact weighting (%):	25%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Reach: The cumulative numbers of teachers and pupils participating in English in Actions primary intervention	Primary teachers: 41,000 (50% F) Primary students: 3.0m (51% F)	Moderately exceeded target / Primary teachers: 42,708 (60% F) (4.2% over) / Primary students: 3.1 m (52% F) (3.3% over)
Practice: The number of teachers incorporating EIA approaches in their classroom practice.	20% student talk in a lesson / 60% of that talk is in English	Substantially exceeded target / 25% of the time students talk in a lesson / 91% of that talk is in English

Key Points
EIA’s Sustainability Impact report (2017) presents the evidence for these achievements. The proportion of student talk time i.e. 25% of the time students are talking meaning they engage in the classroom and of that 91% of the time they talk in English, is a significant change. This is in a context where most classrooms in Bangladesh are typically teacher-centric with low levels of interaction with or between students and in an English classroom even if students talk they mostly talk in Bangla.

Under Output 1, EIA’s primary school component was designed to enable primary teachers to improve the teaching practices in their classrooms through a one-year school based in-service teacher professional development intervention. The intervention included key elements like peer support; follow-up support and monitoring; support through head teachers; alignment of teacher training with curriculum and assessment; the use of offline Audio and Video (AV) materials and enabling technology such as mobile. Cumulatively, these features all work to support teachers and provide guidance to try out new activities in their classrooms. Perspectives from the teachers’ indicates that the offline access to AV materials (both for students and teachers), the role of facilitators and peer support, the phased approach of delivery and follow-up have been particularly effective in ensuring accountability and stimulating exchange of ideas and practice at classroom level.

During the last phase, the project put special focus for staff at Upazila level to work with the local education system, i.e. training, orientation and joint planning with Upazila Education Officers (UEOs), District Education Officers and Primary Teachers Training Institute staff (PTIs). This resulted in greater ownership from local government officials supporting effective implementation and monitoring of the project approach.
During the first phase, the project piloted an English reading intervention in 20 schools in partnership with a NGO called Friends in Village Development for Bangladesh (FIVDB) in Sylhet Division. With technical expertise from FIVDB 18 English Reading books were developed and teachers were trained. It was planned that after piloting, FIVDB would take over this initiative to scale up. But in December 2013, FIVDB’s funding from donors for education was closed and they had to hand over the schools to the community. However, out of 18 books, SHIKHON project of the Save the Children reprinted (around 20000 copies) 10 reading books for their non-formal schools.
Throughout its life the project was presented with on-going challenge of establishing and maintaining a consistent relationship with government counterparts due to the frequent transfer of key staff. In addition EIA operated as a discrete project, while this had its benefits, a real challenge was to ensure ownership of central level government officials. The Project Director of GoB Project Management Unit (PMU) played a positive role here. This has been discussed in greater detail under output 5.

Summary of responses to issues raised in previous annual reviews (where relevant)
The project has been responsive to issues raised and recommendations made in previous annual reviews under Output 1 throughout the lifetime of the project. Examples include, exploring the reasons for underperformance in the improvements in teachers’ English language skills in 2015; and the undertaking of impact research recommended in AR 2014.

Recommendations for future programmes
The project has come to end so there are no recommendations for the project. However some recommendations are made, based on lessons learned, for the stakeholders i.e. DFID, Government of Bangladesh and the project partners for future teacher development intervention in both primary and secondary.

- Evidence generated from project strongly suggests Teacher Professional Development (TPD) through school-based intervention is more effective cascade, center based or one off training models. This enables learning inside the classroom; contribute to early successes for teacher motivation and confidence; increases effectiveness of TPD training.
- Ensure that any TPD inputs follow a staged model of delivery, development and follow-up in order to facilitate change, rather than a block one-off training.
- Work through and build the capacity of district and sub-district teams of local Government Education Officers and teacher trainers as co-implementers. Work with them to adapt their local structures to improve effectiveness and sustainability.

Output Title	Enhanced availability and use of English learning media products
Output number per LF		2	Output Score	A+
Risk:		High	Impact weighting (%):	N/A
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N
[note] This rating was relevant in relation to institutionalisation and sustainability only.
[note] Following the closure of output 2 in 2015 the logframe was revised and impact weighting for this output was not applicable. Original logframe impact weighting was 25%.

Indicator(s)	Milestones	Progress
Reach: / The (cumulative) number of Bangladeshis regularly accessing BBC-produced EIA media products	8.5 million Bangladeshis regularly accessing BBC-produced EIA media products by 2017 (35% female)	Substantially exceeded target / 10.25 million are “highly exposed”, using at least one product five or more times (54% female)
Perception: / The proportion of Bangladeshis accessing BBC produced EIA media products, who report reduced barriers and increased positivity towards learning communicative English	43% of users report reduced barriers and increased positivity towards learning communicative English (47% of male and 35% of female users)	Substantially exceeded target / 60% of those exposed to BBC Janala products self-report increased motivation and/or confidence towards English (62% of male and 59% of female users)

Key Points
A Project Completion Review (PCR) for Output 2 was conducted in December 2015. The PCR report sets out a much detailed analysis of this output.

Under Output 2, English in Action sought to engage the Bangladeshi population and raise public interest in and motivation for learning English. This intervention also supported the Bangladeshi youth and adult population to access, engage with and learn communicative English language through courses available on a non-formal and self-directed basis. BBC Media Action led the implementation of this component under the brand name of ‘BBC Janala’. It included media-led learning modules across multiple platforms i.e. Television; Mobile phones; Online; mobile; Newsprint; ‘BBC Janala’ Books and CDs; and peer-led community-level English Clubs.

As shown above the output has substantially exceeded expectations of audience reach and user perceptions, with a high quality and innovative programme of activities which is recognised nationally and globally.

Against Output 2 Indicators, the project has:
- Exceeded targets for audience motivation and engagement in English language learning, through mass media campaigning and multiple means of access (e.g. Target: 8.5 million by 2017, 35% female. Achieved: 10.25million highly exposed, 54% female).
- Exceeded audience outreach goals (e.g. Target: 8.5million by 2017. Achieved: 28million accessed BBC Janala, 44million aware of BBC Janala products).
- Exceeded the development of high-quality educational media products across multiple platforms (e.g. TV programmes: Target: 24 episodes. Achieved: 110 episodes).

In addition other achievements of the project include -
- The development of structured language learning products (e.g. Amar Engreji) which has now been institutionalised through a partnership with a private organisation.
- The establishment of self-directed community-level forums (English Clubs), some are still being operated by the teachers at local level on their own initiative.
- The innovative use of media & technology to better support learning (e.g. learner tracking systems).
- Significant levels of engagement among lower socio-economic groups (SEC E) and female learners previously regarded as beyond project reach.
- Developing the skills of individuals within national broadcast media through media workshops, production competitions and work-placement on BBC Janala productions, bringing the added benefit of capacity building for the Bangladeshi media sector as a whole.
Secure the availability of English language learning materials beyond the life of the project.

A key driver for Output 2 is a rigorous and continuous process of audience research which has informed the development and regular revision of media and learning content, as well as the development of new adult learning initiatives. This has allowed learning to be locally contextualised in terms of both content and style, choosing the right delivery channels, evidence-based supported by formative research, supporting a range of learning styles.
Closure of output 2 has taken longer than expected. Activities ended in 2015 and it took almost two years to identify the right platform and mechanism to institutionalise the media products. The project completion review looked into the process of last two years. The tendering process continued throughout 2016-2017, the process has been delayed by the complexity of licensing issues and also the limited resources available to BBC Media Action, following the closure, to co-ordinate the process. However, it could be argued that the range of issues surrounding the complications of licensing could have been anticipated and accounted for at an earlier phase of project design. In addition, as discussed under Output 5 below, the project might have had better oversight of these and other issues had outcomes associated with the adult learning component been more fully represented within Output 5: Institutionalisation & Sustainability following the introduction of the I&S output in 2010.
The selected partners are Prothom Alo for newspaper learning content, BRAC to use their libraries for English language clubs and SSD Tech for mobile learning contents.

In terms of the project’s M&E mechanisms and safeguard arrangements to ensure quality, accessibility and affordability of BBC Janala materials, the partners have been selected based on their proposals to add value to the existing content; and their proposed channels, marketing and pricing – all of which will maximise access at low cost for BBC Janala’s target demographic. Licensing details include an annual monitoring exercise overseen or conducted by BBC Media Action and linked to license renewal. Partners will be required to provide data on content usage and audience figures, where available, on a regular basis.
Secondly, formal project support to English clubs ended in June 2014. As of June 2014, 17 English Clubs were run by CSOs, local NGOs, local educational and government bodies and 8 were run by international agencies. As the project is no longer monitoring or supporting the English Clubs, it is not clear how many or if any are still in operation two years after the closure. The project also noted that, based on anecdotal evidence, those English Clubs established and supported by CSOs and local NGOs have survived better than those clubs operating under large scale programmes, such as Save the Children.
[note] BRAC, Dhaka Ahsania Mission, POPI, Sharp, EC Bangladesh, Daffodil International University, ULAB, BMET, Jaago Foundation, Rupantar, UCEP, Uttaran, Shushilon, Amarok Society, RDRS, Dnet, Wave Foundation
[note] ActionAid, Asia Foundation, Practical Action, VSO, Hunger Project, UKBET, Population Council, EIA schools)
In terms of future and on-going activities, BRAC is now engaging with the remaining English Clubs networks and integrate the model into their Skills Development, Education, Migration Programme and a new intervention for university students. Accordingly BRAC allocated an initial investment of around GBP£25,000, with an aim to scale up nationwide if successful.
In terms of project responsiveness to issues raised in previous annual reviews, concern is flagged in relation to the institutionalisation and sustainability of the adult learning component. The handover of BBC Janala materials ahead of component closure were identified as a project priority in the Annual Review for 2014 and also reemphasised in two subsequent annual reviews. While the project sought to address this within the lifetime of Output 2, the process of handover has involved a protracted period of engagement.

Output Title	Greater access to and use of EIA English classroom methods for secondary school teachers and students
Output number per LF		3	Output Score	A
Risk:		Minor	Impact weighting (%):	25%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Reach / The cumulative numbers of teachers and pupils participating in English in Actions secondary intervention	Secondary teachers / 10,000 (69%/31% M/F) / Secondary pupils / 4.2m (48%/52% M/F)	Exceeded target / Secondary teachers / 10,563 (81%/19% M/F) / Secondary pupils / 4.3m (47%/53% M/F)
Practice / The number of teachers incorporating EIA approaches in their classroom practice	20% student talk in a lesson / 60% of that talk is in English	Met target / 20% student talk in a lesson / 85% of that talk is in English

Key Points
Under Output 3, the secondary teacher development programme was initially conceived of as a series of 4 interventions. Three of these were to utilise increasingly sophisticated media and technology: ‘Communicate’, using media players to support communicative language teaching (CLT) activities; ‘Connect’, using smartphones to build professional development networks and link classrooms; and ‘Create’, using multi-media laptops and digital cameras to produce digital media in English language medium. The fourth intervention, ‘Community’, was designed to work with boat-schools serving marginalised rural riverside communities.

However, after the launch workshops for the first and most straightforward media-based intervention (‘Communicate’), the project recognised a need to plan for interventions that were both realistic, in terms of existing capacity, skills and knowledge among secondary teachers and the systems that supported them, and simpler to implement. As a result, Output 3 has re-focused on establishing a basic foundation of effective classroom practices at scale, closely aligned with the approaches and goals associated with the government system and primary school component.

The design of the secondary development programme is also largely school-based and incorporates a similar selection of key elements identified in recent DFID funded rigorous literature reviews as the characteristics of effective teacher development programmes. The key elements of effective teacher development utilised by EIA include: peer support; follow-up support and monitoring; support through head teachers; alignment of teacher training with curriculum and assessment; the use of offline AV materials and enabling technology. Cumulatively, these features all work to support teachers and provide guidance and an enabling environment to try out new activities in their classrooms.
[note] Westbrook, J., Durrani, N., Brown, R., Orr, D., Pryor, J., Boddy, J., and Salvi, F. (2013). Pedagogy, Curriculum, Teaching Practices and Teacher Education in Developing Countries: Final Report. Education Rigorous Literature Review, EPPI-Centre, Social Science Research Unit, Institute of Education, University of London. P.60-64 and Power, T., Gater, R., Grant, C. and Winters, N. (2014), Educational Technology Topic Guide, available at: http://www.heartesources.org/topic/educational-technology/.

Using this model, the project met and in some cases exceeded its targets in terms of both reach and levels of improvement in classroom practices at secondary level. EIA’s Sustainability Impact report details the levels of achievement in terms of reach of EIA interventions through numbers of teachers trained; teachers’ use of EIA approaches, changes in classroom practice and teacher motivation, changes in teachers’ and students’ perceptions of English language learning; and changes in student learning outcomes.

The project faced some challenges to influence change in terms of institutionalisation and sustainability, due largely to the different administrative and systemic structure at secondary school level. This has been discussed in details under output 5. Under the current secondary school system, 98% of secondary schools are private institutions, with lower levels of control or influence from central and local level officials. In-service teacher training at secondary level is undertaken by individual projects, and not through a central or standardised government mechanism.

The project also encountered a number of wider practical challenges to the implementation of central and local-level activities at secondary level due to a different mechanism of Continuous Professional Development (CPD) of teachers; and less substantial GoB District and Upazila administrative infrastructure. As a result, the project was not able to achieve the same level of engagement and influence at Upazila level as in the Primary sector. At central level the absence of one programme framework (unlike primary where there was one sector programme) and working through multiple projects under the secondary education ministry made it difficult and unsustainable to house the EIA methods and materials. These were further compounded by the absence of a PMU counterpart within the Directorate of Secondary & Higher Education (DSHE), thereby making it difficult for the project to establish a formal route for engagement with DSHE.

In response to these challenges, during the final phase of the project, training to secondary teachers continued to be delivered at a local level under the EIA project mechanisms rather than in collaboration with local education systems (as was done in primary). In addition, more was also invested in establishing links between local officials and individual schools, and in intensifying the project’s working relationship with local level structures. This included local level staff capacity building to create a pool of skilled Teacher Facilitators, and strengthening the capacity of Upazila Secondary Education Officers and Academic Supervisors to observe classes and visit schools. Finally, during the final project year, the project established cross-sectoral Upazila teams, where Primary and Secondary sector staff collaborated to plan and implement strategies for the continuation of EIA-based approaches within Upazilas.

However, the review notes that taking similar approaches to engagement and capacity building at both central and regional secondary system mechanisms at an earlier stage of the project may have resulted in better outcomes, both in terms of project impact and sustainability. These and other issues are discussed further in this report under Output 5.

Recommendations for future programmes
Secondary schools operate in a less-structured system and with higher levels of autonomy when compared with primary schools in Bangladesh. This requires greater levels of direct engagement and use of alternative mechanisms, e.g. community-led mechanisms like SMCs and PTAs.

Output Title	Increased knowledge available around improving English language competency and teacher practice
Output number per LF		4	Output Score	A++
Risk:		Moderate	Impact weighting (%):	25%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of knowledge products developed	5 research reports / 4 research briefs	Substantially Exceeded target / 8 research reports / 6 research briefs
Amount of research disseminated via conferences/ book chapters/ presentations peer reviewed, journals chapters in academic books/ distribution of reports to key stakeholders in Bangladesh and to research databases	6 conferences / 2 papers / Distribution at GoB/PSC meetings	Substantially exceeded target / 17 conferences; 4 papers; 4 book chapters ; 1 book; Distribution at GoB/PSC meetings

Key Points
The EIA programme placed a strong emphasis on the importance of research and data-gathering as a core part of project activities and accordingly Research Monitoring and Evaluation (RME) was conceived as a separate Output within the project. The project exceeded both milestone targets against the two indicators of this output as shown above.
Following an adaptive programming approach the project improved its methodology by drawing on strong evidence from research and ongoing evaluation studies to assess the overall context and changes in the English teaching and learning environment in Bangladesh, both in the schools component (Outputs 1 and 3) and the adult learning component (Output 2).
Within the schools component, the project’s ongoing evaluation studies were directed at understanding teacher and student perception of teaching and learning English; examining classroom practice; and measuring teachers’ and students’ English language proficiency. The quantitative evaluations have been accompanied by explanatory qualitative studies, carried out by the Institute of Education and Research at Dhaka University (for perceptions and classroom practice) and by Trinity College London (English language proficiency).
In assessing these measures, at the end of 2011, the annual review reported that, through its pre-testing and post-testing of classroom practice and student learning outcomes, EIA’s research, monitoring and evaluation was a robust, rigorous and comprehensive one, that sets a good example for future such education intervention. This has been evident in all previous annual reviews and also in the assessment conducted by the external evaluator whose report fed into this report. In order to ‘raise the bar’ further, by 2013, DFID requested that the project provide stronger evidence of classroom practice and learning outcomes through experimental research approaches such as randomised control trials.
Building on this, in phase 4, jointly with technical input from South Asia Research Hub (SARH) EIA conducted a quasi-experimental study that sought to evaluate the changes in teaching and learning at EIA schools over time and compared it with changes in comparable non-EIA schools over the same period. This research allowed for causal inferences to be made about EIA’s impact in teaching and learning. The study found that the programme is leading to improvements in the teaching methods in EIA schools compared to control schools, and also provided indications that the programme is leading to improvements in the English language competency of students in EIA schools. However, while it was possible to assess the positive impact of the programme on teaching methods, unfortunately the study faced some set back on assessing learning outcome. The security situation in July 2016 delayed the scheduled intervention in classroom, as a result the intervention was not fully completed at the time of the study. This negatively impacted on making statistically robust inferences on the impact of the programme on learning outcomes.
Another innovative research initiative within the schools component was ‘Teachers’ Voice’, a programme of teacher-led action research assessing school-level teaching practice. Under this initiative, 167 teachers were provided with support and guidance to undertake small action research projects in their classrooms over a period of one year. The initiative encouraged teachers to gain insight into the challenges they face at school, in classroom and in terms of their professional development, including how students perceive their performance/teaching. This initiative provided evidence of the role that teacher-based action research can play an important role in informing improvements to the quality of teaching at school level.
The impact of this initiative has increased capacity, confidence and understanding of research among teachers. This came out clearly in the research reports and also the ‘teacher voice’ book. The role of teacher-led research as part of professional development programmes and informing programme design for teacher and student learning was also widely recognised. Based on its success and effectiveness, this action-research approach has been adopted by the newly-established Centre for Excellence at NAPE. NAPE will use its own research fund to pilot a year-long initiative, involving 8 selected PTIs across 8 divisions. In addition, NAPE indicated that the PTIs will also use this teachers led research approach as part of the DPEd primary teacher training programme.
The EIA-IER research collaboration was an innovative approach to develop national research capacity on English Language Teaching.  Three cohorts of young researchers completed a new M.Phil on ELT and Research, jointly designed by EIA, Dhaka University and the Open University. This included hands on experience of carrying out quantitative and qualitative research studies into EIA alongside their own M.Phil studies and fieldwork. A highlight of this work was the IER conference ‘ELT Programmes, Pedagogy and Research: Issues and Challenges’ in March 2014."
At an international level, research evidence generated from the project contributed to DFID’s Policy-Making for Teaching, authoring of the DFID Educational Technology Topic Guide; and international recognition of EIA’s research impact through a series of awards, including the ELTONs award for Local Innovation (2013), the PIEoneer award for Progressive Education Delivery (2017), and the Times Higher Education Award for International Impact (2017). EIA influenced programmes in other contexts, e.g. Teacher Development Programme (TDP) in Nigeria 2013-2019 (Cambridge Education); Zambian Education School-based Training (ZEST) 2017-2021 (Open University).
EIA has also disseminated its research and evidence through conferences, journal articles and book chapters under the themes of: English Language Teaching, educational research, international development, and technology and mobile learning. Details of these are set out in EIA’s sustainability impact report. Further outputs include the forthcoming book ‘Sustainable English Language Teacher Development at Scale’ (publ. Bloomsbury, London).
Recommendations for future programmes
Advocate for teachers inclusion in the design and delivery of national pre-service and in-service teacher education programmes.

Output Title	Collaboration with key organisations and professionals in the education and media sectors to adopt EiA approaches
Output number per LF		5	Output Score	A+
Risk:		Major	Impact weighting (%):	25%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones* milestones and targets are cumulative across Phase IV (i.e. 2015 to 2018)	Progress
Number and extent of strategic partnerships with key organisations in education and English language media sectors: number of sector professionals taking part in ELT media capacity initiatives	Education partnerships: / 5 or more (with better quality/deeper relations as evidenced through reports/minutes) / Existing media partnerships continue	Target met / 5 education partnerships: / with primary and secondary ministries, directorates, textbook board and teacher training apex body - NAPE; / Media partnerships handed over
Number of policy seminars with key decision makers on English language education policy reform to support communicative teaching and learning	4 policy seminars	Substantially exceeded target / 8 policy seminars
The (cumulative) numbers of local level education officers supported by English in Action	2250 officers orientated to EIA TPD approaches within Government structures	Substantially Exceeded target / 3,317 education officers oriented

Key Points
Institutionalisation and sustainability was added as a separate output following the 2010 annual review. In response to 2015 Annual Review recommendations, the project prioritised institutionalisation and sustainability as the main focus of project activities during its final phase.
The project’s approach to institutionalisation and sustainability has operated across three main alternative axes:
Engagement with central government: With support from DFID, EIA continued to strengthen strategic partnerships with key primary and secondary government ministries and departments. Institutional engagement with central government took place through formal mechanisms, such as Annual Development Plan meetings and other periodic GoB meetings. EIA’s dialogue with policymakers has been based on project’s evidence of how effective teacher development can be incorporated within government programmes to ensure quality and equity of classroom practice and learning outcomes.
[note] Directorate of Primary Education (DPE); Ministry of Primary and Mass Education (MOPME), Directorate of Secondary and Higher Education (DSHE) & Secondary Sector Education Programme, National Curriculum and Textbook Board (NCTB), and National Academy for Primary Education (NAPE).
EIA authored three design notes for the next Primary Sector Programme – PEDP IV (2018-2020). The design notes cover: in-service teacher development, pre-service teacher education and ICT in education. Collectively, these design notes constitute the core concept and principles of teacher professional development promoted by EIA. EIA teaching and learning approaches have been integrated into the Diploma in Education programme, and in-service English subject based training for teachers.

At secondary level, however, the same levels of programmatic integration have not been achieved as at primary education. Despite active engagement with the Teacher Quality Improvement project, EIA approaches have not been incorporated into revisions of the B.Ed for secondary teachers. However, since 2013 EIA has participated in the development of the Secondary Education Sector Program Framework. Key features of EIA’s approach can be seen in the new Secondary Education Development Programme Draft (June 2017).

A number of key factors impacted on the project’s engagement with government. First, the frequency of transfer of key GoB officials created a regular challenge for the project to establish and maintain consistent working relationships with key government officials. Secondly, EIA’s status as a discrete project outside the main primary sector programme influenced the ownership and engagement of GoB officials to support integration into the education system. Thirdly, the Project Management Unit (PMU) was situated within the primary directorate which made it particularly difficult for the project to gain traction to secure engagement and commitment from secondary education.

Institutionalisation and sustainability at local level: EIA’s primary strategy for I&S has been to build the capacity of local education officials, teachers and other educational staff to enable the shift of implementation from project to local education systems. Accordingly teachers, head teachers, education officials and teacher trainers were trained and actively engaged at school, upazila and district level.
As evidence of the quality of teacher development, 1,000 out of 1,311 EIA Teacher Trainers (who are GoB teachers) have been nominated as Government English Language Teacher Trainers who will continue to deliver EIA methods through mainstream training mechanisms.
Engaging the education officers at Upazila level was an important element for local level institutionalisation. Learning from the project showed that in places where education officers were pro-active and committed, EIA approaches were adopted in schools outside the project’s scope. This has also been evidenced by the review team during their field visit. Upazila education officers generated funds locally to support these schools with necessary equipment, materials and training. As part of phase-out strategy in the final project year, the project established Joint Upazila Teams with both Primary and Secondary education officials to develop short, medium and long-term plans to integrate EIA-based approaches into school-level practices.
[note] Teachers copied EIA Teacher Professional Development (TPD) resources (from mobile) and purchased speakers using school funds, incorporated discussion on EIA methods in GoB head teacher meetings and needs-based sub-cluster teacher meetings (in 41 Upazilas so far), arranged dedicated teacher development meetings (in 4 Upazilas reaching 287 schools so far), organised English language forums (in 28 Upazilas so far), created a pool of local resource persons for English TPD.
However, it is also acknowledged that for the continued success of this local I&S model, it relies largely on Upazila-level initiative and commitment by the education officers.
Access to and integration of EIA materials and resources: EIA’s third approach to institutionalisation was wide dissemination of resources, particularly the audio visual (AV) materials for teachers. The digital resources have been provided to Upazila Academic Supervisors, all Teacher Training Colleges, secondary district coordinators and National Academy for Education Management (NAEM). At a central level, all classroom audio recordings for Classes 1-5 are available on the DPE website, audio recordings that are referenced in the textbooks for all secondary grades are available in the NCTB website.

Secondly, at primary level, the new Teacher Guides for Classes 1-5 include EIA techniques and activities, including references to AV resources. Unfortunately in secondary, the same level of integration has not been achieved. However, EIA has worked with NCTB to embed EIA approaches into the new Teacher Curriculum Guides for Classes 6-8 that is being developed as part the new secondary sector-wide programme.

The long-term sustainability of the integration of EIA materials also has challenges. Without the active support from central government in terms of policy and strategy associated with curriculums, there is a possibility that EIA’s current content and materials may be partly or entirely removed from textbooks and teachers guides when the next series of revisions takes place, at some point within the next 2-5 years.

Institutionalisation and sustainability of Adult Learning component: Following the closure of this component in 2015, the institutionalisation arrangement of this component took much longer than planned. Some of these issues might have been addressed if Output 5 I&S explicitly included goals and targets associated with the Adult Learning component. As discussed in the overview of the project, for a range of reasons the Adult Learning component has, by design, operated in parallel to the Schools Component and the project as a whole, rather than as an integral part of the project. The absence of explicit I&S goals for the Adult Learning component is, to a certain extent, a reflection of this.

Summary of responses to issues raised in previous annual reviews
The project has been responsive to recommendations made in previous annual reviews throughout the lifetime of the project. For example, in response to 2010 Annual Review recommendations, the project developed this separate output on institutionalisation and sustainability. Similarly, in 2015, EIA developed Advocacy, Institutionalisation & Sustainability strategy covering the final 18 months of delivery. They also restructured internal mechanisms in order to focus on I&S priorities.
Recommendations for future programmes
- Ensure that from the outset of the project, strategies associated with institutionalisation and sustainability are featured as a key component of design framework, together with appropriate resources and capacity.
- Use of evidence to support advocacy for programme institutionalisation i.e. credible research showing improved learning outcomes; demonstrate affordability and cost-effectiveness of any innovation compared to existing government programmes.
- Use the strategic advantage and role of DFID and other donors to facilitate engagement with government through formal platforms.
## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
EIA’s approach has been school-based teacher development in order to achieve high scale and high impact at low unit cost. In SBTD, training resources can be developed and recorded in advance, reproduced, and distributed to large numbers of teachers, with positive results. While significant fixed costs are incurred in developing the training resources, the variable costs of reproducing and distributing those resources and supporting their use for each additional teacher is low. The main costs associated with the project were in-person training, meetings and support for teachers, development of audio and video materials and multimedia equipment. These costs have been falling over time since the beginning of the programme because of technological changes and improvements in the programmes’ operating model.

VfM performance compared to the original VfM proposition in the business case
Unit Cost	Phase 3	Phase 3	Phase 4
Equipment	£225	£81	£2
Reproduction and distribution of materials	£105	£35	£15

Economy: During the initial phases, the input costs of the teacher-training component were high because of the cost of equipment used. The programme provided Apple iPods to teachers so that they could watch tutorial videos and expensive portable PA systems to schools to use in the classroom. After the pilot phase, the programme switched from providing iPods to low cost mobile phones that could play video. As mobile phone ownership became ubiquitous across Bangladesh, the programme stopped giving mobile phones to teachers. Instead, it handed out memory cards loaded with training material that teachers could watch on their own phones. The programme also stopped providing speakers and asked schools to buy them from their own funds. Because of these efforts, the programme achieved a 100-fold reduction in the cost of providing digital teaching and learning material, from £225 in 2010 to £2 in 2016.

Cost per teacher trained	Phase 3	Phase 4	Total (Phase 1-4) / (incl cost of multimedia content)	Government
Primary school	£496	£94	£203	£43
Secondary teacher	£575	£322	£718	NA
[note] Includes management costs and overheads

Efficiency: EIA trained 7,015 primary school teachers during phase 3 and scaled up its activities to train 34,245 teachers during phase 4. Up to phase 3, EIA provided substantial in-person support and supervision to teachers after the initial training, which caused the cost per teacher trained to be high. While scaling up in phase 4, EIA had to reduce the in-person support to keep the programme financially and managerially viable. The programme made use of government facilities for training and government sub-district education officials to support teachers. This, along with the use of lower-cost equipment, helped reduce the cost per primary teacher trained from £496 in phase 3 to £94 in phase 4. In comparison, the government’s one off subject-based training costs £43 per teacher that does not include any follow up support or materials for teachers.
[note] These costs do not include the budget for developing the multimedia training material incurred during phase 1.
[note] English in Action estimate

The programme incurred substantial up-front cost of developing the multimedia teacher training and teaching material. Taking these costs into account, the average cost per primary teacher trained comes to £203. For secondary schools, the average cost per teacher trained comes to £718. The inclusion of the EIA material into the government’s teacher training programme will improve the VfM of DFID’s investment as the material will be used to train teachers nationally.

Classroom teaching practices	Phase 2	Phase 3	Phase 4
% of student talk in lessons	27%	27%	25%
% of that student talk that is in English	81%	91%	91%

Effectiveness: The expected outcome of the teacher training intervention was improvements in the teaching of English by using techniques and material taught through the programme. To assess this, EIA monitored the use of communicative language teaching approaches, which advocates greater classroom interaction with students. The two indicators monitored were student talk time as a percentage of lesson time and the percentage of student talk that is in English. At baseline, students rarely used English in the classroom (2-4% of lesson time). Following EIA’s teacher training, students talk accounted for 27% of total lesson time in the classroom and over 91% of this was in English during phase 3. This suggests that the programme was effective in improving teaching quality. The classroom practices outcomes were very similar in phase 4, despite reduced in-person support and oversight by programme staff. The use of English by primary school teachers in classroom also increased from 27% of talk time at baseline to 71% in phase 2.

Research evidence shows that even teachers who were not trained by the programme, but taught in sub-districts where EIA operated, improved their teaching practices. This is likely a result of EIA material being gradually included in the government’s teacher-training curriculum. In addition, many teachers also got access to EIA multimedia content during joint meetings and training sessions at sub-district education offices. Monitoring visits by DFID staff to over a dozen intervention schools in different districts found that English teachers had participated in the training and many had EIA digital content saved on their phones. However, most teachers stated that they rarely used EIA audio teaching material during lessons. Programme staff also reported that the use of EIA material was higher in phases 2 and 3 compared to phase 4.

Cost effectiveness: DFID commissioned a research study to assess the impact of the programme on teaching quality and learning outcomes. The study compared students in a sample of schools that received EIA training to students in a control group of similar schools that did not receive the intervention. By the time the research was conducted, the EIA methods and materials were institutionalised through the government education system and it was likely that the control group teachers were also able to access it. The research results showed that teaching quality and English competency in both the treatment and control groups improved. Thus it was not possible to conclusively determine the impact of the intervention. As a result, the review team was unable to assess whether the intervention was cost-effective.

Media and adult learning component
The programme substantially exceeded its targets for producing multimedia English learning content for television, mobile phones, internet and newspapers. For example, BBC Media Action produced 110 episodes of a TV series against a target of 24 episodes and 674 mobile audio lessons against a target of 125 lessons. BBC Media Action also conducted nationally representative surveys to measure the reach and impact of the BBC Janala content. The surveys suggest that the programme exceeded its targets for audience reach and use of the content. An estimated 28 million people used BBC Janala products, of whom over 10 million people used it more than five times. This compares to a log frame target of 8.5 million people regularly using BBC Janala products. These indicators suggest that the programme performed very well in terms of the efficiency of outputs and effectiveness of outcomes.

Assessment of whether the programme represented value for money
The programme trained 53,271 teachers leading to significant improvements in teaching practices, reaching 7.4 million students. Students also improved their English language competency following EIA teacher training although it was not possible to directly attribute this to the programme (i.e. make a causal inference). EIA methods are now used by the government to train primary teachers as it has been incorporated in government materials as part of I&S objective. All primary teachers now receive teaching guides from the government that include EIA methods. This will help the teacher training intervention achieve greater value for money, as it will generate benefits beyond its lifetime.

The data and analysis above suggests that the school-based teacher training components represented good value for money in terms of the economy of inputs and efficiency of outputs. The research and monitoring data also suggests that intervention likely provided value for money in terms of effectiveness of outcomes (i.e. improved quality of teaching). As such, as described above, it was not possible to ascertain whether the intervention was cost effective. The adult learning component also represented good value for money in terms of its efficiency of output and effectiveness of outcomes. But the cost effectiveness could not be assessed as it was not possible to estimate its impact.

Quality of financial management during programme
The quality of financial management over the life of the programme was strong. Invoices have been submitted on a monthly basis in a timely manner for DFID assessment and approval before submitting to DFID HQ for final processing. The invoices have been accurate and where DFID had queries the project team responded promptly. However, during the final phase challenges were faced with forecast and actual spend of monthly funds as the main intervention (training) was dependant on availability of GOB facilities (to reduce costs). Financial reports were supported by a narrative explaining monthly budget variance, setting out how these have occurred, possible impact on future spend and also how the project propose to minimise the impact of these variances to ensure that specific DFID financial commitments are met (ie December and March expenditure milestones). EIA has ensured cost controls are in line with the contract. The project has identified and delivered efficiency savings throughout the current project year e.g. a comprehensive exercise was carried out based on which the project prepared a gradual phase out and exit plan. This allowed the project to close divisional offices earlier than expected, resulting in savings.
Date of last narrative financial report	December 17 (Year 10 Quarter 3, Oct – Dec 17)
Date of last audited annual statement	February 2017 (1 April 2015 to 31 March 2016)

E: RISK (½ page)
Quality of risk management over the life of the programme
The quality of risk management over the life of the programme was high. The initial ‘Low’ risk assessment was adjusted to ‘Medium’ during the Mid-term Review. Political unrest at a specific point during the project was a major challenge: in one year, approximately 120 days were lost as a result. The flexibility of planning and responsiveness significantly reduced the impact on project outcomes. The risk assessments were upgraded largely with regard to concerns about sustainability, and, in 2014, the risk assessment was rated ‘High’. At the time of project closure the institutionalisation and sustainability of some activities of adult learning under Output 2 remain high risk. The project has enacted a process of handover to counterparts, but the process is yet to be completed.

The original Project Memorandum identified 5 key risks. The risks and summary outcomes across the project lifetime are as follows:

Risk: Political/policy change – High level political commitment not maintained
The Government has been heavily involved in the programme with a view to implement and continue the core concepts and principles of teacher professional development. High level policy has remained favourable towards the need for English language skills and a learner-centred education focus. Actual implementation of the policy by the Government has been a challenge. This gap was addressed by working closely with other development partners, which has led, for example, to developing the three design notes for primary sector programme.

Risk: Lack of training capacity developed
A skilled pool of Teachers has been developed; local education officials have been engaged as leaders of change. However, associated capacity development within both the primary and secondary sectors at central level happened at much reduced levels. The project’s substantial work with local stakeholders has been crucial to achieving its results.

Risk: Sufficient human and physical resources are not made available
Formal platforms like project steering committee meetings under the purview of MOPME and continued relationships at local level ensured human and physical resources were available on a timely manner. Investment in relations with central and local Government stakeholders enabled participation of teachers and local stakeholders. During the final phase of the project, schools and teachers procured or used their own equipment in the classroom. During the final phase of the project, delivery of training was done using government facilities.

Risk: The programme design and its envisaged scale up leads to reduced quality and impact
Evidence and progress made during the scale-up and institutionalisation phases demonstrated that quality and impact have remained high. From the initial design, the school-based nature of the programme helped achieve high scale and high impact at low unit cost. It is notable that, at much increased scale, classroom practice changes were maintained e.g. in Phase IV, students’ use of English is 91% in primary and 85% in secondary lessons.

Risk: Corruption in the procurement of goods and services
Procurement of goods and hardware was undertaken by Crown Agents throughout the project. They have provided safeguards against fraud and corruption. There were also controls and monitoring in place by Mott Macdonald to limit this risk. The project control system and a series of internal and external audits did not detect evidence of corrupt practices.

Subsequent risks identified during the programme, plus summary outcomes, include the following:

Risk: Funding shortage – Due to the effects of exchange losses by the depreciating GBP
Robust and regular discussions between DFID and the project produced various options to manage the potential funding shortage whilst ensuring that all the targets were met. Continuous budget analysis and the decision to close the project in December 2017 mitigated the risk while still enabling the project to exceed all the logframe output targets.

Risk: Reduced project human resources as project moves to closure
The commitment, dedication and flexibility of the staff helped to minimise early staff losses. An exit strategy plan was developed that included contract end date of staff according to project closure plan. A small number of key staff left earlier than planned e.g. the Head of Communications & Dissemination. To address this gap the Head of Materials Development were given additional responsibilities to cover this role with support from communication specialists of Cambridge Education and the OU.

Risk: Security - Civil unrest affecting project operations
During 2016, an approximate 120 days of project input were lost. The disruption resulted in overlapping teacher training and delayed the start of some training. Engaging the Teacher Facilitators (previously trained teachers) widened the project resource pool to address the overlap and minimise delays. Nevertheless, as a result of the implementation delay, caused by the unrest, schools were only halfway through the intervention schedule at the time of the quasi-experimental post-testing. The consequence of this has been captured in previous section (under output 4).

Risk: Asset management and disposal – risk of loss of assets
The project has maintained and checked lists of assets which was spot checked by DFID. During 2014 four laptops were registered as lost/stolen and reported to local police. This incident was reported to DFID fraud unit and accordingly actions were taken. The managing agent paid back the cost of the laptops. EIA further tightened its Anti-Fraud Policy aiming to reduce any risks related to misappropriation of funds and equipment; key issues around the policy have been shared amongst the EIA staff and beneficiaries. The project has now completed assets disposal and hand over of assets following DFID guidelines.
Risk: Institutionalisation and sustainability
Under Phase IV of the programme, the main risk for EIA was ensuring the institutionalisation and sustainability of the EIA content, methodology and materials. In addressing these challenges, EIA enhanced the Advocacy and Institutionalisation & Sustainability Strategy to effectively and efficiently address the challenges. This has resulted in parallel approaches to advocacy and sustainability working simultaneously with central and local Government, including developing focused knowledge products for stakeholders.

Key risks include whether the private sector agencies taking on the BBC Janala media products will continue to offer the learning materials at affordable prices to all. This is one of the Request for Proposal (RfP) evaluation criteria, but it remains to be seen how this will roll out in practice. The future of English clubs has been dependent on individual NGOs and CSOs. In this context, BRAC’s proposal to integrate the clubs model into existing groups and activities within their Skills Development Programme, Education Programme and Migration Programme offers significant sustainability.

Risk: Chance of fraud
EIA has an Anti-Fraud policy, which has been in place from the beginning of the programme. Following the decentralisation process during the final phase of the project i.e. setting up cost centre at divisional level, the project was exposed to risks of fraud. Further controls were set up to address risks through this new decentralised structure. A fraud suspicion in 2015 tested the system and showed that EIA had the right mechanisms in place to pick up and address any suspicion. EIA reported its suspicions to DFID immediately and were able to investigate and take necessary action following advice from DFID Fraud unit.

F: COMMERCIAL CONSIDERATIONS (½ page)
Delivery against planned timeframe
All project inputs have been delivered within the overall planned timeframe. However, substantial flexibility and responsiveness was needed in the face of the loss of working days due to political unrest and security concerns from 2015-2017.
Performance of partnership(s)
EIA is led and managed by Cambridge Education, with consortium partners The Open University-UK and BBC Media Action. The Adult Learning component (Output 2) ended in 2015 as originally planned.

The partnerships on the EIA project and on Output 2 have performed well. However, it is possible that changes to early project conceptual design might have ensured greater synergies between partners in delivery across all components and in particular between Outputs 1 & 3 (Schools & Teacher Training) and Output 2 (Adult Learning & Media).

Under these Outputs, individual project partners took exclusive responsibility for technical delivery of specific components. There are a number of common areas across these Outputs where the project might have benefitted further from greater coordination and exchange supported by each partner’s technical expertise and professional experience. Areas include: language learning and assessment; pedagogic design for ELT; multi-media and mobile technologies; and audience research approaches.

With reinforcement from DFID, collaboration and exchange between technical partners improved after 2012, with the managing agent facilitating inter-component collaboration over communication & research and the sharing and development of ELT materials. However, it may have been beneficial to put in place at the project outset the formal mechanisms that would have a) supported mutual approaches to development and exchange, and b) ensured that DFID kept the process of inter-component exchange in full view throughout the project lifetime. Such an approach presents a model for ensuring: greater project efficiencies; reduced duplication; improved sharing of expertise; better cohesion and interaction between EIA partners; and more effective project oversight.

In terms of the projects relationship with Project Management Unit (PMU), discussion with the Project Director (from GoB) suggested that overall it was positive and supportive. The Project Director and team members are government officials who understand the system and facilitated access to government departments. The PMU was funded from the revenue budget. At the initial stage, however, there was no dedicated project director for EIA. Directors from Directorate of Primary Education (DPE) were assigned as PD with additional responsibility. This sometimes created difficulties with timely execution of project activities and also ensuring leadership. It was overcome after a full time Project Director was appointed in Aug 2013.

The PMU arranged government approvals which ensured effective implementation of project activities. Being a senior government official, the PD represented EIA at different meetings and events. He visited EIA classes and provided updates in various government forums particularly at the Annual Development Plan (ADP) meetings (Monthly project meetings at Senior Government level Chaired by the Secretary). The PMU organised experience sharing meetings at divisional levels using the government revenue budget which was attended by senior government officials including the Secretary MOPME. Overall PMU played active role in raising project profile.

Asset disposal and value obtained by DFID
Asset disposal and handover has been completed for all outputs in accordance with DFID’s approved processes. Prior to the closure of the project, usable and unusable equipment and furniture were sold following standard DFID procedures. The project vehicles and equipment i.e. mobile phones and speakers have been handed over to government and schools for further developmental use. As part of the exit strategy and gradual hand over to GoB, teachers are now using their own mobile phones to access materials and 85% of schools now procure speakers using their own funds.  This is a huge achievement and demonstrates potential the sustainability of the programme after closure and also reduces the risk of loss of these assets.

H: MONITORING & EVALUATION (½ page)
Evidence and evaluation
In general terms, including ‘research, monitoring and evaluation’ as one of five outputs for the overall project has ensured that the quality of evidence and evaluation undertaken remained consistently high. It started with pre-testing and post-testing of classroom practice and student learning outcomes, and then moved to a quasi-experimental study. In addition, there was also ongoing internal project monitoring. Project staff and government officials monitored classrooms and sent results back to the central team – data was collated and fed back to the teams for their learning and actions.
In relation to the schools component, EIA evaluation studies have helped to understand teacher and student views about teaching and learning English; examining classroom practice; and measuring English language proficiency. Over the project lifetime, large-scale quantitative evaluations have been accompanied by more explanatory qualitative studies. Evaluations were carried out by the Institute of Education and Research at Dhaka University (for perceptions and classroom practice) and by Trinity College London (English language proficiency) as independent bodies.
EIA has been able to add to the global knowledge and debate around teacher professional development, by proposing a specific model based on 5 elements and by putting teachers at the centre of the classroom, and evidencing what works in the classroom and to build teachers’ capacities. Field visits and meetings with government officials for the purpose of this review and also through interactions demonstrated that the project is well respected and valued for its effectiveness in improving classroom teaching and teachers confidence in teaching English.

In relation to the adult learning component, as noted in the PCR for Output 2 (2015), initial evidence and evaluation measured achievement of against a) audience reach and awareness raising, and b) changes in attitude towards English language learning. The introduction of outcomes i.e. measuring impact on English language competency (in 2011) and the Theory of Change associated with impact of learning on economic status (2013) required the project to develop new tools and approaches to gather evidence. This enabled the component to become more exploratory in its scope and expand its activities to include the design of learning content, the delivery of non-formal education and the establishment of community-level initiatives.

Finally, it is important to note that the initial and follow-up audience research studies were central to the formative evaluation of the project. For example, in the early stages it showed that broadcast radio was not an appropriate channel to reach the target audience in Bangladesh. Later, when the programme was fully operational, it revealed the demand for English learning within the economically marginalised (Sec E) audience segment. The audience studies were conducted with much larger samples than would typically be seen in educational planning. BBC Media Action’s quality assurance procedures ensured robust supervision of researchers and verification of results.

Monitoring progress throughout the programme
The monitoring of progress has been consistent throughout the programme. Regular quarterly project steering committee meetings have been held with DFID throughout the life of the project that reviewed quarterly progress and plans. Both independent and DFID internal (consisting of members outside the lead team) annual reviews conducted every year to assess progress against milestones. While the Annual Reviews have differed in scale and detail from year to year (e.g. AR 2010 and 2015 described as ‘light-touch’), they have frequently undertaken substantial analysis and also challenged programme assumptions and expectations, at times significantly. The programme’s focus on central and local institutionalisation, programme sustainability, and evidence-based advocacy have, in particular, been substantially enhanced as a result of responses to recommendations arising from Annual Reviews throughout the project lifetime.
The project completion review has been led by DFID Bangladesh’s Education Adviser with input from the programme manager and economic adviser and quality assured by the Team Leader (Human Development). This review is based on an independent analysis that was conducted by an external consultant with support from DFID B. The process included document review, data gathering, meetings, interviews, focus group discussions, field visits and data verification. The EIA team supported the whole process and prepared the necessary background papers to assist the review. The review team interviewed the EIA project team, GoB staff, teachers, local level education officials and students. The list of documents reviewed, meetings held and field visits are attached as annex A.
ANNEX A

List of document reviewed – Project Completion Review February 2018

Sl	Documents	Document Brief	Current Status
1	Final ToR for Project Completion Review (PCR)	PCR Terms of Reference from DFID	Uploaded in EIA extranet
2	Presentation for Review Team	EIA 10-year impacts and journey	Uploaded in EIA extranet
3	PCR 2017 reporting template	Outline of project and summary of achievements and lesson learned	Uploaded
4	DFID Project Review reports 2009-17	(i) Annual Review reports 2009-2017 / (ii) Annual Review 2017 action plan / (iii) Output 2 PCR report	Uploaded
5	Logical framework	Logical framework, showing 10-year achievements	Uploaded
6	Impacts reports	(i) Impacts summary at local, national & international levels / (ii) Post PEDP3 design notes for pre-service teacher education, in-service teacher education and ICT & education / (iii) SEDP framework highlighting EIA-promoted approaches	Uploaded
7	Lessons learned	(i) Lessons learned through the implementation of EIA, 2008-2018 / (ii) EIA draft book, to be published by Bloomsbury (pre-final review and pre-edit)	Uploaded
8	Research reports and briefs	(i) Quasi-experimental study / (submitted to AR2017) / (ii) In-school development / (iii) Upazila-led implementation / (iv) TVC book extracts (draft) / (v) QE & QS research brief	All uploaded in EIA extranet
9	Closing events and knowledge products	Uploaded	Uploaded
10	Risk matrix	Project’s assessment of risk and mitigations	Uploaded
11	Value for money	(i) Value for money overview / (ii) 10-year financial perspective plan	(i) Uploaded in draft / (ii) Uploaded
12	Project steering documents	(i) Original Project Memorandum + Technical Annex / (ii) Memorandum of Understanding with Government / (iii) Revised Development Project Proposal (DPP) with Government	(i) Uploaded / (ii) Uploaded / (iii) Uploaded

List of meetings held and people met for PCR November 2017
Project personnel
Sl. No.	Name	Designation	Event	Date
01.	Sue Williamson	Team Leader	Meeting & presentation on EIA at DFID	At various points of the review field work
02.	Marc Van der Stouwe	Project Director EIA
03.	Claire Hedges	Programme Coordinator - Open University, UK
04.	Bikash Chandra Sarker	Head of Communications and Materials Development
05.	Sudeb Kumar Biswas	Head of Teacher Training
06.	Zahir-Bin-Siddique	Deputy Team Leader

Government officials and teachers
Sl. No.	Name	Designation	Event	Date
01.	Prof. Md. Moshiuzzman	Member (Curriculum) - NCTB	Meeting at NCTB	November 19, 2017
02.	Mr. Abdur Rahmim	Senior Specialist - NCTB
03.	Abe Hena Mashukur Rahman	Senior Researcher - NCTB
04.	Raihana Taslim	Deputy Projector Director - TQI II	Meeting at TQI II project
05.	Prof. Dr. S. M. Alamgir Kabir	Project Director - English in Action	Meeting at PMU-EIA
06.	Mr. Iftakher Hossain Bhuyian	Deputy Director-Training, DPE	Meeting at Training division, DPE

Field visit (Government officials and schools)
Dhamrai Girls High School, Dhamrai; Sultanpur Azizia Govt. Primary School, Raozan; Raozan Brister Shoresh Bidyatan, Raozan; Kodomtali Abedia Model GPS, Doublemooring; Postarpar A. K. City Corporation Girls’ High School, Doublemooring

Sl. No.	Name	Designation	Event	Date
1	Umme Habiba Begum	Head Teacher:	School Visit at Dhamrai Girls High School, Dhamrai	November 15th 2017
2	Surma Begum	Teacher
1	Tabsira Islam Liza	UEO, Savar	Meeting with Upazila Team at Savar, Dhaka
2	Nilufa Yesmin,	AUEO, Savar
3	Pali Rani Sarker	AUEO, Savar
4	Mrs. Afroja Khatun,	AUEO, Savar
5	Mina Parvin,	AUEO, Savar
6	Wasma Afrin	AUEO, Savar
7	Safiqul Islam Patwary	Teacher Facilitator, Savar
8	Parvin Akter	Teacher Facilitator, Savar
9	Monirul Islam,	Teacher Facilitator, Savar
10	Rashida Khatun	Teacher Facilitator, Savar
11	Sajeda Khatun	Teacher Facilitator, Savar
1	Ashok Kumar Sarker	Head teacher	School visit / Raozan Brister Shuresh Bidyatan, Raozan	16th November 2017
2	Pranab Kanti Shill;	Teacher
3	Arun Kumar Baidya	Teacher
1	Chowdhuri Abdullah Al Mamun	UEO, Raozan	Upazila Team at Raozan, Chittagong	16th November 2017
2	Md.Hasanul Kabir	AUEO, Raozan
3	Md.Mijanur Rahman	AUEO, Raozan
4	Md. Abdul Mohaimen	AUEO, Raozan
5	Md. Abu Sufian	AUEO, Raozan
6	Md. Abdul Momin	AUEO, Raozan
7	Mohammad Amranul Hoque	Teacher Facilitator, Raozan
8	Kazi Mohammad Jalal Uddin,	Teacher Facilitator, Raozan
9	Mosammat Shahinoor Begum	Teacher Facilitator, Raozan
10	Showmen Barua,	Teacher Facilitator, Raozan
11	Sidul Chandra Nath,	Teacher Facilitator, Raozan
12	Md. Saiful Islam,	USEO, Raozan (secondary)
13	Sajol Chandara Chanda,	UAS (secondary)
14	Md. Azizul Haque	Teacher Facilitator, Raozan (secondary)
15	Madhab Roy, Teacher	Facilitator, Raozan (secondary)
16	Rina Chakrabarti	Head Teacher	School Visit at Kodomtali Abedia Model GPS, Doublemooring	16th November 2017
17	Mohammad Idris	Teacher
1	Md. Nezamul Haque	Head Teacher:	Postarpar A. K. City Corporation Girls’ High School	16th November 2017
2	Fahmida Nazir Musa	Teacher:
3	Md. Sarwar Kamal,	Instructor, URC Doublemooring	Upazila Team at , Doublemooring, Chittagong	16th November 2017
4	Tapan Kanti Dey,	ATEO, Doublemooring
5	Lipi Rani Gope	ATEO, Doublemooring
6	Kamrunnahar,	Teacher Facilitator, Doublemooring
7	Mohammad Azad	Teacher Facilitator, Doublemooring
8	Iqbal Parvez,	Teacher Facilitator, Doubelmooring
9	Mohammad Idris,	Teacher Facilitator, Doubelmooring
10	Rumi Chakraborty,	Teacher Facilitator, Doubelmooring (secondary)
11	Fahmida Nazir Musa,	Teacher Facilitator, Doubelmooring (secondary)
	Mr. Sultan Mia	Divisional Deputy Director - Primary, Chittagong	Meeting with government officials Chittagong	November 16, 2017
	Mr. Rafiqul Islam	Superintend, PTI, Chittagong
	Ms. Surur Jahan Banu	Principal, Teacher Training College, Chittagong
	Sudeb Kumar Biswas	Head of Teacher Training, EIA
03.	Mr. Mir Abu Shalah Samsuddin	Lecturer, Teacher Training College, Chittagong
07.	Prof. Md. Shahidul Amin Chowdhury	Divisional Manager, Chittagong