Project Completion Review - Top Sheet

This Top Sheet captures the headlines on the programmes performance over the course of its lifetime. Teams should attach summary sheets from each annual review over the life of the programme.

Review Date:	Nov 2017

Title: Bangladesh Policy Fund
Programme Code: P0050	Start Date: Nov 2007	End Date: March 2018
If programme was closed >1 month early please describe in a few words why.	The changing context of funding and programming in Bangladesh has resulted in the Bangladesh Policy Fund being under-used.

Summary of Programme Performance

Year	2012	2013	2014	2015	2016
Programme Score	A	A	A	B	B
Risk Rating	Minor	Minor	Minor	Minor	Minor

Financial Position

Original Programme Value	£2.5m
Extensions/ amendments	£2.7m – Oct 2013
Log-frame revisions (with dates)	October 2013 / July 2014
Total programme spend	£2,770,491.79

Follow up actions required following closure

DFID Bangladesh to consider additional means of influencing Government of Bangladesh policy and running early-stage testing on new approaches to complex development challenges that have the potential to be scaled up or replicated.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/4573813.odt
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/4781423.xlsx

Outline of programme and what it has achieved
The 2013 business case for extending the Bangladesh Policy Fund (BPF) described the BPF as being designed to fund targeted, strategic activities to inform and influence the work of the Government of Bangladesh, other development partners and civil society.

The objective of the BPF was to improve pro-poor policy and interventions in Bangladesh to help meet the Millennium Development Goals and wider development aims.
 Projects were envisaged to fall into three categories:
1. Research studies – to generate and disseminate new evidence to inform policy development and programming.
2. Stakeholder consultations – to bring together key stakeholders to share experiences, lessons and approaches to inform policy development and programming.
3. Pilot projects – to test out new approaches to complex development challenges that have the potential to be scaled up or replicated.
During its 3.5 years of operations from 2013 (following a previous phase), the programme achievements included:

2014
Bangladesh Bank Initiative for Financial Education (£121k, March 2012 to August 2013,
score 2) The project supported Bangladesh Bank’s campaign to improve financial literacy and
consumer protection. The campaign focussed on improving understanding of basic financial
issues and raising awareness of the benefits of banking, targeting groups including school
children, women and small and medium sized enterprises. It also sought to help vulnerable
groups protect themselves from abusive financial practices and prevent them from being
overburdened by debt. Project activities included developing a user-friendly website to explain
basic financial issues and direct users to sources of consumer protection, broadcasting radio
and television commercials to promote responsible banking, and publishing messages in
leading daily newspapers to raise awareness of the risks of transacting with non-licenced
banks.

2015
Quarterly Macro-Economic Policy Briefings (£62k, December 2013 to May 2015). This project built on the success of a previous round of Macro-economic policy briefings supported by the Policy Fund in 2013. Its main aims were to increase the overall level of awareness and understanding of macro-economic reforms and to help keep Bangladesh on track against its commitments in the IMF Extended Credit Facility. This was done through four high-profile seminars which linked thematic experts with policy makers responsible for driving reforms. Written briefings were also disseminated to wider groups (e.g. donors, media and civil society).

2016
DFID provided £355,648 to the Bangladesh Youth Leadership Centre (BYLC) as a contribution to its fourth three day Youth Leadership Summit  from 18-20 August 2016. The 2016 theme was ‘Rediscovering Identities and Breaking Barriers for an Inclusive World’. Approximately 400 university students and young professionals from all corners of Bangladesh and 30 plus youth delegates from abroad attended the summit, representing a diversity of religions, educational and socio-economic backgrounds. The Summit was also attended by Ministers, senior government officials, parliamentary and business representatives.

Examples of projects supported under the BPF earlier phase (pre-2013) included:
- Supporting Social Protection Policy Reform in Bangladesh (£177k, 2011-2012)
- Addressing Violence Against Women and Girls in Bangladesh: From Evidence to Policy (£50k, 2011-2013)
- Independent Transparency, Accountability and Monitoring Mechanism for the Bangladesh
- Climate Change Strategy and Action Plan (£25k, 2012-2013)
- Supporting Civil Society Representatives to Attend UN General Assembly and Scaling Up Nutrition Global Events (£4k, 2011)
- Support for the Proposed Investors’ Forum, Bangladesh (£8k, 2010-2011)
- Bangladesh Food Security Investments Forum – Policy Options  for Food Security Investments Plan of Bangladesh (£19k, 2010)
- Mapping Nutrition Interventions in Operation in Bangladesh (£19k, 2009)

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Overall Outcome Assessment

This Project Completion Review assesses progress up to the time of closure, rather than the expected achievements of the programme up to its original end date in March 2018.

As identified in recent Annual Reviews, the BPF has supported too few projects to meet expectations in its latter years. But as it had funded some interesting interventions in its earlier phases and looking at that as a whole on balance the PCR score is A.

The BPF was underutilised in its latter years largely because of the changing context of funding and programming in Bangladesh, DFID Bangladesh staff capacity engage with small projects and partially due to the burdensome application process, making the fund less attractive to potential applicants.

Output Score and Description

The programme’s overall score is: A – Outputs met expectation .

Lessons and how these have been shared

More time was needed to manage the small projects than was envisaged in the design of the BPF.

Monitoring and evaluating influencing activity was very challenging. Follow-up evaluations did not provide adequate evidence of impact.

The influence of small scale discussions and seminars was difficult to evaluate.

The concept of a flexible fund for small strategic intervensions was sound, but in practice DFID Bangladesh did not have the staffing capacity to manage such a fund internally to reap its potential.

Ultimately the two key design elements that led to the failure of this fund, was the overly ambitious estimate of DFID staff capacity to engage with the small projects, and the long and complicated application and reporting format for relatively small grants, making the fund unattractive to potential applicants

These lessons have been shared with DFID Bangladesh Senior Leadership Team.

C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Quality interventions funded through the Policy Fund
Output number per LF		1	Output Score	A
Risk:		Minor	Impact weighting (%):	60
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of interventions which / score 1 or 2 upon project / completion	Evidence that the purpose / achieved. Average project score is 2 or above.

Key Points

In the Annual Review Period August 2015 - August 2016, the Policy Fund supported one project:

Bangladesh Youth Leadership Summit (£355,648, August 2016)

DFID provided £355,648 to the Bangladesh Youth Leadership Centre (BYLC) as a contribution to its fourth three day Youth Leadership Summit  from 18-20 August 2016. This year’s theme was ‘Rediscovering Identities and Breaking Barriers for an Inclusive World’. Approximately 400 university students and young professionals from all corners of Bangladesh and 30 plus youth delegates from abroad attended the summit, representing a diversity of religions, educational and socio-economic backgrounds. The Summit was also attended by Ministers, senior government officials, parliamentary and business representatives.

As part of the closure of the Bangladesh Policy Fund a review of the 2016 financial support to the Bangladesh Youth Leadership Centre was recommended.

Review of the Bangladesh Youth Leadership
The BYLC ran a Youth Leadership Prize with the funding from the BPF. It was found to be an informative and interesting experiment demonstrating the potential and power of socially conscious young people, and what impact they could create with leadership training and funding.

The winning projects verified that young people were creative and resilient when it comes to creating change. However, there were some factors, some personal and some infrastructural, that created challenges for the groups to execute their projects effectively. Through this process, BYLC gained insight into how leadership training impacts young changemakers, and what can be done better to support such initiatives.

Key findings:
It would be more impactful if groups underwent a few weeks of technical training on specific areas such as financial planning and management and managing human resources
- The first round application required a lot of details and dissuaded people from applying, for future programs. A simpler first application was needed.
- 10 months was not sufficient time for the groups to research, execute operations, and assess their ownimpact.
- A team of three people oversaw the projects. It would have been more effective if individual mentors were connected to each project to ensure that all groups received equal attention and support.

Summary of responses to issues raised in previous annual reviews (where relevant)

The 2014 Annual Review was only able to review one of the three projects funded. There had been implementation delays on the other two. The project reviewed (the Bangladesh Bank Initiative for Financial Education) was awarded a score of 2 (purpose largely achieved).

Overall the 2014 AR found the projects funded were were aligned to DFID Bangladesh’s strategic priorities, but the fund was underutilised, largely due to limited staff capacity to develop small, strategic interventions.

The 2015 Annual Review found that the BPF had supported two projects: Policy Fund (Macro-Economic Briefings) had completed, to budget and with only minimal delay (May 2015 rather than the planned March 2015). In terms of outputs, the project partners PRI, delivered 4 workshop seminars, each of which were well attended with prominent Chief Guests. Workshops were supported by briefings and press coverage. A number of limitations however, and the outstanding evaluation, made it difficult to ascertain the extent to which these discussions and the supporting work influenced policy.

The second project (Bangladesh Leadership Challenge) was delayed due to a lack of interest. The format of the training was re-designed and participation costs decreased (identified as currently being a key barrier to participation). The project partners hoped to begin delivery at the end of 2015.

Overall the 2015 AR noted the lack of new applications and the feedback from advisers and the changing context of funding indicated the need for a review of the Policy Fund and the strategic space. The AR also noted that the application and evaluation process was out of balance with the budget sizes and the strategic influence that such small and discrete projects could have.

The 2016 Annual Review found only one project supported, the Bangladesh Youth Leadership Center (BYLC) which delivered the ‘Bangladesh Youth Leadership Summit’. The Summit was to convene and develop young leaders to do work on inclusion and tolerance. This project was found to fit well with the UK’s wider approach to supporting peace, stability and good governance in Bangladesh.

Recommendations for future programmes

Careful consideration needs to be given to the availablility of staff capacity to run these types of funds. It cannot be assumed that because a project is financially small that it will only require a small amount of staff time to run it. The application and reporting process needs to be proportionate to the size of funding on offer.

Output Title	Interventions designed and prioritised to ensure strategic and added value for the DFID Bangladesh development programme
Output number per LF		2	Output Score	A
Risk:		Minor	Impact weighting (%):	40
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Extent to which interventions are aligned with and complement the strategic priorities of DFID Bangladesh.	All successful applications demonstrate fulfilment of this criteria.
Implementation of follow-up activity and monitoring of longer-term impact of projects.	Dissemination and follow-up strategic activity and monitoring took place for all projects where relevant.

The Policy Fund has received no applications in its last year and so no prioritisation was undertaken. The Fund provided no added value to the wider DFID Bangladesh programme during its final year. Over the lifetime of the BPF it has on balance add value to the DFID Bangladesh programme so the Output met expectations.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

Projects were funded by the BPF on an ad-hoc basis as need and opportunity arose.

VfM performance compared to the original VfM proposition in the business case
The Policy Fund constituted less than 0.5% of the DFID programme budget in Bangladesh. The value for money premise for the BPF was its potential to leverage policy and programmatic change through relatively small, strategic investments.
The assumption was that the BPF had the potential to test innovative approaches to complex development problems, which if successful could inform the development of more effective, larger programmes that offer greater VFM.
It was further assumed that the BPF could support VFM by saving staff time that may otherwise be required to develop disproportionately detailed Business Cases for small interventions.

The last two Annual Reviews found limited evidence to support these assumptions.

For each individual project funded the vfm was assessed at the project level. The assessment considered: economy (the price of the research, pilot project or other intervention), efficiency (how well these inputs are converted into quality projects that add strategic value) and effectiveness (the contribution to evidence based policy making and pro-poor interventions).
The vfm assumptions were not realised in the second phase of the BPF, primarily because the much more DFID staff time was needed than envisaged to run small projects (often as much time is needed to run a small project as large project).
The result was that there was low incentive for DFID staff to propose projects for the fund, as there was no additional capacity within teams to manage the small projects. Where projects were identified the lengthy application form made the fund unattractive to potential applicants.

Based on the assessment above the concept of the BPF was sound, but for it to realise is full vfm it required a dedicated member of staff to run it and seek out ideas and support applicants.

Assessment of whether the programme represented value for money

Not in its second phase. This assessment was supported by the 2016 Annual Review. However, while the project underperformed it also underspent, so funds were released to be used more productively elsewhere.

Quality of financial management during programme

The 2016 Annual Review found that the quality of the single project funded by the BPF, the Bangladesh Youth Leadership Centre (BYLC), financial management was satisfactory. The organisation’s expenditures are audited by well-regarded audit firms in Bangladesh. DFID had reviewed all the past audit reports and the findings were found to be satisfactory.

Date of last narrative financial report	N/A
Date of last audited annual statement	N/A

E: RISK (½ page)

Quality of risk management over the life of the programme

The greatest risk for the BPF has consistently been the risk of funds not being spent. This has borne out with the programme underspending due to lack of quality applications and delays to projects.

Risk management of the projects has been good. Risk was assessed for each proposal before being submitted for approval.

The risk of funds not being used as intended was found to be low. The Bangladesh Policy Fund did not support large-scale procurement or long-term activities where the risks of fraud are greater.

The lead DFID Adviser and Programme Manager for each project funded were responsible for monitoring fiduciary risk and project progress. No concerns were identified in any projects during the life of the BPF

Outstanding actions from risk assessment

None.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

No realised and BPF was closed early.

Performance of partnership (s)

Project evaluations were challenging. There is limited evidence of strategic value added and limited evidence of the effectiveness or longer-term impact of the projects on policy influencing, because this was hard to measure given the nature of the projects.

Asset disposal and value obtained by DFID

Not applicable – none of the projects had DFID assets.

G: CONDITIONALITY (½ page)

Partnership principles assessment

Not applicable.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

Monitoring and evaluating influencing activity is very challenging. Activities and outputs are easier to measure than outcomes or impact. Assessing the extent to which specific outputs contribute to general outcomes of influencing policy and programming is a challenge. This becomes more challenging with small descrete projects with limited resources (both financial and human), as a result there was insufficient evidence to say whether there was strategic value added and limited evidence of the effectiveness or longer-term impact of the projects on policy influencing.

Monitoring progress throughout the programme

Throughout the life of the BPF the individual teams who proposed and monitored projects work closely with the delivery partner to undertake light touch monitoring of the projects.

Smart Guide
The Programme Completion Review is the opportunity to reflect on the entire programme, its performance, achievements, lessons and how learning will be shared to inform future programming.

The Programme Completion Report assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with headline information on the programme and any follow up actions / Early closure is likely to be summed up by issues such as ‘poor performance by partners’ and/or ‘major changes in operating environment’
A: Introduction and Context
Briefly outline the programme, results achieved and contribution to the overall Operational Plan and DFID’s international development objectives. Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Outcome Assessment / Brief assessment of whether the programme achieved the Outcome
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Output Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on AMPas part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Minor/Moderate/Major/Severe / Enter: Minor, Moderate, Major or Severe / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Where the Risk for this Output has been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section E Risk
Key points
Summary of response to issues raised in previous annual reviews (where relevant)
Recommendations for future programmes
Repeat above for each Output.
D: Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case. Performance against vfm measures and any trigger points that were identified to track through the programme / If programme was closed >1 month early please describe in a few words why, what savings were made, as well as what money was spent.
Assessment of whether the programme represented value for money? / Overall view on whether the programme was good value for money
Quality of Financial Management during programme / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E: Risk
Quality of risk management over the life of the programme. / How were risks managed, the degree to which they were realised and/or mitigated? / Did any risks materialised throught the duration of the programme which were not forseen? What where they and how was this managed? / What lessons have been learned?
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / Could DFID be a more effective partner
Asset disposal and value obtained by DFID / How were assets managed throughout the programme? How have they been (or will they be) disposed to get maximum value?
G: Conditionality
Partnership principles assessment / For programmes where we have decided to use the PPs for management and monitoring, PCRs should generally include an assessment of commitment to the PPs, including any concerns that have occurred over the year, the partner government’s response, and details of any response by us. Teams should refer to the DFID guidance on reviewing projects.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the programme / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review and PCR process