## SUCCEED Annual Review – 2024
Title: Support, Comprehensive Care and Empowerment for People with psychosocial Disabilities in Africa’ (SUCCEED Africa)
Programme Value £ (full life): £6,941,625		Review date: August 2024
Programme Code: 301134-101	AMP start date: / 18/03/2020	AMP end date: 30/04/2026

Summary of Programme Performance
Year	2021	2022	2023	2024
Overall Output Score	A	A	A	A
Risk Rating	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	N/A
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/90000777.xlsx

A. SUMMARY AND OVERVIEW

Description of programme

Mental health and psychosocial disabilities are among the top five causes of the global burden of disease and are the leading cause of years lived with disability. People with psychosis are among the most excluded groups in society and have a range of concerns that are not addressed by health services alone. There is little evidence from low- and middle-income countries (LIMCs) and particularly from sub-Saharan Africa, to guide decision-making and programming to reduce exclusion of people with psychosis. There is also little evidence on how to involve people with psychosocial disabilities in research or decision-making.

SUCCEED Africa (‘Support, Comprehensive Care and Empowerments for people with psychosocial Disabilities in Africa’) aims to address these gaps, generating new knowledge of ‘What Works’ for people with psychosocial disabilities, particularly focusing on psychosis – schizophrenia, bipolar disorder and other psychotic disorders.

SUCCEED is delivered by a consortium of experienced research institutions: Centre for Global Mental Health, London School of Hygiene and Tropical Medicine (LSHTM); Kamuzu University of Health Sciences, Malawi; University of Ibadan, Nigeria; University of Makeni, Sierra Leone; and University of Zimbabwe.

SUCCEED operates on the principle of co-production: that people with psychosis and their supporting systems are ‘experts by experience’, who are best positioned to define their needs and how to address them.
Over the course of the programme, SUCCEED will:
- Synthesise existing evidence on co-production and psychosocial disabilities in Africa;
- Develop, using principles of co-production, a sustainable, multi-sectoral package of care and support in community settings based on principles of Community Based Rehabilitation (CBR). This package will be evaluated in a randomised controlled trial.
- Generate new knowledge on co-production for mental health research, modelling best practice in disability inclusion, addressing stigma, and building the capacity of people with lived experience to engage meaningfully in mental health research and policy.

SUCCEED’s progress and achievements are shared through its website and twitter account.

Summary supporting narrative for the overall score in this review
The SUCCEED programme has scored an A for its achievements and progress over year 4. Overall, it met the milestones for all three outputs and is well set to continue its strong progress into the forthcoming year.
The most notable achievement this year is the successful running of the pilot intervention. This required a substantial amount of time and effort and was done in the programme’s typically inclusive and collaborative way of working.
Over its fourth year, SUCCEED moved through collating the formative research, finalising the draft intervention manual and associated training package, and piloting its intervention across the four countries. The learning from the pilot has now been used to update the manual and training and inform the final protocol and detailed study design for the full evaluation phase. The result is that at the start of year five, the final intervention plus study protocol are ready, and the main trials and process evaluations are primed to start implementation.
Alongside the pilot work, SUCCEED continued to support capacity building, notably through provision of training for writing papers, and increased its Comms and Research Uptake activities.

Major lessons and recommendations for the year ahead

- The time and effort that went into developing the pilot has paid dividends this year with a result that learning from this has already been put into developing all of the documents, plans and operations for the full trial and evaluations.
- Likewise, the time and effort that has gone into support for writing papers has begun to show progress through the successful publication of six articles (links in output section below), with many more in progress.
- Capacity building has continued to be a strength for the programme this year with promotion of the Comms lead in Nigeria and the Principal Investigator in Zimbabwe.
- The FCDO SRO and Programme Manager attended the SUCCEED annual programme meeting in Malawi during year 4. This was an invaluable experience, not only in getting a broader and more in-depth understanding of SUCCEED but also to meet members of the team from all of the sites, including many of the Peer Researchers. It also enabled more detailed monitoring of all aspects of the programme. Further information on the visit can be found in section G.

Recommendations
1. SUCCEED to build on the momentum and achievements from the pilot intervention to begin delivery of the full trial and evaluation across the four countries. Ongoing.
2. SUCCEED to build on the progress with publications and to continue the support provided to researchers, especially those in the four programme countries and in the early stages of their careers. Ongoing.
3. SUCEED has £3.7m remaining with under two years of the programme left with large underspends each year due to delays to activities. Recommendation for SUCCEED to plan spend in advance and assure forecasts are accurate. Ongoing.
4. SUCCEED have almost completed contract amendment 4 to realign the budget and have advised a new contract amendment will be requested shortly. Recommendation to not depend on consistent amendments as these are at the discretion of FCDO finance business partner. Amendment 5 to be completed by end of calendar year. Ongoing.
5. Going into year 4 of the programme the SUCCEED website is still not clear and should include high-quality media outputs which can be shared with colleagues and the public. Improved Comms and Research Uptake outputs, including better use of the website, publication of blogs, policy briefs are essential. This should include details of the higher-level policy work and influencing that the programme needs to do to be successful in the long term. End of 2024 for website updates including publications.
6. SUCCEED generally produce lengthy quarterly and annual reports which can be difficult to navigate due to the volume of information. Recommendation to reduce the length of quarterly and annual reports. Q1 Yr5
7. SUCCEED to ensure successful running, plus follow-up of the MOOC (massive open online course). Q2 Yr5

Progress against last year’s recommendations
	Recommendations	Actions
1	Assign responsibilities within SUCCEED team to respond, including timeframes. / Improved communication within SUCCEED team with regular internal meetings to discuss priorities.	This has improved, however there are still timeframes where e-mails do not get answered or we are waiting on specific pieces of work. / SUCCEED to ensure that prompt responses are provided to FCDO programme team.
2	SUCCEED to provide further training in financial management and to revisit forecasts with partners during each financial reconciliation to help achieve more precise budgeting. (ONGOING) / SUCCEED to request accurate monthly forecast figures plus detailed financial information from each partner. (ONGOING) / FCDO request invoice narrative with invoice, to explain the quarterly expenditure. (ONGOING) / FCDO will request invoice two months after quarter rather than six weeks.	SUCCEED PM has gone on maternity leave and some of these actions have fallen away. FCDO still require monthly forecasts, financial narrative with each invoice and reduced underspends. / FCDO PM to discuss with SUCCEED PM on how to improve these recommendations, possible monthly calls.
3	SUCCEED to review the timelines for all phases of the programme with a view of being accurate and realistic, and to aid with financial planning. / SUCCEED to review logframe outputs, indicators, weightings, timing and targets	A detailed review of the SUCCEED workplan and logframe were done this year to ensure that programme delivery is planned and managed effectively. / Output 4 (Governance) was removed from the logframe, with the remaining outputs re-weighted. Changes and additions were made to several indicators.
4	SUCCEED to increase proactive monitoring of the safety of researchers and participants, to report potential incidents promptly and to implement adaptations to delivery where required.	As part of the trial design, SUCCEED has written in additional measures to monitor the safety of participants and researchers. This will continue to be an important aspect of programme delivery.
5	SUCCEED to make better use of its website and social media to share its outputs and reach a broader audience [Ongoing] / SUCCEED to update FCDO on relevant content and to join comms working group [within three months of review]	SUCCEED to provide quality media outputs which can be shared within FCDO research department and more widely. / SUCCEED to update website on a continuing basis. / Recommendation rolled over as above.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The Theory of Change (ToC), developed with all country teams, defines the overarching approach of the SUCCEED programme. Country-level ToCs built on this, with specific information related to the country contexts and intervention. The main hypothesis is that an evidence-based enhanced package of care for people with psychosis in community-settings, developed through an inclusive research process, will be more effective in improving the outcomes that matter most to people with psychosocial disabilities, when compared to enhanced usual care alone.

In year 4, the ToC was reviewed in detail at the annual SUCCEED programme meeting, alongside the findings from the pilot phase of the study. The discussions ensured the ToC’s supporting evidence and assumptions continued to hold up against the work done so far. In addition to this, a cross-site ToC specifically designed for the evaluation component of SUCCEED was developed. This was done in order to provide a simple and user-friendly version of the map to guide the country teams when delivering their work in the field.
Similar reviews of the ToC will continue to be undertaken at future programme meetings.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The programme’s outcome is:
Policy makers, state and non-state actors, draw upon SUCCEED research to guide policy reform, increase investment, and change programming practice in mental health care at community and services levels.
Indicators are:
1. Mental health and related sectoral policies and frameworks integrate principles of Community Based Rehabilitation (rights-based, person-centred and comprehensive approaches) at national, regional and global levels.
2. People with lived experience are involved in research and implementation guidelines
During year 4, SUCCEED has started to demonstrate good progress against the outcome indicators. Peer Researchers have been involved in developing local law and policy documents, and have also contributed to two documents published with the Global Mental Health Peer Network (GMHPN) guiding participation of people with lived experience in mental health research. Learning from SUCCEED has informed an International Disability and Development Consortium position paper on safeguarding in development and research with people with mental health conditions.
Members of SUCCEED have contributed to the Africa Countdown to 2030 dashboard on priority indicators for mental health, supported development of guides and training related to people with lived experience and other models and surveys run by GMHPN.
[note] Countdown Global Mental Health 2030 is a global monitoring platform that draws upon a range of factors and indicators, from economic performance to attitudes to mental healthcare, to measure the current state of global mental health.

The programme’s expected impact is:
‘People with psychosocial disabilities in sub-Saharan Africa have a better quality of life, more choice in their care, and participate equally in the community, in services and in global mental health research’.

Although this is a high-level indicator to which SUCCEED can only contribute, the programme has made a promising start towards influencing global actors and policy. SUCCEED has continued to work closely with the GMHPN and the Mental Health Innovation Network and to ensure that people with lived experience are actively involved in research. This year, an MSc project was completed to identify priority indicators for impact of the programme using Delphi process. Unfortunately, the finding was that quality of data available made this an unreliable metric to use. Work, therefore, continues in this area to identify better metrics.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

The SUCCEED programme has scored an A overall, having met the majority of milestones during the past year. SUCCEED adds value to and aligns with FCDO’s Mental Health and Psychosocial Support plan, with strong focus on participatory and rights-based approaches. It is aligned to the WHO’s Special Initiative for Mental Health and will provide an important contribution to gaps in evidence on mental health in LMICs.

The SUCCEED programme remains relevant to FCDO’s overall development strategy and health research portfolio through its ambitions to strengthen health systems and address specific health challenges – with a focus on mental health. There are still critical research gaps in mental health, particularly in poor communities and for women and girls, and the work being implemented by SUCCEED should make a direct contribution towards FCDO’s approach to global health, improving people’s lives and tackling poverty. Furthermore, SUCCEED focuses on working in partnership and collaboration with organisations in the global South.

During year 4, SUCCEED’s pilot intervention was successfully run and used to develop the trial and evaluation, both of which will take place from year 5. Given its ongoing successes and outputs to date, it is clear and justified that SUCCEED should continue.

## C. DETAILED OUTPUT SCORING

Output Title	Research outputs are generated by SUCCEED
Output number:		1	Output Score:	A
Impact weighting (%):		34%	Weighting revised since last AR?	Yes

Indicator(s)	Milestone(s) for this review	Progress
1.1 Number of open access externally peer-reviewed research publications on inclusive community mental health, psychosis and/or involvement: / country-level articles / cross-site articles	a) 12 articles submitted (cumulative) / b) Peer researcher involvement on every paper	Met / a) 2 country-level articles (1 published, 1 submitted) + / 8 cross-site articles (5 published, 3 submitted) / b) all publications include at least one peer researcher
1.2 Number of grey literature reports (scoping reports/situation analyses, DPO mapping, research synthesis reports). Includes national reports, cross-country reports, manuals and trial reports	a) 1 training manual (pilot) b) 4 training reports (pilot) c) 1 intervention manual (pilot) d) 4 situational analyses, 1 per country	Mostly met / a) training manual complete (post pilot revision), and being used for training b) training reports not published separately but assessment in all countries fed into post-pilot update c) Intervention manual finalised (post pilot) and being used in sites d) draft policy report developed for each country
1.3 SUCCEED contributes to external research collaborations: / a) Collaboration on knowledge synthesis/thought leadership / b) Linked research programmes nested within SUCCEED, or with which SUCCEED collaborated / c) Collaborations on research mentorship/hosting students	a) Progress on Lancet commission / b) 2 linked research programmes funded (cumulative) c) Host 3 students for MSc, PhD or fellowship (cumulative)	Met / a) Commission has been reconfigured by the Lancet. b) SUCCEED worked with the NIHR-funded homelessness and psychosis project (HOPE) in Ethiopia plus the Wellcome-funded psychosis research (PROMISE) in Malawi. c) Collaboration with United for Global MH/Harvard on a global mental health dashboard - MSc student completed Countdown 2030. SUCCEED staff have started PhD student (London) and one MPhil student (Nigeria)
1.4 Evaluation of CBR intervention through a pilot study and large scale evaluations	a) Receive ethical approval to begin pilot trial / b) pilot trial training delivered in all countries / c) Conduct pilot study in 4x countries / d) Initiate analysis of pilot data / e) Develop protocol for evaluations in Y5 / f) Submit ethics applications for evaluations taking place in Y5	Met / a-c) Received ethical approvals, delivered pilot training and conducted pilot study in all four countries / d-f) initial pilot data analysis carried out and used to inform the main study development / e-f) Ethics applications submitted at all sites

Briefly describe the output’s activities and provide supporting narrative for the score.
Overall, SUCCEED has met this Output.
Work this year has delivered the first publications from the SUCCEED programme, which is a real achievement and the team has also made substantial contributions to other reports, collaborations etc. The main achievement this year was the successful running of the pilot programme. This was a big piece of work to develop and run, and has already provided invaluable evidence to inform development of the main trial. Alongside all of this has been the critical involvement of peer researchers in all aspects of writing and the pilot.

1.1
SUCCEED has published six articles this year, with a further six submitted or in the later stages of writing.
- Interventions for adolescents and adults with psychosis in Africa: a systematic review and narrative synthesis
- Reprioritising global mental health: psychoses in sub-Saharan Africa
- Lessons of Hope and Resilience: A Co-Produced Qualitative Study of the Experiences of Youth Living with Psychosis During the COVID-19 Pandemic in Nigeria
- Cracks that let the light in: Collective reflections on integrating lived experience of psychosis in research and policy in the context of a global commission*
- Co-Producing Research on Psychosis: A Scoping Review on Barriers, Facilitators and Outcomes
- Community-based rehabilitation for people with psychosocial and intellectual disabilities in low- and middle-income countries: A systematic review of the grey literature
The efforts that the SUCCEED team has put into increasing their publications is starting to be demonstrated and should improve throughout the remaining programme time.

1.2
The SUCCEED sites collaborated on the development of a standardised situation analysis template. Four grey literature reports were produced, one by each country team, with the intention of publishing a cross-site paper to bring this work together. This is the first cross-site paper for the programme and it has proved quite challenging; however, it is now being led by an experienced researcher from the Nigerian team and is in the review process. Alongside this, the team has worked hard to develop the documents required to support design and delivery of the pilot intervention.

1.3
SUCCEED is now recognised as the leader on inclusive and participatory approaches to mental health research with other groups and organisations learning from the work done so far. The SUCCEED programme and several members of the team are collaborating widely on this aspect of work – for example, the Wellcome and Edinburgh University flagship psychosis research programme in Malawi (PROMISE) and a project focused on homelessness and psychosis (HOPE) in Ethiopia, Ghana and Kenya, with King’s College London. Furthermore, SUCCEED Peer Researchers have joined the consultancy service offered by the Global Mental Health Peer Network, and are working on developing guidance for research organisations to better inform their engagement in global mental health research.

1.4
During this year the SUCCEED team has successfully developed and delivered the pilot study to test their intervention. This included receiving ethical approvals from all partner sites and LSHTM, delivering pilot training and conducting the pilot study in all four countries. This was followed up with pilot data analysis, which was used to inform the main study development and the submission of ethics applications at all sites.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

A detailed review of the SUCCEED logframe was carried out this year. Output 4 was removed with the remaining outputs re-weighted resulting in an increase from 30% to 34% for output 1. Amongst other minor changes, an additional indicator was added (1.4) to track progress of the pilot and trial.

Progress on recommendations from the previous AR, lessons learned this year and recommendations for the year ahead

Progress on previous recommendations:

- Additional support for publications: as demonstrated above, the time and effort put into this is starting to show and should result in increased publications by the SUCCEED team.
- Update indicators: text relating to the Lancet commission was updated. Indicator 1.4 was added to track progress on the study pilot and trials, including a breakdown of activities that better reflects the time and effort going into this work
Recommendations for Yr5
1. Development and delivery of the full trial in two sites (Nigeria and Zimbabwe) plus smaller-scale evaluations in two sites (Malawi and Sierra Leone). Ongoing throughout Yr5.
2. Continued support for publications, with an emphasis on early career researchers. Ongoing.
3. Continued involvement and engagement of peer researchers in all aspects of the programme. Ongoing

Output Title	Capacity built among SUCCEED research and non-research personnel; research Institutions; partner organisations (focused on national Disabled Persons' Organisations)
Output number:		2	Output Score:		A
Impact weighting (%):		33%	Weighting revised since last AR?		Yes

Indicator(s)				Milestone(s) for this review	Progress
2.1 Number of individuals in the consortium who demonstrate increased capacity in research skills, management of research, research supervision/teaching, or communication of research. / Disaggregated by: / - Gender / - Peer Researchers/ Managers / - Researchers/ Managers in LMIC / - early career researchers				a) LMIC researchers deliver mental health research training for DPO/NGO in country. b) Delivery of 12 capacity building workshops (30% delivered by country site members) c) MOOC launched/delivered. 400 sign up and 200 complete.	Met / a) LMIC researchers involved in implementation NGO training in each country, and in DPO training in Zimbabwe, Malawi, Sierra Leone b) 20 capacity building workshops delivered (35% delivered by country site members) c) Estimate launch in Y5 Q2.
2.2 Research Institutions have developed and adopted policies or good practice guidelines in participatory approaches.				a) 2 consortium Universities adopt policy or good practice guidelines for co-production. b) Discussions to adopt commenced by the remaining 3 consortium Universities.	Met / Supported a good practice guide for engagement with lived experience researchers which has been co-developed with the Global Mental Health Peer Network.
2.3. Peer Researchers demonstrate skills to communicate their priorities throughout research process, and in external communication of research priorities. / a) Level of Peer Researchers participation in SUCCEED oversight (CAG, LAG and LEAP meetings) / b) Number of external research processes, consultation, funding calls that Peer Researchers from SUCCEED countries contribute to				a) 6 Examples of Peer Researchers leading meetings (all LEAP meetings) (cumulative) b) 3 examples of external processes (cumulative)	Met / a) Peer researchers participated in the Y4 LEAPs and CAGs, and took a lead role in organising and presenting in country LAGs. b) Peer Researchers contributed to the Countdown to 2030 Africa Indicators, Mental Health Policy change in Sierra Leone and the Lancet Psychosis series. They joined the Global Mental Health Peer Network consultancy service.

Briefly describe the output’s activities and provide supporting narrative for the score.
Overall, SUCCEED has met this Output.
SUCCEED has continued to demonstrate good progress and a strong capacity building element. The programme has held many workshops, meetings, etc that have delivered on this area with strong involvement from country partners and with strong engagement with peer researchers and people with lived experience. The main area where the programme hasn’t met its target is delivery of the MOOC. There are internal issues within LSHTM that are currently holding this up but the team are confident of delivery in Yr5.

2.1
Programme staff based in the partner countries have been actively involved in running training sessions, workshops, etc with NGOs and other organisations, and in developing the MOOC. The content of the course is now complete; however, there is a hold up due to IP and legal issues, which are outside the control of the SUCCEED team and should be resolved soon with the MOOC due to run in Yr5.

2.2
Working closely with the Global Mental Health Peer Network the SUCCEED team has developed a guide on lived experience coproduction in research. This will be approved and finalised by the peer researchers in Yr5 with the plan to roll this out and use it as a tool for engaging with other programmes, research groups, etc.

2.3
Peer researchers remain a critical component of programme delivery. They are involved at all levels of implementation, have shown a real commitment to the programme and are a huge and noted success. Peer researchers have continued to be engaged with the lived experience advisory panels, consortium advisory group, and other meetings – often leading sessions and discussions.
Peer researchers contributed to the Countdown to 2030 Africa Indicators, Mental Health Policy change in Sierra Leone and the Lancet Psychosis series. They joined the Global Mental Health Peer Network consultancy service where they are sharing their knowledge and experience gained through being part of SUCCEED.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

A detailed review of the SUCCEED logframe was carried out this year. Output 4 was removed with the remaining outputs re-weighted resulting in an increase from 30% to 33% for output 2.

Progress on recommendations from the previous AR, lessons learned this year and recommendations for the year ahead

Progress on previous recommendations:

- Review of capacity building goals: SUCCEED has continued to include capacity building as a key component of all aspects of its work. Peer researchers are actively involved across the programme but there is also support for academic team members – for example, the Comms lead in Nigeria has been promoted and is now co-lead for the Comms and Research Uptake workstream, and a researcher in Zimbabwe has received her PhD and is now the Principal Investigator at that site.
- Results of increased working with Global Mental Health Peer Network: the consultancy agreement for expert advice and support for our peer researchers and Lived Experience Advisor Panel now sits with GMHPN, an organisation established and run by people with lived experience of mental health conditions. This change has promoted learning and support within the continent, in a way that aligns with the programme’s ethos on participatory approaches. Furthermore, as part of SUCCEED’s commitment to decentralising operations, management of this partnership and contract will transfer to the University of Zimbabwe during Yr5.

Recommendations for Yr5
1. MOOC to be delivered, with feedback captured to inform future work. First half of Yr5.
2. Continuation of strong support for peer researchers and consortium staff, at all levels. Ongoing

Output Title	SUCCEED publications and other means of communication, designed to influence global mental health research and practice at national and international level.
Output number:		3	Output Score:			A
Impact weighting (%):		33%	Weighting revised since last AR?			Yes

Indicator(s)				Milestone(s) for this review	Progress
3.1 SUCCEED model of Community Based Mental Health is shared with relevant stakeholders / a) SUCCEED Package Guidelines/Manual x 1 cross-site, 1 manual per country / b) WHO Community Mental Health Guidelines incorporate SUCCEED results / c) Launch events for final SUCCEED guidelines				b) Commence work on incorporating SUCCEED guidelines within WHO Community Mental Health Guidelines	Met / Intervention manual prepared alongside training resources updated after pilot. Discussions with WHO and Africa CDC ongoing
3.2 Number of uptake outputs sharing and promoting SUCCEED and linked research (in line with Uptake Strategy). / Specifically: / a) Policy briefs / b) Blogs / c) Webinars / d) Reports and evidence synthesis / e) Engagement events with policy makers in countries / f) SUCCEED represented at conferences / g) Public facing annual report / h) Podcasts / i) Videos				a) Policy briefs: 6 / b) Blogs: 6 / c) Webinars: 2 / d) Reports and evidence synthesis: 0 / e) Engagement events with policy makers (per country): 2 / f) Conferences: 1 / g) Public facing report for Y3/2023	Met / a) Policy briefs: 2 / b) Blogs: 4 / c) Webinars: 3 / d) Reports and evidence synthesis: 1 / e) Engagement events with policy makers (per country): 1-4 / f) Conferences: 5 / g) Public facing report published for 2023 / h) Podcasts: 1 / i) Videos produced in Malawi and Nigeria
3.3 Number of communications outputs in line with the SUCCEED Communications Strategy. / Specifically: / a) Unique visits to SUCCEED-related sections of MHIN Africa and LSHTM sites / b) Twitter impressions on MHIN Africa / c) Press releases and press conferences / d) Broadcast engagement with community through radio, TV and online				a) 1200 unique visits to SUCCEED webpages / yr / b) 110,000 X (Twitter) Impressions / yr / c) media releases: 10 a year / d) Broadcast engagement: 8 programmes/slots a year	Met / a) Unique visits to SUCCEED webpages on MHIN = 671, on LSHTM = 636. Total = 1307 / b) 62,546 for SUCCEED and 91,822 for MHIN Africa, 136,100 for MHIN (=290,468) / c) Media releases and press conferences: 79 (see below) / d) Broadcast engagement. Programmes/slots: 4

Briefly describe the output’s activities and provide supporting narrative for the score.
Overall, SUCCEED has met this Output.

SUCCEED has successfully engaged with a wide audience through a broad range of measures. There has been an increase in products across this output an in improvement of the accessibility and visibility of these through the programme website and other channels. However, there is still scope for this to be improved and increased, particularly with the joint Comms/Research Uptake roles and the new media suite in Nigeria.

3.1
SUCCEED developed its intervention manual for the pilot studies, along with various training resources. These have now been updated. The programme team has been actively engaging with WHO and Africa CDC and hopes to influence the competencies for Community Health Workers as relevant to mental health.

3.2
SUCCEED has developed a broad range of comms and Research uptake products this year, more than had been initially planned. These range from detailed reports and policy briefs all the way to podcasts and videos. Alongside this have been several conferences and meetings with policy makers. All of this work is with an aim to influence long-term policy change. It is particularly good to see use of the new media suite for Nigeria to produce videos and support the Comms lead there.

3.3
Alongside the range of products has been a strong online and person presence for SUCCEED. This is demonstrated by the variety of outputs here including poetry, art, seminars, newsletters, TV and radio shows, etc. There has also been good engagement with Mental Health Innovation Network, both in Africa and globally.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

A detailed review of the SUCCEED logframe was carried out this year. Output 4 was removed with the remaining outputs re-weighted resulting in an increase from 30% to 33% for output 3. Additions were made to indicator 3.2 to better track research dissemination and uptake.

Progress on recommendations from the previous AR, lessons learned this year and recommendations for the year ahead

Progress on previous recommendations:

- Improved access to and visibility of digital outputs: SUCCEED’s two websites have improved the availability of its products; however, see the recommendation below.
- Publication of public facing report for 2023: this was completed in March 2024; however, we would expect the public report for 2024 to be published more promptly, especially with the additional support for comms and publications.
Recommendations for Yr5
1. Publication of 2024 public facing report – mid Yr5
2. Although the new SUCCEED website, hosted through the Mental Health Innovation Network, is an improvement on the previous version there is still substantial scope for more products to be available through this and for visibility of SUCCEED’s work to be increased. All SUCCEED products to be available online by end 2024. Update website on an ongoing basis
3. More detailed plans for research uptake, especially around influencing policy change and engagement with WHO Afro and Africa CDC, to be developed and agreed. Due end 2024.

## D: VALUE FOR MONEY

VfM performance compared to the original VfM proposition in the business case

	VfM examples
Economy	Procurement: The Value for Money (VfM) of the SUCCEED programme remains comparable to previous programmatic years and to the original business case – with efforts being made to ensure effectiveness without increasing cost. One of the key elements contributing to the programme's effectiveness is the increasing leadership and independence of consortium partners and various sub-groups, and the use of focused meetings for specific purposes. This has resulted in a large number of deliverables being achieved in terms of finalised manuals, training resources, comms/uptake and capacity building events over the year, contributing to overall programme outputs.
Efficiency	There has been no increase in overall costs, and consortium budget management is improved, with reflection on previous year’s spending being incorporated into budget revisions in subsequent years. Rolling on from last year three out of four countries have experienced substantial currency or other financial instability (related to elections in Sierra Leone and Nigeria); however, the programme’s central management team is working with the consortium to minimise disruption to the programme's effectiveness by supporting budget management. / Due to the rising costs of goods in country SUCCEED have placed an increased emphasis on the procurement processes, getting quotes from multiple suppliers in each country. / A particular ‘win’ was a recent request from LSHTM to purchase a vehicle in Malawi due to increased cost of transport to field sites. The programme team requested the relevant information and liaised with FCDO Malawi colleagues to help facilitate the purchase of the vehicle. There was also an agreement with SUCCEED that once the programme is finished the asset can be transferred to FCDO Malawi to be used on future projects demonstrating excellent VfM.
Effectiveness	By running smaller, focussed pilots of the programme intervention, this has helped to demonstrate and strengthen the effectiveness of the outputs and the overall impact of the programme. The broader aim is for wide-spread implementation of the tool across similar settings, which should not only improve the quality of life of those with severe mental illnesses, but also to reduce the burden on health care, promote poverty reduction, and facilitate meaningful community participation. The longer-term impact is to contribute towards fulfilling the Sustainable Development Goals (SDGs) and foster national progress towards more accessible mental health care.
Equity	The intervention developed is equitable by design and is aligned with the original ToC and has accommodated adaptations following key consortium meetings, thus ensuring that the programme's theory, design, and implementation remain aligned with its strategic goals. The MOOC creation has been rescheduled to the first six months of Year 5, allowing for co-production and publication of papers. The scope of research has been expanded by introducing additional assessments, for example with the piloting of the EquiPar tool. This will enable review of the equitability of programme partnerships and ensure that equitable co-production is core to programme delivery, particularly the intervention.

Assessment of whether the programme continues to represent value for money

Based on the output assessments, progress towards the outcomes and impacts, and VfM measures, the SUCCEED programme continues to demonstrate good VfM.
SUCCEED has maintained cost-effective practices (such as virtual alternatives for meetings), has established strong leadership across the consortium with equitable and decentralised management, plus more efficient processes and use of time. Furthermore, SUCCEED has placed all capacity building activities online alongside programme documents, resources, minutes, reports, communications materials, strategies, and policies.

E: RISK

Overview of risk management

SUCCEED developed a risk register at programme inception, with risks being monitored and updated where required on an ongoing basis through regular team meetings and as part of the monthly LSHTM/Country Team meetings.

SUCCEED and FCDO internal risk registers have been reviewed on a quarterly basis by the FCDO team and risks related to the key outputs have been included in the logframe. Any specific change, novel or high-level risks are communicated to the SUCCEED Senior Leadership Team, considered at monthly leadership team meetings, and discussed with FCDO where relevant. The overall risk is moderate.

Strategy / & / Context	Programme Delivery	Public Service Delivery & Operations	Safeguarding	Financial & Fiduciary	People	Reputational	Overall
Major	Major	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate

Strategy and Context: SUCCEED works in countries at risk of crises against a background of general political unpredictability and economic instability. Over the past few years COVID-19 cases have decreased but they have been replaced by other disease outbreaks such as cholera outbreaks in Malawi and Zimbabwe. Elections were held in Nigeria, Zimbabwe and Sierra Leone, which also experienced an attempted coup. SUCCEED has mitigated these associated risks by providing additional support to teams in country, changing in person meetings when necessary, allowing remote working and keeping in constant communication with country teams.

Additionally, there is the ever-present risk of future pandemics and preparedness for such eventualities. LSHTM maintains a strong emphasis on pandemic preparedness and continuously monitors global health threats to assess their potential impact.

Policy and Programme Delivery: SUCCEED have advised that partners face challenges with stringent FCDO contract processes, which places project activities at risk. Particularly the amendment process which has taken longer than expected this year due to changes in government. SUCCEED have advised this may have a knock-on effect causing delays to the main intervention trial. FCDO have processed the current amendment and will ensure SUCCEEDs next amendment is completed efficiently. FCDO have discussed with SUCCEED and will continue to support in quarterly catch ups. SUCCEED have also flagged that economic inflation is still having an impact on the programme delivery as the cost of goods increases in countries, particularly Sierra Leone and Nigeria. To mitigate this risk, there was increasing emphasis placed on procurement processes, and getting quotes from multiple suppliers as advised in the VfM section.

Public Service and Delivery Operations: SUCCEED have flagged high inflation rates across all partner countries, including the UK, from supply chain disruptions, monetary and fiscal stimulus and the continuing war in Ukraine affecting the programme. SUCCEED have also had issues in Nigeria with exchange rate fluctuations and problems accessing project funds from the Central Bank of Nigeria. SUCCEED continues to work closely with our partners to undertake thorough budget reviews along with ongoing work to ensure fiduciary prudence with the main intervention costs in the remaining two years of the project.

Safeguarding: SUCCEED has no safeguarding issues reported to date and have had no negative reports from the field. SUCCEED continues to promote open disclosure and has trained staff to ensure they are aware of procedures (in addition to consent forms detailing how research participants can communicate any concerns with the programme). LSHTM and partners have strong safeguarding policies, based on guidance from FCDO, with continued refresher training that will help anticipate and mitigate the risks. FCDO SRO & DPM met with the SUCCEED team during their annual meeting in November 2023 where safeguarding was discussed with the wider team along with the process of reporting any safeguarding issues.

Financial and Fiduciary: Previous risk involving SUCCEED’s downstream partners being unable to meet required financial management standards and / or using funding fraudulently have improved due to governance and finance systems put in place. Measures put in place to monitor funds closely, particularly where partners are less experienced, have been successful to date. FCDO undertook spot checks in country when visiting the programme. FCDO continues to review issues with funding being released in Nigeria with SUCCEED.

SUCCEED have less than two years remaining of the programme and have consistently underspent on their budget. There is a reliance on contract amendments to realign these underspends, which may not possible in the final year of the programme.

People: SUCCEED have flagged high staff turnover in year 4 with the project manager in London on maternity leave and loss of some staff in in country, including two principal investigators in Malawi. SUCCEED managed to find a replacement for the project manager and have therefore mitigated this risk. In country SUCCEED has strong teams and systems in place to manage the staff turnover in country, FCDO programme team will monitor.

Reputational: As noted above, risks relating to vulnerable groups and safeguarding have been mitigated with thorough training. At each meeting FCDO request an update on project activities and update the risk register accordingly. A related issue of context – such as the risk of short notice ODA reductions due to fiscal constraints – place a strain on partner relationships and pose reputational risks. Scenario planning and regular communication helps mitigate this.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Delivery: SUCCEED has improved on last year from a programme management point of view, providing financial documents within the increased deadline of two months and forecasts when requested. This can be attributed to refresher financial management training which took place in year 4 for partners. SUCCEED previously advised that the majority of the financial issues were due to the absence of a dedicated programme manager; SUCCEED hired a PM in year 4, however said PM is now on maternity leave. They have found cover for the PM and FCDO has worked with the new PM to get CA4 completed and will continue to work with SUCCEED through CA5.

SUCCEED were only slightly out of the 10% variance for KPI 1; ‘accurate submission of financial forecasts’, and they have scored well on all others, responding to FCDO recommendations, and submitting quarterly and annual reports on time. There have been some slight issues with financial documents not submitted with invoices, but the new PM has managed to rectify these efficiently.

SUCCEED have mentioned contract amendment delays have caused issues with funding for their main intervention study. This should not be the case as FCDO have paid every invoice sent from SUCCEED and approved all requests for extra assets. At a critical stage in the programme, SUCCEED should have planned for appropriate finances for these studies and cannot rely on constant contract amendments moving forward. FCDO will continue communication with SUCCEED on this matter.

Commercial: Contract amendment four has been signed off which was generated to reprofile underspending from Y2-4 to Y5-7. As details above, this amendment took longer than expected due to various internal factors and SUCCEED have advised it may affect delivery. In the amendment SUCCEED advised the Y4 spend would be £1,345,581, the total Y4 spend was £133k less than this. If CA4 was not approved the underspend would have reached £250k approximately. SUCCEED have advised they will now submit a new amendment (CA5) to reprofile the £133k. As advised above, FCDO recommend that SUCCEED do not consistently rely on contract amendments throughout the programme. With less than two years of the programme left there is a substantial risk of SUCCEED having a large budget to clear in their final year.

Financial Performance: The total budget for SUCCEED £6,941,625, of which £3,714,009 has been spent, leaving £3,227,616 for the remaining two years. SUCCEED have advised the main driving factor for LSHTM’s underspend was their MOOC (massive open online course) that has been further delayed by legal issues concerning intellectual property agreements with partner institutions. There was also a sick leave payment for one of SUCCEEDs staff members which was removed from the project and recharged to the faculty.

In Nigeria, there has been continued significant underspending due to difficulties in accessing funds from the Central Bank of Nigeria (CBN). Financial transactions are often delayed there due to internal bureaucracy. The release of funds from the CBN takes a long time for SUCCEED to negotiate, significantly hampering their work. The Principal Investigator (PI) for Nigeria is currently searching for an alternative. FCDO have requested updates from SUCCEED with clear timelines on money withdrawals, which the PI has been providing, but substantial delays continue.

Due to the above FCDO have approved a carry over into FY2024-25, mostly related to the delay with the MOOC (massive open online course). New pro forma and narrative proposing carryover to future years have not been submitted yet, SUCCEED have advised they are working on these. FCDO will continue to support SUCCEED throughout the amendment process.

SUCCEED have advised they will continue with regular project management meetings, along with continual financial oversight of partner budgets and expenditure resulted in major purchases (e.g. comms suite in Nigeria) occurring within Year 4. SUCCEED also intend to continue working diligently with partners, supporting them to produce accurate Y5-Y7 budgets. As discussed above, guidance documentation has been developed and numerous 1-1 meetings have taken place to develop intervention budgets that are both realistic and consistent across trial sites as well as ensuring optimal (economic and efficient) use of funding. FCDO will continue to monitor and FCDO PM will have 1-1 meeting with SUCCEED PM if necessary.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evidence

The FCDO SRO and Programme Manager attended the SUCCEED annual programme meeting in Malawi in November 2023. This was an invaluable experience, not only in getting a broader and more in-depth understanding of SUCCEED but also to meet members of the team, including many of the Peer Researchers. The annual meeting was attended by colleagues from each of the four countries involved in the programme and the Malawi director of student affairs. It provided an opportunity for FCDO to sit down with each country team to discuss how the programme was progressing and any issues they were facing, including the above-mentioned Nigeria finance complexities. It also enabled more detailed monitoring of all aspects of the programme both in theory and in practice, with the opportunity to visit some sites and see the programme in action, including meeting participants.

The meeting was held in Blantyre where the SUCCEED management team initially reviewed the pilot study which had recently finished and discussed the upcoming plans for the main intervention. FCDO team were able to ask questions around the intervention and discuss what had worked well and not so well with the pilot study. There was a great sense of collaboration with a lot of the recommendations coming from the country PI and PR’s. Discussion included the sensitivity of mental health and the stigma involved. There were also sessions around safeguarding, research protocol, communication and research uptake and a private session with the Peer Researchers to discuss their personal experiences and what had led them to work with SUCCEED. The FCDO team also had the opportunity to visit some sites where open clinics were run for participants suffering from mental health conditions in the community. It was an extremely helpful visit for the FCDO team to get an understanding of the challenges facing the programme.

SUCCEED was established during the COVID-19 pandemic, and therefore its systems for maintaining oversight of progress were naturally built around virtual locations, with processes which continue to be the main routine means of monitoring progress. At a country level, PIs in each country manage progress of their own teams’ activities against workplans that are very similar across countries. Each country holds weekly team meetings, with the Programme Manager ensuring progress throughout the range of activities daily. They have an opportunity to engage with the Project Manager in LSHTM during a weekly meeting, which has increasingly become a space for peers to share progress and hold themselves accountable, rather than simply being answerable to the LSHTM team. In a similar way, all team members attend monthly global team meetings, where country teams, Peer Researchers and workstream leads report their activities.

During Year 4, SUCCEED focus was monitoring the implementation of the project during the pilot – both how the intervention worked, and how the proposed research tools performed. Throughout the pilot, supervisors collected details of both these aspects using a detailed Monitoring and Evaluation form. These data were reviewed in advance of a physical cross-site meeting, held in Malawi.

The identification and sub-contracting of implementing partners in each country added an additional level of monitoring that was needed. In general this was done by the university consortium member in each case, and we have seen good use of existing internal university procedures for monitoring activities and budgets for this. Though these processes can be slow, in general they are fit for purpose and we do not want to override them. To date, in all countries, due diligence has been done well and the implementing partners were well managed and performed well in the pilot.

For capacity building, SUCCEED applied an assessment tool for a mid-programme review of progress for individual and team goals for development. Each institution also has established line management procedures for monitoring individual team member performance. This is also true within implementing partners, with SUCCEEDs attention being to monitor specific pilot outputs, and ensuring that safeguarding risks are well managed. As the volume and complexity of work scale up in Year 5, we will need to remain aware of the need to ensure close monitoring of implementing partner performance through the M&E system, which was refined following the pilot, having been found to be overly intense in the way it was applied by supervisors.

Learning
SUCCEED’s systems for evaluating progress continue to function well, with two Consortium Advisory Group meetings held, where the Scientific Oversight Group, Local Advisory Group and Lived Experience Advisory Panel (LEAP) members contributed to reviewing progress. The LEAP is now supported by the Global Mental Health Peer Network, and SUCCEED seek to ensure that work is accountable to this group as a core principle of ensuring people with lived experience meaningfully co-producing the programme.

Beyond these efforts to be accountable to wider teams and end-users in alignment with co-production ethos, evaluation is primarily carried out through regular collation of quarterly and annual reports for FCDO, which are followed by a chance to discuss issues that have arisen. In addition, LSHTM procedures require regular evaluation of administrative and financial progress, as well as research standards. SUCCEED have established a Trial Management Group, which has been invaluable in advising and assessing progress as SUCCEED navigate the complexities of trial design, ethics applications and amendments.

SUCCEED gains valuable support through meetings with other RPCs, in meetings for Research Directors and for CEOs/ Project Managers. SUCCEED have produced a public-facing annual report for year 4, alongside regular newsletters. These are an opportunity to collate information and learning and communicate this in an accessible format to a public audience. SUCCEED contributed to the terms of reference for a mid-term evaluation commissioned by FCDO, and have started preparing for this, looking forward to engaging with this process in 2024.

SUCCEED makes extensive use of digital tools to ensure that all teams are able to keep on top of a large volume of information in a collaborative and convenient way. While it has taken a long time to increase confidence on the use of web-based resources like MS Teams, gradually taking over from sharing everything by email, people do increasingly use cloud-based storage and editing. Meetings on Zoom also generally work fairly well, though poor internet connection and power cuts have proven to be an enduring problem. This digital divide is something the programme has continued to try to mitigate, while recognising the enormous value of these tools in enabling a large consortium to function effectively and deepen relationships.

The central programme teams sends round a weekly Monday morning email to outline priorities and news that teams need to be aware of. This has improved reliability in attendance at meetings (many people do not use calendar apps/Outlook), alongside active WhatsApp groups, which exist for many of the sub-groups in the programme - for country teams, regions, and workstreams. SUCCEED made use of digital data analysis tools like NVivo and Stata, which were used in pilot data analysis, building staff capacity to do this. Development of the MOOC also made extensive use of media tools like video and sound recording and editing, requiring both communication and technical skills. SUCCEED have made good use of the new communications suite in Nigeria, recording videos (including during the cross-site meeting), launching a new podcast, and streaming live events like a theatre play and panel discussion in Nigeria about mental health. These SUCCEED resources are available through the SUCCEED section on MHIN, as well as on the LSHTM and Centre for Global Mental Health sites.

SUCCEED annual meeting November 2023, Blantyre Malawi.

Date of last narrative financial report	19.06.2024	Date of last audited annual statement	31.07.2023