## Annual Review Template

Title: LIGHT (Leaving no-one behInd: transforming Gendered pathways to Health for TB)
Programme Value £ (full life): £7,903,834		Review date: 18/10/2024
Programme Code: [AMP ID#] 301138	AMP start date: 18/03/2020	AMP end date: 30/04/2026

Summary of Programme Performance
Year	2021	2022	2023	2024
Overall Output Score	A	A	A+	A+
Risk Rating	Moderate	Moderate	Minor	Minor

DevTracker Link to Business Case:
DevTracker Link to results framework:

A. SUMMARY AND OVERVIEW

Description of programme

Tuberculosis (TB) continues to be a significant global health problem. Globally, in 2022, 10.6 million people fell ill with TB (5.8 million men, 3.5 million women and 1.3 million children). 1.3 million people died from TB; thus in 2022, TB was recorded as the second leading infectious killer after COVID-19. Notably, men accounted for the majority of the cases and two out of every three cases of TB which go undiagnosed or not notified, are in men. Gender plays a significant role in determining health outcomes, including equitable access to quality TB prevention and care. People of different genders face different challenges and thus require tailored solutions to access the care they need.
[note] Global tuberculosis report 2023. Geneva: World Health Organization; 2023. Licence: CC BY-NC-SA 3.0 IGO.

Leaving no-one behind: transforming Gendered pathways to Health for TB (LIGHT) is a six-year cross-disciplinary global health research programme led by the Liverpool School of Tropical Medicine (LSTM) working with partners in Kenya, Malawi, Nigeria, Uganda and the UK.
LIGHT aims to support policy and practice in transforming gendered pathways to health for those with TB in urban settings to improve health and wellbeing, socio-economic and equity outcomes and to prevent the spread of TB. The research programme will do this by enabling and supporting global and national policy environments and health systems to improve sustainable, equitable access to quality TB services and medical products, to reduce TB mortality and morbidity among men, women and children. TB affects people of both sexes in all age groups, but there are more men than women with and dying from TB.

LIGHT:
- Generates new evidence to improve male access to quality TB healthcare services in urban, to more effectively prevent the spread to the wider population, particularly women and girls.
- Strengthens capacity to generate evidence and promote demand for services.
- Engages effectively with key stakeholders.
- Conducts monitoring, evaluation and learning throughout the programme.
LIGHT’s team is described in this short video. The reporting year (2023/24) marks Year 4 of the LIGHT consortium and the third year of implementation following the inception phase.

LIGHT’s partners are depicted here:

Summary supporting narrative for the overall score in this review

During the reporting year the consortium has considerably progressed on data collection (which is nearing completion), research publications, and stakeholder engagement at national, regional and global level. LIGHT have moderately exceeded the expected achievements for this reporting year.

LIGHT have published seven articles in the reporting year, notably on the political economy gendered gaps to TB prevention and care in Kenya, diagnostic processes for TB by pooling sputum testing, or, community based active case finding for TB. Their ECR-led projects in Uganda, Malawi, Nigeria and Kenya have all progressed as expected and are predicted to complete by Q1 of Year 5 and participatory qualitative studies are undergoing in all LIGHT countries. LIGHT have continued to work on their model calibrations with two of the four now completed and accepted for presentation at The Union World Conference on Lung Health 2024. LIGHT have also completed two Political Economy Analysis manuscripts (Malawi and Kenya) with two more in progress.

LIGHT have continued to display a strong focus on capacity building with extensive training programmes and learning events offered and held to improve practical research skills, academic understanding of LIGHT’s areas of research and the skills of their trainers, both within and external to the consortium.

LIGHT have been involved in National level meetings and events in all LIGHT countries as well as taking part in Pan-African, regional and international events on LIGHT’s research topics of TB and Pandemic preparedness.

Key highlights of achievements of the LIGHT Consortium have been
Interventions and influencing during multi-stakeholder Hearings on TB / Universal Health Care (UHC) / Pandemic Prevention, Preparedness and Response in preparation of the UN General Assembly High-level Meetings on the Fight against TB, Pandemic Prevention, Preparedness and Response and UHC.
- LIGHT partners AFIDEP and ReSoK engaged with the Kenyan Ministry of Health and WHO Kenya on their invitation to review the National Strategic Plan (NSP) for TB, Leprosy & Lung Health. As a result, the new Kenya National Strategic Plan (launched in Jan-2024) now includes “human rights and gender” as one of its six strategic pillars.
- The LIGHT research team took action to influence TB-related data reporting at the global and national levels, specifically in Nigeria advising the National TB Programme where TB data are now disaggregated by gender.
Key lessons learned and any proposed recommendations for next year.
- LIGHT have been able to influence national and international policy already in the fourth year of the programme. This demonstrates its highly respected professional standing to policymakers and suggests a high potential take-up of its findings also towards the end of the programme. It is also a credit to LIGHT’s excellent network amongst national and international key actors.
- LIGHT’s production of published papers and key conference notes is equally a credit to its academic standing.
- The leadership of LIGHT point to the Training of Trainers (ToT) as a successful approach to ensure sustainability of the LIGHT training packages and recommend it in other areas going forward.
- LIGHT consortium staff have implemented good cross-country learnings and sharing of best practices and insights from Kenya, Malawi, Nigeria, and Uganda's TB Programmes.
- There are no specific recommendations resulting from this Annual Review. LIGHT will be expected to take part in the external evaluation of RPCs commissioned by FCDO and follow any specific recommendations that may emerge from there.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case. [1/2 page]

LIGHT aims to have an impact on reduced transmission, catastrophic costs and adverse TB treatment outcomes (mortality and case fatality) from TB resulting from a more effective, gender-sensitive health policy and practice response.

The outcome is: Global and public health policies, programmes, organisations and initiatives in target countries adopt or strengthen TB prevention and control policies and strategies, based in part on LIGHT evidence, such that they are gender-sensitive, pro-poor and able to support introduction and scale-up of new TB-related products by 2025 to meet global TB targets.
[note] Previously ‘care’ instead of ‘control’.
[note] Previously ‘responsive’ instead of ‘sensitive’.
There are two indicators to measure progress towards this:
1. the number of TB policies, guidelines or manuals/operational handbooks adopted or strengthened to incorporate gender responsive components resulting from LIGHT evidence and research uptake, evidenced at national, regional and international level – as reflected in LIGHT case studies.
2. Case studies demonstrating progress over time from engagement towards adoption of LIGHT recommendations into country and international guidelines, drawing on the successful delivery of LIGHT output.
LIGHT aims, ultimately to leave no-one affected by TB in sub-Saharan Africa behind. The research programme does this by enabling and supporting global and national policy environments and health systems to improve sustainable, equitable access to quality TB services and medical products, to reduce TB mortality and morbidity among men, women, and children. TB affects people of both sexes in all age groups, but there are more men than women with and dying from TB.
No major changes to impact statements were agreed; however, some changes to the wording of the outcome statement were added and changed LIGHT to clarify the role of LIGHT (additions given in bold above and changes identified in footnotes).

A fourth Output set originally in the ToC, covering management, governance and routine monitoring was dropped as the consortium excelled in this area and a separate output for this routine process was not considered needed – especially since these were also dropped for other FCDO funded Research Programme Consortia.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead? [1/2 page]

LIGHT expects to meet the defined outcome and impact within the allocated timeframe and budget originally planned. In the reporting year (Year 4 of LIGHT), indicators for measuring progress towards outcome and impact were (i) completing data collection for projects by early-career researchers (ECR), which was achieved; and (ii) ensuring LIGHT’s participation at relevant discussion fora that enable the consortium to bring forward the issue of gender and TB, which was equally achieved. This is demonstrated by six case studies showing examples of our progress against impact, outcome and outputs.

Global and public health policies, programmes, organisations and initiatives in target countries are starting to adopt and strengthen TB policies and strategies based - in part - on LIGHT evidence. This is demonstrated, for example, by the influence of LIGHT on WHO to improve their data reporting practices. Similarly, at national level, LIGHT influenced collection and use of sex-disaggregated data tools in Nigeria, which enabled more accurate reporting and analysis, providing crucial evidence to inform policies appropriately.

Overall, this programme is well on track to meet its stated objectives.

Along all Research Programme Consortia (RPCs), LIGHT will be evaluated externally.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio [1 paragraph]

Overall, this programme is well on track to meet its stated objectives. LIGHT is a highly productive and influential programme operating on a topic that is globally neglected. Early results as described above and in the extensive reporting by LIGHT demonstrate early successes in changing national and global practices. Thus, the programme continues to represent VfM. It also contributes to FCDO’s overall objectives of strengthening gender equity and Leaving-no-one behind.

The Programme should therefore continue according to plan.

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title	New evidence based on the options and approaches for / 1) maximising the numbers of marginalized adolescent, young adult and adult males accessing health care services; / 2) increasing TB diagnosis, care and prevention among marginalised adolescent, young adult and adult males; and / 3) improving health and social outcomes for people living in high TB burden settings.
Output number:		1	Output Score:	A+
Impact weighting (%):		40%	Weighting revised since last AR?	Not Changed

Indicator(s)	Milestone(s) for this review	Progress
1.1 Number of research projects aligned to LIGHT's Research Framework	a) Design stage: 0 / b) Implementation stage: 4 / c) Analysis stage: 0 / d) Completed: 0	Moderately exceeded / a) Design stage: 2 / b) Implementation stage: 1 / c) Analysis stage: 5 / d) Completed: 1
1.2 Number of published open access, externally peer reviewed conference abstracts, research publications and synthesis products, aligned to the DORA principles.	a) Lead author based in LMIC: 5 / b) Female lead author: 5 / c) Female LMIC-based lead or co-author: 5 / d) Research publications: 7 e) Other research products (incl. conference abstracts and posters): 9	Substantially exceeded / a) Lead author based in LMIC: 20 (1 in Y2 + 3 in Y3 + 16 in Y4) / b) Female lead author: 21 (2 in Y2+ 6 in Y3 + 13 in Y4) / c) Female LMIC-based lead or co-author: 12 (1 in Y2, 3 in Y3 + 8 in Y4) d) Research publications: 12 (1 in Y1 + 1 in Y2 + 3 in Y3 + 7 in Y4) / e) Other: 28 (3 in Y2 + 9 in Y3 (6 abstracts and 3 posters) + 16 in Y4 (15 abstracts and 1 poster)
1.3 Number of tools, innovations, national and global guidelines and processes that include consideration of LIGHT’s new approaches to support interventions with gender components, including replicable innovations and additionality.	4	Moderately exceeded expectation / 6 in total (2 in Year 2 + 2 in Year 3 + 2 in Year 4)

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

This output, overall, has moderately exceeded expectations.

LIGHT has generated research evidence and is at a more advanced stage that anticipated.
Thus 2 more studies are now at design stage, while those that were started are now either in analysis stage (5) or even completed (1). The study that is completed is the Photovoice project from Nigeria, with publication awaited (publication date awaited).

LIGHT have produced an impressive number of publications, some of which are pivotal to the topic area of TB and will make a step change for policy change:
1. Gendered gaps to tuberculosis prevention and care in Kenya: a political economy analysis study (BMJ Open)
2. Pooling sputum samples for Xpert® MTB/RIF and Xpert® Ultra testing for TB diagnosis (Public Health Action)
3. Accuracy of upper respiratory tract samples to diagnose Mycobacterium tuberculosis: a systematic review and meta-analysis (Lancet Microbe)
4. Ending TB means responding to socially produced vulnerabilities of all genders (commentary, BMJ Global Health)
5. The 2023 UN high-level meeting on tuberculosis: renewing hope, momentum, and commitment to end tuberculosis (commentary, Lancet Respiratory Medicine)
6. Tuberculosis Immunoreactivity Surveillance in Malawi (Timasamala) – a protocol for a cross-sectional Mycobacterium tuberculosis immunoreactivity (PLOS One)
7. Community-based active-case finding for tuberculosis: navigating a complex minefield (BMJ Global & Public Health)
Four of these papers have a female first author and include co-authors based in LMICs. These publications are important milestones for LIGHT showing how findings are starting to generate new knowledge contributing to advancements in the field of gender and TB research. Paper #4 on socially produced vulnerabilities is in the top 25% of all research outputs scored by Altmetric, received 1,945 full views and 231 downloads. In addition, LIGHT have had 15 presentations at scientific conferences accepted and successfully presented.

So far, LIGHT produced a total of six tools, innovations, national and global guidelines and processes. In Year 4, LIGHT report two case studies (Annual Report, Annex 3) showing examples of their progress against indicator 1.3. Both case studies highlight the importance of early stakeholders’ engagement to achieve policy impact. LIGHT identified key actors and engaged with them strategically building trust that allowed some of our suggestions and recommendations to be included in guidelines at global and national level.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

There have been no substantive changes to this output during the reporting period and no changes are currently planned.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Overall, this output has made very good progress and is above expectations.

For the Political Economy Analyses, we would welcome if LIGHT could dive deeper into what barriers
exist beneath the absence of gender disaggregated data and approaches and what approaches could look like that would address these barriers more consistently.

Output Title	Strengthened individual, institutional and multi-stakeholder networks/platforms capacity in LIGHT countries to produce, adapt, translate and use evidence and manage research.
Output number:		2	Output Score:	A+
Impact weighting (%):		30%	Weighting revised since last AR?	Yes

Indicator(s)	Milestone(s) for this review	Progress
2.1 Number of people within the Consortium accessed training and learning and demonstrate an increased capacity in evidence production and translation and management of research.	190	Moderately exceeded / 397 in total (76 in Year 1 + 62 in Year 2 + 197 in Year 3, 62 in Year 4)
2.2 Number of events where stakeholders outside the Consortium demonstrate increased capacity.	4	Moderately exceeded / 12 in total (2 in Year 3 + 9 in Year 4)
2.3 Number of events that strengthened institutional capacity	6	Moderately exceeded / 11 in total (2 in Year 2 + 8 in Year 3 + 3 in Year 4)
2.4 Number of case studies that demonstrate implementation of new training activities.	3	Met expectations / 4 (1 in Year 2 + 1 in Year 3 + 2 in Year 4)

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

This output has, overall, moderately exceeded expectations. To date, LIGHT trained a total of 397 people from within the Consortium, 62 staff in year 4 alone, with the majority in LMIC. Training and learning covered a wide variety of topics including design and analysis of cluster randomised trials, modelling techniques, virtual R, collaborative writing, understanding gender, equity & TB.

To indicator 2.2, LIGHT also provided a large number of training events for stakeholders outside the consortium. This included trainings on gender and equity as well as on research administration and management (RAMP).

To indicator 2.3, LIGHT strengthened institutional capacity through:
- Training of Trainers (ToT) on Evidence Informed Decision Making (EIDM) for 28 National TB Programme managers of LIGHT countries followed by 6 months of mentorship.
- Training of Trainers (ToT) for Research Administration and Management.
- Participatory health research Training to strengthen institutional capacity of LIGHT partners in conducting participatory health research, recognise own positionality, aspirations, and views about participants and take steps to enhance equitable participation, define principles of ethical and rigorous participatory health research, and identify ethical and methodological dilemmas and take steps to mitigate against harm and bias.
Two case studies on participatory visual methods in TB research and building TB modelling skills were included in the Annual Report.

The Training of Trainers (ToT) represented a cross-cutting capacity strengthening activity as it covered individual and institutional capacity for attendees within and outside LIGHT. The multiplier effect can already be seen as the newly trained trainers already implemented their knowledge by creating policy briefs (see the output on research uptake below) and by delivering the research and administration training in Malawi and Uganda reaching more than 40 external stakeholders (including ministries, NTP and NGOs). Lessons learnt were compiled in an infographic.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

Weighting for this output has changed from 20 to 30%, as outputs had been decreased from 4 to 3, following recommendations of last Annual Review and agreement with the consortium.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Overall, this output has also made very good progress and is above expectations.

For output indicator 2.2, it should be discussed between LIGHT management and FCDO, what increased capacity of external stakeholders (outside of the LIGHT consortium) is targeted. At present, this includes Research and Administration Management. While this is a useful skill for other researchers and institutions to have, it appears that some trainings have now addressed individuals with a research interest that have limited relationship to LIGHT topics. Although LIGHT should be commended for being a model of capacity building through its Training of Trainers, the primary aim of LIGHT (research on gendered pathways for TB) should still be in the focus of participants or targeted audience.

Output Title	High-quality LIGHT evidence products are influential in key policy discussions showing how gender sensitive and/or specific policies can provide a strong driver for better access to TB diagnosis, care and prevention and health system integration.
Output number:		3	Output Score:	A++
Impact weighting (%):		30%	Weighting revised since last AR?	Not Changed

Indicator(s)	Milestone(s) for this review	Progress
3.1 Number of analyses (landscape analyses, stakeholders’ analysis, evidence, policy, political economy) delivered to inform and refine Research Uptake and communications strategies	5	Substantially exceeded / 14 in total 6 in Year 2 (1 landscape report, 4 Comms strategies and Stakeholders interview) + 5 in Year 3 + 3 in Year 4
3.2 Number of communications products aimed at engaging, informing and influencing diverse stakeholders at national, regional and global level	24	Substantially exceeded / 94 (34 in Year 2 + 26 in Year 3 + 34 in Year 4)
3.3 Number of examples of LIGHT Consortium engaging and/or influencing national, regional or international expert panels/working groups/policy makers or networks.	a) Global: 5 b) National: 12	Moderately exceeded / a) Global: 16 (3 in Y2, 4 in Y3, 9 in Y4) / b) National: 30 (8 in Y2, 7 in Y3, 15 in Y4)

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

Delivery of this output has substantially exceeded expectations. To indicators 3.1: In Year 4, LIGHT created three new products that inform and refine Research Uptake and Communication Strategies. This includes:
Firstly, the consortium developed a template for socialising policy briefs on social media to be used across the LIGHT Consortium.
Secondly, three policy briefs were published
1. Enhancing Supply Chain Management for Tuberculosis (TB) Commodities in Kenya: Addressing Key Challenges.
2. Adopting a Gender-Responsive Approach to Ending TB
3. Gender Equitable Access to TB Prevention and Care in Malawi: A Political Economy Analysis
Thirdly, an updated research uptake strategic framework was developed and now shared with all teams across the LIGHT Consortium

To indicator 3.2: In Year 4 alone, LIGHT published 34 outputs in the ‘Communication’ category. Highlights include:
- 3 Podcasts developed by LIGHT partners, including a podcast series on the importance of engaging community voice in political decisions; a podcast on Kenya's Battle Against TB: A Story of Resilience, Hope, & Healing; and finally Ending TB – Gendered Pathways and Health Tech
- 12 videos featuring LIGHT, in particular the early career researcher videos uploaded on the LIGHT YouTube channel.
infographics and blogs
To indicator 3.3: LIGHT recorded 9 global/UK new engagements, including:
- Attending and influencing Multi-stakeholder Hearings on Tuberculosis / Universal Health Care (UHC) / Pandemic Prevention, Preparedness and Response (May 2023) and the UN High Level Meeting on TB (Sept 2023) emphasizing the gender perspective in discussions and influencing the framework for future policy reforms and investments to end TB. The team also arranged a Briefing & Networking Session for academics and healthcare workers participating in the 2023 UN High-level meeting on TB.
- Presentation at Boston University TB Interdisciplinary Approach to Research Alliance and TB Interest Group.
- Westminster Hall Debate, APPG meetings and UK Pandemic Sciences Network (UKPSN)
- World TB Day Symposium organised by UCL and LSHTM presenting on how to address men's barriers to TB diagnosis and care in peri-urban settlements in Nigeria.

LIGHT recorded 15 national engagements, including :
- Science Summit by the Ugandan Ministry of Health and National TB and Leprosy Program; LIGHT presented preliminary findings on male friendly services.
- Engagement with the Kenyan Division of National Leprosy, Tuberculosis and Lung Health Program throughout the reporting year, leading to the inclusion of gender-transformative access to services, especially among marginalised and vulnerable groups in the Kenya NSP 2023/2028 (blog)
- In Malawi, engagement with the National TB Technical Working Group and contribution to the Male Engagement Strategy (MES).
- In Kenya, a sensitisation workshop in Nairobi by LIGHT to enhance understanding and technical capacity in evidence-informed decision-making (EIDM) among key TB stakeholders (including NTP, Kenya Medical Research Institute (KEMRI), Stop TB Partnership Kenya, Nairobi City County Council, etc).
- LIGHT partner AFIDEP attended the Network of African Parliamentary Committees of Health 2024 conference and organised a pre-conference event Adopting a Gender- Responsive TB Programming to Ending TB in Africa and Beyond

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

There have been no substantive changes to this output during the reporting period and no changes are currently planned.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

This output has also made excellent progress. Most important is to see the adoption of LIGHT generated knowledge and evidence in national and global policies and guidelines. Future reporting should focus on this only.
## D: VALUE FOR MONEY (1 page)

LIGHT continues to uphold the principles of VfM throughout its operations by ensuring that economy, efficiency, effectiveness, and equity remain central to LIGHT’s strategy.
In Year 4, LIGHT did so by ensuring that investments and purchases supported long-lasting change and generated significant return in the long term, especially to partners. Both LSTM and LIGHT partners strictly adhere to their institutional procurement principles based on fairness and competition to ensure service providers chosen to offer the quality needed at a fair price.
Value for money principles were upheld in various occasions, some examples, provided by LIGHT include:
▪ Selection of the venue for the Y4 Annual Meeting: Paris was chosen as many colleagues were already travelling to attend The Union World Conference on Lung Health.
▪ Holding training within the University of Makerere’s premises therefore accessing facilities free of charge.
▪ To save on fuel, the site assessment for the photovoice project in Uganda were scheduled together with the ECR project supervision projects. This ensured only 1 vehicle was used.
▪ The consortium purchased cameras for photovoice projects in Europe securing cheaper rates and we delivered them to partners via colleagues travelling to our partner countries.
▪ For all conferences, LIGHT attendees registered well in advance to secure early-bird rates and saving considerable amounts of money.

To ensure more clarity in terms of expenditure, overspend, underspend and transfer of funds to partners, LIGHT have set up a system whereby they email each partner individually at the end of the quarter with a clear summary of their financial situation based on their quarterly financial reports and explain the proposed disbursement of funds for them. This has improved communication, increased clarity, and allowed partners to trace their payments with banks or central finance offices in their organisations.

LIGHT successfully demonstrated outcomes (at higher and intermediate levels) against the logframe indicators, and the theory of change, pathways and assumptions remain appropriate.

E: RISK [½ to 1 page]

Overview of risk management

LIGHT’s approach to risk continues to be cautious and risk registers are completed by each partner and submitted to LSTM quarterly. LIGHT also keeps a Consortium-wide risk register which is monitored and discussed monthly (together with safeguarding) during the Programme Management Working Group (PMWG) meeting attended by all partners. FCDO risk ratings are shown in the table below.

Delivery	External	Fiduciary	Intellectual/Research	Operational	Reputational	Safeguarding	Overall
Minor/ / Moderate	Moderate/ / Major	Minor	Minor/Moderate	Minor/Moderate	Moderate	Minor	Minor

LIGHT’s risk assessment was updated as part of this annual report and is aligned to the FCDO risk management system. The risks were all within FCDO’s risk appetite.

Overview of risk and mitigation
Overall, LIGHT have recorded 32 risks, 19 of which are still ‘Active’.

Delivery – Minor – there are six active risks in this category, which LIGHT are managing confidently and are within FCDO risk appetite. The risk is not anticipated to increase in impact and likelihood.

Financial & Fiduciary – Minor – no change since last year and LIGHT still report four active risks in this category which are within FCDO risk appetite. LIGHT continue robust financial monitoring via quarterly reporting, spot checks, and due diligence on all partners, all of which help protect FCDO funds from fraud and misuse. There is an ongoing exchange rate and currency devaluation risk (especially linked to Malawi Kwacha and Nigerian Naira). This is being effectively managed through setting rates in advance, adjusting financial plans, and close monitoring. Photovoice cameras were vandalised while in the custody of Malawi’s customs department: of the 18 procured boxes, only 4 boxes were complete, 9 boxes were missing an SD card, and 5 boxes had nothing inside. A formal complaint was raised, and the case is under police investigation. Meanwhile permission was granted to replace the lost cameras locally, and procurement processes are underway at AFIDEP. The replacement of the lost camera and its accessories is estimated to cost around 1,000 USD.

People – Minor – Despite initial delays, LIGHT have now managed to appoint all staff and are on track to deliver Outputs as originally planned.

Reputational – Minor – no change since last year; LIGHT’s research topics are not controversial, and they do not foresee the findings to be contentious.

Safeguarding – Moderate – Safeguarding rating increased to ‘moderate’ following three safeguarding reports in Y4 (two involving members of staff and one involving a research participant). All have been promptly dealt with by LIGHT’s partners and are now resolved. The LIGHT Safeguarding Lead at ZRC is planning to organise a 2-day gender and safeguarding training course for staff at ZRC in Y5. Finally, safeguarding and risk management remain part of the contents of the Research Administration and Management Programme (RAMP) training. Safeguarding remains high on the LIGHT agenda, and it is reviewed monthly during the Programme Management Working Group meeting and quarterly via reports submitted by partners to LSTM which include a safeguarding mapping tool. Safeguarding is always included in all new research protocols submitted by the LIGHT team to Ethics’ Committees showing how this is now fully embedded in their standard operating procedures.

Strategy & Context – Moderate – LIGHT research activities remain at risk from political instability and civil unrest in partner countries (including terrorism), and extreme weather events. These risks are being closely monitored via regular check-ins with partners during monthly LIGHT Management Meetings (LMT) and PMWG meetings, monitoring elections schedules, government sources and Crisis24 for real-time updates. Staff also complete thorough travel risk assessments prior to any trip. Project activities are adapted where possible, for example by avoiding certain geographical areas or certain times of the year which coincide with rainy seasons, elections, and festivities which can lead to mass gatherings. In the last months, Kenya experienced severe rains which affected communities making people living with TB even more vulnerable. None of the LIGHT staff/partner was affected with rain during the flood season. Kenya experienced serious public demonstrations due to the revised finance budget. So far, this has not affected any staff/partner in Kenya. However, LIGHT are monitoring the situation closely as this might affect the upcoming activities, especially in Nairobi.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]

The budget for the LIGHT Programme is £7,903,834. The total overall project spend from the consortium as of 31st March 2024 was £4,437,046.21. The Year 4 balance of £299,575.15 has been rolled over to future years resulting to the Year 5 (Apr-2024 to Mar-2025) budget total allocation of £1,974,875. Personnel has been the most significant cost for the programme so far, at 73%, with programme costs at 16% and travel at 5%.

LIGHT has increased their effort as a Consortium to forecast accurately and the submission of an updated forecast in the last month of the quarter will further support accuracy in figures that reflect the planned activities and spend. Communication with partners to review progress and budget spend continues to ensure reporting and monitoring of the budgets aligns with project implementation and value for money. The consortium has increased communication, both virtual and face-to-face, especially given the stage of implementation of the project. LIGHT have initiated spot checks on partners’ quarterly expenditures for compliance with project and budget guidelines. In Nov-2023, LIGHT held their Year 4 Annual Consortium meeting in Paris in conjunction with The Union World Conference on Lung Health. LIGHT have reported that the choice of location was due to many LIGHT colleagues already travelling to Paris to present their abstracts and therefore organising the meeting in Paris represented good value for money and good use of time. The Paris meeting was divided into several sessions:
- An update from all researchers to review progress, identify next steps and check alignment with the logframe and the ToC.
- An internal mid-term evaluation looking at whether LIGHT is functioning as expected.
- A panel discussion with National TB Programme (NTP) Managers from LIGHT countries who joined the LIGHT team in Paris in person to discuss LIGHT’s relevance for policymakers and practitioners, cross-learning, sustainability, and monitoring and evaluating policy discussions. Following the NTP panel discussion, LIGHT country teams followed up with NTPs and this engagement revealed a huge appetite for LIGHT research and capacity strengthening among NTP teams from all countries. This has caused the members of NTPs to seek to come together again in cross-learning sessions through LIGHT platforms, where beyond strategizing on the uptake of LIGHT research, the country teams can learn from each other and seek opportunities for collaboration in the fight to end TB.
- Organise and strategize LIGHT conference attendance to maximise the consortium’s networking and impact.
LIGHT is part of quarterly calls with other RPCs during which the groups share lessons learnt, best practices and try to identify areas of shared interest and overlap leading to potential collaboration. FCDO have been updated on potential delays and adjustments to activities and budget and LIGHT CEO and Finance Manager have held regular conference calls with the FCDO team.

LIGHT’s approach to ensure a more equitable management of the consortium still include rotating chairing and note-taking during all meetings. They also rotate hosting annual consortium meetings to share the administrative burden and allow all partners to take the lead and showcase their work. LIGHT also invite a partner representative during official meetings with FCDO and during External Consortium Advisory Group (ECAG) to bring their perspectives to the discussion table and influence the decision-making process.

All equipment and programme assets are recorded, and the records are held centrally at LSTM. The records are updated quarterly using partners’ reports. In addition to reviewing partners’ internal control systems, LSTM initiated spot checks on partners’ quarterly expenditure to ensure compliance with the programme and budget guidelines.

LIGHT complies with transparency related issues and publish their data on the AidStream portal as per IATI standards (LIGHT identifier GB-CHC-222655-LIGHT). LIGHT maintain their delivery chain mapping which is reviewed periodically to ensure it is up-to-date and it reflects changes in task and budget allocation.

LIGHT receives expert advice from an External Consortium Advisory Group (ECAG) as well as from Country Advisory Groups (CAGs). They invite ECAG to all the annual consortium meetings and hold annual calls with them to provide updates on research progress. The Uganda Country Advisory Group (UCAG) meeting was held virtually on 23 Feb 2024 and attended by the 7 UCAG members and members of the Uganda Project team. Agenda covered ECR project updates, sharing of the PEA findings and upcoming Photovoice project. Similarly, the Nigeria Country Advisory Group (NCAG) met on 5 Dec 2023 and covered ECR project updates.

G: MONITORING, EVIDENCE AND LEARNING [1/2 - 1 page]

Monitoring and Evaluation
LIGHT monitors its progress in several ways: the consortium holds monthly programme management working group (PMWG) calls with project managers, administrators and finance officers from all partners and discuss progress, reporting requirements, issues, safeguarding, risks, and capacity strengthening. They also hold monthly management team meeting with PIs and Research Team meetings which include all researchers. In addition to these consortium-wide meetings, each partner holds internal LIGHT team meetings on a weekly basis.
Further, field support supervision was conducted during data collection for all our ECR projects (e.g. for Uganda, the ECR made 5 visits to the sites).
To measure the impact of our LIGHT activities, the consortium has developed a series of tools:
1. LIGHT impact assessment framework: this includes identifying and mapping our impact at various levels: instrumental, conceptual, capacity building/strengthening, enduring connectivity & networking, culture and long-term impact and contributions.
2. There are also separate assessment tools of the training of trainer workshops and to assess the result and impact of these training and its implementation in Malawi, Kenya, Uganda and Nigeria.

Finally, during the meeting held in Paris, the LIGHT team (PIs, Early Career Researchers and Research Uptake Managers) conducted an internal mid-term evaluation looking at whether LIGHT is functioning as expected and whether there is evidence that their approach continues to be appropriate to achieve our objectives. This resulted in a 6-page document summarising discussions on effectiveness, efficiency, relevance, sustainability / legacy, and Value for Money (VfM) (can be shared upon request).

FCDO’s Global Health Research team (SRO and DPM) has regular (quarterly) meetings with LIGHT management (incl. rotating country PI participation) and FCDO is invited to the annual consortium meetings but had to decline attendance this year due to clashes. We have also connected the LIGHT team to FCDO in-country teams in Nigeria, Malawi, Uganda.

Evidence
LIGHT has developed considerable evidence and capacity building as part of its core mandate of implementation research. The new evidence is described in the sections and above and has been published and shared widely, especially among policymakers and National TB Programme Managers in country. There is no fundamental change in the context surrounding the aim and objectives of this research programme.

The Programme is focussing on particular gendered aspects of TB diagnosis and treatment and is therefore at the core of the ‘Leave no one Behind’ agenda. It is particularly emphasizing the case for gender disaggregated data on TB.

This year, an external evaluation will be conducted of all Research Programme Consortia and LIGHT will participate in this exercise.

Learning
This programme is delivering new knowledge and evidence which is being shared with global and national stakeholders (including national Ministries of Health and National TB Programmes) as well as FCDO. This has already influenced policy and programmes at country and international level.

New learning has been demonstrated on how to conduct Training of Trainers which is now rolled out across other health programmes and LIGHT is a model for this and has multiplied its training approach.
Also, its reporting is a model to other RPCs. To this end, we have encouraged LIGHT to share their reporting with other RPCs to increase overall quality reporting across these programmes.

Date of last narrative financial report	7 August 2024	Date of last audited annual statement	30 November 2023