## Annual Review

Title: Climate Adaptation Water and Energy Programme (CAWEP)
Programme Value £ (full life): £19,550,000		Review date: 10 February 2025
Programme Code : 300164	AMP start date: 10 November 2019	AMP end date: 30 March 2026

Summary of Programme Performance
Year	2021	2022	2023	2024	2025
Overall Output Score	B	B	A	A	A
Risk Rating	Major	Moderate	Moderate	Moderate	Major

DevTracker Link to Business Case:	https://devtracker.fcdo.gov.uk/projects/GB-GOV-1-300164
DevTracker Link to results framework:

A. SUMMARY AND OVERVIEW

A.1 Description of programme
The Foreign Commonwealth and Development Office (FCDO) in Zimbabwe is funding the implementation of CAWEP through the United Nations Development Programme (UNDP) and United Nations Children's Fund (UNICEF). The programme is strengthening the ability of vulnerable communities to withstand climate shocks through supporting the development of climate resilient water and renewable energy infrastructure in the most vulnerable communities of Zimbabwe to enable: (i) continued access to water for productive and household use, including during droughts and floods, and (ii) improved access to clean and affordable energy to support economic activities, ensuring sustainable livelihoods. CAWEP is strengthening Early Warning Systems (EWS) in vulnerable districts, enabling timely access to and use of weather & climate information to better anticipate and respond to climate shocks. The programme is providing technical assistance to the government as well as non-state actors to support the wider use of climate information in designing and delivering resilient water and energy infrastructure. Learning and evidence being generated through this programme is being used to influence climate policy improvement and support national climate adaptation and resilience plans. As such, it aims to build and demonstrate an understanding of what works and what challenges must be overcome to deliver resilient and sustainable outcomes.
[note] Systems put in place to analyse and identify potential weather- and climate-related risks and hazards. All early warning systems aim to enable early action to save and protect lives, livelihoods, and assets of people at risk.

FCDO supports the delivery of this programme in twenty districts across the country and intends to help over seven hundred thousand people to better adapt to the effects of climate change through sustainable access to solar-powered multiple use water and energy supply systems, and to reliable weather and climate information.
[note] Buhera, Mutare rural, Makoni, Mutasa, Gweru, Zaka, Chiredzi, Gutu, Chikomba, Chipinge, Chimanimani, Nyanga, Binga, Insiza, Lupane, Bubi, Umguza, Nkayi, Chivi, Tsholotsho.

The programme has two main components. These are briefly explained below:

A.1.1 Adaptive & Flexible Water and Energy supply- Component 1
This component was designed to flexibly respond to emerging water & clean energy priorities including providing infrastructure support to avert the impact of potential climate or weather-related disasters. This £2.5 million funded component was implemented through UNICEF, providing sustainable basic water supply using climate resilient infrastructure, through the installation of solar powered water schemes in nine districts. It was implemented between July 2021 to June 2022. This review is did not assess this component because there is no partner actively managing it.

A.1.2 Climate Adaptation - Community water & renewable energy infrastructure & Early Warning Systems (EWS) – Component 2
This is the main CAWEP component that seeks to contribute towards community and institutional climate resilience in Zimbabwe. Work under this component is designed to boost climate change adaptation through enhanced climate proofing, development of climate resilient community water and renewable energy infrastructure and strengthening EWS and response in selected vulnerable districts. The total funding for this component is thirteen million six hundred thousand pounds (£13,600,000) covering the period August 2022 to November 2025. This review will mainly focus on this component.
[note] Measures taken to prevent infrastructure from being vulnerable to potential long-term climate impacts. Under this project, this involves infrastructure improvements, solar pumping, and water-use efficient, irrigation technologies (drip, sprinkler systems)

A.2 Summary supporting narrative for the overall score in this review
This review rates CAWEP’s performance over the past year at A score, as the programme largely met expectations and exceeded on two of the four outputs. Notable achievements include
1. Completion of a 200-kilowatt solar mini-grid in Chipinge, one of the most climate-vulnerable districts in Zimbabwe. This is the largest off-grid mini-grid in the country and the first ‘smart green village’. This project, which was launched by the president through the Minister of Energy and Power Development in October 2024, is transforming lives and contributing 10% of Zimbabwe’s emission reduction target through mini-grids.
  [note] A sustainable and environmentally friendly community that incorporates innovative technologies and practices to minimize its ecological footprint. The concept combines traditional village life with modern green technologies and smart infrastructure. Key Features include use of a range of renewable energy sources, less reliance on fossil fuel, energy, and water efficiency.
2. Rehabilitation of an improved, climate proofed dam in Wanezi, Insiza district. This is expected to transform livelihoods and contribute to building resilience.
  [note] Designed and constructed to withstand the impacts of climate change, such as Increased flood risk, changes in water availability, rise in temperature and sedimentation.
3. Government of Zimbabwe’s adoption of the CAWEP multidimensional/integrated model of deploying renewable energy infrastructure and would like it replicated across the country.
4. In the year, CAWEP successfully helped to get the National Adaptation Plan (NAP) and National Energy Efficiency Policy (NEEP) approved by the government. These are key policies that complement and help to sustain work being done under CAWEP.

A.3 Major lessons and recommendations for the year ahead
The following sections highlight key lessons learnt in the year under review and provide strategic recommendations to be taken forward in the coming year.

A.3.1 Key lessons learnt
- Strong partnerships with the government and communities on understanding the critical needs of marginalized communities and the potential of available resources can lead to positive transformation and impact quickly, creating the foundation for resilience building. This is the case of Hakwata mini-grid project, which could be replicated elsewhere.
- Combining a range of interventions on water, renewable energy, EWS, Village Savings and Lending (VSLs) and vocational training is an effective way of building resilience as demonstrated by the Hakwata smart green village project.
- Access to energy is a critical enabler for a wide range of sustainable development goals. As demonstrated in Hakwata, if designed and installed properly with strong community participation, solar energy can deliver multiple benefits. These include health service delivery, learning conditions, employment creation, dignity for women and girls, bridging the technology and digital divide, enabling rural communities to access information, and economic opportunities, as well as access to clean energy.

A.3.2 Key Recommendations
Below are high level strategic recommendations. Other output related recommendations are provided in Section C.
- To help address the outstanding governance issues on water supply and solar infrastructure, finalise and get Memorandum of Understanding (MoUs) with Zimbabwe National Water Authority (ZINWA) and Rural Electrification Fund (REF) signed by 31st March. These should focus on operation and maintenance, water treatment, revenue collection and management.
- Based on learning experiences from implementing CAWEP, explore and document recommendations on ways to get private sector involvement in such projects. This include piloting a model with private sector partnerships in rural minigrids and business management of irrigation schemes.
- A time extension from November 2025 to March 2026 is needed to (i) consolidate works and technical improvements based on findings of this review and the recent technical assessments,(ii) give enough time to monitor and test recently completed infrastructure works, (iii) piloting new models that will inform the designing of future programmes and completing the documentation of a range of learning products CAWEP is developing.
  [note] (i)	Effectiveness and impact of taking a multidimensional approach using water and renewable energy to help people to adapt and become more resilient through enhancing outcomes on livelihoods, health, education, nutrition, entrepreneurship, (ii)	Sustainability built around business models on renewables, irrigation, and markets, private partnerships and working with Micro Financial institutions. (iii)	Understanding the impact of low-cost approach to adaptation through Early Warning Systems (EWS) and institutional systems strengthening on climate adaptation? The programme would like to understand if there is a risk of maladaptation if implemented in isolation. (iv)	Understanding the cost and affordability of climate proofing and what innovation is needed to make it affordable? It also involves identifying opportunities for the private sector in climate adaptation.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

B.1 Theory of Change Description
The long-term impact that CAWEP seeks to make is to help communities and public institutions in Zimbabwe to become more resilient to adverse effects of climate change such as droughts and floods. To achieve this, the programme logic is that poor and vulnerable households are supported to become more adaptive to the effects of climate change through sustainable access to long term climate resilient and multiple use water and renewable energy infrastructure, and Early Warning Systems (EWS). The programme is still following this logic, and the theory of change (ToC) has not changed in the past year. Results from the Outcome Monitoring Survey (OMS) in the past year confirm the programme relevance and appropriateness to address the climate problem. See the Theory of Change below in Fig 1.

Fig 1: CAWEP Theory of Change (ToC)

B.1.2 Stakeholder and beneficiary engagement
Overall positive programme progress is significantly attributed to strong multi-stakeholder engagement and participation. The multidimensional nature of the programme requires strong delivery partnerships and extensive work with a range government ministries at all levels, the private sector, and communities. The successful completion of the first smart green village project in Zimbabwe was a result of strong stakeholder engagement and delivery partnerships. The Steering Committee (SC) which met three times in the year has been the main platform for senior government engagement on policy and strategic issues while at sub-national level, UNDP’s technical team and technical government departments continue to deliver works in partnership with communities and contractors. Strong stakeholder and community engagement has helped to meet key milestones as seen in section C under output reporting. Community engagement this year includes local planning meetings for resource mobilisation in constructing water works and on operation and maintenance. This also helped the programme to remain on track to deliver good Value for Money (VfM) as explained in section D.

B.1.3 Progress towards achieving Outcomes and Impact
CAWEP is making good progress towards achieving outcomes and impact. The El Nino induced drought, experienced in project districts in the past year, tested the programme effectiveness in strengthening community adaptive capacity and resilience. The OMS finds that CAWEP interventions in all project areas have contributed significantly to households’ coping strategies against the effects of El Nino through livelihood diversification activities such as VSLs, renewable energy provision and irrigation schemes. Programme interventions are contributing to building resilience. According to OMS, the Resilience Capacity score nearly doubled from baseline. The percentage of people with a medium resilience score increased from 20% at baseline, to 37%. The percentage of people in the low resilience score decreased from 79% at baseline to 63% at OMS.
[note] A measure of the household capacity to withstand and recover from climate shocks. CAWEP is using the World Food Programme (WFP) Resilience Capacity Score (RCS) approach which measures a household’s perception of their resilience capacities against a specific shock, where they demonstrate ability to anticipate, absorb, adapt and recover.

This review also finds that outputs are on course to deliver the desired outcomes. This is attributed to CAWEP’s contribution in irrigation development, clean water supply and income generation activities, hence food security. The number of people supported to better adapt to the effects of climate change through sustainable access to multiple use water and energy infrastructure, and EWS has increased. Cumulatively, CAWEP has helped 407,264 people to better adapt to effects of climate change and on course to reach the programme target of 700,000.

Figure 2 below shows progress delivering one of the main outcome indicators.

B.1.4 Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

With just over a year before CAWEP closes all set outputs and outcomes on course to be delivered. This year is really important to focus on strengthening programme sustainability. This period is important for, consolidating learning, completing outstanding works and fully deliver its impact and results. Other reasons for the programme to continue are:

- CAWEP is delivering on expectations as set out in the Business Case, helping to address the underlying factors inhibiting communities and institutions’ ability to cope with the effects of climate change, which include, (i) lack of access to weather and climate information to better understand, plan for and reduce the risks and impacts of climate change and of weather extremes and (ii) lack of productive and climate proofed water and energy infrastructure that help to build sustainable livelihoods and reduce risk of people experiencing severe impacts of climate shocks. CAWEP has already helped over 400,000 people to better adapt to climate change through improving access to weather and climate information, multiple use water and clean energy. The Government of Zimbabwe (GoZ) recognises the positive impact that CAWEP is making as evidenced by the presidential commissioning of the 200-kilowatt solar mini-grid in Chipinge district and financial contribution towards the project.
- The programme helps fulfill UK international commitments on tackling climate change, in particular channeling climate finance towards helping vulnerable communities to adapt to climate change.
- CAWEP is providing lessons and evidence on future approaches to climate adaptation and resilience for example on the smart green village model and climate proofing.
- Overall, the programme continues to represent good value for money through its multiple use water and energy approach which is showing potential and having an impact on other UK development priorities on empowering and educating women and girls, health, and energy efficiency.

## C. DETAILED OUTPUT SCORING

Output Title	Developed climate resilient multiple use water and energy infrastructure
Output number:		1	Output Score:	A+
Impact weighting (%):		40	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1 No. of community multipurpose water & clean energy infrastructure developed/rehabilitated with special technical designs and features that respond to climate risks. Disaggregated by type (i) Solar Piped Water Systems (PWS) (i) mini/micro grids, (iii) small dams (iv) Irrigation systems/networks, Biogas digesters	195	228
1.2 Proportion of functional water and renewable energy infrastructure	80%	94%
1.3 Proportion of water and renewable energy infrastructure with a community management structure and business model for maintenance	80%	100%

C.1 Briefly describe the output’s activities and provide supporting narrative for the score.
An A+ rating is given to this output as the programme performed above expectations on all three indicators as shown in the table above. Key achievements during the year include:
1. the completion of Zimbabwe’s first smart green village project in Hakwata, Chipinge district, comprising of 200 kWp minigrid, currently the biggest off grid minigrid in the country. The solar minigrid, which was commissioned by the President of Zimbabwe through the energy minister, has been transformative, making an immediate positive impact on lives and socio-economic development of one of the most climate vulnerable communities in Zimbabwe. Over 12,500 people now have clean, affordable energy from 104 new solar minigrid connections; new business enterprises have been established, as well as a cellular network enabling internet connections for schools, health centres, communities, and local businesses. The improvement in grade seven results from 55% in 2023 to 67% in 2024 is partly attributed the project, in particular through access to solar energy and water. Access to clean energy through solar energy and biogas digester has helped to restore the dignity of women and girls. The intervention is directly contributing to women and girls’ education, empowerment and helping to end gender-based violence often triggered by lack of access to business opportunities, water, and energy resources which the project has provided.
2. completion of Wanezi Dam in Insiza district, which is already filled up, storing 1.7 million cubic meters of water for irrigation and potable water.
3. completion of water supply system in Binga district and setting up of five irrigation systems. Newly established irrigation schemes are producing crops for the first time in Binga.
4. average functionality rate of installed infrastructure is already 94%, against the 80% expected at this stage. The target was set in anticipation of initial difficulties experienced when setting up new systems. While there is good progress on this indicator, it should be noted that a significant number of these facilities are new and expected to be functional. Continuous assessment is needed.
5. the programme’s approach of thoroughly climate proofing all water and energy infrastructure means that it can withstand future impacts of climate change while enhancing resilience.
C.1.1 Challenges
While good progress has been made on this output during the year, the following challenges were experienced:
1. A couple of breakdowns were experienced following the completion of the Binga, Mlibizi water supply system. This temporarily reduced the area under irrigation and crop yield. The problem was mainly due to pump pressure fluctuations and limited community and institutional capacity to operate and maintain some components of the water supply system. This is now being addressed.
2. Delayed completion of water reticulation and irrigation system works at Gororo, due to unsuitability of initial pump house location at Gororo which had weak soils. The contactor was also not able to mobilise all material on site on time. UNDP has engaged the contractor and agreed on new completion timelines. UNDP will claim default liability damages if the new deadline is not met.
C.1.2 Describe any changes to this output during the past year, and any planned changes as a result of this review.
No changes were made on this output during the past year. The programme is not planning any major increase in the coming way but will seek opportunities to reach out to more people through the consolidation works. changes in the coming year.

C.1.3 Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

C.1.3.1 Recommendations from the previous AR
The previous AR recommended the following under this output:

Recommendation	Progress
Recommendation 1: Closely monitoring the functionality of established infrastructure. (Ongoing)	Ongoing: Programme teams continue to monitor functionality on a regular basis. Technical problems identified at Mlibizi water supply system and subsequent solutions were a result of close monitoring.
Recommendation 2: Ensure technical trainings on operation and maintenance of irrigation equipment to ensure proper use (UNDP/Contractors) by June 2024	Completed: O&M technical trainings for users and key government departments were completed. However, refresher trainings are needed before programme closes.
Recommendation 3: Strengthening security of assets at all sites. UNDP to work with ZINWA and REA on this. The programme has a draft security strategy which should be implemented. This review is recommending ZINWA and REA to take up most of security responsibilities, acknowledging community limitations in providing maximum security. (March 2024)	Still in progress: ZINWA and REF employed security guards to guard water and power infrastructure while electric fence installation at Hakwata solar mini-grid is in progress.
Recommendation 4: Work out the most appropriate and sustainable tariff system for water and power. The adopted tariff system should (i) motivate consumers to pay, (ii) balance affordability/ability to pay of consumers, (iii) be sustainable and able to cover maintenance costs and (iv) be replicable and demonstrate this as viable and attractive to others to adopt the models elsewhere. (UNDP, REA, ZINWA) by June 2024	Partially completed: The solar mini grid tariff setting tool and framework was agreed by all stakeholders. Costings are now being finalised. Mlibizi piped water tariff cleared by the ZINWA Chief Executive Officer and will be effected before the handover of the system to ZINWA after the final system testing .
Recommendation 5: Draft and sign a Memorandum of Understanding (MoU) that communicates the mutually accepted expectations, current and future roles, and responsibilities of all of the parties involved in CAWEP. Parties include FCDO represented by the British Embassy in Harare (BEH), Government of Zimbabwe (GoZ), represented by partner departments and UNDP. This will strengthen collaboration and accountability, which are critical in ensuring programme success and sustainability.	Still in progress: ZINWA and REF draft MOUs are now in place and currently under reviewed by the respective departments’ senior management.
[note] ZIMBABWE NATIONAL WATER AUTHORITY

C.1.3.2 Lessons learnt
The key lesson is that large water supply systems with multiple components such as Mlibizi need a phased implementation approach and be given adequate time to fully assess system performance and rectify any technical problems identified before being commissioned.

C.1.3.3 Recommendations for the year ahead
In the coming year, this review makes the following specific recommendations.
- Speed up the completion of the outstanding irrigation schemes in Gororo and Wanezi. The mid-term evaluation identifies this as a potential threat to building resilience.( April 2025, UNDP)
- Strengthen capacity of ZINWA and community operators to operate the system in Binga.(April 2025, UNDP)

Output Title	Established/resuscitated community governance structures are effective in managing installed infrastructure.
Output number:		2	Output Score:	B
Impact weighting (%):		30	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 No. of governance structures trained to operate, manage, and maintain installed infrastructure are operational. Disaggregated by community/ districts referred to as Asset Management Committees (AMCs)	10 AMCs	16
2.2 % of people in community governance structures who are women	70%	69%
2.3 % of representative community governance structures engage effectively with both community and external stakeholders, including maintenance service providers.	80%	100%
2.4 % of the households that pay for water and/or power use/maintenance.	65%	98.7%
2.5 % of targeted communities with a functional income generation/Business model to finance operation and maintenance	70%	100%
2.1.1 No. of women & youth-led enterprises established as a result of technical and business skills training. Disaggregated by (i)Type of training, (ii) Sex, (iii) Age, iv) Type of business	40	39
2.1.2 %ge of women-led enterprises accessing credit from financial institutions Disaggregated by (i) sex, (ii) Type of business	35%	0 (Activity Delayed)
2.1.3 %ge of youth-led enterprises accessing credit from financial institutions Disaggregated by (i) sex, (ii) Type of business	20%	0 (Activity Delayed)
2.1.4 No. of loans disbursed from the Revolving Loan Fund (disaggregated by gender)	40 Female 20 Male 20	0 (Activity Delayed)
2.1.5 Total annual value of loans disbursed to women and youth-led enterprises through the Revolving Loan Fund	80000	0 (Activity Delayed)
2.1.6 Percentage of Portfolio at Risk (PAR)	5%	0 (Activity Delayed)

C.2 Briefly describe the output’s activities and provide supporting narrative for the score.
This output seeks to empower communities to organise themselves, mobilise financial resources, have full control, access and management of infrastructure built or upgraded through CAWEP. This is one of the programme’s key strategies to sustain community water and energy infrastructure and the intended outcomes. In April 2024 six new indicators were added to this output following the approval and funding of the programme’s Business Development Strategy (BDS). Indicators on infrastructure operation and maintenance, vocational skills development, market, and stakeholder engagement were largely met. Notable successes include (i) a significant number of households (98.7%) able to pay for water or electricity despite being a drought year that led to income losses; (ii) Community ability to engage the market and negotiate contracts with private sector. For example, in Gororo (Chivi district), the community led Irrigation Management Committee (IMC) successfully negotiated a deal with Whitney Paprika on production of chillies for export. A chillies nursery has now been established; (iii) impressive enrolment levels by women and youth in vocational skills training. To date, the project has trained 928 beneficiaries (240 Males and 688 Females, including 108 Males and 283 Female youth). Through the BDS, the programme planned to set up a revolving fund to help the trained women and youth to borrow and start up their business using the acquired skills. However, due to delays in procuring the revolving fund manager, the facility was not established on time, resulting in five of the six new indicators not being met. Internal UNDP processes and approvals took longer than expected. Given this, the review rates performance of this output at B, indicating expectations were moderately not met. At the time of the review, UNDP were negotiating with several potential suppliers to provide this service.

C.2.1 Challenges
Besides failure to engage the revolving fund manager on time, no major challenges were encountered in delivering this output.

C.2.2 Describe any changes to this output during the past year, and any planned changes as a result of this review.
Following the approval and funding for the programme Business Development strategy (BDS) to help sustain the programme, additional indicators were added to this output to help tracking the implementation and success of the BDS. No further changes are being recommended by this review in the coming year.

C.2.3 Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

C.2.3.1 Recommendations from the previous AR
The previous AR recommended the following:

Recommendation	Progress
Recommendation 1: Ring fencing the operation and maintenance funding plan, ensuring funds are always there and an up-to-date record is kept. UNDP to help identifying how savings should be used for operations and maintenance. (March 2024)	Completed – VSLs allocated 5% of proceeds to Operations & Maintenance across the programme irrigation plots enabling farmers to repair and manage the infrastructure.
Recommendation 2: UNDP to ensure community-based business plans are inclusive and community owned to get maximum support and everyone’s contribution (ongoing)	Completed - 928 beneficiaries were trained to develop business plans and entrepreneurship. This resulted in 39 new enterprises being established.
Recommendation 3: UNDP, working with government should focus on rolling out the approved programme Business Development Strategy which sets out existing opportunities and actions to create multiple sources for revenue generation to (i) sustain CAWEP investments and (ii) develop local economies, creating jobs and sustainable livelihoods.	In progress- Business Development Strategy started being implemented in August. Funding for the business development was secured in April 2024.

C.2.3.2 Lessons learnt
A key lesson is the importance of ringfencing O&M funds, built up through VSL, to ensure availability of funds when the need arises. This was demonstrated by SABA irrigation scheme where they used the ring-fenced funds for repairs.

C.2.3.3 Recommendations for the year ahead
The following recommendations are made under this output:
- Finalise the procurement of the revolving fund manager and the fund management modalities (March 2025, UNDP)
- Ensure that the revolving loan fund manager has capacity to work and operate with various financial institutions (both commercial banks and microfinance institutions) to ensure respective targets under the project are met (May 2025, UNDP).
- Test and strengthen the capacity of community-based management structures and youth enterprises on financial management, leadership and conflict resolution as the programme gets into the financial year. (Quarterly until August 2025, UNDP)
- Fully implement market linkage trainings, ensuring communities are better equipped to engage, analyse, and respond to the market to get the best out of their produce. (June 2025, UNDP)

Output Title	Enhanced Early Warning Systems (EWS), helping vulnerable communities to better anticipate, plan and respond to negative impacts of climate change and extreme weather events
Output number:		3	Output Score:	A+
Impact weighting (%):		20	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1 No. of districts/communities that receive EWS strengthening support from CAWEP. Disaggregated by type of support e.g. Hardware (Equipment), Software (Training)	16	16
3.2 No. of people that regularly (monthly) receive and understand weather & climate information	300000	322448
[note] Chipinge, Chimanimani, Buhera, Makoni, Mutasa Nyanga, Binga, Insiza, Lupane, Hwange, Bubi, Umguza, Nkayi, Chivi, Tsholotsho, Mutare

C.3 Briefly describe the output’s activities and provide supporting narrative for the score.
The purpose of this output is to strengthen community and key institutional capacity to adapt and become more resilient to climate change by strengthening early warning and response systems to better anticipate and respond to climate shocks. Key activities implemented to deliver this output include setting up of modern automated weather stations (AWS), beneficiary training on reading, interpretation and application of weather and climate information, setting up dissemination platforms and equipping key government stakeholders and community focal persons with hardware and software required to make EWS efficient and effective. The programme entered strategic partnerships with five radio stations covering Masvingo and Manicaland provinces. This enabled a wider reach, going beyond the targeted areas and beneficiaries. This resulted in this output scoring an A+ in this review, moderately exceeding expectations. The programme OMS conducted during the year also notes significant improvement in access to and application of weather and climate information as a result of CAWEP intervention. The evaluation finds that 97.7% of respondents have access to weather and climate information improved and timely access, against a baseline of 15% before the intervention. Overall, there is good progress on timely dissemination of this information. A 5% increase in beneficiaries who are timeously using this information in their planning was recorded. Use of generated data has helped CAWEP communities to respond to the El Nino induced drought in 2024. For example, in Insiza district, 54 farmers from Tsotsi and Nyezi villages received advisories to plant small grains following consecutive and numerous hot and dry weather forecasts. They managed to get a good harvest whilst many others had crop failure.

C.3.1 Challenges
The main challenge is an unstable mobile phone network for a few communities which resulted in delayed messages and in some cases not being able to respond to the messages.

C.3.2 Describe any changes to this output during the past year, and any planned changes as a result of this review
Adding a new indicator that looks at assessing the level of understanding of weather and climate information disseminated.
C.3.3 Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

C.3.3.1 Recommendations from the Previous Annual Review
The table below shows progress on implementing the recommendation made on this output in the last Annual Review.

Recommendation	Progress
Recommendation 1: Continuous monitoring of set up EWS functionality and use and address any technical, policy and social issues that prevent effectiveness or application. UNDP to continue assessing effectiveness of training methods and how well users demonstrate the skills after training.	Ongoing: Programme teams continued to monitor the EWS set up in the year. This has been helpful in identifying and addressing bottlenecks on increasing coverage as mentioned in section C3 above.

C.3.3.2 Recommendations for the year ahead
To ensure the intended outcome on enhancing community adaptation is achieved and sustained, this review recommends the increased use of radio platforms and in vernacular languages to reach out to more people.

Output Title	Improved National Climate adaptation policies/Strategies/learning material supported/developed
Output number:		4	Output Score:	A
Impact weighting (%):		10	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
4.1 No. of policy briefs developed using evidence generated by the programme to influence upscaling or changes to different approached to climate adaptation/resilience	2	2
4.2 No. of policies or strategies developed/supported as a result of programme influence. Disaggregated by Type e.g., specific policy, strategy, learning paper, operational manuals	4	4
[note] National Energy Efficiency Policy Brief and National Clean Cooking Strategy Advocacy summary
[note] National Adaptation Plan (NAP), Piped Water Scheme Protocol (PWSP) Energy Efficiency Policy (NEEP)
[note] NAP, NEEP, National Clean Cooking Strategy NCCS- PWSP

C.4 Briefly describe the output’s activities and provide supporting narrative for the score.
This output is designed to improve the climate policy environment to help sustaining the overall outcomes and impact that CAWEP is aiming to achieve in Zimbabwe. CAWEP policy support and influence has led to the approval of the National Adaptation Plan (NAP) and the National Energy Efficiency Policy (NEEP) in the past year. These are really important policies that outline Zimbabwe’s strategies and priorities on tackling climate change. The UK support on these policies is expected to help Zimbabwe to identify and prioritise areas of investment, reducing climate vulnerability and promote international cooperation on climate change.

In addition, two policy briefs have been developed using evidence from implementing CAWEP and have led to adoption by government. These are the National Energy Efficiency Policy and the National Clean cooking strategy.

The programme has completed the draft National Insurance strategy for rural water supply infrastructure. CAWEP is funding the development of this strategy to enhance long term sustainability and resilience of rural water supply infrastructure through access to finance to mitigate risks related to disasters, theft, and other unexpected events on water supply infrastructure.

C.4.1 Describe any changes to this output during the past year, and any planned changes as a result of this review.
There were no changes on this output in the past year.
C.4.1 Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

C.4.2.1 Recommendations from the Previous Annual Review
The previous AR made the following recommendation. Progress on implementing this recommendation is also provided below.

Recommendation	Progress
Recommendation: FCDO/UNDP to continue lobbying the government on approval and finalisation of NAP. This is also important to help mobilising public and private financing for adaptation. (Ongoing)	Completed: The National Adaptation Plan was approved during the year.

C.4.2.2 Recommendations for the year ahead
- Make strategic recommendations on how government can use lessons learnt from CAWEP to implement approved policies, ensuring there is no implementation gap when CAWEP ends.(September 2025, UNDP)
- Finalise the National Insurance Strategy for Rural water supply and start to mobilise communities under CAWEP to consider getting insurance policies.(May 2025, UNDP)

## D: VALUE FOR MONEY

D.1 Key cost drivers and performance
The main programme cost driver is the procurement of equipment and material for water and solar energy infrastructure. UNDP continued to use the competitive procurement bidding system for all contracting to secure the most advantageous combination of quality and price. This led to reductions of costs on several major purchases leading to savings on the different budget lines. The programme will look at using these savings to deliver more outputs and increasing beneficiary reach.

D.2 Value for Money (VfM) performance compared to the original VfM proposition in the business case
The programme continues to track VfM metrics under the different categories on Economy, Efficiency, Effectiveness and Equity. The programme has VfM performance indicators which this review assessed against baseline indicators. Overall, the programme is making good progress in achieving positive metrics on VfM. Please see detailed VfM assessment below.

D.2.1 Economy:
UNDP competitive bidding practice ensured the goods and services were bought at the right price and not beyond what the market offered. Savings were also made in the process. Strategic partnerships with the government’s Rural Electrification Fund (REF) EF, Zimbabwe National Water Authority (ZINWA) and other departments resulted in the programme making economic gains through financial, expertise, and workforce contributions from these partnerships. This review finds that the main VfM economy indicators performed well, implying the main cost drivers spent less than what was estimated by the feasibility study. For example, the feasibility study estimated that the irrigation development and potable water supply works will cost close to seven million united states dollars against the current actual cost of just over one million united states dollars. Most of the works are completed. It is unlikely that the final delivery costs will increase significantly.

D.2.2 Efficiency:
Efficiency is being achieved through minimizing cost of reaching a beneficiary. Through measures such as UNDP’s Direct Implementation Modality (DIM), community participation and use of government expertise, the programme cost per beneficiary is currently at £14 against the expected £52 from the feasibility study. Efficiency is also being achieved through the use of solar energy to power irrigation, business operations, institutional and household use. CAWEP is achieving more benefits with less cost and effort. For example, more irrigation hectarage and yield is being achieved through solar pumping and efficient drip irrigation in Binga and Insiza districts. More productive time, forests and money are being saved through the use of biogas digesters. For example, one woman in Hakwata said biogas in her kitchen is saving her time because she does not have to travel long distances to fetch firewood. Instead, she is using the time for other productive things. The intervention has also improved her health. She previously suffered from respiratory diseases as a result of continuous use of firewood for cooking. The project could be more efficient by establishing battery storage at Mlibizi for overnight use and enhancing capacity to transfer excess power to the main grid, helping to offset energy consumption and lowering the electricity bill. This is being considered for investments next year.
[note] Modality whereby UNDP takes on the role of Implementing Partner.

D.2.3 Effectiveness:
The main intended outcome of CAWEP is that poor and vulnerable households are better able to adapt to effects of climate change through sustainable access to multiple water and clean energy supply infrastructure to enable productive, household, and institutional use. This review and the OMS judge that the programme is on course to deliver the expected outputs and outcomes. Key achievements made in the year, notably completion of the solar minigrid, Wanezi dam, irrigations systems and automated weather stations demonstrates the programme effectiveness. However, to sustain all this, the focus in the coming year will be on strengthening governance and financing of operations and maintenance.

D.2.4 Equity:
CAWEP operates in the most climate vulnerable districts experiencing low rainfall, very high temperatures and frequent seasonal droughts. These are also among the poorest districts in Zimbabwe. CAWEP is helping poor communities in these marginalized districts to build resilient livelihoods through sustainable access to water, clean energy, weather, and climate information. In the past year, the project reached out to more disadvantaged women and people with disabilities with a range of interventions, including project leadership, entrepreneurship, access to clean energy and water. Due to improved access to electricity, Hakwata is now able to provide 24-hour health services, especially for pregnant mothers. Gender considerations were also captured under output 2- ‘enhanced governance structures’ which saw a lot of women being given leadership positions in key committees for water and energy management. The proportion of women in leadership position is 00%. Women are seen actively participating in committees and leading the management of different project components. For example, in Hakwata the chair of the Energy Management Committee (EMS) is a woman, responsible for planning and assigning daily task related to day to day running of the minigrid.

D.3 Assessment of whether the programme continues to represent value for money
Based on the above analysis CAWEP still represents good value for money.

E: RISK

E.1 Overview of risk management
Risks are reviewed monthly during the progress meetings with between FCDO and UNDP. In-depth risk discussions are done every quarter before updating the risk register. UNDP escalates to FCDO risks with increasing likelihood and rating for actioning. For most of the year, the programme overall residual risk rating has been moderate. Two of the active risks materialised. These are under safeguarding and programme delivery categories. The table below is an update on some major risks which the programme had identified as possible in the year.

Risk category and appetite	Risk description, update, and mitigation measures.
Safeguarding- cautious	Description- Programme activities causing negative environmental and social impact including disruption of social norms and values. This may also involve contractors and partner staff exploiting communities. / Update- A safeguarding incident was raised in one of the project sites. UNDP & FCDO are strengthening mitigation measures. / Mitigations- / UNDP is ensuring contractors, employees and subcontractors adhere to the signed code of conduct on Sexual Exploitation and Abuse (SEA), conducting sensitisation of community and district officials in the Grievances Reporting Mechanism (GRM) and identification of SEA issues.
Policy and program delivery- receptive	Description- Loss of biodiversity & ecosystems that support them due to construction activities. Increase in frequency of interactions between humans and wildlife. / Update- Conflict between people and animals happened at Mlibizi. Crops were partially destroyed leading to financial loss. / Mitigations- A human wildlife conflict mitigation plan was jointly developed with Zimbabwe Parks and Wildlife Authority. This is now being implemented. Measures include electric fencing of irrigation schemes and community training on human wildlife conflict.
Financial and fiduciary- cautious	Description- Misappropriation of project funds by partners and contractors. This include contractors being paid for poor workmanship, inflating quotations, payment of ghost participants at workshops leading to failure to deliver intended results. / Update -There was no evidence of this risk materialising in the past year. However, it is an active risk and continues to be closely monitored as per FCDO’ s updated risk protocols on Fraud Risk Assessments. / Mitigation- Funds disbursements are based on detailed monthly delivery plans showing activities to be funded. This is enabling FCDO to monitor progress and funds usage. Field trips to monitor activities on ground are done quarterly.
Reputational- cautious	Description- Programme activities could potentially involve practices that fail to comply with national and/or international labour or safety & health standards, e.g. child and forced labour during constructions. / Update- there is no evidence of the risk materialising during the year. / Mitigation- Continuous monitoring of project implementation, sensitising community on the prohibition of child labour and employing knowledgeable SHE officers at sites.

In the coming year, the programme will continue to monitor these identified risks and any new ones which may emerge. Increased monitoring will also be emphasised down the delivery chain including at sub-contractors’ level.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

F.1 Programme Overview
The total value of the business case is £19,550,000 funding the delivery of four different components. This review focused on the Community water & renewable energy infrastructure & Early Warning Systems (EWS) component being implemented directly by UNDP working closely with government departments to ensure ownership and sustainability. The contribution agreement between UNDP and FCDO has a total value of £13,600,000.

F.1.1 Financial Management
Programme funds are transferred to UNDP. FCDO receives monthly forecasts and quarterly financial reports for review and approval. A review of these reports show that UNDP has been spending well within the set limits and timeframes, adhering to the proposed forecasts. In the year, £5,000,000 was disbursed to UNDP as set out in the contribution agreement. The expenditure rate by December 2024 was at 96%. All payment documents were reviewed by FCDO ensuring completeness and adherence to FCDO financial management policies. UNDP shared its last audited statement as of February 2023. The main components covered by the audit are on governance, development activities and operations. The overall audit rating is satisfactory highlighting that controls were generally established and functioning but needed some improvement. UNDP is audited every two years, with the next audit due in May 2025.

F1.2 Asset monitoring and control
UNDP purchased some assets for use at the inception of CAWEP. These include laptops, computers, office furniture and two vehicles to facilitate field monitoring. An updated asset register of these items is shared with FCDO every quarter. No asset losses were reported.

F1.3 Governance and Accountability
The programme steering committee is the apex body for CAWEP. It is co-chaired by FCDO and the Ministry of Environment, Climate and Wildlife. It meets every quarter to deliberate on strategic and policy issues affecting the programme. In the year under review, three steering committee meetings were held. These have been very useful platforms to lobby for high level policy decisions. A good example is when the committee successfully lobbied the Ministry of Finance to exempt CAWEP projects from paying Environmental Impact Assessment (EIA) processing fees.

F1.4 Programme Branding
UNDP is fully aware of the FCDO branding requirements. Programme areas visited during the Annual Review showed well labelled signage with UK International Development branding at completed sites such as Mlibizi and Hakwata. Branding is yet to be erected at sites with on-going works. FCDO will follow up with UNDP to ensure appropriate branding is put up after the works have been completed.

G: MONITORING, EVIDENCE AND LEARNING

G.1 Monitoring and Evaluation
Progress towards delivering outputs and outcomes was continuously monitored by programme delivery teams throughout the year. FCDO had scheduled quarterly project site visits in Binga, Chipinge, Chivi and Insiza districts, assessing infrastructure development works, meeting key stakeholders and communities. These helped to provide technical and strategic recommendations, ensuring the programme remains on track to achieve outcomes. Some monitoring visits were strategically done jointly with the steering committee, comprising of different government departments and UNDP. This helped to achieve objective assessment of progress and drawing from different expertise to make appropriate recommendations.

An OMS was also conducted in the year, through an independent consultant. This was aimed at assessing progress towards achieving intended outcomes and testing the programme approach to building climate adaptation and resilience and providing recommendations on what needs to be improved or adjusted in the remaining period of the programme. Overall, this evaluation judges CAWEP to be progressing well and has relevant interventions needed to help build resilience. All four districts with major works recorded an improvement in the resilience capacity score with Insiza recording the highest (76% improvement), followed by Binga (50%), Chivi (44%) and Chipinge (8%). The OMS made recommendations that programme teams are working on. These include (i) accelerating delivery of the business component by ensuring improved market access, market linkages and training on marketing in order to strengthen utilisation of infrastructure and sustainability and (ii) improving financial sustainability by creating cost-sharing mechanisms, revenue generation activities, and partnerships with public and private sector stakeholders

This review is also based on project site visits, OMS report, UNDP quarterly report and stakeholder meetings.

G.2 Evidence
As per programme design, CAWEP is generating a lot of policy and programme evidence on approaches to climate adaptation and resilience building. Some of the evidence has already been used to influence policy development and government decision. For example, the government has adopted the ‘smart green village’ model and wants it scaled up. This follows the successful pilot implemented through CAWEP in Hakwata, Chipinge district. In the year ahead, programme implementing teams will be focusing on consolidating all the evidence into learning or referral products for upscaling and policy implementation.

G.3 Learning
Learning has been a key part of the programme in the past year. In an effort to improve and avoid failures on a range of interventions, project implementing teams and beneficiaries invested time to learn from previous projects. For example, in the year, UNDP, stakeholders and beneficiaries had look and learn visits to viable irrigation schemes in Shurugwi district to learn about high value crop production for export under the Technoserve Takura initiative.

Date of last narrative financial report	31 December 2024	Date of last audited annual statement	February 2023