Evaluation Report for Programme Name: Final Evaluation of the Compete Caribbean Partnership Facility.

Response to Evaluation of FCDO support to improve resilience in the Caribbean
Background / This is a management response to the independent Final Evaluation of the Compete Caribbean Partnership Facility (CCPF). / The purpose of the evaluation is to assess the Facility's importance and topology in relation to other interventions in the Caribbean region and document lessons learned for future iterations. The evaluation assesses the achievements of the programme and presents findings and recommendations that could be used to help shape future support in this area, related to the assessment of sustainability at project level. / The programme / The Compete Caribbean Partnership Facility (CCPF) is a multi-donor facility with a budget of US$34.3 million (part funded by the UK’s FCDO), established with the aim of supporting private firms to increase their productivity and their contribution to economic growth in 13 Caribbean states. CCPF supported projects in the region are intended to: / Improve productivity and innovation in firms to enhance competitiveness in the Caribbean at the firm level, through the support of clusters and value chains, promoting technology adoption, and strengthening ecosystems of entrepreneurship and innovation within the private sector. / Enhance the Business and Innovation Climate and strengthen the legal institutional and regulatory framework for business including the drafting and implementation of policies and regulations to strengthen the institutional framework. / Methodology / This evaluation follows a non-experimental approach given that there are not appropriate control groups to measure impact. As such, our methodology is largely based on a theory-based evaluation approach, drawing evidence from a mix of quantitative and qualitative methods. The approach has been guided by the existing Theory of Change (ToC) of the programme. It includes desk research, 20 interviews at programme level, surveys with beneficiaries and regional experts, and 9 in-depth case studies. The case studies were developed via a combination of desk research – including project documentation and monitoring data - and 50 interviews with a wide set of stakeholders. The case studies have also been analysed using Contribution Analysis Approach. The fieldwork was conducted between January and March 2024. / Overarching questions/framework / The evaluation questions focused on the relevance, coherence, effectiveness, efficiency, impact and the likelihood of sustainability of the programme achievements. / Relevance: How appropriate and aligned is CCPF and the different aspects of its mission, including deliver Innovative and practical solutions to beneficiaries that stimulate Economic Growth, increase Productivity and foster Innovation and Competitiveness. / Coherence - Determine how well the Programme is connected with the region's private sector development (PSD) needs, the technical help required by enterprises, government PSD priorities, and donors'/partners' regional strategy. / Effectiveness: Determine the extent to which the CCPF has performed against its Results Framework, and the factors that have influenced this; and what is the evidence of effects (both intended and unintended) at all levels of intervention that the projects have sought to impact on. / Efficiency: What has been the relationship between the resources mobilized for the implementation of the CCPF compared to the results; and if the most efficient processes have been adopted in terms of organizational set-up, distribution of roles and responsibilities. / Impact: The extent to which the Programme is likely to generate longer-term impact under existing conditions. Whether the existing conditions (funding resources, human resources, governance, institutional arrangements) allow the impacts to be achieved. / Likelihood of sustainability: Has the Programme put in place the right conditions to allow for results to be further developed/ scaled up / multiplied / and financially / institutionally / politically sustained; and if the benefits of CCPF’s work are likely to continue. / Findings / Relevance and coherence / CCPF design and implementation is highly relevant to the challenges of the region / CCPF effectively considers the needs and priorities of beneficiaries’ countries, and specific groups and donors its design and implementation / CCPF has unique value proposition in the region, and complements rather than overlaps other initiatives in the region / CCPF has been successful in aligning its objectives with the needs and goals of its beneficiary countries. / Effectiveness / Overall, effectiveness of the programme (in terms of achieved outputs and outcomes) is positive. CPPF has made good progress towards outputs, and more varied progress towards outcomes and impacts. The latter is part due to the maturity of the portfolio. / Even so it is too early to tell how effective the programme will perform overall. The evaluation does identify concrete examples of contributions of the programme towards impacts. / The programme set ambitious targets in terms of jobs created for women and supporting women-owned business. Those targets have been largely met. / The case studies reveal that most of projects achieved their intended outputs (and in some case additional ones). The picture is more varied when examining the achievement of immediate outcomes, which is expected given the maturity of the portfolio. / Efficiency / The program has a good governance set up to provide strategic oversight, and operational support and risk management. / The CCPF team management the procurement of consulting firms and individuals is line with the best practice as set up by the IDB. / Likelihood of sustainability / Sustainability is embedded in project design, to some extent. / The programme has been successful at mobilizing resources which could in turn support future sustainability. / To further support sustainability of results, CCPF puts a considerable amount of effort into documenting and disseminating knowledge, including both the knowledge emerging from implementing projects, as well as from the relevant knowledge products emerging project activities. / There is however an unclear picture in terms of the sustainability when looking more closely at stakeholder perceptions and project-level evidence. / .

## Recommendations
The following action plan sets out each recommendation in the report and FCDOs response.
General Recommendation	Description	Specific recommendation	Responsible Management Unit	Commitment/Action	Target Completion Date
Recommendations for supporting sustainability	Embedding sustainability as selection criteria of projects. Sustainability is included as a criterion in project selection, but it’s not always carried out through the entire project assessment and selection process. This may help to maximise the probability of selecting projects with higher likelihood of sustainability and / or identifying mitigation strategies within the project design when/ if a risk of low sustainability is identified.	Suggest always / including it explicitly as an assessment criterion, and that this is discussed and assessed as part of the project selection process (including in the different evaluation panels).	Facility Coordinating Unit (FCU)	FCDO agrees with this recommendation. FCDO will ask that the Compete Caribbean Plus (CC+) Investment Panel (IP) include considerations of sustainability in their independent assessment of Pillar I private project proposals to the FCU, prior to the submission of potential projects to the review process. 1 / FCDO will follow up with the FCU on plans to enhance the sustainability of CC+. / CC+ is aligned and will contribute to results under the ONE Caribbean Framework (GN-3201-2)2, CC+ is expected to contribute to ONE Caribbean’s Sustainable Development with Private Sector Engagement, specifically to the results of improved enabling environment to facilitate private sector productivity and enhanced disaster and climate resilience.	February 2024
	Evidence collected via case studies show that some projects could use additional support to fully achieve its objectives and sustain / benefits over time. It is understandable that projects must come to an end but stopping the technical and financial support when not all outcomes have been materialised may mean that in some cases the initial ‘investment’ may not be fully capitalised. This could be / minimised by providing follow on support.	Considering funding projects that have already finished to improve their delivery of outcomes and further support sustainability.	FCU	FCDO to confirm there is no explicit prohibition on projects completed under previous phases of Compete Caribbean, applying for support under the new phase of Compete Caribbean. / FCDO to also engage with the FCU on any initiatives planned to identify and reach out to projects completed under the first two phases, which may benefit from further support.	April 2024
Recommendations for future evaluations	Allowing more time for the first phases of the evaluation. This would also allow for the development / update of the Theory of Change, and validation with relevant stakeholders; as well as discussions around key metrics that could be used to judge the success of the programme. / We also suggest providing a period of 3 months to iterate the draft report to arrive to a final version does feel appropriate.	Allow a longer duration of the study (e.g. 8 months rather than the original 6 months) but most importantly to allow more time for the scoping stage (e.g. 2-3 months rather than 1 month) such that key concepts, approach and data access can be discussed with care. / More time for the field work (e.g. 3 months rather than 1-1.5 months) to allow for a more iterative approach in the data collection, looking for opportunities to identify gaps in the information and present emerging findings before submitting the draft report.	Team developing Terms of Reference	FCDO to discuss this with the FCU and donors to agree that any future evaluations should be for an 8-month period.	April 2027
	Each project in the CCPF portfolio is quite distinct, with in terms of its structure and characteristics, as well as the context in which it is implemented. While each of them could be evaluated independently, conducting evaluations of each individual projects is costly and will create additional, and unnecessary, administrative burden (drafting ToRs, selecting consultants, overseeing the project etc.) / This has been tried in the past and stopped for the reasons stated above.	Conducting evaluations of specific projects, selectively. / taking into two dimensions: degree of the investment (i.e. size of the budget/ total / approved amount) and the degree of novelty of the project (which means that there is significant risk or uncertainty around project outcomes),	FCU	FCDO to discuss this with the FCU and donors regarding any future evaluations.
	All individuals / firms supported / by the technical assistance, including all individual cluster members and all individuals / firms trained and upskilled, executive agencies / counterparts should create databases for / their individual projects. That would allow running large scale survey of (end) beneficiaries (for Pillar 1) and further validating some of the results collected in the Results Matrix.	Create a consolidated / database on all the individuals and firms that participate in the activities provided by the programme and their contact details.	FCU	FCDO to discuss this with the FCU and donors regarding any future evaluations.	April 2024
	Currently the data collection process is more manual, with information being inputted into a word document. A more cost-effective method would be to use an excel file or creating a macro that extracts data in a more automated way.	Consider systematising the process of collating data and indicators to populate the Results / Matrix.	FCU	FCDO to discuss this with the FCU and donors regarding any future evaluations.	April 2024