        Business Case
  Summary Sheet:
Country Plan Summary: / Mission Statement: A modern partnership with a likeminded, peaceful and democratic nation which showcases UK leadership on delivering sustainable growth and climate resilience through the building blocks of public services that empower women and girls and better governance and accountability which reduces corruption. / How: We will draw on the full range of UK resources including: our soft power (both as a Commonwealth partner and championing our values as a modern, inclusive nation to convene across the international community); diplomatic engagement; defence support; HMG expertise and advocacy; flexible and reactive local and centrally managed programmes, and our membership and influence within UN and other multilateral organisations and financial institutions. To drive sustainable change, our focus will be on identifying catalytic opportunities for reform. It will also focus on working with government and civil society to build capacity and ensure programming is aligned to national strategies. We will work in partnership with others, including emerging and influential Malawian civil society leaders to enable them to own and lead their development locally. We will be nimble, and we will be prepared to take calculated risks. / The UK will focus upon 5 goals: / Accelerate sustainable and inclusive investment and growth: building a productive Malawian economy that works for everyone, by tackling unsustainable debt, expanding high value exports to widen Malawi’s narrow export base, and improving the business enabling environment which encourages UK investment. / Support Malawi to remain a peaceful, democratic and like-minded partner with more accountable, transparent and robust institutions that can tackle corruption and provide the essential building blocks for sustainable growth. / Support high-quality public services to build Malawi’s human capital as a foundation for growth: Improvement of government service delivery at national and district level, which delivers better health and education outcomes, prioritises women and girls, and harnesses Malawi’s demographic transition. / Build climate resilience and deliver rapid and agile humanitarian shock responses: reducing the impacts of climate, health, and economic shocks on the most vulnerable and accelerating Malawi’s transition to a more climate-resilient, low carbon, and environmentally sustainable economy well on the path to net zero by 2050. / Strategy, operations and consular services facilitate a functioning High Commission and enhance the safety and security of UK citizens in Malawi. Maintaining an agile, effective and resilient platform to deliver the FCDO’s enduring responsibilities, deliver value for money and excellence for the British people and strengthen UK soft power.

Country: Malawi Sector: Education / Title: Maziko a Maphunziro (Foundations of Learning)
Programme summary: / This programme aims to improve the quality of foundational education in Malawi as part of a joint approach with the Government of Malawi and other key development partners. The programme also includes a specific focus on climate resilience and girls’ education. / The UK will invest £39m over 5 years (2025 – 2030) to: / Support the Government’s commitment to improving foundational learning by delivering a maths curriculum reform and providing complementary technical assistance. / Make the education system more resilient to climate change by expanding school feeding in food insecure communities and leveraging climate finance for education. / Enable disadvantaged secondary school girls to complete their education through targeted scholarships and mentorships.
What is the rationale for UK Aid spending? / In Malawi, 87% of children are unable to read or do simple maths by the age of 10, threatening Malawi’s future development. As a key member of a coalition of development partners, the UK is helping Malawi to tackle this learning crisis, in line with the Ministerial priority to accelerate sustainable growth across Africa. / Current UK funding has catalysed a major transformation in the way mathematics is taught in Malawian primary schools. Beginning in August 2024, 3m children in primary school were taught under a new curriculum informed by global best practices and UK pedagogy experts. In addition, the pilot phase (2023-4) was evaluated in a randomized trial and showed that 1 year under the new maths curriculum was equivalent to at least 1.5 years under the prior one. / This business case proposes to scale and institutionalise this maths reform with the target to raise the percentage of children able to do basic mathematics by 20 percentage points, more than doubling the existing number, and benefiting 7.5 million Malawian children over five years. / Our programming also demonstrates the critical leadership that the UK provides in international development. Through diplomatic and technical skills, UK experts have led and coordinated development partners to adopt a single theory of change for foundational learning and created synergies to multiply the impact of UK funding. For example, the UK has worked closely with the US as they have implemented literacy programs, the World Bank as they target new classrooms and teachers to the early grades, and the Global Partnership for Education, as they fund preschool access expansion. Together, these coordinated efforts are expected to amplify the benefits of the new UK maths curriculum and put into practice the Foreign Secretary’s priority of strengthening UK leadership on international development. / The proposed programme will also address climate change in Malawi, specifically its impact on Malawi’s education system, aligned with UK priorities. Climate-induced shocks (cyclones, droughts, etc.) prevent the poorest children in Malawi from attending school as they damage school infrastructure and increase poverty and food insecurity, also directly threatening the impact of investments in quality education. In the program, school feeding and dedicated scholarships for about 1,500 of the most disadvantaged girls will mitigate this. Small but strategic UK ODA will also help Malawi to access other large international climate financing for education.
Programme Value: £39m		Country/ Region or Sector: Malawi
Department/Post confirmation of review processes		Fiona Ritchie, Head of Mission
Contact name		Arianna Zanolini, Sr Education Adviser
Threshold for final approval of Business Case: Director General
Approval of Concept Note:	19/11/2024	Minister for International Development
Approval of Business Case:	03/12/2024	DG for Africa, the Americas, and Overseas Territories
Programme Code: 400473	AMP Start: 01/2025	AMP End Date: 06/2030
Overall risk rating:	Moderate

Context of Malawi
Malawi is a rural and extremely poor country, with 80% of the population engaged in subsistence agriculture and where the average child grows up in extreme poverty. The average Malawian is at the bottom 10 percentile of income of the average person living in a Lower Income Country (LIC) and Malawi’s GDP per capita (US$634) is one of the lowest in the world. Almost the entire country is at high risk of food insecurity (Figure 1), and the heavy dependency on agriculture makes it particularly vulnerable to climate shocks, such as Cyclone Freddy last year, that are becoming increasingly frequent. The poverty is reflected in the very low absolute value of public spending. Prospects for transformational economic growth in the short term are low, but the population continues to grow at 2.5% per year and is projected to increase to 24m people by 2030, from the current 20m.

Figure 1: Chronic Food Insecurity in Malawi districts: dark purple is severe and light purple is moderate

Context in the education sector
The Malawi Government has demonstrated good commitment to education over recent years, evidenced by consistently prioritising education it in its domestic spending, reserving at least 20% of its public expenditures and 5% of its GDP. However, due to its absolute poverty and the large youth population this only equates to $30 per pupil per year for primary school (vs approximately $200 in neighbouring Zambia and $8,200 in England). The school-age population at primary level is expected to rise from 5.3 million in 2023 to 7 million by 2030 putting additional pressure on the education sector.
[note] Malawi Ministry of Education, Education Statistics Report 2023. This is 2% of the yearly salary of a newly qualified teacher.
[note] https://www.unicef.org/esa/media/12566/file/UNICEF-Zambia-Budget-Brief-Education-2023.pdf
[note] Annual report on education spending in England: 2023 | Institute for Fiscal Studies

Access to education is remarkable for primary school, but very low for secondary. Following universal primary education in 1994, 89% of primary age children are enrolled at primary level, slightly more girls than boys. Due to low quality, however, the system is highly inefficient. 37% of children repeat their first year of primary school due to lack of learning, and a vicious circle of low learning and continuous repetitions lead to high level of dropouts so that only 46% of girls and 43% of boys ever complete primary school (Figure 2). This statistic places Malawi at the bottom 10% of primary school completion rates for Sub-Saharan Africa. The low primary completion rates and severe lack of spaces in secondary schools, along with school fees, leads to a secondary school access at 23%, one of the lowest in the region (Figure 3).
[note] Malawi Ministry of Education, Education Sector Performance Report 2023.

Rural, disadvantaged girls face the highest barriers with less than 15% ever entering secondary school. Yet, for them, secondary school is the only real ticket out of poverty. Those who drop out - mostly because they can’t pay school fees - have few alternative pathways to avoid early marriage and pregnancy. 31% of rural girls are pregnant by the time they are 19 years old. Those who remain in school are at high risk of sexual abuse and violence due to their extreme poverty and the need to find money for transport and living costs. The UK is currently addressing the specific needs of disadvantaged secondary school girls through scholarships and wider support enabling 450 girls a year to remain in education up to 2026. There are several other partners already supporting the Ministry with scholarships for secondary school, but a large gap remains. Last year there were 485,650 students in secondary school; 68,422 applied for a scholarship because they were unable to pay, but only 24,605 received it.
[note] Malawi Education Statistics Report 2024, Malawi Ministry of Education, available at https://www.education.gov.mw

Figure 2: Primary Completion Rates for males and females against the National Education Sector Plan (NESIP) Target, Source: Education Sector Statistics Report 2024, Ministry of Education, Malawi.
Figure 3: Enrolment Cascade for Malawi. Out of 100 children who start primary school, only 45 complete it, only 23 enrol in any form of secondary, and only 5 complete it. Source: authors’ calculations using Education Sector Statistics Report.

Need for better foundational learning
The quality of schools remains very low and inequitable, especially in the early years of primary when the foundations of learning are built. Children are going to school but not learning, a problem not only of Malawi but in the entire Sub-Saharan Africa. Learning Poverty – the share of 10-year-olds who are unable to comprehend a simple passage – is estimated at 87 percent. The Malawi MICS (2021) reports that only 18.9 per cent of children in Malawi aged 7–14 years have foundational literacy skills, and only 12.6 per cent have foundational numeracy skills. If children don’t know how to read or do basic mathematics, they will not be able to meaningfully proceed in school. This reduces their opportunities and ultimately impacts Malawi’s future economic growth potential.
A leading reason for this lack of learning is poor quality of teaching and lack of high-quality materials to support learning. This leads to a “chalk and talk” style of teaching, with lots of chanting and little focus on conceptual understanding. Absenteeism- both of children and of teachers- is another issue, especially for the most disadvantaged children and most remote communities. In a recent representative survey only 65% of teachers were in the classroom teaching during scheduled time, a problem caused by poor teacher management practices, remoteness of the schools with lack of teachers houses, and low teacher salaries that have been flat against an inflation at 35%. Similarly, on any given day only 65% of lower primary education enrolled children go to school, with hunger reported to be the main reason for missing it. Very low preschool access, malnutrition and under-stimulation during early childhood are exacerbating the problem because children enter school already disadvantaged.
[note] Asim, S; Casley Gera, R. 2024. What Matters for Learning in Malawi? Evidence from the Malawi Longitudinal School Survey. International Development in Focus. Washington, DC: World Bank. http://hdl.handle.net/10986/40948
Poor learning environments with severe overcrowding is a very visible issue: the average class in early primary is over 100 children with one teacher, children sitting on the floor and very little space to move. To get all children to learn in a class of fewer than 90 children, Malawi would need to build 35,000 new classrooms at the cost of at least $210m.
[note] Malawi Education Reform Programme calculations, using unit cost of $20,000 per block of two classrooms
Climate change is exacerbating hunger and lack of infrastructure, further lowering learning levels and affecting girls
Hunger and extreme poverty are already the main reason for pupil absenteeism from school. Hunger has increased in the past years due to two years of devastating cyclones in 2022 and 2023 followed by one year of drought in 2024, and it is destined to continue increasing if structural economic changes do not happen. Maize production could drop by 25% worldwide due to climate change. This will lead to more poverty, more absenteeism and less education for the very poorest, in turn creating a vicious circle by reducing resilience of the next generation.
[note] NASA study: “Climate impacts on global agriculture emerge earlier in new generation of climate and crop models”, Nature Food 2, 2021.
Girls and boys are affected in different ways: girls are held back by home chores, then pushed out for marriage and pregnancies; boys are pulled out of primary school to do manual day jobs. Extreme poverty and hunger are particularly impacting girls’ ability to continue studying after primary school as parents in poverty think of secondary school for girls as a luxury that they can’t afford. Disadvantaged, rural girls selected for secondary school are either not starting or dropping out; a missed opportunity for them to break the intergenerational cycle of poverty.
The higher frequency of extreme weather events will also continue damaging the already inadequate infrastructure and disrupt schooling. The estimate is that cyclone Freddy in 2023 damaged more than 600 schools, affected directly 700,000 children through multiple weeks of school closures and inability to get to the schools. A World Bank review of education and climate change points out that countries that had to close schools due to climate disruptions lost on average, 28 full days of school in two school years.
[note] Sabarwal A, Marin S, Spivack M, Ambasz D. “Choosing Our Future: Education for Climate Action”, The World Bank Group

Climate change-exacerbated hunger and weather events are also impacting indirectly by reducing the return of investment in quality education. On the positive side, schools can be used to support community resilience through instilling improved agricultural practices or local adaptations, using the school as the focal point for community engagement. The Ministry of Education is exploring introducing climate change in the curriculum, but action-based interventions are more likely to be impactful.

How this need is currently being addressed
Despite these challenges, the combination of a committed Ministry and well-coordinated partners’ efforts around foundational learning are holding the promise that the statistics of learning poverty could decrease drastically in the next five years. Several evidence-based, large-scale programmes focused on foundational learning are being rolled out in a coordinated way in all primary schools. The UK-supported National Maths Curriculum Reform and US-supported National Reading Programme are curriculum reforms targeting all Standard 1 and 2 learners in Malawi to improve the teaching and learning of foundational literacy and numeracy and ensuring children have the materials they need. Complementary to the curriculum reforms are the system reforms through the Malawi Education Reform Program (MERP), funded by the World Bank and Global Partnership for Education (GPE), providing support for teacher management so that there are more teachers in the foundational learning years, and mentoring for girls in early primary, as well as constructing 10,000 early primary classrooms. The new GPE Programme for Results, also implemented by World Bank, will continue with the systems strengthening with a focus on school readiness and improving teaching, and provide a backbone for a shift around delivering results in Foundational Learning for the sector. The Governance to Enabling Services Delivery (GESD) programme, funded by World Bank with strategic technical assistance from the UK, tackles the governance issues around teacher management, financial flows and advisory services through performance-based financing at the district level.
[note] Previously called “National Numeracy Programme”, the name changed when it was formally approved as the new curricuulum

Over the last five years the UK has forged a long-term partnership with Government of Malawi built on UK expertise and leadership in global education. Our flagship programming supporting the government’s National Mathematics Curriculum Reform has allowed almost 3 million children to learn with a high-quality, revised numeracy curriculum in the first two years of primary school, workbooks based on the “structured pedagogy” best-buy, trained teachers, and a clear focus on problem-solving and critical thinking. The Ministry has embraced it and integrated into the new curriculum, with teachers showing high-level of acceptance and implementation of the reform.

The reform has already started making a difference: a rigorous evaluation has shown that it is improving foundational numeracy with 1 year under the new maths curriculum equivalent to at least 1.5 years under the prior one, making it one of the few international examples of a successful numeracy programme at scale and attracting external co-funding. The work is not finished and requires a patient approach, with its sustainability and full institutionalisation depending on how well the programming coordinates with Ministry and other partners to bring about system-reforms around how teachers are trained, supported, and managed.
[note] The evaluation of the National Numeracy Programme was done during the 2023/2024 school year, when the programme was in approximately 1,200 schools, by a team of independent professors from University of Oregon and the University of Malawi. The evaluation design was approved by EQUALS and is available at the American Economic Association Randomised Control Registry. Preliminary results were presented at the What Works Hub for Global Education conference in 2024, and the full report will be published in DevTracker (following EQUALS QA) and we expect to have the link available before publishing this business case. An academic paper is expected to be published in the 2025 calendar year.

Evidence from our evaluation has also shown how the reform does not work for the most disadvantaged children. Despite the better quality of teaching, children in the bottom third did not improve their understanding of basic mathematics, often scoring a “0” in the number of simple additions that they could do in one minute. The most disadvantaged children are also the most vulnerable to external economic shocks, including climate-change related ones and live in the regions with the highest climate vulnerability, and often not attending school. Absenteeism and hunger are likely to play a large role and needs to be addressed in this context of worsening outcomes. At the moment, development partners are already providing school feeding in some schools, especially WFP through EU funding, promoting the “Home Grown School Feeding” model, an innovative local model where schools receive a grant and buy diverse foods from the local cooperatives for feeding children. The model currently covers about 20% of all primary schools, but not necessarily the most food insecure where the direct provision of food would be required.
[note] Important to put this in context: children can be in the top two terciles of assets ownership in rural, public schools in Malawi and still meet the definition of extreme poverty.
What’s the evidence? Impact evaluation of the UK-supported Mathematics Reform
A randomised control trial, done when the reform had scaled up to 1,200 schools in the country, has been presented and the full report will be ready in December 2024. The results are showing that after the first 9 months of teaching through the new reform:
- children in the reform schools learnt on average the equivalent of an additional half a year of school (1.5 years additional equivalent for Standard 1), with evidence of stronger conceptual understanding, particularly in higher standards
- teachers teaching in the reform are teaching better and implementing the reform with fidelity
These results put this programme among the most successful at-scale, cost-effective (£5 per child) programmes done in numeracy in LMICS. However, the impact was concentrated among the least disadvantaged two thirds of the distribution, with almost no impact among the very poorest. This is likely due to a number of factors, with frequent student absenteeism driven by poverty and hunger being a large reason.

How we propose to address this need
As discussed in the appraisal case and below, we propose to focus on four areas of support through this new programme:
1. Completing the maths curriculum reform and complementary foundational learning support, £27m.
2. Making the education system more resilient to climate change, £8m.
3. Targeting support for disadvantaged secondary school girls, £2.5m.
4. Learning and evaluating what works in practice, £1.5m

1. We propose to invest £27m in completing the maths curriculum reform across all schools in Malawi while working at the system-level partnering with the Ministry and others to make the impact larger than the sum of its parts. The UK is now known as a reliable and respectful partner for foundational learning. We propose to leverage this momentum to complete the reform over the next 5 years by:
1. Completing the scale up through to the 4th year of primary school (standard 4) and provide ongoing coaching and training to ensure the reform sticks given high teacher turnover.
2. Ensuring student teachers learn the new maths curriculum in the teacher training colleges, to make the reform sustainable and minimising need for recurrent trainings.
3. Providing continued support to the workbooks underpinning this reform and build the evidence for a transition to more sustainable textbooks.
4. Ensure children are not left behind by developing learning material to allow disabled children to engage with the new curriculum and inspiring girls to be problem solvers.
5. Providing technical assistance to ensure the wider foundational learning reforms complement each other and deliver measurable results.

Beyond direct programming, the UK is also in a good position to catalyse greater results in foundational learning including through the use of a programme funded adviser to support coordination and prioritisation discussions with government and development partners. The World Bank $86m GPE funding will use a Pay by Results modality and UK could support the achievement of these results through technical assistance to the unit delivering them, connecting the dots between programming and policy and locking-in coordination through the Foundational Learning Steering Committee. For example, agreeing on how we make sector accountable to improving learning outcomes can enable a clear focus on learning rather than intermediate processes.

2. We propose to complement the mathematics reform with £8m to make the education system more resilient to climate change and reach the most disadvantaged, especially by co-funding school feeding to address absenteeism and hunger. This will include efforts to improve and lower the cost of the current school feeding model for Malawi. This would cover the involvement of community, localisation of ingredients, focus on behaviour change as well as a move away from burning charcoal for preparing the food. Addressing hunger in school children will help protect the larger investments we are making with approximately 60% of schools currently not covered by a school feeding programme.

We will also use our development diplomacy and some strategic funding to partner with other organisations, institutions, and private sector to mobilise more funding to protect education from climate change, including for example through retrofitting to make schools less hot and less vulnerable to floods. A small amount of funding will be dedicated to innovation in environmental education. This will, incentivise schools to learn and take action on local climate adaptation issues relevant in their communities, likely through support to a small innovation challenge fund.

3. We propose £2.5m in targeted support for disadvantaged girls. Specific support is needed for adolescent girls selected into secondary school that would otherwise be at risk of dropping-out. We propose to support them with scholarships and mentorships as one of the most effective ways of giving girls a pathway out of poverty. This is a relatively self-contained activity that will directly reach a small number of girls. Keeping girls in secondary is universally recognised as a good investment for diverse outcomes, and removing financial barriers so that girls can access education is a reliably cost-effective investment. We will appraise this component separately against other ways to support rural disadvantaged girls and remain flexible to pivot this support to other mechanisms in the future if a strong case emerges.

4. Finally, we propose £1.5m for activities related to learning and evaluation. Being able to conduct implementation science and impact evaluation should enhance the efficiency of all other outputs by knowing how to implement activities in a way that saves money and increases uptake and/or efficiency. The marginal cost of this component is minimal compared to the difference between a badly implemented and a well implemented intervention.

Our ambition on outcomes and impact
We believe this investment can dramatically reduce the percentage of grade 2/3 children without mathematics foundations by age 10, from 87% to 67%, close the gender gap in primary mathematics results and reduce repetition rates in the first four years of primary school. At the outcomes level we expect a decrease in absenteeism in the schools supported by school feeding and a reduction in the percentage of children who score “0” in the learning assessments. We expect girls supported with secondary scholarships to have a drop-out rate of 30% or less, compared to national average of 80%.

Fit with FCDO’s strategic objectives
The proposed programme delivers the Foreign Secretary’s priority of strengthening UK leadership on international development through a modern partnership that listens to the Government of Malawi’s priorities and delivers at scale as part of a joined-up approach. Education is a key part of building Malawi’s “Human Capital”, recognised by the government as one of the seven enablers in Malawi’s 2063 Vision to achieve a “youth-centric inclusively wealthy” and “self-reliant nation”.

Reforming the repetitive teaching style that has failed to provide the skills needed for a modern labour market will ultimately help deliver better economic growth for Malawi over the long-term enabling an eventual exit from poverty. This supports the Foreign Secretary’s priority on accelerating sustainable growth in Africa.

The shift to tackling the impacts of climate change on the most disadvantaged students also aligns well with the UK priority unlocking climate finance and getting it working in the least-developed countries. This funding will also help deliver UK commitments on gender equality throughout the programme but also recognises the particular challenges girls face at secondary school level in Malawi.

Inclusion, disability and Public Sector Equality Duty
This programme will reach every single child in Std1-Std4 in Malawi, hence reaching even the most remote schools where the most disadvantaged children are. The evaluation of the pilot maths curriculum reform showed greater impacts for girls than for boys showing that improving teaching will help address the gender gap that is evident by the end of primary education. By improving the quality of foundational education, we hope to increase the number of girls completing primary school and close completely the gender gap between boys and girls in mathematics.
The transition to secondary school is another bottleneck where many girls who pass primary do not secure a place. We propose to use scholarships and wider support to help the most disadvantaged girls access secondary school and progress further, acting as role models for younger students.

Throughout the programme we will seek to ensure that disabled children are not left behind and propose to develop learning materials that allow them to engage with the maths curriculum reform as well as targeting a proportion of the scholarship places towards children with disabilities and girls living in the refugee camps. We will take advice on this from local organisations working with people with disabilities and ensure that suppliers are working to improve equality of opportunity and eliminate discrimination across the programme.

Partnership Principles assessment
Our Partnership Principles assessment (2024) finds that, despite some progress on areas of public finance management and commitment to poverty reduction and respect for human rights, there remain shortcomings in GoM’s commitment to financial management and accountability, The assessment concludes that no UK aid will be provided in the form of budget support to the Government of Malawi. In line with this assessment, this programme will be delivered through private suppliers, UN agencies and NGOs with no funding being managed by the Government of Malawi using their fiduciary systems. Technical assistance procured by FCDO may be used to support shared objectives to improve educational outcomes. BHC Lilongwe updates its overall assessment of commitments to the partnership principles on an annual basis which helps inform wider decisions. No further assessment is proposed specifically for this programme.

Counter Terrorist Financing and anti-money laundering
Overall, this programme is assessed has having a very low risk of creating opportunities for financing of terrorism or money laundering. Implementing partners for this programme will be selected to ensure they have no institutional history of terrorism financing and with sound financial management systems as determined through due diligence assessments performed ahead of all funding agreements.

## Appraisal Case

The strategic case makes the case for prioritising foundational learning, including through climate adaptation, and targeting directly the most disadvantaged girls, but there are a range of options to tackle these issues. For foundational learning, for example, building climate-resilient classrooms, tackling the teachers’ distribution inequity, reducing absenteeism of children and teachers are all good ways to tackle the learning deficit, and all have a clear need and evidence of impact in Malawi.

We will appraise the options to deliver the strategic case in two parts: first we will appraise the options to deliver foundational learning; then we will appraise the options to deliver empowerment for marginalised girls. These are different because they have different outcomes, as well as different reach and funding. Foundational learning is prioritised because of its evidence and (hence) policy prioritisation in FCDO, but also because of its overarching impact reaching almost all children and delivering the foundations. In a setting where less than 50% of children complete primary school, foundational learning is the most equitable and effective intervention. Foundational learning also benefits girls more than boys, helping to prevent the gender gap in academic achievement and better equipping girls to be more resilient.

Appraisal for delivering Foundational Learning (including through climate adaptation)

Options not appraised:
- Do nothing. There is already significant investment in foundational learning, including from multilaterals that we fund. However, in absolute terms this is still very low, and the statistics on foundational learning are a clear call for action. Limited economic growth and severely limited government funds means over the medium term, the education sector will not get the allocations it needs to meet the additional investment needed to increase the quality. A committed Ministry and good working relationship with partners means that the investment can bring fruits. FCDO has been leaning into policy reforms beyond our programming. Closing education bilateral support would mean exiting one of the sectors where the UK is most influential, has more expertise both locally and globally compared to other partners, and decreasing the opportunity for the UK to build partnerships that enhance the efficiency and effectiveness of other investments, including the Global Partnership for Education which the UK supports multilaterally. The outcomes already achieved on improved mathematics learning are likely to be lost without the consolidation of this reform.
- Work on teacher management issues, including supporting the hiring of contract teachers from districts. Although teacher distribution is a critical problem in Malawi, with teachers highly concentrated in urban areas and up to a third of the teachers not showing up in the classrooms, the World Bank is better placed to address it through a combination of the Global Partnership for Education (GPE) programme, that has a large component on teachers distribution, and the World Bank Governance for Enabling Service Delivery governance programme, a pay by results programme at the districts level. We are using our technical experts and complementary support from the FCDO governance team to ensure that these programmes build on each other. Thanks to previous investment, the World Bank governance programme is now highly focused in ensuring that districts distribute teachers equitably and we will continue to work with the governance colleagues so that additional resources for education can be spent in enabling districts to improve their teacher management.
- Supporting technological scale-up. BEFIT (Building Education Foundations through Innovation and Technology) is a well-thought-out edtech intervention for foundational learning whereby children learn numeracy and literacy through adaptive games on a tablet. Its national scale up has become a priority for the Ministry of Education. We do not recommend investing at this point because a) the programme has just secured $30m from GPE and a private foundation to expand to a further 500 schools and it will need at least two years before it is ready to further expand; b) a rigorous impact evaluation and rigorous external costing of the model is needed to demonstrate the impact of this intervention at scale.

Methodology adopted to appraise impact and cost-effectiveness.

The options to deliver foundational learning are appraised against the cost needed to deliver a standardised improvement in students’ foundational learning, complemented by strategic and risks considerations. Following best practice, we appraise each individual option as self-standing rather than appraising a combination of options, so that the VfM of each option is clear even if the final programming might include a combination of the options.

In Economics of Education, it is a standard practice to compare impact of interventions by comparing their impact on learning assessments. To compare different interventions on different populations, a common albeit not flawless way is to normalise the distribution of the students’ foundational learning assessments (typically assessments of early grade reading, comprehension and numeracy) so that the distribution has a mean of 0 and a variance of 1. The impact of the intervention then is expressed in how much more children are learning with the intervention compared to the control on that distribution. An intervention with an impact of 0.5SD on that distribution, for example, means that children exposed the intervention score on average 0.5 standard deviations more than the control group on the normalised distribution of learning assessments. As a somehow arbitrary benchmark, we would expect a child in a high-performing learning system to gain 0.8 Standard Deviations of standardised learning per year. We use the highest quality available local evidence whenever available, and we use the Best Buys evidence whenever no local one is available. We do not attempt to make cost-benefit calculations – the cost effectiveness of each option is presented using the same calculation, so their relative value will be unaffected.
[note] See amongst many others: World Bank. 2018. World Development Report 2018: Learning to Realize Education’s Promise. Washington, DC: World Bank. Or Evans, Yuan: “How Big Are Effect Sizes in International Education Studies?”  Educational Evaluation and Policy Analysis, 44(3), 532-540.
[note] This is well explained in Angrist, Evans, Filmer, Glennerster, Rogers and Sabarwal “How to improve education outcomes more efficiently”, World Bank Policy Research Working Paper 9450, page 4: “In countries with different levels of inequality in learning, the same absolute increase in average learning on the same test would generate very different standard deviation improvements. When we compare studies using standard deviations as our metric, we impose the assumption that the difference in learning levels between the median and 66th-percentile student in a fourth-grade math class in Kenya is equivalent to the difference in learning levels between the median and 66th-percentile student in a twelfth-grade history class in Peru.” A better metric would be using the Learning Adjusted Years of Schooling, the paper argues. Converting SD into LAYS for Malawi, under our assumptions, would simply mean multiplying the SD by 0.18- this is because a child in Malawi learns on average at 0.18 the rate of a child in a high performing country. Since all of our options are for Malawi, multiplying by a common ratio wouldn’t change our results.

We make a rough assumption that, since Foundational Learning is defined for both numeracy and literacy, the impact of an intervention that only improves numeracy, with zero impact on literacy, will need to be halved to be compared with interventions that improve both domains. When we calculate the number of beneficiaries, we calculate the number of beneficiaries that are exposed for at least one year. Most of the evidence we have is for one year of intervention, and we do not know exactly how multiple years of exposure will change the overall impact in terms of standard deviations, so it is safest to compare the impact of one year of exposure. The effect of this is likely to prefer school building over the other interventions.

To calculate cost-effectiveness, we use an approach to cost effectiveness calculations which is to calculate the cost of delivering a unit of learning gains for a student, expressed in Standard Deviations. This approach has been used elsewhere. We also calculate cost effectiveness as the increase in SD and multiply it by the number of children, then dividing it by total cost, which is a more standard but less intuitive approach that does not rely on the assumption that buying 0.2SD of impact will cost double than buying a 0.1SD of impact. The results of the ranking in cost effectiveness do not change.
[note] See for example Kremer, Branner, Glennerster, 2013: “The Challenge of Education and Learning in the Developing World”, Science 340, 2013. Here is slightly different as they calculate SD learning gains per $100. E.g., if a program improves learning by 0.1 sd and costs $1/student, then its cost effectiveness is 0.1 * $1 * 100 = 10 sd per $10, but the mechanism and assumptions are the same.

Options to be appraised:

Option 1: Build low-cost, climate resilient classrooms

- What:
  - Build up to 3,000 climate-resilient classrooms in the most overcrowded schools using a low-cost model that includes climate resilient features as per latest evidence.
- Justification:
  - Malawi needs 35,000 classrooms to get all children learning in a classroom of fewer than 90 children (World Bank and Malawi Education Sector Analysis calculations)
  - Situation likely to get worse as population increases and climate change continues to impact schools, like during the cyclone in 2023 when it damaged more than 600 schools
  - Average pupil to classroom ratio in the lower grades (Std 1 and Std 2) is over 100: hard to learn in such large classrooms, especially for the most disadvantaged or children with special needs
  - Extreme heat and other elements likely to compromise learning- FCDO could scale-up low-cost innovations
  - There are more teachers than classrooms, so new classes could immediately be used.
- Evidence of impact on learning:
  - Global evidence on constructing classrooms shows limited impact on learning and providing such inputs is not considered a “Best Buy”. However, this evidence is based on reducing sizes in much smaller classrooms. Classes like the Malawian ones are extreme cases.
  - The World Bank conducted a study of their construction effort as part of a programme that ended in 2021. They found that construction made a large positive impact on foundational learning estimating an impact of 0.4 standard deviations (SD) improvement for districts which benefitted from construction.
    [note] Salman A; Gera, RC. 2024. Are Short-Term Gains in Learning Outcomes Possible? Evidence from the Malawi Education Sector Improvement Project. Policy Research Working Paper; 10845. © Washington, DC: World Bank. http://hdl.handle.net/10986/41884. The conversion in Standard Deviations for a normalised distribution of learning assessment was done by the author of the paper, in an email to FCDO, calculating that “the MLSS knowledge scores use a distribution with a standard deviation of about 100 points. So, the overall effect of 39 points on total scores from MESIP is roughly equivalent to about 0.4SD, a large effect”.
- Beneficiaries and cost
  - Impact of classrooms construction can last a long time. We use some assumptions to estimate the number of beneficiaries at a total of 3m children over the next ten years. With the total funding proposed (£35m) we would be able to build only 3,000 classrooms.
    [note] Classrooms last for ten years, building 3,000 classrooms can benefit 100 children per classroom constructed per year (all classroom constructed will be built in places where PCR is over 100). We can build 750 classrooms per year starting from 2026 at the total cost of £7m per year for four years.
  - Note the use of a 10-year time period – the other options use the five-year period of the programme. Once again, this is likely to prefer school building over the other interventions.
  - Using World Bank estimates, each classroom costs approximately £9,000 plus estimated 30% of supervision and other management costs, so £11,700. Rough division brings a cost per child of £12 (£35m/3m beneficiaries), delivering 0.4SD
  - Hence cost-effectiveness becomes: 0.4 SD * 3m children/ £35m= 0.034
- Risk
  - Maintenance. Historically, classrooms are constructed and then no maintenance means rapid deterioration and safeguarding risk for children who are learning inside. A fund for maintenance could mitigate this, but it would not be easy to set up given the duration of this business case.
  - Safeguarding: FCDO does not have the expertise to fully understand and manage the risks that the buildings are built incorrectly and cause risks for the children who are learning in it. We can mitigate this by subcontracting such expertise, creating a robust supervision and checks and balances system, or pooling funding with multilateral organisations such as World Bank.
  - Uncertainty. This would be a new sector for the BHC Lilongwe and this could mean delays as rules, stakeholders etc are fully understood. Infrastructure projects in other sectors have encountered significant hurdles in cost, timeliness and management.

Option 2: Completing mathematics reform with system-wide investments in foundational learning

- What:
  - Scale-up and maintain reform to all lower-primary grades (so far only scaled up for the first two years) and continue co-funding workbooks for all children while planning transition to textbooks.
  - Scale-up reform to pre-service training so all teachers are trained when they first learn how to teach mathematics.
  - Ongoing support for teachers: co-funding to ensure teachers are supported through coaching and good teachers are recognized, including exploring EdTech synergies with other programmes such as the USAID reading programme, Global Partnership for Education (GPE), and BEFIT
  - Improving the equity of this reform by inspiring girls to be problem solvers and ensuring children with disabilities are supporting through adaptations to learning material.
  - Support for system reforms for foundational learning including:
    - how schools, districts and national level are accountable and incentivised to improving learning outcomes
    - TA supporting delivery of GPE pay for performance results
    - assessments so we can measure foundational learning
- Justification:
  - Fundamental changes on how teachers teach are a necessary condition for children to learn. Current repetition and chanting style learning is not delivering learning for children.
  - The Ministry of Education is prioritising Foundational Learning and partners are well coordinated with the UK co-leading reforms. Complementary UK investments include two Centrally Managed Programmes, one focused on remediation (SCALE) and one on assessments (Data for Foundational Learning) and active roles in the management of the Global Partnership for Education grant for foundational learning. There is interest from private foundations to co-fund the programme given its evidence of impact. This leads to the potential for a transformation in how well children achieve foundational mathematics.
  - FCDO has invested >£20m on the reform through the previous programming (Strengthening Malawi Education Systems) and it is working (see evidence below). There is enough evidence that further investment will bring higher returns for longer by finishing, rooting and fully institutionalising the reform. For example:
    - The reform has been scaled up to Std1 and Std2. Material is ready for Std3 and Std4, it just needs to be rolled out through teacher training and procurement of workbooks. The old curriculum does not meet international standards, emphasises memorisation over understanding, and does not offer enough opportunity for practice.
    - Distributing workbooks for another five years will cement the new way of teaching and allow a transition to more sustainable textbooks once behaviour change has settled.
    - Teachers are changing how they teach, but turnover is high and new teachers are currently learning the old curriculum. Changing how student teachers learn to teach mathematics will help ensure the reform is sustained.
- Evidence of impact on learning:
  - The reform has been proven to work: a rigorous impact evaluation through a Randomised Control Trial is showing that the reform is already having an impact on learning outcomes. After only one year, children are learning on average the equivalent of an additional half a year of schooling in mathematics. In terms that are comparable with the other options, the reform delivered an improvement of 0.2SD on the (normalised distribution of) mathematics achievement. These results align or surpass the ones reviewed in a highly respected worldwide analysis of successful at-scale numeracy programmes in Lower Middle-Income Countries.
    [note] See note 12 for a reference. The full report will be published on DevTracker by the time this business case is pulished, we will include the link. An academic paper is expected to be published by the end of 2025.
  - The design of the reform follows the “Great Buy” of structured pedagogy, where teachers follow a semi-scripted, structured lesson guided by the children’s workbook and each page of the workbook is a lesson. Following the best practice in successful structured pedagogy reforms, the design includes complementary systems-strengthening reforms to enhance the focus and accountability around improving learning, for example by ensuring that learning is measured and progress tracked.
  - For the comparison below we assumed the impact is only on mathematics with no impact on literacy. We therefore halve the impact of the reform when appraising this against options that improve both mathematics and literacy. It has a 0.2SD impact on mathematics, but on average only 0.1SD on foundational learning because the impact on literacy is zero. This was also explained in the methodology.
- Beneficiaries and cost
  - The reform is already at scale and can start delivering from 2025 for all standards, from Std 1 to Std 4, benefitting 3.4m children in 2025, and an additional 1m per year (about 1m new children enrol in Std1 every year). Estimating the programme only impacts children in the period 2025-2029- a very conservative estimate because it assumes that the impact stops immediately- this will be 7.4m children.
  - We estimate that the minimum necessary to deliver the impact shown in the impact evaluation is £27m. More funding would increase the impact, but there is a case to sustain the core of the investment and then attract further financing to improve it even further. The evidence we have is for spending the equivalent of £27m.
  - Assuming £27m, contributing 7.5m children and delivering 0.1SD (0.2 in maths, 0.1 in foundational learning). This means the cost for delivering 0.1SD will cost approximately £4 per beneficiary.
  - Cost-effectiveness becomes: 0.1 SD * 7.4m children/ £27m= 0.028
- Risk
  - This is the continuation of previous investment, so not building from scratch. There is a lot of momentum already, built capacity, mechanisms, governance and Ministry ownership. This makes the delivery risk relatively low.
  - The main risk comes from investing in quality of teaching when the very basic inputs of the education production are so at risk: teachers not attending enough, children not attending enough, and extremely large classes. This is mitigated by evidence that the reform has worked in current conditions. However, conditions are likely to deteriorate as the population continues to grow and climate change negative impact on education intensifies.

Option 3: Support for Early Childhood Education and Development

What:
Work alongside the World Bank and private foundations to expand access to quality early childhood education and development, both through formal pre-school and community-based interventions that would support children from 0 to 6 years old, including a multi-sectorial community-driven perspective that includes nutrition, cognitive stimulation, and school readiness. This would be a mix of home visits for 0-3 years old, support to community volunteers running the community preschool centres, investment in the quality and learning material where not covered by other partners, and connections with the primary school.
Justification:
- If we want to improve foundational learning, we should start from the very foundations. Only 2.4% of the education budget goes to early childhood education and attendance remains low at 34%. Malnutrition in the early years is increasing with stunting at 35%. Stunting impacts cognitive development later on, reducing the effectiveness of investments in schooling.
  [note] UNICEF, WHO, World Bank Joint child Malnutrition Estimates (JME) 2020
- The World Bank has been supporting this sector through the “Investing in Early Years” programme, but that programme is about to end in 2025. Further support will come through the GPE funding; however, that support is only covering scale-up to 1,000 pre-schools across the country for children who are 5 years old. The Ministry of Community Development, alongside the Roger Federer Foundation, has also increased access and quality of community-based early childhood development and education, but much remains to be done. Connections between the Ministry of Gender, Ministry of Health and Ministry of Education need much stronger links for a truly holistic approach to early childhood education.
Evidence on learning:
- Evidence of the impact of investing on Early Childhood Development (ECD) on Human Capital is strong, and so is the evidence of impact of ECD investments on foundational learning. ECD is the sector with the highest return on human capital, partially because it addresses the issue of human development at the very root.
  [note] Heckman (2006). Skill Formation and the Economics of Investing in Disadvantaged Children. Science; Gertler et al.
- Early childhood care and experiences, have a profound impact on brain and cognitive development. Recent evidence has shown that both early stimulation and quality community preschool from age 3 increases cognitive development, and the latter helps directly with early literacy and numeracy. A meta-analysis suggests that the average impact of preschool on both literacy and numeracy is 0.2 SD in lower-income countries
  [note] Sequencing Two Early Childhood Interventions Back-to-back in India https://www.povertyactionlab.org/evaluation/sequencing-two-early-childhood-interventions-back-back-india
  [note] https://documents1.worldbank.org/curated/en/929861625060766293/pdf/Is-Investment-in-Preprimary-Education-Too-Low-Lessons-from-Quasi-Experimental-Evidence-across-Countries.pdf or also Richter, L.M., Behrman, J.R., Britto, P. et al. Measuring and forecasting progress in education: what about early childhood?. npj Sci. Learn. 6, 27 (2021). https://doi.org/10.1038/s41539-021-00106-7
- Providing parent-directed early childhood stimulation programs (for ages 0 to 36 months), providing quality pre-primary education (for ages 3 to 5) are both categorised as “Good Buys”, based on their cost-effectiveness.
  [note] However, we note one study for Malawi that shows no long term evidence impact of ECD on literacy and numeracy specifically.
Beneficiaries and cost
- We approximate cost at £17 per child per year, impact from international evidence of 0.2SD on FLN suggests roughly £8 for a 0.1SD again assuming linearity. We estimate that £35m would deliver through 10,500 volunteers in 3,500 CBCCs (3 volunteers per CBCC, each serving about 40 children) for a total of up to 2.1m children
  [note] Calculated using the assumption that we have 3 volunteer in 2,000 primary schools, paid £500 per year, plus cost of training volunteers of £25 per day for 5 days and indirect costs.
  [note] Here there is an assumption that each year, the volunteer would get a new batch of 40 children to focus on.
- Hence cost-effectiveness becomes: 0.2 SD * 2.1m children/ £35m= 0.01
- Note that we are only counting benefits for foundational learning. This programme would be a lot more cost effective if we counted broader objectives. But, from an education perspective, the problem we are trying to address is foundational learning.
Risks
- This would require working with the Ministry of Gender rather than the Ministry of Education, a Ministry that we do not currently work with. We would have to rely on implementing partners heavily for the initial years and there might be additional risks and constraints that we don’t fully know because we haven’t worked with them.
- GPE and the World Bank working on construction of 1,000 preschool, coordination across two Ministries would be critical.
- There is no investment in climate resilience. For families with nothing and in severe food insecurity, nutrition advice might be frustrating and useless.

Option 4: School Feeding to make education system more resilient to climate change and hunger

What
- Direct support to school feeding in the most food-insecure communities that are still not covered by school feeding.
- Policy/Technical Assistance to support a school feeding expansion strategy for the Ministry of Education, exploring how to lower the cost of reaching the remaining schools, either through community contributions and/or through innovative financing solutions.
Justification
- Food insecurity is high across the country (see Fig 1), with 5.7m people in acute food insecurity (IPC Phase 3 or above) projected between Oct 2024 and March 2025.
  [note] IPC Malawi Food Insecurity Analysis March 2024-March 2025
- Due to climate shocks and macro instability, the situation is worsening over time. In 2020/2021 15% of the population was in crisis level food insecurity; this year, it was 28% of the population.
- School feeding will mitigate the increase in hunger caused by increased climate volatility, including climate-change related crop destruction through cyclones, floods, and famine. For this reason, school feeding can be categorised as a climate adaptation intervention because it increases the number of people who are resilient to climate.
- Although we don’t have definitive data, we believe that absenteeism is in large part exacerbated by hunger. From a previous programme implemented by WFP, school feeding was correlated with improved attendance, from 77% to 92%. Our own evaluation showed that up to a third of children are absent from primary school on any given day, reducing the effectiveness of reforms to improve teaching.
- While cash transfers and social protection programme can mitigate this by providing cash to the families, we know that the intra-household allocation is often inequitable and does not directly benefit the children. For very food insecure families, children might still feel too hungry to come to school. The Malawi Social Cash Transfer programme covers only a minority of children.
- School feeding is already covering 40% of the country, 2,363 schools. 586 of these are supported by WFP, 920 by Mary’s Meals and 378 by communities or by councils, with smaller players covering the rest
- Most WFP schools follow a “home-grown school feeding model”, a promising model whereby schools receive grants to buy diverse foods for school feeding from local farming cooperatives that is undergoing a rigorous impact evaluation. The model is promising because it provides from local markets and because it delivers a diverse diet, but may not be appropriate for communities that do not have an excess supply of food to sell to the school. WFP is interested in understanding how to adapt the model to these communities, which is something that we could support.
Evidence on learning
- School feeding is categorised as an “effective, but relatively expensive” intervention in the Smart Buys paper. However, the paper also acknowledges that school feeding might make sense for very food insecure communities, which is where we would propose to work. In Malawi, school feeding costs about $20 (£16) per child per year- significantly less than other countries that were used for the Smart Buys evaluation (the average spend per year in LMIC is $64 per child per year).
  [note] State of School Feeding Worldwide 202, available at: https://www.inter-reseaux.org/wp-content/uploads/WFP-0000147725.pdf
- The Smart Buys evidence points to an average between 0.15 and 0.2 SD on FL, but with a high variance. Impacts are larger for girls and for children in the early years. Given the high food insecurity in Malawi and the focus on the early grades, we assume 0.2SD. This leads to a £16 for 0.2SD so £8 for a 0.1SD per child.
- In addition, we believe that through school feeding, we can improve the impact of the mathematics reform, although we don’t have enough evidence on how much.
Beneficiaries and Cost
- The cost of £16 is the direct cost, but we assume £19 with indirect costs.
- With £35m, we would be able to fund 1.8 million packages of meals for one year. We have assumed above that benefits are calculated for one year of exposure. In school feeding, there is some scarce evidence of multiplicative effect but the evidence is too scarce. For comparability, we assume that each child would only get school feeding for one year (this would be the case if we only fed the children in grade 1, for example). Any other assumption would be too punitive for this option, because it would assume zero additional benefits of delivering meals for anything more than one year.
- As the benefit is 0.2SD, our assumptions would lead to approximately £9 per child to deliver 0.1SD in learning gains.
- Cost-effectiveness becomes 0.2*1.8/35m=0.01
Risks
- School feeding is a recurrent cost, there is no sustainability, although costs can be reduced. The long-term impacts of this should be thought through in advance. In Malawi’s case the low prospect of significant economic growth in the short term means the need for school feeding is highly likely to remain over the course of this programme.
- The choice of which schools to support can become political and this needs to be mitigated by using transparent criteria of need or strategic relevancy in the selection process.

Summary table for Foundational Learning Appraisal:
Option	Cost of 0.1SD increase in learning, approx.	Risks and other considerations
Option 1: Build low-cost, climate resilient classrooms	£3 per beneficiary	Maintenance concerns; safeguarding risks; new sector for FCDO so overall riskier. / Malawi needs large infrastructure investment and FCDO doesn’t have enough money bilaterally to deliver at scale. Investing a small amount of money to leverage climate finance is more strategic.
Option 2: Complete the mathematics reform with system-wide investments in quality of teaching and accountability for foundational learning	£4 per beneficiary	Low delivery risk given continuation of programme that has worked well; connections with other partners and governance and accountability critical. Key risk remains investing in quality of teaching when so many children are absent from school; reform has not worked for the very poorest 30% of children so needs complementary investment.
Option 3: Support for Early Childhood Education and Development	£8 per beneficiary	Early childhood is not under the Ministry of Education so risks with working with a new sector; 1,000 preschools and ambitious expansion plan from Ministry of Education leaves uncertainty over future ownership of early childhood education. This option would have higher cost-effectiveness if the outcome was broader- consider this as part of cross-sectoral business cases, for example for social protection.
Option 4: School Feeding to make education system more resilient to climate-change and hunger	£9 per beneficiary	No sustainability. Makes most sense for food insecure communities, which are communities that are least able to take advantage of most innovative model. Potential to increase attendance can multiply impact of mathematics reform.

Conclusion for Foundational Learning Appraisal and Analysis of chosen options
From the analysis above, we propose to pursue a combination of Option 2 and Option 4: the majority of available funding will be prioritised for Option 2, combined with a smaller complementary investment for Option 4.

Option 2 is a relatively low-risk option because it builds on the successes and lesson of a programme that has already proven to work well, for a low-cost and in an area where FCDO is already leading and innovating. We have evidence suggesting that the reform can achieve an even higher impact through continuous investment and we believe we know how to fill the gaps in the existing evidence base. Option 1 is slightly cheaper but in terms of broader cost-effectiveness and value, we think Option 2 is justified because it offers a better return for our investment. It is backed by hard evidence that this intervention works, and it would come at a moment when the returns are increasing and risks decreasing.

The choice to complement Option 2 with a smaller investment in Option 4 is justified by the need to increase the resilience of the education system to climate events in the poorest communities. We also believe that Option 4 will deliver higher attendance which should multiply the impact of our core investment in mathematics/foundational learning, especially for the poorest. This choice helps mitigate the risks discussed in the strategic case where hunger may increasingly prevent children from being able to access education. We discussed above how we believe that the actual cost-effectiveness of school feeding may be higher than the one reported in the Smart Buys, because of the lower cost in Malawi and the likely higher impact due to widespread food insecurity. We will continue to gather evidence, especially from the upcoming two RCTs of school feeding in Malawi, and monitor costs and impact, and revise the decision if the impact on attendance is not as high as expected, or other mechanisms to make children more resilient to climate change (such as better targeted child grants as part of social cash transfers) become available.

The investment would be targeted to climate vulnerable and food insecure communities to improve impact with technical assistance contributing to the expansion by reducing the cost. The model will include food diversity, involvement of community, localisation of ingredients, focus on behaviour change to reduce the dependency on maize (a crop that is not resilient to climate change) as well as a move away from burning charcoal for preparing the food to strengthen the climate connection. FCDO should lean into school feeding because famines and hunger are affecting the core education investment, and yet no education partner is leaning into that space. WFP and EU are the main partners but mostly work through an agriculture angle and do not work directly with Ministry of Education. The funding is limited but a mix of careful co-funding and support to the policy space can deliver the needed complementarity.
Alongside the main investment in school feeding we would also consider some small strategic funding if opportunities arose to leverage larger climate financing which could then be used for more resilient infrastructure.

How will it work and what outputs will it deliver?
We will spend £27m on completing the mathematics reform and making system-wide investments in quality of teaching. Based on previous costs, we estimate that with approximately £27m in the next five years we can deliver to over 7m children the same minimum quality that led to the impact in the previous business case, alongside other partners also working in Foundational Learning, the Global Partnership for Education and complementary investment from centrally managed programmes. A focus on inspiring and empowering girls will be included, as well as a deliberate effort and investment to promote women in the accountability and management of the school. Outputs will include a scaled-up reform to Std1-Std4 for the duration of the programme, teachers in teacher training colleges learning the new curriculum, teachers supported to deliver the reform through evidence-based and system-institutionalised continuous professional development and districts taking action over poor foundational learning results. There will be a focus on delivering results that can be verified, either through technical assistance to the wider Education Programming for Results programme or through support to a delivery-minded unit responsible for implementing the objectives of the five-strand foundational learning strategy and measuring success.

We will spend £8m to complement the mathematics reform with co-funding to make the education system more resilient to climate change and reach the most disadvantaged, specifically by co-funding school feeding directly in food insecure communities and through TA to reduce cost of a scalable model.
The £8m would also include smaller strategic investments on climate resilience. We did not appraise these directly because of the low value, but we will still be closely monitoring value for money:
1. Strategic funding to attract climate financing (approx. £0.5m). This would allow us to consider small amounts of strategic funding if opportunities arose to leverage larger climate financing to support the education sector to be more resilient to climate change. This was done in Malawi for climate and health, where a UK investment of £0.4m attracted a Green Climate Fund investment of $37m for Malawi. At the moment, the most promising avenue is to follow a similar process and provide co-funding to support an application for Climate and Education infrastructure in Malawi, but other possibilities are being explored. Education is only receiving 2% of the climate fund, and yet education in Malawi is already being disrupted by climate change. The UK will not be able to solve this bilaterally, but can leverage much larger sums of money through multilaterals, especially for climate resilient infrastructure.
2. Build evidence for a behaviour change intervention, currently proposed to be innovation funds for schools to solve local environmental adaptation challenges in their schools or communities (approx. £0.5m). Education needs to be part of the adaptation response for climate change, both to inspire change in the next generation but also through creating behaviour change with parents. Yet, we know very little about how to do it right, and there have been very few evaluations so far. Many countries have decided to imbue climate change into the curriculum, but this is risky and could be ineffective or even distortive: what children need are not theoretical lessons about a climate change that they can’t mitigate, but a practical, problem-solving mindset about what adaptations can help problems in their communities. An innovation fund or similar where schools can partner with local actors to solve challenges can achieve this. There is some limited but promising evidence that this could work, but the rationale for this investment is to build much needed evidence around how education can contribute to adaptation. It will be accompanied by learning, research and dissemination. The output would deliver evidence of impact on whether and how action-based intervention in school can change behaviour, attitude and understanding of pupils.
  [note] The World Bank climate and education report shows that parents are 13% more likely to change beaviour if the behaviour change agent is their child (Choosing Our Future: Education for Climate Action)
  [note] Practical, problem-solving eco-clubs were evaluated in India and are mentioned as a promising intervention in the Climate and Education FCDO position paper. We know challenge funds are a good mechanism to solve localised problems and motivate around delivering a solution.

Finally, we propose to include a learning and evaluation component (£1.5m) to do implementation research and impact evaluation. This will support the foundational learning outcomes by ensuring reforms and their implementation are evidence-based, leading to better VfM and effectiveness. A recent paper showed that research on better implementing known productive interventions, such as targeted instruction, can be up to 10-fold higher return than discovery of new interventions. The What Works Hub, an education research centrally managed programme, is rapidly building up evidence on how implementation science in education can significantly reduce cost and make the programmes more effective at scale by improving take-up, focusing on the components and improvements that reduce costs and make the most difference.
[note] Implementation Matters: Generalising Treatment Effects in Education | Blavatnik School of Government
Appraisal for delivering targeted support to girls to stay in secondary schools
We appraise support for girls to stay in secondary school separately, because the outcome of this investment is not learning outcomes specifically, but rather keeping disadvantaged, rural girls in secondary school and the significant social benefits this brings. Other actors, including EU and World Bank, are working on improving the quality of secondary education.
As we have prioritised foundational learning, the scale of the girls-specific investment is smaller. The appraisal is in the context of the modest scale of this investment: the outcome needs to be proportional to the investment.

Options not appraised:
- Do nothing and reach girls only through the already proposed impact of foundational learning investment: We prioritised foundational learning because of its impact on all children, including girls, with some evidence that girls benefit more than boys from it. However, rural, disadvantaged girls do need additional and tailored support to overcome gender-specific barriers that open up later in life. Girls thrive until Std 4 and then start falling behind when adolescence starts. Girls who drop out before secondary have very few economic opportunities. The girls and boys who make it to secondary schools are few, but girls are at higher risk of dropping out once they are in secondary and have less opportunities once they do. Girls who do make it to secondary school have overcome so many barriers, and letting them drop-out in secondary school is a large inefficiency and a missed opportunity to stop the intergenerational transmission of poverty. A recent study showed that scholarships for secondary school girls delays childbearing, marriage, allows them to marry a more educated partner, reduces the mortality of her own children by 45% and her children gain 0.25SD more once they are in school. In addition, as the FCDO Education and Climate Position Paper (2022) makes the case, women with secondary education are better equipped and more likely to engage in familial, societal change and taking action on the climate emergency. These are remarkable outcomes. These girls have high potential because they manage to get selected to secondary and are clearly committed to education, but held back by poverty.
  [note] Duflo, E., Dupas, P., Spelke, E. and Walsh, M.P., 2024. Intergenerational impacts of secondary education: Experimental evidence from Ghana (No. w32742). National Bureau of Economic Research.
  [note] Annex B of Addressing the climate, environment, and biodiversity crises in and through girls’ education - GOV.UK (2022)
- Mentorship and financial support to disadvantaged, rural girls to continue upper-primary school and transition to secondary. Mentorship in the upper primary might seem like an obvious investment in that critical period of early adolescence. The previous business worked on this but the results in terms of drop-out and transition were minimal, likely due to structural constraints such as low learning levels coupled with a very low probability of getting selected into secondary school: due to scarcity of available places in secondary, only a handful of the most well performing pupils from each rural school have a chance of getting selected into a secondary school.

Options appraised:
Option 1: mentorship and scholarships for disadvantaged, rural girls once they are selected into secondary school trough an NGO.
Option 2: conditional cash transfers for girls
Option 3: contribution to Ministry-run scholarships scheme through support to a multilateral

Similar options were appraised in 2023 as part of a dedicated small business case called “Bridge for Girls Education” and our conclusion has not changed. Other partners such as EU and World Bank are prioritising secondary school with large investments in expansion capacity and quality, as well as scholarships. The remaining need is still large and the UK does not have enough funding to be a large player in this effort. However, complementing them through a small but high quality and coordinated contribution through scholarships and mentorship can make a tangible difference.
Option	What	Justification and Evidence	Considerations
Mentorship and scholarships to disadvantaged, rural girls who are selected into secondary school, delivered through an NGO	Identification of neediest rural, disadvantaged girls selected into secondary school in selected districts, prioritising girls who excelled at the exams and are also extremely disadvantaged. Support them for 4 years of secondary school through scholarship, financial support, and mentorship so that they can continue secondary school.	Giving merit-based scholarships to disadvantaged children and youth is considered a “Good Buy” due to its cost-effectiveness. / Scholarships for vulnerable girls who were selected to secondary school but can’t afford it have proven to be effective, especially when combined with mentorship and there is a clear unmet need in Malawi. / An NGO can deliver mentorship well, can establish additional checks to reach the most disadvantaged, and can deliver high safeguarding standards.	We provided scholarships and mentorship as part of a small ongoing business case ending in 2025, so far with promising initial outputs. Continuing would be low risk and low management burden, while delivering on a proven effective intervention. Management of safeguarding risks is the largest risk that FCDO team will need to manage carefully, but it can be more effectively managed through an NGO.
Conditional cash transfers for girls	World Bank is in the initial stages of considering conditional cash transfers for girls to complement the main social cash transfer programme, similarly to how it was done in Zambia. FCDO could contribute to the design and co-fund this effort.	There is uncertainty over how this would work, and the target. The evidence on conditional cash transfers does not seem to outperform scholarships and mentorships.	There is an argument for coordinating support and investing TA to augment the overall effectiveness of the World Bank investment, but at the moment there is too much uncertainty for this option.
Contribution to Ministry-run scholarships scheme through support to a multilateral	Ministry is the largest funder of scholarships and World Bank, EU and UNICEF are working to better coordinate this scheme to make it more effective, equitable and efficient and reduce fragmentation of the scholarship landscape.	The Ministry scholarships do not include mentorship. Evidence points to the importance of combining mentorship to financial support. There are advantages in terms of coordination and reduced fragmentation although this is not a major issue in the provision of scholarships.	Some potential in the idea of using UK funding to introduce mentorship and multiply impact of existing scholarships by reducing drop-out, but funding is not enough to expand mentorship to all girls receiving government scholarships. Safeguarding risks may be difficult to mitigate.
[note] See for example a review from the Centre for Global Development with further source links: Girls’ Education: Going from What Works to What Works at Scale | Center For Global Development (cgdev.org) or this Campbell systematic review Policies and interventions to remove gender‐related barriers to girls' school participation and learning in low‐ and middle‐income countries: A systematic review of the evidence - Psaki - 2022 - Campbell Systematic Reviews - Wiley Online Library or this Population Council paper reviewing what we know and what we don’t know Advancing the Agenda in Girls’ Education Research (popcouncil.org)
[note] Lessons on how to approach peer mentorship: gec_learning_brief_peer_mentoring_final.pdf (girlseducationchallenge.org)

Conclusion of appraisal and analysis of chosen options
We propose to continue supporting girls through Option 1, dedicated scholarships and mentorship through an NGO. We believe this is justified by the higher effectiveness through mentorship and the lower safeguarding and fiduciary risks. We can mitigate the risk of fragmentation by being well coordinated and actively participating in the policy discussions around policy. If in the future there is new evidence or a clear case for investing in the World Bank conditional cash transfer without hurting the girls who have started receiving scholarships, the decision will be reconsidered.

How will it work and what outputs will it deliver?
We will provide mentorship and scholarships to an estimated 1,500 girls for four years, with an average cost of £400 per year per girl. The beneficiaries will include girls with disabilities and girls in the Dzaleka refugee camp.
The overall gap of vulnerable students not receiving scholarships is around 44,000, half of them girls. Providing 1,500 scholarships would reduce the gap by 8%.

Theory of Change for full programme
Theory of Change:

Assumptions
Key assumptions for output 1 are that the impact evaluation results continue to hold as the programme continue to scale up and mature, that implementation fidelity continues to remain high, and that teachers become better at delivering the programme both through experience and through effective continuous professional development. To move from output to outcome, the programme inputs on mathematics will not be enough by themselves, and the theory of change relies on coordinated and well-designed complementary programmes, including continuation of the USAID support for foundational literacy, co-funding from the World Bank governance pay by results continuing to be focused on relevant indicators for education delivery, and remediation programmes (coordinated with the new mathematics curriculum) being scaled up. The support will also deliver Technical Assistance to the Ministry foundational learning delivery results framework and the assumption is that the results indicators are meaningful and strategic enough to address key bottlenecks.

Key assumptions for output 2 are that the co-funding for school feeding is feasible in food insecure communities through an adapted home-grown school model, and delivers resilience through less disruption to education, and that the Ministry of Education continues to remain committed to an even cheaper, more affordable school feeding that relies on contributions from communities. Another key assumption of output 2 is that the strategic investment for climate and education financing does bring about additional climate funding before the end of the business case. Output 2 will contribute to Outcome 1 and 2 only if school feeding does bring about the expected increase in attendance and if teachers are present enough to make that matter. Finally, we assume that the levels of climate shocks will be stable enough to

Output 3 relies on effectiveness of scholarship and mentorship in keeping girls in school, i.e. no other forces become strong enough to make our inputs irrelevant. Finally, Output 4 relies on a good collaboration between research and implementing partners and researchers, and researchers identifying the adaptations that have the highest return on cost-effectiveness.

## Commercial Case

This section sets out how the preferred option will be procured and delivered. As this programme aims to deliver a number of separate components, the first step is to determine how this should be done with the following options considered:

1. Deliver all components through a single provider who would manage them all on behalf of FCDO.
2. Commission components separately with FCDO managing each individually.

Option 2 is recommended in order to ensure that the right organisations are charged with implementation with FCDO retaining the right level of management and oversight. The alternative of trying to procure a single supplier to deliver all components was considered and would reduce the management burden on FCDO but is judged to be too unwieldy given the diverse nature of the outputs.

The below sets out how each of the four components of the programme can be delivered and the proposed procurement route.

Component 1: Numeracy and associated foundational learning reforms £27m
This component will require careful management of a number of deliverables in order to successfully implement the roll-out of the numeracy reform up to standard 4 (including workbooks and large-scale training) as well as ongoing support to embed the reform (coaching, technical assistance and adaptations for children with disabilities).

The table below highlights the delivery options considered for this component:
Option	Strengths	Weaknesses	Comment
Commercial contract with private sector supplier	Allows competition between private suppliers for best expertise and VfM. / Allows use of milestones linked to payments to manage performance.	Suppliers will charge a fee (including their profit) for their services. / Large contracts can be inflexible and require commercial management.	A commercial contract has been used successfully up to now to deliver the numeracy reform up to standard 2.
Use of pooled funding mechanism	May allow easier co-funding if other development partners would be interested in using the same mechanism.	Doesn’t allow strict performance controls and more reliant on existing government capacity. / May not be able to access best expertise.	No partners interested in co-funding have so far expressed interest in using such a mechanism.
Delivery via UN or large INGO	No profit motive and simpler agreements without the requirement for commercial management.	May not have right expertise to manage commercial procurements of workbooks.	There is not currently an obvious UN or INGO partner who is already working in the area of foundational numeracy.

Given this component has clear specific deliverables that will need to be delivered through downstream implementing partners and requires strong management to meet the deadlines of the academic year it is well suited to a commercial contract. We therefore propose to use a private sector supplier for this component. This will require commercial management expertise in the British High Commission Malawi but this has been built up on the current programme which allow us to incorporate lessons learned into the commercial design. There is also the possibility that some of the wider foundational learning reforms, for example on assessments, will be better delivered across numeracy (which is a UK lead) and literacy (which is a US lead). It may therefore be beneficial to retain approx. £1m from the total funding which can either be used to co-fund such a reform via a Delegated Cooperation Agreement with USAID/World Bank or added into the main contract with our supplier at a later date.

As discussed further in the management case below, a programme funded position is proposed to support the coordination of this component with government and donors which would not be appropriate for a commercial supplier to deliver.

Interim arrangements for 2025:
As set out in the strategic case, this business case is picking up from an existing programme which has started, but not completed, the roll-out of the new curriculum to standards 1 & 2. Funding from this business case is required to complete this roll-out as the cost of this increased significantly when, in the summer of 2024, the Government of Malawi increased the allowances for public sector workers. This led to an increase in the cost of providing training to the 30,000 teachers who will deliver the new curriculum. It is proposed that funding from this business case is used to allow the existing supplier to complete the roll-out across standards 1 & 2 as well as ensure that workbooks and training are provided for the start of the 2025 academic year for standards 3 & 4. This will allow a fair procurement for a potentially new supplier to pick up the delivery of this component after Sept 2025 for the next five years and reduce commercial risks regarding any transition in supplier.
Market assessment:	There are a good number of commercial organisations who can manage this component, including those on the GDD framework education lot although not all these suppliers will have experience working in the Malawi context. The lead supplier will likely need to manage a number of downstream partners on specific deliverables (see delivery chain mapping in financial case). There are only a small number of organisations with the specialist technical expertise on numeracy curriculum reform that is required so we might expect to see some technical organisations applying on multiple bids. A Prior Information Notice (PIN) and Early Market Engagement (EME) events will be used to seek views from potential suppliers and ensure the market is aware of the opportunity. Strong pre-market engagement is vital from the outset to address the perceived incumbency advantage and test the market’s ability to deliver this output.

Procurement route:	A full sourcing strategy will be developed with commercial advice to determine the most appropriate route to market to get the outcome we want. As set out above the existing supplier will need to deliver the initial activities over an interim period. This allows sufficient time for a full competitive procurement process given there is no justification for sole sourcing. The two options would be: / Open procurement process (or other competitive process within the scope of the new Public Procurement Act 2023, which goes live in February 2025, dependent on tender release date). / Use of the Global Development Delivery (GDD) framework agreement. / The GDD framework lot 3 (for large education programmes) would allow a mini competition between the 15 pre-approved suppliers, many of whom should be capable of delivering this component. This route would take advantage of pre-negotiated fee rates which could help drive VfM but may limit options to extend the programme. The open procurement route would allow any organisation to bid for this contract but would not take advantage of the pre-qualified suppliers and streamlined process of the framework. / Sufficient information will need to be provided alongside the Terms of Reference to allow potential new suppliers to submit credible proposals. One learning from the current programme is the need for flexibility to scale up and down and make amendments throughout the life of the contract. This was partly necessitated by COVID but also due to the challenges of implementing large scale reforms in the Malawi context. This business case has attempted to take a more realistic view of the time needed to complete this reform but the option for contract amendments should be retained given the context.
VfM and partner management:	The key cost drivers for this component will be the procurement and distribution of workbooks, the costs associated with large-scale teacher training along with management and technical assistance staff costs. FCDO has an excellent grasp of these costs through analysis of the existing programme as set out in the most recent Annual Review. Overall the maths reform component represents excellent value for money with an evaluation of the pilot showing increased learning across all standards for less than £5 per child overall. For example, the cost of procuring high quality workbooks under the existing programme has been driven down to £0.16 per book, from £0.44 initially. Approximately 10.5m workbooks will be required each year. Further savings are likely to come from efficiencies in distribution as well as improved equity through good quality material for children with special educational needs. The cost of training a teacher is approximately £25 per day representing a large cost given there are more than 30,000 teachers at standards 1-4. It is therefore crucial to ensure that where training is required it is as effective as possible and that other methods of providing continuous professional development are also fully utilised. A commercial contract allows close control of management fees and the use of Key Performance Indicators (KPIs) linked to specific deliverables which has worked well in driving performance on the current education programme. We would anticipate KPIs on delivery (focused on core metrics such as workbooks distributed), quality (focused on metrics around sustainability linked to long-term impact) and financial management. A key focus of the supplier will be in reducing the costs of embedding this reform to improve sustainability, for example, exploring the eventual transition from workbooks to textbooks. The supplier will also need to be capable of managing the significant challenges of working in Malawi including capacity constraints and inflation running at over 30% while still achieving overall value for money.
[note] SMES 2024 Annual Review - link
[note] Strengthening Malawi’s Education System (SMES) – link.

Component 2: Building resilience to climate impacts £8m
This component would aim to deliver a range of activities aimed at reducing the impact of climate change on education outcomes and helping to build a resilient education system. A large part of this would be co-funding the provision of school meals as well as supporting innovation at school level and helping to leverage climate finance.

Market assessment:	There are currently two large providers of school meals: Mary’s Meals and the World Food Programme (WFP). Of these we propose to work with WFP to continue developing their community-based model and help drive down costs to reach more children. Mary’s Meals provide food directly rather than supporting the local community to grow the necessary ingredients. WFP can also work with local NGOs to support schools on local climate innovations and already do this with World Bank support, and work with Ministry on the expansion of school feeding and on supporting the innovation challenge. Leveraging climate finance will mean providing small amounts of strategic co-financing to organisations applying for large climate finance grants. There are often very few organisations capable of this, for example, Save the Children are currently one of the few organisations accredited to apply to the Green Climate Fund in Malawi.
Procurement route:	As this component aims to co-fund existing work it is proposed to use direct awards with UN/NGO partners rather than competitive commercial procurement. This would utilise a standard UN agreement with WFP and small accountable grants with NGOs who are bidding for much larger climate finance grants.

VfM and partner management:	Key cost drivers will be food prices along with staffing and overheads. The recent global framework agreement with WFP includes a 6.5 - 7% overhead rate which is less than other UN agencies. The overall cost per child is likely to be relatively high compared to the numeracy reform in component 1 with school feeding currently costing approximately $20 per child per year. This can still provide value for money on an equity basis if it improves the impact of the whole programme for the bottom third of children who are not reached by better teaching alone. There is also appetite within the Ministry of Education to drive down the cost of school meals in communities that can afford to contribute part of the costs, thereby improving sustainability. WFP has led the development of a model which sources food from farms near to the school which also supports agricultural productivity and encourages the planting of a diverse range of crops that are more resistant to climate shocks and provide better nutrition than maize alone. This aligns well to wider UK objectives in Malawi. WFP scored strongly in the Multilateral Development Review and FCDO has a good understanding of their performance in Malawi specifically as the UK already channels significant humanitarian funding to this organisation given the wider food insecurity in the country. We have confidence in WFP’s procurement and risk management processes through current due diligence assessments. We would also consider providing small grants to NGO organisations to help unlock climate finance in the education sector in the same way that we have provided £450k to Save the Children to unlock a $37m Green Climate Fund grant.

Component 3: Supporting girls’ education £2.5m
This component is simpler and aims to provide scholarships and mentorship to help disadvantaged rural girls stay in secondary school. It requires a presence in the districts and the schools where it is being implemented to help ensure the right girls are selected and supported.
In 2023 FCDO looked at the options for delivering this support in the “Bridge for Girls Education” business case and concluded that an accountable grant with an NGO is the best route. This assessment still stands as the context has not changed. The alternative would be to work though the UN who have provided scholarships in the past although have less experience of mentorships. As set out in the appraisal case it’s possible that during the programme lifetime there may be a change in context with a coordinated effort to achieve this output through cash transfers with the World Bank which could provide an alternative route that delivers good VfM. Cash transfers can provide a highly efficient incentive but there are currently significant challenges regarding how to target this support effectively and, until this is overcome, we judge the use of NGOs more likely to achieve the desired outcome.
[note] DevTracker Programme GB-GOV-1-300075

Market assessment:	There are a large number of NGOs already delivering this type of activity in Malawi who have a good understanding of the local context. We engaged with 11 organisations in this area during the selection of the NGO to deliver the current support in 2023 with 9 organisations going on to submit applications demonstrating a strong field.

Procurement route:	Call for proposals amongst selected NGOs active in this area. An accountable grant arrangement would then be agreed. An arrangement through one NGO or a consortium with a strong prime is preferable to provide clear accountability and management.

VfM and partner management:	Key cost drivers will include the rate for scholarships which are approximately £200 for community day schools and £400 for boarding schools. Boarding schools can provide significantly higher quality of education for those students able to take advantage of this while community day schools provide education for the most disadvantaged girls in rural areas. We propose to mostly support scholarships to the cheaper community day schools to reach a larger number of girls with a small number of boarding school places reserved for students able to excel in this environment. Staffing and indirect costs also add to the overall cost of this component and will be negotiated in line with existing benchmarks.

Component 4: Implementation science and evaluation £1.5m
This component uses implementation science, learning and evaluation to increase the efficiency and effectiveness of how the foundational learning component is implemented at scale, and has the potential to contribute evidence to the global picture of how to improve learning in low resource settings. To deliver this we are proposing a collaboration with the What Works Hub for Global Education, this is a centrally managed programme implemented by a consortium led by the Blavatnik school of government at Oxford University, and encompassing researchers from the global north and south committed to improving how programmes are implemented and deliver cost-effectiveness. The What Works Hub is already working to help programmes improve take-up of reforms and reduce costs and therefore makes an ideal partner to support this programme to achieve the same aims.

Market Assessment: There are several providers who could help with learning and evaluation, including those pre-approved from the GMM framework or DIME from World Bank, in addition to the What Works Hub. The What Works Hub, however, offers a unique mix of academic excellence, ability to work with Ministry hardwired in their mission, and gravitas that comes from their ability to convene policymakers and academics through their events.

Procurement Route: We are currently discussing procurement options with the What Works Hub programme managers. This could include a “buy-in” into the centrally managed programme.

VfM and Partner Management:
The choice of What Works Hub delivers VfM because Malawi would be able to build the synergies arising from the overall What Works Hub management, structures, and reporting therefore having lower indirect costs, cost-sharing (for example for dissemination events), and time from the What Works Hub senior leadership to help with strategy, direction, and quality assurance. These synergies will allow more funding to spent on the ground.

Commercial risks across whole programme:
Risk	Likelihood	Impact	Mitigation
Delays to the procurement process result in a failure to select a supplier in time for roll-out of teacher training.	Possible	Major	Guidance from senior commercial adviser throughout including careful consideration in the sourcing strategy of the route to market. Using a contract amendment with existing supplier for Term 1 2025 training. Early Market Engagement to help suppliers engage and submit robust proposals.
Perceptions of unfair advantage of the existing supplier results in challenges from other potential suppliers during procurement.	Possible	Moderate	Careful design of terms of reference and criteria. Information shared alongside terms of reference including existing reviews and contracts. Use of Early Market Engagement to ask questions and consideration given to holding further market engagement during proposal drafting period.
ODA cuts result in lack of UK funds for supplier to deliver agreed activities.	Unlikely	Major	Ensure careful prioritisation of funds within BHC Lilongwe to maintain key activities. / Ensure contract has flexibility to extend length to allow contracted activities to take place over a larger time period. Explore alternative funding sources to spread risk.
Supplier fails to deliver programme outputs to sufficient quality for the reform to be effective.	Unlikely	Major	Careful management by programme and commercial team. Use of KPIs to ensure key activities are delivered on time and to sufficient quality. Early escalation and action on concerns of poor performance.
Changes to context (e.g. increase in fuel prices or allowance rates) result in the supplier not being able to deliver the agreed outputs within budget.	Possible	Moderate	Provide clarity in Terms of Reference regarding which potential contextual changes they should price in (e.g. inflation) and which could be grounds for budget amendments. Ensure potential suppliers have carefully considered contextual risks as part of their proposals.

## Financial Case
FCDO will contribute up to £39 million over five years. The programme will be funded from the country budget for Malawi within our Resource Departmental Expenditure Limit (RDEL).
Costs will be prioritised within the existing country budget subject to spending reviews. Costs for 25/26 are reasonably fixed but there is more flexibility after this. Break clauses will be inserted into all contracts and agreements to manage financial risks. VfM is expected to be reasonably high, particularly for the maths component at approximately £3.68 per child reached.
Estimated forecasts by component are set out below and may require adjustments as the programme is delivered. Forecasts will be reviewed monthly throughout the life of the programme.
Component / Forecast £000	25/26	26/27	27/28	28/29	29/30	Total	%share
1: Numeracy and associated foundational learning reforms	9,200	5,300	4,200	4,200	4,100	27,000	69%
2: Building resilience to climate impacts	200	1,700	2,000	2,000	2,100	8,000	21%
3: Supporting girls’ education	300	600	600	600	400	2,500	6%
4: Implementation science and evaluation	300	300	300	300	300	1,500	4%
Total	10,000	7,900	7,100	7,100	6,900	39,000	100%

Payment schedules will depend on management arrangements set out for each of the four components of the programme as described in the Commercial Case above. Implementing partners will provide forecasts of expenditure to FCDO at the beginning of each financial year; these will be revised regularly in accordance with the respective delivery agreements. Payments will be made in GBP and in arrears with any exceptions only approved on the basis of need.
Climate Finance
The intention is that International Climate Finance (ICF) contributions increase over the course of the programme to reach 30% by the final year as set out below. The management case below sets out how climate finance results will be monitored in order to ensure compliance with ICF, including which indicators will be included.

	25/26	26/27	27/28	28/29	29/30	Total
% of prog. that is climate finance	2%	22%	28%	28%	30%	21%

FCDO will maintain a risk matrix assessment register that includes financial and fraud risks –draft register in Annex 1. These risks will be reviewed monthly, and mitigation measures will be implemented to ensure that the impact of the risks is minimised. Any fraud allegations will be reported to the fraud unit at the earliest period. All these steps will be in support of a zero-tolerance approach to corruption and fraud. This programme will also be subject to annual reviews and may be independently reviewed by FCDO’s Internal Audit Department. No payments will use government fiduciary systems to minimise the risk of diversion.
FCDO will conduct an updated Due Diligence assessment on all implementing partners as per in the Commercial Case. In addition, we will review all downstream partners to ensure controls are in place and maximises efficiency. Delivery partners will be required to notify FCDO in advance of any changes to the delivery chain map
As part of the delivery plan to track programme controls, FCDO programme management would ensure that the following activities are undertaken:
- Due diligence follow-up actions and reviews
- Audits
- Project visits
- Financial and assets spot checks.
Each component has a designated lead organisation that will be responsible for managing activities, finances, and all kinds of reporting including annual audits. Payments will be performance based, linked to milestones and compliance criteria, and evidence of need for funding. Payment will be in arrears unless there is a demonstrated need for payment in advance. FCDO will undertake financial spot checks at least once a year, supervisory field visits and annual reviews. FCDO will also review annual audited accounts from each delivery partner, as part of its continuous due diligence. All assets bought by NGO delivery partners and a service provider will remain the property of FCDO until the end of the programme. FCDO will then decide whether to hand over or otherwise dispose of these assets. Delivery partners will maintain an asset inventory and report on changes/additions. As set out in the management case a programme funded position is proposed under component 1 to support coordination with the wider foundational learning reforms. This is expected to cost up to £450k over the lifetime of the programme.
Figure 4: Expected funding flows to partners

FCDO funding:
£39 million

4: Implementation science and evaluation
£1.5 million
1: Numeracy and associated foundational learning reforms
£27 million
Sub Contractors
Supplier

2: Building resilience to climate impacts
£8 million
3: Supporting girls’ education
£2.5 million
NGO

Sub recipient
UN Agency

Centrally managed programme

Suppliers including UK academic institutions

## Management Case

Proposed timeline

- Apr 2025 – Completion of roll-out of maths curriculum reform for standards 1 and 2 and procurement of workbooks for the next year.
- Aug/Sept 2025 – Start of academic year with teach training for roll out of maths reform to standards 3 and 4 as well as selection of girls for scholarships.
- April 2026 – Scale up of climate resilience component and support for school feeding with focus on innovation and VfM
- Sept 2026 – Maths curriculum shifts from “roll-out” to “embedding” through a transition to ongoing coaching and professional development as well as focus on complimentary foundational learning reforms.
- Sept 2029 – Focus on sustainability and exit including potential shift to textbooks to replace workbooks.
- June 2030 – Programme closure.

Programme governance and management arrangements

Internal programme delivery will be overseen through the Malawi Country Board which meets quarterly and includes representation from all teams as well as the High Commissioner and Development Director. Just ahead of each Country Board is a Human Development Pillar Board which allows for more in-depth discussions on specific areas of delivery and is attended by the Development Director and Human Development Team. Aspects of compliance will be overseen by a quarterly Programme Board while the components on climate resilience will also feed into the quarterly Climate Pillar Board to ensure coordination across the mission.
Externally the programme will feed into the Foundational Learning Steering Committee led by the Ministry of Education which includes representatives from all of the major programmes contributing to this joined-up approach to improving foundational learning outcomes.

The Senior Responsible Owner (SRO) will be a grade 7 Education Adviser, based in Malawi, reporting to the grade 6 Human Development Team Leader. The SRO will spend approx. 60% of their time overseeing programme delivery, involving other programme and advisory staff as required, especially those in the governance and resilience teams. The Programme Responsible Officer (PRO) will be a programme manager at HEO level working 100% on this programme. The PRO will lead the commercial and financial management, ensuring compliance with the Programme Operating Framework (PrOF) and other corporate processes. The PRO will maintain a robust programme delivery plan to guide this oversight. The team will report on progress and escalate any major challenges to senior management in Malawi at least quarterly through the governance structures noted above.
To support the delivery and coordination of the wider foundational reforms highlighted in this component it is proposed that a programme funded position be utilised who can be at least partly embedded in the Ministry of Education and support the Foundational Learning Steering Committee to ensure that this programme is delivered in a joined-up way with the other relevant programmes focused on literacy, infrastructure, digital, teacher management, district governance and early childhood education. A programme funded role is preferred due to their ability to contribute to government and donor decisions in a way that would be inappropriate for a private supplier to do.

Additional support will be provided by:
- A senior programme manager (at post)
- A 2nd education adviser focused on multilateral coordination (at post)
- A senior commercial adviser, 30% dedicated to Malawi (in UK)
- A senior results adviser, 50% dedicated to Malawi (in UK)
- A social development adviser (at post)
Risk management
The British High Commission (BHC) Lilongwe has strong risk management approach due to the environment in which the commission operates. This programme will have a ‘receptive’ risk appetite across two of its risks; strategy & context and policy & programme delivery operating and a ‘cautious’ appetite for the rest of the four risk categories.
The programme team will discuss risks monthly and escalate any risks operating above the BHC Lilongwe risk appetite to the Development Director for sign-off or further escalation to Directors. Subject to key changes to risk impact and likelihood, risks will be discussed at quarterly programme/partners meetings and the monthly mission strategic risk meeting of the BHC.

Strategy and context: The programme strategy and context risk appetite is ‘Receptive’ within BHC Lilongwe and HQ risk appetites. This is one of the two risks with receptive appetite while the rest of the risks are ‘cautious’. The climate change-induced threats to education, difficult macro and fiscal situation, and increase in hunger in Malawi form the major strategy and context risks. The high risk of increased absenteeism in schools may impact the ability of the programme to improve educational outcomes if children are not in class due to hunger. Given the high population of 5.7m people suffering from food insecurity this year, the gross risk is rated as severe.  Programme will mitigate these risks through programme design that include climate resilient component for school feeding and promotion of community level sustainable agriculture production. FCDO will also implement humanitarian support programme through the World Food Programme and cash transfer programme to mitigate these risks. Residual risk rating will be major.

Policy and Programme Delivery: The programme has a receptive appetite to Policy and Programme Delivery risks, which is within BHC Lilongwe and HQ risk appetite. This links to moderate risks that the quality of the maths reform may not be sustained at national scale due to size of coverage and the teacher training model that may fail to lead to demonstrable impact on learning. From experience in delivering the previous contract, this can be mitigated by working closely with Ministry and under Ministry leadership, having frequent classroom visits to pick up on what the teachers need most, and by having an adaptive approach to managing the contract skewed toward results rather than processes, so that the contractor has the right incentives to surface emerging risks and, together with the SRO, can act on problems. Delivery risk is compounded by challenges in paying Daily Subsistence Allowance (DSA) and tight timelines for supplier procurement. Programme will mitigate these risks by working with other donors to agree a harmonised DSA rate that covers needs while remaining sustainable. The programme will use a contract amendment rather that procurement of a new contract to ensure immediate needs in 2025 are met (as set out in the commercial case). These mitigation measures will reduce gross risk rating from major to moderate.

Safeguarding: The programme has a cautious risk appetite which is aligned to BHC Lilongwe and HQ. Gross risk is major while the residual risk rating is moderate.
There are safeguarding risks of (i) lack of partner capacity related to management of safeguarding; and (ii) fear of reporting; implementing partners do not adequately monitor, report, respond to safeguarding incidents (including sexual exploitation and abuse), resulting in unintended harm to beneficiaries, reduced programme impact, and reputational damage. There is also a risk of girls facing exploitation or harassment from those responsible for the selection of scholarship beneficiaries. Another major risk may occur during teacher trainings. When Master Trainers train teachers in remote locations, teachers can be taken advantage of by the master trainers because of the power dynamics between them.
Mitigation measures include implementing partners use of a transparent, objective criteria for scholarship selection across all levels; an inclusive selection process which involves not only the school-level Bursary Committees but also community stakeholders, especially women. The risk of teacher training abuse will be mitigated by the implementing partners printing posters for every teacher training classroom. The supplier will have to integrate safeguarding issues into trainings, with all master trainers oriented on child protection policies, the role of teachers in safeguarding, protocols on how to behave, how to spot risks and how to react, and best practices through interactive activities. Whistleblowing policies should be embedded within the broader safeguarding policy to encourage reporting.
Financial & Fiduciary: risk appetite is rated as cautious in line with BHC Lilongwe and HQ risk appetite. Key fiduciary risks include: a) the risk that reimbursements for trainings and workshops go to ghost participants, mitigated with the supplier using digital payments released upon verification of presence at the training, monitored through spot checks, beneficiary interviews to ensure process implemented as described, and review of reconciliations, as well as increasing fraud awareness; b) the risk of fraud in procurements of books, mitigated by reviewing procurement procedures of implementing partner; c) the risk that workbooks, provided for free to children, get sold on private markets, mitigated by allowing MIE to print workbooks for sale at their own cost, marking the UKAID supported ones with a “not for sale” mark, and a plan to monitor markets and schools.
Reputational Risk: The programme has a cautious appetite for reputational risk which is within the BHC Lilongwe and HQ risk appetite. There is reputational risk of budgetary changes under the next spending review and ODA cuts which could negatively impact on effective delivery of programme causing reputational damage. These risks will be mitigated through programme design that has considered financing for international climate funds. The BHC in Lilongwe will also ensure careful prioritisation of funds to maintain key activities and build in flexibility in contracts and other agreements to extend length and allow contracted activities to take place over a larger period.

Programme Risks and Mitigations

The overall risk rating for the programme is moderate in line with the risk profile for the five risk categories discussed above. The key risks are set out in the risk register Annex1. FCDO will dedicate sufficient advisory, programme management and leadership team resources to ensure good risk management and oversight. The delivery options selected are designed to mitigate the delivery risks and maximise effectiveness and value for money.

Risk Management Approach

Every implementing partner will maintain a comprehensive risk register in line with the FCDO risk categories. They will provide quarterly updates to the programme risk register as part of their quarterly progress reports. The programme team will escalate any risks falling outside of appetite, in line with the BHC risk escalation policy. The BHC Lilongwe risk appetite statement sets out the level of risk that we are prepared to take against each risk category, to achieve our set objectives.

The programme team will discuss with implementing partners major and emerging risks as a standing agenda item in quarterly meetings. The Human Development team will also discuss every two months major and emerging risks as a standing agenda item. Any risks outside of appetite, and any severe risks, will also be escalated through the SRO. Cross-cutting risks will then form part of the BHC Lilongwe Strategic Risk register and can be escalated to Directorate level through the British High Commission Lilongwe risk lead. BHC risk lead. There will also be opportunities to discuss wider contextual risks at the monthly Strategic risk meetings.
Any risks operating above the BHC Lilongwe risk appetite will be signed off by the Development Director or be escalated to Directors whenever it is deemed appropriate by the High Commissioner.

The BHC Lilongwe safeguarding champion will provide safeguarding training of trainers to implementing partners to train their own staff. All implementing partners will be provided with FCDO’s fraud and safeguarding policies and information on how to report concerns. Reporting of fraud and safeguarding cases will be reviewed in regular programme management meetings as well as the quarterly Programme Delivery Board. FCDO will maintain a risk management approach through regular field visits.

Assessment of climate and environmental risks

This programme is primarily supporting curriculum reforms and service delivery, there is therefore less environmental risks than programmes proposing major infrastructure development. The main impact will come from the nationwide scope of the programme that necessitates working across the country, particularly for the training of over 30,000 teachers. Transporting all these teachers to Lilongwe or other major towns could result in significant emissions. This will be mitigated by holding trainings close to where teachers are located rather than transporting them to major urban centres. Supporting school feeding also has the potential to cause environmental harm due to the use of local wood for fuel, although this is unlikely to be significantly larger than that currently used in households. The use of modern cooking methods will be explored to mitigate this risk including the potential use of solar power in rural locations if the roll-out of solar installations goes ahead as currently discussed with development partners such as the World Bank.

The programme also proposes to work directly on the impacts of climate change on education in Malawi through the provision of school feeding in areas that are food insecure at least in part due to changes in the climate. There will also be support to leverage multilateral funding to build the resilience of Malawi’s education system and the use of small-scale innovative challenge funds at school level to inspire students to develop local solutions and adaptions. These wider interventions may help tackle other risks associated with climate change and environmental degradation including flooding and other disasters. This will be recorded as International Climate Finance (ICF) with the number of beneficiaries tracked and reported on to meet ICF requirements.

Monitoring and Evaluation

Evidence-based decision making will be hardwired in how this programme takes decisions, adapts and evolves. Results will be carefully monitored throughout the programme lifetime and included in relevant implementing partner agreements (commercial contract, Accountable Grant Arrangement and MOU with the UN). The What Works Hub for Global Education component will be part of the steering committee of the programme and identify the key cost-effectiveness opportunities to test, for example through A/B testing. It will include rigorous impact evaluations through randomised control trials where necessary to have a clear sense of attribution for cost-effectiveness. For example, while the mathematics reform was rigorously evaluated, a follow-up can help us understand the long-term impact; we also envision the need for an impact evaluation on how the investment in teachers is affecting learning outcomes through improvements in teaching. The TOR for the commercial contract will require commitment to evidence-based adaptation and a strong, innovative M&E framework to generate timely findings that lead to action, complemented by regular qualitative/ethnographic research to understand how the programme is changing how teachers are teaching or how communities are responding. Monitoring and evaluation should be defining how the programme evolves and not be something done at the end.
[note] For more information on how implementation research through A/B testing can improve cost-effectiveness, see: A/B testing in education: rapid experimentation to optimise programme cost-effectiveness - What Works Hub for Global Education

We will build on synergies for usage of data with other research and other programmes wherever possible, in line with our commitment to institutionalisation and reduced fragmentation. For example, we plan to build on the school feeding impact evaluation results to take decisions on how the school feeding support will be shaped; we plan to collaborate with USAID and World Bank on common, harmonised learning assessments that are institutionalised into Ministry planning to allow outcomes tracking, increase accountability of districts and communities, and help teachers better shape the pace of their teaching and plan remediation lessons.

Research will be a strong component of some of the most innovative components where we don’t have evidence, including the innovation challenge for behaviour change in climate and education. We are currently exploring collaborations with centrally managed programmes and other FCDO-wide initiatives, for example through the Strategic Impact Evaluation and Learning, so that this small component can build global good evidence on climate and education.

Programme management will be guided by agreements defining requirements for reporting and disbursement of funds, and contract will include at least some milestones-dependent payment. Quarterly progress reports will include achievement of agreed milestones, financial management and updated risk matrix. Implementing partners will also submit scheduled financial reports, mostly on quarterly basis and external audits to FCDO as set out in the contract and Accountable Grant. The UN will be reporting semi-annual reports according to their MOU.
Programme level monitoring will be conducted at monthly SRO meetings with in-depth quantitative and qualitative analysis of progress against each component conducted during annual reviews which will be published. Programme monitoring of results will also be conducted using a logframe with annual progress milestones agreed with the partners.

The programme’s VFM plan will focus on:
- A shared understanding of VfM with our implementing and downstream partners. We are currently working with the central team on piloting a framework so that implementers can record unit costs with a common and transparent methodology starting from inception.
- Management of open competitions for all procurements for goods and services by delivery partners to ensure good quality and best value for money. Partners will be selected based on alignment with programme objectives, ability to deliver expected results, and unit costs. We will assess VFM as part of annual reviews.
- All implementing partners will develop VFM strategies to guide VFM.
- For the National Maths Curriculum Reform, we will ensure continuity so that we can track how unit costs and cost-efficiency and effectiveness is evolving over time and across contracts. VFM will be measured on the key cost drivers: procurement and distribution of workbooks, cost of teacher training and programme management costs in the form of fees. Programme will focus on each of these inputs for economy, efficiency and equity.
- All Service providers will be required to develop a detailed VFM framework covering all components and including VFM indicators that are updated as programming decisions are made. The VFM framework will include methodologies of measuring VFM indicators. The specification of VFM measures will depend upon more detailed programme design.
The table below proposes some key VFM indicators- these will be refined with the respective implementers.

VFM measures	VFM Indicator- qualitative and quantitative
Economy	Management costs as a percentage of total budget / Percentage savings achieved against budgeted procurement costs / Assessment of partner procurement system including benchmarking practices. / Average cost per year of keeping a vulnerable girl in school for four years
Efficiency	Average unit cost for standard 1-4 workbooks. / Unit teacher training cost /day. / Unit cost for feeding a child in school / Average cost per scholarship delivered
Effectiveness and cost efficiency	Impact of the mathematics reform on learning assessments, including for the most disadvantaged; reduction in absenteeism and improvement in learning outcomes in school feeding, by gender / Benchmarking of cost effectiveness with similar programmes / Cost per child of increasing effect size in learning assessment / Additional climate financing leveraged by FCDO investment / Improvement in Junior Certificate Exams (JCE) and Malawi School Certificate Exams (MSCE) pass rates / Retention rate of scholarship recipients
Equity	Proportion of children with learning disabilities and in hard-to-reach places reached with the Maths reform and impact disaggregated poverty and disadvantage / Qualitative assessment of how scholarships and mentorship have impacted the most disadvantaged girls / Pass rates between boys and girls in the end of primary exams / Gender and equality assessments of climate and education component

Draft logframe

Impact statement:
More resilient and educated population better equipped to meet the future challenges
Measured through World Bank Human Capital Index (HCI) for Malawi. The programme is expected to contribute to improvements in the Expected Years of School and in the Learning Adjusted Years of Schooling components of the index. The last measurement is from 2020, and we expect another measurement before the end of the next business case. The current level of HCI for Malawi is 0.4, and we propose to target any improvement- even standing still in a situation of stagnant funding and growing population growth is a positive outcome.
[note] See https://databankfiles.worldbank.org/public/ddpext_download/hci/HCI_2pager_MWI.pdf

Outcomes:
More children, especially the disadvantaged, are gaining the basic education they need to get out of poverty and be more resilient
- Improvements in foundational learning outcomes, gender disaggregated: The goal for the first year will be to have agreed and conduct baseline survey for a measure of literacy and numeracy with Ministry of Education as the common measurement,and have agreed on targets. For mathematics, the percentage of children in grade 3 or 4 without mathematics foundations should decrease from 87% to 67% in the five years of the programme. If baseline shows a different baseline (rather than 87%), the target will be adjusted. There should be a second outcome sub-indicator on reducing the percentage of children who score a “0” in the assessment.
- Reduced absenteeism in the first four years of primary school, nationally and in the schools receiving UK-support school feeding FCDO: Agree with Ministry of Education how to count absenteeism and establish targets for reduced absenteeism. The most promising route is through surprise visits by inspectors. In the schools receiving UK-supported school feeding, absenteeism should be measured with more precision and representativeness.

Outputs:
Component 1: Mathematics Reform and Foundational Learning systems strengthening

  1. The curriculum is implemented with fidelity and quality in the classrooms
- Students in Std 1-4 have access to a teacher trained in delivering the National Mathematics Curriculum Reform and to a workbook to follow the classes.
- Teachers are implementing the curriculum with fidelity and quality
- Children are making progress in their understanding of mathematics based on classroom observations, review of the workbooks, and assessments
- Children with disabilities and special needs have access to quality adaptations and trained teachers
- Teachers are improving the quality of their lessons through TLCs, peer-mentoring, and other forms of decentralised CPDs
  1. Teachers in pre-service training- - including those specialising in children with special needs- are demonstrating understanding and proficiency in the new curriculum
  2. Districts, schools and communities are taking action to improve foundational learning of all children, including the most disadvantaged and the ones with disabilities and showing a shift towards prioritising foundational learning, including a shift to more women-led school management
  3. Role models are improving girls’ attitudes around mathematics and their aspirations
  4. Through dedicated demand-led Technical Assistance to the Ministry, Foundational Learning results agreed with Ministry and partners - including on teacher management and distribution, learning assessments, remediation, and professional development for teachers- are achieved in a verifiable way

Component 2: Building climate resilience of education system

2.1. (Year 1 and 2 only): A hybrid, adapted model of the home-grown- school feeding is developed and piloted together with an expansion plan for community-contributed school feeding that is climate-sensitive
2.2.	Primary school Children in food insecure communities are receiving daily and nutritionally diverse feeding through the selected model (number of children reached will be tracked and reported as part of ICF requirements)
2.3.	By the end of year 4, additional climate and education funding is secured as a result of UK-investment
2.4	Innovation challenge for school is set up together with Director of Science, Tech and Innovation and happens yearly with participation of at least 50% of primary and secondary schools
2.5.	The innovation challenge brings change in understanding of relevant climate adaptation and action-based initiatives from school students

Component 3: Supporting girls complete secondary school

  1. Girls supported with secondary scholarships and mentorships remain in school.
At the end of four years of support, a minimum of 70% of girls should have completed four years of secondary, the majority of which without having to repeat a year.

Component 4: Implementation Science and evaluation

  1. Through the supplier, a set of research questions, ways of working, and strong investigators both international and local have been identified
  2. The component is able to identify cost-effectiveness savings of at least the amount invested (£1.5m)
  3. The component is contributing to Malawi evidence-based decision making in demonstrable ways

Longer term sustainability plan

The Maths Reform, Climate resilience and feeding programmes will implement a sustainability plan from the inception phase to ensure government takes ownership and that the reforms do not create parallel structures that stop to exist after programme closure. A major cost of the programming is the cost of workbooks, which is a recurrent cost that the Ministry cannot sustain. During the programming the cost is justified because the ambition is to transform teaching, and the workbooks help with implementation of the new curriculum and with ensuring that teachers build time for independent learning and thinking into the class. The plan is to transition to a textbook version of the workbook using evidence, and test through implementation science the smoothest way to transition once the behaviour change of teachers is cemented. Communities and parents will be involved in the programme to ensure workbooks are well taken care of to the end of every school term and calendar, collaborating with other partners including USAID. Sustainability of school feeding is difficult, especially for the most insecure communities. Nonetheless, the Technical Assistance will be dedicated to dramatically lowering the cost of school feeding and finding innovative financing to help with sustainability, for example through local production of food, innovative school-level financing, or switch away from hot meals to drastically cheaper snacks among others.

Beneficiary Engagement

BHC Lilongwe engaged beneficiaries in the design of this programme, in particular students and girls as well as the Malawi Ministry of Education both at directorate level and also with the Secretary for Education. This helped inform the priorities to be addressed and how the UK can best achieve the objectives set out in this business case. Programme implementation will involve getting beneficiary feedback for transparency, throughout the programme cycle including during monitoring visits and at annual reviews, to test key assumptions, assess quality of implementation, identify risks and offer a valuable sense check on programme activities. This will include reaching out to beneficiaries from marginalised groups such as people with disabilities. FCDO will ensure the protection of information that beneficiaries share about others and themselves.

Commercial management

This is likely to be a silver level contract for FCDO given the scale of the component with appropriate commercial management in place. The programme manager will have undertaken the relevant commercial training and will be supported by a commercial manager based in the UK.

END