Business Case – August 2024

Summary Sheet

Portfolio/ Business/Country Plan Summary / The Nigeria Strategic Roadmap aims to deepen and broaden the UK-Nigeria partnership based on the economic reforms of President Tinubu and recent development, diplomacy and defence efforts by British High Commission (BHC) Nigeria teams. The UK has a solid foundation on which to build, including a decades long development partnership, and more recently annual bilateral dialogues on: Security and Defence; Migration, Justice and Home Affairs; and Economic Development. / The roadmap identifies potential areas for enhancing our partnerships. We will need to do more work a) in response to the government’s priorities, as they become better defined, and b) taking into account resources from Foreign Commonwealth and Development Office (FCDO) and partners across His Majesty’s Government (HMG). In economic development, the government is making potentially transformative decisions on the economy, creating major opportunities for growth in trade and investment. We will need to step up our economic policy and programme engagement to retain UK influence.

Title: Nigeria Economic Stability and Transformation Programme
Programme summary / The Nigeria Economic Stability and Transformation Programme (NEST) aims to increase the chances that the Nigerian government creates the conditions for higher, sustained growth. Without this programme as part of a wider UK effort, there is a higher chance that a rare opportunity to reset economic management in Africa’s largest economy will be missed. / A new bilateral economic reform programme will demonstrate partnership by responding to the Government’s priorities. Managed in-country, it will provide a platform for the UK’s economic development offer, and enable the programme to respond to changes on the ground in a calibrated, politically smart way. / NEST is part of a coherent UK offer on economic reform that includes a Nigeria window of the Public Finance Resource Centre, and partnerships between His Majesty’s Revenue & Customs (HMRC), Bank of England (BoE), Office for National Statistics and their Nigerian counterparts, as well the UK’s independent Institute for Fiscal Studies. / This programme will have three main themes: / Assisting the machinery of Government to stabilise the economy, mitigating negative impacts on poor and vulnerable people; / Nudging policy making to support growth and economic transformation including diversification away from oil and gas; / Contributing to UK’s global growth, trade and investment objectives.
What is the rationale for UK Aid spending / If Nigeria were to achieve its economic potential, it could become the 21st largest economy in the world by 2050. But on the other hand, if Nigeria fails to unlock high and sustained growth, the country instead risks becoming home to the world’s largest number of poor people. Progress against Sustainable Development Goals in the region and globally will be much harder without stability and growth in Nigeria. / The international community can play a part in supporting Nigeria achieve its economic goals. The period covered by NEST (October 2024 to September 2029) is critical for Nigeria’s economy and people. Attempts to reform the economy have historically been few and far between. The policy decisions of the current Nigerian government early in its political term show a serious intent to reset the economy. But the economy it inherited had deep distortions and vulnerabilities. Already-high inflation has been stoked further by necessary reform measures adding to cost of living pressures and a food crisis. There is a risk that the current reform window will close due to pressures to change policy direction. / Improved economic stability and growth would significantly improve the outlook for most – if not all – HMG Business Plan objectives and official development assistance portfolio results in Nigeria. Sustained economic growth will increase Nigeria’s ability to fund development priorities, create jobs and help raise living standards. Lower inflation and improved forex availability will address the biggest constraints to private sector investment and trade. Establishing a market-based exchange rate is a longstanding, high-level objective in the Nigeria Business Plan. / BHC Nigeria has historic capital in supporting economic reform in Nigeria and HMRC and BoE have recently engaged. Progress will be welcomed by UK investors and underpin the UK-Nigeria Enhanced Trade and Investment Partnership. The UK plays a valued role, supporting reforms in public and private, and engaging with International Financial Institutions. / A new bilateral economic reform programme will demonstrate partnership by responding to the Nigerian Government’s priorities. Managed in-country, it will provide a platform for the UK’s economic transformation offer, including British Investment Partnerships and Centres of Excellence, and enable any drop-off in reform appetite to be handled in a calibrated, politically smart way.
Programme Value: £4.9 million		Country/ Region or Sector: / Nigeria
Department/Country Office confirmation of review processes		The Business Case has been approved by BHC Nigeria’s Delivery Board (13 August 2024) and shared with the Country Strategy Board (3 September 2024)
Contact name		Stuart Tibbs (Senior Economist and programme SRO)
Threshold for final approval of Business Case: / Head of Mission / British High Commissioner to Nigeria and HMG Nigeria Country Strategy Board
Date of Approval of Concept Note:	04/09/2024	Cynthia Rowe, Development Director
Date of Approval of Business Case:	04/09/2024	Richard Montgomery, British High Commissioner
Programme Code:	AMP Start Date / 01/10/2024	AMP End Date: / 30/09/2028
Overall programme risk rating:	Major
[note] Department for Business and Trade, Country Factsheet

## Strategic Case

Rationale
The pattern of Nigeria’s growth in the 21st century
1. Nigeria’s economy underperforms against its potential and against Middle Income Country peers with consequences for jobs, poverty and development, as well as for Nigeria’s standing as a global market, producer and investment destination.
2. Nigeria’s economic growth has been particularly volatile in the last 25 years. There have been periods of growth, but these haven’t been sustained or broad-based enough to create jobs on the scale needed. Table 1 below shows rates of growth of the economy, population and Gross Domestic Product (GDP) per capita for three periods since 2001.
  [note] Data and narrative drawn from World Bank Country Economic Memorandum 2022
Table 1: Phases of economic growth and stagnation in Nigeria since 2001

Several features of Nigeria’s growth in this period stand out:
- The first decade of the 21st Century saw relative macroeconomic stability and openness to investment. New investment in high-value sectors, especially finance, and information communication and technology (ICT) contributed to diversification of the modern sector of the economy.
- The economy is highly dependent on oil and gas as these dominate the fiscal and external accounts (around 50% of tax revenues and 90% of export earnings). Even when global oil prices were high (2001-10), the resulting increases in revenue weren’t used well; windfalls haven’t been saved and used to cushion subsequent periods of low oil prices, notably in 2016 then – as Covid hit – in 2020. Neither have fossil fuel proceeds been used adequately to invest in economic and social infrastructure to boost productivity and future growth.
- Furthermore, the benefits of rapid growth have been concentrated around Lagos and some other urban areas. Periods of growth supported by higher oil prices have led to consumption boom around cities rather than resulting in a production boom. The biggest change in the distribution of work during booms is a drift from low productivity agriculture to low productivity services work. Many of the new jobs created during periods of oil price-led growth are low earning, informal, temporary or unsafe.
  [note] Rents from resource exports increase domestic demand for urban goods and, especially, nontradable services, without increasing the share of manufacturing or services in production or exports (Urbanization With and Without Industrialization, Gollin, Jedwab, and Vollrath 2014)
1. The consequences of low and volatile growth and of the rising cost of living are far reaching. Price shocks, particularly high inflation since 2020 has shown how improvements in living standards can be quickly eroded by rising cost of living. Based on data from the latter part of the previous government, the World Bank estimated that 4 million people were pushed into short-term poverty due to higher-than-expected inflation during the five-month period of January to May 2023.
2. Even when growth occurs in Nigeria, it does not lead to as big a drop in poverty as in more diversified economies. Each 1% increase in GDP per capita leads to only a 0.6% decline in poverty. This the value of this coefficient linking the change in economic growth to poverty in Nigeria is just half the value of the coefficient for all Sub-Saharan African countries, and just one quarter that of other lower middle-income countries. High inflation erodes purchasing power.
3. 3.5 million young Nigerians currently enter a labour market each year in which only 17% will find waged work, more than half of which is in the public sector. Most people find unproductive, low earning or unsafe work. This is a low base of formal, waged private sector jobs. High, sustained private-sector led growth for more than a decade is needed for waged jobs to be widely available. At the same time, the productivity and quality of unwaged work needs to improve as most Nigerians will need see their economic well-being raised through more productive work in the informal sector – whether in agriculture, off-farm work in rural areas, or through service and industry roles in cities.
The task involved in resetting Nigeria’s economy
1. Economic management in Nigeria has tended to ensure that financial crises are averted, but little more. In 2016, 2020 and 2022 policies were adjusted sufficiently to address liquidity risks, but not to reset the economic policy framework so as to build up macroeconomic resilience and lay the basis for sustained growth. In the eight years prior to 2023, the economy had been heavily distorted by the overextended role of the central bank and flawed attempts to control inflation and maintain exchange rate.
2. President Tinubu’s Renewed Hope agenda has the economy at its centre and the government has shown it is prioritising the economy. The starting point in May 2023, was extremely difficult: inflation had reached 22% despite price controls, forex was scarce and revenue and debt indicators were worsening. There had been no positive movements in the assessments of credit ratings agencies between 2015 and mid-2023.
3. The new government tackled two major policies early on – the fuel subsidy and exchange rate. The government has stated commitment to attracting investment and private sector thinking evidently characterises some of new policy making.
4. Markets responded positively to the new direction. The Ministry of Finance is prioritising fiscal responsibility and increasing tax revenues. The CBN has shown that it is giving primacy to the objective of tackling inflation. In the second half of 2023, Standard & Poor and Moody’s both improved their ‘outlook’ for Nigeria’s sovereign debt.
5. The government has reached out to international financial institutions (IFIs) for budget support to back macroeconomic and structural reforms. A $1.5bn loan from the World Bank and a $500m loan from the African Development Bank had been approved and disbursed by mid-2024.
6. Implementation of reforms has been uneven. Comprehensive reform is complex to implement requiring coordination across economic institutions and between executive and legislative arms of government. This is especially true in a federal country like Nigeria. Powerful vested interests also resist reforms. Policy capture by vested interests and corruption especially in the oil sector continue to hold the economy back.
7. Windows for reforms can be narrow and success is not guaranteed. In Nigeria, the immediate impact of subsidy removal has been to deepen a cost-of-living crisis that was already biting. Early economic successes have proved difficult to communicate to the public, partly because many are technical (exchange rate unification, tax revenue increases). Economic factors have combined with other factors leading protests in mid-2024.
8. Nigeria needs to find its own economic strategy – or recipe – for high, sustained growth based around stability, transformation and diversification; these features are important for the growth process itself to be sustained, as well as for growth to be more inclusive. Economic management then needs to be reset to lock-in economic stability while also laying the groundwork for investment and broad-based economic growth.

Nigeria’s economic growth and the UK
1. Nigeria’s economic development is a central tenet of the UK’s Global Middle Ground Roadmap. The Nigerian economy and its management is important for numerous UK equities: UK investors need a sound economic environment; sustained, inclusive growth is needed to reduce poverty; higher tax revenue collection – especially by federal institutions – are required to fund health, education and climate-resilient infrastructure adequately even where these are primary responsibility of state governments; economic diversification is needed to reduce dependence on fossil fuels; and improved livelihoods and economic governance could reduce opportunity and incentive for conflict and instability.
2. Globally, Nigeria is prominent in international fora on issues such as tax cooperation, energy transition and trade – issues for which developing country voices are important to the UK. Nigeria projects its views in UN and OECD contexts as part of its economic and wider foreign objectives. If the UK remains a credible partner to the government on its domestic economic issues this could help UK’s global objectives where Nigeria’s voice is significant.
The role of the UK within the international community in supporting Nigeria’s economic growth
1. The UK has historic capital in supporting economic reform in Nigeria. The UK supported the establishment of two of Nigeria’s most effective economic institutions – the Debt Management Office and Nigerian Sovereign Investment Authority. There is strong interest in UK institutions – HMRC, BoE and the Office of National Statistics have embarked on focused partnerships with their Nigerian counterparts recently. UK aid has also been valued for its responsiveness, its focus on institutional strengthening and governance and its flexibility to dovetail with larger donors. Recent infrastructure and oil and gas governance programmes have fit this mould.
  [note] Infrastructure – the UK Nigeria Infrastructure Advisory Facility (UKNIAF), and for oil and gas – the Facility for Oil Sector Transparency and Reform (FOSTER).
2. However, the UK, in common with other development partners, has had minimal engagement on macroeconomic issues with FGN in recent years. Between 2010 and 2020, the Policy Development Facility (PDF) supported FGN institutions on economic issues, with support extending to the Office of the Vice President, the CBN, the Nigeria Office for Trade Negotiations, the Ministry of Finance (MoF), Federal Ministry of Industry, Trade & Investment (FMITI), the Presidential Enabling Business Environment Council (PEBEC) and others. Due to insufficient macroeconomic reform appetite, the PDF was not succeeded by another programme. But the reform effort started in mid-2023 provides a fresh impetus for UK support to economic stability and growth.
Objectives of the new programme: fit with the portfolio and expected impact and outcomes
1. The new programme, NEST, will form part of a new portfolio of UK ODA to support growth and economic stability. The other elements of the portfolio include:
  1. A £7.5m Nigeria window within the Public Finance Resource Centre, an FCDO centrally managed programme (CMP), which will support tax and public financial management. This window is called the Nigeria Public Finance Facility.
  2. The Centre for Tax Analysis in Developing Countries (TaxDev), a CMP implemented through a partnership between the Institute of Fiscal Studies (IFS) and the Overseas Development Institute (ODI) to support the use of evidence in tax policy formulation.
  3. A peer-to-peer partnership between His Majesty’s Revenue and Customs (HMRC) Capacity Building Unit and the Federal Inland Revenue Service (FIRS) on issues including international taxation and data governance.
  4. A partnership between the Bank of England’s Centre for Central Banking Studies and CBN, under the Global Finance Programme CMP.
2. NEST will be managed from BHC Nigeria would also demonstrate partnership through responding to the new Government’s priorities, increase the chances of higher quality reforms being sustained and also provide a platform helping to bring together the UK’s overall offer on economic development. An in-country programme will also enable BHC Nigeria to respond effectively to any drop-off in reform appetite in a calibrated, politically smart way.
3. The overall objective of NEST is to increase the chances of economic reforms that started in mid-2023 being sustained and to improve the quality of these reforms, helping to create the conditions for higher, sustained growth. Goal level objectives are to contribute to improved economic indicators such as:
- Reduced inflation and improved monetary policy and exchange rate management
- Increased private and development finance
- Improved leading indicators of economic diversification towards non-oil sectors, in terms of new investment and trade, with the UK and others
- Additional IFI finance unlocked in support of macroeconomic and structural reforms.
15.	Outcome level objectives will include improved capability to implement economic reforms, and deeper ownership of reforms, with NEST attribution to strategies, policies and their implementation in some of the following areas:
- Economic growth plans and their implementation
- Improved macroeconomic modelling and use of forecasts in economic policy formulation
- Monetary, exchange rate and financial policies and implementation capabilities
- Structural reforms relating to trade policy and facilitation and business environment reforms
- Investment vehicles for international and domestic savings
- Poverty and social impact analyses of reforms.
Required assurances
Counter Terrorist Financing and Anti-Money Laundering
1. Nigeria has an extensive illicit economy linked to extremism, conflict and trade in drugs and weapons. The country is also currently ‘grey listed’ by the Financial Action Task Force (FATF) and the authorities are seeking to strengthen anti money laundering (AML) and counter terrorism financing (CTF) systems with a view to exiting the list. Nigeria’s economy is home to significant levels of cryptocurrency trading; the government is moving towards a regulated crypto market to manage the challenge it presents, including to macroeconomic management.
2. NEST will be available to support a well-functioning forex market if there is demand and a role for the UK vis-a-vis other international partners. This would support the enabling environment for AML/CTF. The programme could also support specific AML/CTF actions and/or crypto regulation, subject to demand and prioritisation.
Public Sector Equality Duty
NEST complies with FCDO policy on Public Sector Equality Duty in the Equality Act 2010, with respect to age, disability, gender reassignment, pregnancy and maternity, race, religion or belief, sex, and sexual orientation. The commercial agreements with implementing partners will require them to (1) eliminate unlawful discrimination, harassment and victimization; (2) advance equality of opportunity between people who share a protected characteristic and people who do not share it; and (3) foster good relations between people who share a protected characteristic and those who do not share it.
Climate and environment
1. Nigeria is Africa’s second largest emitter of greenhouse gases. Nigeria is also highly vulnerable to climate impacts, especially from flooding and desertification. Population growth, economic growth and industrialisation and urbanisation, risk locking Nigeria in to a hard-to-alter, high emissions pathway. Nigeria’s Revised Nationally Determined Contribution (NDC) targets net zero by 2060. However, there is limited political championing of climate change at the moment due to competing challenges.
2. Economic stability and growth will attract new investment including for climate mitigation and adaptation. This should have a positive impact, for instance on access to renewable energy. But the Tinubu government is also clear that it intends to use Nigeria’s gas resources to support economic growth and to improve performance against the majority of Sustainable Development Goals.
3. NEST will work closely with other targeted UK programmes to support Nigeria to manage its energy transition and improve access to finance for resilient infrastructure. NEST is not expected to count/ contribute towards International Climate Fund (ICF) targets, but throughout implementation, opportunities to count resources as ICF will be explored.
Disability and Meaningful Engagement of Organisations for People with Disabilities
1. NEST focuses on macroeconomic and structural reforms. If successful, these reforms could avert poverty by ameliorating cost of living pressures, and in the longer term, lift people out of poverty through sustained, inclusive growth. However, the benefits and costs of economic reforms are rarely neutral. It is important that Nigerian policy makers take into account the differentiated impact of economic reforms on the poor and vulnerable which may disproportionately include women, disabled and other groups.
2. TaxDev and potentially the Public Finance Facility (see para. 19) will support Nigeria’s poverty and social impact assessment capability of tax and spending decisions. UK work to support social protection as a tool to mitigate impacts of reforms on vulnerable people will also consider those with disability. NEST will similarly explore opportunities to strengthen non-fiscal areas of policy formulation and implementation.
Safeguarding
1. Implementing partners will be required to demonstrate that they are applying adequate measures to provide safeguards against Sexual Exploitation, Abuse and Harassment risks in their operations e.g. with their own staff and with stakeholders they engage with. The safeguarding risk to vulnerable individuals through the direct activities of NEST is very low in a programme of this nature.
2. It is well known that there can be short-term negative impacts of critical economic reforms on people, including the poor and vulnerable. BHC Nigeria will continue to ensure that the Nigerian Government, World Bank and others seek to mitigate the impact of reforms through a well-targeted social safety net programme.
Risk
NEST will proactively manage risks in line with FCDO global policies and within Africa Directorate and BHC Nigeria’s risk management systems. The Management Case sets out the approach and preliminary risk register for NEST.

## Appraisal Case

The appraisal case sets out the evidence for key design options considered, and distinguishes between the options. The structure of the appraisal case is as follows:
1. Summary of relevant evidence needed for creating a NEST design and implementation
2. Indicative activities that the programme will do and channels for delivery
3. Success criteria for selecting the best delivery option
4. Options and assessment against success criteria
5. Description of how the preferred option will work and theory of change (ToC)
6. Description of how value for money (VfM) will be assessed throughout the life of the programme
7. VfM statement

Summary of relevant evidence needed for NEST design and implementation

NEST aims to support Nigeria lay the basis for higher future growth. To be effective, programme design needs to take into account evidence on: a) determinants of high, sustained economic growth in developing countries and policies to support them; b) political economy constraints to policies for growth; c) effective international contributions to supporting policy reforms for economic growth; d) the mutual contribution of economic growth in Nigeria and UK to each other’s economy; and e) choices of depth and breadth in programming under budget constraints.
Determinants of high, sustained, inclusive growth
1. In an accounting sense, economic growth corresponds to how quickly a country’s labour supply and capital stock grows, and how productively it uses this labour and capital. But how long it takes to increase resources and increase productivity varies widely.
2. There is convincing global evidence of the broad corollaries of high and sustained growth. The economies that transformed in the second half of the 20th century used variants of the following five ingredients to a significant extent in their individual recipes for growth: promotion of economic stability, encouragement of investment and savings, credible commitment to growth and capable institutions, market-orientation, and openness – especially the use of deep world markets on a country’s own terms.
  [note] Growth Commission 2008 Spence et al
3. Transformation also plays an important role in enhancing growth and reducing economic volatility. Economic transformation is a positive process of resources – people and capital – shifting between firms, sectors and locations to ever more productive uses. Effective policy measures for accelerating structural transformation often come in “waves” and aim at exploiting the evolving comparative advantages of the economy. When effectively implemented, policies result in improved infrastructure and trade networks, investment in human capital, financial deepening, and reduced barriers to entry for new products. But there is no one-size fits all recipe.
  [note] IMF Sustaining macroeconomic stability and growth in LICs 2014
4. The role of industrial policy – meaning a significant degree of state direction in shaping the pattern of growth, e.g. by prioritising sectors or locations – is a recurring theme in the search for accelerated growth and transformation. Its role in countries’ successes and failures is disputed. Rapid transformations in East Asia between the 1950’s and 1980’s have been explained by some in terms of ‘following the market’, but in terms of ‘governing the market’ by others., There are risks and opportunities from both approaches; finding the best balance for a particular country based on economic and political economic factors is important. A recent International Monetary Fund (IMF) survey of industrial policy concludes that when it works, it can work well, but the governance and institutional requirements for successfully steering the market are high.
  [note] East Asian Miracle, World Bank Public Policy Research Paper, 1993
  [note] Alice Amsden, Asia’s Next Giant 1992, on Korea
  [note] Robert Wade Governing the Market, 1990, on Taiwan
  [note] Industrial Policy is back, but the bar to get it right is high IMF blog on industrial policy and IMF surveillance.
5. Diversification, a related concept, is similarly important especially for Nigeria’s economic stability and growth. An estimated 30-35% of Nigeria’s GDP is linked to the oil and gas sector and constitutes a significant share of the formal economy. Nigeria is diversifying to an extent; high value service sectors based in Lagos such as IT and finance have made strides since the episode of liberalisation in the 2000’s. But much of the diversification from agriculture to services has not led to economic stability and growth; for instance, jobs have moved from low productivity activities in one sector to low productivity in the other.
6. Studies of Nigeria’s economic transformation and diversification suggest broadly that a successful recipe in Nigeria would have the same basic ingredients that have worked in other success stories. For instance, an Overseas Development Institute study of economic transformation drew the following lessons from other countries’ experiences for Nigeria:
- Even for the largest economies, international competitiveness has to be the goal and yardstick of success if the productivity gains of economic transformation are to be realised.
- Investments in infrastructure and, especially middle-range, skills are vital.
- Firms or sectors identified as potentially competitive internationally should [only] receive government support that is linked explicitly to their export performance.
1. An IMF paper on diversification in Nigeria drew similar policy conclusions and furthermore specified agriculture, the digital economy, energy and transport as sectors that could drive future diversification and productivity gains. These findings are high level. A 2016 African Development Bank paper went further than most by exploring promising growth paths and products based on success in similar contexts. But even here the basic ingredients were fundamental to the recipe.
  [note] Diversification of the Nigerian Economy, IMF Selected Issues Papers 2021
2. Implications for NEST:
NEST should adopt an evidence-based approach to supporting Nigeria’s economic growth strategies, encouraging decision makers to draw on relevant lessons of what has and hasn’t worked in Nigeria and elsewhere
Political economy of growth – beyond stabilisation
1. Nigeria’s economic managers have always done enough to stabilise the economy. But they have not done enough to diversify or transform the economy, sufficient to achieve a high and sustained growth path. Policymaking by successive Nigerian governments has been oriented towards short-term crisis management of macroeconomic stabilization, restoring modest growth and selective public sector reforms. Policy making has lacked the proactive economic foresight and planning required to cushion the effects of unforeseen contingencies, such as economic shocks occasioned by fluctuations in oil prices.
  [note] World Bank Country Economic Memorandum, 2022
2. To diversify Nigeria's economy, successive governments must reorient towards a consistent focus on pro-productivity and pro-poor policies, alongside comprehensive civil service and security sector overhaul. The first decade of the 2000’s was a period of economic stability and some growth when better economic policy making was eased by the breathing space afforded by stronger oil prices. However, even during this period, deep structural problems with the economy were left unaddressed; there was limited economic diversification or reduction in poverty.
  [note] Economic Diversification in Nigeria, Zainab Usman 2022
3. Nigeria’s economy is relatively ‘closed’, and this inhibits increased investment and productivity. Institutional factors play a part in the persistence of obstacles to trade, such as the efficiency of the Nigeria Customs Service and of port management. Furthermore, a small number of ‘big players’ in industries are able to excise a strong influence on the detailed design of trade and industrial policies. Where protective policies create rents, these rents do not finance learning and technological upgrading but can underwrite inefficient production processes – the opposite of economic transformation.
  [note] Supporting Economic Transformation in Nigeria, Overseas Development Institute 2016
4. The election cycle is also important for understanding the political economy of reforms. Liberalising reforms benefit an economy, but the benefits materialise only gradually over time. Voters seem to conflate current economic conditions to reforms without fully internalising the delay it takes for reforms to bear fruit. The Tinubu government took major decisions very early in its term, which evidence suggests is a better time to do them than just before an election, especially when economic growth is weak.
  [note] Structural reforms and elections, Alesina et al 2020 NBER Working Paper
5. Broad public understanding of the necessity of reforms is recognised as important for policy is sustainability. Specific global evidence relating to successful fuel subsidy removal emphasises the importance of formal and frequent public announcements of price changes and that these changes are explained in terms of market conditions, rather than policy makers’ decisions. Although communications can never be a substitute for good policies, economic reforms are more likely to fail or even be reversed if they are not understood or accepted by those whom they affect.
  [note] Kojima, Masami. Fossil fuel subsidy & pricing policies. WPS 7531, Policy Research working paper, World Bank
  [note] Frontiers of Economic Policy Communications, Stankova, IMF 2019
6. Implications for NEST:
- Thinking and working politically: for instance, i) where possible supporting in a way that extends the time horizon of policy making, ii) being aware of the political cycle
- NEST should find opportunities to support Nigeria to strengthen communication on economic reforms. This is important for communicating the rationale and benefits for policies with the initial goal of stabilising the economy (tighter monetary policy, removing the fuel subsidy etc). It is also important for explaining how policies are intended to lead to inclusive growth – increasing the number of better jobs, and spreading the benefits of growth geographically in Nigeria.
- Create a space for Nigerians to think about the country’s economic future, developing a shared vision for transforming the Nigerian economy.
What works when it comes to donor intervention
1. An FCDO review of international support to economic reforms, found that interventions varied widely in their effectiveness, ranking from highly effective to largely ineffective.
  [note] Economic Development Best Buys, 2018
2. At the highly effective end of the spectrum, international engagement which is judged to have contributed to a wholesale change in a country’s economic ideology, would be highly valuable. A classic case is the role of international ideas in contributing to India’s liberalisation either side of 1990. Nudging the political consensus in Nigeria towards longer-term economic decision-making that supported sustained growth, would indeed be a major contribution.
3. At the other extreme, providing technical assistance where there is neither high level political support nor institutional ownership, is largely ineffective. For instance, business environment reforms that focus solely on increasing rankings in international league tables, or which focus on legal changes and not implementation, are likely to have minimal impact. However, where there is political support for reforms which address real, binding constraints, technical assistance can be effective.
4. The FCDO review emphasises that what matters most is domestic ownership and leadership; there needs to be a genuine political constituency for reform. Success requires engagement by skilled and long-term advisers, and relationship building.
5. BHC Nigeria’s experience resonates with this evidence. Some of the strongest FCDO programmes have taken a ‘thinking and working politically’ approach. Programmes such as the Partnership to Engage Reform and Learn (PERL) and FOSTER have been at their most effective when combining strong political analysis, insight and understanding; detailed appreciation of the local context; and flexibility and adaptability in program design and implementation.
6. Financial aid can reinforce policies that government wants to do; ‘at the margin’ it can tip choices. The key is that there is significant policy alignment between donors and the government. The World Bank and African Development Bank are providing significant financial aid (budget support) in recognition of Nigeria’s initial reform measures, and to support further steps. There is a broadly good alignment between the international community and government. However, consultation, communication, decision-making and policy implementation, is still difficult, even if high level ‘political will’ is there. UK aid has the flexibility to be used support advocacy, building out from existing reform champions, to engage important wider stakeholders.
  [note] The Future of Financial Aid, DFID/FCDO internal, Dercon & Lea, 2017
7. Implications for NEST:
- The success of the programme will depend on high quality support, well-coordinated with other parts of the international development offer.
- NEST should reflect the UK’s relative strengths to others including: programme design that is responsive to good ideas that arise; accepts higher external context and delivery risks; and is flexible e.g. design can flex based on need – long-term or short-term technical assistance, support change management, or engender broader stakeholder engagement.
- Draw on BHC’s experience in Nigeria from programmes such as PERL and FOSTER and build into design an ability to ‘Think and work politically’.
Mutually beneficial growth opportunities for Nigeria and the UK
1. A range of FCDO evidence reviews between 2012 and 2022 have looked at some of the channels by which development, investment, trade and growth in developing countries benefits the UK.
2. Growth in developing countries is good for the UK. High rates of growth and poverty reduction in developing and emerging economies offer opportunities in terms of increasing UK exports and investment. Global growth has been increasingly taking place outside the OECD. UK Aid is contributing to this by creating the conditions and opportunities for growth in UK exports both directly and indirectly, although there are some legal and policy rationale for not going further.
  [note] Growth in developing economies is good for the poor and good for the UK, Dercon & Lea, 2012
3. The relative size and high growth rates of middle income countries (MICs) has meant that large MICs have been the main drivers of world economic growth over the last two decades. Much of the mutual trade and investment benefits have come from China, India and Upper Middle Income Countries in Asia and Latin America.
  [note] How does UK Aid benefit the British Economy? Chief Economist’s Office and Business Change and Strategy Dept 2013
4. Nigeria’s population is locked in to grow to become the third largest in the world by 2050. Some ultra-long term forecasts project that Nigeria will move from around the 40th largest economy in the world at present, to approach the world’s top 20. But this economic future is far from guaranteed, without significant changes in economic management.
5. UK imports from Africa are mutually beneficial. Imports from developing countries are a crucial component of the health of the UK economy. Imports lead to greater product choice and lower prices for UK consumers, which has a more pronounced benefit for low-income households. Being able to source low-cost intermediary goods and services from abroad increases the productivity and international competitiveness of UK businesses which, in turn, supports job creation and raises wages for UK workers.
  [note] DBT global forecasts project that Nigeria could be the world’s 21st largest economy by 2050
6. Nigeria is the top tech startup hub in Africa. The UK, as the third largest Tech ecosystem in the world and largest in Europe is the ideal destination for Nigerian high growth start-ups looking to raise capital, scale up and establish a presence in the UK as a springboard for international growth. There is potential for high value inward investment to the UK funded from Nigerian capital, supporting UK policy priorities such as Net Zero.
7. Most of these areas require addressing market access barriers. The Venn diagram of measures that would benefit Nigeria’s investment environment and benefit the UK’s would overlap markedly – not least because Nigeria would be able to increase trade and investment with all countries in the world.
8. ODA also benefits UK growth through non-economic channels (although non-economic sectors like health and education are increasingly important sectors for UK trade and investment). ODA reduces the chance of an epidemic hitting the UK through two channels: it helps contain the epidemic and reduces the chance of deadly mutations. ODA investment in conflict prevention tackles the root causes of conflict and fragility and if successful in fragile and conflict affected state such as Nigeria would save billions.
  [note] What has ODA ever done for us? Glennester, Rudge, Trinci, 2018
9. Implications for NEST:
NEST should supplement the BHC’s capability as a platform to enable Nigeria to get the best from its mutual growth, trade and investment partnership with the UK.
Focus – breadth vs depth, and choice of focus issues
1. A lesson from the FOSTER Project Completion Report was that ambitious change – in the absence of pre-existing agreement on reforms – required significant investment and time. This is because of the range and variety of stakeholders to be engaged such as ministries, departments and agencies (MDAs), private sector, accountability bodies, civil society organisations (CSOs). Where reforms are complex or controversial the need for quality technical as well as political economy expertise is paramount.
2. Annual reviews in a similar, though larger, FCDO programme to NEST in Pakistan have recorded that programme’s success in reinforcing ‘a patient and mutually respectful UK relationship with Pakistan, [one that has] significantly enhanced the… UK’s dialogue with the country's senior political and administrative leadership’. However, implementation has shown the value of focusing on depth over breadth to ensure meaningful and sustainable change is delivered: ‘As a general principle, the programme should aim at going deeper in fewer reform areas, rather than… expanding the programme scope.’
  [note] Pakistan Revenue Mobilisation, Investment and Trade Programme (REMIT) 2023 Annual Review
3. Implications for NEST:
- NEST will need to judge its scope and the number of partners it works with carefully to ensure its impact is not diffuse.
- NEST will likely focus on supporting reform implementation where there is pre-existing consensus on change, or where another international partner is working on the technical aspects and NEST can work on a complementary aspect e.g. reinforce stakeholder engagement.

Appraisal options: what the project will do and how

What the project will do
The project needs to be designed in a way that reflects the evidence discussed above and reflects its scale and place within the UK’s wider offer. Specifically, the project will need to be able implement activities including some or all of the following (and in Box 1 below):
- Expertise i) to inform design of specific reforms and implementation strategies, and ii) to help manage change of reforms and build capability of Nigerian MDAs and other bodies.
- Experts working in MDAs alongside GoN staff for i) six months or more on specific priorities, or ii) inputs from short-term experts to deliver specific solutions to clients.
- Support to improved private sector dialogue with government on reforms or to support consultation and strategic communication of reforms to the public or specific groups.
- Analysis, advice and intelligence to link sources of UK and Nigerian expertise and investment in mutually beneficial partnerships.
- Delivery of a process to help shift perceptions on Nigeria’s economic model among target constituencies with influence over policy, including using eminent UK figures.
NB MDAs and partners in this box of indicative examples will be removed before publication / Box 1: Indicative examples of possible partners and activities under NEST / Inputs to new growth strategy, or revision to development plan, with Ministries of Finance and/or Budget and National Planning / Design of industrial and/or regional policy and strategy with MDA, Forum of State Commissioners of Finance etc / Design of catalytic growth fund with involvement of credible partner e.g. Nigeria Sovereign Investment Authority, InfraCredit, British International Investment and other development finance institutions, InfraCorp / Support to PEBEC on business environment reforms, linked to e.g. agro-export, manufacturing, trade facilitation / Support on monetary or financial sector policy implementation under the facility to CBN such as a long-term adviser, or support to change management/business process engineering, closely aligned with BoE/IMF advice / Illicit finance with CBN, others – to come of FATF ‘grey list’; strengthen crypto regulation / Letter of Understanding with IMF for funding a long-term adviser in CBN to support monetary policy reform / Externally Funded Output with the World Bank to fund analytical and advisory work in the World Bank’s areas of expertise, but for which they do not have administrative budget / Lead a conversation – either focused, or a large-scale ‘big conversation’ – on Nigeria’s economic future and growth path e.g. with think tanks/CSOs (e.g. NESG, Agora, academia, Lagos Business School), with high profile UK voices, with IFIs

How the project will do this

NEST will use one or more channels to deliver these activities. The main delivery channels and their merits are:
Facility managed by a private sector manager sourced commercially
A facility managed by a private service provider will be responsible for procuring and contracting individuals or subcontracting firms or not-for-profit bodies to deliver activities. This channel has the advantages of: streamlining and reducing project management responsibilities of BHC staff, including reducing number of contracts and accountable grants (AGs) to manage; flexibility to respond to opportunities and to adjust activities at low marginal cost to BHC; and providing scope to include technical capability to develop a small portfolio. The disadvantages of this channel include the cost of a private sector facility manager and the need to oversee the contract.
BHC-managed facility: low-value contracts sourced competitively
A facility managed internally would involve BHC staff managing several separate, smaller contracts, Memoranda of Understanding (MoUs) and AGs. This channel has the advantage of avoiding the financial cost of a project manager or needing to manage this contract. The disadvantages include: the amount of staff time needed for procuring and managing support, conducting due diligence assessments where required; and not having additional technical expertise to design and deliver the facility.
FCDO CMP or British Investment Partnership instrument
BHC’s economic portfolio already includes CMPs, such as HMRC, the tax and public finance centre of excellence (the Public Finance Facility), TaxDev and the Bank of England. British Investment Partnerships (BIPs) such as British International Investment and the Private Infrastructure Development Group are active in Nigeria and may scale or diversify their activities and investments. CMPs and BIPs have the advantage of strong expertise. Disadvantages include: no existing CMP ready to deliver flexible technical assistance at scale on economic stability and growth.
MoU with an IFI
An MoU with an IFI would see that international institution manage an agreed programme of work in an area of its expertise. The advantages of using an MoU with an IFI: include their deep technical expertise; and the potential for the ODA to improve the impact of large lending programmes. The disadvantages of this channel include: the cost and time or agreeing work plans with the international institution.
AG with not-for-profit organisation
An AG with a think tank, CSO or other not-for-profit organisation would start with a proposal from an organisation that aligned with NEST objectives. The advantages of an AG include the ability to work with a specialist organisation with strong Nigerian presence. The disadvantages to BHC could include the management cost, such as undertaking due diligence assessments and managing for higher risks.
The facility managed by a private sector manager would be the single strongest channel for NEST. However, they can be combined. The options presented below combine these channels in a variety of ways that provide the option of getting the advantage of the other channels.
Success criteria for assessing options based on the ToC

The preferred option will be the one that scores highest against the following success criteria:

SC no.	Weighting	Success Criterion description
SC1	0-4	Value of facility for outsourcing and any MoU partnership
SC2	0-2	How much ‘standing expert capacity’ is built into the programme e.g. economist, sector expert, also reducing reliance on HMG for direction
SC3	0-1	Flexibility on implementing partners, e.g. private implementing partner managing a facility, or activities delivered through MoUs or AGs

Options and assessment against success criteria
The options are outlined below along with scoring against the four criteria. The options are:
Option 0	Do nothing
Option 1	Facility managed by private implementing partner
Option 2	Standing technical expert capability, reduced facility compared to Option 1
Option 3	Option 2 plus provision for MoU (budget moves from facility to MoU)
Option 4	Option 1 plus provision for MoU (budget moves from facility to MoU)

Option 0	Do nothing
If the project does not go ahead, BHC would be able to put the internal staff time that would not be needed to manage the programme to other uses. These could include: additional engagement with UK CMPs and BIPs; own analysis; engaging with IFIs; and managing other parts of the bilateral portfolio including the Public Finance Facility. BHC, however, would not have a flexible offer on macroeconomic reform focused on stability and growth – other than tax, fiscal and public financial management sub-portfolio.
Option 1
1. Under option 1, there would be light touch direction and management of activities under a £4.4 million facility (Table 2 below). Projects to be funded would originate primarily from discussions between government and BHC staff. The facility manager would handle search for consultants and contracting from the firm’s networks and databases. BHC staff would need to provide technical inputs to terms of reference (ToRs) for activities and to review CVs. The indicative costings, in the table below allow for 25% full time equivalent (FTE) for the Project Director, and 60% FTE for programme management, finance and procurement. A senior programme manager would be expected to have significant familiarity with the sector, for instance able to have specific conversations with FCDO and with project stakeholders on their needs.
2. The Policy Development Facility (PDF) has a broadly similar design to this (Project Completion Report 2021). The flexibility was highly valued by government. BHC benefited from a strong programme director and team (full time for a larger programme) which developed a good ability to identify opportunities and to assess risks. The arrangement required a strong partnership approach between BHC and the contractor which was often effective, but also risked blurring accountability. Significant input was needed from BHC staff, including for quality assurance of ToRs, CVs and outputs. The PDF did well to develop a recognised brand, but was not designed to include independent economic and policy capability.
       Table 2: Option 1 Budget – maximises value of facility

Option 2
1. Under option 2, the value available for use on activities under the facility reduces by approximately £0.5 million and the equivalent resource is used for one or more experts (Table 3 below). The indicative budget below allows for 50% FTE for one expert (e.g. a macroeconomist) and 25% for a second expert (e.g. sectoral expertise in demand such as oil & gas, business environment, trade).
2. Under this option, the facility will be managed more proactively by the implementing partner due to the addition of expertise. The experts would identify opportunities, test concepts and develop them with clients, and develop ToRs for delivery. The experts would help identify strong consultants/teams and could themselves be part of the delivery of some activities. In particular, they would be part of any advocacy campaign to help shape thinking on economic growth, working with partners such as IFIs or think tanks. The experts would also be a resource for UK CMPs and BIPs e.g. to draw on for tailored briefings and for their networks.
       Table 3: Option 2 Budget – with standing expert capability

Option 3
1. Option 3 is very similar for Option 2. However, it allows time to identify to add a partner with an IFI or think tank to work support NEST objectives (Table 4). If this were to be an MoU with an IFI, BHC would manage the relationship directly (a separate component under the programme). If it was with a Nigerian institution, a decision would be made on VfM grounds as to whether the implementing partner should manage the relationship, or BHC manage directly.
2. The main difference in design is that it will be important to add flexibility to a contract with an implementing partner to allow for this, including a lower amount to be managed if BHC takes on management of another component.
       Table 4: Option 3 With both standard expert capability and MoU/AG

Option 4
This option is the equivalent of Option 1 but with provision for a separate component managed by BHC (Table 5). It does not include the two experts working on the facility. The advantages are that it allows flexibility to identify a partnership with an IFI, and maintains the budget of the facility. But it has the disadvantages of Option 1, in terms of lack of expert input into management of the fund with consequence dependence on the partnership between BHC and implementing partner.
       Table 5: Option 4 With MoU/AG but no standing expert capability

Preferred option

The preferred option is Option 3 (see Table 6 below) which allows space for technical expertise to increase the quality of the facility, be part of advocacy work and to engage with BHC and BIPs. It also allows flexibility to introduce an additional component to be managed by BHC.
       Table 6: Ranking of options using success criteria

Description of the preferred option and ToC

1. The preferred option, Option 3, will involve an implementing partner with an in-country presence delivering a focused set of activities with government and other stakeholders.
2. The ToC below (Figure 1) draws on international and Nigeria-based evidence set out above and lessons learned from the FCDO portfolios in Nigeria and globally, shows that success depends heavily on implementation incorporating the following features:
Issues and reforms need to be identified carefully with government. The NEST budget is such that choices will need to be made during inception on breadth and depth of engagement.
One approach is that NEST focuses on several areas where there is already a government decision that a reform is required, and NEST then supports broadening ownership of those reforms, or supports their technical implementation.

A approach would be for NEST to concentrate narrowly on fewer critical reforms, and works deeper in the ecosystem around that reform area to increase the chances of success.

1. Agreeing how NEST works with other development partners on the reform. NEST may work independently with government on a reform. But it is more likely that NEST will work closely with other development partners or with other UK CMPs/BIPs. Agreeing the division of labour on how NEST leverages others’ expertise and resources needs to be negotiated carefully.
2. Designing and implementing activities through facility or MoU. Successful implementation in Nigeria depends on very high-quality expertise, fusing global learning with knowledge of Nigeria’s institutions and political economy.
3. NEST outputs will reflect the specific contribution of an activity to a reform. Output indicators will include results: a) quality advice prepared with client counterparts that inform design of a reform, b) evidence of changed state in the behaviour or capability of the MDA to implement a reform, c) evidence of change in perception to a reform amongst a target group.
4. NEST outcomes will assess the likelihood that a reform was implemented well. Outcome indicators will capture whether activities increased the probability of a reform being implemented, the quality, timing and features of the sustainability of the reform.
Figure 1: NEST Theory of change

How VfM will be assessed throughout the life of the programme

1. The drivers of VfM require sound commercial, financial and risk management as well as technical expertise combined with political acuity of institutional reforms will underpin NEST’s effectiveness. We will ensure the lead institutions have a) clear reform strategies, which b) set out the role of international support, and c) want the type of support NEST offers.
2. A VFM framework will be developed during inception phase to assess effectiveness and cost effectiveness, efficiency, economy and equity throughout implementation. An indicative list is as follows:
- Effectiveness and cost effectiveness
  - Increasing the probability, pace, quality and durability of reforms associated with increasing growth via higher investment and productivity
  - Leveraging UK expertise and development and private finance
  - Leveraging IFI finance and expertise
  - Contributing to a shift in perceptions about the future of Nigeria’s economic growth path amongst key groups
- Efficiency
  - Agreeing a baseline for a definition of admin/management costs as a proportion of total costs, and tracking through the project’s lifetime.
  - Qualitative assessment of the design of activities (e.g. mix of skills and expertise to achieve objectives)
- Economy
  - Assessment of quality and unit costs of main cost drivers (experts, travel, events)
- Equity
  - Assessing the effectiveness and cost (the VfM) of measures under the programme to improve the equity or inclusiveness of reforms e.g. whether PSIA measures lead to improved used of evidence in decision-making and implementation quality, and comparing to the cost of these measures.
The VfM framework will include the same discipline as the logframe in respect of setting a small number of annualised milestones and targets for VfM. These will provide a basis for assessing VfM in annual reviews. They will help make decisions on how to improve use of resources and inform the judgement in the annual review on whether the programme should continue each year.
VFM Statement

1. NEST will represent good VfM as UK ODA if there is credible attribution to the programme of improvements in enablers of high, sustained growth in Nigeria. Channels include: increasing the chances and quality of growth reforms being implemented and sustained (improving jobs and livelihoods); reducing inflation faster than would have otherwise been the case (reducing poverty headcount); addressing an impediment to trade investment that enables higher flows from DFIs and private sector (UK and other quality investment); and unlocking policy-based lending from IFIs. A tangible change in perceptions of Nigeria’s future growth path amongst target stakeholders could also constitute a good return on this ODA.
2. The project design is informed by evidence and lessons learnt from FCDO’s economic development globally and in Nigeria. Long-term and short-term advice will be available to government to bring UK and global expertise to bear and provide sustained support to design and implement reforms. The programme would cease to be good VFM if government ownership of the reform agenda waned or if the quality of support was insufficient to increase the likelihood, quality or durability of reforms. NEST design allows for regularly assessing opportunities and risks and recalibrating the programme in response to these.

## Commercial Case

1. The Appraisal Case has begun to introduce commercial decisions. The Commercial Case develops these choices further and explains how they will be managed during mobilisation, inception and implementation.
2. The preferred option (Option 3 from the Appraisal Case) comprises two components:
- Component 1: Contract with commercial supplier through competitive tender, including under a framework
- Component 2: MoU with an IFI for activities which they are best able to deliver or an AG proposal from not-for-profit expert institutions.
Component 1: Commercial supplier
1. A commercial supplier will be selected to manage the facility. A supplier will be selected which is able to demonstrate good knowledge of Nigeria’s economy and institutions. This would include a sector-proficient programme manager and one or more experts. They would develop a small portfolio of interventions, in consultation with MDAs, private sector, think tanks, international partners and BHC and BII and other BIPs.
2. BHC has a strong understanding of commercial suppliers in Nigeria in this sector. Providers under framework contracts and new Centres of Expertise (CoEs) are well represented.
3. The programme will require flexibility and some of this will have implications for contracting. For instance if a partnership with an IFI doesn’t arise, or conversely, if the value of IFI partnerships exceeded £500k, then the amount to be managed under the facility would correspondingly increase or decrease.
Component 2: IFI and/or AG
IFI
The preferred option allows for one substantive partnership with an IFI to deliver a work stream in their area of expertise. This could be a long-term adviser, or resources provided under an MoU for analytical and advisory work to support a specific objective.
AG with think tanks, academia, CSOs
An AG arrangement would be considered under NEST. It is also possible that a think tank could partner with the private sector provider to deliver specific work streams. BHC is familiar with Nigeria’s landscape of academic institutions, think tanks and specialist CSOs. This means we should be able to assess efficiently activities involving such institutions if proposed by the commercial provider – or to consider funding a proposal through an AG.
CMPs and BIPs
A CMP will not be used at the outset of NEST, although this decision could be reviewed during implementation. NEST will, however, assist in preparing the ground for other Centres of Excellence to work in Nigeria in specific areas on growth.
Implementation arrangements

1. Break clauses for 31 March 2025 will be built into all funding agreements under NEST.
2. A sourcing strategy will set out the route to market for the commercial supplier. We will consider the option of frameworks for procuring these services. For commercial suppliers, the bids will be evaluated against the criteria given below:
1. Track record of delivering results on economic reforms and growth in similar contexts, in partnership with government institutions and the private sector, combining high-quality international and national expertise;
2. In depth understanding of Nigeria’s political economy and the working of Nigeria’s bureaucracy;
3. Experience of deploying flexible technical assistance to adapt and respond to emerging needs of the client and working with complex political economy in delivery of technical assistance;
4. Strong management, safeguarding, reporting, commercial and financial management systems.
1. Assurance: Prior to entering into any formal agreement with delivery partners including commercial suppliers, FCDO will have a satisfactory level of assurance on the partner’s capacity to deliver, financial management systems, and reporting structures. An enhanced due diligence will be completed on the supplier and risks recorded in the risk matrix along with mitigation measures to systematically manage risks.
2. Contract Management: During the inception phase commercial supplier selected through the competitive bidding process/framework will mobilise and set out the details of programme activities. Payments will be linked to clear benchmarks. The supplier will be encouraged to combine local expertise with international experts to improve effectiveness and cost efficiency. Lotting or breaking up the contracts in smaller components will not be considered given the interlinked nature of the themes and additional programme management complexity.
3. Key cost drivers of the contract will include: fees for technical experts and management costs. Other cost drivers are reimbursable costs such as workshops, travel and subsistence related costs, and office costs. We will work with the commercial supplier to ensure that costs reflect market prices and overheads are reasonable. The existing fee data of similar programmes will be a useful benchmark to judge costs quoted by the contracted suppliers.
MoU
1. Capacity to Deliver: FCDO’s Multilateral Aid Review and more recent assessments will be used to assess the effectiveness multilateral institutions that want to receive funding under NEST Central Assurance Assessment will used to gauge institutional risk and proportionate country-level due diligence will be undertaken in coordination with FCDO’s International Financial Institutions Department.
2. A results framework will be developed for any MoU. FCDO will agree locally how to drive VfM in line with the NEST VfM framework. Standard management fees will be applied where these exist. Financial reporting and narrative progress reports will be required. Disbursements will be made based on six monthly costed work plan/forecasts of activities and progress made in the last six months.
3. Controlling costs, managing exchange rate risk, local tax and VfM: The SRO, programme team and FCDO’s commercial and financial experts will ensure commercial efficiency with all implementing partners (commercial suppliers, the World Bank and other UK government departments). Implementing partners will be responsible for managing changes in costs due to currency fluctuations and inflation or changing security situation and for managing local taxes including General Sales Tax. FCDO will drive savings by using economy indicators in a strong VfM framework. FCDO will set out clear expectations for its implementing partners on driving VfM, FCDO will hold awareness raising sessions for all implementing partners to improve VfM including recording savings.
4. Performance monitoring: Implementing partners will be monitored throughout the life of the programme. Quarterly progress reports against work plans and financial forecasts, and FCDO annual reviews will be the key performance monitoring tools for the programme. We will also draw on FCDO’s Strategic Relationship Management programme if the supplier is listed on it.

## Financial Case

1. The programme will be funded from the FCDO Nigeria’s bilateral budget (Resource Departmental Expenditure Limit or RDEL only).
2. The 2024/25 budget requirement fits within current planning assumptions. As we approach the end of the Spending Review, we do not know what our future budget levels will be. We are anticipating RDEL ODA budgets similar to current levels and although this is subject to the upcoming Spending Review. As per routine best budget management practices, we will continue reviewing, managing and delivering activities whilst remaining within our country level budget allocations. We will also build suitable break clauses in our funding agreements as per HMT and FCDO requirement.
Overall Programme Budget

Cost profiling: NEST is expected to cost £4.9m over four years and has been budgeted for in FCDO Nigeria’s current Business Plan as in Table 7 below. The programme will be funded from within the Resource Departmental Expenditure Limit. All expenditure under this programme is ODA eligible. No ICF is envisaged at the outset, but this could change if opportunities arise during implementation.
Table 7: NEST budget and indicative split between major items

This indicative budget allows for engagement on 3-4 issues, depending on depth of engagement. Costings are based on past and current economic and governance reform programmes, including PERL, FOSTER and UKNIAF. Commercial supplier costings have been informed by yearly expenditure of similar capacity building programmes delivered by commercial suppliers.
Flow of funds
The fund flow mechanism for each of the programme components will be as follows:
Commercial supplier: FCDO will reimburse the agreed operational and delivery costs to the commercial supplier on a quarterly basis. The commercial supplier will be responsible for making payments to its staff, its consortium partners and vendors of operational supplies. Responsibility for due diligence of any other consortium members and sub-contractors will rest with the lead supplier.

MoU: Funds will be disbursed against detailed work plans/forecasts of activities.

1. Financial Risks: Implementing partners procured through the competitive bidding process are expected to have strong financial and control systems in place as a pre-requisite in the bidding process. To mitigate financial risks further, an annual programme audit will be carried out in line with FCDO Nigeria practice.
2. Fraud and Corruption: Fraud and corruption risks are assessed as low. All partners will be made aware of FCDO’s whistle blowing processes at the start of the programme. FCDO will share bi-annually its zero-tolerance policy on fraud and corruption, along with whistle blowing processes. For MoUs, the institution’s own whistle blowing policies will apply where these are adequate. Annual reviews will include a focus on any downstream partners utilised, in order to assess procurement, financial, fraud and safeguards risks and will make recommendations as necessary to mitigate the risks identified.
3. Monitoring, Reporting and Accounting: FCDO will ensure rigorous technical and financial monitoring for all components, ensuring compliance with FCDO corporate systems. Results frameworks, financial reporting requirements and milestone payment arrangements will be developed and agreed during the mobilisation phase. FCDO will scrutinise partners’ invoices to ensure compliance with agreed fees, reimbursement costs, work plans, results and VfM. Annual reviews will be used to drive partner performance further and to adjust targets and expectations. Fiduciary risks and plans to mitigate them are detailed with other risks in the Management Case.
4. Forecasting: The indicative outer year forecasts in Table 7 will be adjusted during the Inception Phase and routinely thereafter to manage ODA uncertainties. A carefully moderated six-monthly workplan process will enable delivery partners to forecast expenditure accurately. Financial variance from forecast will be measured through quarterly and annual progress reports and monthly management meetings with partners. Implementation risks identified in the Management Case will be carefully assessed as part of this process, and forecasts will be adjusted as appropriate.
5. Audit: Commercial suppliers and their downstream partners will be subject to annual independent audit by a CBN-approved auditor of an international stature. ToRs including scope of work will be finalized in consultation with FCDO. For MoU institutions, audit reports received from implementing partners will be reviewed by the programme team and in case of any observations these will be taken up and followed through at an appropriate level.
6. Asset Management: The commercial provider will be responsible for maintaining a comprehensive asset register. Updated asset records will be submitted to FCDO with quarterly progress reports. The FCDO programme team will also conduct regular spot checks. The project will not create any liability or capital assets.

## Management Case

Programme management responsibilities within FCDO
1. FCDO team roles: NEST will be led by FCDO Nigeria’s Sustainable Economic Transformation Block. The team includes expertise on macroeconomics, trade, private sector development and programme management. The FCDO Programme Team will have the overall responsibility of management oversight of all four components, monitoring the timely delivery of the agreed milestones/results by implementing partners. The team will draw on advisers from other teams for governance and social development, conflict, commercial, and Monitoring and Evaluation advice.
2. NEST will be managed by BHC Nigeria, led by the Sustainable Economic Transformation (SET) Block:
- Senior Responsible Owner (SRO) – UKB Senior Economist
- Programme Responsible Owner (PRO) – CBS Economic Adviser
- 20% of Programme Manager, 40% of a Deputy Programme Manager
- Other advisory inputs will be agreed as required e.g. climate/nature, social development, governance, illicit finance, and conflict.
The SRO will have overall programme delivery responsibility and will be accountable for managing the delivery plan and log frame and quality assurance including VFM of programme activities and management. The SRO will take the lead on relationships with implementing partners (contractors, IFI) and senior government officials; and draw on the SET Block Team Leader / Deputy High Commissioner Lagos, Development Director and High Commissioner to engage with top of government if required.
FCDO management of implementing partners
1. Commercial supplier: The commercial supplier will be NEST’s main delivery instrument providing technical assistance to government counterparts and working with other partners. Where needed, we will agree with the Nigerian government whether technical experts will be based in MDAs or in separate premises. Administrative functions will be housed in a separate office. The FCDO programme team will hold regular meetings with the supplier and monitor progress against the agreed log frame and workplan.
2. IFIs: Organisations will submit technical proposals and workplans, which will be monitored by the FCDO programme team on a quarterly basis but with more regular interaction amongst technical staff.
3. Monitoring and evaluation: monitoring will be conducted by the FCDO programme team in coordination with implementation partners. In addition, the programme team will look for opportunities to use other BHC resources, CMPs and FCDO 10% cadre time to provide periodic in-depth and removed reviews. No formal evaluation is anticipated at this stage.
Strategic governance with government
The Ministry of Finance will be the formal counterpart for NEST in order to support the coordinating function of the Ministry. However, NEST will work with one or more MDAs that may or may not include the Ministry of Finance. Programme governance arrangements will aim to empower the relevant government institutions to direct technical assistance in line with reform objectives.
Programme Delivery Cycle
1. NEST will be implemented in three stages: mobilisation, inception and implementation.
2. Contracting: Immediately after approval, the procurement process for the commercial supplier will be initiated. MoUs or other agreements will be negotiated with an IFI if these arise. Milestones are:
- Sourcing strategy and ToRs for procurement of commercial supplier.
- Procurement of the commercial supplier and contract signed.
Inception phase: Technical assistance through the commercial supplier will have an inception phase of two months during which detailed work programmes will be developed with government and in consultation with other implementing partners. At the end of inception phase the following would be delivered by the commercial facility manager:
- Implementation design work will be completed during the inception phase and will deliver the full intervention ToC, logframe, VfM framework, workplan, budgets, risk register;
- Communication and advocacy strategy (commercial supplier component only).
Reporting and invoicing: Implementing partner organisations will be required to maintain a high standard of reporting as described in the Commercial Case. FCDO annual reviews will check NEST’s progress against the logframe and gauge whether the programme continues to offer good VfM.
Risk Management

NEST is rated as major risk at the time of submission for approval. The main risks are external, delivery and reputational. FCDO Nigeria has a relatively high appetite for External risk, moderate appetite for Delivery risk and a low appetite for Reputational risk.
- External risks relate to ability for the government to continue with its reform effort: Ministers and heads of MDAs also need to champion difficult reforms that may have been opposed for several decades. There will also be institutional resistance to reforms within partner organisations. Risk mitigation will include building in efforts to support MDAs to communicate reforms that the UK and others support, as well as scaling down activities if they are no longer likely to achieve objectives.
- Delivery risks include coordination of UK support with other development partners. Mitigation of this risk has already begun; throughout design of NEST and PFF, the team has engaged closely with the IFIs, to consult on our plans and to get information on theirs. This needs to continue closely drawing on lessons from other programmes.
- Reputational risks include the perception that the UK is influencing Nigeria’s economic policy, or that the UK is responsible for the government making decisions that impact negatively in the short term on poor and vulnerable people. To mitigate this risk, the UK will support poverty and social impact capability and scale-up of safety nets in NEST and other programmes in the portfolio.
NEST will manage the risks proactively. Reasonable flexibility is retained in programme design to adapt to unforeseen situations and shift resources towards high-performing areas. A risk matrix will be discussed regularly in quarterly meetings with implementing partners and mitigation measures suggested to minimise impact on programme delivery. Implementing partner organisations will also develop detailed risk assessments with mitigation action plans as part of delivery planning in the inception phase.