## Result Framework Août 2024
SHER Results Framework
| Indicators | Milestone | Progress - Year 1 | Comments
Overall Goal
Respond to the immediate vital needs of the most vulnerable populations, in particular children and women affected by the Mpox and cholera epidemics through prevention and care measures that save lives and stop the spread of the outbreaks in targeted provinces
Output 1 - Through UNICEF, reduce the morbidity and mortality related to mpox and cholera in affected communities in targeted provinces (Sankuru, South Ubangi, South Kivu for mpox; North and South Kivu for cholera)
Mpox | 1.1. Mpox surveillance/ Community based surveillance: Percentage of suspected case alerts reported by RECO, investigated and referred for management in the appropriate structures | 100% | 100% | Achieved. All alerts (1,422/1,422) reported by the communities were investigated to be validated by the care providers and then referred.
| 1.2. Mpox medical care Number of Mpox treatment centres (MTCs) set up and functional in the 10 targeted HZs | 10 | 11 | Moderately exceeded. 11 have been set-up in the review period. The Treatment Centres are in 7 Health Zones and have 412 beds. There are 4 in Miti-Murhesa, 2 in Nyangezi, 1 in Kitutu, 1 in KimbiLulenge, 1 in Kadutu, 1 in Walungu and 1 in Kalehe. The Shabunda HZ does not yet have Mpox TCs due to difficult accessibility conditions.
| 1.3. Mpox patient food and nutritional support Percentage of targeted mpox patients, children separated from their mothers or orphans, and their companions, who received food support | 100% | 103% | Exceeded. 3,610 mpox patients received food support against target of 3,489; 103% of target achieved.
| 1.4. Mpox risk communication and community engagement. Percentage of targeted Community Action Committees (CACs) strengthened and involved in household home visits and Mpox awareness. | 100% | 59.5% | Moderately not achieved, but likely to achieve by March 2025. 59.5% (1,115 /1,872) CACs trained benefited from monthly operating support. Due to higher-than-expected cost of activities, the others do not benefit from it. However, the planned activities that the CACs are being carried out as programmed. People were reached through different communication strategies such as community engagement and face-to-face communication (home visits, community dialogues, focus groups etc.), communication media and public displays, media and influencers. This was done through CAC members, local leaders and influencers.
| 1.5.Safeguarding Percentage of planned number of women, girls and boys benefiting from risk mitigation, prevention and/or response to gender-based violence interventions | 100% | 43% | Moderately not achieved, but likely to achieve by March 2025. 43% achieved (902 women, girls and boys) were reached with information on available GBV and Child Protection services in their areas as well as information on how to access them. In addition, nearly 5,800 children, family members of those affected, and at-risk community members participated in community-based activities.
| 1.6. Mpox coordination and monitoring Number of health zones that have established their local response coordination | 100% | 100% | Achieved. Support was provided from the national level for this coordination in the 10 HZs in this programme (Miti-Murhesa, Ibanda, Kadutu, Nyangezi, Uvira, Walungu, Kalehe, Shabunda, Kimbi-Lulenge et Kitutu) with various committees established.
| 1.7.Cholera: Targeted rapid response to suspected cases using the CATI (Case Area Targeted Interventions) approach to break the chain of transmission. | 95% of responses within 48 hours | 99.7% | Exceeded. 99.7% of responses were carried out within 48 hours after notification of the suspected case. The responses have included awareness sessions amongst 206,553 persons, 4,131 households received household water treatment items, 475 cholera kits were distributed, and 21,538 houses were disinfected.
| 1.8. IPC/WASH for mpox and cholera in affected areas. PCI/WASH activities established in 10 Mpox Treatment Centres | 10 | 9 | Moderately not achieved, but likely to achieve by March 2025. IPC/WASH activities have been fully implemented in 9 Mpox Treatment Centres (of the originally planned 10). 7 other at-risk health facilities in the targeted health zones have also been provided with WASH materials, and 300 health care providers have been equipped with IPC/WASH. Oral Rehydration Points for cholera have also been established in 19 priority locations in North and South Kivu.
Output 2 - Establish additional mpox response support via WHO
| Establish additional mpox response support via WHO | FCDO to finalise agreement with WHO for additional mpox response support activities by November 2024. | Achieved. The British Embassy Kinshasa has conducted a full proposal review, due diligence assessment and established a Contribution Arrangement with the WHO DRC Country Office as of 22 November 2024.