## Annual Review Template

Title: Strategic Impact Evaluation and Learning (SIEL)
Programme Value £ (full life): £13m		Review date: August 2024 (covering April 2023- March 2024)
Programme Code: 300623	AMP start date / 10 August 2023	AMP end date: / 31 Mar 2030

Summary of Programme Performance
Year	2023-4
Overall Output Score	A
Risk Rating	Minor

DevTracker Link to Business Case:	Not yet published
DevTracker Link to results framework:	In development.

A. SUMMARY AND OVERVIEW

Description of programme

The Strategic Impact Evaluation and Learning (SIEL) programme is the Evaluation Unit’s new flagship programme that will fund impact evaluations in priority areas for the Foreign Commonwealth and Development Office (FCDO). It will look at interventions from the inception/design stage to post implementation to assess impact and long-term sustainability.

It will tell policymakers about the effectiveness of their interventions and why they work (or not) by employing a set of rigorous techniques, including randomised controlled trials, like those used to test new medical treatments.

What will SIEL do?
SIEL aims to achieve an impact evaluation portfolio which provides value for money for FCDO through three key outputs:
#### Strategic and rigorous impact evaluations:

#### SIEL will contribute to the evidence base in under-evaluated areas through impact evaluation studies. It will answer critical evaluation questions which speak to FCDO objectives, filling internationally recognised gaps in the evidence base.

SIEL will trial innovative methods where appropriate.

#### Follow-up evaluative activities to assess programmes’ impact and sustainability in the long-run:

- SIEL will make it possible to carry out follow-up studies in areas of strategic priority for the organisation.
- SIEL will generate robust evidence of the long run impact of programmes by using data from completed programmes, applying impact evaluation techniques.

3) Capacity Building, Engagement and Dissemination:
SIEL will build capacity in FCDO to commission, manage and interpret impact evaluation evidence through a dedicated technical support component for FCDO staff.

Summary supporting narrative for the overall score in this review

The main activity over the review period was procurement. This programme scored an A on the grounds that this two-stage competitive process led to a number of high-quality bids from which the best could be selected. An accountable grant was agreed with Innovations for Poverty Action (IPA), working with the Abdul Latif Jameel Poverty Action Lab (J-PAL), to deliver the programme. The inception period was initiated at the end of this review period in March 2024 and was characterised by good communication, a high rate of workflow from IPA and J-PAL, and very strong progress in terms of clarifying and specifying how SIEL will be delivered in partnership.

This is a high level first review for the programme since a logframe is yet to be agreed at the time of writing but expected during June 2024. The first report against this logframe will be carried out by 31 October 2024, reporting on the June- September period.

Major lessons and recommendations for the year ahead

A lesson learned from previous comparable programmes (e.g. the Centre of Excellence for Development Impact and Learning, CEDIL) is to generate visible outputs early in the programme lifecycle to build the brand and demonstrate clear value add as early on as possible. In this respect, SIEL hopes to produce “nimble” and pilot evaluations to explore different modes of targeting and delivery for interventions and will focus on capacity building activities to build awareness, interest and capability.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The programme’s Theory of Change (ToC) aims to address the following key issues:
- Impact Evaluations (IEs) are not systematically happening in areas of strategic priority for the organisation and/or where the evidence gap is larger;
- To conduct an impact evaluation, dedicated technical expertise is needed from pre-pipeline stage; not all teams have this expertise available, and
- Evaluation budget is linked to programme budget, meaning that rigorous impact evaluations are only happening in programmes with a more generous budget. But this is not necessarily where interesting evaluation questions are.
1. To overcome these issues, the SIEL programme will provide dedicated expertise and funds.
2. Once strategically relevant programmes for collaboration with SIEL have been identified, technical support will be flexibly deployed to help develop the ToC for the programme or activity and identify key assumptions and supporting evidence. This will create a better, shared understanding of what the programme aims to achieve and identify key gaps where there is little and/or anecdotal evidence supporting assumptions.
3. An impact evaluation provides evidence of whether the theory underlying the intervention(s) was right and holds true in the operating context of the intervention. In other words, an IE will tell if the programme worked and “how much” it worked. It can also enable estimation of cost-effectiveness of activities.
4. To maximise the value for money (VfM) of programmes and to ensure validity of IE results, SIEL will promote an adaptive approach to programme management and IEs: the programme will evaluate the overall impact of the intervention but before that it will also make sure the intervention is made as effective as possible through adaptive learning.
5. To achieve this, technical experts will support programme teams to develop not only the overall IE design for the programme (or one or more of its components) but also an evidence and learning plan to generate evidence needed at the beginning and along the lifetime of the programme to enable evidence-based, adaptive decision making able to maximise VfM of the intervention along its life-cycle.
6. Publishing IE results and pro-active communication and dissemination of findings will give the opportunity to influence programmes and policies operating in strategic areas of FCDO interest on a global scale. This will not only magnify the impact of IE investments, but it will also develop the UK’s reputation as a science power and an evidence-committed force for good in the world.
7. The Theory of Change described here is summarised by Figure 1 below and an assessment of the assumptions behind it is considered in Table 1.

Figure 1: SIEL Theory of Change Causal Chain

Table 1: Key assumptions underlying SIEL's Theory of Change, supporting evidence and mitigation and monitoring considerations
Assumption	Evidence and considerations	Mitigation/M&E
Ministers and Leadership must continue to put data and evidence high in the agenda of the organisation for staff to have bandwidth to meaningfully engage. / Decision makers understand and use the evidence generated. / Decision makers understand evidence generated and know how to use it to inform decisions	A policy influencing survey produced by the Fund for Impact Evaluation proves that IE evidence is often used by decision-makers when properly engaged. However, few of the programme’s IEs evaluated FCDO interventions. We have limited evidence that the same results would replicate in FCDO environment. / An FCDO evidence generating programme in Nepal suggests that staff often have the right capability to understand evidence but not enough time to interact with it.	Evidence must be robust but proportionate for teams to absorb and packaged in a format that it is easy to understand and use for decision-makers. / Engagement between the evaluation/research team, FCDO team and implementing partners to make sure that the evaluation results are well received and understood. Role for SIEL steering committee in overseeing this. / SIEL programme to incorporate a capacity building component for FCDO to better understand, absorb and use evaluative evidence for decision making. / Evaluations will have stakeholder engagement and evidence use plans including indicators. The programme will monitor understanding and use of evidence generated on a yearly basis (at minimum) and conduct evaluative activities to understand bottlenecks to evidence use if needed.
SIEL can adapt to shifting FCDO priorities	A challenge faced by many programmes and activities is that they have a lot of traction at the onset but with rapidly shifting priorities and high turn-over of staff they often end up being off-focus after just a few years. / This could be an issue both for SIEL itself and for programmes SIEL will collaborate with, as IE studies must last for the entire duration of the programme evaluated (usually 5 years).	A necessary criterion for an evaluation to be selected will be senior (SCS) buy-in and commitment of staff on the programming/ intervention side to manage their side of the evaluation. / SIEL to incorporate some flexibility to respond to changes in strategic direction to keep portfolio of IE studies in line with current priorities. This could be achieved by phasing thematic windows or by choosing thematic areas that are likely to stay high priority in the long-run (considering long term trends and horizon scanning). / A diversified portfolio including long-term IEs, nimble experiments and follow-up evaluation studies must be built to minimise the risk that the IE portfolio will become obsolete after just 1 or 2 years. / All Studies should not be identified on the first year of the programme but rather in a phased way. / Expectations around how much a long-term IE research study can flex and bend to respond to current priorities must be clear at the outset. Some aspects will be flexible but others won’t to preserve the rigour of the study.
IE results are robust, timely, well communicated, and transferable to other contexts.	The Fund for Impact Evaluation experience suggests that when the implementation partner has experience conducting research and has a network on the ground this assumption holds true. / The generalisability of evaluations can be maximised through their design. The CEDIL programme experience suggests that robust sample sizes, standardising outcome metrics and designing-in analysis of why interventions work, as well as contextual factors that affect this, could help the evaluations generate findings that apply in other contexts	Identifying IEs that fill evidence gaps at the strategic level will contribute to usefulness of findings for other contexts. / RCT methods can be complemented with other methods, e.g., structural models and machine learning to builder deeper understanding. / Adopting a Partnership approach with an organisation with robust IE capability provides some reassurance that the output of the studies will be of rigorous quality and timely available for decision making. / Use of the Evaluation Quality Assurance Service offered by Evaluation Unit. / Annual monitoring of the quality of evidence produced (once findings are available)
SIEL can identify enough programmes in pre-pipeline (or follow-up) stage that are a good match to collaborate with	Matching top-down offer with bottom-up demand is likely going to constitute the main operational challenge. / Experience identifying studies for the Fund for Impact Evaluation programme using workshops was successful, and it included some FCDO studies. However, the different context of SIEL and alignment of investment to strategic priorities will limit the number of eligible programmes to partner with.	We will replicate the successful experience of the DIME Fund for Impact Evaluation workshops as a venue where demand and offer of technical support (and funds) for IE can successfully be matched; / SIEL will conduct systematic engagement with programmes we think can present feasible opportunities to collaborate to stimulate demand. / Communication during early stages of the programme will be crucial to ensure the organisation is aware of the opportunities that SIEL will offer. Head of Profession mailing lists will be an important channel to reach advisors in country posts. / We can use the first thematic window as a pilot to test the effectiveness of seminars and EOIs to identify programmes to partner with in a second window.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The programme is on track to contribute to the expected outcomes and impact. The FCDO Evaluation Strategy (2022) contained a milestone to deliver the Inception Report by March 2024. With delivery expected in July of a high-quality product, the programme remains on track to deliver its aims over the remaining 6 years and has a timeline and process set out in that report for delivering the objectives.

In the next reporting year (2024/5) we expect to deliver the first learning agendas, initial capacity building and set up the first round of Expressions of Interest for impact evaluations.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

The programme is on track to deliver its objectives, which remain highly relevant for the organisation and so delivery should continue.

## C. DETAILED OUTPUT SCORING

Output Title	Procurement and Inception Process
Output number:		N/A – Logframe to be agreed with supplier input	Output Score:	A
Impact weighting (%):		100%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
Accountable Grant signed following due diligence process.	Business case signed off by EED SCS in consultation with RED. / Successful conclusion of Call for Proposals: preferred supplier selected / Due diligence complete / Accountable Grant signed	Complete / Complete / Complete / Complete
Inception report delivered	Inception workshop 25-27 March 2024 / Draft inception report May 2024 / Final Draft inception report July 2024 / Report approved July 2024	Complete / Complete / [] / []

Briefly describe the output’s activities, and provide supporting narrative for the score.

The first reporting year for SIEL covers the period which saw it move from design to delivery , including a competitive procurement process conducted by the SIEL team in collaboration with FCDO Commercial Department. Given the small number of organisations worldwide with the technical and organisational capability to deliver SIEL, an Early Market Engagement (EME) process was undertaken consisting of interviews with key organisations in the impact evaluation field. Based on this initial engagement, a two-stage process selection process was set up inviting outline proposals leading to the selection of Innovations for Poverty Action (IPA) as the preferred bidder.

During November 2023- January 2024 FCDO conducted due diligence on IPA, which did not surface any major concerns for the organisation. FCDO and IPA signed an accountable grant on 4 March 2024 following a detailed but uncontroversial negotiation process in collaboration with colleagues from Commercial Department.

Three weeks after signing the grant agreement, IPA, J-PAL, the FCDO SIEL steering group, and senior officials from the Economics and Evaluation Department (EED) and Research and Evidence Directorate (RED) met in London for a three-day inception workshop at FCDO’s King Charles Street office in London. This further probed FCDO’s priorities for the programme and tested ideas from the IPA proposal with FCDO seniors and colleagues. The SIEL team facilitated conversations with additional staff from the department following the workshop and provided further materials. IPA used these to produce a first draft inception report on 14 May, [followed by a final draft on X 2024]. [FCDO provided sign off to the final inception report on X date].

Lessons learned this year and recommendations for the year ahead

The freedom to design procurement processes to deliver programme aims can support getting best VFM from bidders.

Establishing in-person working relations with a foreign supplier early on can build trust leading to a robust programme delivery.

In implementing year 2 of the programme, FCDO will learn valuable lessons quite quickly about the validity of aspects of the Theory of Change, e.g. whether the programme can be sufficiently flexible in adapting priorities following the 4 July UK General election, and whether sufficient programmes and activities at pre-pipeline stage can be identified for the first Expression of Interest (EOI) round for impact evaluations. The programme may need to be flexible in response to this learning and adapt its approach in a manner which will deliver the programme’s aims considering any new priorities and/or organisational knowledge.

D: RISK

Overview of risk management

The overall risk rating for SIEL is moderate. This is within the risk appetite for the programme which is receptive.

SIEL has six open risks that are categorised into three areas:
- Policy & Programme Delivery
- Public Service Delivery & Operations
- Financial & Fiduciary
Given the stage that the programme is at, the risks identified relate to demand for impact evaluations from FCDO, and high-level financial risks.

As SIEL moves through the delivery stage the risks will be further developed with strong mitigations put in place. All risks will be reviewed quarterly and updated where required.

There are no risks classed as major after mitigation. The residual risk ratings are:

Residual risk rating	Number of risks
Major	0
Moderate	3
Minor	3

E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including consideration of VfM measures of economy and efficiency.

Accurate and timely invoicing and forecasting will be important as we gather pace in the delivery stage, to fulfil FCDO’s accountability obligations and to enable efficient management of funds by the department. FCDO has highlighted this to IPA and reporting on expenditure will be provided as part of the quarterly reports.

The FCDO SIEL Programme Responsible Owner (PRO), and Programme Manager will have regular meetings with IPA and J-PAL staff over this year, currently on a weekly basis. Quarterly reports will provide detailed monitoring on progress and expenditures whilst providing excellent opportunities to review risks and next steps.

Date of last narrative financial report	N/A	Date of last audited annual statement	N/A