## SIEL logframe 19nov2024
Please refer to the Guidance Notes tab for advice on completing the various fields in the logframe.
Please refer to the Results Framework Prof Guide for broader information on the logframe approach
PROJECT TITLE | Strategic Impact Evaluation and Learning (SIEL)
IMPACT | Impact Indicator 1 |  | Baseline | 2025-03-01 | 2026-03-01 | 2027-03-01 | 2028-03-01 | 2029-03-01 | 2030-03-01 | Assumptions
FCDO policies based on evidence on what does and does not work in SIEL's priority areas | Case studies (evidence-to-policy stories) describing FCDO's use of SIEL-supported research results | Planned |  | 0 | 0 | 1 | 2 | 4 | 7 | FCDO can help facilitate interviews and intranet search
Achieved
Source
SIEL website, cumulative These stories document either scale-ups (or scale-downs) of interventions tested with SIEL funds, programs FCDO continues to fund oror other instances of evidence influencing policy per the Evidence to Policy Pathways on the J-PAL website: https://www.povertyactionlab.org/evidence-to-policy
| Impact Indicator 2 |  | Baseline | 2025-03-01 | 2026-03-01 | 2027-03-01 | 2028-03-01 | 2029-03-01 | 2030-03-01
| Number of FCDO policy documents (including e.g. Best Buys), concept notes, business cases, and strategic plans referencing/citing SIEL-supported research | Planned |  | 0 | 0 | 0 | 1 | 2 | 3
Achieved
Source
FCDO intranet and website, as well as narrative reports funded teams, cumulative
OUTCOME 1 | Outcome Indicator 1.1 |  | Baseline | 2025-03-01 | 2026-03-01 | 2027-03-01 | 2028-03-01 | 2029-03-01 | 2030-03-01 | Assumptions
Enhanced generation and use of impact evaluation evidence within SIEL research projects | Number of EOIs received by SIEL per research type (e.g. pilot, RCT, follow-up, nimble, adaptive management) | Planned
|  | Pilot (n=10) |  | 0 | 3 | 6 | 8 | 10 | 10
|  | RCT (n=8) |  | 0 | 3 | 6 | 8 | 8 | 8
|  | Follow-up (n=4) |  | 0 | 1 | 3 | 4 | 4 | 4
|  | Nimble (n=4) |  | 0 | 1 | 2 | 3 | 4 | 4
|  | Adaptive management (n=6) |  | 1 | 3 | 4 | 5 | 6 | 6
Achieved
Pilot
RCT
Follow-up
Nimble
Adaptive management
Source
IPA reporting, cumulative
| Outcome Indicator 1.2 |  | Baseline | 2025-03-01 | 2026-03-01 | 2027-03-01 | 2028-03-01 | 2029-03-01 | 2030-03-01
| (i) Number of SIEL-funded research projects that generated evidence which was used to support program adaptations/improvements, project adoption, scale-up, scale-down, continuation or cancelation decisions (ii) Number of SIEL-funded research projects of which the results are published as part of a project summary on SIEL's website | Planned (i) |  | 0 | 1 | 5 | 10 | 16 | 22
Achieved (i)
|  | Planned (ii) |  | 0 | 0 | 1 | 2 | 4 | 7
Achieved (ii)
Source
(i) based on the narrative reports funded teams submit to us annually, cumulative, (ii) SIEL website, cumulative
| Outcome Indicator 1.3 |  | Baseline | 2025-03-01 | 2026-03-01 | 2027-03-01 | 2028-03-01 | 2029-03-01 | 2030-03-01 | FCDO can track and share user engagement with FCDO pages and newsletters
| (i) Number of FCDO staff who click on links to SIEL-funded research in 'Spotlight' and 'Connecting the dots' newsletters (ii) Number of views of project summaries on SIEL's website (ii) Number of visits to the SIEL-website lasting longer than 5min | Tracking only (i)
Tracking only (ii)
Tracking only (iii)
Source
(i) FCDO data, (ii) and (iii) IPA website Google analytics
INPUTS (£) | FCDO (£) |  | Govt (£) |  |  |  | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTCOME 2 | Outcome Indicator 2.1 |  | Baseline | 2025-03-01 | 2026-03-01 | 2027-03-01 | 2028-03-01 | 2029-03-01 | 2030-03-01 | Assumptions
Strengthened capacity of FCDO staff to commission, manage, interpret, and identify opportunities for future impact evaluations | (i) % of participants in practitioner training ("Impact Evaluation 101"), advanced training ("Impact Evaluation 102"), and J-PAL's Evaluating Social Programs course who self-report a significant improvement in their understanding of impact evaluation methods (ii) % of participants in practitioner training ("Impact Evaluation 101") who self-report a significant improvement in their assessment of the value of evaluating the impact of FCDO programs | Planned (i) |  | 75 | 75 | 75 | 75 |  |  | We will develop a survey tool to assess participants' perceived increase in understanding of IE methods 2.1 (i) and value of IE 2.1 (ii) on a 5 point likert scale, with the top 2 answers counting as "significant" for this purpose. Targets for submissions of EOIs or full business cases are based on assumptions of 20-30 participants per course and two courses per year. Targets are only included for the years with trainings (years 1-4). We expect these percentages to be stable over time.
Achieved (i)
|  | Planned (ii) |  | 80 | 80 | 80 | 80
Achieved (ii)
Source
J-PAL reporting
| Outcome Indicator 2.2 |  | Baseline | 2025-03-01 | 2026-03-01 | 2027-03-01 | 2028-03-01 | 2029-03-01 | 2030-03-01
| (i) % of participants in practitioner training ("Impact Evaluation 101"), advanced training ("Impact Evaluation 102"), and J-PAL's Evaluating Social Programs course who self-report their intention to apply to SIEL when a relevant opportunity arises (ii) % of participants of practitioner training ("Impact Evaluation 101"), advanced training ("Impact Evaluation 102"), and J-PAL's Evaluating Social Programs course who submit an EOI or full business case to SIEL (iii) % of people participating in capacity strengthening activities (motivator sessions and trainings) who reach out to the SIEL help desk | Planned (i) |  | 50 | 50 | 50 | 50
Achieved (i)
|  | Planned (ii) |  | 10 | 10 | 10 | 10
Achieved (ii)
|  | Planned (iii) |  | 20 | 20 | 20 | 20
Achieved (iii)
Source
(i), J-PAL reporting, (ii) and (iii) J-PAL and IPA reporting
INPUTS (£) | FCDO (£) |  | Govt (£) |  |  |  | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | 2025-03-01 | 2026-03-01 | 2027-03-01 | 2028-03-01 | 2029-03-01 | 2030-03-01 | Assumptions
Increased quantity, quality and relevance of evidence available to improve policy design and implementation in SIEL's priority areas | Number of completed learning agendas on SIEL's priority areas | Planned |  | 2 | 4 | 4 | 4 | 4 | 4
Achieved
Source
IPA reporting, cumultative
| Output Indicator 1.2 |  | Baseline | 2025-03-01 | 2026-03-01 | 2027-03-01 | 2028-03-01 | 2029-03-01 | 2030-03-01
| (i) Number of SIEL-funded research projects for high-quality, policy-relevant research proposals that address SIEL's priority areas (unique projects count only once, includes all types of research activities) (ii) % of SIEL-funded research projects per SIEL priority area (iii) % of SIEL-funded research projects per geographical area (iv) % of SIEL-funded research projects with at least one southern researchers included as co-PI (v) % of SIEL-funded research projects with at least one researcher who identifies as female, non-binary, or agender | Planned (i) |  | 0 | 8 | 18 | 26 | 32 | 32
Achieved (i)
Tracking only (ii)
Climate and Nature
Humanitarian
Conflict and State Fragility
Growth
Tracking only (iii)
Sub-Saharan Africa
Middle East/North Africa
Europe and Central Asia
Latin America/ Caribbean
East Asia and the Pacific
South Asia
Tracking only (iv)
Tracking only (v)
Female, non-binary, agender
Male
Source
IPA reporting and annual reports from funded research teams, cumulative
IMPACT WEIGHTING (%) | Output Indicator 1.3 |  | Baseline | 2025-03-01 | 2026-03-01 | 2027-03-01 | 2028-03-01 | 2029-03-01 | 2030-03-01
60% | (i) Number of SIEL-funded RCTs that have a baseline or mid-term output (report, working paper, and/or publication) (ii) Number of SIEL-funded RCTs, nimble evaluation or follow-up that has a final products (final report, working paper, policy brief, and/or publication) | Planned (i) |  | 0 | 0 | 3 | 6 | 8 | 8
Achieved (i)
|  | Planned (ii) |  | 0 | 0 | 0 | 2 | 5 | 11
Achieved (ii)
Source
IPA reporting and annual reports from funded research teams, cumulative
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | 2025-03-01 | 2026-03-01 | 2027-03-01 | 2028-03-01 | 2029-03-01 | 2030-03-01 | Assumptions
Increased capacity of FCDO policymakers to incorporate impact evidence/tools into policymaking | (i) Number of FCDO staff participate in practitioner training ("Impact Evaluation 101," in person) (ii) Number of FCDO staff participate in advanced training ("Impact Evaluation 102," virtual) (iii) Number of FCDO staff participate in J-PAL's Evaluating Social Programs course | Planned (i) | 0 | 25 | 25 | 25 | 25 |  |  | For Output 2.1 (i), the target is based on in-person trainings. This number could be increased if the trainings happen virtually in 2026-2028.
Achieved (i)
|  | Planned (ii) | 0 | 20 | 20 | 20 | 20
Achieved (ii)
|  | Planned (iii) | 0 | 5 | 5 | 5 | 5
|  | Achieved (iii) |  | 1
Source
J-PAL reporting
IMPACT WEIGHTING (%) |  |  | Baseline | 2025-03-01 | 2026-03-01 | 2027-03-01 | 2028-03-01 | 2029-03-01 | 2030-03-01
30% |  | Planned
Achieved
Source
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | 2025-03-01 | 2026-03-01 | 2027-03-01 | 2028-03-01 | 2029-03-01 | 2030-03-01 | Assumptions
Increased awareness and sharing of evidence use through SIEL within FCDO | (i) Number of consultative workshops to develop the learning agendas attended by 7-10 stakeholders | Planned (i) |  | 2 | 4 | 4 | 4 | 4 | 4 | FCDO can track and share registration and participation details
|  | Achieved (i) |  | 1
Source
J-PAL reporting, cumulative
| Output Indicator 3.2 |  | Baseline | 2025-03-01 | 2026-03-01 | 2027-03-01 | 2028-03-01 | 2029-03-01 | 2030-03-01
| (i) Number of FCDO staff participating in SIEL's launch event (ii) Number of FCDO staff participating in SIEL's motivator sessions | Planned (i) |  | 200
Achieved (i)
|  | Planned (ii) |  | 200
Achieved (ii)
Source
IMPACT WEIGHTING (%) |  | FCDO data
10%
INPUTS (£) | FCDO (£) |  | Govt (£) |  |  |  | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
Note on C6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Our estimation for SIEL-funded research projects is: - 10-15 pilots - 8 RCTs - 4-6 follow-ups - 4 nimble evaluations - 6-8 adaptive management engagements Being conservative, we estimate a total of 32 SIEL-funded projects. Based on experience from other initiatives at J-PAL and IPA, we assume we publish case studies for 20% of the SIEL-funded projects (or 7 projects). In terms of timeline, we plan the first EOI in 2024, but first results will not be available until SIEL year 2 (Mar-26 in this timeline) - taking into account the time needed for contracting, conducting the evaluation, and having results.
Note on C11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: We estimate that 10% of the SIEL-funded projects of which a case study is published will also be cited in strategy documents. Is this a reasonable assumption?
Note on C18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: We assume 32 SIEL-funded projects: - 10-15 pilots - 8 RCTs - 4-6 follow-ups - 4 nimble evaluations - 6-8 adaptive management engagements With a 50% acceptance rate, we estimate that our target for EOIs received is 32x2 = 64 in total
Note on C33: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: We assume 70% of the 32 SIEL-funded projects will have results ready within SIEL's 6-year program period. This is a total of 22 projects
Note on C35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Similar assumptions as impact indicator 1
Note on C78: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Our initial estimation is a total of 32 SIEL-funded projects.
Note on C99: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: We estimate to fund 8 RCTs with SIEL
Note on C101: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: We assume 8 RCTs, 4 nimble and 4 follow-ups (16 projects), of which 70% will have this output ready during SIEL's 6-year program period. This is a total of 11 projects

## SIEL logframe 5aug2024
Please refer to the Guidance Notes tab for advice on completing the various fields in the logframe.
Please refer to the Results Framework Prof Guide for broader information on the logframe approach
PROJECT TITLE | Strategic Impact Evaluation and Learning (SIEL)
IMPACT | Impact Indicator 1 |  | Baseline | 2025-03-01 | 2026-03-01 | 2027-03-01 | 2028-03-01 | 2029-03-01 | 2030-03-01 | Assumptions
FCDO policies based on evidence on what does and does not work in SIEL's priority areas | Case studies (evidence-to-policy stories) describing FCDO's use of SIEL-supported research results | Planned |  | 0 | 0 | 1 | 2 | 4 | 7 | FCDO can help facilitate interviews and intranet search
Achieved
Source
SIEL website, cumulative These stories document either scale-ups (or scale-downs) of interventions tested with SIEL funds, programs FCDO continues to fund oror other instances of evidence influencing policy per the Evidence to Policy Pathways on the J-PAL website: https://www.povertyactionlab.org/evidence-to-policy
| Impact Indicator 2 |  | Baseline | 2025-03-01 | 2026-03-01 | 2027-03-01 | 2028-03-01 | 2029-03-01 | 2030-03-01
| Number of FCDO policy documents (including e.g. Best Buys), concept notes, business cases, and strategic plans referencing/citing SIEL-supported research | Planned |  | 0 | 0 | 0 | 1 | 2 | 3
Achieved
Source
FCDO intranet and website, as well as narrative reports funded teams, cumulative
OUTCOME 1 | Outcome Indicator 1.1 |  | Baseline | 2025-03-01 | 2026-03-01 | 2027-03-01 | 2028-03-01 | 2029-03-01 | 2030-03-01 | Assumptions
Enhanced generation and use of impact evaluation evidence within SIEL research projects | Number of EOIs received by SIEL per research type (e.g. pilot, RCT, follow-up, nimble, adaptive management) | Planned
|  | Pilot (n=10) |  | 0 | 3 | 6 | 8 | 10 | 10
|  | RCT (n=8) |  | 0 | 3 | 6 | 8 | 8 | 8
|  | Follow-up (n=4) |  | 0 | 1 | 3 | 4 | 4 | 4
|  | Nimble (n=4) |  | 0 | 1 | 2 | 3 | 4 | 4
|  | Adaptive management (n=6) |  | 1 | 3 | 4 | 5 | 6 | 6
Achieved
Pilot
RCT
Follow-up
Nimble
Adaptive management
Source
IPA reporting, cumulative
| Outcome Indicator 1.2 |  | Baseline | 2025-03-01 | 2026-03-01 | 2027-03-01 | 2028-03-01 | 2029-03-01 | 2030-03-01
| (i) Number of SIEL-funded research projects that generated evidence which was used to support program adaptations/improvements, project adoption, scale-up, scale-down, continuation or cancelation decisions (ii) Number of SIEL-funded research projects of which the results are published as part of a project summary on SIEL's website | Planned (i) |  | 0 | 1 | 5 | 10 | 16 | 22
Achieved (i)
|  | Planned (ii) |  | 0 | 0 | 1 | 2 | 4 | 7
Achieved (ii)
Source
(i) based on the narrative reports funded teams submit to us annually, cumulative, (ii) SIEL website, cumulative
| Outcome Indicator 1.3 |  | Baseline | 2025-03-01 | 2026-03-01 | 2027-03-01 | 2028-03-01 | 2029-03-01 | 2030-03-01 | FCDO can track and share user engagement with FCDO pages and newsletters
| (i) Number of FCDO staff who click on links to SIEL-funded research in 'Spotlight' and 'Connecting the dots' newsletters (ii) Number of views of project summaries on SIEL's website (ii) Number of visits to the SIEL-website lasting longer than 5min | Tracking only (i)
Tracking only (ii)
Tracking only (iii)
Source
(i) FCDO data, (ii) and (iii) IPA website Google analytics
INPUTS (£) | FCDO (£) |  | Govt (£) |  |  |  | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTCOME 2 | Outcome Indicator 2.1 |  | Baseline | 2025-03-01 | 2026-03-01 | 2027-03-01 | 2028-03-01 | 2029-03-01 | 2030-03-01 | Assumptions
Strengthened capacity of FCDO staff to commission, manage, interpret, and identify opportunities for future impact evaluations | (i) % of participants in practitioner training ("Impact Evaluation 101"), advanced training ("Impact Evaluation 102"), and J-PAL's Evaluating Social Programs course who self-report a significant improvement in their understanding of impact evaluation methods (ii) % of participants in practitioner training ("Impact Evaluation 101") who self-report a significant improvement in their assessment of the value of evaluating the impact of FCDO programs | Planned (i) |  | 75 | 75 | 75 | 75 |  |  | We will develop a survey tool to assess participants' perceived increase in understanding of IE methods 2.1 (i) and value of IE 2.1 (ii) on a 5 point likert scale, with the top 2 answers counting as "significant" for this purpose. Targets for submissions of EOIs or full business cases are based on assumptions of 20-30 participants per course and two courses per year. Targets are only included for the years with trainings (years 1-4). We expect these percentages to be stable over time.
Achieved (i)
|  | Planned (ii) |  | 80 | 80 | 80 | 80
Achieved (ii)
Source
J-PAL reporting
| Outcome Indicator 2.2 |  | Baseline | 2025-03-01 | 2026-03-01 | 2027-03-01 | 2028-03-01 | 2029-03-01 | 2030-03-01
| (i) % of participants in practitioner training ("Impact Evaluation 101"), advanced training ("Impact Evaluation 102"), and J-PAL's Evaluating Social Programs course who self-report their intention to apply to SIEL when a relevant opportunity arises (ii) % of participants of practitioner training ("Impact Evaluation 101"), advanced training ("Impact Evaluation 102"), and J-PAL's Evaluating Social Programs course who submit an EOI or full business case to SIEL (iii) % of people participating in capacity strengthening activities (motivator sessions and trainings) who reach out to the SIEL help desk | Planned (i) |  | 50 | 50 | 50 | 50
Achieved (i)
|  | Planned (ii) |  | 10 | 10 | 10 | 10
Achieved (ii)
|  | Planned (iii) |  | 20 | 20 | 20 | 20
Achieved (iii)
Source
(i), J-PAL reporting, (ii) and (iii) J-PAL and IPA reporting
INPUTS (£) | FCDO (£) |  | Govt (£) |  |  |  | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | 2025-03-01 | 2026-03-01 | 2027-03-01 | 2028-03-01 | 2029-03-01 | 2030-03-01 | Assumptions
Increased quantity, quality and relevance of evidence available to improve policy design and implementation in SIEL's priority areas | Number of completed learning agendas on SIEL's priority areas | Planned |  | 2 | 4 | 4 | 4 | 4 | 4
Achieved
Source
IPA reporting, cumultative
| Output Indicator 1.2 |  | Baseline | 2025-03-01 | 2026-03-01 | 2027-03-01 | 2028-03-01 | 2029-03-01 | 2030-03-01
| (i) Number of SIEL-funded research projects for high-quality, policy-relevant research proposals that address SIEL's priority areas (unique projects count only once, includes all types of research activities) (ii) % of SIEL-funded research projects per SIEL priority area (iii) % of SIEL-funded research projects per geographical area (iv) % of SIEL-funded research projects with at least one southern researchers included as co-PI (v) % of SIEL-funded research projects with at least one researcher who identifies as female, non-binary, or agender | Planned (i) |  | 0 | 8 | 18 | 26 | 32 | 32
Achieved (i)
Tracking only (ii)
Climate and Nature
Humanitarian
Conflict and State Fragility
Growth
Tracking only (iii)
Sub-Saharan Africa
Middle East/North Africa
Europe and Central Asia
Latin America/ Caribbean
East Asia and the Pacific
South Asia
Tracking only (iv)
Tracking only (v)
Female, non-binary, agender
Male
Source
IPA reporting and annual reports from funded research teams, cumulative
IMPACT WEIGHTING (%) | Output Indicator 1.3 |  | Baseline | 2025-03-01 | 2026-03-01 | 2027-03-01 | 2028-03-01 | 2029-03-01 | 2030-03-01
60% | (i) Number of SIEL-funded RCTs that have a baseline or mid-term output (report, working paper, and/or publication) (ii) Number of SIEL-funded RCTs, nimble evaluation or follow-up that has a final products (final report, working paper, policy brief, and/or publication) | Planned (i) |  | 0 | 0 | 3 | 6 | 8 | 8
Achieved (i)
|  | Planned (ii) |  | 0 | 0 | 0 | 2 | 5 | 11
Achieved (ii)
Source
IPA reporting and annual reports from funded research teams, cumulative
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | 2025-03-01 | 2026-03-01 | 2027-03-01 | 2028-03-01 | 2029-03-01 | 2030-03-01 | Assumptions
Increased capacity of FCDO policymakers to incorporate impact evidence/tools into policymaking | (i) Number of FCDO staff participate in practitioner training ("Impact Evaluation 101," in person) (ii) Number of FCDO staff participate in advanced training ("Impact Evaluation 102," virtual) (iii) Number of FCDO staff participate in J-PAL's Evaluating Social Programs course | Planned (i) | 0 | 25 | 25 | 25 | 25 |  |  | For Output 2.1 (i), the target is based on in-person trainings. This number could be increased if the trainings happen virtually in 2026-2028.
Achieved (i)
|  | Planned (ii) | 0 | 20 | 20 | 20 | 20
Achieved (ii)
|  | Planned (iii) | 0 | 5 | 5 | 5 | 5
Achieved (iii)
Source
J-PAL reporting
IMPACT WEIGHTING (%) |  |  | Baseline | 2025-03-01 | 2026-03-01 | 2027-03-01 | 2028-03-01 | 2029-03-01 | 2030-03-01
30% |  | Planned
Achieved
Source
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | 2025-03-01 | 2026-03-01 | 2027-03-01 | 2028-03-01 | 2029-03-01 | 2030-03-01 | Assumptions
Increased awareness and sharing of evidence use through SIEL within FCDO | (i) Number of consultative workshops to develop the learning agendas attended by 7-10 stakeholders | Planned (i) |  | 2 | 4 | 4 | 4 | 4 | 4 | FCDO can track and share registration and participation details
Achieved (i)
Source
J-PAL reporting, cumulative
| Output Indicator 3.2 |  | Baseline | 2025-03-01 | 2026-03-01 | 2027-03-01 | 2028-03-01 | 2029-03-01 | 2030-03-01
| (i) Number of FCDO staff participating in SIEL's launch event (ii) Number of FCDO staff participating in SIEL's motivator sessions | Planned (i) |  | 200
Achieved (i)
|  | Planned (ii) |  | 200
Achieved (ii)
Source
IMPACT WEIGHTING (%) |  | FCDO data
10%
INPUTS (£) | FCDO (£) |  | Govt (£) |  |  |  | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
Note on C6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Our estimation for SIEL-funded research projects is: - 10-15 pilots - 8 RCTs - 4-6 follow-ups - 4 nimble evaluations - 6-8 adaptive management engagements Being conservative, we estimate a total of 32 SIEL-funded projects. Based on experience from other initiatives at J-PAL and IPA, we assume we publish case studies for 20% of the SIEL-funded projects (or 7 projects). In terms of timeline, we plan the first EOI in 2024, but first results will not be available until SIEL year 2 (Mar-26 in this timeline) - taking into account the time needed for contracting, conducting the evaluation, and having results.
Note on C11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: We estimate that 10% of the SIEL-funded projects of which a case study is published will also be cited in strategy documents. Is this a reasonable assumption?
Note on C18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: We assume 32 SIEL-funded projects: - 10-15 pilots - 8 RCTs - 4-6 follow-ups - 4 nimble evaluations - 6-8 adaptive management engagements With a 50% acceptance rate, we estimate that our target for EOIs received is 32x2 = 64 in total
Note on C33: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: We assume 70% of the 32 SIEL-funded projects will have results ready within SIEL's 6-year program period. This is a total of 22 projects
Note on C35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Similar assumptions as impact indicator 1
Note on C78: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Our initial estimation is a total of 32 SIEL-funded projects.
Note on C99: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: We estimate to fund 8 RCTs with SIEL
Note on C101: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: We assume 8 RCTs, 4 nimble and 4 follow-ups (16 projects), of which 70% will have this output ready during SIEL's 6-year program period. This is a total of 11 projects

## Business case (hidden)
Outcomes | Indicators | Definition of indicator
1. Improved awareness, demand for and use of evidence in decision making in key sectors | Proportion of project teams participating in SIEL workshops that improve their knowledge of impact evaluation techniques | % of IE teams participating in workshops with a teaching component that show improvement on pre-post knowledge test
| Proportion of project teams participating in an impact evaluation workshop that submit a proposal in the relevant SIEL funding window | % of teams participating in SIEL initiating workshops that submit a proposal to the relevant call for proposals
| Proportion of impact evaluations with multi-arm evaluation designs to test project innovations. | % SIEL IEs that have more than one treatment arm
| Proportion of impact evaluations that influence project during design or implementation | % of IEs that improved design based on clear understanding of the underlying theory of change or whose baseline results were used to stimulate policy dialogue / help identify problems and solutions
Proportion of completed impact evaluations that generate evidence used to support project adoption, scale-up, scale-down, continuation or cancelation decisions
| Robust online and social media attendance and engagement with SIEL | Number of blog and vlog posts published on the SIEL website.
2. Improved effectiveness and impact of new and existing development interventions from FCDO and wider community | Proportion of impact evaluations that have influenced the design or implementation of other projects outside of the IE itself | Proportion of impact evaluations that have influenced the design or implementation of other projects outside of the IE itself - Measured through feedback survey of relevant programmes?
Proportion of completed and published impact evaluations that are cited in the academic literature
| Percentage of SIEL products disseminated to policymakers in the SIEL networks that are downloaded | % of emails sent to relevant policymakers in the SIEL networks that result in the opening of IE product attached, including working papers, policy briefs, and papers
Outputs | Indicators | Definition of indicator
1. Increased quantity, quality and relevance of evidence available to improve policy design and implementation in underserved areas | Number of new SIEL-supported datasets (baseline or follow-ups) | Stock of datasets produced during SIEL support cycle (since selection) across SIEL-supported IEs.
| Number of impact evaluations completed and reported | Number of SIEL-supported IEs with final products (final report, working paper, policy brief, and/or publication)
| Proportion of ongoing impact evaluations that have produced an intermediate report | % of IEs that have a baseline or mid-term output (report, working paper, and/or publication)
| Thematic knowledge reviews for policymaking | Stock of thematic knowledge reviews, e.g., mechanism, sector, country, pillar reviews
| Number of SIEL-supported IEs | Number of SIEL-supported IEs
| Thematic distribution: | % and number of SIEL-supported IEs
SIEL themes tbd
| Regional distribution: | % and number of SIEL-supported IEs covering that area.
Sub-Saharan Africa
Middle East/North Africa
Europe and Central Asia
Latin America/ Caribbean
East Asia and the Pacific
South Asia
| Income level distribution: | % and number of SIEL-supported IEs
Low income and lower-middle income
Upper middle income
| Gender: | % and number of SIEL-supported IEs
Proportion of IEs with a gender specific intervention
| Proportion of IEs performing gender analysis | (for IEs with household and individual level data)
| Number of events (workshops, training sessions, and dissemination events) with FCDO audience | Number of events (workshops, training sessions, and dissemination events) with FCDO participation
2. Increased capacity of FCDO policymakers, implementers, researchers, and partners to incorporate rigorous evidence/tools into policymaking | Number of FCDO staff trained in SIEL capacity building events | Number of people from FCDO trained in SIEL workshops and capacity building events
| Proportion of IEs that improve project team’s M&E | % of IE whose data requirements led to improvements in M&E data collection and/or reporting activities of the project teams
| Number of organisations participating in SIEL workshops | Stock of organizations (donors, Multilateral Development Banks, government agencies, academic institutions, NGOs, etc) that have participated in at least one SIEL workshop
| Number of organisations, universities, research centres, and government agencies participating in SIEL networks | Stock of organizations engaged in SIEL-supported IEs (researcher and counterpart affiliation)
| Number of SIEL seminars | Number of SIEL seminars, which show case ongoing and completed IE work
| Number of IE dissemination events to policymakers | Number of events organized to disseminate IE results (baseline or final) to policymakers
3. Increased Communities of Practice and knowledge platforms for sharing of evidence and its application for policy making | Number of organisations, universities, research centres, and government agencies participating in SIEL networks | Stock of organizations engaged in SIEL-supported IEs (researcher and counterpart affiliation)
| Number of SIEL seminars | Number of SIEL seminars, which showcase ongoing and completed IE work

## Change frame
Use this change log to record all changes to the logframe over the life of the project.
ID | LOGFRAME SECTION | DETAILS OF CHANGE | AUTHOR | DATE
E.g. | Output 1, Indictor 2 | Indicator amended from 'No of children enrolled in primary schools' to 'Number of children enrolled in UNICEF supported primary schools (disagregated by sex) | Joe Bloggs | 2022-01-01
1
2
3
4
5
6
7
8
9
10

## Guidance Notes
Logframe Template Guide
Teams should use the guide below to complete the logframe template.
PROJECT TITLE
The name of the programme to which this logframe applies, from the business case
IMPACT
Long term goal to which the project will contribute towards achieving. When drafting the impact statement, consider how your project fits with other efforts from FCDO and partners to achieve the impact, ie is your project nested within a broader undertaking? This will often be the Impact indicator from the Theory of Change in the Business Case.
OUTCOME
The outcome should link through to the outcome level in the programme Theory of Change as stated in the Business Case. The outcome of your project identifies what will change, who will benefit and how it will contribute to reducing poverty, including contributions to the Sustainable Development Goals (SDGs) or Climate Change.
Ongoing monitoring of progress against outcome milestones takes place as an assessment of whether you expect to achieve the Outcome by the end of the programme in the programme Annual Reviews. An assessment of whether your project achieved the Outcome will be included in the Project Completion Review (PCR) based on the target milestone for the programme completion.
OUTPUTS
Outputs are the specific, direct deliverables of your project. These will provide the conditions necessary to achieve the Outcome. The logic of the chain from Output to Outcome therefore needs to be clear. Outputs should reflect the Theory of Change as set out in the Business Case for the programme.
Progress towards the outputs will be assessed and scored at the Annual Review, using output indicators and milestones. Achievement of the outputs will be assessed at project completion, using output indicators and targets.
IMPACT WEIGHTING
Once you have defined your Outputs, assign a percentage for the contribution each is likely to make towards the achievement of the overall Outcome.
The impact weights of all the Outputs will total 100% and each are rounded to the nearest 5%.
Impact weightings for Outputs are intended to:
1. Promote a more considered approach to the choice of Outputs at project design stage; and
2. Provide a clearer link to how Output performance relates to project Outcome performance.
INPUTS
Clarification of inputs is a key part of results-chain thinking. Inputs are specified at the country-level in country operational plans and the project information contained in logframes should feed up into these.
The input-level boxes show the amount of money provided by FCDO and any partners (£) including, where relevant, the government’s own contribution. This only relates to monetary (not in kind) contributions. At Outcome level this is equal to the sum of Inputs for all Outputs. The FCDO share at Outcome Level is a simple, pro rata calculation of FCDO’s contribution in monetary terms for all outputs.
Information should also be provided for the total number of Annual FCDO Full-Time Equivalents (FTEs) allocated to this project, based on the time individual staff members will spend on the project. It is understood that this may change through the project cycle, and is intended as a management tool.
INDICATORS
Indicators are performance measures, which tell us what will be measured not what is to be achieved. Avoid including elements of the baseline or target.
What makes a good indicator?
Specific – what will be measured? And how?
Measurable - data can be collected
Relevant - to the results chain
Useful – for management decision making
Does not include any element of the target
Can be disaggregated if relevant (especially when the indicator relates to number of beneficiaries reached with an intervention)
A mix of qualitative and quantitative
Already defined - if relevant include indicators which towards the FCDO Outcome Delivery Plan / ICF KPIs / SDGs.
Consider using standard indicators / best practice indicators / learning from other projects
The basic principle is that “if you can measure it, you can manage it”.
Top Tip – select indicators based on relevance to the Theory of Change and the availability of data.
Best Practice suggests a maximum of three Indicators per Output.
Some example indicators for a WASH project are shown below.
BASELINE
Baselines set the starting point and provide a measure of the situation before your project starts (could be zero if a new project).
The baseline is used to measure change and monitor progress.
Include a baseline for each of your indicators. The first 6 months of a project may exceptionally be used for assembling baseline data at output level if agreed by your PRO.
Use existing data where possible, but check reliability and seek assurances regarding the data quality eg use data from national statistical systems / Management Information Systems.
If you need to collect your own data - collect baseline data early – as soon as beneficiaries have been identified but before any results are expected.
MILESTONES
Milestones are the desired trajectory from baseline to target, helping you to track progress and make changes to underperforming areas.
Will depend on sequencing of activities and data availability.
Include REALISTIC milestones given resources and capacity.
At the output level include annual milestones for each year of the project (or monthly if short term). At outcome & impact level data may not be available annually and you should record the expected frequency of data availability.
TARGET (DATE)
Targets set the desired point, showing what is achievable within the timeframe available.
The target is often the last year of the project (or month if its short term).
Include realistic targets given resources and capacity, the baseline situation, funding available and country/operational context. Project targets might be informed by evidence about what has worked in the past and take into account lessons learned from other projects.
Include targets dissaggregated by sex/geography/income etc where appropriate.
Consider using government targets although if they are too ambitious then make a more realistic estimate.
Top Tip - A good Theory of Change will help you think about what is realistic and achievable as it will enable critical reflection of context, external influences & assumptions.
SOURCE
Each Indicator will have a data source to verify the results achieved.
List the specific data sources i.e. give the specific data collection e.g. named survey / report and avoid just naming the organisation.
State the frequency of the data source and ensure consistency with milestones and targets.
Check the source can provide disaggregated data as required.
Consider and specify the data collection and reporting responsibilities to ensure the results planned and forecast rows in the logframe are updated on a regular basis.
Top Tip - Before using a data source, assess its quality and seek assurances from data providers where needed ie consider its validity, reliability and availability. Use the Data Quality Prof Guide to help you consider the quality of your data.
ASSUMPTIONS
Define any assumptions which are linked to the realisation of your project's individual outputs, as well as those which are critical to the realisation of the outcome and impact: these will not all be the same. If you are carrying out any evidence gathering to check your assumptions then make reference to this as part of this section.
VALUE FOR MONEY
Ensure the outputs and outcome projected represent good value for the invested resources, at the beginning of the project, and through its life.
Consider including VfM metrics in the logframe (or other documents such as the Delivery Plan) to allow VfM to be measured through the life of the project and to provide assurance at Annual Review.
VfM is achieved at different stages of the results chain. Thus for each result we seek to achieve we should aim to have metrics for each of the following:
Economy - Are we (or our agents) buying inputs of the appropriate quality at the right price?
Efficiency - How well are we (or our agents) converting inputs into outputs? (‘Spending well’)
Effectiveness - How well are the outputs produced by an intervention having the intended effect? (‘Spending wisely’)
Cost-effectiveness - What is the intervention’s ultimate impact on poverty reduction, relative to the inputs that we or our agents invest in it?
Equity - Is the intervention meeting the needs of all beneficiaries?
FCDO’s Approach to Value for Money (PrOF Guide) provides further advice on ensuring VfM.

## TOC
T
THEORY OF CHANGE (ToC)
1. The programme’s ToC aims to address the following key issues:
i. IEs are not systematically happening in areas of strategic priority for the organisation and/or where the evidence gap is larger;
ii.To conduct an impact evaluation, dedicated technical expertise is needed from pre-pipeline stage; not all teams have this expertise available, and
iii. Evaluation budget is linked to programme budget, meaning that rigorous impact evaluations are only happening in programmes with a more generous budget. But this is not necessarily where interesting evaluation questions are.
2. To overcome these issues, the SIEL programme will provide dedicated expertise and funds.
3. Once strategically relevant programmes for collaboration with SIEL have been identified, technical support will be flexibly deployed to help develop the Theory of Change (ToC) for the programme or activity and identify key assumptions and supporting evidence. This will create a better, shared understanding of what the programme aims to achieve and identify key gaps where there is little and/or anecdotal evidence supporting assumptions.
4. An impact evaluation provides evidence of whether the theory underlying the intervention(s) was right and holds true in the operating context of the intervention. I.e., an IE will tell if the programme worked and “how much” it worked. It can also enable estimation of cost-effectiveness of activities.
5. To maximise VfM of programmes and to ensure validity of IE results, SIEL will promote an adaptive approach to programme management and IEs: the programme will evaluate the overall impact of the intervention but before that it will also make sure the intervention is made as effective as possible through adaptive learning.
6. To achieve this, technical experts will support programme teams to develop not only the overall IE design for the programme (or one or more of its components) but also an evidence and learning plan to generate evidence needed at the beginning and along the lifetime of the programme to enable evidence-based, adaptive decision making able to maximise VfM of the intervention along its life-cycle.
7. Publishing IE results and pro-active communication and dissemination of findings will give the opportunity to influence programmes and policies operating in strategic areas of FCDO interest on a global scale. This will not only magnify the impact of IE investments, but it will also develop UK’s reputation as a science power and an evidence-committed force for good in the world.
8. The Theory of Change described here is summarised by Figure 4 below and an assessment of the assumptions behind it is considered in Table 4.