Programme Completion Review

Title: Work in Freedom Phase II - Preventing Forced Labour and Trafficking in South Asia and the Middle East
Programme Value £ (full life): £10,145,500		Review date: September 2024
Programme Code: 300551	Start date: / April 2018	End date: / June 2024

Summary of Programme Performance

Year	2018/19	2019/20	2020/21	2021/22	2022/23	2023/24
Programme Score	A	A	A+	A	A	A
Residual Risk Exposure Rating	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case (and any addendum):	https://ec.vault.dfid.gov.uk/otcs/cs.exe/open/35722830
DevTracker Links to all logframes used during programme lifetime:	http://iati.dfid.gov.uk/iati_documents/36262230.xlsx

A. Summary and Overview

Description of the programme and what it has achieved

The objective of Work in Freedom phase 2 was to reduce the vulnerabilities of women who migrate for work from India, Bangladesh and Nepal, to Jordan and Lebanon. In India, the programme also focused on internal migration from remote areas to larger cities. The programme took a ‘whole trafficking chain’ (or ‘migration cycle’) approach by developing interventions and policy actions at source, along migration pathways/on recruitment and in destinations.  Activities also addressed three levels of the system of migration: the individual, focusing on the empowerment of women; the intermediary, focusing on the recruitment agencies and processes; and the policy-level, focusing on advocacy and research. The activities included:
- Pre-decision training and skills development for women in their communities;
- Improving standards of recruitment agents, and employers;
- Supporting women at their destination, e.g. through local unions and support groups;
- Working with governments to improve laws and policies; and
- Research and evaluation, to build stronger evidence in this field.

The UK provided £10.1 million from 2018 – 2024 through the International Labour Organisation (ILO) to help prevent the trafficking of women and girls from South Asia into domestic work and garment manufacturing, and to support women’s economic empowerment by helping them to migrate safely to decent work. The programme built on the foundations of Work in Freedom phase one (WIF 1), which the UK’s Department for International Development (DFID) supported (providing £10.4m over 2013-2018).
[note] For more, see the Programme Completion Review of Work in Freedom, phase 1.

WIF points the way to a different and more effective type of anti-trafficking programming that seeks to recognise and develop the agency of those that are potentially vulnerable, and the need to develop their freedom of choice and expand the range of those choices. A learning focused approach was used to achieve iterative improvements over the course of the programme, particularly in countries of origin.

During the programme, WIF had to deal with the restrictions of the Covid-19 pandemic and the effects on employment of the economic downturn in both countries of origin and destination. The programme was able to pivot its activities to respond to these challenges, including the significant loss of jobs in destination locations (in India as well as the Middle East) reduced worker rights and protections, and depressed demand for migrant workers, as well as national domestic workers. (See more, see below)
Achievements:

The Work in Freedom programme has:
[note] Note that these results apply to the whole of the Work in Freedom programme over 2013-24 Results specific to Phase 2 (2018-2024) are contained further below in this PCR.

- Reached over 770,000 women and girls in local communities in countries of origin;
  - For example, through door-to-door outreach in villages across Bangladesh, India and Nepal and providing free training to women before they decide whether to migrate or not.  An independent external evaluation has shown that this improved women’s agency and enabled beneficiaries to make more informed choices, weighing up the risks and benefits of migrating for work, and thereby helping to support better outcomes – be that through safer migration or access to local opportunities and schemes that better suit their needs.

- Helped over 150,000 migrant women join local unions and support groups in their destination;
  - For example, through a Migrant Worker Centre or local domestic worker / women’s group. The independent, mid-term evaluation described how this enabled women to access a range of peer support and professional services, such as helping to address grievances or exploitative practices with their employers, mental health support, or – during the Covid pandemic – help in accessing healthcare and in returning home, when many migrant workers found themselves suddenly without a job or place to live.

- Worked with governments on over 27 laws and policies to better protect vulnerable migrant workers;
  - For example, ILO and WIF partners reviewed, supported and/or undertook advocacy around planned laws (such as on anti-trafficking or domestic work), recruitment industry regulation, and reform of judicial practices (such as supporting migrant women to be recognised as legal workers and enjoy the same legal protections as others in the workplace), or helping to reduce the number of migrant domestic workers detained on false charges; and

- Published over 30 studies and research papers providing new evidence to policy makers;
  - For example, qualitative and quantitative studies of households, migrant women’s experiences, migration pathways, recruitment practices, and legal and policy frameworks, shedding light on current (and often complex) realities around how women and girls are affected or impacted. These studies helped to inform policy and programme responses.
    [note] There are various examples of this contained in this PCR, and in the two main external evaluations. These include: WIF studies on the negative impacts of banning women from migrating helped to reverse these policies for periods of time in Nepal; During Covid-19, a WIF study of migrants trapped on the India-Nepal border resulted in allowing the entrance of migrants to the country; and WIF supported a legal review in Lebanon that contributed to the Ministry of Labour adopting a unified contract for domestic workers (though this was later overturned by courts, demonstrating the complex political-economy contexts in which this work operates – see more below).

An independent, final evaluation of the programme assessed it as highly relevant to its target population – female migrant workers – and identified the following findings:

1. Advancing women migrant workers’ empowerment and choices. WIF shifted from conventional approaches against forced labour towards a ‘pro-choice’ orientation and is ‘a prime example of what a well-led, adaptive ‘learning’ programme can achieve’.
2. WIF’s commitment to analysis and investigation of ‘knotty’ problems such as kafala system reform or improved rights and protections for migrant workers has been ‘remarkable and laudable’.
  [note] The Kafala system operates in many countries across the Middle East and is a system of sponsorship that involves – in practical terms – binding migrant workers to a specific employer during their time in the country. Migrant worker’s immigration status is legally bound to an individual employer or sponsor (kafeel) for their contract period, and a worker unable to enter the country, transfer employment, nor leave the country without explicit written permission from the kafeel. This system is often characterised by migrant workers having their passports taken from them and can leave some migrants vulnerable to exploitation, for example being denied the ability to leave the country or change jobs (which can be critical if women find themselves in abusive situations).
3. A focus on building solid and valued relationships across origin and destination contexts. This improves the likelihood of progress and approaches being sustained in countries of origin through alliances of local partners with local government or other agencies.
4. Facilitation of effective advocacy at different levels. WIF has worked well with district and state governments in South Asia, but of particular importance has been the national advocacy work that WIF has often led or facilitated. This includes changes to the law allowing women domestic workers to migrate in Nepal, the leadership role of WIF in the kafala working group in Lebanon, and the Self Employed Women’s Association (SEWA)’s advocacy for domestic workers with opposition and ruling MPs in India.

At the aggregate level, the Work in Freedom programme has:

- Strengthened women workers’ voice, choice and agency. Unions and women’s rights groups supported by WIF increased their efforts to defend the rights of migrant workers, and increased their membership of migrant women workers, particularly in the domestic work and garment sectors. Programme beneficiaries were able to make better informed choices on migrating for work, better negotiate their wages and working conditions. Examples of this include women domestic workers petitioning MPs in India, and advocating for their rights with housing societies.
- Demonstrated adaptability to work under unexpected and often acute challenges. When Covid-19 brought significant pressures upon migrant workers, many of whom found themselves without work or anywhere to live, and unable to travel home, the programme team were able to quickly pivot and uncover opportunities to advocate for the rights of migrant workers. For example, WIF2 helped migrant women access free Covid vaccinations and government welfare initiatives such as E-shram (in India), and convert their undocumented immigration status under amnesty schemes – all of which helped to reduce the vulnerability of workers.
- Pioneered innovative approaches – Stakeholders and programme evaluators commented that the importance of WIF has been to chart a different path and approach when compared with other, more traditional and law enforcement focussed efforts. WIF2’s focus has been on upstream prevention (rather than downstream ‘victim rescue’), on achieving ‘systemic’ change (rather than more tactical, localised efforts), and on working holistically across migration pathways, in source and destination areas, as well as linking activity at the grassroots level with work on laws, policies and research (a geographic and programmatic span that is not frequently a feature of other trafficking/forced labour programmes). It has also developed approaches that look at migration and employment in the round, rather than as separate areas of policy intervention – an important contribution to seeking long-term solutions to human trafficking.
- Built strong and significant partnerships with trade unions, Community Based Organisations (CBOs), women’s rights organisations and Non-Governmental Organisations (NGOs), researchers and research organisations, and some government officials.  Unions such as SEWA and PTS (Penn Thozhilalargal Sangam - a trade union for women workers) had not traditionally collaborated with NGOs linked to Global Alliance Against Traffic in Women (GAATW), since they have not previously dealt with anti-trafficking issues. Now they are not only cooperating within the context of WIF but also do so on their own outside the scope of the programme. Partners in the field have been committed to the issue and have been a central factor in enabling change.
- Put migrant women at the heart of the design of WIF activities. The programme went from having a relatively limited understanding of this group of women, their lives, motivations and experiences at the outset, to a much deeper understanding through good research by the end. WIF also changed its local partners to organisations who worked directly with migrant workers, often led by women and who employed returnee women migrant workers. This resulted in a more effective approach to engaging, involving and informing potential migrants on their rights and choices. This was different to the ILO’s ‘normal’ approach of working primarily with trade unions.

A more salient achievement of WIF is that it managed to successfully operate in environments that were highly challenging and complicated. Female labour migration across Asia and the Middle East is beset by a series of structural barriers that embed and promote gender inequality, such as the Kafala system, the deep-rooted patriarchal norms that govern societies, and policy frameworks that are often conducive to trafficking and abuse. The WIF team and its partners were able to navigate this well, in pursuit of the programmes objectives.

Challenges

In addition to its clear achievements, the WIF2 programme also experienced a number of challenges that impeded more effective delivery:

1. Influencing legal and policy reform: Despite its highly commended policy advocacy efforts, WIF 2 was not able to influence governments sufficiently enough to bring about strong reform of laws and policies to better protect women migrant workers. The external evaluation found that this was due to a deteriorating and increasingly complex wider policy environment in the region, where we are seeing a marked rollback of rights. However, in this context, WIF2 was found to be successful in ‘holding the line’ and preventing a reversal of laws, policies and practices that currently afford at least some level of protection to migrant women workers, which stakeholders and evaluators have described as a meaningful achievement in itself. (See Section B and Output 4 below for more.)
2. Institutionalising lessons learned:
1. External evaluators and stakeholders highlighted that ILO – as the wider organisation – had “lost the opportunity” to learn from WIF’s rich lessons and innovative practices, and that more should be done to ensure these are incorporated into wider ILO policy and programming.
2. Similarly, stakeholders commented that WIF’s lessons should be better communicated to and institutionalised within the UK’s work, the wider UN system and across more conventional anti-trafficking domains, with more resources dedicated to pursuing this.
1. Outcome and impact monitoring: WIF2 did not dedicate sufficient resources to measuring and evaluating all of its outcome-level targets with the same rigour that it measured and reported against output-level performance indicators. Future programming should dedicate sufficient resource and expertise towards establishing clear, meaningful and measurable pathways to outcomes and impact. This will also support communicating the programme’s approach externally.
2. Global join up: Some stakeholders also commented that ILO and FCDO could have supported better joint programming or approaches that incorporates migrant women workers who travel from Africa to Middle East and face similar levels of exploitation to those migrating from Asia.

These have been the key and salient challenges identified across the WIF2 programme. Further challenges and lessons are explored in the more detailed and output-level analysis below.

Stakeholder voice

Despite the challenges, all external stakeholders contacted for this review painted a picture of a programme that was quite unique, innovative and promising. Comments included:

- “WIF was a special programme. It is rare to have a learning and adaptive programme, managed as well as WIF was, with the coherence and effectiveness of the strategy it had in Phase 2. The research WIF conducted really fed through into evolving its programming approach and sparking new ideas for innovation.”
- “The focus on agency and the empowerment of women migrant workers, and the inclusion of these women as fully as possible in the programme was very unusual for a programme set up on an anti-trafficking agenda, where the women themselves tend to be treated as passive victims. For me this is the single biggest take away that should be incorporated in all future programmes dealing with the issues of circular migration.”
- “The consistency, coherence and adaptive nature of the design, with its focus on expanding choice for all migrant women are all programme strengths.”
- “Through the pandemic too, WIF sought to respond to the more immediate protection needs of Women Migrant Workers, as their situations became more acute”.
- “[WIF] was far more innovative than the organisation [ILO] in general, and that meant it [was] hard for WIF to spread its learning internally.”
- The programme’s “Chief Technical Officer deserves a lot of credit… I was deeply impressed with his patience and willingness to adapt and experiment…”

Major lessons learned and evidence generated

The Work in Freedom programme has amassed a rich set of lessons over the course of its 10-year period of operation, which can help guide future efforts on global priorities such as promoting women and girl’s rights, responsible business, and tackling forced labour and human trafficking. These are documented across a range of publications including: Summary of Lessons Learned from Work in Freedom or more detailed lessons on: Outreach to migrant women in areas of origin; on Recruitment; and on Interventions in destination countries. Also available is this full list of ILO publications and papers produced during the WIF programme including different types of publications published on the ILO website (also accessible from the WIF Phase 2 web page), and further publications and papers produced by partners of the WIF programme are also available through the WIF blog.

Key lessons that have emerged from phase 2 of the programme are as follows:

1. Policy responses need to address the main drivers of forced labour – scarcity of decent jobs and absence of adequate social protection. Focusing just on targeting the perpetrators of abuse or on rescuing victims – while important – is less likely to yield a long-term and sustained reduction in forced labour and trafficking.
2. Focus on improving working conditions e.g. through stronger laws, regulations, policy guidance and effective monitoring and transparency. This is more important than educating workers about potential risks they face in their destinations, because migrant workers often have little power and few avenues to address abuses directly with their employer or through local authorities, and faced with no other viable economic options, might choose to take the risks.
3. Ensure anti-trafficking measures do not inadvertently increase harm – Some anti-trafficking measures can infringe on women’s social, economic and political rights, especially the right to work and freedom of movement. For example, if governments, families or communities prevent women from migrating in an effort to protect them, this limits their freedom and choice, and can mean they take more dangerous migration routes or break all contact with their families, who are then less able to help if needed. Similarly, criminalising all informal recruitment agents (who play a vital business role) can leave women navigating a highly complex migration journey alone.
4. Legal channels into formal work can also lead to abusive labour situations. Programmes and policies should be careful not to promise migrant workers that they will avoid abusive situations if they follow formal migration channels, into formal workplaces. It is important to neither stop women from migrating nor encourage them to migrate, as both can result in harmful outcomes.
5. Freedom of association and collective bargaining for migrant workers are critical. If migrants cannot access guidance and support in their destinations, reducing their vulnerability to forced labour will be unsustainable in the long run. International organisations must be willing to stand by international labour standards, even if this is politically difficult in certain countries.
6. The more women’s mobility and work is restricted and socially stigmatised, the more threats to her safety and agency increase. For example, if governments or communities prevent women from migrating, women either simply don’t migrate (which in itself has potentially negative implications – e.g. not reaping the possible benefits of migrating, or in some cases remaining in possibly coercive/abusive situations at home); Or if they are desperate to leave, can migrate suddenly or secretly to avoid stigma, thus increasing potential harms.

Recommendations for future policy and programme work:
These are the key recommendations of this review, there are further recommendations and lessons throughout the wider document.

Policy-level recommendations:

1. Tackle the macro policies (including decent work and social protection) to make a lasting difference. Ensuring productive employment and decent work are central to national development strategies and macro-economic policies will be more effective and sustainable than prioritising more direct measures to tackle trafficking, such as promoting safe migration, fair recruitment or undertaking labour audits.
2. Bring all excluded occupations or types of workers under the fold of general labour law protections. Vulnerable workers such as migrant or domestic workers are often excluded from full labour protections that guarantee fundamental principles and rights at work.
3. Remove mobility and employment restrictions for women. The WIF programme closely reviewed mobility restrictions in several countries. Bans on women’s mobility and employment are a violation of their human rights, are ineffective and should be removed.
4. Future work by FCDO or others should ensure a focus on women and girls as agents rather than just as victims. Programmes and policies are likely to be more effective if they include women as fully as possible in the design, implementation and evaluation of interventions.
  [note] See also the WIF-funded study: Media representation of women migrant workers: A critical look, Nazneen Ahmed, Drishti Research Centre, February 2023.

Institutional-level recommendations:

1. ILO should conduct a thorough review and assessment of the implications of WIF lessons for its wider work and identify clear opportunities for integrating these into ILO’s policies and operations. While some efforts have been made, ILO should also explore ways to continue disseminating WIF lessons both internally, and with key external partners and stakeholders. While the programme spent considerable time disseminating lessons across FCDO and partners, interviews conducted as part of this review highlighted the continued importance of ILO applying lessons from WIF’s innovative approach to their own wider operations. This was also a key finding from the evaluation – recognising more could be done within ILO to replicate, adapt and apply lessons from WIF. It will also be important for ILO to ensure that the rich set of lessons and documentation generated through WIF continues to be available in a clear and accessible way online/on the ILO website, and if possible, for dissemination efforts on this material to be mainstreamed into ILO’s wider outreach activities with all relevant stakeholders.
  [note] WIF teams have undertaken a range of internal dissemination activities, for example engaging ILO staff within other departments, especially MIGRANT, making links with ILO’s Fair Recruitment Hub and other initiatives, and ensuring WIF’s lessons were reflected in the discussion at the International Labour Conference held in June 2024.
2. There should be better join up between efforts on decent work/forced labour/child labour and economic development and growth, particularly in FCDO (though this may also be relevant to other actors). Combining the best thematic expertise on migrant workers with the best expertise in the inclusive economic development community will help ensure policies and programmes maximise innovation and impact, and avoid working in isolation. This includes improving work with the private sector, for example linking brands directly to workers centres.
3. Future ILO research and evidence products funded through programmes should clarify how they complement and systematically work to close priority evidence gaps – for example by linking to initiatives such as ILO’s Research to Action project.
4. ILO should explore options to build sustainability and scale into the operation of Migrant/Worker Centres. WIF 2 has shown this to be an effective intervention, however the current model is small-scale/localised to particular areas, and reliant on donor funding.
5. Future UK efforts in these areas should explore ways to improve donor coordination. There are a number of other countries active on these issues, for example the UK’s contribution is relatively small compared to others such as the US Department of Labour.

Programme-level recommendations:

1. Programmes like WIF and the ILO should work on twin tracks – with the traditional tripartite partners (government, business and worker representatives) and with progressive women’s empowerment focused civil society organisation, who include or work directly with women migrant workers.
2. Future efforts to tackle exploitation and abuse of migrant women workers should make significant investments in political economy analyses. ILO should continue to invest in this. In addition, programmes should potentially adjust their theories of change and level of ambition, design in adaptive and opportunistic approaches, and devise strong risk management strategies in order to account for the highly challenging and deteriorating environment in relation to migrant work experienced by WIF2, including vested interests, asymmetries of power and a general rollback of rights that can be observed across parts of Asia and the Middle East.
3. Future policy and programme efforts should consider ways to better prevent, mitigate and manage risks of unintended consequences, particularly in light of the deteriorating context and global rollback of rights (and the potential risks of backlash this brings). Mitigating reversals in this context is also a key win, so future results frameworks and Theories of Change should consider how ways to capture responses to backlash/rollback (i.e. if we only measure new policy/legislation we miss capturing this).
4. Future programming should dedicate sufficient resource and expertise towards establishing clear, meaningful and measurable pathways to outcomes and impact. Strong indicators and methodologies are needed to avoid ambiguity around the programme impact pathway and extent to which inputs and outputs have led to the intended outcomes. (E.g.: How were awareness activities or knowledge products taken up by the recipients. What did this lead to? How has this been measured? This could include use of improved qualitative information to bridge the gap between outputs and outcome level statements).
5. Future programmes should consider continuing the successful model of establishing an external programme advisory board. This proved to be an effective and useful mechanism in providing external challenge, scrutiny and strategic oversight of FCDO and ILO programme activities.
6. VFM reporting and analysis: ILO’s annual Technical Progress Reporting process should consider ways to incorporate reporting against Value For Money criteria, to provide some data that can be tracked and better monitored across the course of the programme.

How this report was conducted

This Programme Completion Review (PCR) has taken a mixed methods approach.

It drew primarily on a desk- based review of a wide range of programme documents, reports and evaluations. There has been extensive, independent evaluation work undertaken to assess Work in Freedom 2, which this PCR has drawn extensively on, including:
[note] The desk review looked at a range of documents in addition to the external evaluations, CEDIL work, ICAI reporting and Advisory Board reports, including: multiple ILO annual and quarterly technical progress reports for WIF2, FCDO Annual Reviews, WIF 2 Business Case, Logframe / Results Framework, Financial reports produced covering the review period, lessons learned documents, research reports and papers produced by the programme and its partners.

1. Funding through the Centre of Excellence for Development Impact and Learning (CEDIL) since 2019 to review complex Foreign Commonwealth and Development Office (FCDO) programmes, resulting in a rich set of studies and papers. CEDIL undertook qualitative data collection with women migrants in Bangladesh, Nepal and Lebanon, as well as Key Informant Interviews and a Literature Review. It was conducted by researchers from International Food Policy Research Institute (IFPRI), Australian National University, American University Beirut, Lincoln University, and University of Dhaka.
  [note] Ringler, C. et al., 2023. Gender-Sensitive Risks and Options Assessment for Decision Making (ROAD) to Support WiF2 | CEDIL research project paper 8, Centre of Excellence for Development Impact and Learning (CEDIL). United Kingdom. Retrieved from https://coilink.org/20.500.12592/nmmwc7 on 18 Sep 2024. COI: 20.500.12592/nmmwc7. Multiple additional papers were produced. See also this blog describing CEDIL’s work.
2. An independent Mid Term Evaluation (MTE);
3. An independent End of Term Evaluation (ETE).
  [note] The Mid Term Evaluation was completed in November 2022, and the End of Term Evaluation was completed in July 2023. Both were conducted by external contractors and are published here.
4. Scrutiny from the UK’s Independent Commission for Aid Impact (ICAI) as part of their review of UK modern slavery work; and
5. Conclusions from the WIF 2 External Advisory Board – an independent group of senior academics and practitioners with expertise in the areas in which the programme operates, established to help hold ILO and FCDO to account and provide strategic technical direction.

In addition, the PCR team conducted surveys and some interviews with key stakeholders to ensure primary inputs from those closely involved in the programme and to verify / triangulate the conclusions and recommendations of this PCR and the external evaluations. Results of this are highlighted throughout this document, including in Figure 1 below.

There was no direct fieldwork undertaken specifically for this PCR for two main reasons. First, because fieldwork looking at WIF2 had already taken place through various other channels (including the work highlighted above) providing documented contact with beneficiaries, governments and stakeholders, which this review has drawn on. And second, due to resource constraints involved in undertaking fieldwork in an effective and meaningful way across a wide geographic area.

The PCR team consisted of FCDO staff from the programme team, and from the wider Indo-Pacific Regional Department (from where WIF 2 has been managed), working together with wider expertise, including a Private Sector Development Adviser in the Modern Slavery and Business & Human Rights Team, a Social Development Adviser based at post in South Asia, and Monitoring and Evaluation expertise. This report was also peer-reviewed internally and externally.

Management actions following approval of this report

1. ILO and FCDO to initiate their own action plans that respond to and take forward the lessons and recommendations set out in this PCR.
2. ILO and FCDO to work together to ensure timely recovery of the (minimal) remaining unspent funds and assess the need for disposal of any assets created by the programme.
3. ILO to provide final audited financial statement.

## B: Theory of Change and Outcome Assessment

	Starting point	Final result
Budget	£12,495,090	£10,145,500 / The programme budget was reduced in years 4 and 5 due to reductions in UK ODA (Overseas Development Assistance). In year 6, the programme was extended with additional support of £125,000 for dissemination and lesson learning activities. The final programme spend was therefore £2,349,590 less than the original, approved budget.
Timeframe	March 2018 – March 2023	March 2018 – June 2024
Outcomes	Women have greater ability to make their own choices during the entire migration process. / Increased levels of collaboration and accountability between key actors along migration pathways, building an enabling environment for safe migration into decent work. / Strengthened laws, policies, practices and systems for social protection, safe labour migration and decent work for women.	Women have greater ability to make their own choices during the entire migration process in an enabling environment for safe migration into decent work. / Increased levels of collaboration, accountability and respect between key actors along migration pathways towards an enabling environment for safe migration into decent work. / Strengthened laws, policies, practices and systems for social protection, safe labour migration and decent work for women.
[note] Recognising the significant and unanticipated costs incurred to support the people of Ukraine and Afghanistan escape oppression and conflict and find refuge in the UK, the government provided additional resources of £1 billion in 2022-23 and £1.5 billion in 2023-24. The Government sought to focus spend according to the priorities set out in the UK’s International Development Strategy, while maximising the best value for money and our flexibility to respond to new or emerging priority issues.

Overall assessment of programme outcomes, sustainability and VfM

Despite multiple challenges faced during implementation (e.g. Covid, funding cuts and a deteriorating political economy environment/rollback of rights), output targets have been achieved (largely exceeded) and there is evidence to suggest that the programme has achieved some (but not all) of its intended outcomes.

The End of Term Evaluation (ETE) found that WIF 2 was successful in achieving the programme’s first two outcomes (on building women’s agency and strengthening collaboration with key stakeholders on migration pathways/recruitment). However, it judged that while the third outcome made a positive contribution, it was “not fully achieved”. This was because Outcome 3 (which focused on laws and policies) was highly ambitious to seek substantive reforms in what has been a deteriorating and complex legal, policy and political-economy context for women migrant workers in these countries. Examples of this include the Kafala system in the Middle East, resistance to policy reform due to a range of reasons including societal norms (in relation to patriarchy), vested interests (such as in the garment and recruitment sectors), potentially regressive anti-trafficking legislation in India and wider policy frameworks and practices that are conducive to the trafficking and abuse of women.

In addition, this review has found that the programme did not dedicate sufficient resources to measuring and evaluating all of its outcome-level targets with the same rigour that it measured and reported against output-level performance indicators. For example, as can be seen in the tables below, some outcomes did not have mechanisms in place through which the targets could be measured and assessed, and there was an over-reliance on the role that the End of Term Evaluation would play, despite this being independent and something the programme would not have control over (e.g. in choosing the methodology that the evaluators would use). It is noted, however, that another factor in the poor outcome-level reporting is the result of FCDO’s budget cuts, and in particular the cut of £500,000 that had originally been dedicated to programme evaluation work.

Despite this, this review has found good evidence that WIF 2 has achieved positive and intended outcomes and this is corroborated by multiple sources:

- The independent End of Term Evaluation (ETE) noted that: “Overall, the project showed great results to improve the agency of female migrants and their support system (service providers, partnerships)”. It also described how the programme had good complementarity and alignment with civil society organisations and other national partners and that it contributed well to national strategies and priorities.
- The external Mid Term Evaluation (MTE) outlined how the “consistency, coherence and adaptive nature of the design, with its focus on expanding choice for all migrant women are all programme strengths”. It concluded that the WIF strategy was “progressive, coherent and effective” and that more needed to be done within ILO to ensure the longer-term sustainability and replication of WIF’s strategic approach.
- External stakeholder respondents for this PCR commented that WIF 2 had been “highly effective”, showed “innovation and creativity”, was “adaptive”, strong on learning and use of evidence including support for “excellent research”, and demonstrated a strong focus on “women’s agency and choice”. They noted that the programme was able to operate in innovative ways, for example in the way it partnered with representative civil society that involved or were led by migrant workers. It was also noted that this was “different from the ILO’s ‘normal’ approach of working only with trade union structures, and helped make WIF a much more innovative and effective programme”.
- Extensive work undertaken through the CEDIL-funded complex programme evaluations work found that WIF was “effective” in its community level training programmes for women For example, CEDIL research with a sample of 2,645 women villagers in Bangladesh found those who’d been exposed to WIF interventions were 143 percent more likely to deliberate about migration-related topics than those who had not been exposed.
  [note] Ringler, C. et al., 2023. Page 120
- The Independent Commission for Aid Impact (ICAI) undertook a review of the UK’s approach to tackling modern slavery through UK aid (in October 2020), and looked specifically at the Work in Freedom programme, including visiting activities and beneficiaries in Bangladesh. It drew positive conclusions regarding the programme and commented on how the community level outreach activities with women were effective in their implementation (see below for more).

Assessment of outcome-level results

ILO programme reporting at the outcome level is broadly consistent with the findings of the external evaluation. In summary, of the eight outcome-level indicators for the programme, four were achieved in full, one was not achieved, and for the remaining three there is insufficient quantitative data to assess whether or not the outcome targets have been met yet. However, there is some qualitative evidence and narrative that supports the assertion that positive results were achieved for these outcome indicators.

Outcome 1: Women have greater ability to make their own choices during the entire migration process in an enabling environment for safe migration into decent work.

Outcome Indicator	Target	Was the target achieved?
1.1 Changes in women’s decision-making ability and agency (negotiating power/ shifts in power relations): / - within the family / - in the choice to migrate and the method of migration / - in respect of choices regarding employment, working conditions and wages at source & destination	At least 240,000 women with an increased knowledge and/or skills. / At least 65% of surveyed women having participated in outreach events understand the benefits and risks of available options, strategies and practices	Unclear – While at least 240,000 women were reached in source countries, and 185,000 in destination countries, evaluation teams were unable to undertake surveys to effectively assess women’s level of increased knowledge/skills, due to travel restrictions, and time and resource limitations. (This is a lesson for future programming.) / However, other sources indicate that WIF 2 activities were generally effective in building women’s knowledge and skills, for example as noted by ICAI, the ETE, MTE and CEDIL qualitative research, as well as research undertaken by WIF evidence partners and reporting by WIF implementing partners. / ICAI’s interviews with beneficiaries found they “were able to talk with confidence about risks associated with labour migration and how to reduce them”. As noted above, CEDIL’s research with 2,645 women villagers in Bangladesh found those who’d been exposed to WIF interventions were 143% more likely to deliberate about migration. And the ETE noted WIF2 outreach activities with women were “effective” and “achieved some success in increasing women’s empowerment in all countries”.
1.2 Number of reports documenting cases of targeted women being able to collectively negotiate fair and equal wages and better working conditions.	15	Achieved / 15 reports were produced over the course of the programme, such as on the Al Hassan Migrant Centre in Jordan or the gendering migration pathways reports.
1.3 Number of reports documenting cases of women or unions and other organized groups supporting their peers and other women workers who have faced violence or rights violations.	15	Achieved / 20 reports produced, for example GAATW published several issues of My Work My Life magazine relating to WIF countries (10 reports), Aparajita (2021, 2022) Worker Centre Reports (3 spot reports and 1 annual report), and 5 Legal Agenda articles.

Outcome 2: Increased levels of collaboration, accountability and respect between key actors along migration pathways towards an enabling environment for safe migration into decent work.

Outcome Indicator	Target	Was the target achieved?
2.1 A strengthened discourse on women’s right to migration and safe mobility, at all levels	n/a – no targets were set given the challenges of meaningfully measuring programmatic impact on discourse	Unclear / ILO notes that the state of discourse on women’s rights to migration and safe mobility is described in multiple successive WIF publications – see footnote. The ETE concluded that: “WIF has put in place research to facilitate a change in the discourse regarding migrant women workers”. However, it is also noted that this was context-specific and that there was limited success in sensitising the public and the political elite to migrants’ difficulties in Jordan and Lebanon.
2.2 Number of better recruitment regulations or mechanisms to improve working conditions for migrant women, including allowing them to switch employment, adopted in each country or mechanisms to improve working conditions, or mechanisms enabling women to exit poor employment	At least three better recruitment regulations will be adopted/promoted in each country	Achieved / At least four mechanisms were established in four countries. E.g. In Nepal, the programme supported a bilateral agreement with Jordan that regulated recruitment between the two countries; In Bangladesh, WIF facilitated streamlining of recruitment by working with BOESL. In Jordan reviewed WIF reviewed recruitment regulation (2020/2021) and the Jordan Workers Centre facilitated recruitment of workers; In India, SEWA delivered training and placement of domestic, pre- and post-natal care workers. / The ETE also noted that WIF 2 “was effective and unique in establishing relationships with all key actors of the recruitment process”.
2.3 Percentage of increase of workers recruited through better recruitment practice supported by the programme and/or percentage of workers recruited to jobs that offer decent work.	5% annual increase	Largely achieved / ILO reporting states that this outcome has been achieved and that over 853 people were recruited through better recruitment practices.
[note] Some examples include: Bangladesh: Migration and gender in Bangladesh: An irregular landscape, Therese Blanchet and Hannan Biswas, December 2021; Gendering migration pathways from Bangladesh to Jordan and Lebanon: Before and after the COVID-19 pandemic, Therese Blanchet April 2024; In India: In the shadow of the state: Recruitment and migration of South India women as domestic workers to Gulf Countries, Dr. Praveena Kodoth, June 2020; Gendering internal labour migration corridors: Migrant women workers in southern India’s garment industry | International Labour Organization (ilo.org), Indrani Mazumdar, May 2024; From Home Village to Metro City: Looking back and ahead at a labour migration corridor for domestic workers in India | International Labour Organization (ilo.org). Indrani Mazumdar, May 2024; In Nepal: No easy exit – Migration bans affecting women from Nepal, Bandana Pattanaik, Global Alliance Against Traffic in Women, November 2015; A comprehensive analysis of policies and frameworks governing foreign employment for Nepali women migrant workers and migrant domestic workers. Exploring the migration policymaking process with a specific focus on bans and restrictions on foreign employment (Nepal), Dr. Mark McCarthy, May 2021.
[note] The Bangladesh Overseas Employment and Services Ltd (BOESL), part of the Ministry of Expatriate Welfare and Foreign Employment.
[note] ILO reporting shows that: for 2019, 231 people were recruited through better practices; For 2020 288 workers; In 2021, due to COVID, the figures dropped so only 50 workers were recruited; In 2022, 134 workers were recruited; And in 2023, more than 150 workers were recruited. Therefore there has been an increase on the previous year of at least 5% (as per the target) in all years except 2021. However, it is noted that covid has a significant impact.

Outcome 3: Strengthened laws, policies, practices and systems for social protection, safe labour migration and decent work for women.

Outcome Indicator	Target	Was the target achieved?
3.1 Use of evidence-based research to influence policy discussions	66% of policy-makers including constituents, researchers, practitioners or donors surveyed report understanding and/or use of WIF research and evaluation findings.	Unclear / While the ILO and the ETE did not institute means by which to measure this, it is clear from other evidence that WIF evidence and advocacy efforts have influenced policy discussions. ILO state that: “It is undisputable that thanks to concerted advocacy, [WIF] altered, reframed and reversed policy trends in several key areas. Key examples include: / India: / - Blockage of potentially harmful and controversial anti-trafficking bills in 2020 and 2023. / - Domestic work bills passed in Kerala and discussed in Tamil Nadu and Jharkand. / Nepal: Government admission that the policy of banning migration to reduce exploitation is not effective. / Jordan: Review of covid response legislation based on evidence provided by programme. / Lebanon: The Ministry of Labour passed a reformed unified contract. While this was later turned down by the High Judicial Council, it shows that evidence WIF collected on working conditions had influence in the Ministry of Labour.
3.2 Reforms / changes made at legislative and policy levels that address violation of migrant women worker rights and upholding of greater accountability levels and successful programme interventions that prevented further deterioration of migrant rights in policy frameworks.	20	11 = Not achieved / The programme struggled to achieve traction at this scale, given the challenging and deteriorating political economy context described above/below. / Examples of progress achieved include: / In India WIF supported advocacy to prevent passage of another poor version of the Anti-Trafficking Bill; In Lebanon, WIF prevented a poor recruitment regulation from being introduced; In Nepal, following advocacy support from WIF and other partners, women empowerment featured in Nepal’s 15th Plan; WIF also reviewed the Sexual Harassment at Workplace Act of Nepal and successfully advocated for better inclusion of social security benefits for migrant workers.

Despite Outcome 3 not being fully achieved, WIF did contribute to stronger legal systems, policies and practices than might otherwise have been the case. The External Advisory Board and external evaluation both noted that WIF’s most significant role in this domain has been to push back against “highly problematic policies” that were or would be harmful to migrants (as per the examples above).

WIF’s mixed success in achieving concrete traction on legal and policy reforms is less likely to be the result of poor planning or design – there is good evidence that the programme team deployed tailored approaches in each local context that were well informed by careful political economy analyses. It is more likely that this is because it is not unique to this programme that achieving progressive reform to laws, policies and practices is highly challenging against a general backdrop of increasingly regressive policies, affecting migrant and women’s rights. This raises wider questions for future policy and programme work in the space, in particular how to best balance ambition with complex realities (including the rollback of women’s rights), and how to best navigate and adapt approaches. While achieving change in these contexts is usually never linear and involves both setbacks and advances, it appears that what we’re observing here is a significant trend of rollback and deterioration of women’s rights and the rights of migrant workers.

One stakeholder expressed concern that “the quantitative successes of WIF (high numbers of women contacted, etc.) has the effect of throwing its qualitative successes into the shade, particularly when these successes consisted of successfully resisting efforts to make the situation for workers more oppressive.” As the stakeholder also noted, this raises the question of how programmes can best measure the effectiveness of their advocacy objectives, and whether success should be measured in purely binary form (i.e. – new law or policy instituted or not) or in more qualitative terms (accounting for issues of rollback/holding the line, quality, or necessary staging on a longer-term pathway to stronger legal/policy reforms).

Value for Money
The second phase of WIF is judged to have achieved a good degree of value for money, which is also the assessment of the external end- and mid-term evaluations of the programme. It was able to do this by using its resources creatively to deliver strong overall effectiveness and generate value that went arguably well beyond the sum of its parts. For example, WIF established itself as a highly credible actor in this field by recruiting the right staff and investing in strong research and evidence. It grew strategic partnerships with a large number of groups, helping to ‘build bridges’ and create a stronger ‘line of sight’ between different actors – e.g. from migrant women in rural communities, and informal recruitment agents, through to governments, and to regional organisations and companies, as well as between countries of origin and destination. And the programme was able to use this network to share evidence and learnings, build stronger advocacy action as well as influence discourse and ‘set the agenda’ more effectively across different sectors and countries.

VFM was also in evidence across a number of areas including Cost Effectiveness (e.g. the programme exceeded its targets for numbers of women reached, and its approaches were shown to be well designed, and based on good evidence); Efficiency (e.g. collaborating with other partners, including NGOs and local government, and cost sharing with other donors); and Economy (e.g. blending the benefits of ILO’s geographic reach and tripartite mandate – bringing together governments, businesses and trade unions – with wider expertise through the programme’s carefully-selected local and regional partners with greater experience in key areas, such as research, and women’s agency/representation).

Gender equality
The Work in Freedom programme focussed explicitly on the needs of female migrants and required a comprehensive understanding of the varied gender dimensions involved in migration and the specific needs of women.

The ETE found that the design of WIF 2 “clearly integrated the needs of women and focus on gender equality as cross-cutting concern”. This was in part due to the holistic approach to protecting and upholding the rights of women migrants and reducing risks, targeting three levels (women themselves, stakeholders and service providers, and systems).

The programme also demonstrated a strong approach to gender through its partnerships, for example working closely with and through local, women’s rights groups working at the community level, with female leadership and female membership (such as women domestic workers). Field visits undertaken by FCDO staff demonstrated the value of working through and with such women’s groups, for example in the high degree of empowerment, cohesiveness and ownership this brought the women and girls involved, and thereby the programme’s objectives.

WiF’s adaptive approach also helped to strengthen migrant women’s voice in the design of the programme, for example by actively feeding findings from qualitative and quantitative studies into how programme activities were implemented (e.g. studies undertaken directly with women by Drishti Research Centre in Bangladesh helped to strengthen WIF’s community outreach messaging and approaches by making them more aligned to women’s lived realities – both in local communities and as migrants. And in at least one instance, this helped to rectify and improve messaging that was potentially and inadvertently harmful to women during the first phase of WIF).

The WIF External Advisory Board commented that the programme’s approach was suitable in supporting a gender responsive approach and helped to address the key issues faced by women migrants, although the programme could have gone further in working towards a more gender transformative approach in places, for example exploring existing dynamics of gender inequality such as household dynamics.

An external stakeholder interviewed for this review commented that one of WIF’s strengths was that it “put the migrant women first, and went from having a very limited understanding of these women, their lives and motivations at the outset, to having a much deeper understanding through good research by the end of the programme”.

Sustainability
WIF 2 has made a number of efforts to ensure the sustainability of its work and intended outcomes, some of which have been more successful than others. The design and implementation of the programme had a strong focus on activities that would, by their nature, help to secure a longer-term and more systemic reduction in exploitation suffered by women migrant workers, for example through the programme’s focus on research, capability building, and improving laws, policies and practices. As above, we have seen evidence of success in the delivery of many, but not all, of these areas.

Specific examples of where sustainability has been in evidence include:
- Other donors are now funding elements of the WIF programme in particular locations, for example the US are supporting the Worker’s Centre in Jordan.
- Many WIF activities at the community level have been delivered with the explicit involvement, co-ownership and sometimes co-funding of local government, which has helped these practices to be continued beyond the end of the programme.
- ILO have engaged in widespread further dissemination activities over 2023-24, with further financial support from FCDO. This has included
  - outreach and discussions with donors, policy makers and other stakeholders in multiple regions of the world, including Africa and Latin America, where there are similar issues of exploitation of women migrant workers;
  - producing new knowledge products, including some translated to local languages,
  - new websites containing WIF lessons and products, including WIF publications featuring as resources on the Alliance 8.7 Research to Action website for forced labour and trafficking; and
  - designing and implementing a new training course based on WIF’s lessons through the ILO International Training Centre (ITC) in Turin, which is often used by government officials and other stakeholders from around the world to study and receive training on various aspects of labour markets.
- There have also been efforts by ILO and WIF downstream delivery partners to continue elements of WIF’s work in all the main countries of operation, which has been recognised in the evaluation.

A number of stakeholders interviewed for this review commented on ‘WIF’s very strong legacy’, the ‘many promising options for future work’ in different contexts, and spoke of a desire to ensure “the legacy of WIF is preserved in as many ways as possible”. Another stakeholder interviewed for this review stated that “The success of WIF2” lay in its ability to establish partnerships built around women's positive influence, influence budget allocations by local government, and enhance stakeholder capacity, thereby “ensuring sustainability and community ownership”.

However multiple stakeholders as well as the external evaluation commented that WIF’s rich lessons could have been better institutionalised within the UN, ILO and FCDO, and in more conventional anti-trafficking approaches led by others. This is also consistent with the findings of this review and forms a key recommendation going forward.

It will be important for ILO to ensure that the rich set of lessons and documentation generated through WIF continues to be available in a clear and accessible way online/on the ILO website, and if possible, for dissemination efforts on this material to be mainstreamed into ILO’s wider outreach activities with all relevant stakeholders.

Figure 1 below captures the views of external stakeholder respondents for this PCR, to a question intended based broadly on the OECD DAC guidelines for evaluation of ODA programmes. While this is a small sample (focussed on those external stakeholders who knew the programme well enough to comment on its activities), it shows that the majority of responses rated WIF 2 in the top two most positive categories, in particular for the programme’s relevance, effectiveness, efficiency and sustainability. However, the responses show some mixed views/level of concern around the extent to which WIF 2’s lessons were incorporated within ILO (most acutely), supported regional lesson learning and coherence.

Fig. 1: Summary of responses received from FCDO survey of external stakeholders
familiar with the WIF2 programme (Spring 2024)
[Question: To what extent do you feel the WIF 2 programme has:…]
Summarise the programme’s theory of change and results framework, including any changes to outcome indicators.

WIF 2 focused on supporting migrants and potential migrants by helping them to make well-informed decisions whilst reducing the risks they face. The principle behind this is the recognition that migration can be either harmful or an important tool for empowering women and for development. The programme delivered activities across five areas:
- Supporting potential migrants in their countries of origin to make informed decisions about migration. The Theory of Change stated that this would enable potential migrants to better understand their rights and negotiate access to local entitlements and local or outbound jobs;
- Reducing risk in recruitment practices and along migration pathways. This would be achieved by understanding migration pathways better, helping key actors along pathways to understand them better and piloting better recruitment practices;
- Supporting migrant women to enjoy stronger collective representation by establishing support mechanisms for migrants and encouraging employers to provide better working conditions;
- Supporting policy advocacy work, across the three areas above, to improve and uphold migrant rights.

The programme also commissioned and supported research, which cut across all areas to build evidence on the nature of the problems and on what does and does not work to address them.

The Work in Freedom 2 Theory of Change:

FCDO worked with ILO and partners to evolve the Theory of Change to incorporate learnings from phase 1 of the programme. As a result, an external evaluability assessment conducted in 2021 concluded that: “The strategy is now more holistic than it was previously, and the current theory of change, more robust”.
[note] Drinkwater, M; Roy, P; Gulnar, W: Vulnerability and Commodification (January, 2021): The Challenges of Finding Paths for the Humanisation and Protection of Female Migrant Workers in the Middle East and South Asia Evaluability Assessment of Work in Freedom Programme, Phase II.

Independent research found that WIF 2’s Theory of Change (ToC) was largely well-supported by the available evidence base (judged against evidence gathered through a Literature Review and Key Informant Interviews). The research was undertaken through the CEDIL-funded complex programme evaluations work that ran alongside WIF 2. It found that 11 of the 12 mechanisms identified in the ToC for reducing migrant women’s vulnerability to trafficking and forced labour were supported by the evidence (albeit with some caveats for how the mechanisms should best be implemented). For one mechanism (building the capacity of social workers and government scheme workers), it was judged that the evidence to support it was ‘Unclear’. There were no ToC mechanisms that were judged to not be supported by the evidence. The review stated that:
[note] ElDidi, H., C. van Biljon, M.F. Alvi, C. Ringler, N. Ratna, S. Abdulrahim, P. Kilby, J. Wu and Z. Choudhury. (2021). Reducing vulnerability to forced labor and trafficking of short-term, low-skilled women migrant workers in the South Asia to Middle East corridor. IFPRI Discussion Paper 2049. Washington, DC: International Food Policy Research Institute (IFPRI). Pages 25-29.

“Based on a comparison of the literature and Key Informant Interviews with the WIF Theory of Change, we find that many of the programmatic areas are supported by the literature, such as advocacy to uphold migrant worker’s rights, as migrant bans are strongly associated with more dangerous migration experiences. Another important intervention are freedom of association spaces in countries of work”.

However the review also found that there were some areas were the current available evidence pointed towards an amended approach to elements of the Theory of Change, for example:

- Freedom of association spaces could only reach those migrants with adequate mobility. It was recommended that further options for reaching less-mobile migrants should be explored, e.g. through mobile phones.
- Activities seeking to change employer attitudes have been shown to be less effective than other interventions such as “humanizing migrants in the eyes of their employers through bringing a photo of their family and a small souvenir from the country of origin (Barsbai, 2018)”.
- It was also noted that WIF did not support major reintegration programmes for returnee migrants, which it claimed could help to “break cycles of negative migration experiences”, however there is mixed evidence on this.

In addition, the Mid Term Evaluation of WIF2 reviewed the programme’s theory of change and found it to be “highly relevant” for the nature of the programme and that it represented a “solid strategy”, that was also robust and adaptive:

“The WIF programme theory of change, with its focus on the empowerment of women migrant workers and expanding their knowledge, choices and protections, remains as relevant as ever. The impact goal is awkward since it focuses on a counter-factual (reduction to vulnerability) and it has a direct and indirect component, the latter through policy change. All three outcomes remain highly relevant, as do the related outcome indicators. The reduction to vulnerability can be assessed by the extent to which key risks and vulnerabilities have been addressed through the programme. These exist through both lack of information about the nature of the migration process and how to navigate it safely, and the nature of the patriarchal relations in sending communities, which often limits women’s control and decision-making authority. WIF is tackling both these major factors and attempting to cultivate women leaders and put local institutional mechanisms into place (with their leadership) to sustain mechanisms in the longer term. This is a solid strategy, and its robustness has been shown by the adaptiveness that took place during the pandemic, and now in the post-pandemic phase, with continuing economic fall outs in origin and destination countries and locations.” (MTE p40).

There were no significant changes to the ToC or Logframe targets during the course of the programme, in part due to the fact that substantive updates had already been made based on the lessons learned during the first phase of the WIF programme (2013-18). There were a number of amendments made during the second phase, including to the following outputs and outcomes. These changes were largely to account for UK budget cuts (as detailed in Sections B, D, E & F), the impact of covid and recommendations from an external Evaluability Assessment conducted on the programme.
At the output level, the changes agreed with ILO decreased the original targets for 5 of the 16 output indicators. However, despite these reductions, in the end reporting shows that the strong momentum in place through ILO and its partners meant that the output targets were exceeded:
- 1.1 Number of potential women migrant workers, girls and their families who are reached by outreach activities (door to door visits, community/courtyard meetings, etc.) on issues around mobility by choice, alternative employment or other entitlements, how to make informed migration decisions etc.
  - 2022 target reduced from 58,000 to 16,000, 2023 target reduced from 38,000 to 0. This reduced the cumulative target for this output over 2018-23 to 140,000.
- 1.2 Number of women and  girls  who are reached by pre-decision  orientation (1.5 days pre-decision programmes)
  - 2022 target reduced from 40,000 to 7,000, 2023 target reduced from 24,500 to 0. This reduced the cumulative target for this output over 2018-23 to 81,500.
- 1.3 Number of women reached by amended vocational skills curricula which includes rights.
  - 2022 target reduced from 2,000 to 1,100, 2023 target reduced from 1,500 to 0. This reduced the cumulative target for this output over 2018-23 to 6,600.
- 2.1 Number of women migrant workers organized who are in care and textiles, clothing, leather, and footwear industries (TCLFI)
  - 2022 target reduced from 30,600 to 16,830, 2023 target reduced from 35,700 to 19,635. This reduced the cumulative target for this output over 2018-23 to 113,765.
- 2.2 Number of women workers who access information and get improved support through engagement with NGOs, trade unions and Governments; and percentage reporting satisfaction on quality of support.
  - 2022 target reduced from 25,000 to 13,750, 2023 target reduced from 30,000 to 16,500. This reduced the cumulative target for this output over 2018-23 to 115,650.

In addition, the following changes were made to outcome level indicators, largely in response to a series of recommendations made by an external Evaluability Assessment of WIF2:
[note] The detailed reasoning for each of the changes can be found in the 2021 ILO Technical Progress Report for WIF2 and in the Evaluability Assessment, published here.

1.1 Changes in women’s decision making ability and agency (negotiating power/ shifts in power relations):
- within the family
- in the choice to migrate and the method of migration
- in respect of choices regarding employment, working conditions and wages at source and destination
(text in red added in 2021)

1.2 Sustainability and replication of processes/ methods - if replication of methods/ processes has occurred, by whom and with what resources Following the Evaluability Assessment, this indicator was removed from the results framework

1.4 Number of reports documenting cases of women or unions and other organized groups supporting their peers and other women workers who have faced violence or rights violations. (Text in red added in 2021)

2.2 Number of better recruitment regulations or mechanisms to improve working conditions for migrant women, including allowing them to switch employment, adopted in each country or mechanisms to improve working conditions, or mechanisms enabling women to exit poor employment (Text in red added in 2021)

2.3 Percentage of increase of workers recruited through better recruitment practice supported by the programme and/or percentage of workers recruited to jobs that offer decent work.

3.2 Reforms/ changes made at legislative and policy levels that address violation of migrant women worker rights and upholding of greater accountability levels and successful programme interventions that prevented further deterioration of migrant rights in policy frameworks (added in 2022).
## C: Detailed Output Assessment

Output Number and Title	Output 1: Women understand how to negotiate and take decisions that affect their lives especially in relation to accessing protections and entitlements, mobility and local or outbound employment [contributes primarily to Outcome 1]
Output Score	A+
Impact weighting (%)	20%	Impact weighting revised since last AR?	No

Output Indicator	Logframe Target	Final Result Achieved
1.1 Number of potential women migrant workers, girls and their families who are reached by outreach activities (door to door visits, community/courtyard meetings, etc.) on issues around mobility by choice, alternative employment or other entitlements, how to make informed migration decisions etc	Cumulative target: 140,000 / (India: 65,000, Nepal: 40,000, / Bangladesh: 35,000)	Cumulative total: 239,712 / (India 157,525, Nepal 25,779, / Bangladesh 56,408)
1.2 Number of women and girls who are reached by pre-decision orientation (1.5 days pre-decision programmes)	Cumulative target: 81,500 / (25,000 Nepal; 37,000 India; 19,000 Bangladesh)	Cumulative total: 79,982 / (5,525 Nepal, 59,511 India, Bangladesh 14,946)
1.3 Number of women reached by amended vocational skills curricula which includes rights	Cumulative target: 6600	Cumulative total: 17,957 (Nepal 4,151, India 12,692, Bangladesh 1,114)
1.4 Numbers of master trainers, peer educators, social mobilizers/community leaders have an increased understanding on issues related to gender, migration and trafficking	Cumulative target: 410 trainers of community workers. WiF community workers (peer educators, social mobilizers/community leaders) with increased knowledge on issues related to gender, migration and trafficking.	Cumulative total: 5,022
1.5 Outreach methods are tailored to targeted communities for better effectiveness	Cumulative target: 23	Cumulative total: 23

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score.
WIF 2 significantly exceeded its target of outreach to potential women workers, girls and their families & overachieved its end of programme targets. In each of the three origin countries, the numbers achieved involve outreach through door-to-door visits (facilitated by volunteers), community courtyard meetings etc with the aim of helping potential women migrant workers make an informed choice and learn about options for employment.

A substantial number of women especially in rural areas of source countries do not have access to key public services, and often lack critical information that could help them find better livelihood options and/or decrease their vulnerability if migrating for work. WIF’s outreach activities especially through door-to-door visits and local pre-decision (as well as pre-departure) training ensured that messages about safe migration as well as options for local employment reached a far greater number of women than it would otherwise have been the case. The experience from WIF phase 1 had demonstrated that pre-departure training alone is not sufficient on its own. Hence a pre-decision orientation was added in Phase 2 so that women could judiciously decide whether they would migrate for work or look for local livelihood opportunities instead. Also, as noted in the Mid Term Evaluation (MTE), the programme was able to establish or support services that can reduce female migrants’ vulnerability to trafficking and forced labour, and mobilise women to access these services. The MTE also noted that women in Bangladesh started thinking about their choices for example working in their local area instead of migrating through an illegal channel.
[note] This is consistent with the wider evidence available in the field that finds that providing training and information is useful and important, but is not on its own able to prevent forced labour or exploitation. See an appraisal of the available literature on pages 37-39 of Ringler, C. et al., 2023.

An important shift in WIF’s community outreach approach from phase 1 to phase 2 of the programme was the orientation towards women’s choice to migrate, working conditions and workers’ rights, while the focus on trafficking and its dangers was reduced. Priority was given to developing women’s agency, setting out alternate work options and a freedom to choose. This increased the relevance of the programme for women workers.

The 1.5 day pre-decision orientation programme reached marginally fewer women & girls than originally intended (79,982 against a target of 81,500). More than twice the targeted number of women were reached through vocational skills programmes, including training on rights (17,597 against a target of 6,600). This is in part because there was increased demand for vocational skills programmes during the pandemic, when employment opportunities were more scarce.

Programme activities were adapted in response to the challenges presented by Covid during which rights of workers were severely compromised. Organisations and partners of WIF worked hard to secure workers’ rights. For example, the AP Domestic Workers’ Union advocated better living and working conditions in the slums. In Jharkhand, Orissa and Chhattisgarh, organisations met virtually to discuss strategies in upholding workers’ rights (through GAATW - the Global Alliance against Trafficking in Women) allowing them to better assist women from migrant communities once Covid-19 mobility restrictions were lifted.

The programme was thus successful in increasing awareness and understanding of rights and entitlements at work of women. An enhanced level of understanding on informed choice of migration and ability to make decision on her work and mobility within the family sphere became possible for women in the intervention areas. A series of stories have been documented by GAATW on ‘Our Work, Our Lives’ in their e-magazines that are illustrative of this.

Evidence suggests that WIF 2’s activities under this output were generally effective in building women’s knowledge and skills, for example as noted by ICAI, the ETE, MTE and the CEDIL qualitative research, as well as research undertaken by WIF evidence partners and reporting by WIF implementing partners. ICAI’s interviews with beneficiaries found that they “were able to talk with confidence about risks associated with labour migration and how to reduce them”. CEDIL’s research with a sample of 2,645 women villagers in Bangladesh found those who’d been exposed to WIF interventions were 143 percent more likely to deliberate about migration-related topics than those who were not. And the ETE noted that WIF2 outreach activities with women were “effective” and “achieved some success in increasing women’s empowerment in all countries”
[note] Ringler, C. et al., 2023. Page 120

Lessons learnt

The programme has an in depth collation of lessons learnt covering outreach to women in areas of origin, as well as on recruitment and intervention in destination countries. Aside from that there are lessons drawn from implementing organisations on the ground and through FCDO’s own programme management:
1. Recognising women who migrate for work as ‘workers’ is critical if we are to make sustainable progress. Too often this is not the case, and migrant women are portrayed just as ‘victims’. Ensuring ‘worker’ status means the women are afforded more protections in law (like those enjoyed by migrant men workers), greater status in communities and with employers, and reduced vulnerability.
2. Skilling of women workers is more effective when women’s organisations are involved, and also returnee migrants. This helps to ensure the support provided is more effective in meeting the needs of migrant women workers. In addition, shortened training which is staggered between pre-departure and post-arrival stages also makes this support more effective.
3. Training programmes must be followed by appropriate referral to services for the trainees. For example, in the case of BNPS (a delivery partner in Bangladesh) women who attended initial training then required further assistance in job placement and skills development. Figures show that those women who received referral to further services had a higher probability of gaining employment (and therefore reduced vulnerability) compared to those that did not.

Recommendations:

1. Future programmes involving forms of circular migration could benefit from WIF’s focus on agency, choice, the empowerment of women migrant workers, and the inclusion of these women as fully as possible in the programme.
2. To have a sustained impact on women’s agency, more activities on women’s empowerment and specifically gender inequality are needed, including those addressing patriarchy and caste-based oppression.
3. Future programmes should explore ways to ensure sufficient quantitative and qualitative indicators to assess the impact on women’s agency / rights claiming / empowerment, designing this in close coordination between programme partners and FCDO MEL teams.

Output Number and Title	Output 2: Migrant women, men and children in targeted sectors enjoy better collective representation, support services, and recognition of their rights along the pathways of their migration. [Contributes primarily to outcome 1]
Output Score	A+
Impact weighting (%)	25	Impact weighting revised since last AR?	No

Output Indicator	Logframe Target	Final Result Achieved
2.1. Number of women migrant workers organized who are in care and textiles, clothing, leather, and footwear industries (TCLFI), with shared and articulated collective demands of their own, or number of women migrant workers involved in collective action informed by the project.	Cumulative target: 83,365 / India: 70,665 / Jordan: 11,300 / Lebanon: 1,400	Cumulative: 184,908 / India 178,837, / Jordan 4002, / Lebanon 1488, / Nepal 581.
2.2. Number of women workers who access information and get improved support through engagement with NGOs, trade unions and Governments; and percentage reporting satisfaction on quality of support.	Cumulative target: 85,650 / Other programme countries: / 6% of members of women's groups supporting worker collectives are satisfied with accomplishments supported by the programme.	Cumulative: 177,781 / Note that due to Covid-19 constraints, the Mid and End of Term Evaluations were unable to track satisfaction rates directly with beneficiaries.
2.3. Number and types of interventions to engage community leaders and employers on migrant workers rights and fair recruitment and numbers reached where measurable (as in the first phase of the WIF programme)	15 Initiatives undertaken reaching at least 30,000 people including employers	At least 26 Initiatives reaching 23,767 people including employers plus 137,990 views on social media, TV audience of 900,000 and 387,990 on social media

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

Overall, the programme achieved more than double the target for the organisation of women (output 2.1). This was largely due to results in India, while for some other countries the programme did not achieve anticipated targets due to significant contextual challenges, Covid and budget cuts. For access to information and support (output 2.2) results were double the target. For output 2.3 the indicator targets were twofold, covering number of initiatives and people reached. While the number of initiatives was significantly exceeded, the results given were subdivided into more individual ‘reaches’ and media views. Whether this sub-indicator was achieved depends on the definition of ‘reached’ and whether this covers TV and Media. These outreach channels have no qualitative element. There is no way of knowing what those who viewed the media events did with the information, such as action they took. If these are excluded the sub-indicator was not reached, which is reflected in the A+ rather than A++ score allocated to the Output overall.

While the global Covid pandemic had a considerable restrictive impact on WIF activities, the programme achieved numerous innovative and opportunistic benefits for tens of thousands of workers across all the countries it worked in. Collective organising work, especially for women, helped achieve wage compensations for loss of jobs, access to social security entitlements, vaccines coverage among migrant workers, Covid relief measures and dissemination of information on protocols and government assistance. Specific examples of both Covid related and wider work included in India support for collective action initiatives resolving pay issues and job retention for domestic workers during Covid, and resolving health and safety and factory lock-out issues for garment sector workers. Also, in India the Self-Employed Women’s Association (SEWA) enrolled thousands of women workers and organised a National Platform to lobby for legislation. Through becoming members of the SEWA Union, women developed confidence and the ability to negotiate and protest.

In Jordan, where much of the development focus was on refugee support and rights, WIF did a valuable job of increasing attention by stakeholders on migrant workers. Migrant garment workers in Jordan are effectively deprived of collective bargaining rights through unions. The programme instead focused on support to the Al-Hassan worker centre, an approach that has been widely commended given the overarching context. Technical support to the centre enabled workers to successfully negotiate for accident compensation, social security, overtime, working conditions and other improvements. The centre also provided workers with a channel to resolve personal issues such as passport retrieval, registering grievances on an official complaint platform, obtaining critical PCR Covid tests, and facilitating returns to home countries, as well as an important networking hub. It was observed that the centre began to change the attitudes of more formal unions, with evidence of them giving more recognition to migrant workers and increasing their own office hours of opening. WIF also helped to resist pressure to curtail the centre’s activities, for example during the Covid pandemic, and helped to identify an alternative donor once UK support through WIF came to a close. Similar worker centre support was provided in Lebanon at a smaller scale, where WIF also supported media initiatives that reached hundreds of thousands of domestic workers.

Lessons learned through this output, and recommendations for future programming

- The considerable flexibility granted to and used by the programme during Covid allowed it to not just continue its work (even though seriously impacted), but to develop innovations that brought multiple benefits to migrant workers under this output in the most challenging of circumstances. This was enhanced by the programmes efforts to work with grass roots organisations.
- Through working with CSOs that involved or were formed by migrant workers, WIF enhanced traditional approaches that have largely focused on the trade union route. This was felt to have increased the effectiveness and innovation of the programme. This especially strengthened the inclusion, agency and understanding of women’s experiences as migrant workers.
- Unintended consequences can arise, such as where shedding light and attention on a theme such as migrant worker rights can provide a trigger to vested interests wishing to maintain the status quo coming together to resist change. An example of this was in India where gated communities came together to resist efforts by domestic workers to organise. It is important to record and publicise such unintended consequences so that awareness and mitigations / countermeasures can be built into future work.
- More opportunity might be taken to connect with and raise visibility of programmes with Posts. For example, in Jordan, while the ILO and FCDO programme had been in contact with UK officials in country, those working on economic development at the Embassy were not aware of the programme, even though they were working on related themes for refugees and were engaging with the ILO’s Better Work project. There might have been opportunities for synergies, increasing influence or compounding impact.
- A recommendation was made that WIF might usefully have produced baseline studies on law and policy which would offer direction to future work in relation to some of the deeply embedded legal context issues in some of the focal countries, such as restrictions on collective organisation.
- Work with innovative alternatives such as the workers centre can unlock considerable benefits and channels for worker grievances, however this can bring them into tension with wider efforts to influence through more formal official channels, where there is a risk of them harming relations. The alternative routes provide powerful opportunities for innovation, and this balance is therefore one that needs to be approached carefully.
- It was reported that some employers supported the Jordan workers centre as they believed it enhanced their businesses image with brands (but a backlash against the centre by other employers was also noted). This highlights that there could be opportunities to build stronger awareness and linkages between brands and centres such as this, and even the investors into those brands, to strengthen the recognition of the centre, its resilience to other pressures, and its sustainability, bringing more employers into its sphere of influence, and ultimately beginning to challenge more entrenched contextual resistance to worker rights and support.
- The new phase of the ILO Fairway programme in the Arab States should be encouraged to draw and build on WIF learning and recommendations, to enhance its impact on migrant worker rights and conditions.
- A number of innovations are evolving that provide innovative platforms for capturing worker feedback, grievances and challenges, especially through the use of social media and mobile phones. These include both apps and trained and skilled call centres with local trained and sensitive staff knowledgeable of the local context. Future work might support and explore how these can be evolved further to become scaled up and sustainable shared resource market solutions (e.g. contracted by brands, multinationals and smaller local businesses) to providing workers with information, sharing intelligence between concerned companies and tracking worker conditions and issues, especially in difficult contexts such as those in WIF destination countries.
- The experience of the programme has been that mainstream trade unions were often (but not always) conspicuous by their lack of support for migrant women workers, due to a number of factors including local and national political economy considerations and vested interests, and attitudes towards migrant women in their destinations (many trade unions have a male dominated leadership). This is why it is important to employ a wider strategy of engaging with other bodies and mechanisms (women’s organisations/CSOs; worker centres; etc) that have the ability to understand and represent effectively migrant women workers in those particular localities.
- As noted as a theme across other outputs, experience from the delivery of this output supports the view that learning becoming isolated within ILO as it doesn’t fit with the ILO tripartite approach.

Output Number and Title	Output 3: Employers and labour recruiters adopt more accountable recruitment practices along migration pathways based on international labour standards and are subject to better monitoring and enforcement.
Output Score	A
Impact weighting (%)	15	Impact weighting revised since last AR?	No

Output Indicator	Logframe Target	Final Result Achieved
3.1. Number of new assessments of recruitment practices	At least 4 new assessments or reviews of recruitment practices will be conducted	7 Assessments / Achieved
3.2. Number of relevant recruitment stakeholders engaged in interaction with ILO and its advocacy partners	16 Strategic stakeholder engagements	30 Strategic Stakeholder engagements / Achieved
3.3. Number of better recruitment practices tested in a recruitment pathway	8 identified pathways	16 initiatives

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

The programme achieved all targets under this Output, but there was a variance between countries, where challenging contexts limited opportunities to impact.

An important feature of the programme’s work was to better understand recruitment pathways and actors, and make the clear point that many informal recruitment agents play a vital business role, and that attempts to criminalise all informal agents can leave women navigating a highly complex migration journey alone.

The programme also sought to increase recognition of migrant women as workers rather than just victims, increasing their agency and acknowledging both their value and their motivations. An important observation was made by a PCR respondent, arguing that women do not want to be ‘liberated’ from work. They want this work to be fair, decent and free. This is exemplified by broadening the approach from a narrower anti-trafficking lens towards a recognition of the value of destination work to women, and efforts to improve this experience.

WIF work to assess recruitment practices included research on recruitment channels by the Indian Institute of Human Settlements, which revealed the deep informality and importance of local networks within the domestic work recruitment pathway in its focal locations, as well as the varying importance of caste. Such intelligence is vital to develop and refine initiatives to limit exploitation in the domestic work recruitment process.

The programme developed a useful case study and organised recruitment pathway agents and other actors to explore ways of overcoming worker challenges, as well as working to create space for migrant women workers to express their concerns and suggestions. Lessons learned were compiled into a resource document Lessons Learned Part 2: Recruitment of migrant workers.

In India the programme supported an initiative resulting in an airport booth to assist migrant workers, and alongside important wider collective action support to SEWA the organisation was assisted to mediate collective employment during the Covid crisis. Achieving recruitment practice change in Jordan struggled, where despite an amnesty period declared by the government for migrant workers to rectify their status, challenges remained for migrant workers, particularly in the garment sector where difficulties persisted in correcting their situation without approvals from their previous employers.

Lessons learned through this output, and recommendations for future programming

- Particular challenges faced by the programme under this output included: considerable political connections and influence of those resisting change, including recruitment agencies; high unemployment; and considerable supply and demand challenges created by the Covid pandemic. For example, in Lebanon the adoption of the Unified Contract was watered down following pressure from vested interests. Law makers in certain countries also have personal stakes in the highly lucrative recruitment industry.
- WIF work should be retained, disseminated and tagged as a valuable resource to help navigate the challenges for migrant workers during future ‘shocks,’ whether these be pandemics or other crisis that place obstacles in the recruitment pathway.
- Respondents to this review felt that there were opportunities to increase the use of returnees knowledge and experience, and more tailored use of media. Global best practice increasingly recognises that survivors and those with lived experience should be fairly rewarded for their expertise and time as would be the case with other staff, and this principle should be built into activities that utilise their skills and knowledge. This then raises the need to explore sustainability models to grow and spread the use of fairly-rewarded returnee expertise.
- On a related point, due to low connectivity it was demonstrated that door-to-door information services were effective at building awareness and options among pre-migration women. To scale this would of course require considerable resource to fund such door-to-door campaigns across wide geographies and populations, which also raise the need to explore sustainability models if this is a methodology to be further employed.
- Beneficiaries appreciated activities to raise awareness of more local opportunities, however increased support for these alternative livelihood opportunities was raised in relation to the decision-making stage of the recruitment pathway journey. It is important to ensure that efforts to work with pre or post migrant scenarios tap into the wider inclusive economic development community of global practice, to ensure that initiatives do not reinvent alternative livelihood approaches, but combine the best of the migrant worker thematic expertise with the best expertise from the inclusive economic development community, and not in isolation from each other.
- As with other activities in this area of work, record should be made of unintended consequences, both to inform others and to build mitigations into project designs. For example, it was observed that in a counter reaction to project work, some recruitment agencies used this to try and influence against policy changes they did not favour.
- It was felt that there could be an increase in developing more use of safe space channels for migrant workers to network, interact and obtain information, especially through social media.
- While the role of migrant workers’ own embassies in destination countries should be an important channel for resolving migrant worker issues and grievances, future attention might also be paid to the role of embassies of those countries whose businesses might be directly or indirectly impacting worker rights and support, as further avenues for influencing improved conditions.
- Building on the studies and learning around recruitment agencies and pathways, and broadening the expertise focused on this theme, there might be opportunities to explore with market systems and private sector development experts whether new recruitment agency business models might be supported to evolve away from the more challenging, entrenched and vested interest models. There continue to be negative practices, such as where existing agencies allegedly accept payment for recruitment services paid for by companies looking to ethically recruit, and then discreetly double charge migrant workers, including sometimes through bullying and threats to both them and their families, or perpetuating local beliefs that if recruitment fees are not paid, it must mean that the job on offer in the destination country can’t be a good one.
- Beyond this, a degree of market consolidation around better recruitment agencies might be encouraged, for example employers sharing knowledge or migrant workers rating agencies against good and exploitative practice, allowing the market to gravitate towards and favour the better agencies. This would require evolving a model that addresses the market system failures and encourages inter-employer knowledge sharing and collaboration, while ensuring sufficient testing and monitoring of this theory of change.

Output Number and Title	Output 4: Advocacy work ensures that policy makers have improved knowledge and commitment to reform laws and policies to protect migrant worker rights.
Output Score	A
Impact weighting (%)	15%	Impact weighting revised since last AR?	No

Output Indicator	Final Logframe Target	Final Result Achieved
4.1 Number and names of advocacy networks effectively bringing knowledge to policy makers	15 Advocacy groups for each policy initiative	At least 50
4.2 Number of policy knowledge products (e.g. policy brief) produced or policy reviews conducted and communicated to policy makers.	15 policy briefs or policy review processes of which at least five at a regional or global level.	111 (86 national and 25 regional)
4.3 Number of policies targeted with evidence of technical advice and recommendations.	25 (13 South Asia; 12 Middle East)	66 (29 South Asia, 37 Middle East)

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

As the WIF programme has matured – including its research and evidence base – the ILO and its partners have been able to ensure an increased focus on advocating for reform of laws and policies, and have exceeded the targets for this output, in some cases significantly.

ILO coordinated an extensive set of advocacy activities under this output, including:
- Building collaborative advocacy networks of individuals and organisations able to share evidence and experience, and bring their respective influencing capabilities to bear in targeting policy-makers;
- Sharing evidence and lessons with policy makers and stakeholders through multiple events, conferences, meetings, webinars and other engagements and communications at the local, national, regional and global levels;
- Closely supporting or co-organising consultations on new, government laws and practices, such as on domestic workers bills at the state level, and national anti-trafficking legislation.
- Producing over 100 knowledge products for policy makers covering both broad lessons on trafficking and migrant rights, as well as focussed on more specialist areas such as fair recruitment in the garment sector or fairer trials for migrant domestic workers.

The independent End of Term Evaluation found ‘clear examples of how research contributed to a change in law or policy’ and stakeholders interviewed for this review commented that the programme’s advocacy efforts were well founded and well-targeted.

However, while targets were surpassed, the programme has been operating in a wider policy environment that is highly unfavourable and showing signs of deterioration, in line with wider evidence of a general rollback of rights across the region. This has made it more difficult to achieve the intended, (and more enduring) outcome of strengthened legal systems, policies, and practices. In addition, there is not comprehensive evidence of whether the events and activities delivered under this output resulted directly in the desired improved knowledge across all the key, targeted policy makers. Taken together with the score of ‘A’ for the dissemination work over 2023-24 (see below), the score for this output is therefore judged to have achieved A overall.

Despite the challenging political-economic contexts, as the evaluation notes, WIF delivery partners managed to develop good relationships with governments and build strong advocacy networks, which meant the influence remained broadly speaking as effective as it could be during the programme. The Evaluation documented a range of “concrete successes”, contributing to strengthening legal systems, policies and practices on safe labour migration and counter-trafficking. WIF effectively advocated against flawed elements of the Anti-Trafficking Bill in India, contributed to increasing penalties on human traffickers and increasing funds for victims in Jordan, helped reform of judicial practices around litigation involving Migrant Domestic Workers (MDWs), with the aim of reducing the number of women detained on false charges. Some research had direct impact, i.e., the Situational Analysis of Migrant Workers Stranded on the India- Nepal border resulted in allowing the entrance of migrants to the country. And in Lebanon, WIF successfully helped to raise public awareness of the discrimination of migrant workers in the judiciary system.

WIF has also successfully advocated against laws that ban women’s migration (e.g. in Nepal and India), which can increase women’s vulnerability, however gains here were not sustained as a result of new and less favourable political contexts and drivers (for example, new bans were re-introduced in Nepal). There have been other setbacks faced by the programme, for example in Bangladesh (expansion of mandatory pre-departure training from one month to two months), in Jordan (a decision to exclude domestic and garment workers from new occupational mobility rules, and a new collective bargaining agreement legitimising a decline in real cash wages of migrant workers) and in Lebanon (e.g. a new bilateral agreement with Ethiopia that undermines legal protections for domestic workers).

However, as has been expressed by some stakeholders, WIF’s success in this area has been to help ‘hold the line’ and avoid a deeper regression of laws and policies that would have been more harmful to women migrant workers. And the Evaluation notes that overall, the research and advocacy work “was extensive and contributed to the effectiveness of WIF”.

Key outcomes achieved in India include:
1. WIF research has supported evidence-based policy-making, for example sensitising central and state government to the pitfalls of restricting women under 30 to migrate for work (which often leads to more harmful outcomes as it forces them to use unsafe channels). As a result, Kerala state is now ready with a draft legislation on domestic work that addresses this, and the states of Tamil Nadu and Jharkhand have also expressed interest and taken steps in this direction.
  [note] The ILO and its constituents have worked to promote recognition and legislation for domestic workers throughout WIF 2. At the national level, support for drafting a National Policy for Domestic Workers (pib.gov.in) was provided. In Kerala, SEWA submitted a draft bill. The state government announced 8 hr work-days, weekly off: Kerala to bring in law for domestic workers (thenewsminute.com) Sustained follow up was carried out towards finalisation Kerala government drafting Bill to provide job security to domestic workers, home nurses - India Today WIF received a request from Labour Commissioner, Jharkhand to present lessons learned and inputs towards a bill under consideration. WIF participation was requested in meetings and consultations organised by the Tamil Nadu Human Rights Commission and Women's Commission to discuss a draft legislation. A draft bill has been prepared in Tamil Nadu and Delhi with inputs from trade unions that were supported by WIF. This demonstrates progress on issues that WIF has been advocating and working with government on, however this PCR does not seek to claim that these outcomes are wholly and solely the result of WIF’s work.
2. As a result of WIF’s advocacy efforts, the Government of India is more amenable to taking up the issues facing the unorganised sector. For example, it has taken advice from the ILO on how best to include domestic workers on the government’s E-Shram platform, providing workers with access to various benefits such as a pension, death insurance or financial aid in case of personal injury.
3. The Government of India has shown willingness to include domestic work in the Minimum Wages Act.
  [note] Domestic workers have been included in the schedule of employment under the Minimum Wage Act in some states such as Kerala, Andhra Pradesh, Jharkhand, Maharashtra, Tamil Nadu. Please see Press Release Ifrma Page: Press Information Bureau (pib.gov.in) which mentioned that domestic workers will be covered under the Codes enacted in 2022 however, the rules are yet to be notified. A contributory pension scheme has been rolled out under E-shram portal. Please also see union budget: Budget 2024: Domestic staff may get minimum wage, pension ahead of general elections - The Economic Times (indiatimes.com). This demonstrates progress on issues that WIF has been advocating and working with government on, however this PCR does not seek to claim that these outcomes are wholly and solely the result of WIF’s work.
4. ILO is now called upon by state and national government to give its views and position on various matters related to women workers in different sectors (including domestic work).

In the specific period since the last FCDO Annual Review, WIF 2 further consolidated networks on domestic worker rights in India and in Lebanon, developed a legal manual for judges to uphold the rights of domestic workers and prioritised disseminating research and lessons learned for regional and global policy makers. This was in response recommendations from the previous Annual Review and the programme’s Advisory Group. For example, WIF held workshops and discussion panels with stakeholders in Delhi, Dhaka, Kathmandu, Beirut, Geneva, London and Brussels.

Further dissemination and advocacy activities in 2023-24
As detailed in sections A and F, FCDO provided additional funding of £125,000 to support an extension to WIF 2 that focussed exclusively on deeper dissemination, engagement and advocacy over 2023-24, and agreed an additional logframe and set of targets for this.

From June 2023 to August 2024, 23 dissemination events were held, including online and in-person events and invited presentations organised by ILO constituents, stakeholders and development cooperation donors. A wide range of audiences were targeted and attended these events, including donors and governments, practitioners, academia and trade union members. Efforts also focussed on a wider geography – given feedback from the Evaluation, Advisory Board and other stakeholders on the global relevance of WIF 2’s lessons – and activities were held across the Asia Pacific as well as Africa, Central Asia, Europe and Latin America.

During this extension period, ILO also developed a new (and free) training course at its International Training Centre, based in Turin, with 6 modules based on the lessons identified from WIF2. In addition, ILO delivered a series of communications products, such as the publication of studies as well as video of impact stories, and a WIF website/blog. WIF’s sustainability was also supported during this period through a proposed engagement with Alliance 8.7 on WIF’s lessons as well as the experience of workers’ centres, and by initiating future seminars with ILO’s Global Business School Forced Labour Network.

In terms of quality and timeliness of delivery, it is noted that ILO experienced delays on a few deliverables across the extension period, for example the ITC training course was initially intended to be finalised by February 2024 but will instead be launched in early 2025. There have also been some budgeting and forecasting difficulties, for example with some underspend at the end of the extension period. However, all outputs agreed for this work have been successfully delivered and to a decent standard of quality, which warrants a score of ‘A’ for these outputs.
[note] This is judged from available evidence by the FCDO PCR and programme teams. Evidence included ILO Technical Progress Report, September 2024, and activities and deliverables the programme team looked at. Activities and reporting for this period of work took place after the external evaluation of the main programme concluded so has not been within scope of the evaluation, however represented a very small proportion (~1%) of the UK’s overall funding for WIF2.

Lessons learned through this output, and recommendations for future programming

The Work in Freedom programme has documented an important set of lessons for future policy-making in this field. These include:
[note] These are documented across a range of publications including: Summary of Lessons Learned from Work in Freedom or more detailed lessons on: Outreach to migrant women in areas of origin; on Recruitment; and on Interventions in destination countries.
1. Policy responses need to address the main drivers of forced labour, which are the scarcity of decent jobs and absence of adequate social protection. Focusing only on targeting the perpetrators of abuse or on rescuing victims, while very important, is less likely to yield a long-term and sustained reduction in forced labour and trafficking.
2. Policy makers should focus on improving working conditions, for example, through stronger laws, regulations, policy guidance and effective monitoring and transparency. Policy makers should bring all excluded occupations or types of workers under the fold of general labour law protections. Vulnerable workers such as migrant or domestic workers are often excluded from full labour protections that guarantee fundamental principles and rights at work. Regulation of recruitment, for example, often focuses on instituting more formalised recruitment processes, however if the jobs that migrant women end up working remain abusive, and if working conditions do not improve, any type of recruitment model however well intended cannot ensure a decent work outcome. Focusing on working conditions is also, ultimately, more important than educating workers about potential risks they face in their destinations because migrant workers often have little power and few avenues to address abuses directly with their employer or through local authorities.
3. Anti-trafficking measures should not inadvertently increase harm. Some laws, policies and practices can infringe on women’s social, economic and political rights, especially the right to work and freedom of movement. For example, if governments, families or communities prevent women from migrating in an effort to protect them, this limits their freedom and choices, and can mean that they take more dangerous migration routes or break all contact with their families, who are then less able to help if needed. Similarly, criminalising all informal recruitment agents (who play a vital business role) can leave women navigating a highly complex migration journey alone.
4. Legal channels into formal work can also lead into abusive labour situations. Programmes and policies should be careful not to promise migrant workers that they will avoid abusive situations if they follow formal migration channels into formal workplaces. It is important to neither stop women from migrating nor encourage them to migrate as both can result in harmful outcomes.
5. Freedom of association and collective bargaining are critical for migrant workers. Even in countries where these are not banned, in practice they remain a distant reality for the significant majority of migrant workers – especially, but not limited to, live-in domestic workers and garment workers living in hostels. If migrants can’t access guidance and support in their destinations, reducing their vulnerability to forced labour will be unsustainable in the long run.
Programme-level lessons include:
- WIF could have built on its research to produce baseline studies on law and policy in the various countries which would offer direction for future advocacy.
- As noted by a number of stakeholders interviewed and in the external programme evaluation, while WIF has uncovered and documented some critical lessons in this field, ILO has been slow to adopt these within its wider operations and policies at the global level, including through its headquarters in Geneva. It is recommended that ILO conducts a thorough review and assessment of the implications of WIF lessons for its wider work to identify clear opportunities for longer-term and sustainable impact.

Output Number and Title	Output 5: Improved analytical understanding of risks and vulnerabilities in the migration process leads to improved intervention measures and evidence bases [Contributes primarily to outcome 3]
Output Score	A
Impact weighting (%)	25%	Impact weighting revised since last AR?	No

Output Indicator	Logframe Target	Final Result Achieved
5.1 Number of research activities conducted to understand gaps in knowledge on emerging vulnerabilities to forced labour, policy determinants of forced labour, etc., in the targeted countries	Cumulative target: 6 major research papers completed and disseminated.	Cumulative: 30 studies completed
5.2 Number of new activities/interventions initiated by WIF to address research findings)	Cumulative target: / At least 5 WIF interventions are reviewed based on research findings	Cumulative total: / 9 interventions

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

The programme exceeded targets set for output 5, which focused on improving interventions and the quality of evidence, with research-based activities providing a comprehensive overview of migration processes.  30 research activities were conducted against a cumulative target of 6, and at least 9 interventions were initiated based on research findings. However, the evidence papers have not all been very accessible or well communicated, and uptake of the evidence has been good, but variable.

According to both the mid-term and end-term evaluations of the programme, WIF was unique in providing real-time insights into the problems associated with female labour migration.  WIF was heavily focused on research and knowledge generation, and by combining the large amount of information collected with a flexible implementation approach the programme was able to increase its effectiveness.  The ETE stated that “nearly all interviewees agreed that the programme has produced important and transformative research”. The MTE emphasised that the project was exceptional in using its research and extensive knowledge to reform its operations, and, in comparison to other initiatives, it was more effective in tackling human trafficking, because it focused on strengthening individual women’s agency.

The many interventions which addressed knowledge gaps included studies on industrial relations in Jordan and the Gurugram industrial area in India, which have contributed to the understanding of working conditions in the garment sector and how they could be changed by improving business practices, the regulatory framework, and workplace relations. These studies have the potential to impact future programming and also have the potential to raise the awareness of governments and provide an oversight into problems in the industry. WIF also supported an in-depth study of migrant women trajectories from Kerala, Telangana and Andhra Pradesh to Gulf countries for domestic work. The study reviewed research data collected over seven years, filling major research gap with significant findings used for advocacy purposes.

The WIF Advisory Board have stated that there were some excellent research reports from WIF and highlighted the large-scale study of paid and unpaid domestic work in Bangalore and Chennai, titled: Reproducing the Household which contains data drawn from surveys of nearly 9,000 households which the Board described as groundbreaking. Studying both unpaid as well as paid domestic work generated a wealth of data likely to “problematise received wisdom on the organisation of both paid and unpaid domestic work and the conventional policy responses to promoting the rights of paid domestic workers”.

Researching domestic work also increased the impact of the WIF programme. The sector is not fully analysed especially in the Middle East. Therefore, research on workers’ living and working conditions and surveys of employers contributed to the understanding of major problems.

In terms of interventions initiated by WIF to address research findings, a comprehensive legal review of jurisprudence on disputes related to domestic work and a study: “Migrant domestic workers before Lebanon’s courts: A system that buries grievances” recommended the Ministry of Labour review and adopt a unified contract for domestic workers. In response to the recommendations, the ILO advocated reforms accordingly and the Ministry of Labour agreed to create a Working Group on Kafala Reform. The Working Group, coordinated by the ILO drafted the contract and presented it to the Ministry of Labour. Focus group discussions undertaken by the Al-Hassan Worker Centre, and separately by GAATW, recommended in 2018-19 that training be undertaken for migrant garment workers on how to deal with sexual harassment in Jordan’s garment factories. The Worker Centre organised training sessions on “Responding to workplace sexual harassment” in September and December 2019. Model trials performed in Lebanon, which were informed by extensive research, raised awareness of the public to discrimination of migrant workers in the judiciary system.

Research publications and policy briefs published under WIF have also promoted International Labour Standards, including, for example, inputs to the draft anti-trafficking bill in line with relevant conventions such as C111, C181, Advocacy on Occupational Safety and Health.

Lessons learned through this output, and recommendations for future programming

All research activities should ensure that strong dissemination plans are built into the activities and allocation of resources from the outset to maximise value for money. It can often be that the dissemination and uptake of research takes longer than the research activity itself, and requires careful and considered approaches (for example understanding of and ability to operate in the political-economy contexts of the target audiences for the research, as well as strong communication and engagement capabilities.

D: Value for Money

VfM performance compared to the original VfM proposition in the business case

Independent evaluations of the programme, in particular the mid-term evaluation (MTE) and a final evaluation, judged the programme to have achieved a high degree of value for money. The mid-term evaluation completed in November 2022 assessed the value for money of the programme against the following criteria:

Economy: 1. ILO has tripartite mandate and expertise and reach across all countries. 2. Is recruiting local and regional partners with greater experience in organising unions and associations and in empowerment programming.

Efficiency: 1. Ability of partner organisations to inform and support potential, existing and returnee migrant women through unions and other types of solidarity groups. 2. Ability of ILO to continue to generate innovative ways of addressing long term intractable policy problems.

Effectiveness: 1. Number of women reached by partners who have enhanced decision making ability and agency. 2. Actions to promote policy reform that promotes rights and protections of migrant women and mitigate the effects of government actions that undermine these. 3. Catalytic replication of WIF initiatives.

The MTE concluded that indicators for Economy and Efficiency had been achieved, whilst those under Effectiveness had been constrained by unavoidable budget reductions introduced by FCDO. The MTE also looked at whether or not the programme had leveraged resources with other projects/programmes, and through partnerships with other organisations/networks, to enhance the programme’s impact and efficiency and commented that:

“WIF has been good at integrating its work into that of its civil society partners; all have talked about the WIF work as being fully aligned with their own organisational objectives. Nevertheless, the WIF resources have been instrumental to the partners being able to undertake the work they have. Some additional resources have been leveraged in Nepal, but not yet at the scale needed to ensure the full continuation of programme objectives. More attention will need to be paid during the remainder of the programme to how resources can be raised to ensure key activities are continued, with the Workers Centre in Jordan being one institution of real concern.”

In terms of funding, the MTE concluded that the programme had used its resources effectively, and demonstrated good value for money when the achievements from comparatively low investments in local partners was analysed. It also highlighted that the reduction in budget had unfortunately prevented the WIF programme from being able to test and explore the degree of scale up of activities that could have been managed in origin locations in India and Nepal, with the proven orientation methodologies, which could have been a real demonstration of the value for money of the approach developed.

In terms of effectiveness and whether the approaches used had been appropriate in achieving the objectives of the programme, the MTE commented that the interventions in countries of origin had been highly effective, whilst the tenacity of country of destination interventions continued to chip away at outdated and abusive systems and practices and inject opportunities for change. The MTE considered the immediate objectives had been achieved except where the necessary funding had not been available (e.g. community outreach targets in Nepal). The number and quality of publications has also enabled the programme to strengthen advocacy efforts.

The 2023 independent final evaluation concluded that overall, the programme was highly efficient throughout the whole implementation period particularly in its use of financial and human resources, and that collaboration with other projects and the ability of partners to request funding from other sources also contributed to this outcome. The report commented that:

In the last two years of implementation, sequenced annual budget reductions in programme funds were introduced and overall, 80% of the original budget was delivered. Despite that change, most activities reached the same targets as in previous years, and the Programme could manage with the resources remaining.

Overall, the Programme was highly efficient in its use of financial and human resources. Collaboration with other projects and the ability of partners to request funding from other sources also contributed to this outcome. Analysis of the Programme’s value for money showed a high level of efficiency throughout the whole implementation period.

Efficiency was achieved through synergies or cooperations with other projects or, in some cases, the support from the local government. For example, in Nepal, the staff explained that multiple other resources were used for completing activities. “Most of the activities at the community level are integrated with those of the local government. In terms of efficiency, there are examples where we coordinated with other migration projects or other projects.” For instance, women’s fora were organised by local government in Nepal Cost-sharing with other international organisations were also utilised, for instance, the British Council provided funding to some activities in the country. GIZ provided some activities in the Al-Hassan Workers’ Centre. In Lebanon coordination was set up with the FAIRWAY programme, and resources were shared in some activities.

The Programme also frequently helped migrants through increasing their access to government schemes in origin countries. Additionally, as mentioned above, pooling resources from other international activities.

The ETE also noted that WIF2’s efficient project management and use of partners were important factors mitigating the impact of budget reductions.

It is concluded therefore that the programme represented good value relative to the funding allocated over the 5-year period. Expectations were met or exceeded against most of the criteria above. However, a lack of granular and regular VFM reporting by ILO has meant this was more difficult to track. This review therefore recommends that ILO’s Annual Technical Progress Reporting process incorporates improvements that would achieve this.

E: Risk

Overview of programme risk during the past year and over the life of the programme, drawing on FCDO’s Risk Management Policy and Risk Appetite Statement and wider risk guidance.

The programme was exposed to a number of risks and issues over its 5 years of implementation, some of which were identified in the original risk log contained in the business case, but some were not anticipated and therefore had no mitigation plan in place. Risks and issues overall have been managed effectively with the ILO through a close and open working relationship, enabling the programme to continue to deliver results despite obstacles.

The most significant risks to the programme, in terms of potential impact, were related to funding and health shocks. January to March 2020, saw significant changes in terms of risk exposure for the programme. A pandemic, or any other global health emergency, had not been considered as part of FCDO or ILO risk management strategies and therefore mitigation actions were not in place when Covid-19 occurred. Initially, in the absence of information on the likely impact, FCDO actions were limited to accepting that certain activities would have to be postponed or cancelled, while maintaining a focus on the health and safety staff, stakeholders and those involved in the programme.

As the crisis deepened the ILO provided regular updates on the impact of Covid-19 on migrant workers and began to re-orientate activities on the protection of migrant workers affected by the crisis. In May 2020 ILO submitted a Project Document Supplement to FCDO on scaling up their response to the pandemic through WIF. This included re-orientating some research towards the impact of Covid-19 and monitoring the strategies that migrant workers have taken in response. The programme and its delivery partners also established safety and health measures for staff, constituents and other beneficiaries, stakeholders, contractors etc. Project beneficiaries were provided with material in local languages about Covid-19 transmission and precautionary measures at home/dormitory as well as at workplace. Considering this was an unprecedented situation it was managed extremely well. The External Advisory Board commented that WIF was able to find unexpected opportunities to advocate for the rights of migrant workers during the pandemic, and helped to support access to free Covid vaccinations, access to government welfare initiatives such as e-shram in India, and the conversion of undocumented immigration status under amnesty schemes.

The pandemic and other factors contributed to the second most damaging risk materialising. The financial stability of the programme started to become a risk midway through 2020 and continued into 2022. Partly through FCDO reprioritising funding to respond to the pandemic, and then later the availability of ODA reducing in line with a shrinking economy, resulted in both a significant reduction to the WIF budget, as well as introducing significant level of unpredictability to the funds that were available year on year. Some flexibility had to be built into the programme to cope with funding changes/challenges but ultimately the reductions were at a level where milestones indicators had to be reduced.

FCDO’s inability to provide the ILO with certainty on funding levels from year to year caused delays to agreements being set up or renewed, and in some cases meant work that could have gone ahead did not. One ILO technical progress report from that period noted:

“Uncertainty in funding situation delayed workplans and contracting processes generating additional administrative work and undermining attention to programme priorities. The programme had to cut funding for staff in Kuwait, and many implementing partners in countries of origin.”

It would not have been possible to mitigate the above risks entirely, even if they had been anticipated in the beginning, mainly due to the cause and impact being outside the control of the programme. They were however managed as far as possible to enable the programme to continue safely and deliver results.

F: Programme Management: Commercial and Financial Performance, Monitoring and Evaluation

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including VfM measures of economy and efficiency.

The implementing partner for Work in Freedom was the International Labour Organisation (ILO). The form of agreement with the ILO was a Memorandum of Understanding (MoU). The MoU was signed in March 2018, for a 5 year programme, starting in April 2018 and ending March 2023, with a total budget of up to £12,495,090. In June 2023 an amendment to the MoU was agreed to accommodate additional dissemination and lesson learning from the programme. The amendment extended the programme to 31 March 2024 (and later 30 June 2024) in order to carry out the additional work, and it also formalised a revised budget of £10,151,563, which took into account budget reductions made in years 4 and 5, and small uplift of an additional £125,000 for the dissemination and lesson learning. The amendment reduced the total budget by £2,343,527.

In terms of the management of the programme, the ILO have been implementing the Work in Freedom programme since 2013, which amounts to over 10 years across two phases. This has been a successful long-term partnership which was only possible due to their professionalism, experience in the sector, and a high level of competence, particularly in their ability to adapt to changing circumstances while maintaining focus on the key outcomes of the programme. As mentioned in the risk section above, the most significant challenges the programme faced were during the Covid-19 pandemic and budget constraints in the final years 4 and 5. To minimise the impact of Covid-19, the ILO were tasked to put together a proposal building on the existing results framework to take into account mobility restrictions, the unemployment surge and the increased vulnerabilities to forced labour among women workers in the domestic and garment sectors. In the face of significant budget constraints, the ILO were required to adjust the programme and revise output targets responsibly, while protecting the overall impact of our work. The ILO managed these and many other challenges professionally and at very short notice.

Commenting on Phase 2 of the programme, the independent Mid-Term Review noted that: “Programme staffing has been much improved this phase of WIF, and overall the management and staffing has been excellent.”

The final spend for the programme was just over £10m. The table below shows the budget schedule as per the original MoU and also shows the actual amount disbursed by year.

	Disbursed	Original MoU budget
Year 1	£2,177,300	£2,177,300
Year 2	£2,499,018	£2,499,018
Year 3	£2,720,736	£2,820,736
Year 4	£1,380,000	£2,499,018
Year 5	£1,243,446	£2,499,018
	£10,020,500	£12,495,090
Dissemination and Advocacy	£125,000	n/a
Total	£10,145,500	-

Years 4 and 5 show actual spend was approximately half of the original budget allocation which was due to FCDO budget constraints which were brought about by a number of factors including the reduction of the UK ODA commitment from 0.7% of GNI (Gross National Income) to 0.5%. As described above, the ILO worked effectively with FCDO to adjust the programme and reduce programme activity where necessary. As a result of FCDO financial constraints, the ILO had to stop making commercial commitments beyond the funds they have received. The uncertainty in the funding, particularly in years 4 and 5, delayed workplans and contracting processes in order to avoid the risk of the ILO making financial commitments FCDO could later not meet.

ILO’s financial management has been strong throughout the programme. Accounts have been managed effectively to ensure that payments were not made in advance of need. A running tally of commitments against available budgets were presented before requesting any new funding, which ensured FCDO only provided funding for known commitments across a 6-month period.

The ILO have provided annual audited statements as FCDO requires every year. The last Independent Auditors Report, dated April 2024, provided by Commission on Audit stated that:

“In our opinion, the accompanying consolidated financial statements present fairly, in all material respects, the financial position of the ILO and its controlled entity, the ITC, as at 31 December 2023, and their financial performance, changes in net assets, cash flow, and comparison of budget and actual amounts for the year then ended, in accordance with International Public Sector Accounting Standards (IPSAS).”

Programme-level approach to monitoring and evaluation

Due to resource constraints, the £500,000 originally allocated for monitoring and evaluation in the business case was removed from the budget. However, the International Food Policy Research Institute (IFPRI) were asked to evaluate different streams of work under the Work in Freedom Programme through a separately funded monitoring scheme to support complex programme evaluations. The WIF programme teams from Bangladesh, Nepal, Lebanon and Jordan participated in IFPRI organised Net-map & ROAD workshops conducted at the national level. Delivery partners of WIF in Bangladesh supported IFPRI in conducting a phone-survey on the impact of Covid-19 on women migrants.

As noted in the independent evaluation of the programme, the ILO had multiple feedback mechanisms in place to monitor relevance for beneficiaries. These included the publication of yearly technical progress reports (TPRs) and other activities designed to monitor various aspects of the programme. ILO’s TPR documents provided an overview of the programme’s status on a yearly basis and provided detailed analysis of progress against each output. The ILO also developed a stakeholder consultation system which ensured that implementing partners provided regular updates to the ILO WIF team, who verified the information and then informed FCDO on progress or any changes in the project implementation. For example, in Nepal, the partners of the programme conducted focus group discussions and interviews asking women migrants questions related to the payment of wages, access to various services, their experience of stigmatisation, and to gauge to what extent migrants found programme activities useful. This stakeholder feedback mechanism helped to identify emerging problems that could then be addressed by the programme efficiently, with research activities helping to identify the most viable and effective solutions and communication activities that facilitated coordination of actions.

In addition, the programme was able to reap strong benefit from the existence of the WIF 2 External Advisory Board. This was an independent group of senior academics and practitioners with expertise in the areas in which the programme operates, and was established to help hold ILO and FCDO to account and provide strategic technical direction, in support of overall monitoring and evaluation of the programme.

FCDO’s own monitoring and evaluation included conducting annual reviews of programme activities, in consultation with programme partners and stakeholders. ILO and FCDO regional and country-based staff also undertook field visits to monitor implementation of activities by programme delivery partners. However, this was significantly curtailed due to the impact of the Covid pandemic.

In October 2020, the Independent Commission for Aid Impact (ICAI) undertook a review of the UK’s approach to tackling modern slavery through the aid programme. This review looked at a number of UK interventions including the Work in Freedom programme. Overall, ICAI gave a score of Amber/Red for this review, meaning: The UK government has successfully raised awareness of modern slavery globally, but has not built sufficiently on the experience of others and lacks a systematic approach to analysing the problem and building evidence on 'what works' to develop an effective set of programmes in the future.

In their conclusion ICAI stated that: “The UK’s modern slavery aid portfolio remains in its infancy and has so far generated limited data on results. Programmes have generally been well managed and have delivered a range of useful activities and outputs, including practical support on safe migration, reducing child labour and support for returnees to reintegrate into their communities.”

Also noted in the review was positive feedback about the Work in Freedom programme in Bangladesh from those who had benefitted directly. The review commented that:

“we interviewed a number of women who had participated in training sessions. We found that they were able to talk with confidence about risks associated with labour migration and how to reduce them. They were informed about some of the formal requirements for regular migration, such as health checks, visas and age restrictions for accompanying children. They described being taught how to deal with cultural and language barriers, what the types of exploitation are and how to respond to them. They had been taught measures such as memorising important telephone numbers, registering with the Bangladesh embassy and keeping copies of their passports in safe places. We heard accounts that women had shared this knowledge with members of their communities who were considering migration. A number of participants had gone on to work as project staff or volunteers, using their lived experiences to help communication with other women in their communities.”

In October 2022, an independent mid-term review of the programme was undertaken. This review looked at the relevance and validity of the programme design and implementation strategy, the efficiency of the programme, vfm and achievements against outcomes.   It concluded that:

Overall, Work in Freedom has pursued an approach to anti-trafficking work that rehumanises women migrant workers, and in this process of decommodification lies the future seeds for reform. Despite the cuts to the community outreach work in South Asia in the last two years WIF has shown it is capable of consistently exceeding its outreach targets. With its programmatic work influenced by the topical research undertaken to explore migration contexts in countries of origin and destination, there is much the programme has been doing right. What is critical now is that ways continue to be found to build upon and expand this success.

As is standard of all ILO programmes, WIF was independently evaluated on completion in 2023. Some of the key conclusions from that evaluation were that:

the programme was highly relevant to the target population, female labour migrants. During the implementation their needs were assessed multiple times, and the activities were updated accordingly. Their access to services and institutions who could represent their interest increased due to the activities carried out by WIF. The challenges they faced due to gender inequality and inequality of socio-economic background, were also addressed to a degree, through activities of awareness raising, community work and advocacy.

activities addressed some of the needs of governments, as both countries were dependent on fair and safe labour migration (origin countries as a source of income, destination countries as a source of labour force). Origin countries were supported by increasing the safety of their nationals abroad and being provided technical support in the implementation of certain policies. Whereas destination countries were supported through some advocacy activities, for instance the work of the Kafala Working Group, because they were facing backlash against labour abuses from the international community.

project activities were valuable for partners, including trade unions and CSOs representing migrant workers, because they addressed the improvement of working conditions. To achieve their goals, trade unions and CSOs were supported in the form of capacity building activities. Some project activities also focused on including employer organisations more in the dialogue concerning working and living conditions of migrant workers. However, the programme experience shows that not all organisations considered this an important issue.

outcomes and outputs displayed a great level of coherence with the UN Sustainable Development Goals (SDGs) and with the Global Compact for Migration (GCM). Programme outcomes will contribute to the envisioned goals of gender equality, sustainable economic development, and productive, decent, and inclusive employment, as well as the reduction of poverty. The outputs, especially concerning research activities were also aligned with GCM goals.

the programme was aligned with the goals of origin countries: it aimed to increase the opportunities and safety of women both abroad and in their home countries, and it aimed to support safe migration. There was no evidence that destination countries issued plans or strategies that focused on migration, therefore coherence between their plans and the programme could not be established.

the programme achieved successes in increasing the ability of women to make choices during the whole migration process in all countries. Efforts to empower women were fruitful and women became more aware of their rights and of the consequences of their decisions. At the same time, external forces that constrained women could not be fully overcome. According to the findings, more activities could have been done to increase awareness of women’s issues in their communities as well.

the programme achieved progress in key actor collaboration, accountability, and respect along migration pathways, although much remains to be done. According to the findings, activities produced some changes in actors’ perceptions, especially in trade unions’ and origin countries’ governments’, and somewhat increased the respect of labour migrants. However, major external factors, such as the economic downturns in destination countries, decreased collaboration and accountability.

the rather ambitious outcome to strengthen legal systems, policies, and practices on decent work was not fully achieved in most countries as the policy environment was unfavourable and shown a deteriorating trend. The programme effectively blocked harmful policies in two cases. The programme’s contribution to this outcome in the form of conducting relevant research was noted by all stakeholders. However, in the case of the Kafala system, which significantly contributes to increasing the vulnerability of female migrants, it could not achieve changes due to multiple external factors.

initial signs of impact on the agency and awareness of women were seen, therefore their vulnerability was somewhat reduced. It was found that in all countries, female labour migrants became more aware of their opportunities and rights. Notably, since most causes of distress migration remained, individual-level impact will not result in reducing women’s vulnerability fully.

sustainability of the results can be achieved because implementing partners are highly committed to their work and will continue many of the interventions. The commitment of governments could also increase sustainability; however, it was not present in most countries. There is some progress in destination countries, who have priorities in the field of women’s empowerment. However, the fact that governments have not yet shown a persistent interest in sustaining results can threaten the long-term viability of the outputs.

Despite multiple challenges faced during the implementation, outputs have been achieved and the project met its targets. In certain cases, targets were exceeded.

Date of last narrative financial report	October 2024	Date of last audited annual statement	April 2024