Business Case
Summary Sheet
Portfolio/ Business/Country Plan Summary: SGA-PSEAH helps achieve Goals 3 (capability and coherence) and 4 (partnerships: promoting global action) of Development & Open Societies Directorate FY24/25 Business Plan.

Title: Strengthening the Global Architecture for Protection from Sexual Exploitation, Sexual Abuse, and Sexual Harassment (GA-PSEAH)
Programme summary (100 words maximum): / This programme will provide up to £20m over 5 years to support and develop global architecture to improve protection from sexual exploitation, sexual abuse, and sexual harassment (PSEAH) in humanitarian, development and peace settings. Key priorities are to: / Scale up, pilot and implement PSEAH global tools, cross sector initiatives and approaches. / Support PSEAH coordination and multistakeholder dialogue to address common challenges and to improve collective action. / Seek the PSEAH tools and ‘global public goods’ of the future through research and pilots to address critical gaps in evidence on what works to prevent and respond to SEAH in different contexts.
What is the rationale for UK Aid spending? (200 words maximum): / SEAH committed by people engaged in humanitarian, development or peace (HDP) work causes harm to people and communities, damages trust in our institutions and programmes, and fundamentally undermines the integrity and impact of UK and global efforts to build a safer, more equitable and sustainable future as set out in the 2030 Agenda for Sustainable Development and SDGs. / This programme will allow the UK to support and improve cross sector PSEAH standards and practices and so protect the integrity and delivery of FCDO, UK and wider HDP work. It will underpin and build on the UK’s strong reputation as a credible and influential leader in PSEAH and deliver on our ongoing commitment to harness our global convening power to drive up standards, best practice and coherence on PSEAH. / The programme is a successor to the Safeguarding Innovation and Engagement programme (ends September 2024). It will sustain and scale-up cross sector tools supporting international standards, vetting and data which are now evolving into PSEAH global public goods and, using the Common Approach to Protection from SEAH as an anchor for dialogue and collective action, support coordination and multi-stakeholder dialogue to improve coherence of PSEAH approaches and seek the PSEAH tools of the future,.
Programme Value: Up to £20 million		Country/ Region or Sector: Global
Department/Country Office confirmation of review processes		Departmental processes have been followed
Contact name		Jennifer Smith – SRO / Benjamin Jacques – PRO / Peter Taylor – Deputy Director, Safeguarding Unit, DOSD
Threshold for final approval of Business Case: Director > £5m but <£20m
Date of Approval of Concept Note:	25/03/24	Name and role of Approver: Minister Mitchell, Deputy Foreign Secretary
Date of Approval of Business Case:		Name and role of Approver: Christian Rogg, Director, DOSD
Programme Code:	AMP Start Date:	AMP End Date:
Overall programme risk rating:	Moderate
[note] As articulated in the 2023 International Development White Paper (pages 29-30: tackling SEAH is one of the four values that the UK is championing); 2020 UK SEAH Safeguarding Strategy; 2023 FCDO International Women and Girls Strategy (pages 19-24); 2022 PSVI Strategy and the Development and Open Societies Directorate Business Plan which commits to “maintaining the UK’s reputation as a global leader on SEAH, protecting the most vulnerable from harm by advocating for improved international standards, and preventing and responding effectively to SEAH cases through our programming”.

## Strategic Case

Context
SEAH committed by people engaged in humanitarian, development or peace (HDP) work causes harm to people and communities, damages trust in our institutions and programmes, and fundamentally undermines the integrity and impact of UK and global efforts to build a safer, more equitable and sustainable future as set out in the 2030 Agenda for Sustainable Development and Sustainable Development Goals.
Protection from SEAH (PSEAH) means taking all reasonable steps to prevent and actively manage and mitigate the risk of SEAH and respond appropriately when it occurs.  International efforts to tackle SEAH have strengthened since multiple high-profile cases led to a renewed focus and commitment, articulated in the outcomes of the International Safeguarding Summit in London in 2018. Policies, commitments and approaches to protect against SEAH have been adopted, but standards and systems are of varying maturity across HDP sectors, cases still happen frequently, and underreporting and lack of resource are still significant issues. Rising conflict, climate change and other causes of instability increase the risk of SEAH and the need for countries, organisations and individuals to adapt to evolving SEAH risks in contexts where HDP needs, work and organisations evolve, overlap and interact. It is more important than ever that international actors work together to improve and align PSEAH standards and approaches, collaborate and coordinate to test what works and share best practice, and to prioritise adequate resourcing and find efficiencies. This requires ambition, focus, leadership, coordination, scrutiny, and testing of new ideas and perspectives.
[note] See summary of Cross sector commitments and list of policies, training and initiatives.
This proposed programme will support global tools, dialogue and coordination to encourage collective action and share best practice, and through research and pilots to develop new PSEAH tools and approaches to address gaps in practice. Relatively tiny funding amounts (compared to UK and Global ODA) will enable the FCDO to influence and support a wide range of partners and activities, underpinning the UK’s reputation as a global leader in PSEAH and harnessing our convening power to drive up standards, improve the evidence base, and promote coherent and collective action on PSEAH across humanitarian, development and peacekeeping settings and so ultimately better protect 1) people from harm, and 2) the integrity and delivery of FCDO, UK and wider HDP work.
The programme will build on previous programmes and form part of a refreshed four-programme portfolio for 2024-30, alongside programmes designed to 1) Empower victims-survivors of SEAH, 2) build delivery partner capabilities at a local level and 3) improve vetting and case response.

Evidence Base

1. Collaborative, collective, cross sector tools elevate PSEAH standards and approaches and drive progress: The proposed programme is a successor to the successful 2018-2024 Safeguarding Innovation and Engagement programme. Since inception that programme has consistently scored A or above and has successfully supported and convened partners around a suite of new global tools which are improving coherent and collective action, informing best practice and translating into improved practice and impact at country, organisational and project levels:
  1. Core and earmarked funding for the Core Humanitarian Standard Alliance (CHS Alliance) is promoting key PSEAH standards, guidance and tools:
    1. providing coordination, guidance and support to CSOs and other actors and promoting the CHS PSEAH standards and best practice through a global community of practice;
    2. preventing the rehire of perpetrators through hosting the Misconduct Disclosure Scheme facilitated by the Steering Committee for Humanitarian Response. Established in 2019, the scheme has grown from around 2.7k vetting checks in 2019 to over 50k in 2023, with almost 400 known perpetrators excluded from recruitment processes.
    3. gathering cross sector data on PSEAH through the development of a harmonised reporting Scheme for SEAH incidents which enables the collection and reporting of comparable data on SEAH to analyse trends and patterns. Early findings from the pilot are already helping the sector better understand the overall issue of SEAH to prioritise corrective actions and resource mobilisation.
    4. training SEAH investigators through the Investigation Qualification Training Scheme (IQTS)), with a focus on training more women and staff based in low- and low-middle income countries to become qualified investigators
- The Humanitarian Quality Assurance Initiative (HQAI) certifies organisations against the Core Humanitarian Standard (CHS), helps build good practice, transparency and accountability across the sector, including a Facilitation Fund that helps national and local organisations to access support to meet the standard. Through our support the number of organisations certified as meeting the standard has grown from a baseline of 35 in 2018 to over 200 in 2024.
- The SEA-RO Risk Overview is a Composite Index that brings together indicators on a range of different factors that can influence the risk of SEA, helping actors make the most strategic use of limited humanitarian resources by prioritizing issues and countries of concern.
- The Safeguarding Resource and Support Hub (RSH) was started under the Innovation and Engagement Programme and has developed a strong global brand, underpinned by effective regional hubs which are in turn improving capability and approaches at national/organisational levels.
- The Common Approach to Protection from SEAH is a new online guide and tool to help all people and organisations working in HDP settings take action to protect people from SEAH. Hosted by RSH, CAPSEAH brings actions from existing practice, policies and standards together to provide a basis for more coherent and collective action and to act as an anchor and repository for multistakeholder dialogue and best practice on PSEAH approaches, challenges and resourcing.

1. Cross sector dialogue can identify opportunities for collective action and scale up best practice, but this requires vision, coordination and prioritisation:
  1. Since hosting the London Summit in 2018, the UK has built a strong reputation as a credible and influential global leader in PSEAH, convening other donors and actors across the aid sector to drive up standards and discuss implementation challenges. Safeguarding Unit convenes quarterly meetings of like-minded donors at the Technical Working Group (TWG) and wider international partners via the Cross-Sector Safeguarding Steering Group (CSSG) to track and maintain progress towards the implementation of SEAH standards across the aid sector. We also co-chair the OECD Development Assistance Committee Reference Group on Ending SEAH and support private sector engagement through the Safeguarding Leads Network, via British Expertise International.
  2. This international engagement has informed and promoted the development and use of the tools listed under para 1 above, and identified new areas that require attention. For example a Wilton Park event to discuss the Common Approach to Protection from SEAH identified common cross sector challenges and initiated a cross sector working group looking at sustainable resourcing requirements for PSEAH at global, country and organisational levels.
  3. While there is growing consensus about where sustained and scaled-up investment is needed to support and further develop the global architecture that underpins PSEAH efforts, and growing willingness to adopt common tools and approaches and to support pooled funds (such as the IASC PSEACap project administered by OCHA), there is also a continuing need for dialogue and coordination (and a growing need for engagement with national governments from developing countries), and some structure to ensure that priority issues are targeted, the correct long-term resourcing mechanisms are designed and supported, and stakeholders feel included and buy-in to collective approaches.

More research, evidence and piloting is needed to seek and build tools and approaches that can overcome known challenges: Despite the progress above there continues to be weak sector-wide evidence and agreement on what works to prevent and respond to SEAH across the aid sector.
- In 2021 the Safeguarding Resource and Support Hub (RSH) conducted a Global Evidence Review of SEAH in the Aid Sector which confirmed evidence gaps are still widespread. The report found a lack of clarity in terms of what constitutes an ‘effective approach’ to prevention and response efforts, few studies on the effectiveness of leadership and organisational culture change, and a lack of evidence of what works to address the needs and rights of people most at risk of SEAH.
- In order to build a robust evidence-base, research into what works to prevent and respond to SEAH needs to be contextualised and unpacked as well as accessible, with findings used to strengthen global and regional knowledge. Research which provides evidence of ‘what works’ can inform pilot approaches and then potentially improve the whole sector. Thematic areas for exploration include organisational culture change, sustainable resourcing models, improving response to cases (e.g. improving investigations), improving reporting mechanisms, community outreach, child/LGBT+/Disability safeguarding, and sectoral approaches (e.g. PSEAH in health and education).

Proposed action
The proposed programme will sustain and scale-up cross sector tools supporting international standards, vetting and data which were developed under the successful Safeguarding Innovation and Engagement programme, and are now evolving into PSEAH global public goods. Using the Common Approach to Protection from SEAH as an anchor for dialogue and collective action it will also provide structured support for ongoing targeted PSEAH coordination and multi-stakeholder dialogue to improve coherence of PSEAH approaches, and support research, innovation and pilots to seek the PSEAH tools of the future.

The programme proposes three components to:

1. Sustain and scale up PSEAH global public goods and cross sector tools supporting international standards, vetting and data harmonisation by providing core funding and technical support at the global level to
  1. the Core Humanitarian Standard Alliance (CHS Alliance), which delivers the PSEAH Index international standard, the global Misconduct Disclosure Scheme which screens thousands of applicants each year to prevent perpetrators moving between roles, and work to develop a Data Harmonisation tool to gather multi-stakeholder/cross sector information on SEAH cases.
  2. the Humanitarian Qualification Assurance Initiative (HQAI) which develops and owns methodology to assess compliance to the CHS PSEAH index.

1. Support PSEAH coordination and multi-stakeholder dialogue by:
  1. contributing to PSEA-CAP, a UN pooled fund to deploy dedicated full-time interagency PSEA coordinators to the most at-risk humanitarian emergencies, create a roster of experienced talent, provide PSEA guidance and technical support to field leaders, and inform global policy through a community of practice;
  2. funding the coordinator of the UK Safeguarding Leads Network;
  3. supporting cross-sector dialogues on common barriers and challenges through coordination and events (e.g. through Wilton Park events and engaging ministries from developing countries) and supporting UN and other cross sector coordination efforts as needed, including through piloting resourcing models and exploring ways to support key posts (either through direct funding or potential secondments).
2. Seek the PSEAH tools of the future by supporting research, innovation and pilots to address critical gaps in evidence on what works to prevent and respond to SEAH and develop workable solutions and accessible tools to overcome challenges, expand and share knowledge, and promote collective action.
The desired impact of programme is a world where fewer people are likely to be harmed as a result of SEAH perpetrated by people engaged in humanitarian, development and peace activities. While it remains challenging to attribute direct impact to this programme, the UK’s continued global leadership on protection from SEAH, along with the tools, guidance, and dialogue that the proposed programme will support, will contribute to increasing awareness, coordination and best practice on PSEAH and it is reasonable to expect this will drive up standards and improve practice, which will in turn reduce harm.
The desired outcome is that HDP actors have stronger and more aligned safeguarding standards, access to tools, guidance and support which promote a culture of zero tolerance to inaction on SEAH and embed PSEAH best practice across the sector.
The programme will target the bulk of funding to tools and initiatives where predictable and consistent funding is necessary to achieve lasting improvements. Failure to continue support risks losing the progress that has been made since 2018, and potentially shutting down or drastically reducing tools, networks and practices that are relied upon by multiple actors across the international community. This would harm the UK’s reputation as being a committed to tackling SEAH and undermine our credibility as a reliable partner on wider policy issues such as empowering girls and women. Sustaining support and encouraging more collective action will help actors across humanitarian, development and peacekeeping settings to improve PSEAH standards and practices and so better protect 1) people from harm, and 2) the integrity and delivery of FCDO, UK and wider HDP work.

Wider strategic considerations
Poverty reduction: This programme supports poverty reduction and gender inequality, in line with the International Development Act (2014), by supporting organisations that deliver poverty reduction programmes to prevent SEAH.
Public Sector Equality Duty and Disability: Evidence shows that SEAH is rooted in power imbalances and persisting inequalities mean that certain groups of people can be more vulnerable to SEAH being perpetrated against them. These include (but are not limited to) children, women and girls, people with disabilities, people disempowered by poverty and social exclusion, as well as racial/ethnic, sexual and gender minorities. Given that the majority victim-survivors of SEAH are women and girls, a focus on gender equality and vulnerability will be fundamental for this programme which should also make a positive contribution to all protected characteristics linked to heightened vulnerability under the Public Sector Equality Duty. It will seek to address gaps in the evidence base around how best to prevent sexual harassment, exploitation and abuse, and seek to empower and better protect women, girls, and other marginalised groups. The programme will request partners consider risk to these groups and to monitor that interventions do not have adverse impacts.
Climate and environment: There are no specific climate risks identified for the programme related to environmental protection, Paris Alignment or International Climate Finance. The programme takes a do no harm approach and does not invest in fossil fuels or go against any Nationally Determined Contributions.
Partnership Principles: We do not plan to provide any funding directly to partner governments and so the Partnership Principles are not relevant for this programme. Should an opportunity arise to work directly with a national government the Principles will be fully considered and implemented.
Safeguarding: It is vital that through our operations the programme does no harm and all reasonable steps will be taken to prevent social and environmental harm from occurring to local people and to respond appropriately when harm or allegations of harm occur.
Terrorism and financing: The risks associated with terrorism and financing for this programme are considered to be low. The Safeguarding Unit will work with well established PSEAH experts and delivery partners mainly and the nature of the deliverables (e.g. online tools, studies, evidence reviews, webinars, events etc) means the risks are low. Appropriate due diligence will be carried out.

## Appraisal Case

Theory of Change: The below Theory of Change summary provides our high-level thinking behind the programme. It builds on the UK’s Theory of Change for safeguarding against SEAH in HMG’s 2020 Strategy on Safeguarding against SEAH (see Annex A).

The following programme design options have been considered to address the needs set out in the Strategic Case and deliver the outputs outlined in the Theory of Change.

Option	Analysis/Recommendation
Option 1: Do nothing (counterfactual)	Not Recommended. Under this option the UK would stop support for global PSEAH tools, research, approaches and architecture when the current Innovation and Engagement Programme ends on 30 September 2024. This option has significant disadvantages: / UK is one of the major donors supporting global architecture, tools and dialogue for PSEAH. By ‘doing nothing’, we would be sending a signal that this is less of a priority for us, undermining years of progress and our international reputation as a champion for PSEAH and wider gender/human rights and preventing violence initiatives. This would open us up to criticism for abandoning a key pillar of the UK’s Safeguarding Strategy and misalignment with the standards, principles and actions we are promoting through the Common Approach to Protection from SEAH. / Not investing would undermine the investments FCDO has made since 2018 and present poor value for money. The Innovation and Engagement programme has created significant new global public goods for PSEAH. Continued/ new funding can build on this. Discontinuing support would put these at risk, and pull resources from the thousands of global users who rely on them. / The UK is in a good position to influence others. If we ‘do nothing’, we miss the opportunity to engage others meaningfully to build on progress so far and encourage a drive towards more collective action which could achieve a global shift in PSEAH action over the coming 5 years.
Option 2: Outsource the programme to an overarching delivery partner who would manage an international consortium to sustain existing tools, engage stakeholders and design and oversee new projects and innovations.	Not recommended. / In this option FCDO would enter into a contract with a lead partner who would be responsible for both programme delivery, and identifying and selecting best-practice training and offers to invest in, and for convening partners to ensure buy-in to and use of emerging approaches. This option would require less FCDO resource in terms of management and administration day-to-day, and should provide good coherence across the programme. / While the idea of supporting a new independent group tasked with improving PSEAH is attractive, this would be a significant cultural and governance shift for the PSEAH sector. At the moment there is not an international partner with the capacity, credibility and power to convene a wide range of international actors, including national governments, in this way. Significant work would need to be done to identify a model and governance structure that priority partners would trust and engage with. The costs of such a model are unknown. / The programme requires leadership from a national government who can engage donors and other governments in partnership, both bilaterally and through multilateral fora such as the UN. The UK is well placed to play this role. As a significant donor we are also well placed to leverage our funding to encourage the multilateral system and other delivery partners to improve PSEAH approaches (and to encourage other significant donors to work with us to do this).
Option 3: Manage in-house, selecting, funding and delegating projects to external partners according to their expertise, capability and capacity required to deliver	Recommended. / In this option, the overall strategic direction and coherence of the programme will be managed by Safeguarding Unit, with potential projects assessed and prioritised according to the level of need and buy-in perceived from our engagement with international partners. A preferred delivery partner will be selected to lead each project, based on their expertise and ability to deliver. / By leaning in to engage the wider sector, coordinate dialogue, agree priorities and develop approaches in partnership with others, the UK can help revitalise commitment to PSEAH across the sector, and galvanise action where most helpful. This approach makes the most of our in-house expertise, technical support, diplomacy and convening power while also engaging delivery partners and others where they can add most value and in the most inclusive way possible to encourage best practice, collective ownership and buy-in. We can also more easily flex the programme to track and manage value for money, risk and ensure it stays aligned with emerging UK priorities. This approach has worked well in the Innovation and Engagement Programme.

Summary appraisal of programme options

Appraisal categories:
- Effectiveness: How effective would this option be to enable delivery of the key output components?
- SGU Oversight: What level of oversight and control would FCDO have?
- Strategic Impact: How likely is this model to deliver the desired outcome?
- Risk: is the risk (to PSEAH efforts and UK reputation and programming) higher or lower?
- Cost: What is the comparative level of cost of this option?
Appraisal Score:
(L=Low, M=Medium, H=High)

Programme options	Effectiveness	SGU Oversight	Strategic Impact	Risk	Cost	Recommended
1. Do nothing	L	L3	L	H	M	No
2. Outsource	M	M	L-M	H	Unknown but anticipated to be H	No
3. Manage in-house	H	H	H	L	M	Yes
[note] While there would be an immediate management and cost saving from not continuing this sort of programme support, it is likely that FCDO over time would have to replicate many of the functions provided by the tools (e.g. recruitment vetting, more time spent on due diligence because partners aren’t being supported to meet standards by CHS and HQAI etc.). Time and costs associated with this are unknown but would be less effective, efficient and VfM than the current tools available.

## Commercial Case

The programme is unique in the PSEAH sector, as the only programme with a flexible approach to enable multiple cross-sector, multistakeholder projects through engagement, buy-in and endorsement with different implementing partners. Through supporting a range of innovative projects, the programme will sustain and contribute to the creation of new products that can be used as a global goods for public use, with the potential to have a wide impact, and create a step change in collective action to tackle SEAH. The recommendation from the appraisal case is to establish a source of flexible funding capable of supporting a range of partners according to their expertise and ability to help achieve programme objectives. This means that there will be multiple partners within the programme and a variety of delivery mechanisms (MOUs, grants, contracts) as appropriate to need, context and delivery partner.

An early market engagement (EME) survey was conducted in May 2024 and showed that there is wide interest from organisations with expertise across the sector in engaging in this type of work. Themes and key principles relevant to this business case which emerged from feedback include:
- Strong (universal) support for collaborative partnership working, across sectors, with most partners showing flexibility on whether to be lead or downstream partners, depending on the project objective and how it relates to their area of expertise.
- Significant importance placed on the need for delivery partners to have strong expertise in PSEAH and broader gender responsive models and operations, as well as strong awareness of and alignment to current global standards and best practice on PSEAH.
- Advocacy skills and the ability to convene partners was also highlighted as important.
- Respondents agreed that programming needs to be flexible and agile programming structures in order to adapt to emerging or changing risks, opportunities and contexts. Also the need to provide a mix of core funding to ensure stable, sustainable progress and earmarked funding for activities and specific projects.
- Respondents flagged the importance of ensuring that lessons learned from organisational, local, national and global contexts inform each other.
- Assurance that our early thinking on potential areas of research, studies etc to address gaps in evidence and architecture are shared by PSEAH experts.

The Innovation and Engagement Programme has given us a good understanding of the supply base. Delivery options for work at a global level tend to sit with a small number of key multilateral and INGO partners. Over 60% of planned funding will be to sustain and/or scale up existing projects through their delivery routes with current partners. Delivery models across the three components are expected to be as follows:

Sustain and scale up PSEAH global public goods and cross sector tools supporting international standards, vetting and data harmonisation – this will build on the Innovation and Engagement Programme and agree new MOUs and workplans to provide core funding and technical support at the global level to the CHS Alliance and Humanitarian Qualification Assurance Initiative (HQAI). Funding under this component is therefore expected to start as soon as the programme goes live (expected Oct 2024).

Support PSEAH coordination and multi-stakeholder dialogue – this will also build on the previous programme through continuing to support the UN pooled fund PSEA-CAP and funding the coordinator of the UK Safeguarding Leads Network. However the programme will also need to be strategic and flexible to be able to seek out, prioritise and support new opportunities and ways to support cross-sector dialogues, coordination and events. Two Wilton Park events (on sustainable resourcing for PSEAH and on Accountability) are being developed, within wider thinking on how to use CAPSEAH as an ‘anchor for dialogue’ on PSEAH challenges and approaches at global, national and sectoral levels. The CAPSEAH resourcing workstream is also expected to propose potential models to resource PSEAH efforts which could be piloted. We will also engage other donors, the UN and other multilaterals to prioritise and explore other ways to support cross sector coordination efforts as needed (e.g. through funding key posts or potential secondments in the international system). The programme is expected to support CAPSEAH rollout and dialogue over the remainder of FY 24-25, and over this time a costed plan for structured support for dialogues and coordination over the remaining lifetime of the programme will be produced including analysis of potential partners and delivery routes.

Seek the PSEAH tools of the future by supporting research, innovation and pilots - a strategic overview and delivery plan for the research and innovation workstream will be worked up (with the programme team, Commercial and through consultation with the sector) and approved over the first year of the programme. We will retain a flexible approach on mobilisation time and adapt as needed (e.g. ensuring we are able to take advantage of any immediate proposals or opportunities that are strongly aligned to programme objectives and are clearly competitive) but it is expected that this component will not be fully mobilised until FY 26/27 and will factor in availability of funding in FY 25/26.

For each component, Safeguarding Unit will ensure PRoF guidance is followed, especially around effective management, protection of vulnerable populations, and seeking the best VfM. We will use MOUs and Accountable Grants and explore pooled instruments (MOUs/AGs) to test more sustainable collective funding models at global/regional/national level. Where a tender is required (most likely under component 3) we will explore the best route, in collaboration with Commercial, wherever possible using existing framework arrangements to take advantage of speed of contracting, flexibility around contract size and pre-negotiated terms which support VFM. For example, the Education, Social Inclusion and Gender theme under the FCDO’s Global Development Delivery (GDD) Framework Agreement aligns well with the proposed programme objectives and should provide access organisations currently offering the needed expertise, reputable services and efficiency.

All delivery partners will be managed through performance criteria, including delivery against workplans with milestones, and including key performance indicators (KPIs) where appropriate (at a minimum (i) Quality delivery of key deliverables and (ii) Timely delivery of key deliverables). These will be agreed with partners before funding is agreed (and for tenders set out in the terms of reference, in the pre-procurement stage). We will build in flexibility to the programme, so that delivery continuously informs implementation.

Key Cost Drivers
Delivery partners will be expected to demonstrate that their costs, fees and charges are competitive and in line with, or more competitive than market norms. We will agree costed workplans for each project and closely monitor risks that may drive up costs as part of our routine programme management. We will seek additional funding and co-funding investment from other sources and pool funding where possible, to embed collaboration, ensure wide buy-in and long term sustainability of tools.

Value for Money
Enabling the creation of open access, sustainable ‘global public goods’ means the programme benefits are not just limited to its lifetime and therefore indirect impacts are high. FCDO will also actively engage with other donors and funders to encourage engagement and contributions to support project initiatives, in order to reduce UK burden share and build their long term sustainability. Ensuring and measuring VfM will be emphasised with all partners across the programme lifecycle.

The distress (unquantifiable) and cost (lost income, psychosocial impact, professional support required) to individuals of sexual abuse, exploitation and harassment is very high. Emerging thinking from the CAPSEAH Resourcing Working Group shows that proactive investment to prevent incidents of SEAH can save organisations the more substantial costs associated with investigations, legal proceedings, reparations, and the cost of rebuilding trust and credibility with communities, partners, and donors, and repairing impact on funding flows.

The programme will ensure VfM as set out below:
- Economy: The bulk of programme funding (over 60%) will go to organisations that are delivering global tools developed under the Innovation and Engagement Programme and have shown themselves to have the expertise to deliver innovation, engagement and results in a cost-efficient way. New implementing partners and projects will be assessed to ensure that they are competitive and that estimated costs are in line with or below market norms.
- Efficiency: Investing in global public goods and common PSEAH tools, working with other key actors to explore sustainable funding models at global and national levels, and ensuring different projects work together coherently will all help improve global efficiency on tackling SEAH. Within the programme, we will aim to minimise indirect costs so that they do not impact on programme effectiveness and all funding and activity will be monitored against agreed workplans to ensure good control and oversight.
- Effectiveness: The programme will seek to engage partners who have expertise and credibility in this area and are best placed to deliver projects and convene others. The programme team will monitor the effectiveness of projects, liaising closely with implementing partners and the wider sector to test buy-in, impact and long term sustainability.
- Equity: The programme seeks to create standards, guidance and tools that will help the international aid sector better tackle an issue which is driven by power imbalances and often underpinned by gender inequality, recognising that SEAH is known to particularly affect women and girls, minority groups, disabled persons and other groups who may have less power or be more marginalised. As such programme outputs are designed to be inclusive, fair, and considerate of the needs of those groups. We will engage with key stakeholders who have expertise in relation to key vulnerable groups to inform this. Data will be disaggregated where possible to ensure that vulnerable groups are reached.
- Cost effectiveness: We expect to build on existing strong VfM evidenced through that programme which maximised impact by leveraging relatively small funding amounts to influence and support a wide range of PSEAH partners and cross sector tools that reach large audiences and improve action at global, national and local levels.

## Financial Case

This Business Case seeks approval for up to £20m over a five-year period (October 2024 to October 2029).

The programme will be funded from the Development and Open Societies Directorate’s (DOSD) ODA budget and Resource Expenditure Limit (RDEL). All costs are ODA-eligible and will be accounted for on a resource basis. The funding for the first year, FY 24/25 will come from existing programme resource allocation for the Safeguarding Unit for the FY. Funding for future years will depend on the outcome of Safeguarding Unit’s budget bids in future Spending Reviews. We will seek approval from Management Accounts Group for the full programme commitment as the majority of spend will incur beyond the current SR period. FCDO will add a break clause to all agreements where funding crosses into a new SR period to allow flex to meet any changes in prioritisation or budgets.

Budget Breakdown: An estimated proposed breakdown of the programme budget is set out below. These are indicative figures that will be finalised on review of proposals and there will be flexibility in how the budget is allocated to allow unforeseen opportunities to be supported and so that activity can be scaled up and down as deemed appropriate. For example, should budget or other internal capacity constraints occur over the life of the programme, its flexibility means that we will be able to target resources on the core tools and engagement that others across the international system rely on, minimising wider adverse impacts on PSEAH action, while scaling back support for new research and innovations. Activities 1.1, 1.2, 2.1, and 2.2 sustain activities developed under the previous Innovation and Engagement programme and therefore have a high degree of confidence on annual costs. Activities under 2.3, and 3.1 are new areas of work with less predictability and certainty on costs but with high degree of control over what projects to support and to what degree.

Workstream	Activity	Estimated costs / FY 2024-2030
1. Sustain and scale up PSEAH global public goods and cross sector tools supporting international standards, vetting and data harmonisation	1.1 Core funding and technical support at the global level to CHS Alliance’s to support their work on / the PSEAH Index international standard; / the Misconduct Disclosure Scheme; / a harmonisation tool to gather multi-stakeholder/cross sector data on SEAH cases / 1.2 Core funding to the Humanitarian Quality Assurance Initiative (HQAI)	1.1: £1.021m per year / £525k / £66k / £430k / 1.2 £400k per year / £1.421m per year / (£7.11m over 5 years)
2. Support PSEAH coordination and multi-stakeholder dialogue	2.1 UK Contribution to PSEA-CAP (a UN pooled fund to support sustainable long term PSEA Country PSEA coordinators in high risk geographies) / 2.2 Funding for a coordinator of the Private Sector Safeguarding Leads Network (SLN) / 2.3 Ad hoc support for cross-sector and dialogue on common barriers and challenges and other potential support for UN and other cross sector coordination efforts (e.g. Wilton Park events working groups and smaller, high level roundtable events and policy dialogues including venue hire, catering, logistics, delegate management and additional convening costs such as travel, publishing materials, translations etc)	2.1 £600k (£200k will cover 1 position for 2 years) / 2.2 £60k / 2.3 up to £750k / Up to £1.4m per year / (Est £7m over 5 years)
3. Seek the PSEAH tools of the future	3.1 Support for desk reviews, studies, research and pilots to address critical gaps in evidence on what works to prevent and respond to SEAH	3.1 up to £750k per year, with lower spend anticipated 24-25 and potentially 25-26. / (Est up to £3.8m over 5 years)

Financial management: The SRO is ultimately accountable for the expenditure of funds against this business case. The PRO will work closely with the SRO to ensure the programme expenditure is in line with budgets and project workplans, and is compliant with the PrOF rules, and advise accordingly. The lead partners for delivering specific workstreams will be responsible for implementing activities, financial management, and narrative and financial reporting.

Budgets will be agreed with all programme partners prior to signing funding agreements. Payment schedules will vary by project and will be clearly set out in the agreements. All payments will be based on performance against logframe milestones, contractual/MoU criteria being met, and evidence of funding need. Payments will mostly be made in arrears upon successful delivery but payments may be made in advance where there is clear justification and approval in line with PrOF rules. Partners will submit quarterly financial reports and forecasts alongside project updates when requesting disbursement of funds. Forecasts will be revised regularly in accordance with respective delivery agreements. Any changes will be monitored at regular management meetings between FCDO and partners, then updated promptly on FCDO’s internal finance systems. FCDO will undertake occasional spot checks, supervisory field visits and annual reviews. We will also review annual audited accounts and annual financial reports as part of our continuous due diligence and annual reviews.

Based on experience from the Innovation and Engagement Programme, this programme will use MOUs and Accountable Grants to fund most projects. If a contract/tender is required (e.g. for research, consultancy expertise or comms) we will explore the best route, in collaboration with Commercial, and funds will be administered in line with FCDO’s standard terms and conditions. The programme may also explore pooled instruments to test more sustainable collective funding models at global/regional/national level.

Asset Management: No significant assets are expected to be procured or held by the programme or its suppliers. Studies, research papers etc will belong to FCDO but will be made publicly available along with tools and other global public good created and supported by the programme. Implementing partners will be required to maintain an up-to-date asset register of all assets purchased using UK funds in line with arrangements. Funding agreements will specify long term ownership of any assets after programme closure. FCDO will ensure that the disposal of any assets at the end of the programme maximises value for money in line with the PrOF rules. We do not expect to create any financial assets through the programme. For workstreams where the UN is the delivery partner any assets bought by a UN agency will become the property of the UN. The relevant UN agency will decide how to dispose of assets in line with its own procedures. UN agencies will maintain an asset register and share this with FCDO.

Financial Risk and Fraud: FCDO will mitigate fraud risks through risk controls:
- We will maintain a zero-tolerance approach to corruption and fraud and ensure adherence with the UK Counter Fraud/Bribery and Counter Terrorism legislation. The programme will be subject to annual reviews and delivery partners may be subject to additional assessments if deemed appropriate.
- FCDO will conduct a proportionate Due Diligence Assessment on all prospective delivery partners prior to signing any funding agreement. This will provide assurance that delivery partners have robust financial checks and measures in place and reduce risk, including through their own due diligence of any downstream partners (given the nature and size of work supported by the programme, the expected length of supply chain is short, reducing some risk). We will follow up and ensure recommended actions are taken for all suppliers throughout the lifetime of the programme.
- As set out above, ensuring suppliers have robust financial management and accountability systems, as well as reporting and auditing arrangements will ensure financial and fraud risk are adequately managed. Specific risk of fraud will be mitigated through enforcing robust and transparent monitoring and reporting processes. Any fraud committed must be reported to the FCDO promptly. FCDO procedures and requirements to report and act on fraud and aid diversion concerns will be made clear to all partners. Any changes to the delivery chain will require notification to the FCDO.
- The Programme Team will ensure all spend is properly accounted for, through close engagement with suppliers and scrutiny of financial reports. Instances of actual or alleged fraud will result in immediate action in line with FCDO’s approach on the misuse of public funds. The Programme Team will work closely with FCDO’s Counter-Fraud Team, to address any case of alleged fraud in line with the law and FCDO protocol.
- Financial reports, including certified financial accounts, will examine the effectiveness of control systems and fiduciary management. These will be complemented by partner meetings to discuss progress, risks and mitigation measures. These will be attended by the SRO, PRO and lead advisers. Finance will be a standing agenda item at all partner meetings.
- Invoices will be supported by a breakdown of the costs being claimed against each budget line. The PRO will be responsible for ensuring due diligence in the disbursement of funds, and for advising the SRO on any action deemed necessary.
- Partners will be required to publish transparency data in line with FCDO’s Standard Terms and Conditions.

Transparency: The PRO, with oversight from the SRO, will ensure transparency and accessibility of programme information and documents in accordance with FCDO requirements, adhering to PrOF rules. Programme information will be publicly available on DevTracker.

Exit Options: Break clauses will be built into funding agreements so that projects that do not deliver or that the FCDO deprioritises (e.g. if other funder contributions will ensure long term sustainability without UK support) can be stopped.

## Management Case

Governance and management arrangements
The programme will be managed through FCDO’s Safeguarding Unit. The programme will be overseen by the G6 Head of Multilaterals and Strategy as Senior Responsible Office (SRO). The SRO will escalate key issues and report to the Head of SGU who will agree the overall strategic direction of the programme and help ensure coherence with the wider SGU portfolio. The HEO Programme and Policy Office will act as PRO, leading on programme management and delivery. The programme will also draw on the wider Safeguarding Unit for policy and advisory expertise on particular projects.

The programme team will be as follows:
- The Senior Social Advisor will advise on international standards and our support to the Core Humanitarian Standards through CHS Alliance and oversee the Humanitarian Quality Assurance Index (HQAI - with support from the G7 Human Development Advisor).
- The G7 Humanitarian Adviser will advise on support for PSEA-CAP, data harmonisation and potential innovations and pilots that may emerge from international discussions on sustainable resourcing for PSEA architecture at global and national levels.
- The G7 Engagement lead will oversee our support and relationship with the private sector Safeguarding Leads Network (SLN), and any specific projects led by NGOs.

This model was successful in managing SGU’s Innovation and Engagement Programme, to which this programme is a successor. The team is fully resourced, and no additional staff will need to be recruited. The required programme staff time is likely to be 20% of the G6 SRO, 30% of the PRO on programme management, and 10% of each lead advisor: percentages will be adjusted on an ongoing basis factoring in SGU’s overall staffing and the wider work on safeguarding against SEAH.

The programme will also draw on internal and external expertise and advice as needed:
- SGU Programme Interlinkages - the programme will have a strong focus on strengthening lesson learning and seeking to scale up best practice where it is identified and may draw on networks, emerging lessons and opportunities from other SGU programmes where these offer insight into the effectiveness of global tools and approaches, or where they identify best practice that has potential to be scaled up into new global approaches, architecture or tools that address critical gaps in survivor support or sector capability. Interlinkages with the Capability Programme will be particularly important given the strong connection between global dialogue and collective approaches on PSEAH and CAPSEAH. Global work by HQAI across this programme and their local work under the Capability Programme will be overseen by the same adviser.
- Internal - SROs from other SGU programmes, the Safeguarding Investigations team, Audit, HR, Centre for Delivery, and Multilateral teams as needed.
- External – through dialogue and joint working with the Donor Technical Working Group and DAC Reference Group on SEAH (and bilateral donor engagement); the Independent Reference Group on SEAH (of researchers and academics with PSEAH/Gender expertise; the Cross Sector Safeguarding Group (including multilaterals and other organisations) or its successor, the CAPSEAH resourcing Working Group, and other PSEAH global experts and networks such as the Resource and Support Hub.

Selection criteria for agreeing to fund specific activities

The programme will be flexible so that it can respond to ideas, innovations and opportunities as they arise. The SGU monthly programme board meeting will be used to flag potential new projects and ensure balanced prioritisation, affordability and fit with the wider SGU portfolio.

Continued funding for existing tools will be based on proposals and agreed workplans with those delivery partners. Selection criteria for new projects and activities will be set in close collaboration with programme advisers and SGU senior leadership to ensure robust prioritisation alongside the flex and ambition needed to test new approaches. Key principles will be:
- Sustaining progress already made to ensure long term impact;
- Sufficient sectoral engagement, interest, support and buy-in for emerging ideas to ensure that they can be well user-tested and developed to meet cross sector needs and deliver impact for the most vulnerable (e.g. girls, women and marginalised groups).
- Clear articulation of the case for intervention and VfM, including assessment of alternative delivery and do nothing options;

Funding for existing tools (CHS Alliance (Misconduct Disclosure Scheme and data harmonisation), HQAI, PSEA-CAP and SLN) will begin immediately as a continuation of support under the Innovation and Engagement Programme. Support for the online platform for CAPSEAH will also continue until this is transferred to the new Capability Programme after March 25. Plans for PSEAH dialogue and coordination under the umbrella of CAPSEAH in 24-25 will continue under this programme and longer term plans for the life of the programme will be developed. A delivery plan to design the research and innovation workstream will be worked up and approved over the first year the programme.

Monitoring

A draft logframe is included in Annex X. This will be updated and finalised as workplans and proposals with delivery partners are agreed. The SRO and PRO will ensure that robust monitoring is in place and that work stream leads are accountable for this and overarching relationships with relevant delivery partners. This will include:
- Clear and regular (quarterly) reports from delivery partners against workplans, on project progress and milestones, linked to payments where appropriate.
- Agreed ‘reflection points’ to review progress to date, consider any barriers/setbacks, and assess the value of continued support.
- Feedback from other donors, multilaterals and international development partners (e.g. civil society, private sector, global south) on the influence and value of FCDO leadership in this area.
FCDO will meet at least quarterly with partners to review progress against agreed targets and assess key challenges to delivery – and adapt the programme where necessary. The programme team will also regularly engage with key stakeholders in the sector, including other donors, to amplify information about the programme, engage in peer learning and assess opportunities for collaboration or complementary engagement with other work in the sector. FCDO will receive quarterly financial and narrative reporting from partners.
FCDO will monitor overall programme performance through the Annual Review process. The programme team to assess progress against the outputs and whether results are on track, whether the components continue to represent value for money, and whether particular activities need to be scaled up or down. The logframe will be reviewed at least annually based on performance and adapted where necessary.
Risks and risk appetite

The overall risk rating is Moderate and the overall risk appetite is receptive. The level of risk is judged to be manageable, proportionate and within the Safeguarding Unit’s risk appetite given the potential high returns in terms of prevention of and safeguarding against SEAH.

Safeguarding Unit Risk Appetite
Strategy and Context	Policy & Programme Delivery	Public Service Delivery & Operations	People	Reputational	Financial & Fiduciary	Safeguarding
Receptive	Receptive	Cautious	Cautious	Cautious	Minimal	Minimal

The Programme is designed to support tools, research and dialogue which in themselves are intended to improve governance and address risk across the international sector. We consider the programme interventions to be moderate risk: the highest levels of support will go to previously supported projects and delivery partners with a stable and credible track record on delivery. New innovations will be funded proportionately to mitigate financial loss and while the risk of these projects failing to achieve desired impact is higher, even where projects fail to prove concept and move to scale up, they are still expected to provide valuable experience and evidence on what works and challenges to progress.

A draft risk matrix is below. This will be finalised and updated as the programme becomes operational and on an ongoing basis. It will evolve over the life of the programme as the global PSEAH landscape matures and as new innovations and approaches come onstream. All risks and mitigations will be monitored closely by the FCDO Programme Team in line with FCDO’s risk management framework. The SRO will be responsible for escalating any risks outside of appetite to the Safeguarding Unit’s Deputy Director, who will in turn approve escalation to the DOSD Director.

The top 3 risks are:
- Delivery: risk that projects don’t deliver in line with expectations, gather sufficient buy-in or otherwise fail proof of concept.
- Finance/Sustainability:
- Reputational: This programme will fund global public goods that will bring together the SEAH sector. Any sudden funding cuts may appear as the UK deprioritising SEAH.

Category	Description	Likelihood	Impact	Mitigation	Residual risk
Strategy and context	Increasingly difficult geopolitics and the rollback of women’s rights makes it more difficult to sustain international commitment to tackling SEAH, and the resulting loss of sector momentum and/or engagement on safeguarding means we achieve only weak gains in building capability, limiting impact	Possible	Severe	SGU will drive engagement and buy-in across the sector through its range of stakeholder engagement and communication mechanisms. We will work closely with multilateral missions and likeminded member states to tactically protect PSEAH as a priority.	Major
Policy and programme delivery	Multiple workstreams and partners requires complex management and risks lack of coherence, duplication of effort, reducing VfM & impact.		Moderate	SGU will oversee all programme components and support a coherent suite of projects, coordinate closely with partners and other funders to reduce duplication and maximise impact.	Minor
Policy and programme delivery	The Programme is unable to sufficiently engage and influence the PSEAH sector to adopt emerging tools and approaches, limiting overall impact.	Unlikely	Major	The programme will benefit from wide buy-in already achieved to tools supported by the Innovation and Engagement Programme, and increasing interest in, and commitment to, collective approaches shown through CAPSEAH engagement. Where lack of buy-in is significant and unlikely to change, the programme will be able to flex to prioritise promotion or change to models with more chance of success.	Moderate
Policy and programme delivery	Established architecture becomes dependent on UK support. If UK funding cannot be sustained, and other sources of funding aren’t found then this could leave gaps in global PSEAH architecture.	Possible	Moderate	FCDO will fund mechanisms that show the most promise to promote cross-sector use and buy-in. We will work closely with partners to set ambition and gain buy-in and funding contributions. Exit strategies and contingency planning will be developed to protect long-term sustainability of programme outputs. Where UK burden share remains high, we will make a virtue of this in comms.	Moderate
Financial and fiduciary	Funds are mismanaged or used for activities which do not align with Safeguarding Unit strategy and priorities	Possible	Major	FCDO will undertake a due diligence of partners, and they will be expected to do the same for all downstream partners. FCDO will maintain robust financial oversight and regular contact with partners to ensure delivery in line with agreed workplans.	Moderate
Reputational	Reputational risk to FCDO, where activities supported fail to gain wide buy-in or adequately consider or target vulnerable groups such as women and girls	Possible	Moderate	SGU will engage key stakeholders throughout the design and implementation of the programme overall and individual projects to ensure that they are designed and delivered in an inclusive way which maximises buy-in and relevance for vulnerable groups.	Moderate

Exit strategy and closure scenarios

Driving up standards and seeing real culture change across the international development sector will take time and require sustained commitment, flexibility and adaptation from the sector. This is reflected in the five-year implementation frame. Given the ongoing need for vigilance and action to tackle SEAH we judge it unlikely that the programme will close early, but the programme is designed to be flexible to meet new challenges and priorities as the safeguarding agenda develops or changes, and also to ensure we can halt support for innovations that do not deliver as hoped. If wider budget or other capacity constraints occur over the life of the programme, its flexibility means that we will be able to target resources on the core tools and engagement that others across the international system rely on, while scaling back support for new research and innovations. Exit strategies and break clauses will be included in funding agreements to allow the programme to adapt, change or reduce if needed.

Annexes

Annex A: Theory of Change from HMG’s 2020 Strategy on Safeguarding against SEAH