Programme Completion Review

Title: Product Development Research programme (PDPs)
Final Programme Spend £ (full life): £450,741,365.75	Review Date:	August 2024
Programme Code: 300341	Start Date: 1st March 2017	End Date: 31st May 2024

Summary of Programme Performance

Year	2018	2019	2020	2021	2022	2023	2024
Programme Score	A	A+	A+	A	A+	A+	A++
Residual Risk Exposure Rating	Major	Major	Major	Major	Major	Major	Major

DevTracker Link to Business Case (and any addendum):	Business case summary: https://iati.fcdo.gov.uk/iati_documents/43502608.odt / Business case addendum: https://iati.fcdo.gov.uk/iati_documents/58918556.odt
DevTracker Links to all logframes used during programme lifetime:	Original logframe: / https://iati.fcdo.gov.uk/iati_documents/45845355.xlsx / Updated logframe: / https://iati.fcdo.gov.uk/iati_documents/D0005604.xlsx

A. Summary and Overview

Description of the programme and what it has achieved

The UK Government created the Ross Fund Portfolio, led by both the Foreign, Commonwealth and Development Office (FCDO) and the Department for Health and Social Care (DHSC), to bring together its investments in anti-microbial resistance (AMR), diseases with epidemic potential, and neglected tropical diseases (NTDs). Within this, the FCDO leads three programmes that cover epidemic, implementation, and product development research. This annual review assesses the latter, the ‘Ross Fund Portfolio – Product Development Research’ programme, which supports the development of new products (such as drugs, vaccines, diagnostics and insecticides) for targeted diseases, including the full remit of diseases of emerging resistance (that are becoming an increasing global health security threat), NTDs (that affect over a billion people worldwide, causing disability, disfigurement and death), and diseases of epidemic potential (such as Ebola, which can rapidly spread if not stopped).

The total portfolio consisted of 14 separate product development partnerships and research projects:
Development of Triple Artemisinin Combination Therapies (DeTACT) to accelerate the development of these types of therapies for malaria (2018 – 2023).

Drugs for Neglected Diseases initiative (DNDi) for the development of new, effective treatments for neglected tropical diseases (NTDs) and diseases with emerging resistance (2017 – 2023).

Foundation for Innovative New Diagnostics (FIND) for the development of new diagnostic tests for epidemic diseases, diseases with emerging resistance, and NTDs (2017 – 2023).

Global Alliance for TB Drug Development (TB Alliance) to fund the development of new, safe, and effective drugs for tuberculosis (TB) (2017 – 2023).

Innovative Vector Control Consortium (IVCC) for the development of new insecticides to control insects that carry malaria, diseases of epidemic potential, and some NTDs (2017 – 2023).

International Partnership for Microbicides (IPM) for the development of women-controlled HIV prevention technologies (2017 – 2021).

Medicines for Malaria Venture (MMV) for the development of new anti-malarial medicines (2017 – 2023).

PATH Centre of Excellent for microarray patches (MAPs) to support the development of skin patches to simplify the administration of vaccines and drugs (2018 – 2023).

PATH Development of Devices, Diagnostics and Drugs to Address Women’s Needs (DAWN), particularly around childbirth (2018 – 2022).

PATH Diagnostics Group to develop and evaluate the performance and appropriateness of diagnostic tests to be used in conjunction with treatments for relapsing malaria (G6PD tests) (2017 – 2022).

1. PATH drug solutions (PDS) for the development of tools and treatment options for diarrhoeal and enteric diseases (2017 – 2022).
2. PATH Meningitis Vaccine Project (MVP) for the development of vaccines to prevent bacterial meningitis (against serogroups A, C, W, X and Y where no current vaccine is available) (2017 – 2023).
3. PATH vaccines solutions (EDD) for the development of vaccines for a range of organisms that cause enteric and diarrhoeal diseases (2017 – 2022).
4. Scientific Research Partnership for Neglected Tropical Snakebites (SRPNTS) to reduce morbidity and mortality of venomous snakebite by increasing availability and uptake of snakebite therapies (2018 – 2021).

FCDO’s funding for this type of product development (though not necessarily these partners) will continue under the Global Health Security and Ending Preventable Deaths (EPD) Research and Development (R&D) business cases. A competition is underway and funding decisions are expected by the end of 2024.

During its lifetime, the programme had several costed extensions, given its high performance, which means it ran for almost twice as long and spent almost twice as much as originally intended. However, in line with this, the output and outcome indicators more than doubled in ambition, again based on the high performance. Against an initial ambition to see between 4 and 8 products reach the market, the programme has supported 44 new products to reach the market (noting this includes 11 COVID-19 diagnostics that had a different development process to usual). Rather than the initial target of 125 publications per year, the programme has seen on average over 180 publications per year. Similarly, the PDPs have increased, and reached, their ambitions on policy influencing, market shaping, and capacity strengthening. Most importantly, this has translated into real-world impact and lives saved, including:
1.2 billion people have received an MMV supported product, saving an estimated 15.4 million lives and generating US$28.5 billion in economic benefits.

- More than 42,000 courses of TB Alliance’s new BPaL regimen, for extremely drug resistant TB, has been shipped to 48 countries and it is estimated that it will save an additional 15,000 – 43,000 lives by 2025.
- IVCC’s novel indoor residual spraying products are estimated to have protected 310 million people, averted up to 27 million malaria cases, and saved 40,000 – 68,000 lives.

For these reasons, and considering the overall performance against initial ambitions, the programme has scored an A++, reflecting that it has significantly exceeded high expectations. It is important to note that because of the programme’s high performance, targets have been regularly increased, which is why this programme scores more highly in the round than it did in individual years.

Major lessons learned, evidence generated and recommendations

Lessons:
A central lesson is that the PDP model works. This PCR presents not only the high performance of this programme but the findings of several wider assessments of the PDP approach and investment in neglected disease R&D. All the evidence supports that they are delivering on their missions and addressing the critical challenge of commercial market failures. Their approach to bringing public, private, and academic partners together seems to be efficient and effective.

Localisation is an increasingly critical issue but not necessarily straight-forward to address within global organisations. More work needs to be done to increase low- and middle-income country (LMIC) leadership and ensure there are genuine equitable partnerships with the global south. Increasingly, decision makers should be located in the countries affected by the diseases. However, this is tempered by the challenge that PDPs are conducting-edge laboratory research that requires very specific facilities. Whilst these are available in a few LMICs (e.g. Senegal and South Africa) they are not common, and building up this infrastructure and scientific context will take time.

Relatedly, COVID-19 highlighted how critical it is to have local production and manufacturing for equitable access. Whilst several PDPs have done more work in this space (e.g. FIND and MMV), it should also be a priority for PDPs to support this agenda and consider how they can support local production of their products.

Another key lesson from COVID-19 was the importance of anticipating unexpected delays and having contingency plans prepared. Overall, the most significant uncertainty for many programmes was unforeseen delays to trials in Africa, which are often on a project critical path to market launch. Positively, this has included opportunities to adapt their portfolios so they will be able to respond to the next outbreak more effectively.

There is a significant challenge around regulatory processes and the time (often years) between the end of a successful trial and people having access to the product. PDPs need to consider what their role is, which is not having full responsibility, and where they can make the most impact. PDPs should consider how to work together and with their funders to influence change. They also need to ensure they are planning for the regulatory processes from the outset of product design and engaging early with the WHO and target countries.

Whilst most of the PDPs have performed very highly, there are outstanding questions about their governance. The informal PDPs Funder Group has been an effective forum for collecting lessons and driving progress but ultimately does not have influence over the PDPs direction. In many ways this is deliberate given the PDPs have the scientific and technical expertise to take stop/go decisions on their pipeline and it is critical that the PDPs maintain the independence of their scientific advisory committees. However, funders could provide more guidance on overall strategic direction and remit (e.g. taking on new diseases or tackling access issues that are traditionally outside of R&D).

Whilst the PDPs have managed to maintain sufficient funding for their work, almost all cite increasing challenges during the last few years. This has been particularly true in terms of securing multi-year commitments and core (unrestricted) rather than project-based funding, which give the PDPs the flexibility to follow the science, minimises the risk, and reduces management overheads. Several have also specifically cited uncertainty over future UK funding.

Finally, the vast majority of PDPs are focused on infectious diseases. Given the effectiveness of the model, there is an urgent need for more PDPs addressing the needs of women and girls and sexual and reproductive health and rights (SRHR).
Recommendations:
The PDP model works and has exceeded FCDO’s expectations in terms of the number of products delivered, lives saved, and wider economic benefits generated. FCDO should continue their support for PDPs and, where appropriate, consider core funding which provides maximum flexibility and lowers management overheads.

Given the importance of localisation, FCDO’s new call for product development funding should (amongst other criteria) explicitly look for, and assess against, the existence and planned development of equitable partnerships and locally led approaches. It is important for FCDO to continue to champion the issue with the selected partners.

FCDO should work with future PDPs (selected under the ongoing competition) to unpack the types of activities they plan under policy engagement, capacity strengthening, and research uptake, so that a more tailored and therefore useful set of indicators could be designed. This should include discussions around reasonable expectations for PDP involvement in work outside their core mandate (e.g. manufacturing). Ideally these should combine quantitative indicators with qualitative case studies.

Combined with the above, the PDP reporting template should continue to be refined so that more consistent and clear reporting is achieved across the different partners.

FCDO should explore commissioning an independent assessment of the return on investment of FCDO’s product development investments, which could build on the work done by Policy Cures and others and bolster future value for money assessments.

PDPs should explore more opportunities to collaborate on policy influencing, particularly around streamlining regulatory processes, and look to conduct cross-partnership capacity-building to learn from each other’s relative strengths

Note: a summary of the evidence generated has not been included here as this is a research programme so that has been captured throughout sections B and C.

How this report was conducted

This programme completion review was completed as a desk review by the Global Health Research Team’s Policy and Results Adviser, who is an accredited Evaluation Adviser and does not work on any of the programme components. It included reviewing the last set of annual reports, all previous annual reviews, interviews with key internal stakeholders, and where necessary (for clarification) previous partner’s reports, supplemental documents, and websites.

Actions following approval of this report

There are no outstanding actions required after completing this PCR. Lessons and recommendations will be taken forward in selecting and managing the next round of PDP funding.

## B: Theory of Change and Outcome Assessment

	Starting point	Final result
Budget	£264,000,000	£450,865,817.03
Timeframe	1st March 2017 – 31st March 2021 (4 years and 1 month)	1st March 2017 – 31st May 2024 (7 years and 3 month)
Outcomes	Develop new products and evidence which can be used to control epidemics, control and eliminate targeted NTDs and reduce drug resistance: / i) Evidence demonstrating that FCDO funded research programmes have influenced policies, guidelines, plans, strategies, roadmaps, and/or leadership initiatives and products included in treatment guidelines / ii) Evidence demonstrating the benefits of research on gender equity or other vulnerable groups in the research context / iii) Number of products distributed / iv) Number (cumulative) of products registered in Africa, Asia, and Rest of the World	Final indicators were just (i) and (ii) – indicators (iii) and (iv) were dropped because different partners track products after approval differently and it was difficult to get consistent figures

Overall assessment of programme outcomes, sustainability and VfM

Overall, this programme has made exceptional progress against the expected outcomes and impacts. The individual programmes have built on their strong track records over previous periods of FCDO (then DFID) funding and, during the current funding period, have developed and/or brought to market 44 new products: eight drugs, two diagnostics, and four insecticides for malaria; one drug/regimen and four diagnostics for TB; one treatment and one diagnostic for hepatitis C; two treatments for sleeping sickness; two treatments for leishmaniasis; one diagnostic, one microbicide device, and one drug for HIV; one diagnostic and one device for maternal health; one vaccine for rotavirus; one vaccine for meningitis; and 11 COVID-19 diagnostics.

Evidence of impact from across the portfolio includes:
FIND conservatively estimate that 226 million of their supported products will have been distributed between 2021 – 2025, averting 12 million disability-adjusted life years (DALYs), and providing $42 billion in societal value (this includes $18 billion in 2023 alone). This has included diagnostic tools that improve our detection, and therefore treatment, of TB, malaria, and HIV.

- 1.2 billion people have received an MVV supported product, saving an estimated 15.4 million lives. Within this:
  - Over 53 million children were protected with seasonal malaria chemoprevention across 18 countries in 2023 alone.

  - Coartem Dispersible has saved over 1 million children’s lives.

DNDi has developed 13 new treatments (under this and previous funding), with at least 542 million treatments being rolled out, contributing to disease control and elimination. This has included revolutionising the treatment of sleeping sickness and supporting Bangladesh to become the first country to eliminate visceral leishmaniasis as a public health problem.

IVCC’s novel indoor residual spraying (IRS) products (Actellic® 300CS, SumiShield™, and Fludora® Fusion), which they have developed since 2016, are estimated to have protected 310 million people, averted up to 27 million malaria cases, and saved 40,000 to 68,000 lives.
35 million of IVCC’s new long-lasting insecticidal nets (IG2) have been distributed across 13 countries in sub-Saharan Africa, protecting around 63 million people. This new type of dual action net, which has been replicated by other brands, is estimated to have prevented 13 million malaria cases.

TB Alliance has directly impacted on paediatric TB with over 4 million courses of its child-appropriate medicines having been shipped to 130 countries since being made available in 2016.

More than 42,000 patient courses of TB Alliance’s Pretomanid for extremely drug-resistant TB have been shipped to more than 78 countries. They estimate that BPaL will be used to treat between 100,000 and 280,000 drug-resistant TB patients by 2025, saving an estimated 15,000 – 43,000 additional lives.

Population Council (who acquired the product from IPM) have distributed over 100,000 dapivirine rings, which help discreetly protect women from HIV.

MenFive, developed by PATH with the Serum Institute of India, received WHO pre-qualification in 2023 and was used for the first time during an outbreak in Nigeria in March 2024, with 1,043,377 doses deployed.

Underpinning these impacts is the inclusion of products in WHO guidelines, the Essential Medicines List, and national guidelines. It is clear the impact PDPs have had on how their target diseases are treated and, even more importantly, by actually reaching target populations and saving lives. The achievements at outcome level match the programme score of A++.

Whilst the outcome indicators (iii) and (iv) were dropped, due to different approaches to tracking and therefore inconsistent reporting, it is worth saying that in 2023 alone more than 350 million products were distributed (particularly driven by high figures from MMV) and at least 27, 17, and 12 of the products were registered in Africa, Asia, and the rest of the world respectively (though figures likely higher).

Overall, this programme, and investment in PDPs, has provided exceptionally good value for money. Whilst £450 million is a large investment, it has produced game-changing new products for a wide variety of infectious diseases, with hundreds of millions of products distributed and tens of millions of lives saved, which will continue beyond the end of the programme. Whilst it is easy to look at the biggest numbers, such as the number receiving malaria treatments supported by MMV, it is also important to consider the nature of the problem being tackled. Whilst only 42,000 courses of BPaL/Pretomanid have been distributed so far, this is a far more effective treatment for extremely drug-resistant TB than any previous TB drug, and therefore a critical step in tackling the danger of antimicrobial resistance (AMR).

In 2024, Policy Cures also published a thorough evaluation of the neglected disease R&D landscape and the value of investing in this type of research. They found that investment over the last 20 years, including by this programme, will have saved 40.7 million lives, or 2.83 billion disability-adjusted life years (DALYs), by 2040, which translates to an economic benefit of $49.9 trillion, or a return on investment of $405 for every $1 invested. Whilst the return on investment for this specific programme may be different, the PDPs funded here contributed many of the most successful products for that analysis, which would imply a similar return on investment for this programme. A full discussion of value for money can be found in section D.

Summarise the programme’s theory of change and results framework, including any changes to outcome indicators.

The theory of change for this programme aligns to that of the overall health research portfolio. The basic inputs are research activities, scientific expertise, influencing, and partnerships. These are brought together to guide the research and development (R&D) of new health technologies/products, including by: developing disease strategies and target product profiles; designing the product, which, for example, can include identifying suitable compounds (drug discovery) and translating that into a form which can be used; trialling the safety, tolerability, and efficacy of products (e.g., drug development); and navigating the complex process of regulatory approvals. Beyond the scientific development, the theory of change also has partners working on engaging with policymakers and the WHO, market positioning, creating access plans, modelling cost-effectiveness, policy influencing, manufacturing, and engaging with local populations and health care systems in order to strengthen the enabling environment and allow products to be made accessible, available, and affordable to the most vulnerable around the world. It also assumes that a portfolio approach, at both the project and programme levels, will allow the most effective distribution, and redistribution, of funding to products with the most potential (e.g., it is relatively easy to stop researching a drug or product and move funds to a more promising area).

These outputs were expected to lead to the development of, and wide-spread access to, new products and evidence, which could be used to control epidemics, control and eliminate targeted diseases of poverty, and address issues of growing drug resistance. In turn, these products should help prevent and treat some of the world’s most serious infectious disease threats, reducing morbidity and mortality, improving the health of some of the poorest and most vulnerable people, as well as reducing the economic burden from the diseases.

For the overall programme, there was no formal change to the theory of change, though increasing emphasis was placed on an end-to-end approach that therefore elevated the importance of policy engagement, manufacturing capacity, etc. However, several of the individual partnerships updated their theories of change (e.g. DNDi developed disease level theories of change, FIND restructured so that its health programmes are aligned across four implementation pillars, and MMV has recently developed a climate strategy and adapted their approach to consider the impact of the new malaria vaccines) but these changes remain aligned with the logic of the overall programme.

The outcome indicators have changed slightly over the course of the programme. The biggest change is that indicators (iii) and (iv), which aimed to count the number of products distributed and registered in different regions, were dropped because different partners track products after approval differently and it was difficult to get consistent figures. However, it would be worth revisiting what might be possible under any future funding.
## C: Detailed Output Assessment

Output Number and Title		1. New products developed, designed, and tested
Output Score		A++
Impact weighting (%)		60%	Impact weighting revised since last AR?	No

Output Indicator	Starting Target		Final Logframe Target	Final Result Achieved
1.1 Number of products receiving their first regulatory approval / *Note: Not all products require regulatory approval, which is why there is a difference between this number and the total number of products reaching market	At least 4 products by 2021 / (Note: this was originally an outcome indicator and was not tracked as an output indicator at the start of the programme).		At least two new products receive their first regulatory approval, for a cumulative total of 21 products receiving their first regulatory approval during the programme’s lifetime.	Significantly exceed original expectations - two products received their first regulatory approval since the last annual review, for a cumulative total of at least 24.
1.2 Number of products in the pipeline, disaggregated by stage: / i) research / ii) translation / iii) development / iv) post-approval implementation	215 products by 2021		230	Met expectations* - 212 / i) 57 / ii) 31 / iii) 79 / iv) 45 / (*See narrative below)
1.3 Products stopped at each stage of the pipeline based on the science, disaggregated by stage: / i) research / ii) translation / iii) development	20 products stopped by 2021		35 (cumulative)	Significantly exceed expectations - 25 products were stopped in 2023: / i) 8 / ii) 5 / iii) 12 / Cumulative total: At least 79

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

At the end of 2023, the FCDO-supported product pipeline stood at 212 products but peaked at the end of 2022, at 250 products, before components started to close. This indicator alone demonstrates impressive growth compared to the 2017 baseline of 171. This target should have been adjusted for the closure of components, but given the final target was exceeded previously, this indicator has met expectations. Importantly, the pipeline continues to demonstrate advancements through every stage of product development, including 114 active clinical trials (which is a significant increase on past years) and the first regulatory approval of two new products since the last annual review. Individually, each of the active components showed robust progress within their pipeline and we expect to continue seeing breakthroughs in the next few years; for example, DNDi alone expects to deliver 8 – 10 new treatments between 2024 – 2028.

Relatedly, partners have stopped the development of 25 products in 2023 alone, for a cumulative total of at least 79 since 2017 (note reporting was inconsistent in some past years, which is why the figure is a minimum). When considered with the robust pipeline and steady stream of regulatory approvals, this significantly exceeds expectations and reflects strong portfolio management and high value for money as resources are continuously being reallocated to the most promising options. For example, PATH DAWN paused their work on a fast-dissolving tablet formulation of oxytocin as it was not showing sufficient bioavailability. This allowed them to move additional funding to their other projects, including driving forward the RELI delivery system, which is a reusable, electricity-free, low-cost infusion pump that is appropriate for treating paediatric and obstetric emergencies where it is often challenging to deliver the necessary medications intravenously.

However, by far the most important metric for assessing this output, and the performance of this programme overall, is the number of new health products that have been successfully developed. Research and development (R&D), particularly for new drugs, vaccines, and other health tools, is inherently risky and many promising products fail in the process of bringing a few to market. Progress also isn’t steady and won’t necessarily be evenly spread across years. For this reason, there was not an official target for the majority of the programme, but the initial goal was to see at least one new product receiving stringent regulatory approval each year (four in the original lifetime of the programme, or seven by 2024), and based on high performance, this was increased to two per year (21 in the lifetime, taking into account high-performance in early years).

As part of this PCR, a thorough assessment has been done to ensure that all new products or treatments have been captured from all partners across all years. This involved cross-checking previous annual reviews, annual reports, supplemental partner reports, and partner websites where necessary. This process identified several products from previous years that had not been captured at the time; this is likely due to unclear reporting. Additionally, it is important to note that achieving equitable access to products does not end with the first regulatory approval; for this reason, even products that received their first approval under previous FCDO-funding have continued to be supported by this programme (to receive more stringent or additional approvals, to support manufacturing, and other aspects of access). Four products (one malaria and one leishmaniasis diagnostic, a paediatric fixed dose treatment for TB, and co-packaged ORS-zinc) that were previously being counted under this programme have been removed from the list as they received their first approvals prior to this programme starting (2014, 2016, 2016, and 2014 respectively) and only received additional approvals during this programme. However, we have decided to prepare two tables to accurately summarise the products this portfolio has supported. Table 1 lists all the products that have been developed and received their first regulatory approval with funding from this programme (addressing indicator 1.1). Table 2 (annex A) lists other products that the PDPs had previously brought to market and continued to receive varying degrees of support under this programme.

Table 1. All products developed and receiving their first regulatory approvals with funding from this programme

Target disease/health condition:	Type of product:	Description:	Developed by:	Year:
Malaria	Drug	Larinate – injectable treatment for severe malaria	MMV	2018
		Tafenoquine – the first single-dose treatment for the radical cure of P. vivax malaria	MMV	2018
		Artesunate rectocaps – emergency intervention for severe malaria in children	MMV	2018
		Artecap – another version of the above rectocaps but from a different manufacturer	MMV	2018
		Supyra – a monthly preventative treatment for malaria	MMV	2019
		Tafenoquine paediatric – the first single-dose treatment for P. vivax malaria for children	MMV	2022
		Wiwal – the first preventative malaria treatment manufactured on the African continent, designed for pregnant women and infants	MMV	2022
		Argesun – a new formulation of injectable artesunate (like Larinate), which is easier to prepare	MMV	2023
	Diagnostic	STANDARD Q Malaria/CRP Duo Test – tests for both malaria and bacterial infection, helping efficiently diagnose febrile illness	FIND	2018
		STANDARD G6PD Test – the first point-of-care test for G6PD, an enzyme, deficiency, which can cause serious complications during malaria treatment	PATH	2017
	Insecticides	SumiShield – was the first new IRS product recommended by WHO in over 40 years	IVCC	2017
		Fludora Fusion – the first indoor residual spraying (IRS) product that combines two unrelated modes of action	IVCC	2018
		Interceptor G2 – uses the first new insecticide found to be safe and effective on nets in over 40 years	IVCC	2018
		VECTRON T500 – is another new IRS product that uses a different mode of action to any existing products, which means it can be used in areas with resistance	IVCC	2023
TB	Drug	Pretomanid and BPaL regimen – BPaL is a far more effective and shorter (with less side-effects) treatment for extremely drug-resistant TB	TB Alliance	2018
	Diagnostic	MTB/Rif Ultra (GeneXpert) – fast and accurate diagnosis of TB and resistance to the most common TB drug (update of Xpert MTB/Rif with even greater sensitivity)	FIND	2017
		TrueNat TB & Rif – point-of-care test for low resource settings that can diagnose TB and resistance to the most common TB drug	FIND	2018
		SILVAMP TB LAM RDT – a urine-based point of care test for TB, which was 30% more sensitive than existing tests, for people with HIV	FIND	2019
		Xpert MTB/XDR – used in combination with MTB/Rif Ultra (above) to test for a wider range of drug resistance	FIND	2020
Hepatitis C	Drug	Ravidasvir + sofosbuvir – first hepatitis C drug to be developed through South-South collaboration and significantly more affordable than existing treatments	DNDi	2021
	Diagnostic	HCV-VL (GeneXpert) – detection and quantification of hepatitis C virus in about an hour	FIND	2017
Sleeping sickness	Drug	Fexinidazole for T.b. gambiense – first all-oral cure for the common form of sleeping sickness, making treatment much simpler	DNDi	2018
		Fexinidazole for T.b. rhodesiense – first all-oral cure for a rarer but more acute/lethal form of sleeping sickness. Replacing an arsenic based treatment that killed up to 10% of patients	DNDi	2023
HIV	Drug	4-in-1 (ABC/3TC/LPV/r) paediatric HIV treatment – child-friendly, strawberry-flavoured, treatment specifically designed for infants and young children with HIV	DNDi	2022
	Diagnostic	HIV-VL (GeneXpert) – a rapid and adaptable HIV viral load test	FIND	2017
	Microbicide device	Dapivirine ring – a discreet vaginal ring that reduces the risk of HIV acquisition	IPM	2020
Leishmaniasis	Drug	Combination of liposomal amphotericin B with miltefosine – first evidence-based treatment for people living with both HIV and visceral leishmaniasis (regulatory approval not required but WHO recommended)	DNDi	2022
		Lipsomal amphotericin B (Americas) – shorter and safer first-line treatment (regulatory approval not required by PAHO recommended)	DNDi	2022
Maternal health	Diagnostic	Test-it PrCr Test – an innovative urine test for pre-eclampsia	PATH	2019
	Device	Ellavi balloon tamponade – the first commercially available, low-cost, fully assembled uterine balloon tamponade for post-partum haemorrhage	PATH	2019
Rotavirus	Vaccine	ROTAVIN – a locally manufactured, affordable, and suitable rotavirus vaccine in Vietnam	PATH	2021
Meningitis	Vaccine	MenFive – the first vaccine against the five most common serotypes of meningococcus meningitis in Africa, including the only vaccine for type X	PATH	2023
COVID-19	Diagnostic	Flowflex SARS-CoV-2 RDT – COVID-19 rapid lateral flow test	FIND	2021
		OnSite COVID RDT Self-Test – COVI-19 self-test	FIND	2021
		SAYTU COVID-19 Ag Test – COVID-19 rapid test	FIND	2021
		bioPerfectus COVID Ag-RDT Self-Test – COVID-19 self-test	FIND	2021
		GeneFinder Self-Test – COVID-19 self-test	FIND	2021
		Covid-19 Antigen Test – COVID-19 rapid lateral flow test	FIND	2021
		Surestatus RDT – COVID-19 rapid lateral flow test	FIND	2021
		Immuno-Rapido COVID-19 – COVID-19 rapid lateral flow test	FIND	2021
		COVID-19 NP RDT – COVID-19 rapid lateral flow test	FIND	2021
		Surestatus RDT Home Test – COVID-19 self-test	FIND	2022
		COVID-19 NS RDT – COVID-19 nasal swab self-test	FIND	2022

Overall, this means that partners have delivered 33 new products during this funding period: eight drugs, two diagnostics, and four insecticides for malaria; one drug/regimen and four diagnostics for TB; one treatment and one diagnostic for hepatitis C; two treatments for sleeping sickness; two treatments for leishmaniasis; one diagnostic, one microbicide device, and one drug for HIV; one diagnostic and one device for maternal health; one vaccine for rotavirus; and one vaccine for meningitis. Additionally, FIND has supported the development of at least 11 COVID-19 diagnostics, for an overall total of 44 products (note that the COVID-19 diagnostics are being counted separately as the development process was slightly different than usual). Since the last annual review, two new products (Argesun for malaria and fexinidazole for T.b. rhodesiense) have received their first regulatory approvals, for a total of four products in 2023. Not all products require regulatory approval, rather adoption in guidelines or other types of certifications, but at least 24 products have received their first regulatory approval under this programme. Within this impressive list of products, all of which will benefit their intended targets, particularly notable products include:
Pretomanid is a new drug to treat highly drug-resistant TB and one of only three TB drugs to be approved by the US Food and Drug Administration (FDA) in over 40 years. As part of the BPaL regimen (beqaquiline, Pretomanid, linezolid), it can cure over 90% of extremely drug resistant TB with only 6 months of treatment, significantly reducing side effects.

- Tafenoquine (Krintafel/Kozenis), and its paediatric formulation, which is the first single does oral treatment for relapsing (P. vivax) malaria. Previously, primaquine was the only available treatment for the prevention of relapsing malaria, which was difficult to administer as it had to be taken for 14 days.
  - This goes hand in hand with the development of the STANDARD G6PD test, as it is not safe to treat individuals with relapsing malaria with either tafenoquine or primaquine if they have a G6PD deficiency, which is more common in women. This new test, followed by the administration of tafenoquine, makes treating relapsing malaria far simpler and safer.

Fexinidazole, which has been approved for treating both types of sleeping sickness, is the first all-oral treatment for sleeping sickness. The previous treatment for T.b. gambiense involved both oral and intravenous drugs and required 14 days of hospitalisation, whilst the only available treatment for T.b. rhodesiense was an arsenic based treatment that killed up to 10% of patients. This, in combination with a diagnostic developed by FIND under previous funding, has revolutionised the treatment of sleeping sickness. DNDi continues to push the frontier forward with positive Phase 3 trial results for the single-oral dose acoziborole.

Interceptor G2 is a groundbreaking, first of its kind, dual-action pyrethoid-chlorfenapyr bed net that kills mosquitoes resistant to traditional insecticides by making them unable to move or fly, and significantly reduces malaria infection in children.

MenFive is the first vaccine effective against the five most common serotypes of meningococcus meningitis in Africa, including being the only vaccine against type X. It is an affordable and suitable (e.g. not requiring refrigeration) vaccine for the Meningitis Belt where most cases and deaths occur.

Overall, this programme has far exceeded expectations with 33 new products (not including those for COVID-19) reaching the market against an initial ambition of seven, and this output has, therefore, been scored an A++

Lessons learned through this output, and recommendations for future programming

The PDPs have adapted their approach throughout the lifetime of the programme and continue to evolve. Key lessons include:
Flexible funding is important to ensure that a dynamic portfolio of the highest potential products is pursued.

Smaller portfolios and products that are in earlier stages of development are much higher risk investments; however, some of these have still provided important scientific advancement (e.g. progressing microarray patches).

Target product profiles (TPPs) should be developed early in the process and ideally with industry partners.

It is essential to keep industry engagement in the process, for successful product development. Having more than one supplier engaged at the outset can strengthen the negotiating position of the programme and may overcome some of the issues arising when companies are merged or acquired by others, as some development projects may be halted during the changeover period.

The processes for local and national permissions and agreements for acquiring and transporting tissue samples, blood samples and other biological products need to be factored into the timeline of and risk management by the individual partnerships, to avoid unnecessary delays in development activities.

- It is important to build strong working relationships with regulatory authorities and jointly develop new approaches with them, especially when products are innovative and regulatory agencies may not have encountered anything similar in the past.
  - This includes early and close engagement with the World Health Organization to understand data requirements early in the pathway and build appropriate studies into the development programmes.

The use of open label trials, following the results of late-stage development trials, can provide more ‘real-life’ experiences e.g. IPM found that during open label trials (DREAM and HOPE) there was increased adherence to the microbicide ring, compared to the blinded late-stage ring trial. Modelling data suggested greater HIV risk reduction, by at least 50%, compared to the blinded trials.

Implementation and context-specific research can be a very effective tool to influence policy change as it tends to answer more of the practical questions of concern to policy makers when introducing a new medical product to their market.
Output Number and Title		2. New evidence and knowledge generated to inform service delivery
Output Score		A+
Impact weighting (%)		25%	Impact weighting revised since last AR?	No

Output Indicator	Starting Target		Final Logframe Target	Final Result Achieved
2.1 Number of externally peer-reviewed research publications published in the reporting period, and % with: / i) lead or co-author with home institution in a LMIC / ii) female lead or co-author / iii) female lead or co-author with home institution in a LMIC / iv) are open access	125 publications per year, for a cumulative total of 500 publications by 2021 (or 875 by 2024) / i) 30% / ii) 50% / iii) 20% / iv) 90%		200 externally peer-reviewed publications in 2023 / i) 30% / ii) 50% / iii) N/A – no longer tracked / iv) 90% / Cumulative total: 1,200	Moderately exceeded expectations - 233 publications in 2023: / i) 42% (98) / ii) 58% (134) / iv) 71% (166) / Cumulative total: 1,300 publications / i) 33% (for years reported) / ii) 51% (for years reported) / iv) 83%
2.2 Effective research uptake and dissemination activities, through providing examples of work that had the most impact on research uptake/dissemination	50 activities per year in later years		55 activities in 2023 but with a focus on capturing case studies of high-quality activities	Moderately exceeded expectations – over 14 detailed narrative examples provided, in addition to over 290 dissemination activities (including policy briefs, webinars, conferences, and meetings with key stakeholders) in 2023

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

This output has moderately exceeded expectations in its final year, though given the significant increase in the targets, particularly for indicator 2.1, an argument could be made for significantly exceeded.

The PDPs achieved another high publication year, with 233 peer-reviewed publications, which was driven by especially high numbers from DNDi (73) and FIND (103). Examples of publications supported by the programme include:
DeTACT published a paper mathematically modelling the significant impact that introducing triple artemisinin combination therapies (TACTs) could have on delaying the emergence of drug resistance in Nature.

PATH published the results of their MenFive (NmCV-6) vaccine trials in Mali and Gambia, which showed the vaccine was at least as effective as existing vaccines and the only vaccine effective against type X, in the New England Journal of Medicine.

IVCC published the results of a large-scale community randomised trial in Tanzania, which showed that their long-lasting dual-action bed net is safe and reduced malaria prevalence by 43% in the first year and 37% in the second year compared to existing nets.

PATH MAPs co-authored three articles in the journal Vaccine in December 2021 focused on how they should tackle vaccine innovation. These were on how the Vaccine Innovation Prioritisation Strategy (VIPS) Alliance will go about prioritising work, the findings from country consultations on key factors to be considered in vaccine development (e.g., the need for heat-stable vaccines and barcodes on primary packaging), and the barriers to developing innovative vaccine products for LMICs.

In the last year, targets were exceeded for LMIC and female authorship, but did fall short (in fact to a programme low) on open access publication. It is worth noting that we stopped tracking the intersection of female and LMIC authorship, as it was being too inconsistently reported by partners. Taking the programme as a whole, the LMIC and female authorship targets have been met and the open access target has been missed (though was met in 2022), though at 83% open access, they continue to show commitment. Additionally, several of the partners support other open access initiatives. MMV leads the way with their work on:
MMV Open, which provides free access to data and compound libraries.

MMV Sola, which is a free, user-friendly pharmacokinetic and dose prediction tool that uses state-of-the-art mathematical modelling. It has been instrumental in allowing Discovery to identify compounds with long predicted half-lives suitable for monthly chemoprevention.

Malaria Libre, which is an open-source drug discovery programme that offers a collaborative platform for the sharing of data and ideas to accelerate innovation. An Early Lead is expected to be delivered from a new azaindole sub-series in 2024.

The Malaria Box (2012 – 2016), Pathogen Box, Pandemic Response Box with DNDi, and the Global Health Priority Box, which all provide researchers with free access to hundreds of compounds or drug-lice molecules to test against their pathogens. They have shipped 260, 350, 230, and 112 of the boxes respectively, which has led to over 165 publications.

All partners have provided examples of research uptake and dissemination activities in each and every year of the programme. It continues to be difficult to measure the quality of these activities, and whilst it is good to see the sheer volume of activities, further work needs to be done to capture the breadth and potential impact of them. Indicators like the progress in regulatory approvals for multiple products or inclusion in WHO and national guidelines suggest that the PDPs are very successful at getting their research into the right hands. Impactful examples include:
Based on the data generated by IVCC, the Who Global Malaria Program announced it had finalised recommendations for two new types of nets in March 2023, including one developed by IVCC.

In 2022, DNDi launched a new Global Partnership for Dengue Treatment, which will ensure they work closely with endemic countries including India, Brazil, Malaysia, DRC, and Ghana to develop therapeutics from this dangerous disease.

A BBC video and associated podcast were produced on the dapivirine vaginal ring developed by IPM, and a press release on the same product was then profiled by the Economist. Other partners have also leverage media coverage, including that SRPNTS highlighted the need for investment in snakebite research and IVCC saw promotion of their new nets.

IVCC launched the Zero by 40 platform to support the aim of eradicating malaria by 2040, and which has resulted in a commitment from five key companies to support vector control product development and marketing.

DNDi launched the Open Source Mycetoma community (MycetOS) in January 2018 using GitHub, Reddit and Twitter, with the aim of stimulating discussion between global researchers and initiating new experiments to discover new treatments for fungal mycetoma (eumycetoma).

PATH DAWN partnered with the Kenyan Ministry of Health, University of Nairobi, and Ghana Health Service to conduct two national workshops with local stakeholders on introducing the Ellavi uterine balloon tamponade (UBT) to stop postpartum haemorrhage. This engagement, and the publication of their implementation research, led Kenya to quickly agree that the Ellavi UBT could be added to their national procurement channels (the Kenya Medical Supplies Authority (KEMSA) and the Mission for Essential Drugs and Supplies (MEDS)).

Lessons learned through this output, and recommendations for future programming

The biggest challenge with this component has been around how to capture, measure, and incentivise the right activities. It is clear the PDPs generate a huge amount of new knowledge and undertake a wide variety of activities to ensure that the right individuals and groups are being exposed to and understand their discoveries, from the general public to technical scientific committees and regulatory authorities. Importantly, the PDPs are far better placed to decide what are the most important and impactful activities to progress their products through different phases. Therefore, a recommendation for future programming is to work with the PDPs to understand how they measure their effectiveness in this space and revamp the indicators to cover a wider variety of activities but also be more focused on their impact and how the PDPs are learning to be more impactful.

A second recommendation is to have an open discussion with the PDPs about the barriers and challenges to open access publication – unpacking why the 90% open access publication target has not been met. Based on this assessment, FCDO can ensure an appropriate target is set for future programmes but also that learning is fed into wider departmental initiatives on open access, which is a priority for the UK Government.

Output Number and Title		3. Increase the capacity of partners to undertake all aspects of research and to identify suitable partners to work with to ensure access to new products
Output Score		A+
Impact weighting (%)		15%	Impact weighting revised since last AR?	No

Output Indicator	Starting Target		Final Logframe Target	Final Result Achieved
3.1 Evidence demonstrating how FCDO funding has been used to engage and/or influence national or international expert panels/ working groups/ policy makers (through case studies/narrative)	15 recorded influences per year		15 recorded influences in 2023 / Cumulative total: 120 recorded influences	Moderately exceeded expectations – 17 narrative examples provided in 2023, with strong contributions demonstrated towards national and international guidelines, policies, and strategies. / Cumulative total: over 150 recorded influences
3.2 Evidence generating how FCDO funding has helped build local capacity and/or infrastructure – number of people who have gained new knowledge or skills	70,000 people (cumulative) given new skills or knowledge by 2021, or extrapolated to 85,000 people (cumulative) by 2024		5,000 people given new skills or knowledge in the last year / Cumulative total: 90,000 people given new skills or knowledge	Significantly exceeded expectations – / Cumulatively at least 70 narrative examples have been provided and over 120,000 individuals and 6,000 facilities have benefitted / 14 narrative examples provided in 2023 from training clinical staff, to upgrading facilities, to supporting local communities to advocate for themselves.

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

2023, as with all previous years, proved to be a busy period for the PDPs with a wide range of policy influencing and capacity building activities taking place. They continue to effectively identify their key stakeholders, building the relationships necessary to influence policies both directly related to their products and the wider approach to the relevant disease and product development process. They have also continued to shape the wider enabling environment, including looking at how prices can be reduced, regulatory processes streamlined, and investment continued. As with research uptake, it is more important to track the nature of and outcomes from activities, rather than provide a simple count (i.e., did they actually change an important policy). Examples of policy influence include:
The latest edition of the World Health Organization Essential Medicines List (23rd), published in July 2023, contains six MMV-co-developed medicines, as well as several from other partners.

In 2023, TB Alliance brokered a volume guarantee between the UK-based non-profit MedAccess and Viatris that resulted in a 34% price reduction for Pretomanid. The maximum price of Pretomanid in about 150 countries, which bear the brunt of the TB pandemic, is now reduced to $1.33/day. As a result of this deal, BPaL/M is now priced at $563-592/treatment

- IVCC and Duke University worked with key stakeholders to create a Vector Expedited Review Voucher (VERV) programme to provide additional financial incentives for the development of vector control tools. The scheme was signed into US law in 2022.
- The PATH diarrhoeal treatments group worked with Diarrhoea Innovations Group (DIG) members to establish global normative guidance around the use of co-packaged ORS and zinc for childhood diarrhoea. DIG submitted a petition to the WHO to add combined ORS and zinc to the Essential Medicines List, which it was in 2019.

- FIND supported national COVID-19 coordinating bodies in 12 countries to either develop or update their national COVID-19 testing strategies, especially in decentralized settings where access to PCR testing was limited.
- Increased awareness of G6PD deficiency due to workshops and publications by PATH, coupled with increasing availability of low-complexity tests, resulted in the inclusion of tests for G6PD deficiency in WHO’s first Essential Diagnostics List.

- FIND provided data that contributed evidence to the first ever WHO recommendation on hepatitis C self-testing; this has expanded testing for key populations and vulnerable groups that might be reluctant to get tested at a facility and directly catalysed uptake in Georgia, Malaysia, and Pakistan.
- IPM engaged in virtual meetings and written communication to keep its US congressional champions up to date on their progress on regulatory approvals, market introduction, and next-generation microbicides. This led to uncontested bipartisan and bicameral support for continuing to provide $45 million for microbicides in the US Congress’s FY22 budget.

Similarly, the PDPs have also continued a wide range of capacity building activities; these range from improving clinical facilities to strengthening the capacity of communities to advocate for themselves. They have also taken on much more ambitious aims, particularly around manufacturing capacity, than was initially envisioned. This growth has been a real strength for the programme. Although partners have consistently struggled to report on the number of individuals trained, they estimate that at least 120,000 individuals have benefitted from capacity building or technology transfer activities (incl. at least 9,000 individuals and 1,900 facilities in 2023), and that is a very conservative estimate. Examples of high-impact activities include:
FIND’s access-related investments and technology transfer programmes led directly to 60 million COVID-19 RDTs and self-tests being manufactured in LMICs each month, available at US$ 1–2 per test.

FIND has partnered with the Botswana Harvard AIDS Institute (BHP) to strengthen the country’s whole genome sequencing capacity for SARS-COV-2. This is critical for global health security as has been shown by the rapid spread of several COVID-19 variants around the world. Since the beginning of FIND’s support, Botswana has submitted an additional 2500 genome sequences and BHP was one of the first laboratories to report the Omicron variant.

As part of MMV’s commitment to supporting African manufacturing capacity, they partnered with Universal Corporation Ltd. in Kenya to manufacture quality-assured sulphadoxine–pyrimethamine, which received WHO prequalification in March 2022. In 2023, MMV and Africa CDC signed a memorandum of understanding to support strengthening of African pharmaceutical manufacturing capacity, in line with the organisation's Strategic Plan for 2023–2027.

DNDi participated in the first international training workshop on mycetoma in Khartoum, Sudan. 79 medical and health workers from 32 countries were trained on specimen collection, diagnosis, treatment and follow-up of cases, and were also briefed on laboratory and clinical management protocols.

DNDi also worked with local partners in Colombia and Guatemala to develop and launch the iChagas app, which empowers remote health workers to diagnose and treat Chagas disease. The app has been rolled out across Latin America.

TB Alliance has continued to develop local communities understanding of TB drug R&D through their Community Engagement Programme.

Over the last 10 years, MMV has funded several successful Discovery projects in Africa, providing approximately USD 1 million annually to drug discovery leaders based in sub-Saharan Africa.

Lessons learned through this output, and recommendations for future programming

Important lessons include:
There can be significant challenges to getting new products adopted where there are entrenched lobbies. For example, intravenous artesunate has been conclusively shown to save more lives from malaria than intravenous quinine, however in some high-burden countries where quinine is manufactured, strong national protectionist stances can make it difficult for good public health decisions to be implemented.

- Many partners continue to find the regulatory approval process difficult and cumbersome to navigate, with it often adding significant delays to new products reaching those in need. However, several partners have started to see improvements through strong relationship building with regulatory authorities.
- Online training and communications are vital in mitigating against unanticipated challenges/delays with partners. For example, during COVID-19, IVCC put procedures in place to conduct training, site initiation, and monitoring visits via videoconferencing and/or cloud-based platforms.

Recommendations:
PDPs should explore more opportunities to collaborate on policy influencing, particularly around streamlining regulatory processes, and look to conduct cross-partnership capacity-building to learn from each other’s relative strengths. The examples above show that PDPs have a good basis on which to expand the collaboration.

As with output 2, future programmes should carefully consider how to best measure these types of activities. This will need to balance qualitative evidence with a few quantitative indicators that must be based around specific activities that the PDPs plan to conduct. Indicators around LMIC manufacturing capacity, clinical trial capacity, and engagement with the regulatory environment should be considered.

D: Value for Money

VfM performance compared to the original VfM proposition in the business case

Overall, the portfolio has provided excellent value for money. Our PDP investments have brought far more important new products to market (e.g., this year’s new meningitis vaccine) than expected, filling a fundamental gap where for-profit pharmaceutical companies could not meet population’s needs. They have done so whilst keeping the costs of both the research and end-products as low as possible. All are driven by a mission to reach the poorest and most vulnerable around the world and many are developing products that will help particularly vulnerable groups (e.g., women and girls). Taken together, this means the programme is having a large impact on those most in need for a reasonable cost.

Economy:
All the PDPs look to streamline their own staffing, leverage partnerships, and work at economies of scale in order to drive down the cost of medical product development. Some specific examples include:
Several PDPs (including TBA, IPM, and MMV) leverage public, philanthropic and private sector resources. This includes in-kind support such as product marketing expertise, statistical work (e.g., demand analysis) and access activities. MMV estimate that for every USD 1 billion spent, USD 2.5 billion is generated in partner contributions, and PATH estimates that for every $1 FCDO has invested in the Microarray Patch Centre of Excellence, it has attracted $6 in other funding.
- DeTACT is partnering with Fosun Pharmaceuticals who will be providing the drug combination therapy artemether-lumefantrine + amodiaquine (AL + AQ), related placebo, and packaging for free to the trial. This is a huge saving for the programme.
- DNDi, and other partners, keep their full-time equivalent staff costs below industry levels by at least 50% but still manage to attract top R&D leadership from pharmaceutical firms who want to support delivering the best science to the most neglected.
- PATH DAWN, SRPNTs, and IVCC cost-share staff expertise with other programmes to minimise cost.
- FIND initiated several cost-saving, efficiency improvement projects in 2022; these include a benchmarking of consultancy rates and a data transformation project designed to facilitate the integration of financial planning, management and reporting across the organization.
- By working with the Serum Institute, PATH has ensured that access to their MenFive vaccine will be prioritised for meningitis belt countries and that the pentavalent vaccine will be priced significantly lower than existing quadrivalent meningococcal conjugate vaccines (no more than $3 per dose, versus approximately $20 per dose for existing quadrivalent vaccines).
- FIND worked hard to bring down the cost of COVID-19 Ag rapid diagnostic tests (RDTs) from US$2.75 to US$1.50. They estimate that, for example, in Zambia this led to a 36% reduction in cost per life-year saved.
- IPM are working to bring down the cost of their dapivirine ring by increasing manufacturing scale by five-fold.
Efficiency:
First and foremost, a portfolio approach allows partners to redistribute funding to the most promising and high-priority areas, which includes quickly stopping projects that are not meeting scientific or clinical milestones. All the organisations also work to reduce their timeframes wherever possible and make sure from early stages that products are well-targeted to meet the population’s needs. MMV, for example, achieves similar timeframes to commercial R&D with higher probabilities of success (>10% vs. 5-10%) and significantly lower costs. Some other specific examples of work to improve efficiency, include:
DNDi, MMV, TB Alliance and others have partnered with Deep Mind, Exiscentia, and other leading artificial intelligence (AI) firms to streamline the process of searching and screening for promising chemical compounds. For example, DNDi and AlphaFold are using AI to address a challenge that has confounded biologists for 50 years: how to predict the shape of a protein using the amino acids that constitute it and therefore make it easier and more efficient to identify compounds that will bind with it.

TB Alliance has prioritised the long-term affordability of Pretomanid and the sustainability of the market by securing an affordable price at launch through partnership with a pharmaceutical company (Viatris), whilst also working to introduce generic competition as quickly as possible to further drive down the price by partnering with a further three pharmaceutical companies (Macleods Pharmaceuticals, Hongqi/Fosun, and Lupin). An assessment published in PLOS Global Health estimates that BPaL is 40-90% cheaper than conventional regimens and could save governments around $740 million per year if provided to all who need it.

DNDi estimates it can efficiently develop and register new treatments that combine or repurpose existing drugs for EUR 4-32 million and new chemical entities for EUR 60-190 million, far below estimated private sector rates (of approximately EUR 1.2 billion).

Since cost-effectiveness analysis is usually essential to government decision-makers, PATH includes product affordability into the target product profile from the outset and conducts early modelling and analysis of cost-effectiveness. Recently Kenya has approved adding the Ellavi UBT to procurement lists without colleting further cost-effectiveness data, significantly speeding up the process, as they could use PATH’s existing work.

During TB Alliance’s work, they identified three chemical classes with compounds that show potential for treating infections that frequently found in people with cystic fibrosis. They are now working with the Cystic Fibrosis Foundation to advance this research.

In order to conserve a US$4.4 million investment in a BD-developed G6PD test when a commercialisation plan could not be resolved, PATH G6PD quickly completed a technology transfer to Wondfo, a Chinese point-of-care test manufacturer, who have already begun to develop product prototypes based on the BD design with parts that can be procured in China.

Effectiveness:
Sections B and C outlined some of the key accomplishments of the various projects. Effectiveness is ensured through rigorous science that focuses on developing the most promising candidates, alongside a realised commitment to ensuring they are adoptable, available, and affordable for all. Some additional examples include:
FCDO has supported MMV since its inception in 1999. Since then, it has built the largest-ever pipeline of antimalarial drugs, treated an estimated 1.2 billion people, saved around 15.4 million lives, and generated an estimated US $28.5 billion in economic benefits.

The PDPs have strong global links which encourage continued engagement and uptake; networks include research institutes, academia, health ministries and disease control programmes, commercial partners, bilateral and multilateral organisations, and clinical trial sites. All the PDPs actively engage with the UN system, in particular the World Health Organisation (WHO). FIND, for example, has collaborations with over 200 institutions.

TB Alliance accounted for only 17.8% of the total global funding for TB drugs reported by the Treatment Action Group in 2018 and yet the organisation is leading the development of the most comprehensive portfolio of drug candidates in history.

As the dapivirine vaginal ring gets ready to enter new markets, IPM is ensuring that they will be available to women and adolescent girls by conducting end-user research studies and checking for unexpected barriers to their uptake. This supports the product to have its intended impact.

Equity:
All the product development work is underpinned by the principle that all products developed should be adoptable, available, and affordable to all those who need them, driven by public health need, not profit. For example:
DNDi is not only focused on tackling NTDs but also ensures that their new drugs will help strengthen healthcare systems. For example, most are designed to be delivered in primary health care settings, rather than hospitals, which greatly expands access, particularly for rural populations and those in the ‘last mile’ (e.g., they created the first oral treatment for Sleeping Sickness, which can be taken at home rather than requiring a 10-day hospital stay).

SRPNTS aims to benefit the poorest populations in affected low- and middle-income countries. Snakebite envenoming disproportionally affect rural farmers or children in poor environments with currently very limited access and affordability to treatment.

IVCC’s new strategy explicitly includes NTDs and has a specific focus on improving outcomes for smallholder farmers. They have also conducted additional investigations to secure feedback from marginalised communities when developing new product classes like attractive targeted sugar bates (ATSB).

MAPs is developing products that address health needs that disproportionately impact women, that will help displaced and migrant populations more easily access preventative health care, and that aim to prevent and treat diseases that have the greatest burden among the poorest people.

MMV are also paving the way for the first malaria drug trial in women in their first trimester of pregnancy, the Safety of Antimalarials in the FIRst trimester (SAFIRE) study, which will start in 2024. This study is truly groundbreaking, being the first time that an interventional drug study has been done in Africa in the first trimester of pregnancy and will set important precedents for future work in this area.

Since 2003, FIND has been instrumental in the delivery of 25 new diagnostic tools, including ten for tuberculosis. Over 50 million FIND-supported products have been provided to 150 low- and middle-income countries since the start of 2015. FIND has helped to create an enabling environment to encourage more engagement in diagnostic development, for a variety of diseases, through the provision of specimen banks, reagent development and better market visibility which reflects a willingness to address market entry barriers for diagnostics globally.

E: Risk

Overview of programme risk during the past year and over the life of the programme, drawing on FCDO’s Risk Management Policy and Risk Appetite Statement and wider risk guidance.

Strategy & Context	Policy & Programme Delivery	Public Service Delivery and Operations	People	Safeguarding	Financial & Fiduciary	Reputation	Overall
Major	Major	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate

The overall residual programme risk stayed consistent throughout the programme at major. Most of the risks are the same as in previous years, including that there was a growing, and now major, contextual risk around the PDPs overall funding (discussed below). All risks remained comfortably within our risk appetite, particularly for this type of pioneering and potentially high impact work.

The inherent risks in product development research are high, with potential to have significant impact. Some of the individual programmes have severe risks, but, as part of the risk mitigation strategy, this is managed by funding several different component programmes within the umbrella programme. In addition, risk is shared between several core donors, lowering the risk for each individual one.

The individual programmes had robust approaches to risk and strong, integrated approaches to managing them, including the use of risk registers, which were updated and approved by FCDO quarterly, that capture the likelihood, impact, and owner of a given risk, and detailed any potential mitigation activities. FCDO also undertook regular internal assessments of risk, proactively monitoring progress.

Strategy and context – major residual risk:

The international political and funding context continued to be very challenging, with the impacts of COVID-19, the war in Ukraine, and the global cost of living crisis having affected downstream partners ability to deliver programmes. Within this, there had been a trend to less core/unrestricted funding and more project-based funding. This left less flexibility for PDPs to select between different priorities and products, undermining some of the efficiencies and risk reduction of a flexible, portfolio approach. FCDO continues to lobby for other partners to increase their share of core funding, but the risk here remains major. There was also a more manageable risk, through close monitoring, that changes in other donor’s priorities would have a wider impact. Linked to this, some of the projects (IPM and DAWN) worked on sexual and reproductive health, where the international political and funding context continues to be challenging. The organisations continue to develop risk mitigation strategies on an ongoing basis.

Policy and programme delivery – major residual risk:

One of the major inherent risks in product development is that they will fail at various stages of testing. However, the individual projects’ (PDPs’ and other organisations’) portfolio approaches mean that failing projects are stopped early and resources can be moved to more promising options. Most of the PDPs have a healthy pipeline of products to replace a failure. COVID-19 also posed a significant risk to product development timelines; it caused significant delays to many products in 2020/21 but partners shifted their approach and portfolio to work around this as best as possible (e.g., slowing certain areas, rearranging timings, etc.). The PDP funders group continues to monitor the situation closely.

Public service delivery and operations – moderate residual risk:

Compared to the formal PDPs, to which we provided core funding, the product development programmes (the PATH projects, DeTACT, and SRPNTs) required greater FCDO team input to ensure compliance with the terms and conditions of FCDO funding agreements.

Safeguarding – moderate residual risk:

Clinical trials involve close contact with often vulnerable groups, including children, and have the potential to risk their safety. However, this type of research also has internationally recognised standards, which include robust safeguarding processes, ethical approvals, and close monitoring. The completion of the extended ‘Safeguarding’ Due Diligence report, required by FCDO, provided a greater level of understanding of the risks, and mitigation measures in place, for the activities of the individual organisations.

Financial and fiduciary – moderate residual risk:

Whilst misappropriation of funds is always possible, thorough Due Diligence assessments were conducted, which showed robust systems were in place, and appropriate financial monitoring was undertaken.

People – moderate residual risk:

The quality of product development programmes rests on the calibre of the individuals executing the activities. An inability to attract and/or retain the talent needed to effectively execute their vision across the different geographies in which they operate would have posed a risk to overall programme effectiveness.

Reputational – moderate residual risk:

As described above, safety of subjects, participants, and mismanagement of FCDO funding are all reputational risks for FCDO. However, all the organisations were aware of these risks and managed them appropriately. There was also a reputational risk that reductions in funding, particularly at short notice, could be very disruptive to their operations (this was a particular risk during COVID-19 and the in-year ODA reductions).

F: Programme Management: Commercial and Financial Performance, Monitoring and Evaluation

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including VfM measures of economy and efficiency.

Overall, the programme performed strongly against commercial and financial standards. The programme did run for several years longer than initially envisioned but these were costed extensions and reflected the programme’s high performance. This consisted of a costed extension of £115m in September 2019, £23m in 2020, and £51m in 2021. It should be noted that under this programme’s agreements, DNDi (£2m), FIND (£3m), IVCC (£3.5m), MMV (£4.5m), and TB Alliance (£4m) received additional bridge funding under the new R&D to help end the preventable deaths of women, children, and newborns (EPD) business case; the impact of this funding will be reported on under the new PDP programme that will be established in FY 2024/25.

As with the rest of the research portfolio, COVID-19 inevitably had an impact on the progress and timelines of many PDPs. Problems included significant supply-chain disruptions, reallocation of funding and personnel to COVID-19, prioritization of manufacturing of COVID-19-related commodities at the expense of life-saving interventions for other diseases, the changing priorities of national health systems, and COVID-19-related behavioural changes at the community and individual level impacting on the progress of clinical trials. However, the PDPs showed great resilience and got the vast majority of projects back on track. A few required no-cost extensions but all these funds have now been used.

The collaboration between FCDO and the different partners, as well as other funders, has been strong, and only strengthened over the course of the programme. Interdisciplinary teams of FCDO staff met regularly with each of the programmes, all of which were productive.

The individual PDPs provided annual funders reports to all their donors in April/May of each year, reporting on progress for the previous calendar year. This PCR has, therefore, used the most recent reports covering 2023.

The likelihood of funds not being used as intended was low. The projects completed financial and performance reports which provided a comprehensive analysis of indicators, governance structures, and spending activities, alongside a separate report from their respective statutory external auditors. The different programmes have strong policies, principles, and/or Code of Ethics to safeguard high standards of behaviour and maintain independence and effectiveness in pursuit of their missions. The organisations have strong governance structures, with independent Boards. They have strong anti-corruption policies with zero tolerance towards bribery and corruption and have whistle-blower policies to enable disclosure of any potential wrongdoing. All the Annual Audited Accounts were unqualified. For those programmes not receiving core funding (in which case there are no identifiable FCDO assets), all the organisations-maintained asset registers that could be reviewed by FCDO if required.

A detailed assessment of value for money is provided in section D but it is also worth considering estimates of return on investment.
In 2019, the Global Health Research Team conducted some preliminary work with health economists at Imperial College to estimate the overall rate of return of our investments. This ‘proof of concept’ analysis compared the total investment costs in MMV with net monetary health gains for one intervention – Coarterm Dispersible, a child friendly anti-malarial medicine developed by MMV. This was chosen as it was one of the earliest products developed and had high-quality data available on distribution. Our best estimate of the internal rate of return from investment in malaria research through MMV was 21%. In other words, for every £1 invested in MMV we can expect a return of at least £1.21 in monetised benefits each year in perpetuity. While subject to many caveats and assumptions, our analysis is the first systematic estimate of return on investment from malaria research through a product development partnership.
[note] See RED Health Team Working Paper: Developing a framework for estimating the economic return on investment from product development research: An analysis of the Medicines for Malaria Venture Product Development Partnership. May 2019.

As mentioned previously, in 2024 Policy Cures published their in-depth analysis on ‘The Impact of Global Health R&D’, which looks more broadly than just the PDPs funded here but does include many of the products listed above, as well as other similar type products. They estimate that investment in this type of R&D will have saved 40.7 million lives, or 2.83 billion disability-adjusted life years (DALYs), by 2040, which translates to an economic benefit of $49.9 trillion, or a return on investment of $405 for every $1 invested.

Programme-level approach to monitoring and evaluation

Each component had its own Senior Responsible Owner (SRO) and programme manager who carefully monitored progress. This included receiving regular reporting from, and engaging in discussions with, partners. In addition, FCDO is a driving force in the regular meetings of the informal ‘PDP Funders Group’ – an international group with representatives from other funding agencies who also support many of the individual programmes. The UK was key in its establishment and took over as co-chair with the Swiss in 2022. This group shares benefits and risks of each of the components, working together to address issues and drive improvements. They also have annual calls with the CEOs of the established PDPs to facilitate identification of aligned interests, common goals, and shared bottlenecks (e.g. WHO pre-qualification process). In 2024, the group convened in South Africa, which included site visits to manufacturers, clinical trial sites, and government partners. Component SROs have also visited all of the PDPs at least every couple of years; for example, DeTACT’s SRO conducted a field visit to Thailand and Cambodia for DeTACT’s annual investigator meeting, as well as laboratory and field site visits, in 2023.

Throughout the lifetime of the programme, several assessments have been conducted of the PDP’s performance. This includes:
A 2020 FCDO-funded review of the role of PDPs in accelerating global health R&D. It aimed to: (i) provide an up-to-date overview of the PDP landscape, activities, and impacts, (ii) assess the extent to which assumptions underpinning the PDP model are still valid, and (iii) provide strategic recommendations to FCDO and other funders on how to optimise future investments in health R&D. The findings confirmed that the PDP model has been one of the most successful approaches to address the need for technologies to tackle poverty-related and neglected diseases (PRNDs), and that the five key assumptions underpinning the PDP model (addressing market failure, utilising a portfolio approach to R&D, maximising cost-effectiveness, building R&D capacity and catalysing access for health impact) remained valid. Three key areas identified for improvement were: (i) strategic development of access partnerships (and end-to-end approaches) starting earlier within the R&D process, (ii) improved coordination and a more joined-up approach among all stakeholders throughout the R&D process, and (iii) strengthened product prioritisation mechanisms to inform priority setting and funding allocations across the entire portfolio of products.

In 2021, the PDPs published a commissioned report on “Keeping the Promise”, which looked at the impact and performance to date of the FCDO-funded PDPs plus the additional non-FCDO funded core PDPs. This found that the PDPs had delivered 66 new health technologies since 2010, reaching more than 2.4 billion people, mostly in LMICs.

A 2021 PDP Fund evaluation by the government of the Netherlands (which highly overlaps with the PDPs funded here) both found that PDPs are highly relevant, the logic underpinning them remains valid, and they are a very successful approach to tackling poverty-related and neglected diseases.

In 2023, “Keeping the Promise” was updated, and reports that the featured PDPs have introduced over a dozen new health technologies in the past 2 years, with > 100 new products in late-stage development (Phase 2 or beyond), an impressive achievement given the reduction in global funding of PDPs for neglected disease product development. PDPs also continue to play a significant role in enhancing global research capacity, with updated data from “Keeping the Promise” finding that, since 2010, PDPs have worked to enhance research capacity in > 700 sites in 98 countries.

In 2024, Policy Cures published their major evaluation of the product development landscape, which also found that investment in neglected R&D is highly effective, estimating that 40.7 million lives will be saved by 2040 and return on investment of $405 for every $1.

Date of last narrative financial report	All reports received by July 2024	Date of last audited annual statement	All reports received by July 2024

Annex A: Additional Information

Table 2. Products that received first approval under previous FCDO-funding

Target disease/health condition:	Type of product:	Description:	Developed by:	Year:
Malaria	Drug	Pyramax (tablets for adults) – artemisin combination therapy (ACT) for both uncomplicated P. vivax and P. falciparum malaria	MMV	2012
		Pyramax (granules for children) – paediatric formulation of the above	MMV	2015
		Coartem dispersible – the first high-quality, fixed-dose ACT developed especially for children	MMV	2009
		Eurartesim tablets – ACT for uncomplicated malaria	MMV	2011
		ASAQ Winthrop – more affordable and easier to administer fixed dose ACT for uncomplicated malaria	DNDi (taken over by MMV in 2010)	2007
		ASMQ – easy-to-use ACT for uncomplicated malaria with high cure rates and long period of protection	DNDi (taken over by MMV in 2015)	2008
		SP+AQ-CO – monthly treatment for seasonal chemoprevention in children under 5	MMV	2014
		Artesun – injectable artesunate for severe malaria	MMV	2010
	Diagnostic	LAMP Assay for Malaria – field-tool to detect low-density malaria infections during elimination programmes	FIND	2014
		Highly sensitive RDT – point-of-care test for low-density infections	PATH/FIND	2016
	Insecticide	Actellic 300CS – is an effective indoor residual spray that only requires annual treatment	IVCC	2012
TB	Drug	Paediatric fixed dose combinations – the first child-friendly versions of standard TB treatments	TB Alliance	2016
	Diagnostic	LAMP Assay for TB – simple, accurate, robust, and affordable test for Tb that has been developed for high burden and low resource settings	FIND	2016
		Hain’s LPA for 2nd line drugs, the MTBDRsl – test for resistance to second line TB drugs	FIND	2016
		Nipro LPA for 1st line drugs, 2nd gen - test for resistance to first line TB drugs	FIND	2016
		Xpert MTB/Rif – Revolutionised TB diagnosis, taking diagnosis time from weeks to approximately 3 hrs. It has unprecedented sensitivity and can simultaneously check for resistance to the most common TB drug.	FIND	2010
Sleeping sickness	Drug	Nifurtimox-eflornithine combination therapy (NECT) – this was a ground-breaking treatment for sleeping sickness and spent 10 years as the first-line treatment until DNDi developed fexinidazole	DNDi	2009
	Diagnostic	HAT RDT 1st and 2nd gen – a rapid point-of-care test for sleeping sickness that is affordable, simple to use, and provides results in 15 minutes	FIND	2013/2017
		LAMP Assay for HAT – a screening tool in elimination settings	FIND	2015
HIV	Drug	Superbooster Therapy for Paediatric HIV/TB – there is a negative drug interaction between the most common treatments for HIV and TB, but DNDi showed that providing additional antiretroviral overcomes this	DNDi	2016
	Diagnostic	Xpert HIV-1 Qual - Qualitative 90-minute test enabling early HIV detection in high-risk and paediatric patients, including infants as young as 2 months old	FIND	2015
		Alere Filodetect (HIV combo) – Point-of-care diagnostic that runs in just 20 minutes	FIND
Leishmaniasis	Drug	New VL treatment for Asia – single-dose liposomal amphotericin B was revolutionary compared to the previous 28-day first-line treatment	DNDi	2011
		SSG&PM – a combination treatment for patients in Africa that is as effective as previous treatments but shorter, less likely to develop resistance, and affordable	DNDi	2010
	Diagnostic	LAMP Assay for leishmaniasis – less invasive and more reliable than other common diagnostics	FIND	2016
Ebola	Diagnostic	Xpert Ebola – rapid, high throughput, near-patient diagnosis for Ebola	FIND	2015
Chagas	Drug	Paediatric Benznidazole – first treatment for children with Chagas, they were previously having to cut up adult tablets	DNDi	2011
Diarrhoeal disease	Drug	Co-packaged ORS-Zinc – life-saving treatment for diarrhoea, PATH supported this getting added to the Essential Medicines List in 2019	PATH	2004