Concept Note for Approval
Please refer to the Concept Note PrOF Guide when completing this template. The final Concept Note should not exceed four pages (including the Annex).
	Title: Effective State and Democracy Programme
	Programme Value: £38 million			Directorate/Department/Post: FCDO Zambia
	Contact name: Ben Powis, Team Leader, Governance, Politics and Human Development			[[Point of Contact for CN]]
	Threshold for Approval: <£40 million			Ministerial Approval
	Programme duration: 7 years		Start Date: April 2024		End Date: December 2031
	Overall programme risk rating: / [[Choose from drop down menu]]		Major
	Novel and Contentious: [[Indicate if the programme is considered novel and contentious –Y/N]]	N	Reputational risks and UK political handling issues: / [[Indicate if there are any major/ severe reputational risks or political handling issues that SpAds/Pads will need to review – Y/N]]			N
	Programme Code (for legacy DFID programmes):		Vault Number (for legacy DFID programmes):
PROGRAMME NARRATIVE	Consolidating Zambia’s democracy is essential for achieving its development goals. Zambia has the potential to drive democratic values across the region. Yet despite progress since the 2021 election, Zambia’s democracy continues to represent some groups and issues more effectively than others. The Government of Zambia has committed to reforms that would entrench accountability, transparency, citizen participation and an enabling legal/judicial framework, as well as combat corruption - all key areas for good governance and development. But progress implementing reforms has been slow. There is a risk that people, particularly those marginalised from political priorities and the growing youth population (who voted at the highest rate ever in the 2021 election), don’t see democracy delivering for them and Zambia’s democratic institutions and practices erode over time. / The ESD programme aims to embed democratic values in Zambia’s institutions and practices and support an inclusive, effective state, which delivers poverty reduction and growth for all its citizens. It will bring together support for a) public sector delivery b) evidence-based policy and c) constructive engagement to drive long term improvements in Zambia that demonstrate the values and dividends of open society and democracy. We will do this by working with the centre of government on prioritisation and delivery, and with non-state actors (like CSOs) to help tackle key governance issues. The programme will be designed to flex in response to political opportunities, including the potential for a new government following 2026 elections. / It is likely that at least initially there will be a strong focus on anti-corruption, civic space and inclusive economic growth policies (which are current priorities of the Government, where the UK has a comparative advantage).

STRATEGIC	There are two strategic drivers for implementing this programme: / It aligns with the UK’s vision in the Integrated Review Refresh and FCDO’s Africa Strategy to promote democracy and good governance. This matters geopolitically; a more democratic Zambia will be a more valuable partner for the UK, not only in terms of the bilateral relationship but also in regional and multilateral fora. Strengthened institutions will be more resilient to malign influence. It also matters for Zambia’s development outcomes, as outlined in the International Development Strategy: “When people have more power and choice, populations become more prosperous, peaceful and healthier”. Ensuring a focus on women’s full and equal civic and political participation and leadership throughout this programme will be vital to underpinning a healthy democracy. / We have a window of opportunity now which we can seize. Since the 2021 election, there has been a political openness to change in Zambia. Young people, who constitute more than half the electorate, are increasingly politically active. This, combined, with the quality of relationships the UK has with key decision makers, brings important political opportunities for reform. We will design a programme that can seize these opportunities and is flexible enough to adapt to changes in political context if required.
PORTFOLIO FIT	ESD will predominantly deliver against three outcomes in BHC Lusaka’s country plan: / Zambia represents and drives shared democratic values and increasing UK alignment in regional and international fora. / Strong institutional capacity that secures and deepens democratic practice, civic freedoms and constructive dialogue. / More effective policy prioritisation, coherence and implementation capacity in public sector to deliver on evidence driven national development priorities. / Evidence tells us that countries with more effective governments have been able to make more progress towards the Sustainable Development Goals. The building of “effective, accountable and inclusive institutions at all levels” (Goal 16) is a critical enabler for success in every development sector. ESD will underpin successful delivery of all the UK’s equities in Zambia, including in local governance and service delivery, green growth, and strengthening economic ties. / It will have impact at scale with a relatively modest annual budget by drawing on our loadbearing diplomatic relationships with key decision makers, the UK’s ability to target technical advice in areas that deliver big wins, be responsive to political opportunities, leverage expertise through the UK Centres of Excellence and use agile programme design to ensure value for money (VfM) throughout its lifespan.
ECONOMIC	We will test these four options during the design stage: / Option One: Do nothing. / Option Two: Contract one management agent to implement all programme activities (technical assistance and grants). / Option Three: Contract a management agent to implement the technical assistance and use accountable grants for non-state partners. / Option Four: In-source the management of the programme (with up to three programme funded posts). FCDO directly manage technical assistance and non-state windows. / We expect the cost of individual activities in this programme to be relatively small. Costs will include consultancy fees, non-state partner activities, and learning and evaluation costs. A VfM framework will be developed to ensure we maximise impact per pound spent. We will ultimately achieve VfM in this programme if the influence and technical assistance (a ‘great buy’) provided is of the appropriate quality and time to have impact. / The other key cost driver will be the management structure. Previous UK democracy and governance programmes in Zambia have succeeded when they were designed to adapt and when they engaged in cross-learning between different implementation partners to maximise collective impact. However, ensuring local partners have the capacity to manage this kind of programme could be a challenge (hence the options above), as is designing a programme that can easily shift focus and partners to maintain impact in a fluid political environment. BHC Lusaka’s existing programmes have given us experience of implementation which we can build on.
COMMERCIAL	The ESD will build on existing programming with multiple partners working in close cooperation with government on a range of reform issues. A number of key questions will be assessed during design: / Value for money of using a fund manager (versus multiple contracts/direct management). / Relationship impact of merging technical assistance with non-government grants / Value/need for direct FCDO engagement in key relationships and case for programme funded posts. / Market options for delivery of all or aspects of the programme. / Design will include early market engagement as well as comparative value for money assessment that will feed into appraisal, commercial and management cases.
FINANCIAL	We propose £38 million over 7 years with an expected spend of £5 million in the first year (from March 2024). This is within the current budget agreement for 24/25. The programme is likely to then have higher spend (around £7million) in the run up to the 2026 and 2031 elections but will have the flexibility to scale up or down as needed.
MANAGEMENT	The FCDO has demonstrated capacity to design and manage effective governance and democracy programmes, bringing together development and diplomacy skills. This programme will be led by a full time G7 UKBS SRO, who will be supported by a CBS Governance Adviser and programme officer, with oversight from the G6 team leader. We will be assessing the rationale for up to three programme-funded posts under this project, with at least one seconded to key government counterpart, and one potentially to an implementing partner. This will ensure strong policy linkages between FCDO and its partners, enabling our wider development diplomacy effort around the programme.
RISK	This programme is expected to be rated moderate/major risk based on the below three key drivers (we anticipate strong mitigation to be possible for each risk): / Political: Government partner(s) fail to demonstrate commitment and progress on democracy, undermining case for close engagement. / Delivery: Scale of support and timing insufficient to reach a ‘tipping point’ on change. / Context: Political or other crisis necessitates rapid change of approach and unpicking MoU or agreements with counterparts. / The adaptive programme design will be critical for managing risk; it will enable the programme to adapt to changes in the political, delivery or contextual environment.
RECOMMENDATION	We recommend approval of the design of a £38 million 7-year programme on Effective State and Democracy in Zambia. If approved by Ministers, the detailed design process will begin in October 2023 in order to seek approval of the Business Case to allow start up by April 2024.
Outcome:		[[Approved/ Approved with Conditions/ Rejected]]
Conditions (if applicable):
Notes:		[[Feedback to accompany any full approval or rejection]]

Annex A: Assurances Table
Legislation: Development Act, Gender Equality, / Public Sector Equality Duty, Counter-Terrorism	We anticipate that this programme will make a significant contribution to gender equality (Gender Equality Marker 1: Gender equality is an important and deliberate objective, but not the principal reason for undertaking / the project/programme). This programme will challenge unequal power relations and enable participation and leadership of women and accountability to the needs and priorities of women. The programme will ensure that gender discrimination issues are identified and addressed to contribute to eliminating all forms of discrimination against girls and ensure gender equity. This programme will also comply with the Public Sector Equality Duty. / This programme complies with the International Development Act. It will encourage elected leaders to focus on issues which citizens care about. It seeks to mandate elected leaders to reduce poverty by holding them accountable for spending domestic resources for that purpose. / The threat of terrorism in Zambia is low. The risk that any of our partners will divert funds to finance terrorism is also low.
Safeguarding Considerations:	This programme will adhere to FCDO safeguarding standards and related risks will be pro-actively monitored, considered, and managed. The main safeguarding considerations pertain to the risk of intimidation, threats, or attacks on programme partners (minor) due to the politically divisive nature of governance and the risk of violence against women and girls, particularly SEAH, whilst engaging in programme activities (minor). Safeguarding will be prioritised throughout the programme lifecycle, with an acute focus on women’s protection issues. While Enhanced Due Diligence Assessments will be required, partners are expected to have strong safeguarding protection and zero tolerance policies against bullying, harassment, and sexual exploitation.
Climate and Environment: / Paris Alignment / Environmental Protection / International Climate Finance (ICF	Given the nature of this programme, it is unlikely to have significant climate impacts. The highest impacts are likely to derive from driving long distances to reach rural populations. As part of the design process, we will undertake a climate and environment risk assessment to understand these risks fully. The programme may contribute to improving climate change by addressing policies linked to climate change adaptation and mitigation (e.g., agriculture subsidies). We do not anticipate that this programme will contribute to the ICF target.
Nutrition:	Nutrition will not be targeted through this programme, although it is possible there will be indirect contributions through policy and service delivery improvements. Malnutrition and food insecurity are high in Zambia. Zambia’s staple crop (maize) is low in nutritional value, contributing to one of the highest rates of child stunting in the world. Zambia’s size, its dispersed population and distance from global value chains limits market access for farmers. This is likely to be a political priority for rural populations and women, who are the primary targets for this programme.