Programme Completion Review

Title: Learning and Evidence for New Strategies in the Sahel (LENS) programme
Final Programme Spend £ (full life): £499,565	Review Date: December 2024
Programme Code: 300536	Start Date: 17/11/21	End Date: 31/12/24

Summary of Programme Performance

Year	2022	2023	FINAL
Programme Score	B	B	B
Residual Risk Exposure Rating	Moderate	Moderate	Moderate

DevTracker Link to Business Case (and any addendum):	https://iati.fcdo.gov.uk/iati_documents/90000211.odt
DevTracker Links to all logframes used during programme lifetime:	https://iati.fcdo.gov.uk/iati_documents/D0003849.xlsx

A. Summary and Overview (1-2 pages)

The Learning and Evidence for New Strategies in the Sahel programme (LENS) was designed to generate and facilitate the timely use of context-relevant research, analysis and evidence products that inform UK engagements and influence those of others in the Sahel. It aimed to provide a mechanism to commission, strategically disseminate, and support the effective use of research and evidence products that target stakeholders at critical decision-making points.

The programme design focused on selected thematic areas where it was judged that targeted and context-relevant research, analysis and evidence products could help deliver improved policy, diplomacy, and programming by the UK (particularly where the UK has no bilateral investments), and our partners. This included the priority thematic areas of the FCDO’s [then] third strategic objective in the Sahel i.e. Support sustainable development by (a) Empowering women and girls, and the most vulnerable, and (b) Building climate resilience, accelerating access to climate finance and supporting sustainable growth. It also included engagement to strengthen the impact of partnerships and alliances developed to improve international coordination and accountability, and to increase the impact of UK contributions through International Financing Institutions (IFIs) and multilateral and global financing initiatives in the Sahel.

The LENS programme was designed to be delivered through three components:

Component 1: a Delegated Cooperation Agreement (DCA) with the French development agency AFD to “buy” into the Sahel Analysis, Monitoring and Learning Platform (PASAS). PASAS generates context analyses and thematic studies and is implemented by the Institut de Recherche pour le Developpement (IRD) in consortium with International Consulting Expertise-France (ICE) who mobilise a pool of local experts. Partnering with AFD was supposed to allow the UK to co-commission research activities in areas and themes of joint interest and to support research uptake in the region. This was to be achieved through 2 x £500,000 contributions to AFD to be spent by 31 March 2024. More than the added value of the research itself, UK co-funding aimed at strengthening the partnership with France and other Sahel Alliance members and contributing to a joint use of evidence towards coordinated approaches to development in the region.
[note] In 2018 the NSC agreed to scale up UK efforts in the Sahel, to (i) combat terrorism and support stability, (ii) tackle extreme poverty and build resilience and (iii) strengthen global partnerships (particularly with France).

Component 2: a Flexible Facility to be procured directly by FCDO that would have provided on-demand services to FCDO staff (and, via FCDO, to our partners, e.g. other Sahel Alliance members). Support provided by the facility would have included learning and evidence syntheses, technical advisory services, and translation services as well as capacity building for local research institutions.

These two components aimed to complement each other. The Flexible Facility would primarily produce synthesis products (rapid evidence assessments, literature reviews, etc) and provide a focus on research dissemination and uptake, while the PASAS – LENS partnership would support longer-term primary analysis to fill any identified research gaps.

The programme also has a third minor component (3) to enable the payment of fees for the UK’s membership of the Sahel Alliance. It recognised the opportunity that this provided to share analysis and coordinate policies and approaches with key partners, in line with the overall theory of change.

Major lessons learned, evidence generated and recommendations [1/2 page]

LENS was designed at a time of projected expansion of UK ODA in the Sahel region.
- Shortly after the programme started in 2021, the UK announced a reduction of its Official Development Assistance (ODA) spending to 0.5% of gross national income (GNI) until the fiscal situation allows a return to 0.7%.
- As a result of ODA cuts, Components 2 (Flexible Facility) and 3 (Sahel Alliance membership fee) of LENS were suspended.
- The cuts in the Sahel Department budget in FY22/23 and FY23/24 led to a delay in procuring the Flexible Facility and reduced the need for an on-demand evidence and research facility within a much-reduced portfolio. The consolidated FCDO central research and evidence offer also reduced the need and justification for a regional research facility.
- The Sahel Regional Board agreed, on 21 September 2023, in a constrained ODA context, to cut the Flexible Facility and reprioritise the funds elsewhere. This affected the overall capacity of LENS to achieve its outcomes.
- Component 1 (PASAS) was also affected by changes in the political and security context in the Sahel following the significant deterioration in France’s relationship with several Sahel countries and increasingly difficult position of French institutions in the region. Throughout 2023/2024, the programme has been operating in an increasingly unstable context, with Mali, Burkina Faso and Niger all posing significant operational and policy challenges following France’s decision to suspend its support in those countries. This has made it impossible for AFD to conduct field work in three of the five countries that the programme is set up to have an impact in (Mali, Niger, Burkina Faso) and to actively disseminate and engage in the other two.
- Given AFD’s difficulty to spend, it was decided not to release the second tranche of funding and to close the PASAS component early by December 2024.
- The mobilisation and payment of the Sahel Alliance membership fee proved challenging because of the Sahel Alliance’s status and this component was not procured.
- With Component 1 closing on 31st December 2024, and the other two components cut, it was decided to close the LENS programme early.
- Delays in implementation and output delivery were a combination of UK ODA constraints and changes in operational context and were largely outside of the programme’s direct control.
- There was a clear need for a regional research and evidence programme at the time of design. The Flexible Facility component would have provided a useful draw-down service to support evidence-based programming design and policy engagement in a region where the UK had a relatively new and small footprint (at the time of programme design in 2020 embassies in Niger, Chad and Mauritania were only just opening for the first time).
- The need for evidence generation on development needs in the Sahel is likely to arise again as the
  Sahel department refreshes its strategy and future-proofs its portfolio, as ODA budgets stabilise and/or increase and as the development looks for resources to fund development diagnostics and scoping studies to inform UK added value and support new programme design as well as technical assistance on policy engagement.
- As the department looks to fill the evidence gap, it is important to learn lessons from LENS. A dedicated research programme might not be the most cost-effective way to fill the gap. Without a dedicated regional research platform, the Sahel department can leverage the existing R&E offer and research CMPs or build R&E into existing and future programmes. There are also questions of efficiency around the procurement mechanism of such a facility in a region like the Sahel where few actors (in particular outside French institutions) are operating on the ground and the need to remain flexible in the types of partners that can be commissioned.
- The main component of evidence generation and dissemination in the design of LENS was the flexible facility. Without it, it is difficult to assess the programme’s performance against its objectives. The programme’s main outcomes were designed as a combination of PASAS and the Flexible Facility, with the two components working in synergy, complicating the task of assessing the performance of PASAS on its own.
- The main lesson learnt from PASAS is the need for more clarity on UK co-funding objectives when ‘buying into’ an existing research programme. The PASAS component was included in the LENS design mainly as a vehicle for strengthening cooperation and coordination with France and the Sahel Alliance members. In practice PASAS did not play its planned role in coordinating Sahel Alliance members’ research and evidence needs and leveraging this evidence to influence common approaches. The independent mid-term review of PASAS highlights many of the programme’s shortcomings both on timeliness and relevance of outputs and dissemination and on PASAS’s consultative efforts. Beyond coordination benefits, PASAS provided limited value in terms of generating new research and evidence and in terms of supporting UK engagement, partly due to the deteriorating context, but largely due to the capacity of the PASAS team to provide relevant, timely and accessible research targeting a policy audience and to adapt and respond to FCDO research needs.

How this report was conducted [1 paragraph]

This report was led by the LENS team (SRO and PRO), with inputs from previous LENS PRO, Sahel advisers and programme managers and Sahel Posts and drawing on AFD’s mid-term reports submitted in September and November 2024 and the independent mid-term evaluation shared by AFD.

Actions following approval of this report [1-2 paragraphs]

All financial disbursement and operational closure activities have taken place for LENS. Archiving of relevant programme documentation will take place at the appropriate time.

Additional actions following this report will be to ensure that the lessons learned from LENS are fed into the design and business planning for any future programmes in the Sahel, particularly around taking advantage of CMP R&E offers and considering inclusion of R&E within new programme design.

## B: Theory of Change and Outcome Assessment (1-2 pages)

	Starting point	Final result
Budget	£4m	£499,565
Timeframe	17/11/2021 - 31/12/2025	17/11/2021 – 31/12/2024
Outcomes	Increased use of policy-relevant analysis and evidence products in decision-making across priority areas for UK engagement in the Sahel / Increased leadership and capacity of Sahelian actors to generate research and evidence	The programme delivered a number of in-depth research outputs and policy briefs. UK funding supported the translation of evidence into English and a switch to more accessible and policy relevant products to support decision-making.

Overall assessment of programme outcomes, sustainability and VfM [1/2 – 1 page]

- Outcome 2) on ‘Increased leadership and capacity of Sahelian actors to generate research and evidence’ was linked to the Flexible Facility. LENS did not expect to deliver against this outcome through Component 1 (PASAS). LENS effectively did not directly contribute to Outcome 2 although it is possible that UK funding indirectly contributed to building capacity of local researchers through capacity building by AFD and its downstream research partners who, according to the independent mid-term review, support and train local researchers from Sahel countries.
- Through PASAS, the LENS programme contributed to Outcome 1 ‘Increased use of policy-relevant analysis and evidence products in decision-making across priority areas for UK engagement in the Sahel’.
- This Outcome combined Components 1 and 2. Since Component 2 was not procured, we can only assess the contribution of PASAS.
- A key strength of PASAS is the online platform that brings together in one place all PASAS research as well as other research available in French and English on issues relevant to the programme i.e. research and evidence that can help tackle fragility and the root causes of conflict in the region. The platform has known delays in its launch and improvement of its functionality. The mid-term evaluation assesses that this is partly due to a lack of dedicated resources for dissemination in the contract with IRD and lack of technical capacity in the team. The platform has limited reach, analytics for 2024 show that the website had 320 users only over the whole year with 50% of viewers based in France, 8% (around 20 views) in Senegal and China, and 5% (around 10 views) in Cote d’Ivoire, Burkina Faso, Mali and Belgium.
- Although one of PASAS’s objectives is to support a more cohesive approach to evidence generation and policy decision within the Sahel Alliance, in practice Sahel Alliance members were seldom aware of the PASAS offer or consulted on joint topics of interest. The main stakeholder of the AFD team managing the contract with IRD/ICE are AFD internal teams, and dissemination almost exclusively targeted AFD teams, with limited dissemination in Sahel Alliance platforms, and limited awareness of the existence of the PASAS online platform even amongst regional expert networks and research institutions.
- In terms of policy-relevance for the UK, most of the studies which the UK co-funded in 23/24 were ongoing studies that started before the FCDO’s partnership and were therefore not agreed with the FCDO and did not benefit from FCDO advisory and post input, which limited any opportunity to make them more relevant to UK policy and programme design. In addition, the IRD approach to research is very academic, it is not always accessible to a policy audience and was only available in French, which made the research outputs of limited relevance to FCDO.
- The AFD project team was relatively open to considering research topics of interest to FCDO, they would however be clear that any topic suggested would need to fit with AFD priorities. This limited the relevance of the programme to the two thematic areas identified as key interest for the UK at the time of programme design i.e. empowering women and girls and building climate resilience. Once a topic was suggested, FCDO would seldom have an opportunity for input until an advanced ToR was shared by AFD, often after a few months, which would not always fit the original request and be difficult to shift, again limiting the relevance of the final output to FCDO policy and programming objectives.
- From 2023 onwards and due to the operational challenges, PASAS pivoted to a regional (including west and coastal Africa), desk-based approach rather than country-based field research. This shift and AFD’s need to restructure the research contracts with IRD, opened some space to negotiate expected results from FCDO funding and increase, marginally, the relevance of PASAS to UK knowledge needs. AFD agreed to produce summaries and infographics in English for existing research, as well as concise and timely policy briefs on topical issues going forward, through a new framework contract with IRD. This new framework contract took several months to be agreed between AFD and its downstream partner, further limiting value of an existing network of researchers as a responsive tool for policy decision in fragile contexts. The mid-term review makes several mentions of PASAS’s internal challenges, cumbersome programme management and slow pace of delivery, and inability to deliver research outputs in short timeframes.
- UK funding to PASAS somewhat contributed to Outcome 2 in the short term. AFD is planning to extend and geographically expand the programme. Through FCDO lobbying with the AFD project team, the UK’s investment contributed overall to the agility of PASAS (through timely briefs), its availability to an English-speaking audience and improvements in dissemination (through podcasts and infographics). This might increase the value and sustainability of UK investment in PASAS in the long-term if AFD maintains these policy-relevant outputs in the next phase of the programme.

PASAS timeline from 2018 to date:

Theory Of Change:

The programme has had limited capacity and time to deliver planned results due to ODA cuts between 2021 and 2023. The only component procured (PASAS) met expectations and contributed to Outcome 1. Where objectives have not been completed this does not necessarily reflect on the quality of programme design or delivery.

## C: Detailed Output Assessment

Output Title Analysis, learning and evidence products that respond to evidence and knowledge needs of UK, international coalitions (including those of which the UK is member) and Sahelian decision-makers / Output number: 1 Output Score: B (PASAS scored an A but this output assesses against both PASAS and Flexible Facility) / Impact weighting (%): 70 Weighting revised since last AR? No
Output Indicator	Starting Target	Final Logframe Target	Final Result Achieved
1.1 Number of quality assured studies and context analyses carried out, including joint analyses with partners.	PASAS / 22/23 Milestone / 2 context analyses, 3 thematic studies. / Flexible Facility / N/A	PASAS / 23/24 target / 4 thematic studies / English language summaries and infographics of previous studies	2 x Context analyses completed. / 3 x Thematic studies completed (22/23) / 4 Thematic Studies completed (23/24) / 1 x Context analysis published on the digital platform. / 3 x Thematic studies published on the digital platform. / English summaries provided for 3 studies / Infographics on 4 studies
1.2 Number of evidence synthesis products produced. / E.g. rapid evidence assessments, literature reviews, systematic reviews / (FF studies signed off by SSD, non-cumulative)	N/A	N/A	N/A

Output 1.2 does not apply to PASAS, so we are not assessing it in this PCR.
Output 1.1 includes both PASAS and the Flexible Facility, we are only assessing PASAS’s performance against set milestones and targets, for which expectations were met in terms of number of research products produced.

Overall, the UK funded:
the following 9 PASAS thematic studies:

1. "Women, Peace and Security: The Case of the Lake Chad and Ouaddaï Provinces"
2. "Protection Issues in Prolonged Crisis Contexts in West Africa: Bridging Responses Between Humanitarian Aid and Development"
3. "Governing Food Crises in the Central Sahel: Managing Risks or Strengthening Actors?"
4. "Taking Mental Health into Account in Crisis Contexts in the Sahel / West Africa"
5. “Analytical mapping of social science studies and research on the Sahel region” (published in March 2023)
6. “Territorialized analysis of the fragilities in Chad” (published in April 2023): This is awaiting publication due to sensitivities around the report and is currently being reviewed by the French Embassy in Chad to check if it is publishable on the digital platform. At the end of May 2023, a short briefing of part of the study focussing on eastern Chad and the crisis in Sudan was provided.
7. “Civil societies in the Sahel: a reasoned cartography. From understanding contexts to supporting social change” (published in April 2023)
8. “Capitalisation on gold mining dynamics in the Sahel region” (Published on 5 December 2023)
9. “Analysis of vulnerability and resilience factors in the governance sector in Niger” (published on 5 December 2023)

Contextuel briefings :
1. The impact of the Malian security crisis on Mauritania”
2. “Rethinking the management of the migration crisis in the border countries of the Sahel region”
3. “The challenges of disinformation for international and national players in the Sahel and Gulf of Guinea countries”
4. “Updated focus on the humanitarian, security and political situation in Eastern Chad” (French version only) in June 2024
5. “Military coups in the central Sahel: What perspectives for democracy and the return to constitutional governments?” in August 2024;
6. “Challenges and Issues of digital sovereignty in West Africa in 2024: From the principle of sovereignty to a strategic, adaptive, and resilient digital autonomy” in September 2024;
7. “How has the terrorist threat changed the paradigms of international aid?” in October 2024
8. “Possible approaches to address deteriorating France-Africa relations” in November 2024

Translation and infographics for previous studies:
1. « Capitalisation on Artisanal Gold Mining in the (Former) G5 Sahel Countries and Senegal », which restitution workshop took place on June the 14th 2024.
2. « Analysis of Vulnerability and Resilience Factors in Governance in Niger », which restitution workshop took place on June the 5th 2024.
3. « Civil Societies in the Sahel », which restitution workshop took place on February the 2nd 2024.

Quality assurance is being done and is carried out throughout the research process. This starts with the Terms of Reference, which should be shared with the FCDO, AFD colleagues in charge of conflict and crisis prevention work, and other researchers. Draft research papers are then shared with the same group and follow up conversations are held with senior researchers. IRD are a predominant public research centre in France and so have their own research standards.

Output Title	Research uptake and engagement activities that support access and use of research products by key decision-makers in the Sahel
Output number:		2	Output Score:	B
Impact weighting (%):		30	Weighting revised since last AR?	No

Output Indicator	Starting Target	Final Logframe Target	Final result achieved
2.1 % of research products that have accompanying dissemination/uptake strategies and activities. / (FF & PASAS)	100% of PASAS and FF products have accompanying research uptake plans and activity.	100% of PASAS and FF products have accompanying research uptake plans and activity.	Most of PASAS research outputs are published on the online platform. Most of the research undertaken with FCDO funding was shared within AFD and FCDO audience through webinars.
2.2 Number of activities undertaken to support the use of LENS-produced evidence in policy and practice, with a clear theory of change linking the Output to Outcome and then Impact. / E.g. policy briefs, webinars, roundtables, workshops / (FF & PASAS, per year, non-cumulative)	1 Research Uptake activity (PASAS) / FF – N/A as the Flexible Facility was not procured.	1 Research Uptake activity (PASAS)	-Webinar on the "Fragility basins in Chad" study at AFD's Chad country / meeting in January 2024 / -Webinar on the "Analysis of vulnerability and resilience factors in terms of governance in Niger" study for the Sahel Alliance in April 2024; / -Series of webinars of studies produced for the FCDO between January and December 2024.
2.3 Number of technical assistance (FF) tasks undertaken to engage and sensitise decision makers in the G5 Sahel to PASAS-LENS and other research and evidence. / (FF only, per year, non-cumulative)	N/A – this output indicator was for the Flexible Facility only.	N/A
2.4 Number of translation products produced. / (FF only, per year, non-cumulative)	N/A – this output indicator was for the Flexible Facility only.	N/A

We can only assess PASAS against outputs 2.1 and 2.2 as the other sub-outputs relate to the Flexible Facility.

The quality of dissemination of research outputs and capacity to monitor uptake is limited due to absence of PASAS monitoring framework for research dissemination and of an uptake strategy from AFD.

Launching of the products is done predominantly through the publicly available PASAS digital platform. This has been improved since its launch in 2021 and includes new features, added in February 2023, with more precise search filters and a renewed home page highlighting the newest studies. AFD has improved the frequency of dissemination through briefings / webinars and is starting to improve its use of social media, newsletter and podcasts as dissemination tools, as a result of FCDO lobbying. More recently the products have been sent to the Sahel Alliance coordinator with the suggestion that they are communicated via their social media pages. It should be noted that the PASAS platform aims to be not only a repository for PASAS research output but a knowledge hub on the Sahel and to this end includes a significant amount of research carried out by different actors working on the Sahel, in French and English. It has therefore potential value beyond the PASAS research produced but given low uptake at the moment this value is difficult to gauge.

The digital platform is the main way that PASAS sees their products being disseminated, and as stated previously, the PASAS digital platform has been improved during the reporting period, but the platform still has limited reach (only 320 viewers in 2024). Part of the difficulty in ensuring accompanying dissemination and uptake strategies is the current context in the Sahel, which has worsened during the reporting period. This has made it difficult to carry out large dissemination activities and ensure the uptake of knowledge in the Sahel region.

Overall, the focus of the AFD project team was skewed towards dissemination for an AFD internal audience, with limited vision for a wider uptake strategy, and with most dissemination efforts delivered through invitation-only meetings or webinars and often in French, limiting its accessibility by FCDO colleagues but more widely by Sahel Alliance members and other key stakeholders in the region.

Output Title	Activities to support local capacity to conduct research and analysis, and communicate research findings effectively to decision-makers
Output number:		3	Output Score:	N/A
Impact weighting (%):		0	Weighting revised since last AR?	N/A – not assessed at the last AR.

Output Indicator	Starting Target	Final Logframe Target	Final result achieved
3.1 Number of events or training sessions organised to support learning and exchange between national and regional researchers. / (FF)	For Flexible Facility only	For Flexible Facility only	N/A

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score. [1/2 page]

No activities were planned for this output over the review period, as the flexible facility was not procured. The impact weighting of this Output was therefore set to 0% for the Annual Reviews and for the PCR.

D: Value for Money

VfM performance compared to the original VfM proposition in the business case:

The business case estimated that together, the Flexible Facility and PASAS would provide greatest value for money. As we did not proceed with the Flexible Facility, this section looks at the VfM for the AFD – PASAS partnership.

Economy: The business case stated that partnering with PASAS, and using their broad local network, would save the UK costs and time. Working with PASAS would also allow the UK to help shape the remaining investments made with the €4.9m French investment in PASAS.

AFD charge 9% of the total programme budget for the work that is carried out by PASAS. This is seen as a reasonable cost that represents good value for the administration and management of the programme. The programme also spent €97,276 ensuring the IRD consortium is maintained. This represents 17% of the overall programme spend to date. The programme budget is split 50:50 between FCDO and AFD, and this helps to drive the value for money of the programme. Of note; without the Flexible Facility, the ability for the UK to shape the PASAS programme has been limited and so the joint funding has not had the effect originally detailed in the business case.

Efficiency: In accordance with the business case, the LENS partnership with PASAS was meant to build on HMG and broader research work carried out in the Sahel to deliver more outputs for a given number of inputs.

As mentioned above, the lack of a Flexible Facility and active dissemination of the products reduced the programme’s efficiency. Additionally, budget cuts led to a smaller Sahel portfolio and reduced the need for a draw-down evidence facility both for programme design and policy engagement. The Sahel Board also agreed that the FCDO central research and evidence (R&E) offer was sufficient to cover the need for evidence and includes opportunities to support local research through centrally managed programmes, which would offer better efficiency than a regionally procured research programme. The Sahel Department is currently drawing on centrally managed R&E resources such as the CMF (Climate Mainstreaming Facility), the Nature facility, SPARC (climate finance), BASIC (social protection), West Africa research hub, and CLARE.

Effectiveness: The business case estimated that LENS would achieve maximum effectiveness by helping policy and programmes have better impact.

The digital platform that has been developed has had a total of 192 users (January 2024 data), of which 118 are based in France, 19 in Mali, 7 in both Belgium and Senegal, 6 in Burkina Faso, 5 in Mauritania and 4 in Chad. Given the platform was launched in February 2023 this figure appears low, and therefore more work is needed to ensure it reaches its potential both in terms of number and geography. As mentioned under output 2, to ensure real effectiveness PASAS need to actively promote all of the products that are produced. Some of this has not been possible due to the changes in the operating context, for example, there had been plans to present Niger country research in Niger, however this was put on hold due to the current political and security situation following the coup in July 2023. Moving forwards, active promotion of the products with follow up should be prioritised wherever possible and this will subsequently be more likely to lead to changes in policy or programming.

Equity: The business case stated that by partnering with PASAS, the UK would be able to leverage its contribution to promote the mainstreaming of gender and social inclusion into the French research and evidence agenda, where this doesn’t already exist.

The research that has been carried out so far generally does not have a specific focus on gender, social inclusion, or disability. The PASAS team are planning to have a Women, Peace and Security (WPS) focus in future studies, however this has not been promoted over the current reporting period.

E: Risk

The overall risk rating for LENS remains as moderate, the same as all the annual reviews.  This understanding is formed from the project risk register, which has 7 moderate residual risks and 2 major residual risks.

Strategy and Context:  The risk appetite for strategy and context is receptive.  LENS is operating in a fragile and insecure context. Four of the five Sahel countries (Burkina Faso, Chad, Mali, Niger) are considered as Fragility, Conflict, and Violence (FCV) affected countries.  All five countries host refugees or Internally Displaced People (IDPs).  The largest issue for the PASAS element of the programme was the disruption to programme activities due to the deterioration of the political and security situation in the areas of operation.  Since July 2023, PASAS has only been able to actively work in Mauritania and Chad.  Additionally, the PASAS AFD team was relocated from Ouagadougou in Burkina Faso to Dakar, and the same happened in October 2023 for part of the PASAS team who were based in Bamako in Mali.  Therefore, the biggest risk to the programme as a whole has been around the effectiveness of PASAS and the research they were able to carry out given the continually deteriorating security and political situation.  Recommended literature reviews and analysis completed outside these countries failed to mitigate this risk.

Policy and Programme Delivery:  The risk appetite for policy and programme delivery is receptive.  The key delivery risk for LENS was that the products produced did not meet the requirements to ensure effective use by the UK and enable policy change. This risk has been realised over the period of the programme and AFD/PASAS actions taken to mitigate this risk failed.  A further risk for PASAS was around the content of the products not being acceptable to the authorities in the country they are focused on, as has been evidenced in the territorialised analysis of fragilities in Chad. This risk was also realised over the period of the programme.

Financial & Fiduciary Risk:  The risk appetite for fiduciary risk is cautious.  This risk centred around fraud which is key due to the fragile operating context.  The due diligence assessment stated that AFD assesses the downstream partner’s financial guarantees and HR capacities as well as conducting a thorough investigation to identify potential fiduciary risks.

Safeguarding:  The safeguarding risk appetite is cautious and remained a risk throughout the programme. Although there were not any safeguarding incidents reported during the life of the programme, there was no specific AFD mechanism in place for safeguarding incidents to be reported except through the monthly operational meeting.  However, IRD have a policy / procedure for reporting incidents and as PASAS’ implementing partner, this procedure was applied across all research carried out.

The main risk over the length of the programme has been the increasingly fragile context that LENS operates in. This has affected PASAS’s ability to carry out effective research and disseminate information from the products that are produced.  In turn, this influenced the ability to achieve the milestones set out in LENS’s output and outcomes and is why we have decided to end the programme earlier than originally envisaged.

F: Programme Management: Commercial and Financial Performance, Monitoring and Evaluation [1 - 1 ½ pages]

The partnership between FCDO and AFD is established, and some progress has been made to ensure a joint understanding of the research that is required. However, there is little evidence that the products produced have been of a genuine use to the UK.

Flexible Facility: This was not procured and, after going to the Sahel board in September 2023, it was decided that the funding for this part of the LENS programme should be repurposed.

PASAS partnership: For the PASAS partnership, management of the programme was through AFD, who provided programme oversight of the operational delivery of this component. AFD draw upon suitable experts, commodities, and goods to deliver the programme through an IRD-ICE consortium based in the region.

The DCA with AFD stated that AFD would provide the FCDO with 6-month and 12-month progress reports to highlight the progress of the PASAS workstreams, challenges and issues, as well as any key learning. The programme started in November 2022, however, the 6-month report was first submitted in September 2023, which did not allow for the oversight that had been expected. The same report was then updated in November 2023 as AFD’s 12-month report. A final narrative and financial report were provided in December 2024.

Sahel Alliance: The business case saw LENS provide an annual membership fee for the Sahel Alliance (SA) that would enable the running of the secretariat in Brussels amongst other areas. The understanding was that payment would be requested at the start of the calendar year by the SA and that this would then be paid. This did not happen as we could not find a payment modality that would both meet FCDO rules and whose reporting requirements would be acceptable to GIZ, who fund the Sahel Alliance Secretariat. Although it was suggested in the last annual review that this funding be used to ensure the most effective way of working with the SA moving forwards, this was therefore not taken forward.

Financial management: The approved budget for LENS was £4m spent over 4 years and 4 months. The programme will end after 3 years and one month. The only funds disbursed were £500,000 disbursed to AFD and of this, £499,565 was spent. FCDO’s contribution for PASAS was to fund research on the 5 countries in the Sahel. The contribution went to AFD, who contributed an equal amount, and therefore the products that PASAS produced were effectively shared 50:50 to enable the research to be carried out.

The PCR process was carried out by the LENS core team comprising of the SRO and PRO. Inputs were sought from the wider department, including from development councillors. The review also used input from AFD’s final narrative and financial report submitted in December 2024.

One issue that has become increasingly obvious over the course of the programme is that due to the change in context, there are other forms of research across the Sahel that better fit the FCDO’s requirements.

Date of last narrative financial report	31/12/2024	Date of last audited annual statement	26/4/2024 (AFD 2023 Annual Report, annual audited financial statement at Chapter 6 (p. 145)– 2024 due April 2025)