## Logical Framework
Please refer to the Guidance Notes tab for advice on completing the various fields in the logframe.
Please refer to the Results Framework Prof Guide for broader information on the logframe approach
PROJECT TITLE | South Sudan Humanitarian Assistance and Resilience Programme
IMPACT | Impact Indicator 1 |  | Baseline |  |  |  | Y4 Targets (FY 27/28) | Assumptions
Humanitarian Response in South Sudan saves lives, alleviates suffering, protects dignity, bolsters residence and reduces conflict. | IPC levels remain stable or reduce (from 4 & 5 to 3) | Planned | Sept 24- Nov 24 IPC5 - 41,000 IPC4 - 1,707,000 IPC3 - 4,564,000 |  |  |  | Stable or reduced numbers of people in IPC 4 & 5 (SSHARP Target Areas)
Achieved
Source: Integrated Phase Classification reports.
OUTCOME ONE | Outcome Indicator 1.1 |  | Baseline (Dec 2023) | Y1 Targets (FY 24/25) | Y2 Targets (FY 25/26) | Y3 Targets (FY 26/27) | Y4 Targets (FY 27/28) | Assumptions
Humanitarian needs including food security, nutrition and protection are met for the most vulnerable people & households | Percentage of households with poor to borderline food consumption | Planned | Host Communities = 58% (F=59%:M=58%) Refugees= 55% (F=57%:M=53%) | Hosts Com = 54% (F=55%:M=54%) Refugees= 49% (F=51%:M=47%) | Hosts Com = 50% (F=51%:M=49%) Refugees= 45%(F=48%:M=42%) | Hosts Com = 46% (F=48%:M=44%) Refugees= 41% (F=44%:M=38%) | Hosts Com = 44% (F=46%:M=42%) Refugees= 37% (F=40%:M=35%) | As a result of the war in Sudan which started in April 2023, the number of returnees and refugees entering South Sudan continues to increase, with needs of vulnerable people managed as effectively as possible with available funding and integrated into overall humanitarian response. The war in Sudan does not spill over directly into South Sudan or cause substantial economic impacts.
Achieved
Source: WFP Outcome Indicator 1.1.1
| Outcome Indicator 1.2 |  | Baseline (Dec 2023) | Y1 Targets (FY 24/25) | Y2 Targets (FY 25/26) | Y3 Targets (FY 26/27) | Y4 Targets (FY 27/28)
| Percent of children and women benefiting from quality integrated nutrition, WASH, and protection services | Planned | NA | 85% | 90% | 95% | 100%
Achieved
Source: UNICEF Outcome Indicator 1.2
OUTCOME TWO | Outcome Indicator 2.1 |  | Baseline (Dec 2023) | Y1 Targets (FY 24/25) | Y2 Targets (FY 25/26) | Y3 Targets (FY 26/27) | Y4 Targets (FY 27/28) | Assumptions
Resilience to conflict and climate shocks is strengthened in vulnerable communities. | % of targeted households applying emergency and crisis livelihood coping strategies | Planned | WFP - 43% | WFP - 41% | WFP - 39% | WFP - 37% | WFP 35% | 1) Climate shocks remain significant and, over time, are better understood to enable better preparedness by government, local authorities, and international community. 2) The international community continues to push the government to provide security and protection for citizens, and for greater investment in basic services whilst continuing to provide services in the interim.
Achieved
Source: Y1 WFP Outcome Indicator 3.4 - Livelihoods Coping Strategy Index. From Y2 will be average of THRIVE Impact Indicator 2 AND WFP Outcome Indicator 3.4. NOTE: THRIVE developing baseline and targets to be added in 2025.
| Outcome Indicator 2.2 |  | Baseline | Y1 Targets (FY 24/25) | Y2 Targets (FY 25/26) | Y3 Targets (FY 26/27) | Y4 Targets (FY 27/28)
| Number of people supported to better adapt to the effects of climate change as a result of International Climate Finance (ICF KPI 1) | Planned | 0 | TBC by April 2025 | TBC by April 2026 | TBC by April 2027 | TBC by April 2028
Achieved
Source: WFP and THRIVE (ICF4)
OUTCOME THREE | Outcome Indicator 3.1 |  | Baseline (Dec 2023) | Y1 Targets (FY 24/25) | Y2 Targets (FY 25/26) | Y3 Targets (FY 26/27) | Y4 Targets (FY 27/28) | Assumptions
Humanitarian response is more effective and efficient. | Number of examples of humanitarian actors prioritising their response, informed by the use of evidence, data and UK advocacy | Planned (annual) | 0 | 4 | 6 | 6 | 6 | A capable international humanitarian system continues to function, guided by strong leadership, and there is increasing coordination and collaboration between humanitarian, development, climate, and peacebuilding actors.
Achieved
Source: REACH Outcome Indicator 2, with narrative reporting from HLT advisors
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Y1 Targets (FY 24/25) | Y2 Targets (FY 25/26) | Y3 Targets (FY 26/27) | Y4 Targets (FY 27/28) | Assumptions
Rapid emergency responses to new shocks are agile and conflict- and gender sensitive. | # Number of households receiving multi-purpose cash assistance | Planned | 0 | 1960 | TBC if project extended | TBC if project extended | TBC if project extended | 1.3 assumes SSHF will attract similar levels of funding, UK contribution wall remain stable and the number of people assisted will remain comparable year on year.
Achieved
Source: ERRM Output Indicator 1.1
| Output Indicator 1.2 |  | Baseline | Y1 Targets (FY 24/25) | Y2 Targets (FY 25/26) | Y3 Targets (FY 26/27) | Y4 Targets (FY 27/28)
| # Number of households with improved access to water | Planned | 0 | 4000 | TBC if project extended | TBC if project extended | TBC if project extended
Achieved
Source: ERRM Output Indicator 1.2.4
IMPACT WEIGHTING (%) | Output Indicator 1.3 |  | Baseline (2023) | Y1 Targets (FY 24/25) | Y2 Targets (FY 25/26) | Y3 Targets (FY 26/27) | Y4 Targets (FY 27/28)
10% | # Number of people assisted through emergency response (proportion of UK funding) | Planned (annual) | 156000 | 156000 | 156000 | 156000 | 156000
Achieved
Source: SSHF Annual Report (results taken as a % of the total number of people assisted as a proportion of UK funding)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Y1 Targets (FY 24/25) | Y2 Targets (FY 25/26) | Y3 Targets (FY 26/27) | Y4 Targets (FY 27/28) | Assumptions
Inclusive and accountable provision of cash, food, nutrition and WASH for households and communities in areas of greatest need. | # Number of IDP’s affected by flood/conflict receiving cash assistance sufficient to meet basic needs (measured by receipt of cash to the value of a "Survival Minimum Expenditure Basket). | Planned (cumulative) | 6780 | 9180 | 11580 | 13980 | 16380 | Subnational conflict and intercommunal violence remain prevalent as slow implementation of the peace agreement continues, but areas of relative stability remain to enable effective humanitarian and resilience assistance. The international community continues to push the government to provide security and protection for citizens, and for greater investment in basic services whilst continuing to provide services in the interim. A capable international humanitarian system continues to function, guided by strong leadership, and there is increasing coordination and collaboration between humanitarian, development, climate, and peacebuilding actors. Sufficient trusted partners are available and can access populations most in need whilst managing risks appropriately. South Sudan remains a priority for the UK and the UK retains sufficient credibility to influence decision-making of wider actors in-country.
Achieved
Source: IOM Output Indicator 1.3.4
| Output Indicator 2.2 |  | Baseline (Dec 2023) | Y1 Targets (2024) | Y2 Targets (2025) | Y3 Targets (2026) | Y4 Targets (2027/28)
| #Number of people receiving food assistance unconditionally (disaggregated by sex) | Planned (annual) | 0 (F=0:M=0) | 125,778 (F=69,178 :M= 56,600 ) | 102,733 (F= 56,503:M= 33,595) | 107,333 (F= 59,033:M=38,155) | 130,778 (F=71,928:M= 61,600)
Achieved
Source: WFP Output Indicator 1.1.1
| Output Indicator 2.3 |  | Baseline | Y1 Targets (2024) | Y2 Targets (2025) | Y3 Targets (2026) | Y4 Targets (2027/28)
| Number of primary caregivers of children aged 0-23 months who received MIYCN counselling services | Planned (annual) | 423510 | 429862.65 | 451355.7825 | 464998.011 | 464998.011
Achieved
Source: UNICEF Output Indicator 1.1.2
Description: The Maternal, Infant and Young Child Feeding Nutrition (MIYCN) campaign aims to promote new norms around feeding practices among mothers and families, cultivate greater understanding about good nutrition-related behaviour and improve nutrition outcomes for children in the first 1000 days. UNICEF indicator 1.1.6 refers to a pilot the FCDO is supporting around the number of pregnant and lactating women (PLW) that receive cash transfer AND counselling. This is focused in Ruweng Administrative Area and will be a point of learning for SSHARP, building on previous FCDO funded activities.
IMPACT WEIGHTING (%) | Output Indicator 2.4 |  | Baseline | Y1 Targets (FY 24/25) | Y2 Targets (FY 25/26) | Y3 Targets (FY 26/27) | Y4 Targets (FY 27/28)
50% | # Number of displaced individuals having access to sufficient and safe water for domestic use in Malakal PoC and Bentiu IDP Sites A&B. | Planned (cumulative) | 0 | 40427 | 40427 | 80853 | 80853
Achieved
Source: IOM Output Indicator 1.1.1
Description: Access to 'sufficient' water refers to a minimum of 15 litres per person per day (15L/p/d). This will be measured by calculating the total volume of water provided and dividing it by the number of individuals directly benefiting from the supply.
Output 3 | Output Indicator 3.1 |  | Baseline | Y1 Targets (FY 24/25) | Y2 Targets (FY 25/26) | Y3 Targets (FY 26/27) | Y4 Targets (FY 27/28) | Assumptions
Effective GBV prevention and response initiatives and psychosocial support for women and girls, men and boys | # of women and youth participating in economic empowerment activities | Planned (cumulative) | 0 | 1020 | 39420 | 66840 | 82260 | The international community continues to push the government to provide security and protection for citizens, and for greater investment in basic services whilst continuing to provide services in the interim. A capable international humanitarian system continues to function, guided by strong leadership, and there is increasing coordination and collaboration between humanitarian, development, climate, and peacebuilding actors. Sufficient trusted partners are available and can access populations most in need whilst managing risks appropriately. South Sudan remains a priority for the UK and the UK retains sufficient credibility to influence decision-making of wider actors in-country.
Achieved
Source: Aggregate of GOAL Output Indicator 4.1 and IMC Output Indicator 5.1
IMPACT WEIGHTING (%) | Output Indicator 3.2 |  | Baseline | Y1 Targets (FY 24/25) | Y2 Targets (FY 25/26) | Y3 Targets (FY 26/27) | Y4 Targets (FY 27/28)
10% | # of individuals benefiting from GBV response services | Planned (cumulative) | 14414 | 17044.9 | 24216 | 29059.2 | 34871.04
Achieved
Source: Aggregate of IMC Output Indicator 2.1 and UNICEF 2.2.1 (Y1)
Description: Access to specialised GBV services that will include management of cases by appropriately-trained providers and ensuring providers can deliver psychosocial support. Management of cases can include more technical elements such as Clinical Management of Rape (CMR). SSHARP will also support Women and Girl Safe Spaces (WGSS), and case management services which include referrals, and provision of emergency cash as needed. Survivors will also be invited to participate in group psychosocial support activities.
Output 4 | Output Indicator 4.1 |  | Baseline | Y1 Targets (FY 24/25) | Y2 Targets (FY 25/26) | Y3 Targets (FY 26/27) | Y4 Targets (FY 27/28) | Assumptions
Livelihood interventions which strengthen coping capacity implemented with vulnerable communities. | # of value chain actors supported with training, inputs, equipment, or services by the programme | Planned (cumulative) | 0 | 50 | 9620 | 9820 | 9984 | Subnational conflict and intercommunal violence remain prevalent as slow implementation of the peace agreement continues, but areas of relative stability remain to enable effective humanitarian and resilience assistance. Climate shocks remain significant and, over time, are better understood to enable better preparedness by government, local authorities, and international community. A capable international humanitarian system continues to function, guided by strong leadership, and there is increasing coordination and collaboration between humanitarian, development, climate, and peacebuilding actors. Sufficient trusted partners are available and can access populations most in need whilst managing risks appropriately.
Achieved
Source: sum of GOAL Output Indicators 1.1, WFP 3.2.1; 3.2.2; 3.2.3 – potential to add extra outputs from GOAL if not double counted by RAF
Description: This indicator is an aggregate of the different kinds of support SSHARP is providing to market actors (smallholder farmers, producer groups, veterinary pharmacies, aggregation centres, financial service providers) through WFP and THRIVE. It demonstrates support for community/market-level coping capacity as described in the output, as market actors have improved capacity to be self-sufficient, increase productivity and output, and respond to changing conditions.
IMPACT WEIGHTING (%) | Output Indicator 4.2 |  | Baseline | Y1 Targets (FY 24/25) | Y2 Targets (FY 25/26) | Y3 Targets (FY 26/27) | Y4 Targets (FY 27/28)
20% | % of Community Action Groups that have implemented at least 70% of their Community Action Plan activities (for risk management and preparedness) | Planned | 0 | 40%(19 out of 48) | 55%(26 out of 48) | 70%(34 out of 48) | 85%(41 out of 48)
Achieved
Source: GOAL Output Indicator 2.2
Description: This indicator shows the output of support to community action groups - i.e. the actions the groups take as a result of support to form and plan for risk management
Output 5 | Output Indicator 5.1 |  | Baseline | Y1 Targets (FY 24/25) | Y2 Targets (FY 25/26) | Y3 Targets (FY 26/27) | Y4 Targets (FY 27/28) | Assumptions
Humanitarian actors better demonstrate approaches that are inclusive, accountable to affected populations, and value for money. | Number of analytical products produces to support humanitarian strategic planning, and annual prioritisation | Planned (cumulative) | 0 | 12 | 32 | 50 | 69
Achieved
Source: Impact Initiatives Output 2 (aggregated across outputs 2.2 - 2.7)
IMPACT WEIGHTING (%) | Output Indicator 5.2 |  | Baseline | Y1 Targets (FY 24/25) | Y2 Targets (FY 25/26) | Y3 Targets (FY 26/27) | Y4 Targets (FY 27/28)
10% | Number of assets built, restored, or maintained as a % of planned. (% of km roads and dkyes) | Planned | 0 | 80% | 90% | 90% | 100%
Achieved
Source: WFP Output Indicator 3.3.1
Description: The indicator measures the type and number of physical resources built, restored, or maintained for households and communities to improve their livelihoods and/or their natural resource base. This includes Km of roads upgraded (disaggregated by medium term and all weather) and KM of dykes constructed or renovated).

## Logframe Change frame
Use this change log to record all changes to the logframe over the life of the project.
ID | LOGFRAME SECTION | DETAILS OF CHANGE | AUTHOR | DATE
E.g. | Output 1, Indictor 2 | Indicator amended from 'No of children enrolled in primary schools' to 'Number of children enrolled in UNICEF supported primary schools (disagregated by sex) | Joe Bloggs | 2022-01-01
1
2
3
4
5
6
7
8
9
10

## VfM Framework (2)
PROJECT TITLE
1. Economy | Indicator 1.1 |  | Baseline | Y1 Targets (2024/25) | Y2 Targets (2025/26) | Y3 Targets (2026/27) | Y4 Targets (2027/28) | Comments
buying inputs of the appropriate quality at the right price. | Difference in exchange rate used to convert USD to SSP between UN rate and the market rate | Planned | 0 |  |  |  |  | Useful to measure over time but economy indicators will not be a focus of the VfM framework. ACTION: Include cost driver indicator.
Achieved
2. Efficiency | Indicator 2.1 |  | Baseline | Y1 Targets (2024/25) | Y2 Targets (2025/26) | Y3 Targets (2026/27) | Y4 Targets (2027/28) | Comments
how well partners convert inputs into outputs | Average cost transfer ratio (non-transfer costs/value of cash transferred) | Planned
Achieved
WFP, UNICEF, IOM, ERRM, IMC
| Indicator 2.2 |  | Baseline (Dec 2023) | Y1 Targets (2024/25) | Y2 Targets (2025/26) | Y3 Targets (2026/27) | Y4 Targets (2027/28)
| Percentage of people reached, within the timeframe agreed | Planned | 0
Achieved
ERRM Logframe
| Indicator 2.3 |  | Baseline (global average?) | Y1 Targets (2024/25) | Y2 Targets (2025/26) | Y3 Targets (2026/27) | Y4 Targets (2027/28)
| SSHARP coordination response | Planned | 0 |  |  |  |  | SSHARP Coordination response will likely be an internal indicator - Claire suggested survey scores after SSHARP/EEAL led lesson learned sessions. FURTHER DISCUSSION NEEDED
Achieved
| Indicator 2.4 |  | Baseline | Y1 Targets (2024/25) | Y2 Targets (2025/26) | Y3 Targets (2026/27) | Y4 Targets (2027/28)
| Percentage of supplies prepositioned before XX | Planned | 0
Achieved
WFP
3. Effectiveness | Indicator 3.1 |  | Baseline | Y1 Targets (2024/25) | Y2 Targets (2025/26) | Y3 Targets (2026/27) | Y4 Targets (2027/28) | Comments
how well are the outputs of an intervention having the intended effect. | Average percentage of outcome targets met across partners (disaggregated by output - prioritise, prevent, protect and evidence) | [6 empty] | Indicator 3.1 will be calculated internally, with PM's taking the average for their outcome indicators.
All partner logframes
4. Equity | Indicator 4.1 |  | Baseline | Y1 Targets (2024/25) | Y2 Targets (2025/26) | Y3 Targets (2026/27) | Y4 Targets (2027/28) | Comments
how fairly are the benefits distributed, in particular amongst marginalised groups. | Percentage of SSHARP indicators that are disaggregated by sex, age and disability | Planned | 0 |  |  |  |  | Indicator 4.1 would require teams to select inidcators that CAN be disaggregated. Equity is a big part of SSHARP, therefore more indicators, covers targeting, compliance with disaggregated data and AAP.
Achieved
Partners Logframes
| Indicator 4.2 |  | Baseline | Y1 Targets (2024/25) | Y2 Targets (2025/26) | Y3 Targets (2026/27) | Y4 Targets (2027/28)
| Percentage of SSHARP target counties that are listed as priority 1-3 in latest HNRP | Planned | 0
Achieved
Latest HNRP prioirity lists/ counties
| Indicator 4.3 |  | Baseline | Y1 Targets (2024/25) | Y2 Targets (2025/26) | Y3 Targets (2026/27) | Y4 Targets (2027/28)
| Percentage of partners (including downstream partners) with a functioning community feedback mechanism | Planned | 0
Achieved
Source: Partner progress reports and VfM?
| Indicator 4.4 |  | Baseline | Y1 Targets (2024/25) | Y2 Targets (2025/26) | Y3 Targets (2026/27) | Y4 Targets (2027/28)
| Average satisfaction survey scores disaggregated through community feedback | Planned
Achieved
|  | Source | Community Feedback monitoring
5. Cost Effectivess | Indicator 5.1 |  | Baseline | Y1 Targets (2024/25) | Y2 Targets (2025/26) | Y3 Targets (2026/27) | Y4 Targets (2027/28) | Comments
how well are the outputs of an intervention having the intended effect | Ratio of SSHARP budget spent on long-term, sustainable response activities vs reactive response activities | Planned | [5 empty] | Indicator 5.1 to be worked on, but should capture the value added for balancing humanitarian assistance and resilience building.Indicator 5.2 is capturing ICF spend and 5.3 IRF, how are we spending it?
Achieved
Source: Partner budgets and progress reports
| Indicator 5.2 |  | Baseline | Y1 Targets (2024/25) | Y2 Targets (2025/26) | Y3 Targets (2026/27) | Y4 Targets (2027/28)
| Average cost per beneficary for International Climate Finance KPI 1 (number of peoploe supported to adapt to the impacts of climate change) | Planned
Achieved
Source: ICF partners VfM
| Indicator 5.3 |  | Baseline | Y1 Targets (2024/25) | Y2 Targets (2025/26) | Y3 Targets (2026/27) | Y4 Targets (2027/28)
| Additional number of people reached with funding from the Internal Risk Facility (disaggregated?) | Planned
Achieved
Source: Partner's recieving IRF funding logframes/ change frames
Note on I22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: On qu re ‘global baseline’. This issue came up on the final HARISS report for ERRM where they said their “TCTR” - total cost to transfer ratio - was 57:43. Since we accepted ECHO’s final report, I looked at the ECHO guidance for what ‘acceptable’ TCTR was. This is the quote: TCTR targets will vary according to scale and context but will be expected to reach a minimum standard of 85:15 for large-scale programmes (currently defined as EUR 10 million or above). See the large-scale cash guidance note for more detail. When cash programmes are less than EUR 10 million, rather than seeking globally applicable benchmarks, DG ECHO uses TCTR to assess the reasonableness of the cost of delivery in a specific context. In such settings, DG ECHO country offices and partners should define appropriate TCTR efficiency rates adapted to the context and the programme.” LINK: Cash Transfers

## Guidance Notes
Logframe Template Guide
Teams should use the guide below to complete the logframe template.
PROJECT TITLE
The name of the programme to which this logframe applies, from the business case
IMPACT
Long term goal to which the project will contribute towards achieving. When drafting the impact statement, consider how your project fits with other efforts from FCDO and partners to achieve the impact, ie is your project nested within a broader undertaking? This will often be the Impact indicator from the Theory of Change in the Business Case.
OUTCOME
The outcome should link through to the outcome level in the programme Theory of Change as stated in the Business Case. The outcome of your project identifies what will change, who will benefit and how it will contribute to reducing poverty, including contributions to the Sustainable Development Goals (SDGs) or Climate Change.
Ongoing monitoring of progress against outcome milestones takes place as an assessment of whether you expect to achieve the Outcome by the end of the programme in the programme Annual Reviews. An assessment of whether your project achieved the Outcome will be included in the Project Completion Review (PCR) based on the target milestone for the programme completion.
OUTPUTS
Outputs are the specific, direct deliverables of your project. These will provide the conditions necessary to achieve the Outcome. The logic of the chain from Output to Outcome therefore needs to be clear. Outputs should reflect the Theory of Change as set out in the Business Case for the programme.
Progress towards the outputs will be assessed and scored at the Annual Review, using output indicators and milestones. Achievement of the outputs will be assessed at project completion, using output indicators and targets.
IMPACT WEIGHTING
Once you have defined your Outputs, assign a percentage for the contribution each is likely to make towards the achievement of the overall Outcome.
The impact weights of all the Outputs will total 100% and each are rounded to the nearest 5%.
Impact weightings for Outputs are intended to:
1. Promote a more considered approach to the choice of Outputs at project design stage; and
2. Provide a clearer link to how Output performance relates to project Outcome performance.
INPUTS
Clarification of inputs is a key part of results-chain thinking. Inputs are specified at the country-level in country operational plans and the project information contained in logframes should feed up into these.
The input-level boxes show the amount of money provided by FCDO and any partners (£) including, where relevant, the government’s own contribution. This only relates to monetary (not in kind) contributions. At Outcome level this is equal to the sum of Inputs for all Outputs. The FCDO share at Outcome Level is a simple, pro rata calculation of FCDO’s contribution in monetary terms for all outputs.
Information should also be provided for the total number of Annual FCDO Full-Time Equivalents (FTEs) allocated to this project, based on the time individual staff members will spend on the project. It is understood that this may change through the project cycle, and is intended as a management tool.
INDICATORS
Indicators are performance measures, which tell us what will be measured not what is to be achieved. Avoid including elements of the baseline or target.
What makes a good indicator?
Specific – what will be measured? And how?
Measurable - data can be collected
Relevant - to the results chain
Useful – for management decision making
Does not include any element of the target
Can be disaggregated if relevant (especially when the indicator relates to number of beneficiaries reached with an intervention)
A mix of qualitative and quantitative
Already defined - if relevant include indicators which towards the FCDO Outcome Delivery Plan / ICF KPIs / SDGs.
Consider using standard indicators / best practice indicators / learning from other projects
The basic principle is that “if you can measure it, you can manage it”.
Top Tip – select indicators based on relevance to the Theory of Change and the availability of data.
Best Practice suggests a maximum of three Indicators per Output.
Some example indicators for a WASH project are shown below.
BASELINE
Baselines set the starting point and provide a measure of the situation before your project starts (could be zero if a new project).
The baseline is used to measure change and monitor progress.
Include a baseline for each of your indicators. The first 6 months of a project may exceptionally be used for assembling baseline data at output level if agreed by your PRO.
Use existing data where possible, but check reliability and seek assurances regarding the data quality eg use data from national statistical systems / Management Information Systems.
If you need to collect your own data - collect baseline data early – as soon as beneficiaries have been identified but before any results are expected.
MILESTONES
Milestones are the desired trajectory from baseline to target, helping you to track progress and make changes to underperforming areas.
Will depend on sequencing of activities and data availability.
Include REALISTIC milestones given resources and capacity.
At the output level include annual milestones for each year of the project (or monthly if short term). At outcome & impact level data may not be available annually and you should record the expected frequency of data availability.
TARGET (DATE)
Targets set the desired point, showing what is achievable within the timeframe available.
The target is often the last year of the project (or month if its short term).
Include realistic targets given resources and capacity, the baseline situation, funding available and country/operational context. Project targets might be informed by evidence about what has worked in the past and take into account lessons learned from other projects.
Include targets dissaggregated by sex/geography/income etc where appropriate.
Consider using government targets although if they are too ambitious then make a more realistic estimate.
Top Tip - A good Theory of Change will help you think about what is realistic and achievable as it will enable critical reflection of context, external influences & assumptions.
SOURCE
Each Indicator will have a data source to verify the results achieved.
List the specific data sources i.e. give the specific data collection e.g. named survey / report and avoid just naming the organisation.
State the frequency of the data source and ensure consistency with milestones and targets.
Check the source can provide disaggregated data as required.
Consider and specify the data collection and reporting responsibilities to ensure the results planned and forecast rows in the logframe are updated on a regular basis.
Top Tip - Before using a data source, assess its quality and seek assurances from data providers where needed ie consider its validity, reliability and availability. Use the Data Quality Prof Guide to help you consider the quality of your data.
ASSUMPTIONS
Define any assumptions which are linked to the realisation of your project's individual outputs, as well as those which are critical to the realisation of the outcome and impact: these will not all be the same. If you are carrying out any evidence gathering to check your assumptions then make reference to this as part of this section.
VALUE FOR MONEY
Ensure the outputs and outcome projected represent good value for the invested resources, at the beginning of the project, and through its life.
Consider including VfM metrics in the logframe (or other documents such as the Delivery Plan) to allow VfM to be measured through the life of the project and to provide assurance at Annual Review.
VfM is achieved at different stages of the results chain. Thus for each result we seek to achieve we should aim to have metrics for each of the following:
Economy - Are we (or our agents) buying inputs of the appropriate quality at the right price?
Efficiency - How well are we (or our agents) converting inputs into outputs? (‘Spending well’)
Effectiveness - How well are the outputs produced by an intervention having the intended effect? (‘Spending wisely’)
Cost-effectiveness - What is the intervention’s ultimate impact on poverty reduction, relative to the inputs that we or our agents invest in it?
Equity - Is the intervention meeting the needs of all beneficiaries?
FCDO’s Approach to Value for Money (PrOF Guide) provides further advice on ensuring VfM.