Annual Review
Title: International Development Association 20th Replenishment (IDA20)
Programme Value £m (full life): £1,414m		Review date: July 2023-June 2024 (FY24)
Programme Code: 300958	AMP start date: 01/07/2022	AMP end date: 30/06/2025

Summary of Programme Performance
Year	FY23	FY24	FY25
Overall Output Score	Not Assessed	A (Outputs met expectations)
Risk Rating	N/A	Moderate

DevTracker Link to Business Case:	International Development Association 20th Replenishment (IDA 20)
DevTracker Link to results framework:

A. SUMMARY AND OVERVIEW
Programme Description
The International Development Association (IDA) is the arm of the World Bank Group which provides financing to low-income and vulnerable countries. IDA supports the world’s 78 poorest countries and is the single largest source of donor funds for basic social services in these countries. IDA aims to reduce poverty by providing grants, zero or low-interest loans, and policy advice for programs that boost economic growth, build resilience, and improve the lives of the poorest and most vulnerable around the world. IDA’s support to developing countries helps address some of the most pressing global challenges, including famines, climate change, refugee crises and irregular migration, and conflict.
IDA is currently in its twentieth replenishment cycle (IDA20, FY23-FY25). The replenishment consists of contributions from IDA partners, contributions from the World Bank Group’s net income, and financing raised from the capital markets. IDA partners and representatives from borrower countries come together every three years to replenish IDA funds and review IDA’s policies. Due to pressures from the COVID-19 crisis, the IDA 20 cycle began a year earlier than planned on 1 July 2022, after IDA’s historic decision to compress the IDA19 cycle into two years to support IDA countries’ response to the pandemic.
IDA20’s overall replenishment total was $93 billion – $48bn of which will be disbursed as grants. At least 35% of IDA20 financing will support efforts to tackle climate change and up to 20% in expected in financing for supporting fragile countries - two policy priorities the UK pressed for. IDA20 maintained the five special themes from IDA19: Climate Change; Fragility, Conflict and Violence; Gender; Human Capital; and Jobs and Economic Transformation. However, IDA20 also aimed to deepen recovery efforts by focusing on four cross-cutting issues: crisis preparedness; debt sustainability and transparency; governance and institutions; and technology. In the financial year ending 30 June 2024, IDA commitments totalled $36 billion, of which $12.1 billion was grant funding.
The UK played a central role in the negotiation of the overall IDA20 financing and policy package, championing financial innovations, ambitious policy commitments, and a strong results framework. The size of the UK pledge reflects the value for money that UK contributions to IDA represent through its alignment with UK objectives, its operational effectiveness, and the efficiency and scale of its leveraged financing model.
The UK contributed £1,414m (5.7% of the total IDA20 partner contributions). This was a reduction of 54% compared to IDA19 due to a reduced overall ODA budget and the increasing costs supporting refugees in the UK. The UK remained a leading donor to IDA and was the third largest donor to IDA20, after the US and Japan.
In IDA20, the UK pressed for, and is closely monitoring the following commitments:
- Economic development. Around $3bn of investment in high-risk environments to create markets and mobilise private finance.
- Jobs and Investment. Support for country platforms in the poorest and most fragile countries targeted on supporting trade, inclusion, and climate friendly investments.
- Women’s economic empowerment. Support for at least 15 countries to increase childcare access and 10 countries to integrate gender into their fiscal policies.
- Girls’ education. Commitment to close learning gaps and improve learning outcomes in 20 IDA countries, monitoring the impact on learning for girls, contributing to UK-led G7 global targets on girls’ education.
- Climate change. At least 35% of IDA20 financing will tackle climate change with all operations aligned with the Paris Agreement by 2023.
- COVID-19 vaccines. Support for all IDA countries with vaccine roll-out, testing, and treatments (IDA has made around $10bn available to date) and to strengthen inclusive health systems.
- Stability. An increase of up to 20% in expected financing for supporting fragile countries.
- Crisis preparedness. Strengthened support for crisis preparedness, including enhanced availability and incentives for the use of contingent financing.
- Science, research and technology. Support for countries to develop digital infrastructure and further operations in digital development, financial inclusion and agriculture aimed at increasing women’s access to and use of digital technology.
This annual review is based on a sub-set of the agreed commitments and indicators tracked in IDA20.
Summary of Progress
IDA20 began in in a challenging global context marked by deepening crises. The aftermath of the COVID-19 crisis had significant health, social and economic impacts on IDA countries, further setting back their development and compounding existing inequalities. Additionally, countries were faced with increasing debt vulnerabilities, inflation, and a slowdown in the global economy. Given this backdrop, progress over the past year has been impressive.
In the first two years of IDA20 implementation, IDA commitments reached $66 billion – over 70% of IDA20 envelope. This has supported 77 countries with a population of 2 billion people, with the most vulnerable receiving 40% of the financial support.
IDA20 has scored an A in FY24 against the output indicators. Indicators are predominantly meeting FY24 milestone targets – meeting nearly 80% of the targets set – and demonstrating significant progress from the baseline (IDA19 FY22). IDA20 also continues to deliver across all the five special themes and is on track to meet or exceed cycle targets for almost all policy commitments tracked in the annual review. Notable results include:
- People provided with improved urban living conditions: 16.5m people, meeting the end of replenishment (FY25) expected value early.
- People provided with access to improved water sources: 12 million people have improved access, which is at the lower end of the end of the expected range for the entire cycle.
- Supporting IDA countries in Fragile and Conflict-affected Situations to establish and/or strengthen core government functions: 33% of countries were supported, 7ppt above the FY24 milestone.
- Countries supported to expand access to quality, affordable childcare: 16 countries supported, exceeding the end of replenishment target a year early.
- Climate co-benefits as a share of total commitments in IDA-supported operations: 43%, meeting the end of replenishment expected value a year early.
IDA has also responded well to calls from shareholders to assess how it could stretch its existing equity further. The World Bank undertook a review of the IDA capital adequacy framework (CAF) and revised several key assumptions, including right-sizing buffers and adjusting down the capital held for operations through its private sector window. Combined with other measures such as issuing more fixed rate debt and seeking donor contributions to the Crisis Response Window+, IDA was able to mitigate the effects of a significant appreciation of the USD against SDR. Without the implementation of these measures IDA’s financing capacity would have fallen by $8bn in 2024/25. The flexibility offered by IDA’s Hybrid Financial Model, allowing it to scale up financing in response to severe and large-scale global crisis, has also contributed to its effectiveness. Moreover, the average number of satisfactory outcomes for IDA operations was 91% far exceeding the target set for FY24 of 80%.
[note] The SDR is an international reserve asset. The SDR is not a currency, but its value is based on a basket of five currencies—the US dollar, the euro, the Chinese renminbi, the Japanese yen, and the British pound sterling. Most of IDA’s loans are denominated in USD or EUR but its accounting currency is SDR. The appreciation in USD vs SDR meant that for a given amount of equity in SDR it could provide less USD financing.
Recommendations for FY25
Number	Recommendation
Output 1 – IDA support delivers strong and inclusive development results in partner countries
1.1	FCDO/UKDel to work with management to ensure a holistic approach to crisis preparedness and to better understand how the Bank’s new crisis toolkit is being deployed at the point of crisis.
1.2	FCDO/UKDel to work with management to consider how to expand the use of crisis preparedness diagnostics piloted under IDA20 to more IDA countries.
Output 2 – IDA enhances support to, and improves performance in, fragile and conflict-affected states
2.1	The UK should continue to encourage management to improve the Bank’s approach to staffing in FCV countries, including as part of the IDA21 replenishment.
2.2	UKDEL/FCDO should continue to engage with Management on the Bank’s successor FCV strategy in FY25 to ensure better targeting of FCV drivers through Bank operations, a greater focus on prevention, a more strategic approach to partnerships, and third-party implementation
Output 3 – IDA projects mainstream gender and disability to enhance equality in IDA countries
3.1	FCDO/UKDel to work with management to further disaggregate data to include disabilities, age and urban/rural.
3.2	FCDO/UKDel to encourage Management to scale up their ambition on ambition in Sexual and Reproductive Health Rights and ensure it is integrated into most IDA health and gender programmes, given the absence of quantitative commitments in the WBG Gender Strategy
3.3	FCDO/UKDel to ensure IDA21 replenishment targets remaining gaps in areas such as access to reproductive and adolescent health, economic opportunity, and prevention and response to GBV; and that policy commitments align with the new WBG Gender Strategy
Output 4 – IDA supports evidence-based policy making, job creation, and economic development
4.1	As a key priority for the FCDO, UK and WBG teams should continue to share learnings on approaches to measure the impacts of IDA operations on jobs and economic transformation outcomes.
4.2	Going forward FCDO/UKDel to work with management to push for a strong focus on sectors with high potential for job rich structural transformation, strengthening exports, and integrating into global value chains.
4.3	FCDO/UKDel to work with management to ensure strong focus on encouraging private investment and improving institutional capacity in IDA countries, including through the IDA21 Private Sector Window alongside a scale up in FCV/LICs from IFC’s own account.
Output 5 – IDA supports climate adaptation and resilience and crisis preparedness and response in IDA countries.
5.1	FCDO/UKDel should closely monitor indicator 5.5 (share of adaptation co-benefits over total climate co-benefits) and ensure it does not deteriorate any further in IDA20.
5.2	FCDO/UKDel should work with Management to ensure the World Bank continues to explore options for partnerships with other MDBs to maximise support for implementing and updating NDCs and LTSs.
5.3	For IDA21, FCDO/UKDel to work with management to push for a 45% target for the share of climate co-benefits in IDA-supported operations
Output 6 – IDA is efficient, financially sustainable and effective
6.1	Considering all indicators have outperformed their targets, FCDO/UKDel to work with Management to consider options for setting higher ambition targets where appropriate.
6.2	FCDO to consider tracking indicators for IDA21 for FCV regions to ensure operational and organisational effectiveness even in challenging IDA contexts.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES
The original theory of change included in the business case is set out below. IDA is expected to deliver continued concessional financing for IDA countries, deliver policy commitments (including the Bank’s five Special Themes (Climate Change and the environment; Fragility, Conflict and Violence; Gender and Development; Crisis Response; and Jobs and Economic Transformation) and increase organisational and operational effectiveness in order to progress towards longer-term development goals in IDA Countries. Ultimately, IDA contributes to the WBG’s mission to end extreme poverty and boost shared prosperity on a liveable planet.

While these long-term development outcomes are not directly attributable to IDA (they are the collective efforts of countries and their development partners), IDA is the largest development actor in low-income countries globally and therefore its efforts will have a significant impact on whether countries make progress. These twin goals are aligned with the Sustainable Development Goals (SDGs) and IDA is working with client countries to deliver on the 2030 agenda – supporting country-led and country-owned policies to attain the SDGs.
The outcome and impact indicators remain the same as in the initial business case, and the TOR logic and steps to achieving outcome and impact are still valid. There is no material change to the programme design.

## C. DETAILED OUTPUT SCORING

Output Title	IDA support delivers strong and inclusive development results in partner countries
Output number:		1	Output Score:	A - Output met expectations
Impact weighting (%):		25	Weighting revised since last AR?	Increased from 10%, because of combining 2 previous outputs

Indicator(s)	2024 Milestone	Progress
1.1 People provided with improved urban living conditions (millions) [cumulative]	The milestone for FY24 is 10-13 / The expected range for FY25 is 15-20	Output has substantially exceeded expectation, meeting the FY25 expected range / 16.5m people have been provided with improved urban living conditions in FY24
1.2 Children immunised (millions) [cumulative]	The milestone for FY24 is 70-133 / The expected range for FY25 is 105-200	Output is substantially below expectation. / 40.7 million children were immunised in FY24
1.3 People provided with access to improved sanitation services (millions) [cumulative]	The milestone for FY24 is 8-12 / The expected range for FY25 is 12-18	Output has met expectation, on track to meet the FY25 expected range / 17.1 million people were provided with access to improved sanitation services in FY24
1.4 Women and children who have received basic nutrition services (millions) [cumulative]	The milestone for FY24 is 93-100 / The expected range for FY25 is 140-150	Output is moderately below expectation / 80.8 million women and children have received basic nutrition services in FY24
1.5 Number of large-scale assessments completed at primary or secondary level [number of assessments]	The milestone for FY24 is 17-23 / The expected range for FY25 is 25-35	Output has substantially exceeded expectation, meeting the FY25 expected range. / 28 large scale assessments have been completed at primary or secondary level
1.6 People provided with new or improved electricity service (millions) [cumulative]	The milestone for FY24 is 23-33 / The expected range for FY25 is 35-50	Output has met expectation, on track to meet the FY25 expected range / 31.3 million people were provided with new or improved electricity services in FY24
1.7 People provided with access to improved water sources (millions) [cumulative]	The milestone for FY24 is 8-14 / The expected range for FY25 is 13-20	Output has met expectation, on track to meet the FY25 expected range / 12.0 million people were provided with access to improved water sources in FY24
1.8 To prevent zoonotic diseases and ensure pandemic preparedness, support at least 20 IDA countries with One Health approaches which address the nexus between human, animal, and ecosystem health.	The milestone for FY24 is 13 / The target for FY25 is 20	Output is moderately above expectation, on track to meet FY25 target / 16 countries were supported with One Health Approaches in FY24
1.9 People who have received essential health, nutrition and population services (million)	The milestone for FY24 is 190-287 / The expected range for FY25 is 285-430	Output is moderately below expectation / 143.6 million people received essential health, nutrition and population services in FY24.
1.10 Expanding adaptive social protection and building resilience to shocks: To ensure inclusive and effective response against shocks and crises, support at least 20 IDA countries’ resilience by building adaptive social protection systems, including the use of digital technologies.	The milestone for FY24 is 13 / The expected range for FY25 is 20	Output has substantially exceeded expectation, has met the FY25 expected range. / 27 countries have been supported to build adaptive social protection systems in FY24
1.11 Number of countries supported toward institutionalizing disaster risk reduction as a national priority with IDA support	The milestone for FY24 is 36-47 / The FY25 target is 55-70	Output has moderately exceeded expectation, on track to meet FY25 target. / 52 countries have been supported toward institutionalizing disaster risk reduction as a national priority in FY24.
[note] Indicators 1.1-1.7 and 1.9 reflect cumulative results from FY23 up to the given year

Overall, IDA has delivered strong development results in the year under review. Several results achieved in key indicators during the first two years of IDA20 (FY23-24) have exceeded the total achieved during the previous two years (FY21-FY22). These include access to improved sanitation (1.3) (IDA19: 10.2 million; IDA20: 17.1 million);; new or improved access to electricity (1.6) (IDA19: 24.4 million; IDA20: 31.3). Of the eleven expected ranges given within these categories, eight have met or exceeded expectations. Although both nutrition ranges (1.4,1.9) are moderately below expectation, they are expected to meet the 2025 target.
IDA20 also introduced Crisis Preparedness as a Cross-cutting Issue to accelerate countries’ preparation for crises. A series of Crisis Preparedness diagnostics were established to monitor this – a subset of which are included in output 1 (1.8, 1.10, 1.11). All the indicators in this category have performed well and have either already met the FY25 target or are on track to meet it early.
However, the immunisation of children (1.2) is currently substantially off track with 40.7 million children immunised relative to a FY23-24 milestone of 70-133 and compared to 76.1 million immunisations in FY21-22. This was affected by the evolving country demand that shifted the IDA’s portfolio away from delivery of specific services/interventions (e.g. immunisation) to system-wide support to strengthen institutional capacity and delivery systems.
IDA’s Results Measurement System (RMS) have not set yearly milestones, but FCDO has set them for indicators to track progress for FY24. The logframe originally included a policy commitment on delivering COVID-19 vaccines. However, as IDA20 began 52 IDA countries had already received vaccines or pandemic preparedness interventions meaning that very few additional IDA countries were seeking support with IDA20 funds. Therefore, the IDA20 mid-term review recommended that this should instead focus on preparedness for health emergencies given declining demand for vaccines. Accordingly, the COVID-19 policy commitment has been removed from the IDA20 logframe.
[note] The IDA Results Measurement System (RMS) tracks and measures how IDA inputs and activities help countries deliver tangible results. The RMS includes indicators which track: long-term development outcomes and the broader context of countries in which IDA operates; development results in countries supported by IDA operations; and, the operational and organizational effectiveness of IDA.
As noted above, relative to IDA19, three additional indicators were included to monitor progress on IDA20’s cross-cutting issue on crisis preparedness (indicators 1.8, 1.10, 1.11). There are no planned changes as a result of this review.
Lessons Learned
While the COVID-19 pandemic is now largely over, the negative impacts in many developing countries on areas such as health, nutrition, education, social protection were still being acutely felt at the start of IDA20. Given this context, IDA20 has performed well and provided a solid foundation for a strong and sustained recovery.
As noted in the IDA19 PCR, the COVID-19 pandemic exposed the need for extensive preparedness and resilience building measures. Cross-cutting attention to crisis preparedness in IDA20, however, has helped improve coordination among a wide range of stakeholders on what is a complex agenda. Many governments struggle to prioritise ex-ante investments in crisis preparedness and instead rely on ex-post responses once crises strike, often through donor funds. Even when preparedness plans and policies are put in place, financial and technical capacity constraints can slow operationalisation, and therefore effectiveness.
2024 Recommendations
1. FCDO/UKDel to work with management to ensure a holistic approach to crisis preparedness and to better understand how the Bank’s new crisis toolkit is being deployed at the point of crisis.
2. FCDO/UKDel to work with management to consider how to expand the use of crisis preparedness diagnostics piloted under IDA20 to more IDA countries.

Output Title	IDA enhances support to, and improves performance in, fragile and conflict-affected states
Output number:		2	Output Score:	A+ Outputs moderately exceeded expectation
Impact weighting (%):		15	Weighting revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
2.1 Core IDA financing approved by the Board for FCS/FCV countries ($ billion) [cumulative]	The milestone for FY24 is 20.6 / Target for FY25 is 30.9	Output has moderately exceeded expectations, on track to reach FY25 target / $12.2 billion core IDA financing was approved by the Board for FCS/FCV countries in FY23 and $11.8 billion IDA financing was approved by the Board for FCV countries in FY24
2.2 Number of IDA FCS supported in building capacity to use field appropriate digital open-source tools for collection and analysis of geotagged data, and apply this technology to enhance project implementation and coordination (number of countries)	The milestone for FY24 is 17 / The expected value for FY25 is 18	Output has met expectations, on track to reach FY25 expected value / 17 countries were supported in building capacity to enhance project implementation and coordination in FY24
2.3 Supporting IDA countries in Fragile and Conflict-affected Situations (with active portfolios) to establish and/or strengthen core government functions that facilitate effective, inclusive, and responsive public services, enhance transparency and accountability, and promote resilience and trust, including by partnering with key national and international stakeholders (% of countries)	The milestone for FY24 is 26% / The target for FY25 is 40%	Output has substantially exceeded expectations, on track to reach FY25 target / 33% of countries of IDA countries in FCS were supported in FY24
2.4 Facetime index in Fragile and Conflict-affected Situations (Index/number of days)	No milestone or target set but index/days should be expected to be increasing	Output has met expectations. / Face time in number of days in FY24 was 182,758 compared to 155,953 in FY22
[note] Staff presence on the ground in IDA-eligible FCS per year, measured as mission days in-country, resident staff days (assumed number of days per year x staff number) and local consultant days worked.

IDA is one of the largest development actors in Fragility Conflict and Violence (FCV) affected countries, with these results represent a subset of IDA’s work in FCV situations. Amid increasing instability and fragility in countries worldwide, IDA achieved strong development outcomes in FCV countries. Face time index in FY24, measured by number of days staff were present on the ground in FCS per year, has increased by 17% since FY22 (2.4). IDA has already supported 17 countries (out of the 18 originally planned by FY25) in building the capacity to use field-appropriate, digital, open-source tools for collection and analysis of geotagged data, and to apply this technology to enhance project implementation and coordination (2.2). These technologies systematically enhance monitoring and evaluation and project supervision in FCV settings, enabling IDA to see what is happening on the ground, in locations where it is not always possible to have a physical presence.
Across the indicators in FY24 there is strong performance, with all indicators measured meeting or exceeding expectations.
These indicators do not include yearly milestones, but FCDO has set them for some indicators. There are no planned changes because of this review.
Lessons Learned
Overall management has made good progress on a challenging agenda, especially on the sustained effort to remain engaged in conflict and crisis.
The increase in conflict-related violence, successive political upheavals and deteriorating security, highlights the importance of flexible approaches to adapt to volatility as well as supporting efforts to address to address FCV drivers and risks earlier. This includes developing conflict expertise and sustained effort to remain engaged in conflict through expanded presence on the ground to ensure programming adapts to the context and remains relevant.
WBG interventions are most effective in FCV settings when they are developed and implemented in the context of broader political, security, and humanitarian elements. In this regard, working with the UN and other international players is key. There is a need to codify Bank cooperation with the UN system, maximising alignment to promote peace-positive choices.
Private sector engagement is critical for building resilience and supporting transitions out of FCV. However, as noted in the FCV Strategy Mid-term Review, challenging investment conditions in FCV settings/countries limit the Bank’s capacity to support private investment, highlighting the need for a more integrated WB approach to align IBRD/IDA, IFC, and MIGA interventions to further support private sector development and the mobilization of private capital. The 2018 IFC Capital Increase set an ambitious target for IDA and FCS. The 2023 validation report by the Independent Evaluation Group (IEG) found that the IFC had made limited progress increasing the proportion of its investments in IDA countries and in countries classified as having fragile and conflict-affected situations (FCS). The IFC is laying the groundwork for scale up of projects in IDA and FCS through upstream and advisory, enhanced technical assistance to improve management capacity of clients and their compliance with environmental, social and governance (ESG) standards.
Recommendations for 2024
  1. The UK should continue to encourage management to improve the Bank’s approach to staffing in FCV countries, including as part of the IDA21 replenishment.
  2. UKDEL/FCDO should continue to engage with Management on the Bank’s successor FCV strategy in FY25 to ensure better targeting of FCV drivers through Bank operations, a greater focus on prevention, a more strategic approach to partnerships, and third-party implementation

Output Title	IDA projects mainstream gender and disability to enhance equality in IDA countries
Output number:		3	Output Score:	A+ Outputs moderately exceeded expectation
Impact weighting (%):		15	Weighting revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
3.1 Percentage of IDA-supported projects that demonstrate a results chain by linking gender gaps identified in analysis to specific actions that are tracked in the results framework (%) [annual]	60	Output has substantially exceeded expectation / 96% of IDA-supported projects that demonstrate a results chain by linking gender gaps identified in analysis to specific actions that are tracked in the results framework in FY24
3.2 Ratio of girls' to boys' Lower Secondary gross completion rate (%)	No milestone for FY24 but the ratio should be increasing	Output has met expectation / The ratio of girls’ to boys’ lower secondary gross completion rate was 95.5% in FY24 falling slightly from 95.6% in FY23
3.3 Number of IDA countries supporting women’s empowerment, through restoring and expanding access to quality and affordable sexual and reproductive, adolescent, and maternal health services, including countries with the lowest HCI (number of countries/(of which are the lowest HCI)) )	The FY24 milestone is 20/(10) / The FY25 target is 30/(15)	Output has met expectation / In FY24 20 countries supported women’s empowerment through restoring and expanding access to quality and affordable sexual and reproductive, adolescent of which 13 had the lowest HCI.
3.4 Countries supported to expand access to quality, affordable childcare (number of countries)	The FY24 milestone is 10 / The FY25 target is 15	Output has substantially exceeded expectations, has met the FY25 target / 16 countries were supported to expand access to quality, affordable childcare
3.5 Number of deliveries attended by skilled health personnel (millions) [cumulative]	The FY24 milestone is 27-53 / The FY25 expected range is 40-80	Output has moderately not met expectations / 22.1 million deliveries were attended by skilled health personnel in FY24
3.6 Number of IDA countries with expanded access to core services for persons with disabilities by implementing the principles of non-discrimination, inclusion, and universal access as per the Environmental and Social Framework.	The FY24 milestone is 12 / The FY25 target is 18	Output has substantially exceeded expectations and has met the FY25 target / 42 countries had expanded access to core services for persons with disabilities by implementing the principles of non-discrimination, inclusion, and universal access
[note] As of 2020, 15 countries with the lowest HCI are as follows: Central African Republic, Chad, South Sudan, Niger, Mali, Liberia, Nigeria, Mozambique, Angola, Sierra Leone, Congo Dem. Rep., Guinea, Eswanti, Yemen, Sudan.
[note] New indicator for FY18

IDA20 sought to deepen the implementation of the 2016-23 WBG Gender Strategy and focus on impact across the strategy’s four pillars. The figures captured in the table above reflect the IDA-supported results achieved during the first two years of IDA20 under the umbrella “IDA projects mainstream gender and enhance gender equality in IDA countries”.
The Gender Tag (3.1), which was developed to track progress in implementing the pillars of the strategy, seeks to distinguish projects that: 1) identify relevant gaps in endowments, jobs, assets, or voice/agency between women and men, boys and girls; 2) aim to address these gaps through specific actions supported by the project; and 3) link them to appropriate indicators in the results framework. In FY24, 96% of all IDA projects approved by the Board were gender tagged, substantially exceeding the IDA20 RMS expected value of 60% and 3ppt above the IDA19 results.
More broadly, IDA20 results to date have exceeded the total results achieved during the previous two years of IDA19 (FY21-FY22), namely, the ratio of girls to boys’ Lower Secondary gross completion rate (3.2) (IDA19: 93.5; IDA20: 95.5) and number of deliveries attended by skilled health personnel (3.5) (IDA19: 19.9 million; IDA20: 22.1 million).
IDA20 also includes new ambitious targets in the areas where gender gaps were exacerbated by the COVID-19 crisis, including in access to sexual and reproductive and adolescent health services (monitored through 3.3 where 20 countries have been supported) and in women’s return to paid employment (monitored through 3.4 where 16 countries were supported to expand access to quality, affordable childcare which supports women’s labour force participation). Additionally, to promote inclusive societies, IDA20 reached 42 countries to address the needs of persons with disabilities, substantially exceeding expected performance and exceeding the FY25 target one year early.
Overall, the indicators are performing well, with 5 of the 6 indicators substantially exceeding expectations or meeting expectations. Where the indicators have moderately missed the FY24 milestone we are confident that they are still on track to meet the FY25 target.
IDA’s RMS have not set yearly milestones, but FCDO has set them for indicators to track progress for FY24. As noted above, three additional indicators were included to monitor progress on IDA20’s aim to reduce gender gaps and meet the needs of persons with disabilities (indicators 3.3, 3.4, 3.6). There are no planned changes because of this review.
Lessons Learned
It was noted in the IDA19 Project Completion Review that a lot of the indicators failed to disaggregate results/beneficiaries by gender and that we should expect improvements. IDA20 has performed well in this regard. The share of gender-tagged projects—i.e., those that identify a gap through analysis, take specific action to address it, and monitor progress—has continued to rise and currently stands at 96%, far surpassing the expected value of 60%. Building on progress in designing projects to be gender-sensitive, more attention should be placed on implementation. A key finding of the recently published IEG 10-year evaluation on the WBG engagement for gender equality was that progress has happened at the level of engagement but more in breadth (quantity) than depth (quality) and more in design than in implementation, with limited evidence of results.
The pandemic also halted, and in some cases set back, efforts to narrow gender inequalities in IDA countries. However, the Bank has made excellent progress on gender and IDA has continued to prioritize the advancement of gender equality and delivered strong outcomes for women and girls and are now at least 50% of project beneficiaries.
Recommendations
  1. FCDO/UKDel to work with management to further disaggregate data to include disabilities, age and urban/rural.
  2. FCDO/UKDel to encourage Management to scale up their ambition on ambition in Sexual and Reproductive Health Rights and ensure it is integrated into most IDA health and gender programmes, given the absence of quantitative commitments in the WBG Gender Strategy
  3. FCDO/UKDel to ensure IDA21 replenishment targets remaining gaps in areas such as access to reproductive and adolescent health, economic opportunity, and prevention and response to GBV; and that policy commitments align with the new World Bank Gender Strategy

Output Title	IDA supports evidence-based policy making, job creation, and economic development
Output number:		4	Output Score:	A – Outputs met expectations
Impact weighting (%):		15	Weighting revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
4.1 Supporting interventions to address market failures and remove constraints in sectors with high potential for the private sector to drive sustainable and inclusive economic transformation and create better jobs, or where women and youth disproportionately work, of which 5 are FCS (number of countries/number of FCS countries)	The FY24 milestone is 13/3 / The FY25 target is 20/5	Output moderately exceeded expectations / In FY24 14 countries have been supported to address market failures and remove constraints in sectors with high potential for the private sector of which 4 are FCS countries
4.2 Beneficiaries in IDA countries of job-focused interventions (million)	No target set but indicator should be increasing	Output has met expectations / 24.3 million beneficiaries reached in FY24
4.3 Supporting IDA countries, of which 10 have a score of 3.0 or less on Country Policy and Institutional Assessment Dimension 16 covering transparency, accountability and corruption, to identify the governance constraints to the development, financing, and delivery of quality infrastructure investments (number of countries / number of countries with CPIA16 score under 3.0)	The FY24 milestone is 13 of which 7 have a CPIA16 score under 3.0 / The FY25 target is 20 of which 10 have a CPIA16 score under 3.0	Output has moderately exceeded expectation / 13 countries have been supported on Country Policy and Institutional Assessment Dimension of which 12 have a CPIA16 score under 3.0
4.4 Supporting IDA countries including those with ongoing statistical operations (i) to strengthen institutions and build capacity to reduce gaps in the availability of core data for evidence-based policy making, including disaggregation by sex and disability where appropriate; and (ii) to increase resilience of statistical systems, including through investments in digital technology and high-frequency monitoring capabilities (number of countries)	The FY24 milestone is 23 / The target for FY25 is 34	Output is substantially below expectation / 16 countries were supported in FY24
[note] The Country Policy and Institutional Assessment (CPIA) is a diagnostic tool that helps capture the quality of a country's policies and institutional arrangements, focusing on key elements that are within the country's control. This tool outputs a score from 1 (low) to 6 (high).

The indicators above reflect a subset of the indicators for the IDA20 special theme on job creation and economic transformation, seeking to address both the immediate needs of minimizing job losses and mitigating risks, while also helping them to seize longer-term job creation post COVID-19.
Overall, this output has performed well. In FY24 there were 12.5 million beneficiaries in IDA countries of job-focussed interventions (4.2), a 7% increase from FY23, taking the total for FY23-24 to 24.3 million.
Two of the indicators have moderately exceeded their targets, delivering on providing infrastructure investment support to countries with governance challenges (4.3), supporting interventions to address market failures and remove constraints in sectors with high potential for job growth (4.1). IDA’s RMS have not set yearly milestones, but FCDO has set them for indicators to track progress for FY24. There are no planned changes because of this review.
Lessons Learned
The introduction of the Jobs and Economic Transformation agenda as a Special Theme in IDA18 has been broadly successful in creating a platform from which IDA can start supporting structural transformation, private sector-led job creation, increased job quality and strengthened inclusion of women and youth.
The Special Theme has also been successful in expanding private investment, stimulating growth of sectors with potential for jobs and value addition, increasing connectivity and integration, and facilitating the adoption of technology, innovation, and entrepreneurship.
As noted in previous ARs for IDA, large-scale job creation needs to come from sustained private sector investment, accompanied by strong institutional capacity, and supported by WBG portfolio-wide approaches. As highlighted in the IDA20 Mid-term review, interventions are therefore more effective when support is integrated across a strategic portfolio of connected projects in collaboration with IFC and other development partners.
IDA 19 PCR also noted that the current policy commitments measure the number of countries that IDA19 has successfully engaged at the country level only and failed to capture the collective impact generated. The PCR therefore recommended that in IDA 20 there are more impact driven indicators and data can be designed and collected to measure effectiveness, including private sector capital mobilisation. Although IDA20 does not include these indicators this is reflective of IDA20’s approach to create a supportive foundation to encourage private investment and promote job creation, including through infrastructure and adoption of digital technology. IDA21, however, will include greater data disaggregation for jobs (e.g. % by gender and age) and the amount of private capital enabled/mobilised in the new Scorecard.
The Private Sector Window (PSW) has been a core part of catalysing private sector investment in IDA-only countries, helping to ensure the sustainability of growing the labour market. Overall, the PSW has been successful in supporting job creation and the expansion of IFC and MIGA into a greater number of low-income and fragile countries. Emerging lessons from PSW implementation highlight the need for robust and diversified project pipeline given the high volatility and low conversion rates in IDA countries; streamlining of internal processes to improve PSW delivery; the need for greater transparency around the reporting of the risk taken and impact delivered through PSW investments.
Recommendations
  1. As a key priority for the FCDO, UK and WBG teams should continue to share learnings on approaches to measure the impacts of IDA operations on jobs and economic transformation outcomes.
  2. Going forward FCDO/UKDel to work with management to push for a strong focus on sectors with high potential for job rich structural transformation, strengthening exports, and integrating into global value chains.
  3. FCDO/UKDel to work with management to ensure strong focus on encouraging private investment and improving institutional capacity in IDA countries, including through the IDA21 Private Sector Window alongside a scale up in FCV/LICs from IFC’s own account.

Output Title	IDA supports climate adaptation and resilience and crisis preparedness and response in IDA countries.
Output number:		5	Output Score:	A – Outputs met expectations
Impact weighting (%):		15	Weighting revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
5.1 Share of climate co-benefits over total commitments in IDA-supported operations %	The FY24 milestone is 35 / The FY25 expected value is 35	Output substantially exceeded expectation, already meeting the FY25 target / 43% share of climate co-benefits over total commitments in IDA-supported operations in FY24.
5.2 Countries supported to update and/or implement Nationally Determined Contributions or long-term strategies (number of countries)	The FY24 milestone is 33 / The FY25 target is 50	Output is moderately below expectations / 23 countries supported to update and/or implement Nationally Determined Contributions or long-term strategies in FY24
5.3 Number of IDA countries supported to implement and/or update their National Biodiversity Strategies and Action Plans (number of countries)	The FY24 milestone is 13 / The FY25 target is 20	Output substantially exceeded expectation, already meeting the FY25 target / 23 countries supported to implement and/or update their National Biodiversity Strategies and Action Plans
5.4 IDA projects with an AA Resilience rating.	The FY24 milestone is 5 / The FY25 target is 10	Output moderately did not meet expectation / 3 IDA20 projects have an AA resilience rating
5.5 Share of adaptation co-benefits over total climate co-benefits in IDA supported operations (%)	The milestone for FY24 is >=50 / The FY25 target is >=50	Output substantially not met expectation / In FY24 the share of adaptation co-benefits over total climate co-benefits in IDA supported operations was 39% falling from 53% in FY23
[note] Resilience ratings rate the confidence that expected investment outcomes will be achieved in spite of climate and disaster risks and a project’s contribution to the resilience of beneficiaries, communities and systems. Ratings are from A+ to C.

Overall, this output has met expectations, with two indicators (5.3 and 5.1) substantially exceeding expectations. In FY24, the share of climate co-benefits over total commitments in IDA reached 43%, exceeding the target of 35 percent on average over the IDA20 cycle (5.1). However, the share of these commitments with adaptation co-benefits (5.5) has fallen from 53% in FY23 to 39% in FY24. The decline is driven by high demand for energy access projects, which have high mitigation finance and lower adaptation finance.
Advancing work on long-term low-emission development strategies calls for coordinated, concerted efforts, including via updating and implementing Nationally Determined Contributions (NDCs) and long-term strategies (LTSs), aiming to integrate development and climate action consistent with the Paris Agreement. However, indicator 5.2, which tracks progress, is below expectations. Meeting the target has been challenging as NDCs and particularly LTSs are country-owned and developed through internal government processes. Therefore, they involve many stakeholders and are costly, time-intensive activities that are not typically financed through core lending, relying instead on trust funds for support.
Lessons Learned
The overall progress and results achieved for climate change has been strong, demonstrating how the Bank is operationalising the Climate Change Action Plan and delivering commitments. While the increasing share of climate finance in IDA-supported operations is positive, the drop in commitments with adaptation co-benefit has shown that the Bank should continue with efforts to increase adaptation and resilience in operations across sectors and enhance climate finance tracking and reporting to consider joint adaptation and development goals, in coordination with other MDBs.
Support for countries in developing LTSs has been slower due to limited budget to support LTS engagements, which are more lengthy and costly than engagements around NDC implementation. The World Bank is partnering with other multilateral development banks (MDBs) to maximize the number of countries supported.
Recommendations
  1. FCDO/UKDel should closely monitor indicator 5.5 (share of adaptation co-benefits over total climate co-benefits) and ensure it does not deteriorate any further in IDA20.
  2. FCDO/UKDel should work with Management to ensure the World Bank continues to explore options for partnerships with other MDBs to maximise support for implementing and updating NDCs and LTSs.
  3. For IDA21, FCDO/UKDel to work with management to push for at least a 45% target for the share of climate co-benefits in IDA-supported operations
Output Title	IDA is efficient, financially sustainable and effective
Output number:		6	Output Score:	A+ Outputs moderately exceeded expectation
Impact weighting (%):		15	Weighting revised since last AR?	Decreased by 5%

Indicator(s)	Milestone(s) for this review	Progress
6.1 IDA Budget Anchor (%, expenses over loan revenue) [cumulative]	<=100	Output moderately exceeded expectation / The budget anchor in FY24 was 66% falling from 70% in FY23 and 74% in FY22
6.2 Overall satisfactory performance in IDA financed operations (% IEG Rating, 3-year rolling)	80	Output substantially exceeded expectation / 90.7% of IDA operations in FY24 were judged as satisfactory
6.3 Client feedback in IDA countries on WBG effectiveness and impact on results (average rating, 1-10) [annual]	7	Output met expectation / The average rating for client feedback on WBG effectiveness and impact on results was 7.6
6.4 Proactivity Index (%) [annual]	80	Output substantially exceeded expectation / Proactivity index in FY24 was 95.6% rising from 82.4% in FY23.
6.5 Disbursement ratio (%)	20	Output moderately exceeded expectation / Disbursement ration in FY24 was 21.2% rising from 18.8% in FY23
6.6 Quality of M&E in IDA-financed operations (%) [3-year rolling average]	60	Output substantially exceeded expectation / Quality of M&E in IDA-financed operations was 70.8 in FY24
[note] The ratio of projects in “actual” problem status 12 months ago that have had a proactivity action in the last 12 months over total number of problem projects from 12 months ago. Actions are upgrade, close, cancel >=20%, suspend, or restructuring
[note] Ratio of disbursements during the fiscal year to the undisbursed balance at the beginning of the fiscal year for IDA Investment Project Financing projects.

This output focusing on IDA20’s operational and organisational effectiveness has performed exceptionally well, with all targets being exceeded and half of the indicators substantially exceeding the target.
On the quality of work delivered by IDA20, the performance in IDA financed operations rated as “moderately satisfactory” or higher on achievement outcomes by the Independent Evaluation Group (IEG) (6.2) was 90.7 in FY24 rising from 87.9 at the end of IDA19 (FY22). Similarly, the quality of IDA’s monitoring and evaluation has continued to improve (6.6), with 71 percent of all IDA operations rated as substantial or high on M&E quality up by 6ppts since FY22. Client perceptions of IDA’s effectiveness and impact (6.3) have continued to see an uptrend since IDA19 and remain above the expected index value of 7.
Lessons Learned
Considering IDA 20 launched in a challenging environment marked by deepening crises, the outcome of IDA20’s operational and organisational effectiveness has been exceptional and continued to deliver positive outcomes for people in client countries.
Recommendations
  1. Considering all indicators have outperformed their targets, FCDO/UKDel to work with Management to consider options for setting higher ambition targets where appropriate.
  2. FCDO to consider tracking indicators for IDA21 for FCV countries to ensure operational and organisational effectiveness even in challenging IDA contexts.
## D: VALUE FOR MONEY
FCDO uses the ‘4 Es’ framework (economy, efficiency, effectiveness and equity) to ensure that UK ODA is cost-effective and delivers value for money. An assessment of IDA20 against each of the 4 Es is provided below.
Economy (“spending less”)
IDA20’s budget anchor – administrative expenses as a share of IDA revenue – is at 66%, well below the benchmark of 100%. A figure below 100% indicates that the IDA revenue can fully cover the administrative expenses without pulling resources from other sources. This has fallen from 70% in FY23 and 74% in FY22. We have seen an improvement on this indicator in the recent track record from IDA.
The average cost of IDA supervision projects has been increasing since IDA17, from $147,000 per project in FY13 to $246,000 per project in FY24. Taking into account the global inflation rate, this represents a real increase of around 20% over the last decade. We judge that an average real increase of ~2% p.a. over a decade amid the global economic environment to be reasonable.
Efficiency (“spending well”)
IDA20 has been highly efficient in terms of converting FCDO’s input (donor’s contribution) into outputs.
IDA’s unique leveraging model, which leverages donor funding with market borrowing to further maximize impact, enables it to achieve greater value from contributions – every dollar from donor contribution supports approximately $4 in lending to recipient countries. And it has allowed IDA to grow from $52bn in IDA17 (FY14-17) to $93bn in IDA20, with similar levels of donor contributions. IDA has increased the efficiency of its financial model during IDA20: issuing more longer-term fixed-rate debt, which releases some capital held against interest rate risk; right-sizing its capital buffers; and adjusting the capital held against private sector operations to better reflect its characteristics since IDA18. All of this has enabled IDA to provide greater financing volumes than it would have been able to otherwise.
As noted in the Multilateral Performance Assessment Network (MOPAN) report, IDA’s hybrid financial model is strong and able to expand the scale of concessional funding available to eligible countries far beyond donors’ contributions, promoting sustainable lending over the medium-term and reinforcing value for shareholders.
Effectiveness (“spending wisely”)
The impact of IDA20 has been strong, with some of the metrics – which include ambitious targets – outperforming or achieving end-replenishment targets early. Overall, 28 of the 36 milestones for the indicators have been met or exceeded expectations.
The policy priorities of each replenishment are also agreed by both the donor countries and the recipients of IDA – almost all of which have met or exceeded expectations in this Annual Review. Furthermore, with horizontal coverage across sectors, IDA provides a ‘menu’ from which countries choose priorities based on their needs. Both of which ensure that the IDA is aligned to recipients own strategies and priorities and delivers against UK development priorities.
Equity
IDA20’s effort has helped protect development gains and continued making progress in other important areas. As assessed by output 1 and 3 above, IDA20 has also ensured this important development progress is inclusive, including for women. Notably, the share of gender-tagged projects currently stands at 96 percent, far surpassing the expected value of 60 percent, and 42 countries now have expanded access to core services for persons with disabilities well above the IDA20 target of 18.
## E: RISK
The UK actively monitors and manages identified risks through a risk register, which is reviewed and updated on a quarterly basis. Given the diversified nature of IDA’s portfolio, the Bank’s track record of effectively managing risks, robust mitigation strategies, and FCDO’s overall risk to investment, IDA20 programme risk is assessed to be moderate. The programme’s risk appetite profile is in line with the FCDO departmental risk appetite profile.
Mitigating IDA risks involves working closely across the different reform processes and new/refreshed Bank strategies to ensure UK asks and the Bank’s plans are coherent and monitoring them closely through some strong risk management in key areas.
The Multilateral Organisation Performance Assessment Network (MOPAN) review, published in August 2023, gave the World Bank (IBRD and IDA) a satisfactory rating overall, with half of the key performance indicators rated as “satisfactory” and the other half as “highly satisfactory”. In particular, the detailed risk management strategies at the Bank to ensure the identification, mitigation, monitoring and reporting of risk has received a “highly satisfactory” rating. FCDO has noted MOPAN’s suggestions and concluded that there are no new material risks arising from the findings of the report.
Latest risk register
The table below shows the active risks currently in the risk register. We assessed the programme level residual risk level (for specific risks) against the programme risk appetite for the relevant risk category. The risk profile for this programme is aligned with the default FCDO risk appetite profile.
Risk Category	Description	Residual Risk Level	Programme Risk Appetite*
Policy and Programme Delivery	Demand for IDA resources. The likelihood of the exhausting the IDA allocation before IDA21 due to strong demand and need. Countries including the UK would be asked to contribute additional resources bilaterally. This risk is also cross-cutting as a Financial and Fiduciary Risk.	Major	Receptive
Reputational	Risk in FCAS settings. The Bank's risk appetite in FCAS settings might be greater than the FCDO's, exposing the FCDO to excess risk.	Moderate	Cautious
Safeguarding	Environmental and Social Framework. The Bank is now applying the ESF in a context-based approach. We will watch this early phase of implementation of the new approach and carefully mitigate any unintended consequences during its implementation.	Moderate	Cautious
Policy and Programme Delivery	Resources. The IDA team lack the resources, resilience or capabilities to effectively support the delivery of UK objectives through, or manage risks relating to IDA	Minor	Receptive
Policy and Programme Delivery	Climate co-benefit target. IDA off track in terms of its target of 35% of climate co-commitments by 2024 and fails to use its influence with finance and planning ministries to encourage	Minor	Receptive
Reputational	Public. Public or Parliamentary concerns about IDA projects, HMG financial contribution to IDA and/or HMG positions at the Board being questioned/challenged	Moderate	Cautious
Policy and Programme Delivery	Fragility. IDA focuses excessively on short -term relief as opposed to long-term development, in its work on FCAS.	Minor	Receptive
Public Service Delivery and Operations	Risk management. IDA fails to have a strategic approach towards managing financial and programming risks.	Minor	Cautious
Policy and Programme Delivery	Project implementation. The use of recipient executed programming reduces IDA's ability to ensure robust and timely delivery.	Moderate	Receptive
Safeguarding	Safeguards. Risk that IDA projects result in harm to people or the environment. This could be compounded by insufficient numbers of staff in country; however, this has been on a steady upward trajectory (50.3% overall in June 2024).	Moderate	Cautious
Policy and Programme Delivery	Private finance. IDA fails to support the scale of private finance mobilisation needed to meet the need for finance in particular in the poorest and most fragile countries, with risks to the delivery of HMG objectives. (Both off its own balance sheet, and through the joint IFC/MIGA/IDA Private Sector Window	Major	Receptive
Policy and Programme Delivery	Resources. IDA countries might be disadvantaged if the WB evolution Roadmap were to divert significant Bank staff time or if the global challenges agenda were to pull limited donor concessional resources away from LICs and toward MICs.	Moderate	Receptive

*The FCDO risk appetite refers to the risk level that FCDO is willing to operate at for specific risk categories. The FCDO risk appetite levels are presented in a 4-grade scale, labelled as “Minimal”, “Cautious”, “Receptive” and “Eager”. In this review, we have translated these FCDO level risk appetites into the same scale used to assess programme level risks for easier comparison. Programme level risks are again evaluated across 4 grades: “Minor”, “Moderate”, “Major” and “Severe”. The latest FCDO department risk appetite statement dated in September 2024 has a “receptive” risk appetite for context and programme delivery risks, and a “cautious” risk appetite for other risk categories.

FCDO Risk Appetite	Equivalent Programme Level Risk Appetite
Minimal	Minor
Cautious	Moderate
Receptive	Major
Eager	Severe

## F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

The World Bank Group is the largest source of development finance, expertise and knowledge globally. The UK’s partnership with IDA is critical in delivering UK poverty and prosperity objectives. The UK contributions to IDA extends the reach of our ODA across geographies and sectors given its sheer scale.
In FY24, the Independent Evaluation Group (IEG) rating – a collection of independent assessments and validations for World Bank – of Satisfactory outcomes of performance in IDA financed operations has remained high at 90.1%, rising from 87.9% at the end of IDA19. FCDO programme management scoring has shown that IDA20 has achieved an A overall rating in FY24 with outputs meeting expectations overall. So far 28 indicators have met or exceeded the FY24 milestone target; just 8 indicators did not meet expectations. In the first 15 months of IDA20, IDA commitments reached $39.9 billion (including PSW) and commitments through the windows, including the PSW, reached $13.1 billion which is significantly higher than the first 15 months of IDA19.
To ensure the UK’s policy asks for IDA20 was reflected sufficiently throughout the replenishment cycle, the UK had routine engagement with the Bank’s senior management to cover key strategic and policy issues, including influencing the Bank’s development on various thematic strategies and operational measures. This ensures the UK’s priorities can be reflected in the Bank’s strategic direction and subsequently, in IDA’s operations and projects. The Bank and FCDO have a strong partnership and open communication channels to discuss critical matters.
IDA has also been improving in its financial sustainability. The IDA budget anchor (IDA administrative expenses over IDA loan revenue) has been declining since FY22 to FY24, from 74% to 66%. The net disbursement volume has increased from $14.5bn in FY22 (final year of IDA19) to $20.0bn in both FY23 and FY24. The WB’s financial management is subject to a high degree of scrutiny, including by credit rating agencies, internal and external audit, and periodic independent reviews of the internal control system. There is also a carefully designed system for financial governance within the Board, where shareholders play an integral role.
## G: MONITORING, EVIDENCE AND LEARNING

Monitoring
The UK monitors IDA’s progress closely through the UK Delegation to the World Bank (UKDel) and our single seat on the Board. The Bank is accountable to its shareholders through the Board of Executive Directors.  The Board approves all IDA projects (except advisory projects and top up finances for existing projects), with relevant documentation circulated to the Board at least two weeks in advance of formal approval. Most projects are now approved under an Absence of Objection basis, with the riskier or more high-profile projects discussed at the Board. All Bank strategies for a country are discussed by the Board.
The UK supplements information received from World Bank management with feedback from FCDO country offices on World Bank performance in country. IFID has established a regular country engagement mechanism to complement ad hoc interactions with country offices on specific projects to flag any concerns on proposed Bank projects. Alongside FCDO’s country offices, other HMG departments continue to play a part in our monitoring of projects.
The Bank produces routine briefings and conducts regular project consultations with shareholders. The World Bank’s Independent Evaluation Group produces regular evaluations and other commentary of the WBG’s performance across a range of themes.
[note] Examples include: The IDA Private Sector Window: Unlocking private investment in the poorest and most fragile countries; World Bank Support to Jobs and Labor Market Reform through International Development Association Financing
Evidence
IDA20 was closely monitored with results made available in its RMS, which is updated annually (in October). The RMS reports results disaggregated by gender and FCV-affected countries. It has three tiers of indicators:
Tier 1. These indicators report long-term development outcomes and the broader context of countries in which IDA operates, such as the number of people living on below US$2.15 per day. This relates to the ultimate impact that IDA, and FCDO’s support for it, seeks to achieve.
1. Tier 2. This tracks development results in countries supported by IDA operations, such as the number of people benefitting from social safety net programmes, supported by IDA.
2. Tier 3. Tier 3, which includes measures of both the operational and organisational effectiveness of IDA, such as the share of IDA operations reporting positive outcomes.
RMS information is also supplemented by results information from reporting to the Bank Board and Bank wide public results reporting in the Corporate Scorecard.
Learning
IDA operations continued to incorporate evaluative approaches into project design, drawing lessons from other operations and deploying knowledge from within and outside the Bank. Furthermore, the Bank implements a range of instruments to assist results-based decision-making across the operations cycle to support alignment, implementation and results. Performance and Learning Reviews (PLRs), Mid-Term Reviews for operations, and regular Country Portfolio Performance Reviews (CPPR) provide opportunities to consider implementation challenges to improve performance. As noted by a Multilateral Organisation Performance Network (MOPAN) 2023 assessment of IDA, IEG has also been increasingly active in disseminating lessons from evaluations in collaboration with WBG Management.
However, there is still room for improvement. A consistent theme in the ‘lessons learned’ outlined in the output scoring section, is the importance of flexible approaches to adapt to volatility and crises. The Bank should draw on its experience in fragile states and its response to COVID-19 and continue expanding its work to simplify IDA to ensure it is able to adapt to and respond to emerging challenges. Additionally, the Bank should continue to build on experience coordinating with other MDBs and organisations such as the UN. This is particularly the case for climate, both for increasing adaptation and resilience operations and developing LTSs; and interventions in FCV settings where working with the UN and other international players is key.

Date of last narrative financial report	30/06/2024	Date of last audited annual statement	30/06/2024