Evaluation of the impact of the Human Development Innovation Fund (HDIF) on the Tanzanian Innovation Ecosystem

March 2023

This evaluation was commissioned by UNDP Tanzania through the FUNGUO Innovation programme with funding from UKAid, European Union and the United Nations Development Program
Produced by INOMER: / Sirin Elci / Gulden Bayaz / Gulenay Dogan / Manuel Ricardo Galindo Moreno / Jerome Helfft	Reviewed by / Jamie Proctor (FCDO) / Alexa Haden (UNDP) / Joseph Manirakiza (UNDP)

Contents

List of Figures

List of Boxes

List of Tables

Acronyms and Abbreviations

ATIP	Africa Technology and Innovation Partnership
AU	African Union
CCBRT	Comprehensive Community Based Rehabilitation in Tanzania
COSTECH	Commission for Science and Technology
COWSO	Community Owned Water Supply Organizations
CBWSO	Community-Based Water Supply Organizations
EAIRH	East Africa Research and Innovation Hub
ECOWAS	Economic Community of West African States
FCDO	Foreign, Commonwealth and Development Office
FUNGUO	Funguo Innovation Programme
GDP	Gross Domestic Product
GERD	Gross Domestic Expenditure on Research and Development
GII	Global Innovation Index
GNI	Global National Income
GO-SPIN	Global Observatory of Science, Technology and Innovation Policy Instruments
HDI	Human Development Index
HDIF	Human Development Innovation Fund
ICT	Information and Communications Technologies
MEL	Monitoring, Evaluation, and Learning
MVP	Minimum Viable Product
MEL	Monitoring, evaluation and learning
M&E	Monitoring and Evaluation
NFAST	National Advancement of Technology Fund
NGO	Non-Governmental/Civil Society Organisations
SADC	Southern African Development Community
SDG	Sustainable Development Goals
SME	Small and Medium-Sized Enterprise
SNA	Social Network Analysis
STEM	Science, Technology, Engineering and Mathematics
STI	Science, Technology and Innovation
TANZICT	The Information Society and ICT Sector Development Project in Tanzania
ToC	Theory of change
ToR	Terms of References
TZS	Tanzanian Shilling
UK	United Kingdom
UKNIAF	United Kingdom Nigeria Infrastructure Advisory Facility
UNDP	United Nations Development Programme
UNECA	United Nations Economic Commission for Africa
UNESCO	United Nations Educational, Scientific and Cultural Organization
UNICEF	United Nations International Children's Emergency Fund
UNIDO	United Nations Industrial Development Organization
VfM	Value for Money
WASH	Water, sanitation and hygiene

# Executive Summary

Funded by the Foreign, Commonwealth and Development Office (FCDO) with a budget of £39.1 million, the Human Development Innovation Fund (HDIF) aimed to “support innovative approaches to improving the quality, value for money and sustainability of basic services in the education, health and water and sanitation sectors in Tanzania”. It was implemented from January 2013 until March 2022. This independent evaluation of the impact of the HDIF on the Tanzanian Innovation Ecosystem was commissioned by the United Nations Development Programme (UNDP) to INOMER, and took place from January to March 2023.
[note] https://devtracker.fcdo.gov.uk/projects/GB-1-203539/summary
The HDIF provided competitive grant funding and technical assistance to 43 successfully completed projects which developed innovative solutions in health, education and water, sanitation and hygiene (WASH) sectors. The programme underwent a gradual evolution to respond to needs, and with the changes in its theory of change, it offered capacity building and support for developing the innovation ecosystem in Tanzania in addition to project funding.
[note] HDIF 2021. Final Report: Human Development Innovation Fund
The final evaluation of the HDIF used a mixed-methods approach that included face-to-face and virtual interviews, an online survey, as well as a detailed document review. It also used an innovation network analysis and a Value for Money (VfM) assessment.
Main findings and conclusions: The evaluation found that
The •	The HDIF was a successful programme that achieved notable impact in Tanzania not only through the innovation projects it financed (see Box 1 as an example) but also with the initiatives it implemented to develop the innovation ecosystem. The programme helped the creation of a vibrant and dynamic ecosystem in the country by forming linkages between various actors (Figure 1).
Figure 1. Linkages created or strengthened in the Tanzanian innovation ecosystem with the help of the HDIF Programme

Source: INOMER SNA survey and analysis.
More than 90% of the evaluation survey respondents indicated that HDIF was strong aligned with development priorities, and addressed innovation ecosystem needs and challenges in Tanzania.

Box 1. Ubongo Kids’ Impact / Ubongo Kids, one of the grantees of HDIF, has created a very significant impact not only in Tanzania but also across Africa thanks to the support it received from the programme. The organisation generates and distributes fun, localised and multi-platform edutainment programmes for children. / Ubongo Kids’ localised early childhood education programme development project (“Akili and Me”) was supported by HDIF for five years until 2020. The rationale of the project was based on research showing that the first few years of life play a crucial role in a person's future development, with 90% of brain development occurring between birth and age 5. Many children in sub-Saharan Africa miss out on this critical period, with 44% of 4-year-olds having low cognitive or social-emotional development. “Akili and Me” has proven to be successful in improving early cognitive skills, including literacy and numeracy, by 13%. / As of the end of 2022, Ubongo Kids expanded their operations from Tanzania to 22 African countries, offering programmes in 12 languages. They have reached 32 million families across the continent through TV and radio programmes and have had around 3 million users on digital platforms. They have also established partnerships with 1,300 organisations that use Ubongo Toolkits content to reach kids in underserved communities. Notably, they have managed to maintain a cost of $0.10 per child in Africa for broadcast through TV and radio. The organisation has also made an effort towards equality as well, such as giving female characters in the programmes 60% of screen and speaking time. / By 2030, Ubongo Kids plan to have 120 million kids across Africa learning with their programmes and improve their cognitive, social-emotional, and life skills.

- The key success factors, which should be considered in innovation programming, include:
  - Capacity building and project management support offered to the grantees, in addition to the innovation finance provided, in the areas that they need the most for effective and efficient project management and deployment of innovations developed.
  - Awareness raising, networking and other related initiatives, notably, the Innovation Week; technical assistance to policy-makers, and support to hubs that helped expanding and dynamising the innovation ecosystem.
  - Adaptive management and programming strategies used for effective delivery, as well as flexibility and agility of HDIF and FCDO teams to respond to the emerging needs and challenges both at the programme and project levels.
  - Resource efficiency achieved, quality of financial management maintained, risk management strategies and effective VfM measures implemented.
- The stakeholders believe that the programme has had an impact on the improvement of the Global Innovation Index of Tanzania. According to the World Intellectual Property Organization (WIPO), Tanzania ranked 8th out of 27 sub-Saharan African economies in 2022, compared to the 18th position among 31 sub-Saharan African nations in 2013, the year the HDIF was launched. While it is difficult to measure the impact at that level, taking into account the programme's effects on the ecosystem, it is plausible that the HDIF has made a contribution towards achieving this result.
There are valuable experiences gained and lessons learnt from the HDIF that could be taken into account in the design and implementation of new innovation programmes. These are incorporated into the recommendations below.
Recommendations: In line with the conclusions summarised above and within the context of broader evaluation findings, the evaluation team recommends that the FCDO
- Continues funding innovation in Tanzania to build on the success of the HDIF and sustain the progress achieved in innovation ecosystem development so that the benefits of the investment made so far are consolidated and expanded.
- Replicates the HDIF model in other countries, and directs donor support to finance frugal innovation projects in education, heath, WASH and other relevant fields in accordance with societal needs and development challenges of the countries.
- Integrates the innovation ecosystem development approach utilised in the HDIF as an essential component of future innovation programmes for the sustainability and scaling up of results.
- Ensures that a varied set of financial instruments (such as equity investments, soft loans, innovation vouchers, matching grants, etc.) are used in innovation programmes according to the needs and capacities of target groups which could be defined as start-ups, grassroot innovators, SMEs, established businesses, etc.
- Considers financing innovation programmes and projects in stages based on milestone achievements for more effective allocation of resources, greater flexibility in response to changing needs, and reduced risk of funding ineffective projects as well as for more informed decision-making based on the assessment of progress against milestones and adjustments in programme accordingly.
In addition, innovation programme design and implementation teams are recommended to
- Engage sufficient number of diverse ecosystem actors in the design process through extensive consultations and in-depth needs and capacity analyses.
- Establish effective communication with policy-makers to develop a shared understanding and sense of ownership of the programmes.
- Implement effective strategies from the outset for mainstreaming women, youth, and other underrepresented communities, such as indigenous peoples, as well as integrating environmental sustainability and climate change as cross-cutting issues in programmes and projects.
- Make collaboration with different organisations an eligibility criterion for applicants of project funding, specifically encouraging partnerships between the private sector and academia/research institutes to leverage their respective resources and expertise for knowledge and technology transfer, including the creation of start-ups and spin-outs.
- Establish a robust M&E framework for programmes and projects during the design phase as well as a small and VfM-focused set of metrics with cost element and pre-determined SMART targets with milestones.
- Provide capacity building on M&E and VfM to the programme management teams to ensure effective implementation and use of framework developed.
The full list of recommendations is found in Section 5.2.
Evaluation of the impact of the Human Development Innovation Fund (HDIF) on the Tanzanian Innovation Ecosystem

# Introduction

This report presents the results of the independent evaluation of the impact of the Human Development Innovation Fund (HDIF) on the Tanzanian Innovation Ecosystem that was commissioned by the UNDP to INOMER. The evaluation was conducted over a period of three months from January to March 2023, and is based on the collection and analysis of primary and secondary data using a mixed-methods approach.
## A brief contextual background
Tanzania is the second largest economy after Kenya in East Africa with a Gross Domestic Product (GDP) of $67 billion and a population of over 63 million in 2021. In 2015, the country achieved the status of a lower-middle-income economy. According to the latest data available, Tanzania’s Global National Income (GNI) per capita was $1,927 in 2017.
[note] https://data.worldbank.org/indicator/NY.GDP.MKTP.CD?locations=TZ
[note] https://data.worldbank.org/indicator/SP.POP.TOTL?locations=TZ
[note] https://data.worldbank.org/indicator/NY.GNP.PCAP.KN?locations=TZ
Tanzania's Human Development Index (HDI) value has been steadily increasing over the years, although it remains relatively low in comparison to the world’s average of 0.732 in 2021. In 1994, the country's HDI value was 0.370, and by 2021 it reached 0.549, ranking 160th among 191 countries. This improvement is indicative of the progress made towards achieving the Sustainable Development Goals (SDGs), especially regarding education, health and water, sanitation and hygiene (WASH). However, the country still faces challenges. In general, despite efforts to achieve universal access to primary education, persistent issues exist in relation to poor learning outcomes, high dropout rates, and inequitable access for marginalised groups. In the health sector, the HIV/AIDs epidemic, shortage of human resources, and insufficient funding remain major issues. Moreover, illnesses related WASH, such as diarrhoea and stunted growth, are widespread due to limited access to improved sanitation facilities and clean drinking water. As a result, Tanzania spends a significant share of its health budget on preventable WASH-related diseases.
[note] https://hdr.undp.org/data-center/human-development-index#/indicies/HDI
[note] https://www.unicef.org/tanzania/what-we-do/education
[note] https://www.afro.who.int/countries/united-republic-tanzania
[note] https://www.unicef.org/tanzania/what-we-do/wash
According to the 2022 Global Innovation Index (GII), Tanzania performs above the expectations for its level of development. The country was categorised as an “Innovation Achiever” four times between 2017 and 2022. As demonstrated by its top-performing Global Innovation Index (GII) sub-index, "Institutions," which ranked 74th out of 132 countries in 2022, the country has been striving to establish a supportive environment for innovation. However, its performance in the "Human Capital and Research Institutions" sub-index has been poor, with a ranking of 126th in 2022.
[note] https://www.wipo.int/edocs/pubdocs/en/wipo-pub-2000-2022-en-main-report-global-innovation-index-2022-15th-edition.pdf
Despite the increasing interest of young people in entrepreneurship as an alternative career path, the start-up ecosystem presents several challenges. These include inadequate training opportunities in science, technology, engineering, and mathematics (STEM), insufficient business services, limited access to early-stage investments, and insufficient focus on scaling up in international markets.
[note] https://www.itcbenchmarking.org/download-file/792
## A brief overview of the programme evaluated
The evaluated programme, the Human Development Innovation Fund (HDIF), was initiated in January 2013 “to support innovative approaches to improving the quality, value for money and sustainability of basic services in the education, health and water and sanitation sectors in Tanzania”. Funded by the Foreign, Commonwealth and Development Office (FCDO) with a budget of £39.1 million, it ended in March 2022 with a three-month extension granted by the donor to ensure that it is finalised in line with the closure standards of the FCDO.
[note] https://devtracker.fcdo.gov.uk/projects/GB-1-203539/summary
[note] FCDO (2021) Programme Completion Review
The HDIF provided competitive grant funding and technical assistance to 48 projects (of which 43 were completed successfully) that aimed to develop innovative and sustainable solutions in health, education and WASH sectors. While the initial design aimed at supporting innovation among non-public sector actors with a focus on the private businesses, it underwent a gradual evolution based on the needs and lessons learnt at the early phases. With the changes in its theory of change, the programme then included measures for fostering the growth of an innovation ecosystem in Tanzania in collaboration with the Tanzania Commission for Science and Technology (COSTECH).
[note] HDIF 2021. Final Report: Human Development Innovation Fund
## A summary of evaluation objectives and approach
In line with its Terms of References (TOR), the evaluation aimed to conduct external assessment of the outcome level impacts of the HDIF. The focus of the study was the identification and reporting of “key success, best practices and lessons learnt; and evaluate value for money and the impact the program had on the innovation ecosystem in Tanzania”. The evaluation tools and techniques used included detailed document review, value for money analysis, semi-structured in-depth interviews, online questionnaire survey and innovation network analysis. The cut-off date for data collection was 15 February 2023.
## Report structure
The remainder of the report is set out as follows: Section 2 presents a description and the theory of change of the HDIF. Section 3 provides information on the purpose and methodology of evaluation. Section 4 presents the main evaluation findings triangulated from the various lines of evidence in response to the evaluation questions, including a Value for Money (VfM) and innovation ecosystem analyses. Conclusions and recommendations drawn from the evaluation findings are given in Section 5. Additional information is provided in the annexes at the end of the report.

# Programme description and theory of change
As explained in the programme documents (Annex 1 ), the Human Development Innovation Fund (HDIF) aimed to improve outcomes in education, health, and WASH sectors in Tanzania by funding and promoting innovations with the potential to transform the delivery of basic services. It aimed to complement the UK budget and sector support to the Government of Tanzania, providing a mechanism to encourage innovation and to support scale up of promising approaches. The programme placed significant emphasis on experimenting with novel service delivery models, exploring the use of new technologies, engaging with new service providers and forging new partnerships, with particular emphasis on the private sector and public-private collaborations.
[note] In HDIF, innovation was defined as primarily to the use of approaches for the first time, or new ways of applying ideas, technologies or ways of doing things, in a country. The focus is on working with and re-working the existing stock of knowledge in a novel way rather than doing something brand new, so the distinction between invention and innovation – in the sense of first application – is crucial. Innovation also referred to experimentation, with the attendant risk of failure as long as lessons are learned and the implications of failure are appropriately considered (FCDO (n.d.) Business Case: Human Development Innovation Fund (HDIF) for Tanzania https://devtracker.fcdo.gov.uk/projects/GB-1-203539/documents
Moreover, the programme aimed to enhance the COSTECH’s capabilities, foster a culture of innovation, promote the application of science and technology to advance development, and facilitate the dissemination of knowledge and lessons learnt to the government and other key stakeholders.
The HDIF was initially planned as a five-year programme for the period between 2013 and 2017/18. As a result of the extensions given through contract amendments, it was ended in 2022. According to the Programme Completion Review, the final programme spending was £39,199,196.70 as opposed to the initial planned budget of £30,000,000, based on an increase with the 4th contract amendment as a costed extension.
As set out in the Business Case of the programme, the initial design included funding projects through two windows and three rounds of funding. The first window aimed to fund projects of up to £400,000 to test new ideas and approaches through small-scale pilots, selected through open competition. With the second window, it was envisaged to fund projects of up to £3 million to test at scale ideas and approaches for which there were more evidence. One-third of the available funding (approximately £8 million) was planned to be allocated to innovative projects, and two-thirds (approximately £16 million) was to be allocated to projects testing ideas at scale. It was aimed to allocate the first two rounds of funding in 2013, for projects of up to 4.5 years’ duration, and the third in 2014, for projects of up to 3.5 years’ duration. The objective was to obtain counterpart funding from all projects to ensure strong commitment from recipients and minimise risk. The priority target groups for funding were identified as non-state actors, including the private sector and civil society organisations, and they were expected to work closely with government to implement projects and to ensure sustainability.
[note] https://devtracker.fcdo.gov.uk/projects/GB-1-203539/documents
The HDIF was managed by a dedicated Fund Manager, who was responsible for the day-to-day operation of programme, by, among others, managing grants, ensuring effective financial oversight and reporting, supporting and monitoring projects, ensuring that all projects are rigorously evaluated, and sharing evidence and lessons learnt. The programme also worked closely with COSTECH, which has a mandate to encourage innovation and support the translation of research and evidence into policy and practice.
Over the course of eight years, the programme evolved and was ultimately structured into three interrelated components:
- INSPIRE focused on innovation promotion and ecosystem building. This component implemented measures, such as providing funding and support for innovation events, organising innovation challenges and competitions, supporting innovation hubs, and hosting strategic events.
- CATALYZE focused on innovation financing. The programme carried out five competitive funding rounds. Each round was designed and implemented differently, based on specific objectives and lessons learnt from previous rounds. The funding component was aided by targeted technical assistance provided through the Business Advisory Fund to the organisations that received funding.
- TRANSFORM focused on promoting an enabling environment for innovation by generating insights and learning from the other programme components and using them to engage with the government, private sector, and development partners to influence policies and processes.
  [note] https://devtracker.fcdo.gov.uk/projects/GB-1-203539/documents
Based on the data provided in the Final Report, 57.2% of the programme's total funds was allocated for project grants to innovators under the CATALYZE component (Table 1).

Table 1. Summary expenditure against project budget
Description	Head Contract CA5 (£)	Total Invoiced 09/2013 to 07/2021	Variances
A: Fees
Personnel Input	4,010,504.00	4,010,458.82	0.00%
B: Reimbursable
Fares	1,112,062.00	1,015,249.43	8.71%
Equipment	139,449.00	131,210.00	5.91%
Operating Costs	944,029.00	940,562.08	4.94%
C: Milestones	4,011,070.00	4,011,070.00	0.00%
D: Programme Activities	6,581,741.00	6,519,047.84	0.03%
E: Grants	22,436,802.00	22,436,619.95	0.00%
Total	39,235,658.00	39,199,196.70	0.28%

Source: HDIF Final Report. 2021
Out of 48 grantees, 19 were international non-governmental/civil society organisations (NGOs) and 17 were national NGOs (Figure 2). Around 78% of the total funding was provided for the projects of these organisations, while four private sector companies received 6% of the funding (Figure 3).

Figure 2. Number of grantees by organisation type	Figure 3. Amount of grants by organisation type18
[note] The categorisation uses the HDIF classification in http://hdif-tz.org/wp-content/uploads/2022/10/ApproachPaper_web.pdf considering that it is based on the common terminology used by the HDIF stakeholders. Accordingly, “Academia” includes universities/research institutes; “Enablers” cover incubators and hubs; “Funders” are defined as banks and donors; “HDIF” refers to programme management; “Industry” includes start-ups and national and multinational businesses; and “NGOs” are international and national non-governmental/civil society organisations.

Source: HDIF Grantee List, Calculation: INOMER

The theory of change (ToC) and results framework of the HDIF were modified multiple times in response to the evidence and insights gained from programme inception and implementation. These changes were made to ensure that the programme's ToC remains relevant to achieving the intended outcomes and impact. The ToC given in the Programme Completion Review defined the desired impact of the programme as “Dialogue and practice in innovation improve basic services in human development in Tanzania” (Figure 4). The initial outcome statement of the HDIF, which was “Innovative solutions that improve the quality and value for money of basic services in the public and private sectors” was redefined as “Outcome A: HDIF intervention accelerates the diffusion of innovative ideas, approaches, and solutions to human development challenges” and “Outcome B: HDIF intervention accelerates conversations, debates, and policymaking on innovation in human development”. The results framework was updated accordingly to incorporate changes, and was considered a living document.
The Completion Review also states that, in 2014 and 2015, major changes were made to the ToC based on new evidence and insights from various sources. These changes included increasing funding rounds with a focus on smaller awards to support early-stage innovations and adding an additional round to support human development-focused innovations in education, health, and WASH. The engagement with COSTECH was also strengthened, and the focus was expanded beyond the traditional challenge fund structure. These modifications were incorporated into the revised ToC as part of the 2016 cost extension of the programme. The revised ToC was aligned with the “human-centric approach” to innovation programming, which focuses on supporting the development of the innovation ecosystem and using challenge funds as an incentive for it.
In line with the alterations in the ToC, the logframe of the HDIF saw several major changes, as explained in the Review:
- In June 2014, the outcome statement of the programme was expanded to focus on assessing the impact on beneficiaries' lives and the innovation ecosystem growth. The HDIF's outputs were also refined to track strategies for strengthening the ecosystem and adopting evidence into policy and practice.
- In 2014 and 2015, the HDIF revised its ToC and high-level results to adopt the Principle of Acceleration and increase indicator targets. A “Super Impact” result statement was developed, and the impact result statement was extended and supported by new indicators. The outcome statement was divided into two, as noted above, to assess the acceleration of diffusion of innovation and human development innovation dialogues.
  [note] According to the Review, the Principle of Acceleration Human development was planned to be accelerated by inspiring new innovators, catalysing the diffusion of innovations in Tanzania, and transforming the evidence base to shape policies and practices related to the adoption of innovations in the country.
- In 2017 and 2019, the HDIF refined and redefined its outcome and impact indicators to measure progress more clearly, due to overachievement of annual results. The impact indicator for improved basic services was moved to outcome indicators, output indicators were revised to include institutional capacity building for grantees as well as more ambitious targets for overachieved indicators.
Figure 4. HDIF Theory of Change

Source: HDIF Final Report. 2021
The Review’s overall conclusion was that the HDIF has successfully achieved its outcomes within the timeframe and budget and demonstrated strong value for money and met and exceeded targets of the indicators under the two main programme outcomes.

# Evaluation purpose and methodology

The assignment mainly aims at assessing the outcome level impacts of the HDIF. The focus of the evaluation is the identification and reporting of “key success, best practices and lessons learnt; and evaluate value for money and the impact the programme had on the innovation ecosystem in Tanzania”. The study covered the period from the start of the HDIF in September 2013 to the end in July 2021.
[note] The Terms of Reference of the Evaluation are presented in Annex 1
The evaluation used a mixed-methods approach and took place in three phases: inception, data collection and analysis/reporting. The inception phase included a kick-off meeting, preliminary review of available documents and scoping interviews. In the second phase, both primary and secondary research activities were carried out by the evaluation team. For this purpose, the following methodological instruments were used:
1. Detailed desk research of secondary data and information sources (the main documents reviewed are listed in Annex 2. Key documents consulted.)
2. Semi-structured in-depth interviews with 34 stakeholders and grantees, including brief cases to provide evidence on lessons, challenges, best practices, unexpected outcomes (Figure 5) (interviews with selected grantees were conducted face-to-face through field visits)
3. Online questionnaire surveys completed by 63 stakeholders and grantees (Figure 6)
4. Innovation network analysis carried out using the survey to provide evidence on the impact the HDIF had on the enhancement of innovation ecosystem
5. Value for Money (VfM) analysis conducted using the FCDO’s Framework.
  [note] The following resources and guidance were referred to in the VfM analysis: Better VfM: Framework for Measurement and Management of VfM Indicators, ITAD, 2014; Prosperity Fund Value for Money Approach, WYG, LTSI, Integrity, 2018; Value for Money and Adaptive Programming, ODI Working Paper, March 2021; VfM Guidance: VfM in Education Programmes, FCDO, June 2017; Smart Guide DFID’s Approach to Value for Money, Guidance for External Partners, 2020.

The primary data collection following the inception was carried out between 24 January and 20 February 2023. The cut-off date for document review was 15 February 2023.
The list of interviewees and the evaluation matrix are given in Annex 3. List of interviewees and Annex 4. Evaluation Matrix, respectively.
The evaluation team has developed brief case studies and highlighted main findings around specific issues, such as gender mainstreaming, and presented them in boxes in the following section of this report.
An innovation network analysis was conducted using data obtained from stakeholders and grantees through the online survey implemented as part of this evaluation. It aimed to identify new linkages created among participants of the HDIF activities, as well as the reinforcement of already existing connections with the help of the programme. Survey participants were asked to assess the intensity of their connections, whether strong or weak. Due to the tight timeline of the evaluation, it was not possible to collect additional information about the connections declared by survey respondents. Furthermore, the analysis was limited to organisations for which contact details were provided by the UNDP. Despite these limitations, it provides a good understanding of the innovation ecosystem developed by the programme and could serve as a baseline for monitoring and assessing further developments in the Tanzanian ecosystem. Furthermore, interviews provided valuable input on the ecosystem building aspects of the programme and complemented the ecosystem analysis given in Section 4.3.3.

Figure 5. Interviewees by organisation type	Figure 6. Survey respondents by organisation type
[note] The categorisation uses the HDIF classification in http://hdif-tz.org/wp-content/uploads/2022/10/ApproachPaper_web.pdf considering that it is based on the common terminology used by the HDIF stakeholders.

Source: HDIF impact evaluation. Analysis by INOMER

## Limitations
As the evaluation was conducted approximately 1.5 years after the programme ended, obtaining detailed information, especially regarding VfM, was challenging. As a result of this limitation, accounting data was restricted, and access to VfM annexes in several reports was not possible. Moreover, some of the available documents had incomplete information. Despite extensive efforts put by the UNDP, FCDO and INOMER to locate as much data and information as possible, it is essential to acknowledge this limitation and interpret the results accordingly. In addition, some staff involved in the design and implementation from the programme and donor sides were not available for interviews. Finally, the evaluation had to be conducted in a short time frame. Despite these limitations, with the support of the UNDP and through a rigorous risk management approach implemented by the INOMER team, the study was carried out successfully and the evidence collected has been sufficient for the evaluation of the HDIF in line with the requirements of the TOR.
[note] Main issues were explained as unavailability to locate the files since the change from DFID to FCDO meant that a number of files were lost. Also from Palladium side, the files had not been saved on the company server and had been lost when people left the project as they were in their personal folders.

# Main findings

The triangulated evaluation findings are presented below with sub-sections addressing the evaluation questions.

## Relevance
The evaluation survey findings indicate that the programme's objectives were well aligned with the country's development priorities, as well as the needs and challenges of the innovation ecosystem (Figure 7).
- Over 90% of participants agreed that the programme was adaptable and flexible to address evolving needs and priorities.
- Specifically, 92% of respondents strongly agreed or agreed with the programme's alignment with development priorities, while more than 90% strongly agreed or agreed with its consideration of innovation ecosystem needs and challenges.
- 86% of participants strongly agreed or agreed that the programme was sufficiently adaptive and flexible.

Figure 7. Survey respondents’ assessments of the relevance of the HDIF

Source: HDIF impact evaluation survey. Analysis by INOMER

Interview results are consistent with these findings as explained in the following sub-sections.

### Pertinence to the needs and priorities
The evidence collected under the evaluation indicated that the HDIF corresponded to the overall development priorities and national agenda of Tanzania. According to the stakeholders, the programme filled the funding gap in innovation and ecosystem development in the country, at a time when the only major funding source, the Information Society and ICT Sector Development Project in Tanzania (TANZICT) funded by Finland, came to an end.
[note] https://tanzict.wordpress.com
The stakeholders explained that when the HDIF was initiated, one of the priorities of the Tanzanian Government was to establish innovation hubs. However, funding sources for building capacities of the hubs were limited and were insufficient. COSTECH was also in need of building its capacities on innovation policy design and implementation. The stakeholders believed that the HDIF was of strategic importance to the development journey of Tanzania since it addressed the needs of all actors in the innovation value chain, focused on the sectors essential for addressing societal needs, and had a regional and rural focus, unlike the previous efforts which prioritised the capital and city centres in innovation support.
The interviews with the grantees also confirmed the relevance of the programme for the innovators. It was explained that the programme’s funding and technical assistance helped innovators to develop and implement solutions to address the societal needs and challenges through collaboration, as also underlined in national policies, plans and strategies, such as the National Development Vision 2025 and Five-Year National Development Plans.
The pertinence of the HDIF to the needs of the innovators were also evidenced by the interviews as they mainly lacked funding opportunities for their projects, faced difficulties in access to markets, needed capacities and technical expertise to put ideas into practice. The interviewees believed that the programme helped the development or adaption of innovations according to the local conditions in alignment with the actual needs of the end beneficiaries and ecosystem actors.

### Adaptability and flexibility

Interviews indicated that the programme had a difficult inception phase due to operational issues mainly stemming from the misalignment between the original Business Case and the Tanzanian context as explained in Section 5.2.1. The recognition of this issue at an early stage resulted in the modification of the design and adaptation of the HDIF according to the local conditions. The programme management, together with the FCDO, updated the ToC (as also explained in Section 4.2.2), based on the lessons learnt with the ultimate goal of effectively supporting innovation activities in Tanzania and improving the delivery approach, not only by providing finance but also offering capacity building and facilitating collaboration among the actors in the ecosystem.
From the perspective of the stakeholders and grantees, adaptability and flexibility were notable positive features of the HDIF (see Box 2). The stakeholders believed that it was thanks to this adaptability that the HDIF, a programme which was regarded as unsuccessful at the initial years, was turned into a success. The stakeholders mentioned, for example that, as a result of the lessons learnt and shared by different actors about the necessity of supporting incubators, the final round of grants focused on incubators. Other examples of adaptability were explained as supporting early-stage entrepreneurs through capacity building and networking with enablers, and partnering with hubs and extending the non-financial support to the regions through parallel events of the Innovation Week in the second half of the programme. Adaptability was also observed in answering the changing needs at the policy-making level. The stakeholders explained that the HDIF was able to respond to the expectations of COSTECH in supporting its activities and increasing collaboration with the decision-makers.
The stakeholders also experienced positive response to their needs during COVID-19 when new working approaches required to be adopted. The programme used unspent funds to finance projects responding to the pandemic-related challenges.
On the other hand, the lack of adaptability of the programme in terms of the types of financial instruments used was expressed as a weakness in the interviews. As also specified in Section 4.3.2, the programme's sole provision of grants has led to a situation where the grantees have become overly reliant on this form of finance, impeding their capacity to attain sustainability and maximise the potential impact of their projects.

Box 2. Adaptability of the HDIF for grantees / According to the grantees interviewed, the HDIF was agile and adaptive to the changes not only in needs but also in context and conditions. It was also explained that the programme management team was open to learning from experience and embraced the uncertainties involved in the innovation process. As such, projects were allowed to be modified flexibly according to the emerging issues, changing conditions and unforeseen challenges. / One of the grantees explained, for instance, that, in 2017, the changes in the laws and regulations governing water management altered the structure of the entities in charge. For example, the Community Owned Water Supply Organizations (COWSO) was transformed into Community-Based Water Supply Organizations (CBWSO) to bring more transparency into the management of water resources. These changes required engaging a broader group of stakeholders in the project, and their buy-in became important to ensure continuity of the project funded under the HDIF. To address this emerging need, the programme offered the grantee the flexibility to work with the new structures and train their staff on the innovation. / The grantees had emphasised that the HDIF was adaptable to changes in scope and budget, taking into account new and actual requirements that may arise during project implementation. An example of this flexibility was seen in the Menstrual Hygiene Management project of the organization Dorcas. During implementation, it was identified that approximately 20% of the target community, who were semi-nomadic and pastoral, needed special attention due to their lack of permanent housing, which limited their ability to practice good hygiene. As a result, the HDIF expanded its support by providing additional funding for latrines and raising awareness of the importance of hygiene. This ultimately led to an improvement in the project's impact, demonstrating the programme's ability to adapt and respond to the needs of the communities it served. Similarly, a grant recipient (Sense International) expressed that community support played a pivotal role in the success of their project that focused on innovating disability learning. This required the involvement of higher number of staff in the project activities at the community level. The HDIF has been receptive and supportive to this need. / The HDIF demonstrated its responsiveness to reduction in scope as well as to achieve quality assurance. An example was the Gongali Model Co's project where the company originally intended to install its innovative water purification system at 1,000 distribution centres. However, as it reached around 200 centres, it became apparent that not all distribution centres would follow guidelines for installation and use, posing sanitation risks and damaging the product's brand. To address these issues, the innovator proposed a radical change in the business model, that involved developing smart kiosks for water delivery to be deployed in 100 locations. Despite increased production costs and a drastic reduction of the number of locations, the result was increased water quality, improved monitoring capabilities, and a similar final customer reach compared to the original model. / The grantees also benefited from the programme’s agility and flexibility during COVID-19 when new working approaches had to be adopted. As exemplified by a grantee, this included funding for the acquisition of IT infrastructure to ensure adoption of remote working modalities.

## Effectiveness and efficiency:
The evaluation survey results indicate that the HDIF was efficient in addressing risks and challenges during implementation, with 81% of participants indicating that the programme was effective in this regard. In addition, the majority of respondents (77%) strongly agreed or agreed that the programme achieved coherence and synergies with similar programmes and projects in Tanzania, highlighting its efficiency in leveraging existing resources and partnerships to drive sustainable development (Figure 8).

Figure 8. Survey respondents’ assessments of the HDIF’s efficiency

Source: HDIF impact evaluation survey. Analysis by INOMER

The survey findings also demonstrate that the HDIF was effective in achieving its intended goals and objectives, with a significant proportion of respondents (72%) strongly agreeing or agreeing with this view, as indicated in Figure 9. Furthermore,
- 66% of survey participants expressed strong agreement or agreement that the programme successfully addressed the basic service needs of the local population, highlighting its effectiveness in driving sustainable development.
- 65% of respondents strongly agreed or agreed that the programme had met the requirements of underrepresented groups, further underscoring its effectiveness in promoting inclusivity and equity (also see Box 4).

Figure 9. Survey respondents’ assessments of the HDIF’s effectiveness

Source: HDIF impact evaluation survey. Analysis by INOMER

Detailed findings from interviews and documents on efficiency and effectiveness are given in the following sub-sections.

### Design and planning
A review of the programme documents indicates that the HDIF’s design was based on an analysis of national and international data and information sources to identify the needs and priorities. On the other hand, according to the interviews, the initial design did not sufficiently include the stakeholders and target groups. The design process did not assess the capacities and needs of target groups and potential beneficiaries either using effective and participatory tools and techniques, including a wide stakeholder consultation when developing the Business Case.
The main focus of the programme at the design was on the “private sector engagement for improving service delivery”. However, the programme was risk-averse and as a result, it targeted projects with high probability of success. It also prioritised beneficiaries with a capacity to manage operational and financial aspects of grants based on a set of obligations imposed for the grantees in terms of financial management and reporting, which could not be fulfilled by small businesses and start-ups. Added to this was the high project budget requirements (up to £400,000 and £3 million, respectively, for the first and second window) which limited the access of the private sector, and notably start-ups, to the programme. Consequently, the programme primarily funded mature organisations and particularly national and international NGOs (see Section 4.3.2). Main design issues of the programme are summarised in Box 3 below.

Box 3. Design challenges in the HDIF / The main challenges facing the programme in achieving its goals stem from a disconnect between commercial viability and social impact. As explained in the interviews, since the programme focused on innovations with social impact, it ended up partnering with NGOs that had innovative solutions lacking commercial viability. Conversely, commercially viable innovations lacked social impact. According to the stakeholders interviewed, the programme tended to fund the same established organisations, creating challenges in funding young and smaller innovators since it was not geared up for preparing start-ups for investment. / Opinions on the use of grants to work with NGOs were divided among interviewees. While some considered grants appropriate for non-profits, others felt that the programme was unable to overcome limitations inherent in its financial instrument and risked the sustainability of the project results. Several interviewees explained that this situation resulted in grant-dependency among the beneficiaries hindering their focus and ability to achieve sustainability and make a bigger impact with their projects. According to an interviewee, this situation led to the emergence of 'grant-preneurs' who prioritise chasing grants over ensuring the growth of their projects. / The interviews also revealed that there was a mismatch between the expectations of policy-makers and the programme’s objectives. The interviewees stated that the government’s priority was to support grassroot innovators and local social entrepreneurs who had innovative ideas but lacked capacities and funding. However, the programme did not have such an objective, possibly due to insufficient communication and consultation with the government during the design phase.

In the later stages, recognising the issue of not being able to attract the private sector to the programme, the HDIF management made efforts to achieve the engagement particularly with the digital sector. The HDIF designed various interventions including Innovation Challenges, such as Mawazo Challenge, COVID19 Response Challenge, Recovery & Resilience Innovation Challenge, to reach the early-stage innovators who were outside the HDIF scope. These efforts also included the inception of the Innovation Week. Interviewees explained that despite its efforts, the HDIF has had limited success in supporting start-ups.

### Management and goal attainment

On the programme management side, the HDIF was initiated under the responsibility of two teams: Palladium as the technical team and KPMG as the team in charge of grant management. Acknowledging the management challenges created by this situation, the KPMG team was merged with Palladium. Over time, the HDIF team developed a culture and identify as an independent fund management organisation, and did not consider itself as a consultancy firm, according to the interviews. The ownership of the team was important for successful management of the programme and establishing strong relations with the external stakeholders, as also evidenced by the feedback provided by the programme participants, including the grantees.
The stakeholders explained that the donor and programme management were proactive in identifying the design constraints and limitations in the operating environment and therefore modified the design based on the lessons learnt. They were also successful in communicating the lessons and collaborating with both the government and innovators, and created an environment and opportunities for cross-learning among ecosystem actors to improve the design and implementation the programme. The stakeholders noted that the ability of the HDIF in bringing together donors, development partners, government and innovators to address societal challenges through innovative solutions was a notable achievement. In addition, the grantees stated that they received assistance from the Partnership Manager of the HDIF for accessing and communicating with other stakeholders, such as the government entities. These features of the programme have contributed to the creation of new connections and reinforcement of existing linkages between the ecosystem actors, as also explained in Section 4.3.3.
A weakness in the implementation process that could have been mitigated during the design phase pertained to the development of technical skills and expertise within the hubs. Stakeholders interviewed suggested that more resources could have been allocated and a more precise identification of the skills and capabilities that the hubs should offer to innovators was necessary. To achieve this, a comprehensive skills mapping and needs analysis should have been undertaken during the design and inception phase of the programme.
According to the interviews with the grantees, the improved programme management structure of the HDIF included a relationship manager and a focal point to reach out and receive answers to questions and guidance in the implementation of their projects. It was also mentioned by the interviewees that the HDIF management effectively used the revamped logframe to guide the planning, implementation and monitoring and improvement of the programme.
According to the interviewees, overall, the programme had a favourable and adaptable management system that encouraged collaboration. The management was receptive to feedback and willing to provide additional support, both technical assistance and funding, based on the results of project implementation. The grantees mentioned that the management addressed the implementation issues instantly and constructively. Overall, operational processes were considered smooth and efficient by the grantees as they were assigned with a focal point to communicate their needs and issues.
The programme management put in place an online system to receive grant applications. However, this system did not encompass the remaining stages of the grant management process. Reporting was done using templates provided separately. While some grantees found reporting obligations as cumbersome, the others believed that the reporting process was clear and user-friendly, with easily adaptable templates. Some grantees interviewed stated that the programme management allowed them to use their own reporting system provided that the information needed for donor reporting was retained. They explained that the management was flexible and collaborative in financial reporting and this helped increasing the efficiency.
Although the majority of interviewees deemed the programme effective and efficient, some grantees found it complicated to make alterations to their projects. Specifically, they reported that there were numerous budget modifications that were time-consuming and took away from actual implementation of the projects. Furthermore, some grantees and especially start-ups found the procurement processes complicated and difficult to implement.
According to the interviews, programme monitoring and evaluation was under-invested. It was explained that overall, the programme team was missing the capacity for understanding and implementing results frameworks and logframes, as well as conducting validation and coaching grantees. On the other hand, the internal and external stakeholders consider the risk management framework and approach of the HDIF successful. Linked with the high expectations of the donor for effective management of risks, existence of a rigorous risk management was evidenced both by the interviews and the survey.
The evaluation found that the VfM focus of the donor and high-performance expectation of Palladium put the internal management under pressure and led to the development of an organisation culture that solely focused on performance. Both this and the lack of a gender safeguarding policy at the early stages of the programme created a difficult environment for female staff of the programme management team. This was further influenced by the Tanzanian patriarchal culture, according to the interviews. At the later stages of the programme, the FCDO introduced a gender safeguarding policy which partly addressed the issue.
The interviewees agreed that the programme was unique in Tanzania in the sense that it offered funding for innovations, helped the development of institutional capabilities at policy, programme and project levels and reinforced the innovation ecosystem. The HDIF took over secretariat of already existing Development Partner Group on Science Technology and Innovation. The group’s objectives were to share experiences of other donor-funded projects and identify and pursue collaboration opportunities.
The evaluation found that the main strengths of the programme, after the improvement of the ToC and logframes, included effective communication and coordination between programme management and participants. As per the feedback received from the grantees, the management team's accessibility and constructive attitude were notable attributes of the programme, fostering a partnership relationship between the parties rather than a funder-beneficiary dynamic. Several grantees highlighted that the management team was friendly, flexible and approachable. The team was also commended for their smooth and participatory operational processes, which were perceived as beneficial to the grantees.
The grant recipients also noted the positive evolution in the management approach, as lessons were documented and the programme and projects were adjusted to local conditions. Creating mutual learning and knowledge and experience sharing platforms was also recognised as a positive aspect, with the Innovation Week being cited as a particular strength in this regard. Furthermore, the constructive feedback given to unsuccessful proposals has aided certain applicants in enhancing their proposal writing skills. A grantee, whose project initially failed to secure funding in the first round, was selected in the second round after improving it according to the comments received from evaluators.
On the other hand, certain programme participants have raised a concern regarding the provision of progressive funding to successful grantees for further scaling up of their innovations. They believed that this approach places undue pressure on the innovators and restricts the opportunities for other innovators who encounter challenges in accessing finance.
Box 4. Gender mainstreaming and inclusiveness in the HDIF / According to the interviews, gender mainstreaming was not prominent in the programme implementation at the early stages. While the HDIF Business Case makes an emphasis on “approaching innovation through a gender lens” in the programme “to maximise opportunities for utilisation of new technologies and approaches to improve the lives of girls and women”, gender mainstreaming was not prioritised or supported by adequate tools in the early years. The stakeholders interviewed stated that the programme adopted a gender lens across its activities starting from the second year. This was made possible in large part due to the development of a knowledge product on how to incorporate a gender lens early in the innovation process. The publication was highly regarded and considered a main reference in Tanzania. / The grantees confirmed that during the second half of the programme, there was a notable increase in attention and targeting of female-led innovation and female grantees. While gender was not at the centre of many grantees' works, the programme retroactively implemented a gender strategy, requiring grantees to have a gender focus. Interviewees explained that with this new gender-focused approach, the HDIF began to highlight and profile female innovators, and some became the faces of female innovation in Tanzania. / Most of the HDIF's activities focused on youth due to the context of the country, which resulted in their inclusion being possible. For example, the programme supported various innovation competitions such as the Mawazo Challenge, which was created to support innovative project ideas and solutions for problems in the health sector by building the capacity of students in health and allied sciences universities across Tanzania. The competition received 30 innovative ideas, and 10 winners were selected and provided with seed funding and mentorship to help them produce viable pilots of their ideas. The awardees also received continued support from the partners of the challenge after the competition ended. HDIF was also involved in other innovation competitions, such as the Shule Direct Digital-Learners competition, Apps & Girls competition, Jenga Hub competition, and She Codes competition, through grants or other forms of support and collaboration. / On the other hand, interviews found that the programme did not have a specific strategy to target other vulnerable groups, and initiatives specifically designed for disabled or indigenous peoples were limited. Nevertheless, some projects were able to extend their reach to disadvantaged communities, such as the case of a WASH project that aimed to improve menstrual hygiene in an area where indigenous communities were present. To work with these communities, the project requested a costed extension, which was ultimately approved.

## Impact and sustainability:

Based on the survey results,
- A significant proportion of respondents agreed that the HDIF had a positive impact on the Tanzanian innovation ecosystem, with 84% strongly agreeing or agreeing (also see Section 4.3.3).
- 75% of respondents strongly agreed or agreed that the programme contributed to the country's long-term development goals through innovation.
- 69% believed that the HDIF successfully achieved its intended outcomes and had an impact on the targeted areas of health, education and WASH (Figure 10).
Figure 10. Survey respondents’ assessments of the HDIF’s impact

Source: INOMER Evaluation, 2023

The survey findings on the sustainability of the HDIF's outcomes demonstrate that a majority of stakeholders believe the programme has made significant contributions to the development of skills and capacities among ecosystem actors, including the ability to design and implement innovation policies and measures (Figure 11). In addition,
- 82% of survey respondents strongly agreed or agreed that the lessons learned, best practices, and experiences from the program are transferable to similar programmes in other countries.
- 56% of respondents strongly agreed or agreed that the innovations developed under the HDIF can be sustained in Tanzania.
- 45% strongly agreed or agreed that they can be sustained in other countries within the region where they were implemented. However, 24% stated that they had no opinion on the matter.

Figure 11. Survey respondents’ assessments of the HDIF’s sustainability

Source: INOMER Evaluation, 2023

Findings from interviews and document review are elaborated in the following sub-sections.
### Achieving intended outcomes and impact in selected sectors

According to stakeholders, with the improvement of the selection criteria over multiple funding rounds, the programme generated a stronger portfolio of innovations that reflected the realities of different sectors. The portfolio was rebalanced based on the actual sectoral context, with less innovative and sustainable solutions accepted in WASH, while focusing on community-driven solutions and replicability instead of financial viability. Innovators were also supported in commercialising their products, and the capacity building component was valuable in stimulating the ecosystem to come up with solutions. Furthermore, it increased its focus on innovations in the health sector. The interviewees stated that an ongoing dialogue with the FCDO was necessary during the process, and that the donor displayed a flexible and constructive approach in effecting necessary adjustments.
It was explained that the funding of innovative healthcare projects had a notable impact, especially for the government. The work was transformative, leading government officials to acknowledge the potential for innovation in Tanzania. For example, the HDIF helped to aggregate data and improve the management of healthcare facilities such as Comprehensive Community Based Rehabilitation in Tanzania (CCBRT), resulting in its recognition as a model for improving healthcare. By providing support and expertise, the programme helped to shorten the learning curve for managing such facilities.
With respect to the direct impact on human development, there were good examples, such as the transformative Ubongo Kids and CicoCell innovation in WASH pre-paid technology. The collaboration between the private and public sectors proved to be highly effective in implementing prepaid healthcare technologies, and the results were particularly noteworthy in the success of Ubongo Kids, which exceeded initial expectations by reaching a significantly greater number of households.
Another example highlighted was the WASH project implemented by Dorcas that had a focus on menstrual hygiene, with efforts to strengthen the value chains of female pads production to create income-generating opportunities for communities. By promoting artisanal production, the project provided access to these essential products to individuals with the lowest income and built connections between established manufacturing enterprises and local producers and distributors.

### Benefits of the programme and their sustainability

The evaluation found that the impact of the HDIF was diverse, exhibiting varying degrees of effectiveness and sustainability. According to the stakeholders, the primary benefit of the HDIF is that is has effectively created awareness of the importance of innovation in Tanzania by promoting innovation through knowledge products, facilitating engagement with multiple development partners, and creating spaces for dialogue and exchange. They also believed that the programme accelerated engagement with policymakers, and established synergies with other development partners and similar programmes, thereby contributing to the development of the country's innovation ecosystem (also see Section 4.3.3). Linked with this result, the government has acknowledged the significance of fostering innovation and recognised the imperative to provide support and establish an environment conducive to innovation. Also, the HDIF generated interest among various stakeholders, including development partners and government officials, in supporting innovation start-ups and small and medium-sized enterprises (SMEs).
According to the grantees interviewed, the programme provided valuable capacity building in project and performance management and technical assistance skills. A grantee also explained that thanks to the support they received under the HDIF, they secured additional grants in collaboration with other partners. Grantees interviewed stated they were equipped with the necessary skills to drive their innovation across the product cycle, and these skills were expected to remain within the ecosystem for a longer period. Additionally, the programme also encouraged alignment with the Principles of Digital Development with case studies demonstrating the successful application of them, resulting in the use of these principles in shaping innovation content. A grantee also noted that the programme also fostered a culture of collaboration and partnership among private sector actors, leading to increased interaction and collaboration between NGOs and private sector entities through which certain NGOs adopted private sector methodologies to enhance the effectiveness of their solutions.
Nonetheless, interviews also indicated that numerous grantees that were from a non-profit background, pursued grants while neglecting to prioritise their Minimum Viable Product (MVP) development and sales strategy. While this phenomenon was not exclusive to the HDIF, but rather a prevalent issue in the overall ecosystem, where innovation heavily relies on donor funding, it risked the impact and sustainability of the programme.
As also noted previously, the programme's original Business Case aimed to support the private sector, but this goal was not achieved both due to the fund’s conditions and a limited number of private sector start-ups and their questionable sustainability. One of the most successful grantees even pivoted from business to NGO. Additionally, the HDIF's focus on working with NGOs and government limited its impact on the business sector, presenting challenges for long-term sustainability. The objective of addressing funding gaps in start-ups was also not met, as many transitioning from early stage to growth were dissatisfied with the model due to its conditions and requirements.
Nevertheless, certain grantees interviewed explained that the programme helped create a favourable environment for the private sector. According to the interviewees, currently, the private sector plays a role in driving the innovation ecosystem, working closely with the public sector.
In addition, the efforts to establish and reinforce hubs played a role in the development of start-up accelerators supported by corporate partners, such as Vodacom. According to the interviews, in spite of these efforts, the programme's impact on the creation of sustainable start-ups has been limited, resulting in a low number of jobs generated by them.
The HDIF’s impact on the development of hubs has been notable. The interviewees mentioned that while at the beginning of the programme, there were only a few hubs, the number has grown to over 60 during HDIF implementation. The capacities developed and services standardised in the hubs with the programme are seen as important measures for sustainability. One of the strategies of the HDIF was, for instance, to encourage hubs to conduct innovation challenges which were financed by the programme and helped build capabilities in managing similar initiatives. One example of such challenges was the hackathon and skills development programme organised by Sahara Ventures for medical students (Mawazo Challenge). This event also included a bootcamp and provided access to seed funding and an acceleration programme for participants.
Furthermore, in 2020, the HDIF and COSTECH through their shared aim of fostering a stronger innovation ecosystem, convened 13 innovation hubs, business incubators, labs and co-working spaces, building their capacity to enable a stronger innovation ecosystem in Tanzania. This led to the formation of the Tanzania Hubs Network. During the 2021 Innovation week, the Tanzania Hubs Network organised and hosted its own parallel events.
[note] Project Completion Review, FCDO, August 2021
The HDIF has also established connections with East African hubs to share knowledge and experiences. Despite these efforts, some interviewees remain doubtful about the quality of services provided by the hubs stating that their curricula, trainers, and activities exhibit significant variability. Furthermore, existing hubs have limited capabilities to cater to the diverse growth stages of start-ups. Although it was not a mandate of the programme, there were missed opportunities regarding the establishment of a viable and sustainable business model for the hubs, according to interviews.
At the grantee level, the HDIF addressed a gap in funding for innovation, as very few funders offer non-restrictive grants. The combination of financial support and technical assistance proved critical to the success of the projects funded. Although grants required project owners to report on their progress and promoting accountability, it was not a sustainable solution as it led to grant dependency. As a result, the effectiveness of grants has been hindered by a dependency mindset among the recipients. The interviewees found that, to address this issue, Switzerland tries the “Synchronized Collaboration” approach, which involves a contribution from the grantee and additional funding upon achievement of specific goals.
The interviewees were unable to establish a direct correlation between the knowledge products developed by the programme (such as the policy briefs) and their impact on policies or regulations. However, they expressed that the policy dialogues, knowledge sharing during events, such as those organised under the Innovation Week, and other similar initiatives of the HDIF have led to advancements in innovation policy-making in some sectors, notably ICT. The programme supported the development of guidelines for digital learning content in collaboration with the Tanzania Institute of Education. The government also developed its own digital learning content, which some view as duplication of efforts.
The stakeholders believed that requiring supported projects to remain active for one year after their completion was a measure of sustainability for the programme. Also, the project implemented by Dorcas to support WASH through a menstrual hygiene initiative is seen by the stakeholders as a successful pilot initiative with sustainability prospects. Its effectiveness suggests that it could be replicated in other countries in the region, such as South Sudan, with support from Dorcas’ local offices. Dorcas Tanzania is currently advising on these new projects. This project also piloted the 'outcome management methodology', which aims to facilitate behavioural change.
According to the interviews, the lessons learnt by the programme underscore the importance of building a strong innovation ecosystem, adapting to changing contexts, and collaborating across sectors. The stakeholders believe that the HDIF achieved notable impact through the innovation projects it financed. Unlike a traditional challenge fund, the programme also provided support for capacity building and project management, and the flexibility and openness of the FCDO allowed it to take risks and experiment with new approaches.
The stakeholders consider that the programme has had a positive impact on the improvement of GII of Tanzania. While it is difficult to measure the impact at that level, taking into account the program's effects at the ecosystem level, as well as its financial allocation within the country's context, it is plausible that the HDIF has made a contribution towards achieving this result.
### Impact of the HDIF on the innovation ecosystem in Tanzania
The evaluation found that the HDIF has been impactful in enhancing the Tanzanian innovation ecosystem. The stakeholders believed that one of the most successful aspects of the programme has been the connections forged within the ecosystem through various initiatives, such as the Innovation Week that provided a platform for numerous partners to interact and collaborate since it was launched in 2015 (see Box 5).

Box 5. The Innovation Week as an ecosystem building platform / Both the stakeholders and grantees often cited the Innovation Week as a facilitator for creating and expanding linkages among stakeholders and grantees in the Tanzanian innovation ecosystem. For the organisations with projects funded by the programme, the event provided a platform to network, access additional funding opportunities, and learn from the experiences of others operating in different sectors. For the other stakeholders it was a platform to learn about various organizations' activities, exchange ideas, and initiate collaborations on innovation matters. The programme management also benefited from the event as it offered them with an opportunity to share information about the funded projects, exchange experiences and lessons, demonstrate how the activities were contributing to the programme's goals and share the annual knowledge products. In addition to showcasing innovations, the event was used as a platform to discuss challenges and propose policy solutions. / The Innovation Week also promoted inclusiveness by engaging youth in its activities. Through the event, youth were given a platform to showcase their innovative solutions, connect with potential partners and investors, and take part in various competitions and challenges. A key objective of the Innovation Week was to curate promising organisations like TAI, which was started by a group of university friends to help young people lead development projects in their community, and to provide them with networking and learning opportunities. In addition, the Innovation Week presented awards to the winners of the competitions and challenges, recognizing their achievements. Moreover, in partnership with MagilaTech and VETA, COSTECH organised an event to present V-SOMO, a mobile learning platform that specifically caters to young people pursuing vocational training. / The Innovation Week was initially funded by the HDIF, but it later attracted funding from other sources. By 2022, it received financial contributions from more than 20 public and private organisations and development partners, growing into a flagship activity. In 2021, the event had 7,500 attendees. By the end of the HDIF, COSTECH took over its management to ensure its sustainability. The stakeholders view this as an important step in demonstrating government ownership of innovation, as donor-funded activities typically disappear once the programme ends. However, some interviewees are concerned that resource scarcity and capacity challenges within COSTECH, due to high staff turnover rates, could pose constraints in successfully organising the event.

According to the interviews, the selection criteria for grants have also played a role in building connections among various actors since there was a requirement for establishing partnership with other organisations. For example, one application was initially rejected because it was not being implemented as a partnership, but in the second round, after a collaboration was established, the project was accepted.
The HDIF’s collaboration with COSTECH was also instrumental in enhancing the ecosystem. The capacity-building grant approved by the FCDO enabled COSTECH to develop the necessary staff and budget to implement ecosystem development activities. COSTECH’s involvement in the programme also included participation in priority setting and project selection. By the end of the HDIF, the Innovation Week was passed over to COSTECH. However, some interviews highlighted that COSTECH faces internal capability challenges mainly due to high staff turnover, which could limit the effectiveness of capacity-building efforts and raise questions about the resource availability and sustainability of the Innovation Week.
According to the grantees, by creating a dynamic innovation ecosystem, the programme exceeded its goals and objectives as it helped advance policies and regulations in several areas, such as digital content learning. The ecosystem development efforts have also helped them showcase their innovations both within and outside the country and establish linkages with the government. As a result, they have developed confidence in themselves and their innovations.
The interviews conducted revealed that increased interaction and cooperation among players led to the creation of political awareness about the significance of innovation for the country's development. Consequently, the government adopted innovative ideas (such as the implementation of Standard Operating Procedures in the healthcare sector) for scaling up and making them available for public use.
According to the interviews, the programme had another significant contribution in fostering a culture of consultation in policy-making as well as public-private partnership in ecosystem development (see Box 6). For instance, the work on draft Start-up Bill involved consultation with start-ups, and the Ministry of Information and Communications is now engaged in dialog with them. Moreover, the programme helped the National Advancement of Technology Fund (NFAST), established in 1986 and managed by the COSTECH, to enhance its fund management practices. COSTECH also awarded at least one round of funding through NFAST with HDIF funds, as a result of which the capacity and practise of the fund was also built and an innovation window was established (NFAST-I).

Box 6. Public-Private Partnership for Innovation Ecosystem Development / In 2018, the HDIF team introduced the Innovation Week to Vodacom Tanzania executives, which led to the development of a strategic partnership with the company. Starting in 2019, Vodacom not only became one of the main sponsors of the event but also an active partner by hosting multiple events during each Innovation Week. These events included discussions and webinars on Connected Agriculture and digitisation in the health sector, sessions with financial institutions on fin-tech, launching E-Fahamu, an education platform, and organising a series of general sessions on the opportunities and challenges of innovation in Tanzania, while identifying collaboration prospects. / In partnership with Smart Lab, a local innovation platform, Vodacom Tanzania launched the “Vodacom Digital Accelerator” startup accelerator programme in 2019. The programme aims to support early-stage and growth-stage technology startups in achieving profitability, focusing on sectors such as mobile, telecom, fin-tech, media, health, education, and e-commerce. Through expert training, mentorship, technical support, and funding, the accelerator empowers startup founders to grow their businesses and generate revenue. Vodacom’s initiative was highlighted in the Ministry of Education, Science and Technology's Draft National Innovation Framework of August 2022 as an example of a private sector intervention that fosters the growth of urban innovators and ensures their solutions reach the market. During the 2022 Innovation Week, the government endorsed Vodacom Tanzania’s health sector innovations and their provision of key data.

As explained by several stakeholders, while the connections within the innovation ecosystem appear to be sustainable, there is a decline in the extent to which innovation actors collaborate with one another. Furthermore, hubs tend to operate in isolation or silos rather than functioning as a network to facilitate stronger collaboration among players. Additionally, one interviewee noted that the programme’s initiatives to foster ecosystem linkages resulted in the emergence of a group of individuals who are well-known in the ecosystem and serve as “gatekeepers”. These individuals have a strategic advantage by being part of a tightly-knit network of partners that have worked together for a significant period of time. However, for new actors, gaining access and establishing relationships within this network presents a challenge.
Interviews also indicated that the HDIF played an important role in expanding the innovation ecosystem to include development partners by serving as the Secretariat of the “Development Partner Group on STI”. The purpose of the group was to share information on the projects implemented by different partners and identify opportunities for collaboration. Some of the activities implemented included mapping partner’s activities in the area of innovation, sharing lessons learnt with the programme and organising “Hub Tours” to showcase various hubs, incubators, and accelerators.
Figure 12 provides a visual representation of the linkages formed through the HDIF, based on data gathered from a survey conducted for this evaluation. The survey aimed to identify new linkages created and strengthened among stakeholders and grantees, with participants assessing the intensity of these connections as either strong or weak. The survey findings corroborated the results of interviews, confirming that the programme effectively reinforced the innovation ecosystem in the country.
[note] It is important to note that due to the tight timeline of the evaluation, it was not possible to collect more information about the connections declared by the survey respondents. Furthermore, the analysis is restricted with the organisations, contact information of which was provided by the UNDP. Nonetheless, the findings provide a valuable snapshot of the networks that have been created or strengthened through the programme, as also confirmed by the interview participants. The results can also serve as a baseline for monitoring and evaluating the continued development of the linkages in Tanzania, particularly for future programmes, notably for FUNGUO.
The innovation network map depicted in the figure illustrates the linkages among 86 organizations in the system, names and contact information of which were provided by the UNDP, representing various types of entities. The most active actors in the ecosystem, as expected, have been the “enablers” (incubators, hubs, etc.), having established linkages with 21% of all organisations in the ecosystem (Table 2). National non-governmental/civil society organizations have also been active players in the innovation ecosystem, with connections created or strengthened with 17% of the organizations covered by the study. Both government entities and international organizations have demonstrated a high level of activity in the ecosystem, despite their low representation among all entities covered by the research.
The data from the innovation network map presented in the figure shows that while universities and research institutes have connections with funders/donors, they have created limited linkages with other entities in the innovation ecosystem. Compared to other organisation types, this group of stakeholders also has the lowest number of strong linkages with other actors. These results indicate the need for enhancing the research-innovation interaction and collaboration, which is essential for the transfer of knowledge and technology from academia to the economy and society.
Table 2. Distribution of organisations in the innovation ecosystem based on linkage intensity
Organisation type	Breakdown of organisation types covered by the analysis (%)	Breakdown of linkages established by organisation type (%)
Academia (Universities/Research institutes)	6%	6%
Enablers (incubators, hubs, etc.)	26%	21%
Funders/donors	9%	10%
Government	2%	7%
Industry (national and multinational businesses, and start-ups)	12%	15%
International non-governmental/civil society organisations	20%	13%
International/multilateral organisations	6%	11%
National non-governmental/civil society organisations	20%	17%

Source: INOMER SNA survey and analysis.

Finally, it is also important to note that COVID-19 might have a negative impact on the further development of innovation networks during the last two years of the programme. Both the COSTECH’s “Hub of Hubs” strategy that was developed in 2019, and the HDIF’s and COSTECH’s increased efforts for strengthening linkages in 2020 fall into the pandemic period. Despite the expectation that connections among ecosystem actors would continue to grow with these additional efforts, the pandemic might negatively impact the generation of new connections and the forging of existing ones between various actors.
[note] According to the Project Completion Review, “HDIF carried two studies on innovation hubs in 2017 and 2018 which informed and enabled development of COSTECH’s ‘Hub of Hubs’ strategy in 2019. In 2020 HDIF and COSTECH through their shared aim of fostering a stronger innovation ecosystem, convened 13 innovation hubs, business incubators, labs and co-working spaces, building their capacity to enable a stronger innovation ecosystem in Tanzania. This led to the formation of the Tanzania Hubs Network. During the 2021 Innovation week the Tanzania Hubs Network successfully organised and hosted their own parallel events”.
[note] For example, the evaluation of the UNESCO/Sida project on “Strengthening Science Technology and Innovation Systems for Sustainable Development in Africa” conducted by INOMER between September-November 2022 found that the pandemic decreased the level of networking in the ecosystem in Tanzania.

Figure 12. Linkages created or strengthened in the Tanzanian innovation ecosystem with the help of the HDIF Programme

Source: INOMER SNA survey and analysis.

## Value for Money (VfM) analysis

To conduct the VfM analysis, the evaluation team formulated VfM questions and mapped them out to the corresponding “Es” (Economy, Efficiency, Effectiveness, Equity) that they represent (Table 3). The resulting findings have been categorised based on their VfM implications, and discussed in detail below.

Table 3. VfM questions identified for HDIF
Design: Effectiveness	To what extent did HDIF design consider the cost-effectiveness and VfM of its interventions, and global and local evidence base?
Procurement: Economy and Efficiency	How did the programme fare in using competitive processes in procurement to secure the best value for UK Aid investment? / Are there any best practices that emerged from HDIF in terms of grant selection, management and close out processes and risk management?
Implementation: Efficiency and Effectiveness	How efficiently did the programme manage its resources (e.g. funding, staff time, training, etc.) to achieve value for money? / To what extent did the grants achieve their intended outcomes and impact in the areas of health, education, and WASH in Tanzania, and how well did they represent value for money? To what extent were coherence and synergies achieved? / How do the results of HDIF innovations compare to what was anticipated in its economic appraisal and Business Case?
Closure: Effectiveness	To what extent did the closure and handover activities and interventions by HDIF contribute to sustainability and value for money?
Learning: Economy, Efficiency, Effectiveness, Equity	What key lessons (positive and negative) have been learned from HDIF experience with regards to VfM, which can inform the design and implementation of future grant-giving programmes or initiatives?

Source: HDIF Evaluation Inception Report, January 2023

A review of programme documents on the VfM reporting indicated that there was a good effort by the HDIF management to provide several rounds of reporting, based on indicators which often featured targets to allow benchmarking. In addition, the set of indicators was suitable and relevant for the type of modalities that the programme used. However, the evaluation team identified a number of issues in the VfM. Firstly, there were too many indicators to keep track of, which should have brought additional reporting burden to the monitoring, evaluation, and learning (MEL) team. Secondly, at VfM efficiency, effectiveness and equity levels, the indicators mostly duplicated the logframe indicators. It would be advisable to track a smaller set of robust VfM indicators with cost elements, such as cost of outreach. Thirdly, there were some inconsistencies from year to year on the actual reported results, whether it was a number or a percentage or a cost. This has made it difficult for the INOMER team to reach conclusions based on the indicator trends. Finally, the evaluation team did not have access to any detailed financial statements and had only access to readily-made VfM calculations for some of the indicators. More detailed information regarding these topics will be presented below, and recommendations were made in section 5.2.
### VfM Economy

VfM Economy is about competitive procurement of appropriate and high-quality inputs. In order to assess the performance of HDIF in this criterion, the evaluation team used the following sources: HDIF’s own VfM reporting of VfM metrics; FCDO Annual Reviews of HDIF and their VfM sections; interviews with HDIF programme management and FCDO programme management at the time. A number of good VfM practices were also identified and are highlighted below, which were harvested from the interviews.
The economy metrics tracked and reported by HDIF over several years were suitable and relevant for the programme modalities (Table 4). As a grant making programme also using technical assistance, the metrics analysed unit costs of key personnel, other routinely used input costs, share of key cost categories in overall expenditure, and finally cost savings. They also allowed external comparisons to be made, as well as the internal trends, as discussed below. As noted above, the evaluation team may not have all the VfM reports by the HDIF, and did not have any detailed financial expenditure statements, and therefore, the trend analysis is presented with that caveat. Finally, one good practice that was noted on the VfM metrics was the identification of targets by the HDIF themselves to compare to the results. Those targets were either information from other programmes, or the previous HDIF reporting, which provided an adequate context for VfM economy judgments to be made.
[note] It appears that this target setting was done in 2019.
Table 4. Summary of VfM Economy indicators of HDIF
VfM Economy metric	2016/2017	2018/2019	2019-2021*
Realised cost savings (£)	33,578	25,204	118,926
Unit costs in key inputs (includes fees, accommodation, conference venue rates, vehicles, flights, etc.)	Presented by HDIF with comparisons, and the results were deemed fair and reasonable.	Presented by HDIF with comparisons, and the results were deemed fair and reasonable.	Presented by HDIF with comparisons, and the results were deemed fair and reasonable.

Source: HDIF. VfM Reports for 2016-17,2018-19, 2019-2021
*This report was prepared in mid-2021 and it is understood that it reports the period from 2019 to the end of HDIF implementation.

On the management costs, one comparator FCDO-funded programme (East Africa Research and Innovation Hub, EAIRH) was identified by the evaluation team. The EAIRH reported 9% management costs. Similar to the HDIF, the EARIH was managed by a service provider contracted at the outset of the programme, PwC Kenya. The HDIF’s result of 5% is lower. Another programme that provides demand-led technical assistance in Nigeria on infrastructure development (United Kingdom Nigeria Infrastructure Advisory Facility, UKNIAF) reported 25% management fees; however, it reports management and milestone costs together. The HDIF reported total milestone share in total expenditure: 10.2% and 5.3% for management costs, which is around 15.5%.
[note] VfM Review of UK FCDO’s Demand Responsive Research Programmes in East Africa and South Asia’, LAMP Development, 2022, p.21.
[note] Regarding management costs, other known similar programmes such as Africa Technology and Innovation Partnership (ATIP) or Spring Accelerator were also analysed. We could not find information on Devtracker details regarding ATIP, however it is understood from the ATIP Annual Review that one of the programmes funded under ATIP has a Fund manager similar to HDIF (called ‘RISA’ fund). There was also no information on the SPRING Accelerator that was implemented by the same service provider that managed HDIF. SPRING Accelerator was also a challenge fund programme funded by FCDO.
[note] As reported in Programme Key Cost Drivers in the Final VfM Framework, Annex 6 of the HDIF Final Annual Report.
VfM Economy also concerns the quality of financial management. As well as the positive trends on the Economy metrics, the INOMER team found that having a contract featuring milestones (deliverable linked payments) for the programme management contributed to ensuring VfM. Pre-agreed deliverables at bi-annual or annual reporting points were linked to these milestone payments, which were predominantly programme management fee payments. As above, studying the total expenditure reported by HDIF, the milestones were found to be at 10.2% of total costs. This is a VfM measure that is enforced increasingly on the FCDO contracts.
[note] Annex 6 HDIF VfM Framework (spreadsheet), HDIF final Annual Report, 2021.
Further on quality of financial management, all audit reports covering the HDIF gave them a clean bill of health on financial management, all featuring unqualified opinions thereof.
[note] In the 2020/21 audit, there was an issue concerning withholding tax which was escalated and resolved accordingly, as per the PCR, p.16.
Finally, a small number of grants (5 out of 48) had to be terminated under HDIF. There were several reasons behind this action, for instance in one, the concept had not fully matured and in another one, the grantee lacked sufficient experience in service delivery. At each instance, the objective of the HDIF team was to manage a “responsible close out”, especially if some funding was already disbursed. The undisbursed and unused part of those closed grants would go back into the pool of grant funding available for the subsequent rounds. During the initial investment round of the programme, a project that had received one of the largest grants through a "FASTRACK" process was ultimately terminated. Interviews revealed that this project would not have been selected had it gone through the routine project application and selection process that was later implemented.
[note] There are 5 grants overall that were terminated during HDIF. Some were selected for support, but then did not continue with a contract; whereas some had started project implementation, but then were terminated.
[note] Interviewee testimony.
The economy performance of the HDIF was therefore assessed to represent good VfM, using the HDIF metrics, external comparisons and the quality of financial management.
### VfM Efficiency

VfM Efficiency analysis focuses on cost of outputs generated by the programme. However, quality and timeliness of delivery are also important for efficiency.
Table 5 shows the HDIF reporting and trends on efficiency. There are a few more indicators proposed than those covered here, either in the 2016/2017 report, or the latter VfM report. They include the same indicators from the HDIF logframe on the number of events or learning publications etc. which was not included here. They were not technically VfM indicators as they did not include a cost element or targets.

Table 5. Summary of VfM Efficiency indicators of HDIF
VfM Efficiency metric	2016/2017	2018/2019	2019-2021
Management costs as % of total costs	5%	12% (management costs and milestones presented together in the VfM report)	5%
Budget execution rate*	54%	96%	100%
Average speed to process funds requests after the first disbursement (days)	24 days	16 days	Not reported (likely dropped later from the VfM framework)
% of HDIF funded projects that have achieved at least 80% of their output milestones	21%	50%	69% (as per final logframe results. The last VfM report does not include this info).
% of grantees who rate HDIF's assistance, input or collaboration as 6 or better on a 10-point scale	60%	100%	60% (the VfM report does not include this data. However, logframe results as per PCR show 60%)
Average budget per grantee (£)	557,476	31% (reported like this, but should be a number)	N/A (the report does not have this information)

Source: HDIF. VfM Reports for 2016-17,2018-19, 2019-21
*This was presented by the HDIF for all cost categories; however, the overall execution rate at the reporting rate was presented here.

As seen above in the table, it is difficult to judge on VfM Efficiency based only on the metrics used by the HDIF. While the metrics cover the most relevant aspects of efficiency such as management, fund utilisation, output delivery or speed of turnaround, data corresponding to those metrics is patchy. Some of the metrics had targets proposed, but not the value achieved. On the management costs and budget execution (which were later shifted to Economy as per the HDIF reporting) there was a good performance. Further, it should be noted that indicators 4 and 6 above were under VfM Effectiveness in 2016/2017 VfM reporting, and later moved to Efficiency in 2019/2021 reporting. An important efficiency metric here is the percentage of projects achieving minimum 80% of their output milestones. The results show that year on year, this was improved and finally stood at 69%.
The HDIF endeavoured to develop appropriate governance structures and financial management capabilities to support innovators. One example identified was regarding a financial officer at the programme working on grants budgets, who was then moved on to a position which had a larger oversight on the overall finances of the HDIF. The former job equipped the officer with a solid understanding from the grants’ perspective, which was valuable for the latter job.
Another learning was that HDIF management engaged people with relevant sector experiences in the core team, such as one expert with significant experience of working with the Ministry of Health of Tanzania. This helped the team manage the grants more efficiently.
In terms of HDIF’s management quality and communications with grantees, the feedback from the interviews was positive, as also explained in Section 4.2.
Based on the above evidence and findings, VfM Efficiency performance of the HDIF was assessed to represent good VfM.
### VfM Effectiveness and Cost-Effectiveness

An examination of the metrics proposed by the HDIF for tracking VfM Effectiveness indicated that they were actually taken from the logframe indicators at outcome and impact levels. They did not include cost elements either, but were proxy VfM indicators that attempted to provide evidence towards effectiveness through results. The challenge was that some of them were dropped or revised later in VfM reporting, and the targets and result values did not always match, according to the VfM reports available to the INOMER team. However, verifying from the logframe, the evaluation team found that on all three indicators, the HDIF exceeded the targets (Table 6).

Table 6. Summary of VfM Effectiveness indicators of HDIF
VfM Effectiveness metric	2016/2017	2018/2019	2019-2021
Percentage of innovations supported by HDIF that have been adapted within 3 months after grant closeout.		75%	The final logframe results show that the final result was 74% against a target of 60%.
Number of instances in which funders or policy makers across sectors utilize learning generated by HDIF interventions to inform practices and complementary approaches to supporting innovation.		19	A target was given as 6, however no result was seen. As at June 2021, the result was 25 against a target of 17.
Percentage of HDIF supported initiatives that have produced evidence suggesting contribution to improved basic services.	This was counting the number (not %) of initiatives in 2017 reporting, which was given at 6.	58% (as per the VfM report)	A target was given as 20% at the VfM report; however, no result was provided. A cumulative number of 25 such initiatives was reported at HDIF Final Report.
[note] HDIF Final Report, Palladium, 2021, p.18.

Source: HDIF. VfM Reports for 2016-17,2018-19, 2019-21

The HDIF’s Business Case emphasised a two-tier approach for VfM assessment. This approach stipulated that the first tier was the value from the HDIF as a fund and how management of that fund represented VfM. The second tier would be the value derived from individual grants funded by the HDIF. Again, in the Business Case, a case study approach was used, estimating benefits stream from sample grants to be funded by HDIF. The total estimated benefits were presented ex-ante, which outweighed the proposed grant levels (costs), indicating good value for money. The evaluation team, although studied reports from a number of grants on the HDIF website, did not find any case study-based cost benefit analyses that were carried out on any of the grants. A few respondents in the interviews conducted for this evaluation that they conducted cost-benefit analysis before initiating an innovation project and it was confirmed that most grantees submitted basic cost-benefit calculations at application stage to the HDIF. One grantee explained their findings, as shown in Box 7 below. The Fund’s own VfM reporting documents VfM effectiveness to some extent through periodic metrics. However, there was a need to have stronger and more systematic evidence if ex-post economic analyses were carried out on a small set of grants, for example one in each sector that the HDIF supported.
Moreover, as also noted previously, the HDIF grants only produced a small number of startups with sustainable business models, where a majority of grantees were already well-established NGOs. Those cost-benefit analyses may have estimated social impacts; however, often the mechanisms that can provide financial viability and profitability were not always existent. Therefore, it is difficult to assess any impacts such as increased firm profits or job creation that may have occurred, compared to the original thrust of the programme which was strengthening the private sector through supporting innovation as well as delivering human development outcomes.

Box 7. Cost-benefit analysis by a grantee / According to the findings of the interview with the Catholic Relief Services, one of the grantees in the WASH sector, the innovation deployed has improved revenue collection in the water sector from 20% to 182%. The project has not only met but overachieved its objectives. For instance, the pre-paid meter system implemented by CRS in collaboration with HDIF significantly reduced downtime from one to two months to merely a week if troubleshooting or direct technical support was required, and two weeks if on-site assistance was necessary. Furthermore, the revenue collection saw an impressive improvement with actual collections reaching TZS 5 million by the end of the programme. It is worth noting that the pre-paid meter system has also been adopted by the government. The program's impact extends beyond the immediate outcomes, as it successfully introduced new technology and management concepts to the water sector, previously relying mostly on manual processes. / The interviewee further stated that a cost-benefit analysis was conducted for the project which confirmed the viability of the business model. The analysis demonstrated that the cost could be recovered after a certain period. The analysis assumed a cost of $1,500 to purchase a single pre-paid meter system from a manufacturer. When the project ended in 2018, CRS had provided 20 water dispensers. However, during a field visit with the HDIF management three years later in 2021, the rural community raised funds and constructed 10 additional water points, expanding their reach by 20 km, as explained by the grantee. / The interviewee stated that in their case, the manufacturer of the water prepaid system did not have the capability for mass production, resulting in a high unit cost of $1,500. This cost was deemed too expensive and could have hindered the scaling out of the innovation by the two communities throughout the project duration. However, the cost of the system has significantly reduced in the country since the grant, currently costing as low as TZS 100,000 per unit (equivalent to approximately £36), thus making it more affordable.

There was an important metric which was initially in the HDIF VfM reporting; however, it was later removed: “Grantees' matching commitments as a proportion of total value of the grants by HDIF”. In 2016/2017 reporting, this was 32%. This indicator was also not a part of the HDIF final logframe, so the end result is unknown at the time of writing.
While it was not part of the HDIF VfM reporting, the INOMER team was able to calculate cost per beneficiary from the HDIF projects, using cumulative number of beneficiaries as at July 2021 and the total expenditure. The result was £3.17 which potentially represents good value considering the large number of beneficiaries reached (over 12m). Programme reports and stakeholder testimony suggest that there may have been a larger outreach since the program ended in mid-2021, possibly due to spillover effects from some of the grants. For example, Ubongo, a social enterprise operating in children's edutainment and media sector and a successful HDIF grantee, plans to reach 60 million children in Africa by 2025 through 20 new broadcast services in 6 additional countries.
[note] 12,342,997 as per the Programme Completion Review, p.17.
[note] £39,235,658 as per the HDIF VfM report (2019-2021).
[note] HDIF Final Report, Palladium, 2021, p. 54.
It should be noted that, in relation to delivering results, HDIF was scored A+ by FCDO every year in implementation except its first year, which indicated good effectiveness performance. Finally, the programme was largely credited with raising the profile of innovation in Tanzania and cultivating interest amongst development partners to support innovation in the country. For wider impact and prospects of sustainability of the HDIF grants, this VfM Effectiveness summary should be read in the context of the findings elsewhere in this evaluation report.
### VfM Equity

Equity is about extending the benefits of a program to disadvantaged groups. In this context, the HDIF aimed to ensure that its benefits reached these groups, although it did not have a specific gender lens at the start. However, it later adopted a gender lens during implementation (also see Box 4). Gender was treated as a cross-cutting theme across the programme portfolio, and consideration of different outcomes for women and girls, along with the disaggregation of relevant data, was encouraged.
As seen in the Table 7 below, the gender composition of central teams was monitored and reported periodically as part of the VfM framework. However, equity reporting focused solely on the gender aspect. The projects themselves did not target vulnerable groups such as the disabled. Nevertheless, some grants managed to reach indigenous communities.
As part of their logframe monitoring, the HDIF reported that 100% of the grantees had gender strategies in place, compared to an 80% initial milestone. The HDIF logframe included an indicator for the overall number of beneficiaries, which was intended to be disaggregated by gender according to its definition. However, it is understood that this was not carried out.
[note] Project Completion Review, FCDO, August 2021, p.10.
[note] In the 2018/2019 VfM report, there was an attempt to provide the gender breakdown. However, the figures presented do not add up to the total number provided.
Table 7. Summary of VfM Equity indicators of HDIF
VfM Equity metric	2016/2017	2018/2019	2019-2021
Proportion of programme technical advisors that are female	49%	53%	49%
Proportion of instances in which the programme’s bid review team included at least one female member	100%	100%	100%
No of people trained on HDIF gender resource pack	13	34	n/a

Source: HDIF. VfM Reports for 2016-17,2018-19, 2019-21

# Conclusions and recommendations
## Conclusions
Based on the evidence presented in this report, the following main conclusions were drawn:
- Overall, the programme addressed the development challenges and needs of Tanzania and created notable impact through the innovation projects it financed. Unlike a traditional challenge fund, the programme also provided capacity building and project management support to the grantees. The combination of both were important to generate results in education, health, and WASH and make contributions to the country’s overall development goals.
- The initial programme design had some limitations as it did not sufficiently take into account country context and capacities of target groups and consultation with stakeholders remained limited. With the early recognition of the issues, the HDIF team took steps to improve the programme’s ToC and logframe. The adaptive management and programming strategies employed were effective and contributed to success. The HDIF and FCDO teams were flexible and agile to respond to the emerging needs and challenges both at the programme and project levels.
- The programme mainly attracted large and mostly international non-governmental organisations that have the capacity to absorb larger amounts of funds and meet grants requirements, mainly because the financial and administrative requirements that were difficult to fulfil by the private sector, small organisations and start-ups. While the grantees were successful in delivering innovative solutions in line with the HDIF objectives, the programme’s sole provision of grants has led to a situation where the beneficiaries have maintained reliance on this form of support, impeding their capacity to attain sustainability and maximise the potential impact of their projects.
- The programme has significantly contributed to enhancing the national innovation ecosystem through several initiatives, notably, the Innovation Week. These efforts have resulted in increased collaboration among stakeholders, public-private partnerships, and access to funding opportunities for grantees. Additionally, the programme has played a crucial role in building capacities in COSTECH, improving policy-making processes and increasing the government’s commitment to innovation-based development as a result of the improvements in the ecosystem.
- The programme managed resources efficiently to produce outputs in the selected sectors and progress toward expected outcomes. It also effectively addressed risks and challenges faced during the implementation. The flexibility and openness of the FCDO allowed it to take risks in the projects supported.
- During its first year, the HDIF did not use gender lens although it was planned in the Business Case, largely because of the absence of a strategy with clear indicators and targets on gender mainstreaming. This issue was later overcome by putting necessary tools in place. Although not extensively, the programme implemented initiatives promoting inclusiveness of youth. However, it did not have a specific focus on other vulnerable groups, and projects specifically designed for disabled or indigenous peoples were limited.
- During HDIF implementation, the number of innovation hubs increased from 3 in 2004 to over 60 in 2021 throughout the country including those created in rural areas, facilitating the country-wide expansion of the ecosystem. Various stakeholders believed that HDIF contributed to this expansion. It also helped build capacities of hubs. However, although it was not a mandate of the programme, the establishment of a viable and sustainable business model for hubs has remained a work in progress which could further strengthen the innovation ecosystem.
- The HDIF’s M&E system was weak, and capacities for effective monitoring and reporting were insufficient. The VfM indicators and logframe indicators lack complementarity. Overall, the VfM performance of the HDIF was assessed to represent good VfM while there were limitations in data for a comprehensive analysis.
- The stakeholders believe that the programme has had a positive impact on the improvement of the Global Innovation Index of Tanzania. According to the World Intellectual Property Organization (WIPO), Tanzania ranked 8th out of 27 sub-Saharan African economies in 2022, compared to the 18th position among 31 sub-Saharan African nations in 2013, the year the HDIF was launched. While it is difficult to measure the impact at that level, taking into account the programme's effects on the ecosystem, it is plausible that the HDIF has made a contribution towards achieving this result.
## Recommendations
### Recommendations for donors
- Continue funding innovation in Tanzania to build on the success of the HDIF and sustain the progress achieved in innovation ecosystem development so that the benefits of the investment made so far are consolidated and expanded.
- Replicate HDIF model in other countries, and direct donor support to finance frugal innovation projects in education, heath, WASH and other relevant fields in line with societal needs and development challenges of the countries. Integrate the innovation ecosystem development approach utilised in the HDIF as an essential component of future innovation programmes for the sustainability of results.
- Ensure that a varied set of financial instruments (such as equity investments, soft loans, innovation vouchers, matching grants, etc.) are used in innovation programmes according to the needs and capacities of target groups, such as start-ups, grassroot innovators, SMEs, established businesses, etc.
- Consider financing innovation programmes and projects in stages based on milestone achievements for more effective allocation of resources, greater flexibility in response to changing needs, and reduced risk of funding ineffective projects as well as more informed decision-making by enabling the assessment of progress against milestones and adjustments in programme design and funding accordingly.
### Recommendations for innovation programme design and implementation teams
- Engage sufficient number of diverse ecosystem actors in the design process through consultations and in-depth needs and capacity analyses.
- Establish effective communication with policy-makers to develop a shared understanding and sense of ownership of the programmes.
- Implement effective strategies from the outset for mainstreaming women, youth, and other underrepresented communities, such as indigenous peoples, as well as the integrating environmental sustainability and climate change as cross-cutting issues in programmes and projects.
- Make collaboration with different organisations an eligibility criterion for applicants of project funding, specifically encouraging partnerships between the private sector and academia/research institutes to leverage their respective resources and expertise for knowledge and technology transfer, including the creation of high-growth start-ups and spin-outs.
- Establish a robust M&E framework for programmes and projects during the design phase as well as a small and VfM-focused set of metrics with cost element and pre-determined SMART targets with milestones.
- Provide capacity building on M&E and VfM to the programme management teams to ensure effective implementation and use of frameworks developed.
- Identify and employ measures that can lead to improved VfM and better outcomes. For instance, the use of a simplified and resource-efficient project application and selection procedures (similar to FASTRACT in HDIF) could be an option. However, it should be limited to the projects with low budgets and should include a rigorous project evaluation and selection process.
### Additional recommendations for increased impact and sustainability of innovation programmes
- In line with the above recommendations, in Tanzania or a similar context, the following target groups could be prioritised in different programme components:
  - Grassroot innovators and social enterprises under the concept of frugal innovation for encouraging development of accessible, affordable, resource-efficient, high-quality and sustainable solutions for the underserved or low-income populations through matching grants based on a competitive selection
  - Start-ups/spin-offs through equity investment and soft-loans with long grace periods to turn their innovative ideas into commercially viable products and services to create economic and social value
  - Established companies, with a focus on micro, small and medium-sized enterprises, through soft loans with long grace periods and innovation vouchers to increase the quality and productivity and innovate new offerings
  - Research institutes and universities through research grants or fellowships to develop new solutions addressing pressing social and environmental challenges.
  - Enablers through seed funds to support local innovation-based entrepreneurships and addressing region-specific challenges and needs by empowering the local innovation ecosystems.
- Innovation ecosystem efforts could include the following aspects:
  - Establishing a legal definition and status for social enterprises as companies under law
  - Creating angel investors networks and a database of early-stage investors, venture capitalists and impact investors; involving them actively in the programme activities
  - Developing a business model for innovation hubs to promote their sustainability and success in fostering innovation and entrepreneurial ecosystems in the regions. Such a model could include revenue streams from events, services, or equity investments, strategic partnerships with corporate or government entities, and a clear focus on the needs and priorities of the local start-up community. Moreover, the programmes like HDIF could provide matching grants to hubs to prepare their strategies and business plans with the help of external experts.
  - Designing and implementing actions for creating and strengthening networks at the national, regional and international levels. The Innovation Week could be replicated in other contexts as a good practice scheme in ecosystem building. The actions for integrating national ecosystems with regional and international ecosystems could include study visits, staff exchange programmes and events such as regular thematic conferences and workshops. In the case of Tanzania, this could also involve opening the Innovation Week to international visitors and participants to further enhance opportunities for innovators, facilitate knowledge and experience sharing, and fostering regional and international partnerships.
  - Proactively identifying synergies and complementarities with the regional and international organisations working in the value chain of science, technology, innovation and innovation-based entrepreneurship (such as the UNECA, UNESCO, UNIDO, UNICEF, the World Bank, AU, ECOWAS and SADC).
  - Establishing an active communication and interaction with the parliamentarians and decision-makers at line ministries to advocate for creating favourable conditions and incentives for innovation.
    [note] In the case of Tanzania, INOMER’s evaluation of UNESCO/Sida funded project found that an STI Caucus by a group Parliamentarians led by Hon. Judith Kapinga was established to champion research and innovation. Ongoing and future programmes could benefit from this development to increase ownership and commitment for innovation at the political level.
- In order to achieve VfM and carry out robust VfM analysis, it is recommended that ongoing and future programmes take the following into account:
  - Consolidation of more evidence, particularly on effectiveness and cost-effectiveness, which is the crux of VfM.
  - Development of a framework that consists of fewer and more focused metrics. The VfM indicators should not duplicate logframe indicators.  A small and VfM-focused set of metrics with cost element and pre-determined SMART targets with milestones should be established. This will ensure a more robust and consistent VfM reporting that contains pertinent data. Developing internal capacities on VfM, results framework, logframes, and monitoring is also essential.
  - Using VfM case studies along with VfM metrics. VfM case studies focus on one intervention or activity, have a clear resource (cost and benefit) focus, and are systematically documented. They are particularly useful to showcase what is not meaningfully assessed in periodic metrics. It is also possible to use the tool to document a negative lesson or a failure, as this also represents value, as it creates learning for programme stakeholders and others.
  - Encouraging grantees to carry out VfM reporting at the project level, as well as overall programme level, and compile VfM relevant data also from them. Particularly, case study types of well-documented VfM stories can be compiled and reported by grantees, which would help reach robust VfM conclusions. This requires a well-resourced M&E and learning function both at the programme and project levels.

# Annex 1. Definition of Background and Evaluation Scope in the Terms of Reference
Agency/ Project Name:	UNDP Tanzania, Funguo Innovation Program
Duration:	2 months
Country of Assignment:	Tanzania
Duty station:	Dar es Salaam
Type of Contract:	Service Contract (Consultancy)

##### Introduction
These terms of reference have been prepared to secure consultant(s) or a consulting firm to undertake an evaluation of the 7-year Human Development Innovation Fund (HDIF) Program. The purpose of the impact evaluation is to assess key achievements against the intended outcomes, document lessons learned, and evidence of value for money achievements, as well as the influence of the Human Development Innovation Fund on the wider Tanzanian innovation ecosystem. The primary users of the evaluation report will be British High Commission to understand the impact HDIF had on the innovation ecosystem and if it provided value for money.

##### About the FUNGUO Innovation Programme
The Funguo Innovation Programme is a UNDP Tanzania’s initiative cofounded by the European Union and the British Government through FCDO. Building on the work of the former Human Development Innovation Fund programme (HDIF), the aim of FUNGUO is to increase the number of successfully scaled innovation start-ups to contribute to the national development goals and the SDGs in Tanzania. This will be achieved through the programme’s contribution in addressing the obstacles and gaps in the innovation ecosystem that hinder innovative impact ventures from scaling while promoting an environment that empowers innovators and enablers

##### Overview of the Human Development Innovation Fund
The UKAid’s Human Development Innovation Fund (HDIF), was implemented by a consortium led by The Palladium Group and was the only major broad-range innovation program in Tanzania after the TANZICT project (which closed in early 2015). The HDIF programme ran from September 2013 to July 2021. HDIF was set up to provide grant financing and technical assistance to organizations with innovative development projects in Health, Education and WASH, but the program also contributed to the development of the Tanzanian innovation ecosystem through various targeted interventions. Its mandate was later on expanded to include contributing to the development of the innovation ecosystem in Tanzanian. Desired impact and outcome indicators of the HDIF program are shown in the table below:

HDIF Outcome indicators
INTERMEDIATE OUTCOME		Intermediate Outcome Indicators
HDIF intervention is adapted beyond HDIF funding support.		1.1 Percentage of innovations supported by HDIF that have been adapted within 3 months after grant closeout
IMMEDIATE OUTCOME A		Immediate Outcome A Indicators
HDIF intervention accelerates the diffusion of innovative ideas, approaches and solutions to human development challenges		1.1 Number of HDIF generated "reach" for innovative approaches or products supported by HDIF
		1.2 Growth in innovation ecosystem network-enabling organizations supporting new or growing social enterprises disaggregate by type of organization (hubs or incubator)
IMMEDIATE OUTCOME B		Immediate Outcome B Indicators
Dialogue and practice in innovation improve basic services in human development in Tanzania		1.1 Cumulative number of HDIF supported initiatives that have produced evidence suggesting contribution to improved basic services
IMMEDIATE OUTCOME C		Immediate Outcome C Indicators
HDIF intervention accelerates conversations, debates, and policymaking on innovation in human development		1.1 Number of instances in which funders or policy makers across sectors utilize learning generated by HDIF interventions to inform practices and complementary approaches to supporting innovation
		1.2 Cumulative number of discussions involving HDIF, its grantees or partners, held in private sector or public sector forums (i.e. government policy making, traditional and digital media, social media, etc.) concerning innovation in human development that have received coverage or has the potential to influence government policy making
		1.3 Key innovation ecosystem stakeholders express and exhibit learning, excitement, energy, momentum, and hope from the prior year of activities in the Tanzania human development innovation ecosystem
HDIF IMPACT INDICATORS
SUPER IMPACT	Improved human development impact, measured by:
Innovation in basic services contributes to human development outcomes in Tanzania	1.1. Improved inequality-adjusted Human Development Index (IHDI) score for Tanzania
	1.2. Improved Global Innovation Index (GII) score for Tanzania
	1.3. Cumulative number of new innovations implemented by HDIF partners and funded by other donors/funders that have shown evidence suggesting contribution to improved basic services
IMPACT	Impact Indicator
HDIF interventions are sustainable or geographically scaled up	1.1. Proportion of HDIF-funded grantees innovations that are sustainable or have been geographically scaled up
	1.2. Number of HDIF partners that have received support from other funders to test or scale new innovations in Tanzania.

##### Evaluation Objectives and scope
The key purpose of this evaluation is to assess the HDIF impact at the outcome level through engagement of relevant project stakeholder’s including the beneficiaries. From this evaluation the consultant(s) are expected to document key success, best practices and lessons learnt; and evaluate value for money and the impact the program had on the innovation ecosystem in Tanzania.
The evaluation should provide credible, useful, evidence-based information which enables timely incorporation of its findings, recommendations and lessons into decision making processes of FCDO, UNDP and other key stakeholders.
The evaluation will cover the time span from 2013 (the beginning of the HDIF Program) to 31st July 2021. The evaluation will be conducted from Dar es salaam, involving beneficiaries, development partners, COSTECH, and HDIF former staff. Additional interviews and visits may need to be done with beneficiaries and partners or hubs outside of Dar es Salaam, including virtual interviews with relevant stakeholders out of Tanzania.
##### General Objectives of the evaluation are to:
The objectives of this evaluation exercise are:
1. To provide the FCDO Tanzania office, national stakeholders, and UNDP, as well as a wider innovation ecosystem with an independent assessment of the performance and impact of the HDIF Programme.
2. To broaden the evidence base and inform the design of the future development interventions and implementation approach by FCDO and other development partners. To assess the Relevance, effectiveness, efficiency (value for money) and sustainability of the project interventions.
##### Specific objectives:
This impact evaluation is expected to achieve the following specific objectives:
1. To provide an independent assessment of the relevance, effectiveness, efficiency (value for money), and sustainability of HDIF contribution to the innovation ecosystem.
2. To assess the extent HDIF’s impact on the wider innovation ecosystem in Tanzania.
3. Through selected cases, examine the extent at which the program contributed towards addressing the initially identified needs i.e. improving the quality, value for money and sustainability of basic services in the education, health and water and sanitation sectors and increased innovation in Tanzania.
4. Document key successes, best practices, lessons learnt and challenges/constraints regarding implementation of the project interventions and provide recommendations for future programming.
5. Assess both negative and positive factors that have facilitated or hampered progress in achieving the project outcomes, including external factors/environment, weakness in design, management, and resource allocation, with a particular focus on assessing whether there is evidence that supported innovations achieved better value for money in basic services.
6. Assess the extent to which the application of gender mainstreaming was integrated within planning and implementation of the HDIF project and what effect, if any, this had on the innovation ecosystem.

##### Evaluation design, tasks and deliverables
It is expected that the consultant(s) will design and elaborate the evaluation methodologies and sampling techniques for the coverage of relevant groups to be involved in the evaluation and where possible the consultant(s) will propose additional methods that will result in desired results and purpose.

In addition, the methodology used in the final evaluation, including data collection and analysis methods should be human rights and gender-sensitive to the greatest extent possible, with evaluation data and findings disaggregated by sex, age, etc. Detailed analysis on disaggregated data will be undertaken as part of final evaluation from which findings are consolidated to make recommendations and identify lessons learned for enhanced gender responsive and rights-based approach of the project. The proposed design and methodological approach including interview schedule and data to be used in the evaluation should be clearly outlined in the inception report and fully discussed and agreed between UNDP, stakeholders, and the consultants.

# Annex 2. Key documents consulted
DFID (n.d.) Business Case: Human Development Innovation Fund (HDIF) for Tanzania https://devtracker.fcdo.gov.uk/projects/GB-1-203539/documents
Baker Tilly DGP & CO (2014) Financial Audit
Crowe Horwarth (2016). Financial Audit for the Year ended 31 August 2016
DFID (2019) VfM Guide for Partners.
DFID (n.d) Addendum to Business Case Including for Bridge Funding and Scale-Up Cost Extensions. https://iati.fcdo.gov.uk/iati_documents/11788388.odt
FMO (n.d.) Landscape Analysis of The Tanzania Entrepreneur Ecosystem.
FUNGUO (n.d) FUNGUO Results Framework.
FUNGUO (n.d) FUNGUO Theory of Change.
HDIF (2013) Work Plan 2013-14
HDIF (2014) HDIF Grantee Guidelines.
HDIF (2014) HDIF Grants Manual.
HDIF (2014) HDIF Operational Manual (Section A).
HDIF (2014) HDIF Operational Manual (Section B).
HDIF (2014) HDIF Operational Manual (Section C).
HDIF (2015) Annual Review. https://iati.fcdo.gov.uk/iati_documents/4364483.odt
HDIF (2015) Combined Annual Performance and Quarterly Performance Report 2014-15
HDIF (2015) Financial Statements for the Year ended 31 August 2015
HDIF (2016) Combined Annual Performance Report & Quarterly Report 2015-16
HDIF (2016) Financial Statements for the Year ended 31 August 2016
HDIF (2016) HDIF Costed Extension proposal to DFID.
HDIF (2016) HDIF LogFrame.
HDIF (2017) Business Case. https://iati.fcdo.gov.uk/iati_documents/4448524.odt
HDIF (2017) Combined Annual Performance & Quarterly Report 2016-17
HDIF (2017) Financial Statements for the Year ended 31 August 2017
HDIF (2017) VfM Report 2016-2017.
HDIF (2017a) Annual Review. https://iati.fcdo.gov.uk/iati_documents/3934147.odt
HDIF (2017b) Annual Review. https://iati.fcdo.gov.uk/iati_documents/4243272.odt
HDIF (2018) Annual Review. https://iati.fcdo.gov.uk/iati_documents/11788387.odt
HDIF (2018) Combined Annual Performance & Quarterly Report 2017-18
HDIF (2018) Financial Statements for the Year ended 31 August 2018
HDIF (2018) Innovation Week Report 2018.
HDIF (2018) Mawazo Challenge Project Report.
HDIF (2018) Workplan and Budget 2018-19
HDIF (2019) Annual Performance Report 2018-19
HDIF (2019) Annual Review. https://iati.fcdo.gov.uk/iati_documents/45739338.odt
HDIF (2019) Financial Statements for the Year ended 31 August 2019
HDIF (2019) HDIF LogFrame.
HDIF (2019) Risk Register.
HDIF (2019) Work Plan 2019-20
HDIF (2020) Financial Statements for the Year ended 31 August 2020
HDIF (2020) HDIF LogFrame.
HDIF (2020) Risk Register.
HDIF (2020) Work Plan 2020-21
HDIF (2021) Final Report
HDIF (2021) HDIF LogFrame.
HDIF (2021) HDIF Quarterly Performance Report Feb-May 2021.
HDIF (2021) HDIF Quarterly Performance Report Nov 2020-Feb 2021.
HDIF (2021) Impact/Outcome Level Results 2021.
HDIF (2021) Workplan and Budget 2021.
FCDO (2021) Programme Completion Review.
https://devtracker.fcdo.gov.uk/projects/GB-1-203539/documents
HDIF (2022) Annual Review. https://iati.fcdo.gov.uk/iati_documents/45739338.odt
HDIF (n.d.) Risk Matrix.
HDIF (n.d.) Risk Register.
HDIF (n.d.) Smart Guide PCR (template).
HDIF (n.d.) Stakeholder Interview List.
HDIF (n.d.) Theory of Change.
HDIF (n.d.) VfM matrix Example.

# Annex 3. List of interviewees
Name	Organisation
Alexa Haden	HDIF/FUNGUO
Askwar Hilonga	Nelson Mandela University/ Gongali
Brenda Msangi	CCBRT
CatherineRose Baretto	independent
Christina Murimi	Vodacom
David McGinty	HDIF/Palladium
Edgar Masatu	Anza Entrepreneurs Ltd (ICB)
Erasto Mlyuka	COSTECH
Flora Tibazarwa	former COSTECH support
Gertrude Kihunrwa	FCDO
Gidibo Tindwa	Segal Family Foundation (former independent consultant)
Godfrey Mpangala	Catholic Relief Services (CRS)
Hannah Mwandoloma	HDIF
Hassan Mshinda	Botnar Foundaiton
Ikunyigulila Lazaro	Shule Direct
Ivana Damjanov	UNCDF
Jamie Proctor	FCDO/EdTech Hub
Jane Miller	HDIF
Joseph Manirakiza	HDIF/FUNGUO
Jumanne Mtambalike	Sahara Ventures
Lilian Michael	Dorcas
Marjolijn Wilmink	HDIF
Maulilio Kipanyula	MOEST
Muzafar Kaemdin	HDIF/Palladium
Naomi Rouse	R Labs Tanzania
Natalie Smith	FCDO
Nisha Ligon	Ubongo Kids
Patience Abraham	Buni Hub (COSTECH)
Paul Damocha	UNCDF
Peter Sidler	Swiss Embassy
Revocatus Vedasto	HDIF/Palladium
Zacharia Mtema	Ifakara Health Institute /Zipline
Zahra Nensi	Deloitte

# Annex 4. Evaluation Matrix
Evaluation dimensions and questions	Desk review	In-depth Interviews	Online Survey	Innovation / ecosystem analysis (SNA)
Relevance
How well were the HDIF programme's goals and objectives aligned with the overall development priorities of Tanzania?	**	***	**	*
How well did the programme take into account innovation ecosystem development needs and challenges of Tanzania?	**	***	**	**
To what extent did the adaptive management and adaptive programming strategies employed in the HDIF programme contribute to its success, and how effectively were changes to the theory of change and logframe able to be implemented and monitored? Based on this experience, what lessons could be drawn for donors looking to implement similar programs in the future?	*	***	**	*
Efficiency
How efficiently was the programme managed?	**	***	***
How well were risks and challenges addressed during implementation?	**	***	***
Effectiveness
How well did the programme achieve its intended goals and objectives?	**	***	***	**
To what extent did the programme meet the needs of its intended end beneficiaries?	**	***	***	*
To what extent were the gender responsiveness and rights-based approaches of HDIF Programme effective in addressing the specific needs and challenges of the underrepresented groups (notably, women, youth and indigenous peoples) [equity]?	**	***	**
Impact
To what extent did the programme achieve its intended outcomes and impact in the areas of health, education, and WASH in Tanzania and to what extent did it contribute to the country's long-term development goals through innovation?	***	***	**	***
To what extent did the programme contribute to the enhancement of the national innovation ecosystem?	**	***	***	***
What unexpected results, positive or negative, has the programme yielded?	*	***	**	*
Sustainability
To what extent did the programme contribute to the development of skills and capacities of ecosystem actors, including the capabilities in the design and implementation of innovation policies and policy measures?	**	***	**	*
To what extent were the innovations developed under the programme able to be sustained in Tanzania and in other countries in the region where they were deployed?	*	***	***	*
To what extent can the lessons learned, best practices, and other experiences from the programme be applied to similar programmes in other countries (including those related to gender responsiveness and rights-based approaches)?	*	***	***	*

***	Critical contribution
**	Medium contribution
*	Limited contribution