Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Human Development Innovation Fund (HDIF) for Tanzania
Programme Value: £39,787,725		Review Date: January 2018
Programme Code: 203539	Start Date: January 2013	End Date: March 2020

Summary of Programme Performance
Year	2013	2014	2015	2016	2017	2018	2019	2020
Programme Score	B	A	A+	A+	A+	A+
Risk Rating	Moderate	Minor	Major	Major	Major	Major

Summary of progress and lessons learnt since last review
The Human Development Innovation Fund (HDIF) has continued to preform well exceeding the majority of its targets and expectations again for this reporting year. Two of the three outputs scored an A+ (moderately exceeded expectations) and one scored an A++ (substaintially exceeded expectations).

2017 was certainly an eventful year for the programme, with the following highlights reported by HDIF funded projects:
- Through Akili & Me, Tanzanian children aged three to six who watch the show one time per week for one month outperform their peers by 24% in counting, 13% in English, and 9% in fine motor skills – even when accounting for age, socio-economic status, and prior knowledge.
- CCBRT, the country’s largest provider of disability and rehabilitation services is now able to treat 20% more eye patients. Ophthalmology services account for approximately 70% of all services provided at CCBRT, seeing approximately 300 patients per day.
- Through Afya Microfinance’s (AMiF) innovative financing programme, there has been a 52% increase in women and 35% increase in children (0-5 years) attending and utilising medical services from target health facilities, and 98% of participating business owners affirmed that, as their businesses have grown, their household economics improved, including their ability to pay school fees.
- PharmAccess’ SafeCare health facility guidelines and benchmarks have improved the quality of services available in target health facilities. PharmAccess has secured Government’s approval to roll out SafeCare guidelines to all private health facilities in the country and Government has shown an interest in rolling this out at public health facilities also.
In addition to these achievements, the HDIF team has demonstrated strong resilience and adaptability throughout the year through a number of changes and challenges, while managing to continue to effectively achieve all its targets.

Key lessons from this reporting period include:
- HDIF has built a strong “brand” within Tanzania and more widely for its role in the innovation network in Tanzania – it is worthwhile for DFID to explore further options to get the most out of this investment, through for example leading a new policy dialogue with the Government of Tanzania on innovation; and drawing out lessons learnt from HDIF grantees for DFID’s work on education, health, and water and sanitation.
- HDIF has significantly increased its efforts under outputs 1 (support to the innovation “ecosystem”) and 3 (developing and disseminating evidence and learning) this year, while the work on grantees (output 2) has evolved and shifted towards close-out. Feedback from interviews and site visits, particularly with ecosystem partners, has illustrated the valuable role HDIF plays in the wider ecosystem and evidence agenda. As less time and resources are required to manage grantees, more could be done on the ecosystem and evidence agenda, particularly to strengthen the vision and role of Government for the sustainability and replicability of the innovations supported by HDIF.
  [note] Drawing on biological and ecological science, the term “ecosystem” is used to encapsulate dynamic interactions between an array of different actors or organisms and their environment. For the concept of innovation, “it’s about how people meet, talk, trust, share, collaborate, team, experiment, and grow together. When an ecosystem thrives, it means that its constituent parts have developed patterns of behaviour – or culture – that streamline the flow of ideas, talent, and capital throughout a system.” Hwang, Victor, W. https://www.forbes.com/sites/victorhwang/2014/04/16/the-next-big-business-buzzword-ecosystem/2/#337f25cf3c04.

Summary of recommendations for the next year
The current end date is March 2020, however, given delays in finalising contract amendments to cover Round 3, there are plans underway to extend the end date until July 2021. It is still considered worthwhile for HDIF to work closely with its partners (notably DFID and the Government of Tanzania) to begin to plan for the HDIF close-out. Crucial to this will be the role of key stakeholders – the Government being the most important. With changes to key Government personnel, HDIF will need to refocus its efforts on building new relationships with key individuals and work to understand and support the Government’s vision and role in leading the development and growth of the innovation ecosystem in Tanzania. Since less time and resources will be required to manage grantees in future years, HDIF should use this capacity to work with key Government partners to strengthen the vision and role of Government and the wider enabling environment for innovation in Tanzania (for example through its output 1 and 3 activities). This will in turn help to improve the sustainability and replicability of the innovations supported by HDIF. HDIF should draw DFID in more to these wider ecosystem discussions, utilising HDIF’s role as the Secretariat to the Development Partners Group on Innovation and Technology and DFID’s role as the Co-Chair of the Group (alongside the World Bank). As Secretariat, HDIF is uniquely placed to convene both the donor partners and related Government of Tanzania partners on issues and activities related to science, technology and innovation. Moreover, through the HDIF grant with COSTECH, HDIF has a remite to support the Government’s industrialisation and science, technology and innovation priorities.

Finally, an outstanding action is to approve the fifth contract amendment (CA5) to allow the newly approved Round 3 grantees to be contracted. There have been delays to this process by both HDIF (specifically, Palladium) and DFID, with the final steps requiring action from DFID Tanzania. If delays continue, Round 3 grantees face a shorter grant period than anticipated, which will certainly impact their ability to deliver results by the end of the grant. It is recommended that this is deemed a high priority for the DFID team over the next two months.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-203539/documents
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-203539/documents

The Human Development Innovation Fund (HDIF) is a £39.8 million, seven-year challenge fund programme funded by the UK’s Department for International Development (DFID) and managed by a Palladium International-led consortium in Tanzania. HDIF aims to identify and support innovative and market-driven solutions that have the potential to create social impact in education; health; and water, sanitation and hygiene (WASH) across Tanzania. HDIF seeks to catalyse the development, testing and scaling of innovative models of service delivery, use of Information and Communication Technologies for Development (ICT4D), and product solutions within these three sectors. HDIF was designed to catalyse new ways, models, approaches, technologies and more importantly participation of non-state actors, notably the private sector, in the delivery of quality, pro-poor basic services. The programme aims to incentivise and partner with both private-for-profit and private-not-for-profit players who demonstrate a high appetite for risk to invest in the hugely untapped market of pro-poor basic service delivery in Tanzania.
[note] In May 2017, a costed extension of £9.7m and 18 months, was approved to support the third round of funding of innovations specifically targeted to a sub-set of a few sectors.

The HDIF team is a consortium that includes Palladium (covering overall fund management, operations, technical leadership, and technical assistance on health); KPMG East Africa Limited (responsible for financial oversight of the grantees and building capacity of COSTECH in fund management); Newcastle University (providing technical assistance on education); Loughborough University (providing technical assistance on water, sanitation and hygiene); and the Institute for Development Studies (IDS) (providing support in knowledge mobilisation). The programme has built a close relationship with the Tanzanian Commission for Science and Technology (COSTECH), as the key government interlocutor on innovation. The programme supports a capacity building plan for COSTECH, who has a key role in stimulating innovation in the country – as well as forming a bridge between successful innovations and the sectors ministries.

The intended impact of HDIF, outlined in the business case, is ‘improved human development outcomes for poor people in Tanzania’. The expected outcome of the HDIF programme is that ‘innovation in basic services contributes to human development outcomes in Tanzania’, specifically measuring the adoption of innovations in human development and changes in policy and practice by government actors and funders related to human development innovation.

HDIF seeks to achieve these results through 3 outputs:
1. ‘Inspire’: HDIF has cultivated the ecosystem on innovation in human development through inspirational, quad-aligned (cross-sector) networking and strategic awards.
  [note] Quad-aligned has evolved from traditional theories of innovation ecosystems which assume universities, industry and government were necessary components of the ecosystem, to also include civil society as a key fourth component, crucial in providing a voice for the community and individuals.
2. ‘Catalyse’: HDIF has identified and catalysed the diffusion of innovations in human development.
3. ‘Transform’: HDIF has transformed the focus and quantity of evidence available to key stakeholders on the practice of innovation in human development.

A number of funding rounds have been launched:
- Initial Investments: Open to ideas in education, health, and water and santitation through a closed call for proposals developed in collaboration between the HDIF team and DFID Tanzania. Three successful grantees were chosen, absorbing around £6m. One grantee from the Initial Investments “closed-out” during this reporting period, and one closed early in a prior period due to poor performance.
- Round 1: Open to ideas in education, health, and water and sanitation, Round 1 opened for applications from 13 May to 31 August 2014. 1,353 applications were received and 21 successful grantees were chosen with 20 winners contracted, absorbing around £7.3m. Four Round 1 grantees “closed-out” during this reporting period, with over 20 expected in the next year.
- Round 2: Opened for applications from 15 June – 14 August 2015 and was also targeted broadly at innovative ideas in education, health, and water and sanitation. 267 applications were received and 13 successful grantees were chosen with 12 winners contracted, absorbing around £4.5m.
- Round 3: Focusing on early childhood development, and sanitation and hygine, Round 3 was open for applications from 19 June – 11 September 2017 (during this reporting year). 137 applications were received, with 42 being eligible for consideration. Applications were evenly split across the two topics. Seven projects were approved and due diligence and contract negotiation is now underway. It is anticipated that the projects will absorb around £5m of funding.
- COSTECH receives around £1.5m of grant support alongside being HDIF’s Government of Tanzania strategic partner. HDIF are working with COSTECH to strengthen the Tanzania innovation ecosystem by supporting innovation hubs, starting with BUNI Hub (an innovation and entrepreneur space hosted at COSTECH in Dar es Salaam).

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Development impact
The balance between supporting early-stage innovation and achieving development impact is a challenge. Given the nature of innovation, not all the HDIF supported projects will be successful – some will fail early; many are likely to hit delays in implementation; some may take much more time than the grant period to achieve sustainable impact. In addition, around 60% of the HDIF grantee portfolio are considered pilots: new initiatives with a prototype that has been used/tested by customers/beneficiaries and deemed effective; the remaining are considered scale-up: an existing pilot project that seeks to expand. As such, all the projects are early-stage and are not likely to achieve significant development impacts during the course of the grant. Indicators which focus on development impacts (i.e. improved basic services) are only considered at impact and outcome level for the programme and tend to focus on “evidence” of contribution to the improvement of basic services. However, it is certainly possible that there will be direct improvements to service delivery in education, health, and water and sanitation, from a number of HDIF grantees. This reporting year for example, at least four grantees have demonstrated evidence of directly contributing to human development impacts. These are:
CCBRT: Lean management strategies to improve provision of quality health services
CCBRT is the largest provider of disability and rehabilitative services in Tanzania – treating thousands of patients every year in four main service areas, ophthalmology, obstetric fistula, orthopedic and reconstructive surgery. Ophthalmology services account for approximately 70% of all services provided at CCBRT, seeing approximately 300 patients per day. At its busiest in 2016, CCBRT’s Ophthalmology Department was forced to turn away approximately 80 clients per day. With HDIF support, CCBRT has implemented lean management strategies to its Eye Outpatient Department (OPD). Data collected at the eye OPD after the adoption of the lean approach shows that patients waiting time reduced and CCBRT is able to treat 20% more eye patients: a jump from 1,463 to 1,821.
[note] The core idea being “lean” strategies is to maximise customer value while minimising waste. Simply, lean means creating more value for customers with fewer resources. See: https://hbr.org/2016/03/lean-strategy.
Ubongo Learning: Akili and me
Early childhood education is an urgent developmental issue to be addressed in Tanzania, where less than half of children receive any formal education before entering primary school at the age of six. While primary education access has been improving across Tanzania, there are few pre-primary schools. Those that do exist have an average student to teacher ratio of 100:1. With HDIF support, Ubongo Learning created “Akili and Me,” a multi-platform edutainment series that helps young children develop school readiness skills through fun learning on TV and radio. “Akili and Me” is now broadcasting daily on Tanzanian national TV with up to 1.3 million households watching each day. Ubongo has developed and is rolling out complementary mLearning services for both basic mobile phones and smart phones. A randomized control trial found that Tanzanian children aged three to six who watch ‘Akili and Me’ for a month outperform their peers by 24% in counting, 13% in English and 9% in fine motor skills, even when accounting for age, socio-economic status and prior knowledge.
APHFTA: Microlending to private health facilities
Despite the presence of more than 8,000 Accredited Drug Dispensing Outlets (ADDOs) and 1,333 private health facilities across Tanzania (servicing approximately 67% of the population in rural areas, mainly women, children and the elderly), credit to the private health sector is estimated to be less than 1% of the total loan portfolio of regulated banks and ﬁnancial institutions. With HDIF support, APHFTA has developed a microlending product suited to the needs of the private health sector, offering both group (ADDO) and individual loans at 2-2.5% interest per month. Individual facilities received loans in cash, and ADDOs received loans in the form of product (i.e. drugs, supplies, etc.). The microlending product has reduced stock-outs and increased access to quality drugs. Target health facilities have seen a 52% increase in women and 35% increase in children (0-5 years) attending and utilising medical services. There has also been a postitive impact on facilities’ owners – 98% of the owners affirmed that, as their businesses have grown, their household economics improved, including their ability to pay school fees.
PharmAccess: The business of quality in health (SafeCare)
Given the importance of private health facilities in delivering health services to the rural population, quality of care is crucial. Without clear quality standards, neither the Ministry of Health nor facility managers can benchmark or compare quality levels. With the support of HDIF, PharmAccess has been implementing SafeCare: a structured quality improvement program that rates health facilities’ performance from Level 1 to Level 5 across themes such as: health care organisation management, care of patients, specialised services and ancillary services. Facilities are provided with mentors who advise and support facilities’ leaders on improvements over a one-year period. PharmAccess recently conducted an assessment for 95 facilities that showed an average improvement of 15 points. The majority of the assessed facilities improved by more than one level – for example, jumped from level one to level three. PharmAccess has secured Government’s approval to roll out SafeCare guidelines to all private health facilities in the country. PharmAccess managed to successfully roll out the SafeCare guidelines in private health facilities and improve quality of service provision in these facilities. As the result of this achievement, the Government has shown an interest to partner with PharmAccess to roll out the guidelines in public health facilities as well.

Annual outcome assessment
The expected outcome is that ‘innovation in basic services contributes to human development outcomes in Tanzania’. This outcome is measured through two outcome statements, each with three indicators, as shown in the table below. For this reporting period, performance towards the outcome targets is assessed as A+ (exceeded expectations). All measured indicators have substantially exceeded the 2017 milestone targets.

Outcome statement	Indicators	Milestones / (Nov 2017)	Progress
HDIF intervention accelerates the diffusion of innovative ideas, approaches and solutions to human development challenges	1.1 Number of HDIF generated "reach" for innovative approaches or products supported by HDIF	Not measured in 2017	Not measured in 2017
	1.2 Percentage of innovations supported by HDIF that have been adapted within 3 months after grant closeout	30%	80% (4 of the 5 grantees which have closed and three months has elapsed) / Results are captured through a questionnaire conducted via interviews with grantees within 3 months of closing. Questions are based on international methodology to assess “adaptation” of innovations.
	1.3 Growth in innovation ecosystem network-enabling organizations supporting new or growing social enterprises disaggregate by type of organisation (hubs or incubator)	9 innovation ecosystem-enabling organisations	25 innovation ecosystem-enabling organisations / Data was captured through a deep dive study on the services offered by innovation spaces across the country.
HDIF intervention accelerates conversations, debates, and policymaking on innovation in human development	1.1 Number of instances in which funders across sectors utilise learning generated by HDIF interventions to inform practices and complementary approaches to supporting innovation	2	6 / Information is gathered via open source data and self-reporting, and is likely to be an underestimate since not all funders will report utilising HDIF learning.
	1.2 Cumulative number of discussions involving HDIF, its grantees or partners, held in private or public forums concerning innovation in human development that have received wide coverage or influenced government policy making	10	12 / Information is gathered via open source data and self-reporting. Five HDIF grantees, partners or projects received wide media coverage. All 12 are deemed to have potential for influencing government policy through ongoing government engagement.
	1.3 Key innovation ecosystem stakeholders express and exhibit learning, excitement, energy, momentum, and hope from the prior year of activities in the Tanzania human development innovation ecosystem	Completed	Achieved / 25 stakeholders’ opinions and views were gathered via a in-person interview or an online survey seeking to assess opinions over time. Results suggest ecosystem stakeholders do express and exhibit excitement, energy, momentum and hope.
[note] An innovation is considered to have been adapted if a grantee or its partners have continued implementing the innovation, at any scale, after HDIF support has ended. The concept has been developed by the Springfield Centre for Business in Development. More details can be found here: http://www.springfieldcentre.com/wp-content/uploads/2016/04/Systemic-and-Systemic-Change-clarification-of-concept-V2-BT-260416.pdf

Overall output score and description
Overall output score is A+: outputs exceeded expectations. Detailed output scoring is provided in the next section, however a summary table is provided below.

Output	Summary of output progress	Output score and weighting
Output 1: HDIF has cultivated the ecosystem on innovation in human development through inspirational quad-aligned (cross-sector) networking and strategic awards	HDIF has exceeded all milestone targets under this output and is often the first place people go to for any information on the innovation ecosystem in Tanzania. This extends beyond human development. There remain some challenges with the buy-in and leadership from the Government, but this may shift with changes in personnel.	A++ – 10%
Output 2: HDIF has identified and catalyzed the diffusion of innovations in human development	HDIF exceeded all but one indicator for this reporting year. The one indicator that was not met was due to changes in Government personnel which resulted in a delay to some of the activities. The performance of grantees is improving and there is good evidence that at least six of the grantees are contributing to improved basic services.	A+ – 75%
Output 3: HDIF has transformed the focus and quantity of evidence available to key stakeholders on the practice of innovation in human development	Similar the output 2, HDIF has exceeded all but one indicator this year (the outstanding indicator focused on building capacity of the Government). HDIF has produced a number of high quality reports with evidence and lessons learnt from grantees. These have been disseminated to a wide audience. HDIF has also launched a number of new, exciting research products over the reporting year.	A+ – 15%

Key lessons
This year was a significant one in HDIF’s history with the first grantees being closed-out (after reaching the planned end of their grant period with HDIF); publication of a range of knowledge products from grantee case studies to HDIF lessons and best practice on specific topics; a contract extension was approved by DFID and Round 3 of funding was launched; the Mawazo Challenge was launched, a HDIF first as a facilitator of an ideas competition; and key personnel in HDIF’s most important partners (DFID and COSTECH) changed. As a result there have been a huge array of lessons learnt throughout the year, by HDIF activities as well as through grantees activities and case studies. It would not be possible to list all these lessons here – these are well documented in HDIF’s Annual Report. Some of the high-level and key lessons from this reporting year are included below.
- It is great to have champions in key organisations who are passionate and drive forward the agenda in their respective organisation, and engage regularly with the programme, but when these individuals move on, there is a risk to the continued performance of the programme. This has been the case with the loss of two key stakeholders from COSTECH who have moved on to other roles and are no longer leading/championing engagement with HDIF. This has resulted in delays for key programme activities (e.g. capacity building for COSTECH). In addition, political and personnel changes at DFID slowed some approval processes necessary to launch and implement Round 3 (with a fifth contract amendment still outstanding at time of writing this report). These crucial government partners can be subject to sudden and unavoidable political changes, which requires HDIF to be flexible and adaptable. In addition, HDIF should always seek to build relationships with the institution itself through a number of individuals, rather than rely on a key advocate to drive the agenda forward.
- There remains some reticence from the Government of Tanzania in supporting private sector innovation ecosystem players. Much of the emphasis from the Government appears to be focused on public sector hubs and innovation spaces (e.g. in universities and other public institutions). In addition, there is some uncertainty about the future of BUNI Hub (currently hosted at COSTECH) with COSTECH suggesting it should not have a hub itself, but provide support to multiple hubs with different models. There is still some work to do to “on-board” Government counterparts into the innovation agenda. While COSTECH is updating its strategy to recognise its role on supporting innovation, there is some concern that it will continue to focus heavily on research and technology and not innovation in its broader sense (business models, social innovation, etc.). HDIF could be instrumental in helping to shift this perception, but there is also a role here for DFID (particularly as the Co-Chair of the Development Partners Group on Innovation and Technology) and other development partners.
- With over 20 grantee projects due to close-out in the coming year, there is an opportunity to shift focus within HDIF away from output 2 – grant management, and into the other outputs on the ecosystem and evidence and learning. HDIF and DFID should discuss balance of support given to these areas, framed on which drives greatest impact and value for investment in Tanzania in innovation/entrepreneurial space to cement the HDIF legacy as the programme draws to an end. HDIF has built a strong “brand” within Tanzania and more widely for its role in the Tanzanian innovation ecosystem – it is worthwhile for DFID to explore options to get the most out of this investment.
- Finally, much reference was given by ecosystem partners about “changing the mindset” of Tanzanians and that there is a lack of a “culture of innovation” in Tanzania. Perhaps, instead of trying to change a mindset, HDIF, DFID and other key partners could explore what are the values in Tanzanian culture that may be conducive to innovation and further explore how to build on these as part of outreach and ecosystem activities. For example, attributes such as national pride (Tanzanian first and foremost), and politeness and tolerance are likely to be highly pertinent for innovation. These should be considered in addition to the current support HDIF and other ecosystem players provide to boost the enabling environment to allow innovation to thrive (including the regulatory framework, access to finance, and access to new technologies).

Key actions
Actions for HDIF and DFID are listed below.

HDIF actions
1. Discuss next year’s targets for indicators that are repeatedly overachieved with DFID and agree approach to ensure targets are ambitious, stretching and meaningful. Update all indicators that are cumulative to reflect performance this year in the targets for future years. To be completed by March 2018.
2. Present options to improve financial forecasting to DFID and commit to ensuring forecasting improves in the coming year. To be completed by March 2018.
3. Agree with DFID to remove indicator 2.1, since no further funding rounds are anticipated and it will not be measured in future years. To be completed by March 2018.
4. Agree with DFID the best option to address concerns of accurate presentation of grantee performance as represented by indicator 2.2. To be completed by March 2018.
5. Discuss with DFID methodologies/definitions within indicators 3.1, 3.2, 3.3, 3.4 and 3.6 to ensure common understanding. To be completed by March 2018.
6. Agree with DFID targets for each of the value for money (VfM) indicators, so an assessment on rates of improvement can be made in future years. To be completed by June 2018.
7. Update the risk register following a discussion with DFID’s Senior Responsible Owner (SRO) and Programme Manager. To be completed by March 2018.
8. Continue to review the balance between international and national technical advisers to establish whether greater value for money and impact could be achieved with greater utilisation of Tanzanian experts. To be completed by June 2018.
9. Explore the value of hosting additional future events outside Dar es Salaam and discuss options with DFID HDIF team. To be completed by April 2018.
10. Finalise the Communication Strategy that includes (existing and potential) stakeholder mapping and targeting, and to align the Communications Strategy with the Knowledge Products Strategy and Roadmap to ensure knowledge products are disseminated effectively to the right audience at the right moment. To be completed by April 2018.
11. Follow up the Gender White Paper with working with grantees on incorporating the findings into their individual projects. HDIF should also do a refresh of gender with all HDIF staff (following a number of staff changes recently). To be completed by June 2018.
12. Work with COSTECH and TANZIS programme to identify what role HDIF can play to assist and support the sustainability of innovation ecosystem-enabling organisations. To be completed by June 2018.
13. Explore opportunities to boost the capacity and awareness of innovation across COSTECH and the Government, for example through events focused on young Government professionals or by targeting outreach that links innovation to industrialisation. To be completed by June 2018.
14. Determine next year’s resources requirments and identify opportunities to HDIF to provide more business TA as needed by grantees. Options to be discussed with DFID by April 2018.
15. Discuss with DFID the balance of support given to the three output areas, framed on which drives greatest impact and value for investment in Tanzania in innovation/entrepreneurial space to cement the HDIF legacy as the programme draws to an end. To be completed by June 2018.
16. Explore with DFID and other key partners the values in Tanzanian culture that are conducive to innovation and futher explore how to build on these as part of outreach activities. To be completed by June 2018.
17. HDIF to develop a plan to close-out the programme, alongside DFID and other ecosystem partners (particularly Government). Early thinking of a responsible exit will help to ensure there is a sustainable plan for innovation to continue to thrive. Draft plan for close-out of HDIF to be discussed with DFID and partners by November 2018.

DFID actions
1. DFID to prioritise securing internally approval for CA5 to ensure Round 3 grantees have sufficient time to implement their projects. To be completed by March 2018.
2. Discuss with HDIF indicators that are repeatedly overachieved and agree approach to ensure targets are ambitious, stretching and meaningful. To be completed by March 2018.
3. Review the updated risk register (Annex A), particularly the number and variety of risks identified, the risk owner, and the risk categories (aligned to DFID’s new guidelines). Agree required changes with HDIF, including an overarching risk appetite statement for the programme. To be completed by March 2018.
4. Discuss with HDIF the balance of support given to the three output areas, framed on which drives greatest impact and value for investment in Tanzania in innovation/entrepreneurial space to cerment the HDIF legacy as the programme draws to an end. To be completed by June 2018.
5. DFID SRO to facilitate a greater engagement between HDIF and DFID Tanzania Advisers in education, health and WASH to share the findings and lessons learnt from HDIF grantees and partners. Advisers should also explore sharing these findings more broadly amongst their cadre groups where worthwhile (e.g. particularly in sectors where DFID Tanzania is not engaging but others in DFID are). Ongoing.
6. Engage more in the policy dialogue around innovation alongside HDIF to leverage DFID’s investment. This includes ensuring continuation of DFID’s role as Co-Chair of the Development Partners Group on Innovation and Technology. A new DFID DPG-IT representative is required (as the current rep goes on maternity). Ongoing, with new DPG-IT Co-Chair required by February 2018.
7. With around three years remaining for the programme and given DFID Tanzania’s current portfolio refresh, DFID should initiate internal discussions on its vision for HDIF’s legacy and explore options for future DFID investment in the innovation ecosystem in Tanzania. Possible areas to explore include continued support for innovation in human development, but also the link between innovation and economic development, prosperity, jobs and competitiveness. To be completed by June 2018.
8. DFID should work with HDIF to develop a plan to close-out the programme. This could include considerations of whether a new programme (for example, with an expanded focus beyond human development, including economic development, or with more support for ecosystem activites) would be worthwhile and represent good value for money for DFID. Draft plan for close-out of HDIF to be discussed amongst partners by November 2018.

Has the logframe been updated since the last review?
Yes, the logframe was updated in August 2017 following recommendations in the 2016 Annual Review.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	HDIF has cultivated the ecosystem on innovation in human development through inspirational quad-aligned (cross-sector) networking and strategic awards
Output number per LF		1	Output Score	A++
Risk:		Major	Impact weighting (%):	10
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicators	Milestones	Progress
1.1 Cumulative number of articles or digital media produced by HDIF related to grantee innovations and disseminated to at least two relevant quad-aligned actor(s) within the innovation ecosystem, disaggregated by whether targeted to COSTECH or not	20 (50%)	90: 4 press releases and 56 videos (>50% targeted COSTECH) produced this year / Two press conferences and four press releases resulted in 34 printed articles centering around grantees’ innovations,more than half targeting COSTECH. / 56 videos produced, 42 of which are dissimentated via YouTube and social media.
1.2 Cumulative number of HDIF co-curated and designed quad-aligned events, meetings, forums, or other networking opportunities that bring together stakeholders across at least three of the six key actor categories (alongside human development), disaggregated by events in which COSTECH is engaged as a collaborator	20 (35%)	56 (61%) / This year HDIF took part in 21 networking opportunities, 17 (81%) of which engaged COSTECH as a collaborator.
1.3 COSTECH develops, implements and redesigns as necessary its Strategic Plan with HDIF support	Not measured in 2017 as not anticipated to be completed this year	HDIF has supported consultants to help COSTECH redesign its 5 year plan as requested by the Government of Tanzania to align with the Government’s Five / Year Development Plan (in particular, an industrialisation agenda).
1.4 Percentage of partners in supporting the innovation ecosystem who rate HDIFS's input, assistance or collaboration as 6 or better on a 10-point scale	60%	83% / Data collected via a survey sent to 17 stakeholders, 12 responded. Of the 12, 10 rated HDIF’s input as 6 or higher.
1.5 Cumulative number of new, innovative ideas in human development generated or mobilised through HDIF strategic awards	Not measured – no result expected by November 2017	Mawazo Challenge is underway. 12 ideas have been through an 8 week training and mentorship programme. The top 10 ideas will receive seed funding support following a pitch event.
1.6 Percentage of work plan targets achieved by HDIF in building the capacity of Government of Tanzania (including COSTECH) in activities related to innovation ecosystem	60%	100% / Upon COSTECH’s request, HDIF’s support to COSTECH in this area was redeployed to support BUNI Hub. Funding remains to support COSTECH in this area, once its Strategic Plan is agreed and activities are identified.
1.7 Size of the HDIF curated digital ecosystem, disaggregated by type of platform, e.g. social media, unique website impressions, HDIF email mailing list, etc.	SM followers: 1,250 / Mailing list: 3,300	SM followers: 13,491 / Mailing list: 6,324 / Significant increases over the reporting period correlate with HDIF funding opportunities (i.e. Round 3) and paid post boosting (e.g. during Innovation Week).
1.8 Continued, active engagement in the broader HDIF network through HDIF's Newsletter	Average opens: 6% / Click-through: 1%	Average opens: 14.5% / Click-through: 4.3% / Increases highly correlated with HDIF funding opportunitites (Round 3).
[note] Strategic awards are awards (not grants) by HDIF or its representative aimed in supporting early stage innovators to generate new, innovative ideas in human development.

Summary of performance
This output measures and monitors HDIF’s role in strengthening Tanzania’s innovation ecosystem. It is important to note that results from this output are responsible for only 10% of HDIF’s logframe targets, however, success under this output could have a significant impact on the sustainability of other areas of HDIF’s work, particularly the grantees. By engaging with ecosystem partners to share lessons and build knowledge and awareness, including building the long-term capacity of Government partners (notably COSTECH), HDIF is enhancing the enabling environment for innovation now and in the future in Tanzania.

HDIF is performing extraordinarily well against its established targets for this output, exceeding expectations on all six indicators with milestone targets for 2017. In particular, HDIF has been over performing significantly on its outreach targets, particularly through digital media. Some work has been done to understand and identify who is actively following and engaged in HDIF’s ecosystem activities. HDIF continues to have a strong following among youth (18-35 year olds) across social media platforms with 71% of all Facebook followers and 82% of all Twitter followers within this demographic. In addition, followers are mostly male across all social media platforms (e.g. 81% male, 19% female on Facebook and 67% male, 33% female on Twitter). Female followers increased when content included a female role model or was linked to female-specific topics (e.g. International Day of the Girl). Analysis also shows that HDIF receive the highest interest when their outreach is linked to or offers information on funding opportunities (e.g. Round 3). As there are no more HDIF funding rounds, numbers of followers and click-throughs on HDIF’s website and newsletter may have reached a peak during this reporting year. HDIF should also use its outreach activities to share funding opportunities and learnings from other ecosystem stakeholders where possible (e.g. other donor programmes, COSTECH funds, etc.).

This overachievement is likely to also reflect milestone targets not being sufficiently stretching – reflecting comments from last year’s Annual Review that quite a number of output indicators were very significantly exceeded and there is a case to be made for increasing some of these targets to levels that are more challenging, based on past experience. In its Annual Report, HDIF does not recommend increasing milestone targets for next year for various reasons (including the increase in social media interest correlates to funding opportunities, and HDIF will have no future funding opportunities therefore the number of social media followers is likely to remain constant from now). It is recommended that the DFID SRO and HDIF team discuss these suggestions, and consider the case for increasing targets or for refocusing indicators that are repeatedly overachieved to ensure they are stretching and meaningful. Where targets are cumulative, future year targets should be updated to reflect the high performance to date.

One of the main challenges faced by the programme this year has been changes in key partner personnel – notably within the Government of Tanzania, but also within DFID Tanzania – which has resulted in some delays and uncertainties for continued implementation of the programme and its activities. During the reporting year, the day-to-day contact for HDIF in COSTECH moved on and was replaced, and the Director General of COSTECH (a supportive and highly engaged stakeholder in the design and implementation of HDIF) was replaced by an Acting DG. Throughout these changes, there has also been delays to finalising other donor support to COSTECH and the wider ecosystem (e.g. Finland’s Tanzania Innovation Support programme or TANZIS). Fortunately, the TANZIS programme was approved by the Government of Tanzania in December 2017, and HDIF is establishing a relationship with the new personell in COSTECH.

Key reflections from site visits and interviews
1. Many interviewees commented on the HDIF hosted Innovation Week and how valuable the event is, particularly providing opportunities for ecosystem partners to showcase their own work and host their own sessions/events alongside (e.g. She Codes for Change). Some suggested this should happen more often (e.g. twice a year). Others suggested that focusing on expanding the network would be valuable, as there is a sense that “we’re just talking to the same people”.
2. There is an ongoing debate (inside HDIF and within ecosystem stakeholders) about how to encourage and support innovators and ecosystem stakeholders outside of Dar es Salaam (or the other major centres such as Arusha and Mbeya). Holding key events in Dar only limits the audience to those that either live in the area or can afford to travel. The “Hubs Research” supported under output 3, alongside findings from the Mawazo Challenge team (who travelled the country engaging with university students) can provide some insights into which locations across the country may be suitable for future events.
3. While the hubs and innovation spaces that exist outside Dar es Salaam are staffed with passionate and talented individuals who are driven to find innovative solutions to local problems, they tend to have a number of disconnected initiatives (e.g. transport apps and fashion) rather than people working together on opportunities. All would benefit from technical and financial support to help develop coherent strategies and programmes as well as mentoring and communication. Working with COSTECH and the new TANZIS programme, HDIF could help develop a better understanding of sustainability (particularly funding flows) for hubs. This will help develop a much more coherent proposition for this high-potential area.
4. HDIF has done a lot of research on its audiences, but this could be improved further to ensure it effectively targets key players (established and new) in the ecosystem with the right products at the right time. A stakeholder mapping alongside a communications strategy is in development and should remain a priority.
5. Given the recent changes in key Government of Tanzania personnel and ongoing updates to COSTECH’s Strategic Plan and other key policy documents (including the Science, Technology and Innovation Act and Policy), HDIF should harness opportunities to support COSTECH to raise understanding and awareness of the value of innovation to a wider Government audience, including young professionals. In addition, highlighting the link between innovation and competitiveness to support the Government’s industrialisation agenda, would be worthwhile.
6. A number of interviewees suggested that HDIF should look beyond Government and focus attention more on private sector organisations. This recommendation was also identified in last year’s annual review (see below). It is recommended that HDIF continue to explore opportunities to pull in more private sector organisations as a way of supporting sustainability of innovations and expanding HDIF network and audience.

Summary of responses to issues raised in previous annual reviews (where relevant)
Target some communication activities in the ‘inspire’ component on private sector associations in Tanzania in order to stimulate interest in innovations that enable businesses to operate effectively in ‘bottom of the pyramid’ markets.
Private sector associations (e.g. TPSF, CTI, TCCIA, and sector-specific trade associations like APHFTA) were included in HDIF’s email outreach with some direct 1:1 outreach.
Consider additional ways of promoting a stronger role for Government in the innovation ecosystem e.g. technical adviser within COSTECH, promotion of public-private partnerships on innovation.
HDIF has been supporting COSTECH in strengthening their capacity to cultivate the innovation ecosystem. This is done through HDIF consortium partner, IDS, helping COSTECH shape up their knowledge management capabilities, and developing a strategy to influence the evidence-based policy making through Government ministries and agencies. HDIF has also commissioned a Technical Advisor assisting COSTECH with a framework on developing and managing innovation hubs in the country.
Depending on cost, consider commissioning more detailed analysis of the composition of event participants, mailing list recipients and social media followers to help target relevant communications more effectively.
An analysis was done internally, with support from the social innovation consultant, on the composition and growth in number of mailing list recipients and social media followers. Moreover, the team analysed the composition and the number of viewers of videos posted in the programme’s YouTube channel. Findings from this analysis were presented in the HDIF Annual Report and will be used to inform the programme communication strategy that is currently under development.

Recommendations
1. DFID and HDIF to consider next year’s targets for all indicators and discuss options for increasing targets to ensure these are ambitious and stretching. HDIF to update all indicators that are cumulative to reflect performance this year in the targets for future years. To be completed by March 2018.
2. HDIF to finalise the Communication Strategy that includes (existing and potential) stakeholder mapping and targeting (including new private sector linkages). This should help inform future ecosystem support, including location of events and outreach and targeting of HDIF material and information. To be completed by April 2018.
3. HDIF to explore the value of hosting additional future events outside Dar es Salaam and discuss options with DFID HDIF team. To be completed by April 2018.
4. Building on the Hubs Research, HDIF to work with COSTECH and TANZIS programme to identify what role HDIF can play to assist and support the sustainability of innovation ecosystem-enabling organisations. To be completed by June 2018.
5. Following the publication of COSTECH’s new Science, Technology and Innovation Policy (expected to be shared for consultation in January 2018), HDIF should explore opportunities to boost the capacity and awareness of innovation across COSTECH and the Government, for example through events focused on young Government professionals or by targeting outreach that links innovation to industrialisation. To be completed by June 2018.

Output Title	HDIF has identified and catalysed the diffusion of innovations in human development
Output number per LF		2	Output Score	A+
Risk:		Major	Impact weighting (%):	75
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicators	Milestones	Progress
2.1 Percentage of applications submitted to HDIF that are eligible for consideration	7%	31% / 137 applications were received, of which 42 were considered eligible for scoring.
2.2 Percentage of HDIF funded projects that have achieved at least 80% of their output milestones	20%	25% / While calculating this result, HDIF observed that the wording does not allow for a true reflection of the performance of projects and is ambiquous. HDIF has recommended revised wording to ensure a more accurate reflection of performance.
2.3 Percentage of grantees who rate HDIF's assistance, input or collaboration as 6 or better on a 10-point scale	60%	92% / Data is collected through grantee’s quarterly self-assessment reports. Of the 36 grantees, 92% rated the TA from HDIF as six or higher.
2.4 Average speed to process funds requests from grantees after the first disbursement	28 days	27 days / Available data shows that it takes HDIF an average of 24 days from when HDIF complete a Payment Approval Form to disbursement of funds to a grantee. The policy is that a PAF form must be completed within 3 days of receiving a funds request.
2.5 Percentage of grantee self-assessment reports submitted to HDIF on time	75%	83%
2.6 Cumulative number of innovative approaches supported by HDIF focused on improving access to basic services for women and girls	9	14 (39% of grantees)
2.7 Cumulative number of funded innovations that are driven or enabled by ICT or mobile technology	15	24 (67% of grantees)
2.8 This indicator has been removed in the reporting period as agreed between HDIF and DFID.	NA	NA
2.9 This indicator has been removed in the reporting period as agreed between HDIF and DFID.	NA	NA
2.10 Percentage of work plan targets achieved by HDIF in building the capacity of Government of Tanzania in innovation fund management	60%	50% / Much of this work was completed via HDIF’s fund management consortium member, KPMG. However, the overall target was missed in large part due to changes ongoing during the reporting year within COSTECH (HDIF’s main GoT partner), including a change in the Director General and the update/revision of the Strategic Plan.

Summary of performance
This output measures and monitors HDIF’s core role: to effectively identify, select and support innovative human development projects through the innovation fund, and therefore is responsible for 75% of HDIF’s logframe results. Results for this year show that 8 of the 10 indicators have exceeded expectations, while two indicators were not intended to be measured this year as HDIF and DFID agreed that their measurement was no longer relevant.

Key highlights for the reporting year include the significant increase in eligible applications received for Round 3 funding. Of the 137 applications received, 42 (31%) were deemed eligible for consideration and scoring by technical advisers. This is much greater than the 7% target, and greater than the 8% and 18% recorded in Round 1 and 2 respectively. Unlike Rounds 1 and 2, Round 3 was specifically targeted at two areas of human development: early childhood development, and sanitation and hygiene. This allowed HDIF to target its outreach to potential grantees much more which is likely to have contributed to the increase in the quality of applications received. This is not uncommon and is seen in other challenge/innovation funds. Before contracts can be signed with Round 3 grantees, a fifth contract amendment (CA5) is required between HDIF and DFID. There have been some delays in finalising recent contract amendements (due to processes within both Palladium and DFID), however, the final action required for CA5 is internal DFID approval, which DFID Tanzania is leading. It is important this final step is done over the next few months to provide Round 3 grantees sufficient time to implement their projects and achieve results.

Another significant milestone for HDIF this year, is that this is the first year in which six grantees have reached the end of their grant period, and a ‘closing out’ process has ensued. As reported in the outcome indicators, five of the six grantees are considered to have their innovations adapted within three months after their grant has closed: MUHAS, CCBRT, APHTA, SNV, and Shirati KMT Hospital (three months has not yet elapsed for the sixth grantee, MSABI). Three grantess are currently under the close-out process and 18 are in their last year of implementation (with 10 expected to close by June 2018). It will be important for HDIF to learn from the first phase of close-outs to ensure a smooth process for these grantees. Good feedback was received from the site visits and interviews on the close-out process, with grantees suggested the HDIF team were helpful in providing details and schedules.
[note] The HDIF 2017 Annual Performance Report provides a detailed justification for why each of these projects are considered to be adapted.

Unsurprisingly, many grantees were optimistic in their implementation plans and project milestones have required updating to reflect delays in implementation due to many issues including delays in recruiting staff, school year cycles, changes in key Government personnel, changes in regulations and policies following the 2015 election, etc. HDIF has received ten requests for extensions and has approved nine in the reporting year, and anticipate another ten requests next year. This has had an impact on the measurement of performance against indicator 2.2, requiring the HDIF team to more actively ensure grantee logframes are updated when related budget or programmatic changes are approved by HDIF. Often project level indicators on logframes are not updated as regularly as HDIF and the grantee agree to changes to the implementation plan, resulting in a mismatch between the plan and the logframe.

Moreover, the measurement of indicator 2.2 is ambiguous. HDIF has recommended changes to the indicator in its Annual Report to ensure the indicator is useful and actionable. In addition to this, it is recommended that HDIF commit to updating project logframes more regularly so that the indicator accurately reflects performance of projects facing changing conditions and circumstances.

Key reflections from site visits and interviews
1. Feedback from grantees on the engagement and support from HDIF was overwhelmingly positive across all projects and locations visited. Grantees highlighted:
  1. The usefulness of having the funder (HDIF) in Tanzania (not located in London or Washington) which meant much more interaction and understanding of their project. The openness and transparent approach by HDIF programme managers was also praised, with a sense that HDIF is there to help rather than oversee progress (grantee and programme managers go work through things together).
  2. While reporting has been challenging for some grantees, it has helped them professionalise their systems with the support from HDIF. Some even claimed that halting payments until grantees met certain conditions/milestones was a good thing, as it focused the grantee’s attention to crucial areas.
  3. Technical assistance provided from technical experts in HDIF (health), Newcastle (education) and Loughborough (WASH) has in general, been seen as incredibly helpful (e.g. APHTA was a standout case). A number of grantees suggested it would be helpful to have TA contacts in Tanzania who understand the dynamic local context. There is some movement towards this in some sectors, but it depends on the talent available in the country.

1. Some areas identified where further support and attention from HDIF included:
  1. Business development technical assistance, particularly in the areas of:
    1. Financials and business models: some grantees need more support to help them understand the balance of costs and how to determine pricing within their business models.
    2. Business management: advice on software systems available that could support the grantees in monitoring their projects and analyse their data for business decisions.
    3. Follow-on funding opportunities: advice on funding opportunities and how to raise the next phase of finance is required for many grantees, including marketing and communications (this should build on HDIF’s work under output 3).
It was suggested that some of these skills could be shared amongst grantees themselves (e.g. Fundacion Paraguaya has a good process for how to set up a business (develop business plan, market research, understand costs, pricing, time to recover investments, risks etc.).

One challenge that may effect sustainability of projects is the pace of change in technologies, particularly ICTs. While simple technologies may be preferred due to cost and literacy, particularly in rural areas, these could go out of date within a few years and need replacing/upgrading.

Summary of responses to issues raised in previous annual reviews (where relevant)
Consider offering more targeted business related technical assistance to social enterprises, for example, in such areas as financial management and projections, marketing and branding, tax and legal issues.
Over the reporting period HDIF provided targeted support following requests/demand from the following grantees: Nelson Mandela African Institution of Sciences and Technology (NM-AIST); Maji Safi kwa Afya Bora Ifakara (MSABI); Dageno Girls Centre; Totohealth Ltd; Ubongo Learning Limited; and Association of Private Health Facilities in Tanzania (APHFTA).
Networking support to grantees, a highly-valued aspect of the project, should be extended from one-on-one linkages to a more systematic approach to providing linkages with financial institutions or brokers that may help facilitate grantees’ access to finance and to business entities that may help commercialise their innovations.
HDIF has been supporting grantees in mobilising additional financing to fund their innovations through providing references (both written and verbal). HDIF has assisted the likes of Shule Direct, Ubongo Learning and APHFTA mobilize grant funding from various organisations. Through HDIF support, some grantees have managed to engage financial institutions to raise additional funding (APHFTA’s credit line from EXIM Bank) or implement other initiatives (NMB’s Wajibu initiative implemented by Shule Direct).
In the third funding round, in the case of scale-up and commercialisation of projects, increase the required contribution to project funds and avoid 100% funding of innovations.
The selection process for Round 3 has taken this in consideration by avoiding instances of having non-established applicants that would fully depend on the grant to run their operations. Besides the ability to fund their operations, most applicants committed some level of counterpart funding in their applications.
A more complex new indicator on risk and risk management is planned for measurement in 2017.
This recommendation was addressed through updates to the HDIF risk register (Annex A) and the updated Value for Money framework.

Recommendations
1. DFID to prioritise securing internally approval for CA5 to ensure Round 3 grantees have sufficient time to implement their projects. To be completed by March 2018.
2. HDIF and DFID to agree to remove indicator 2.1, since no further funding rounds are anticipated and it will not be measured in future years. To be completed by March 2018.
3. HDIF and DFID to agree to the targets for indicator 2.2 based on HDIF’s proposed methodology. HDIF also commits to updating project logframe targets more regularly. To be completed by March 2018.
4. As grantees close-out (or are closed due to non-performance) in the coming year, there will be some resources and time available from HDIF programme managers to provide further support to current grantees on the areas identified above (e.g. business development, etc.). HDIF Team Leader should determine next year’s resources requirements and identify opportunities to HDIF to provide more business TA as needed by grantees. Options to be discussed with DFID by April 2018.
Output Title	HDIF has transformed the focus and quantity of evidence available to key stakeholders on the practice of innovation in human development
Output number per LF		3	Output Score	A+
Risk:		Major	Impact weighting (%):	15
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicators	Milestones	Progress
3.1 Cumulative number of analysis reports exploring and documenting innovation at national level (i.e. clustering and trends, mapping and systems, typology, language, etc.) produced by HDIF or its partners (including local hubs or conveners), disaggregated by percentage to incorporate findings on ICT, mobile tech, women, girls, jobs, or work skills	3 (66%)	5 (100%) / Analysis reports attributed to this reporting period are: / Hubs of Hubs research / Innovation Ecosystem Map Analysis Report
3.2 Cumulative number of learning documents developed by HDIF or HDIF grantees on grantee innovation diffusion and challenges, and disseminated to stakeholders, disaggregated by percentage to incorporate findings on ICT, mobile tech, women, girls, jobs, or work skills	5 (60%)	18 (100%) / Learning documents developed and disseminated in this reporting period are: / Two HDIF White Papers on gender and innovation, and scaling digital technology / Three Digital Principles into Practice case studies / Five HDIF grantee case studies
3.3 Percentage of learning documents developed and disseminated by HDIF, HDIF partners, or HDIF grantees on the diffusion or challenges of grantee innovations with a dissemination strategy that results in mass media coverage	40%	70% / Seven of the ten learning documents produced and disseminated resulted in media coverage.
3.4 Cumulative number of engagements held with other funders about participating in HDIF operations (including collaboration in outreach, co-funding grants, ecosystem, or evidence-generating activates, or co-funding HDIF with DFID), sharing lessons learned or generating evidence on grant making to support innovation in human development	10	46 / During the reporting period, HDIF engaged in 23 meetings and 8 events with a range of funders and policymakers in Tanzania.
3.5 Percentage of partners in learning and insight generation who rate HDIF's assistance, input or collaboration as 6 or better on a 10-point scale	60%	100% / Data collected via a survey sent to 23 stakeholders, 8 responded. Of the 8, all rated HDIF’s input as 6 or higher.
3.6 HDIF explores and encourages potential scaling of HDIF innovations within DFID's portfolio by sharing experiences and evidence with related DFID programmes	2	7 / Programmes and interactions reported this year include: EQUIP-T, I4ID, Ideas 2 Impact, EdTech, E-Water, DFID Digital Services Team, and DFID Advisers retreat.
3.7 Percentage of work plan targets achieved by HDIF in building the capacity of Government of Tanzania (including COSTECH) in knowledge management	60%	43% / Implementation of the work plan activities has been limited by the availability of GoT (mostly COSTECH) staff.
[note] This indicator measures the total number of reports with at least 1 mass media outlet covering the information or dissemination. Mass media coverage is defined as any media coverage that reaches a large number of people.

Summary of performance
This output measures and monitors HDIF’s work strengthening the evidence base on innovation for human development outcomes, and supporting the translation of findings and lessons learned from HDIF into policy and practice. This output is intrinsically linked to the work to strengthen the ecosystem under output 1 and its important that the two are aligned (e.g. research and evidence is targeted to ecosystem stakeholders), for example by aligning the Communication Strategy being developed under output 1 with the Knowledge Management Strategy and Roadmap being developed under output 3. The HDIF team are actively thinking about this.
Activities under this output for the reporting year have increased tremendously, and 6 of the 7 indicators have exceeded expectations. The only indicator that has not been met is the one that relys on availability and buy-in from the Government, and given the ongoing changes in personnel, it is unsurprising that this has not been achieved this year. Key highlights for this year include: two White Papers (Gender and Digital); three Digital Principles in Practice reports; 5 grantee case studies; Hubs of Hub research; updated and more detailed innovation ecosystem map; and research underway on edtech and e-water. All published reports and papers were disseminated widely through a variety of events and to a variety of stakeholders.

The outputs under this area of work have been impressive and have led HDIF to be seen as a leader, not just within Tanzania, but more globally, on many key issues related to innovation and development. HDIF’s championing of the digital principles is an excellent example. Introduced to HDIF by its DFID counterparts as valuable guiding principles all HDIF activities, partners and grantees should apply, HDIF commited to bringing the principles into the programme, and build capacity and understading around the use of the principles to support best practice amongst its stakeholders. HDIF hosted an event during Innovation Week to introduce the principles to partners and provide the space to discuss their relevance in Tanzania. The team followed this up with a survey to a representative group of attendees. Throughout the reporting year, HDIF has been engaging with the “lead” on the Principles – the Digital Impact Alliance (DIAL) as well as DFID’s Digital Service team in the UK to feed in valuable findings from its partners on putting the digital principles into practice. This led to DIAL opting to have a Practicing the Principles event in October 2017 in Tanzania, with the event co-hosted by HDIF. In addition, DFID’s recently launched Digital Strategy includes a number of case studies from HDIF to demonstrate the value of the principles. It is worth noting, HDIF case studies are regularly used by teams across DFID and other development partners to illustrate the impact of innovation for development outcomes, and HDIF are increasingly requested to share their experiences with other DFID programmes – as demonstrated by indicator 3.6 above.

The Gender White Paper also received excellent feedback by many interviewees, but it has been less obvious what the next steps are in terms of dissemination to influence and feed into global best practice on gender and innovation. To date the team have been opportunistic, hooking knowledge products into other agendas (e.g. International Day of the Girl) in an attempt to attract a wider audience. The new Communication Strategy should support more targeted dissemination activities, not just within Tanzania, but globally.

Some challenges exist in the methodology/definitions used for some of the indicators which requires further discussion between DFID and HDIF, including:
1. Definition of “mass media coverage” is ambiguous (“any media coverage that reaches a large number of people”).
2. Definition of “analysis report” and “learning document”. HDIF has provided recommendations in its 2017 annual report for DFID to consider.
3. Ensure HDIF and DFID are clear on what is included as “engagements” (3.4) and how 3.6 is measured (by activities/engagements, DFID programmes or by types/kinds of lessons/evidence shared).

Key reflections from site visits and interviews
The knowledge products disseminated by HDIF this year, particularly the White Papers on gender and digital principles, as well as the Hubs of Hubs research and Ecosystem Mapping received positive feedback from ecosystem stakeholders. One stakeholder commented that the gender report has been particularly valuable for them, and has been used to fine-tune their own strategy and for awareness raising and fundraising purposes.

The survey on digital principles highlighted that many found the principle on being open (using open data, open standards, open source, open innovation, etc.) the most difficult to comprehend. This was echoed in many conversations with stakeholders – that there is a reluctance in Tanzania to be open, particularly arising from a fear that others might steal your idea. While there was a suggestion that this may be changing in the younger generation, there was still some nervousness to being open. This is also reflected in the recent move by the Tanzanian Government to withdraw from itself from the Open Government Partnership (OGP) in June 2017. Looking forward, this may be an area HDIF want to explore with future research and evidence in the value of openness for promoting innovation for development outcomes.

Some interviewees, including the Mawazo Challenge team, praised HDIF’s approach to learning and support to document learnings from partners. It was suggested that other important parts of the ecosystem (such as the Government and BUNI Hub) don’t tend to document and share learnings with the wider ecosystem. This may be an area HDIF explore going forward, particularly under indicator 3.7.

Summary of responses to issues raised in previous annual reviews (where relevant)
Prioritise research and advocacy activities on specific policy issues within the gender and ICT clusters (e.g. use and impact of tablet computers in education) or other issues on which grantees jointly are working.
This was addressed during the reporting year through the various research projects launched, including: the use of tablets to improve learning outcomes among pre-primary, primary and secondary schools in the country (working with four grantees); the effectiveness, sustainability and scalability of pre-paid water solutions (working with two HDIF grantees and another DFID funded project); and how innovation is helping women and girls to access better-quality services to have a greater ability to make decisions, to drive change and to influence others. All these research project have been making links to policy makers in Tanzania.
Identify ways in which project outcomes – or signs of success in achieving project outcomes – in terms of improvement of quality, access or value for money of basic services or likelihood of sustainability and replicability can be identified earlier during grant implementation. Project annual reviews could be a mechanism for this type of measurement.
HDIF conducts annual reviews for each of its grantees during which it assesses grantees performance and, when relevant, assesses improvement of quality, access or VfM of basic services. The likelihood of sustainability and replicability of the grantees innovations is also assessed during the annual reviews. Moreover, HDIF requires and supports its grantees to develop project sustainability plans. These plans are usually reviewed during the grantees annual reviews and, if necessary, revised after the reviews.
In future ecosystem mapping exercises, widen the scope to examine innovation activities within more mainstream health, education and WASH research institutions and within the private sector. Review logframe indicators where data on outcomes and impact might be disaggregated by gender.
During the reporting year, HDIF focused on improving the quality of the map data, doing further analysis of the map data and sharing the findings of the mapping exercise to stakeholders. HDIF is planning to outsource the management of the map to another organisation through a competitive tendering process. This will be supported by a ToR that will include future mapping activities. The recommendation above will be taken into consideration when developing the ToR.

Recommendations
1. HDIF to update all indicators that are cumulative to reflect performance this year in the targets for future years. To be completed March 2018.
2. HDIF and DFID to discuss methodologies/definitions within indicators 3.1, 3.2, 3.3, 3.4 and 3.6 to ensure common understanding. To be completed March 2018.
3. HDIF to align the Communications Strategy with the Knowledge Products Strategy and Roadmap to ensure knowledge products are disseminated effectively to the right audience at the right moment (as much as possible). To be completed April 2018.
4. HDIF to follow up the Gender White Paper with working with grantees on incorporating the findings into their individual projects. HDIF should also do a refresh of gender with all HDIF staff (following a number of staff changes recently). To be completed by June 2018.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
During the reporting period, the key costs under the programme were the grants to projects (roughly 67%), followed by the costs of consultants hired through Business Advisory Fund (19%). Long-term personnel and operating costs have contributed about 9% of total spend this year. A proportion of the payment to HDIF is made on meeting milestones (all of which have been met on time this reporting year).

VfM performance compared to the original VfM proposition in the business case
HDIF has revised the VfM framework based on the previous Annual Review recommendations. The revised version was shared with DFID in September 2017. DFID’s SRO consulted with DFID Tanzania’s Economist before approving the framework.

Economy
Economy is measured by an assessment of unit costs (fee rates, hotel costs, vehicle hire, flight costs, cost of events) and realised, monetised cost savings.
- This year unit costs have been benchmarked against another DFID funded, Palladium implemented programme (Institutions for Inclusive Development) where possible. While some unit costs under HDIF are slightly higher than I4ID (notably related to travel and accommodation), fee rates for key HDIF personnel (Team Leader; Communications Specialist; Monitoring, Evaluation and Learning Specialist) are significantly lower.
- By seeking out at least three quotes when procuring goods and services, HDIF has managed to make a total of £33,577 of savings this reporting period. This is calculated as the average of highest bids values minus the average of HDIF selected (awarded) bid values.

Efficiency
Efficiency is measured by the budget execution rate (the proportion of the forecast budget that was actually spent) and the percentage of management/administration costs of total costs.
- For the reporting period, the budget execution rate was 54% - driven mainly by the deployment of grant funding to the projects (67% of the costs, but achieved an execution rate of 53% this year). As with many other challenge funds, innovative projects and grantees are often overly ambitious and face unforeseen challenges during their project lifetime which inevitably has an effect on funding dispersals. It is recommended HDIF push grantees on their budgets and forecasts at the beginning of each reporting period to improve this ratio.
- Management/administrative costs include costs for all key HDIF personnel (e.g. Project Director, Team Leader, Director of Finance, Driver Costs, Office Attendant). This year, management/admin costs were 4% of total costs.

Effectivenes
Effectiveness measures the transition from outputs to the programme’s outcome and impact objectives. It is measured using four indicators:
- Percentage of grantees achieving at least 80% of their output milestones (indicator 2.2 in the logframe), which measures the extent to which grantees are successful in achieving their set output targets measured. The result is 25% in this reporting period.
- Grantee’s matching commiments as a proportion of total value of grants by HDIF (as a measure of cost-effectiveness of HDIF). The result is 32% in this reporting period.
- Number of HDIF supported initatives that have produced evidence suggesting their contribution to improved basic services, which measures the extent to which innovative ideas, products and models developed or supported by HDIF have positively impacted basic services in Tanzania. An initiative is considered to have "contributed" to the improvement of basic sevices if there is evidence that it has improved either quality, VfM or access to basic services within 3 months of close-out. As such, this only applies to those grantees who have gone through the close-out process and at least 3 months has elapsed. The result is 5 for this reporting year.
- Average budget per grantee in the current portfolio as a proportion of average budget per grantee that was originally intended (i.e. cost-effectiveness of programme). The result for this reporting year is 33%.

Equity
HDIF’s three equity indicators are all focused on gender. It would be valuable to explore additional equity concerns and associated indicators, such as poverty/income, marginalised groups/ regions, children and youth. The three gender indicators are:
- Proportion of programme technical advisors (long-term and short-term) who are female. The target of this indicators is 50% with a variance of 5%. The programme was on target this year, with a result of 49% (18 female technical advisers and 19 male). The team may wish to consider measuring the use of Tanzanian versus international technical advisers in future.
- Proportion of instances in which HDIF’s bid review team included at least one female member, which measures the extent to which HDIF involves its female staff in decision making processes. This year, in all nine bid review processes, a female was on the panel/involved. In four of these instances, female representation was 50% or more.
- Number of people (grantee staff and stakeholder representatives) trained on HDIF's gender resource pack, which measures the efforts made by HDIF in building the capacity of its grantees and strakeholders on gender equity in innovation ecosystem. This reporting period, 13 HDIF staff (8 male and 5 female) have been trained on the gender resource pack. No grantee staff and other stakeholder representatives have not been trained on the pack this year.
There is also scope to consider gender considerations in relation to all the grantees and innovations that are supported, and whether or not they disproportionately disadvantage one gender over the other.

Assessment of whether the programme continues to represent value for money
The programme is assessed as continuing to represent value for money, particularly as this year, the programme has began to record outcome achievements and is producing valuable knowledge products to disseminate lessons and finding from the programme and grantees to date. Only one of the 36 contracted grantees has had to close early due to poor performance, and one is currently on a Performance Improvement Plan (PIP). These achievements have been made while HDIF has continued to perform well against VfM indicators as described above. For future years and assessments, it would be helpful to include targets for each of the VfM indicators to assess rates of improvement.

As suggested in the last Annual Review and by a number of grantees this year, HDIF should continue to review the balance between international and national technical advisers to establish whether greater value for money and impact could be achieved with greater utilisation of Tanzanian experts.

Quality of financial management
Some challenges with forecasting have persisted over the reporting period. During this period Palladium changed its internal financial systems, which presented specific issues in forecasting. Additionally, given that grants are roughly 67% of the funding for this reporting year, and (as with most challenge funds) grantees tend to be overly ambitious about what they can achieve by when, it is likely that delays from the grantees are causing the challenges with accurate forecasting for HDIF. HDIF should continue to “risk adjust” grantee disbursements when forecasting spend. This is critical for DFID who require more accurate financial forecasting throughout the year.

The financial audit for the period from 1 September 2015 to 31 August 2016 was finalised during 2017, and the audit report and management letter have been shared with DFID. HDIF received an Unqualified Audit Opinion since there were no major findings observed. The 2017 financial audit is expected in February 2018.

Date of last narrative financial report	November 2017
Date of last audited annual statement	March 2017

E: RISK (½ page)

Overall risk rating: Major: given the nature of the programme (a challenge fund supporting innovative, high risk/potential high impact projects).

Overview of programme risk
The risk register has been updated following a review of DFID Tanzania’s risk management processes and recommendtions from the pervious Annual Review. It is available in Annex A. The new register categorises risks as programmatic, financial or operational. No risk is rated higher than “moderate” following mitigation actions. Risks that are deemed moderate include:
1. Risks associated with the impact of the grantees and their projects/innovations, such that impact will not be demonstrated during the lifetime of HDIF from projects given the time required for most innovations to be scaled up; or that some innovations funded are not sustainable without on-going donor support.
2. Financial risks associated with misuse of DFID funds (fraud, corruption, etc.), and macro economic changes resulting in exchange rate flucatations or reduction in DFID commitments.
3. Risks associated with the uptake of lessons and evidence from all stakeholders, particularly Government of Tanzania, which negatively effect achievement and sustainability of impacts.

Outstanding actions from risk assessment
The DFID SRO and Programme Manager should review the risk register (Annex A); it could be condensed further. The risk owner should be reviewed and agreed, with a mind to determine where DFID or other partners might be responsible for managing the risk. The appetitie column is not entirely clear (with yes/no response) and may need further narrative. As per DFID’s updated guidelines, risks should be categorised as: delivery, operational, fiduciary, context, reputational or safeguarding. Finally, an overarching risk appetite statement for the programme is required.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
The programme has met delivery/milestone targets this year, however, a greater focus on accuracy of forecasting throughout the year would be welcomed.

Performance of partnership(s)
Feedback from the DFID team, stakeholders interviewed during the review, and evidence from engaging with the HDIF team during the review, suggests the performance of the partnership between DFID and HDIF is strong. The quality of the HDIF team (including all consortium partners) is very high, particulary the programme management and management teams. The team is technically strong; understand the external environment well; are realistic about opportunities and potential of the programme; and have strong and trusting relationships with both grantees and ecosystem partners. Changes in key personnel in HDIF’s key partners (DFID and the Government of Tanzania, particularly COSTECH) have brought some challenges for the delivery of the programme, including delays to contract approval and uncertainty on future activities. However, these challenges should lessen over the coming year. The team will also need to continue to be close to grantees and ecosystem partners to remain adaptable to any changes or needs in the ecosystem (particularly as new programmes are implemented – such as TANZIS), to ensure HDIF support can be leveraged effectively.

Asset monitoring and control
Asset registers are maintained for each grantee and reported in quarterly updates and in funding requests. These are validated roughly annually by KPMG and HDIF when they undertake an expenditure verification or a spot check. Assets are also verified during the close-out process, which includes recommendations on how assets should be handled after the grant has formally closed. HDIF then follows-up on these recommendations after 3 months and takes necessary action if the recommendations have not been addressed.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)
Not applicable.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation
The programme’s theory of change is described in the logframe (and digramatically in Annex B). While the diagram is limited with respect to assumptions underpinning the ToC, the assumptions within the logframe are appropriate and relevant, particularly the support required from Government (notably COSTECH) in leading the innovation agenda and private sector’s engagement in the ecosystem. These remain two crucial challenges to HDIF building the ecosystem versus HDIF being the ecosystem – without these two crucial stakeholdes playing a role, it is uncertain how the ecosystem itself will grow and develop once HDIF has closed. It is important the theory of change and assumptions continue to be updated to help to build an effective HDIF legacy and exit strategy for the coming years.

In addition to the evidence HDIF is generating through its fund management (shared via grantee case studies) and the learning papers and analysis reports highlighted in output 3, HDIF also is involved in two research projects inputting lessons from innovations its supporting: research on e-water or pre-paid systems for rural water supply; and research on the use of tablets to support educational outcomes.

e-Water Research
The e-Water research project is being undertaken by the Nelson Mandela African Institute of Science and Technology (NM-AIST) in collaboration with WEDC to evaluate the contribution of pre-paid systems to the functionality and sustainability of rural water systems in Tanzania as well as the potential of pre-paid systems to improve the current challenges of rural water supply. The study will look at pre-paid water solutions currently being tried in the rural districts of, Dodoma (Water Mission), Babati (E-Water pay Ltd), Karatu (Catholic Relief Services) and Kishapu (ICS and Susteq) districts in Tanzania and will seek to make recommendations to the Government of Tanzania as to the viability of pre-paid water systems as a solution for improved water supply in rural parts of the country. The study itself is expected to take place from November 2017 and March 2018 with dissemination activities also planned.

Education Technology
As part of the KM strategy, HDIF is partnering with Newcastle University to carry out research on the use of technology to support education outcomes in Tanzania. Titled ‘Understanding Teacher and Student Perspectives on the Use of Tablet Computers and Innovative Teaching Methods’ the research will explore the use and impact of tablet computers from 1 March 2017 to 9 September 2018 and is currently focused on grantees: CAMFED, CSSC, Shule Direct and World Vision. Initial findings suggest that the success or failure of the tablet is, to a certain extent, largely dependent on the teachers and how well they are trained, supported and motivated. the next period data will be collected from Shule Direct and World Vision.

Monitoring progress throughout the review period
Progress with key HDIF partners (grantees, COSTECH and Mawazo Challenge consortium) is monitored through annual reviews, quarterly reporting and site visits (as required). Quarterly reports are reviewed by the project’s specific HDIF contact point/programme manager and the technical adviser. All reports are reviewed and signed off by the Team Leader, who maintains an escalation list for challenging projects and fortnightly updates from the HDIF lead. Those projects on the escalation list are required to have a six monthly check in with an executive level employee of the project and the HDIF Team Leader.

HDIF provide quarterly narrative and financial reports to DFID Tanzania. Monthly meetings are also held between the HDIF Team Leader and the DFID Tanzania SRO and Programme Manager to monitor progress throughout the year.

Key tasks undertaken this year to support effective and accurate Monitoring, Evalution & Learning (ME&L) processes include:
- Hiring of a ME&L Specialist, who joined the HDIF team in July 2017
- Revising the logframe in response to last year’s Annual Review and to ensure programme indicators are non-ambiguous, clearly defined and measurable
- Development of an electronic Information Management System (IMS) to enable HDIF’s staff to enter, securely store and efficiently retrieve data on programme and project performance
- Development of Data Quality Assessments for grantees to ensure more accurate and timely information and data capture from grantees to HDIF and HDIF to DFID

ME&L priorities for the next year are: implementation of the programme’s learning agenda; provision of ME&L support to Round 3 grantees; assessing grantees data quality (Data Quality Assessments); and continued measurement of the programme’s performance.

Annual Review process
This review was undertaken by three DFID staff members: Leanne Jones, Climate and Environment Adviser, DFID Tanzania led the annual review process with support and inputs from Daryl Burnaby, Health Adviser in DFID London and Natalie Smith, Deputy Team Leader, Human Investment Team, DFID Tanzania. The review included field visits to a sample of HDIF projects and partners in Mbeya, Iringa and Dar es Salaam during November and December 2017. Further meetings were conducted with HDIF staff and other key stakeholders, including various officials from the Government of Tanzania.

Annex A: Risk register

Risk Number	Risk Category	Risk Description	Risk Impact	Risk Likelihood	Gross Risk Rating	Mitigation Actions	Detailed Residual Risk Impact	Detailed Residual Risk Likelihod	Gross Residual Risk Rating	Appetite	Change/Trend	Risk Owner
1	Programmatic Risk (Impact)	The public benefits are insufficient to justify providing public money to profit makers	Moderate	Possible	Major	1) Include 'public benefits' among the criteria to guide the selection of innovations funded by HDIF 2)Fund applications that are most likely to result in public benefits 2) Closely monitor the performance of funded innovations and support grantees in meeting their intended objectives	Minor	Minor Impact Unlikely Occurance	Minor	Yes	Most funded innovations are currently on track or have achieved their planned results. It is still possible that a few innovations may fail to demonstrate public benefits. The programme's mitigation measures have been successful in keeping the number of unsuccessful innovations down and thus reducing the impact of this risk. As the program moves on to the third round of funding it foresees a reduction in the likelihood of this risk	Team Leader
2	Programmatic Risk (Impact)	Investments exacerbate or create new gender inequities and geographical	Major	Unlikely	Moderate	1) Carefully assess funding applications to make sure that funded innovations do not exacerbate or create new gender or geographical inequities 2) Closely monitor HDIF-funded innovations and assess whether they exacerbate or create new gender or geographical inequities 3) Redesign or terminate innovations that exacarbate or create new gender inequities	Minor	Rare	Minor	Yes	A close monitoring of HDIF funded innovations shows that this risk has been well managed. The risk's mitigation measures will be applied to the innovations funded in the programme's third round of funding and, if successful, the likelihood and impact of this risk will decrease.	Team Leader
3	Programmatic Risk (Output 1 & Output 2)	Due to a small innovation ecosystem, grant funding goes to a few clusters of informed individuals or institutions with knowledge of innovation, technology, applied research, cross-sector collaboration, or HDIF funding requirements	Insignificant	Possible	Major	1) HDIF works on inspiring more players in the innovation ecosystem to come up with innovative ideas 2) HDIF conducts effective outreach activities during funding rounds 3) HDIF works on having a good mix of its fund recipients during funding rounds 4) Consistently conduct fiduciary risk assessments	Insignificant	Unlikely	Minor	Yes	Despite this risk's insignificant impact, HDIF works on decreasing the likelihood of its occurance and its mitigation measures have, to a large extent, been successful	Team Leader
4	Programmatic Risk (Output 2)	Timeframe too short to demonstrate impact or for promising approaches to be scaled up or adopted	Major	Possible	Severe	1) Assess innovations proposed timeframes during funding applications reviews and revise if necessary 2) Closely monitor implemented innovations and offer extensions whenever necessary 3) Support grantees in developing sustainability plans for the innovations 4) Require grantees to submit sustainability plans during project closeout 5) Handover project assets during closeout if the grantee demonstrates capacity and willingness to continue with implementing the innovation	Moderate	Unlikely	Moderate	No	With time, programme stakeholders have learned to be more realistic as to what can be achieved during projects durations and to plan accordingly. Thus, although the likelihood of this risk may stay the same, its impact may can decrease.	Deputy Team Leader
5	Programmatic Risk (Output 2)	Funding recipients lack the skills and capacity to pilot or scale up approaches, including M&E and financial management capacity	Major	Possible	Severe	1) Conduct Organizational Capacity Assessment (due diligence) for pre-approved organizations during funding applications review 2) Provide technical support to grantees in M&E, financial management capacity etc. 3) Have grantees rate technical support provided by HDIF 4) Improve HDIF's technical support based on grantees' feedback	Minor	Rare	Minor	Yes	The programme has witnessed an increase in the capacity of its funding recipients - partly attributed to its technical support. Moreover, in its third round of funding, the programme targets larger, more established and more capable organizations. The likelihood and impact of this risk will therefore decrease with time	Deputy Team Leader
6	Programmatic Risk (Output 2)	Certain interventions funded are not sustainable without on-going donor support	Moderate	Likely	Major	1) Support grantees in developing sustainability plans 2) Require that grantees share their sustainability plans during closeout 3) As much as possible, support grantees on working towards having their innovations taken up by existing public and private systems and structures	Moderate	Unlikely	Moderate	Yes	The programme has had its first closing projects/innovations this year and the rating of this risk hasn't changed.	Deputy Team Leader
7	Programmatic Risk (Output 2)	Approach to the programme differs amongst the grantees and the Fund Manager	Moderate	Possible	Major	1) Build capacity of HDIF's programme managers 2) HDIF's programme managers and other staff clearly communicate programme's approach to grantees and other stakeholders 3) Closely monitor grantees/key's stakeholders' approach to the programme	Minor	Rare	Minor	Yes	As the HDIF moves into later years, there is a better understanding of its approach among its key stakeholders. The occurance of this risk will soon be unlikely	Deputy Team Leader
8	Programmatic Risk (Output2)	Programme unnecessarily duplicates or overlaps with other on-going activities.	Moderate	Possible	Major	1) Include innovation's uniqueness among the scoring criteria of funding applications 2) Have multiple, experienced and well-read reviewers score funding applications 3) Closely monitor funded innovations to ensure that they are impletemented as planned and provide feedback to grantee 4) Remain secretary of DPG-IT meeting 5) Involve government in designing projects	Minor	Rare	Minor	Yes	The occurance of this risk is still possible and its impact moderate. Gross rating of this risk may change as HDIF moves onto its third round of funding	Team Leader
9	Programmatic Risk (Output 2)	Funds spread across too many projects or solutions to measure overall impact.	Moderate	Possible	Major	1) Limit the number of funded projects/innovations/solutions to a number that can effectively be managed by the programme considering available resources. 2) Select SMART impact indicator(s) for the programme 3) Devise a clear methodology to measure programme's impact indicator(s) 4) Allocate resources towards measurement of the programme's impact indicators	Minor	Rare	Minor	Yes	The programme's mitigation measures have been successful in managing the impact and likelihood of this risk. The likelihood of this risk may increase as HDIF moves to the third round of funding but only by a small degree since some innovations funded in the programme's previous rounds will be closing.	MEL Specialist
10	Programmatic Risk (Output2)	Grants awarded by HDIF distort or cause harm in the education, health and WASH market systems	Moderate	Unlikely	Moderate	1) Closely monitor HDIF-funded innovations for any undesirable effects 2) Terminate funding for innovations that distort or cause harm in the education, health and WASH market systems	Minor	Rare	Minor	Yes	So far, there has not been a case where an innovation funded by the HDIF distorts or cause harm in education, health or WASH market systems. HDIF therefore expects the likelihood of this risk to decrease with time.	Deputy Team Leader
11	Programmatic Risk (Output 3)	Lack of GoT commitment to support innovation or collaborate in the project, leading to slow decision making, operating in silos and lack of engagement of government stakeholders	Major	Possible	Severe	1) Involve GoT in the design of the programme 2)Build the capacity of GoT in innovation ecosystem management 3) Share programme lessons and progress with GoT	Moderate	Unlikely	Moderate	No	The occurance of this risk is still possible and its impact major. Both the likelihood and impacto of the risk are expected to decrease as HDIF experiences more buy-in from GoT.	Strategic Partnership Advisor
12	Programmatic Risk (Output 3)	HDIF’s risk taking theory of change with assumed failures and a focus on learning is not reflected by UKAid stakeholders	Moderate	Unlikely	Moderate	1) Document and clearly communicate HDIF's theory of change 2) Document and clearly communicate evidence supporting HDIF's theory of change 3) Document and disseminate lessons generated by implementing HDIF's theory of change	Moderate	Rare	Moderate	Yes	As the programme demonstrates concrete achievements, both the impact and likelihood of this risk will decrease	Strategic Partnership Advisor
13	Programmatic Risk (Output 3)	Limited interest from the private sector and government in service delivery and partnerships.	Major	Unlikely	Moderate	1) HDIF works on inspiring the private sector to engage in the innovation ecosystem 2) HDIF shares its lessons and success with the private sector 3) HDIF effectively cultivates, manages and nurtures its relationships with the private sector and other key stakeholders 4) HDIF's conducts effective outreach activities during its funding rounds 5) HDIF puts in place mechanisms to reduce risks that can be encountered by its partners	Major	Rare	Moderate	No	The occurance of this risk is still unlikely. HDIF continues to cultivate and maintain successful partnerships with the private sector and it is possible that the impact and likelihood of this risk will decrease	Team Leader
14	Programmatic Risk (Output 3)	HDIF fails to disseminate clear lessons learned from funded innovations	Moderate	Rare	Moderate	1) Asign a role within HDIF team for disemmination of lessons 2) Develop a dissemination plan for lessons generated from grantees 3) Allocate a budget for dissemination of lessons from innovations that do not continue to scale	Insignificant	Rare	Minor	Yes	The occurance of this risk is still rare and expected to remain so	Strategic Partnership Advisor
15	Fiduciary Risk	Fraud, corruption or misuse of DFID funds	Major	Possible	Severe	1) Conduct due diligence for pre-approved organizations during funding applications review 2) Clearly stipulate how issues related to fraud, corruption or misuse of DFID funds are going to be dealt with in grant agreements 3)Grantees develop implementation plans and budgets that are then approved by HDIF 4) Require and ensure that grantees submit financial and programmatic reports to HDIF on a quarterly basis 5) Periodically conduct grantee expenditure verifications 6) Disallow expenditures that are not in accordance with agreed purpose 7) Terminate grantees that are involved in fraud or corruption	Moderate	Rare	Moderate	Yes	Despite the possible occurance of this risk, the programme's mitigation measures have been successful and any resulting residual risks are of a rare occurance and moderate impact	Team Leader
16	Financial Risk	Donor funding may be cut off, reduced, or slowed in approval disbursement due to changes in policy	Severe	Possible	Severe	1) Prioritize funding to grantees with matching resources to implement the innovations 2) Share HDIF lessons with other donors 3) Support grantees in developing their sustainability plans 4) Require that grantees share their sustainability plans during closeout 5) Encourage and support grantees in sharing their lessons and success to other donors 6) Encourage and support grantee in applying for funds from other donors	Severe	Rare	Moderate	Yes	The likelihood of this risk is expected to increase with time. HDIF will closely monitor this risk and work on identifying additional mitigation measures if necessary.	Team Leader
17	Financial Risk	Macroeconomic conditions change due to exogenous shocks (e.g. global recession, rising food prices) leading to increase in inflation rate, or fluctuation in exchange rates between sterling, US dollars and Tanzanian shillings	Severe	Possible	Severe	1) Take into account possible changes in inflation rate and exchange rate when developing budget forecasts	Moderate	Unlikely	Moderate	Yes	The impact of this risk is still severe and its likelihood possible. HDIF will closely monitor, manage and, if necessary, adjust its rating	Deputy Team Leader &Director of Finance and Administraton
18	Financial Risk	Delays in reporting fund use from grantees delays reporting of finances and impact to DFID and key stakeholders	Minor	Possible	Major	1) Document grantee reporting dates and communicate these dates with the grantees 2) Remind grantees when reports are due 3) Closely track grantee reporting and provide feedback to grantee	Insignificant	Rare	Minor	Yes	There has been a few cases of delayed reporting from grantees but they haven't resulted in delayed reporting of HDIF's finances and progress to DFID. HDIF will continue mitigating this risk with the plan to further decrease its likelihood.	Program Managers
19	Operational Risk	Due to the unique nature and theory of the programme, HDIF is unable to attract and retain quality staff with a shared vision for its outcomes	Major	Rare	Moderate	1) Develop high quality ToRs to include in HDIF's job adverts 2) Develop SoPs to guide the recruitment process ensuring that it is of high quality and merit-based 3) Conduct thorough due-diligence as part of recruitment 4) Offer competitive remuneration to HDIF staff 5) Make proffessional development and capacity building core to HDIF's culture 6) Provide constructive feedback to staff both formally and informally whenever relevant 7) Staff to develop result-based performance plans on an annual basis 8) Staff KPI are revised to reflect changing roles within the team 9) Supervisors to work with staff in monitoring and updating staff's perfomance plans	Minor	Rare	Minor	Yes	With time, the programme has managed to strengthen mitigation measures for this risk and reduce its likelihood. The occurance of this risk is expected to remain rare albeit with a high impact.	Director of Finance and Administration
20	Operational Risk	The Investment Committee is not perceived as being independent	Moderate	Unlikely	Moderate	1) Involve multiple people in the selection of investment committee members 2) Require that investment committee members declare any conflict of interest 3) select investment committee members solely on merit basis	Minor	Rare	Minor	Yes	Going into its third round of funding, HDIF uses lessons generated from its previous rounds of funding to improve the management of this risk. The occurance of this risk is expected to decrease further and its impact to remain moderate	Team Leader

Annex B: HDIF Theory of Change