 Annual Review

Title: Human Development Innovation Fund – Tanzania (HDIF)
Programme Value £ (full life): £39,787,725		Review Date: January 2020
Programme Code: 203539	Start Date: January 2013	End Date: July 2021

Summary of Programme Performance
Year	2013	2014	2015	2016	2017	2018	2019	2020	2021
Prog Score	B	A	A+	A+	A+	A+	A+	A+
Risk Rating	Moderate	Minor	Major	Major	Major	Major	Moderate	Moderate

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-203539/documents
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-203539/documents

A. Summary and Overview (1-2 pages)

Description of programme (1/2 page)
The Human Development Innovation Fund (HDIF) aims to improve outcomes in education, health, and water and sanitation in Tanzania by funding and promoting innovations with the potential to transform the delivery of basic services. Since its inception in 2013, the programme has funded 43 grantees through three rounds of funding. Twelve grants are currently active. In addition to funding grants, the programme supports the development of Tanzania’s innovation ecosystem by promoting cross-sector collaboration and learning on innovation for human development. The programme is managed by a consortium led by Palladium Group, with the Institute of Development Studies (IDS), Loughborough University, and KPMG, and has its key government partner in the Commission for Science and Technology (COSTECH), under the Ministry of Education, Science, and Technology (MoEST).
[note] An innovation ecosystem is the diverse range of resources and participants that are necessary for continuous innovation in an economy. These include investors, entrepreneurs, technical and business development service providers, the public sector, innovation spaces, and researchers amongst others.

This year the HDIF programme saw significant change, with the Palladium Project Director, Team Leader and Project Manager all leaving post, as well as 7 grants reaching the end of their implementation. The programme also “pivoted” its approach, in response to the 2019 Annual Review and reflecting the stage in the programme cycle, to focus more staff and programme resource on influencing, coalition building, and lesson sharing with government, the private sector, and other donors in order to promote further development of the innovation ecosystem post programme implementation.

This year’s annual review takes place with 1.5 years of programme implementation remaining. Given this, and the changes to the programme this year, the 2020 Annual Review set out to answer three overarching questions:
1. Is the HDIF programme on course to achieve sustainability of its interventions and results (including sustainability of grantee innovations as well as the overall promotion of innovation in Tanzania)?
2. Do the theory of change and logframe remain relevant and useful after 6 years of intervention to support the innovation ecosystem? What outputs should be prioritised and measured in the final year of the programme to ensure HDIF maximises results and opportunities for sustainability?
3. Has the HDIF programme continued to deliver strong results with a major change in leadership?

Summary supporting narrative for the overall score in this review (1/2 page)
Overall, the programme has continued to meet or exceed expectations on all indicators this year, earning an overall score of A+.

The largest component of HDIF continues to be grant funding for innovations in human development. Yet again this year, a number of HDIF grantees have demonstrated impressive results and have secured paths to sustainability and scale.
- PharmAccess International’s (PAI) Business of Quality (BoQ) project worked with 487 private health facilities to improve quality of care, strengthen business models, and support facilities to access affordable loans to invest in improving care. Facilities were assessed against the international SafeCare standards and given a rating based on the quality of their care, which was then displayed around the facility. As a result of the project, 47% of facilities enrolled moved from SafeCare level 1(low quality) to SafeCare level 3 or 4 (high quality). A recent randomized control trial carried out by the London School of Health and Tropical Medicine evaluated the impact of SafeCare and found that intervention facilities enrolled in the BoQ project had higher SafeCare scores at endline than control facilities by 4.3% percentage points. Moreover, facilities enrolled in the project had, on average, 145 more visits per month and TZS. 3.77 million more revenue per month than control facilities. At policy level, PAI undertook deliberate efforts to ensure that the SafeCare methodology was aligned with the National Quality Improvement framework to suit the Ministry of Health (MOHCDGEC)’s star-rating approach. As the result, PAI was approached by the MOHCDGEC and requested to provide technical support to the Ministry to rate the quality of care provided by all public regional referral hospitals and guide the hospitals in improving their ratings.
- Shule Direct’s “Makini SMS” project provides quality education and revision materials to Ordinary-Level secondary school students through a mobile platform with the vision of making education more fun and interactive. HDIF funding for the project closed in June 2019, and Shule Direct incorporated the project into their wider operations, scaling up the platform by going beyond facilitating access to the education materials through mobile to include an app and web-based platforms. Makini SMS currently reaches over 100,000 active users, including teachers who can use the materials for teaching. Shule Direct won the ‘Best Online Education Platform of the Year’ award at the Tanzania Elimu (education) awards in August 2019.
- Ubongo Learning beat start-ups from around the world to win the ‘Next Billion’ EdTech Prize 2019, which recognises the most innovative technology destined to have a radical impact on education in low income and emerging world countries. Ubongo’s recognition is the result of its successful edutainment initiatives including the HDIF-funded ‘Akili and Me’ and ‘Akili and You’.
- The Nanofilter project, a Public Private Partnership between Nelson Mandela Institute of Science and Technology (NMAIST) and start-up business Gongali, has developed low-cost water filtration technology to produce clean, safe water, with acceptable levels of fluoride and minerals, which can then be sold as a small business from kiosks, and at a much lower price than the biggest brands. The HDIF-funded project was implemented in Arusha region, reaching 250,000 people with clean water, and employing 90 women as water station operators. Since HDIF funding ended in April 2019, the project has continued in Arusha and been geographically scaled up. Gongali have started working with Kiludi -Handeni, Tanga region where they have set up 14 water stations. Gongali have also secured funding with Southern African Innovation Support (SAIS) to roll-out a water project in Zambia that will set-up 20 water stations and are working with an entrepreneur in Nairobi on a franchise model.

Perhaps equally importantly to the performance of HDIF grantees, the HDIF programme itself has now fully established its credibility and authority as an ‘elder statesperson’ of innovation in Tanzania, advising partners and potential funders of innovation across multiple sectors. At least partly as a result of the visible success of the HDIF programme, this year there has been a growing interest among development partners (notably UNDP, the EU and the Swiss) to support and fund innovation in Tanzania. HDIF has been central as an advisor to shape the strategy and design of these new investments. This year has also seen growing engagement from private sector partners on supporting the enabling environment for innovation in Tanzania. HDIF has worked with angel investors, impact investors, commercial banks and telecommunications companies, alongside development partners and government to identify gaps and opportunities in innovation financing in Tanzania and to explore ways to jointly contribute to a full innovation funding pipeline for the country. This is a strong indication of the viability of the HDIF theory of change - combining catalytic finance with broader support to the enabling environment for innovation and deliberate coalition building and lesson sharing among funders, leading to further investment and support for innovations to transform basic services.

Finally, this year has also seen improvements in the programme management of HDIF, as a result of a successful transition in HDIF’s leadership. Of particular note is the proactive and holistic approach that has been taken to safeguarding, addressing not only risks at the grantee/implementation level, but also the broader culture of the HDIF team, by promoting a more transparent, feedback culture and a focus on developing self-awareness and emotional intelligence skills.

Recommendations for the year ahead (1/2 page)
Whereas last year’s annual review called for a fundamental “pivot” in the programme approach to reflect the final stages of implementation, this year’s annual review is largely about consolidating progress in the final year. Recommendations are set out in their relevant sections throughout this document, but they broadly fit into three themes: (i) anchoring the progress that HDIF has made in building support for innovation in Tanzania to ensure this continues after the programme closes, and that others can step into the coordination and facilitation role that HDIF has played; (ii) prioritising the most important results to be achieved. Whilst the programme is rightly ambitious and the HDIF team are full of ideas on how to take the programme further, it will be important to be clear on the essential outputs and outcomes to be achieved in the final year to maximise programme impact. This review makes some suggestions on this; and (iii) maximising learning from the programme and embedding this with partners in innovation in Tanzania, as well as with DFID and with the global community supporting innovation for human development.

## B: DETAILED OUTPUT SCORING (suggest 1 page per output)

Output Title	HDIF has cultivated the ecosystem on innovation in human development through inspirational cross-sector networking and strategic awards.
Output number per LF		1	Output Score	A+
Impact weighting (%):		20	Impact weighting % revised since last AR?	Y (last year’s weighting: 10)

Indicators	Milestone(s) for this review	Progress
1.1 Cumulative no. articles/digital media produced by HDIF related to grantee innovation and disseminated to at least 2 relevant quad aligned (cross sectoral) actors within ecosystem (disaggregated by those for which COSTECH is targeted)	342 (50%) / [91 this year]	340 (68%) – Met / [89 this year]
1.2 Cumulative no. HDIF curated and designed quad aligned events, meetings, forums that bring together stakeholders across at least 3 of 6 key actor categories (disaggregated by % of which COSTECH is collaborator)	138 (40%) / [41 this year]	175 (72%) – Exceeded / [78 this year]
1.3 % partners in supporting ecosystem who rate requested and agreed TA as 6 or better on 10-point scale	60%	81% - Exceeded
1.4 Cumulative no. new innovative ideas in human development generated or mobilised through strategic awards	3 ideas in the generation phase	6 ideas generated - Exceeded
1.5 % Work-plan targets achieved by HDIF in building capacity of GoT (incl. COSTECH) in activities other than strategic planning, fund management, knowledge management and Zanzibar policy)	70%	100% - Exceeded
1.6 % increase in the size of the HDIF curated digital ecosystem, disaggregated by type of platform e.g. social media, HDIF email list	10% (5% SM, 10% email list)	17% (9% SM, 145% email) - Exceeded
1.7 Continued active engagement in broader HDIF network through HDIF newsletter	6% average opens; / 1% Click through.	24% average opens; / 6% Click through - Exceeded

Provide supporting narrative for the score
The weighting of this indicator was increased following last year’s annual review to reflect the additional effort expected on supporting the innovation ecosystem in Tanzania. All indicators for this output were met or exceeded, leading to a score of A+.

Last year’s annual review called for a ‘pivot’ in approach to this output, reflecting the stage of programme implementation and the need to ensure the momentum and energy among innovation ecosystem players in Tanzania continues after HDIF ends. The review called for the programme (i) to support local ecosystem partners to play the convening and facilitating role that HDIF has played after programme closure, (ii) to incentivise and encourage greater collaboration between different sectors in innovation, including large private sector companies and universities, and (iii) to promote innovation outside of Dar es Salaam. This year HDIF has shifted ways of working for this output in line with these principles, for example:

HDIF took a more strategic approach to indicator 1.4, designing a programme of awards to provide intensive capacity building support to innovation enabling ‘institutions’ such as hubs and incubators on either (i) creating a financially sustainable business model or (ii) improving project management processes, as these were identified as significant gaps. Seventy-six eligible organisations were nominated for awards, 13 were shortlisted, and 6 developed and pitched concept notes to a judging panel of key local innovation stakeholders. Priority was given to pitches from organisations outside of Dar es Salaam, working in human development, and demonstrating partnerships across sectors. Smart Lab in Dar, Anza in Arusha, Mbeya University of Science and Technology, RLabs Iringa and Cube Zanzibar all delivered successful pitches and will implement their projects next year. This activity is called Institutional Capacity Building (ICB).

HDIF put greater focus this year on bringing different innovation stakeholders together to build and share knowledge through workshops, as opposed to HDIF sharing written lessons from its implementation in a one-directional way. This is reflected in the significant over-achievement against indicator 1.2, despite the target for this indicator having been increased to match last year’s already-strong performance. Highlights included a workshop co-organised by HDIF, COSTECH and the National Economic Empowerment Council (NEEC) for officials from 5 Government ministries and agencies to promote the use of innovation and technology by and within government; and a series of Finance for Innovation workshops bringing together angel investors, impact investors, commercial banks, telecommunications companies, and development partners to identify gaps and opportunities in innovation financing in Tanzania and explore ways to jointly contribute to a full innovation funding pipeline for the country. Outcomes from these workshops included a concept paper that has shaped planned new innovation programming from UNDP, the EU and Switzerland.

HDIF continues to gradually step back from the organisation of Tanzania Innovation Week in order to increase the chances of sustainability after HDIF closure. This year, for the first time, Innovation Week engaged an external organising committee, including representatives from 6 local innovation hubs plus COSTECH, and attracted external sponsorship from Vodacom Foundation and the Swiss Embassy, among others. This year also saw the first time that Innovation Week held events outside of Dar (in Iringa and Arusha) and next year this will be expanded further to include Dodoma, Mbeya and Zanzibar. Of the 2237 participants in Innovation Week, 45% were female, although women made up 60% of speakers, facilitators and exhibitors.

Finally, HDIF shifted its approach to working with the media with a view to maintaining quality media coverage of innovation in Tanzania after the programme closes. This has included linking its grantees directly with media houses to facilitate ongoing relationships, providing training on communications to grantees, running a workshop for print and broadcast media in Tanzania on how to increase quality and coverage of reporting on innovation, and sponsoring a Media Council of Tanzania ‘Excellence in Journalism’ award for the best coverage of innovation stories and news.

Lessons identified this year, and recommendations for the year ahead linked to this output
While there is interest from development partners in Tanzania to develop new programming to support the innovation ecosystem, this cannot be assumed and relied upon to take on the convening role that HDIF has played.
Recommendation 1: In the final year of implementation HDIF should prioritise supporting multiple pathways to anchor the innovation ecosystem and take on the convening and facilitating role that HDIF has played. In practice this could include: (a) supporting local innovation hubs to accelerate the formation of a ‘hub network’ to collaborate and represent themselves with funders and government; (b) supporting COSTECH’s BUNI hub to realise its ‘hub of hubs’ vision of supporting universities to set up innovation spaces; (c) supporting development partners and other potential funders in their emerging plans to form a multi-partner platform to co-finance innovation in Tanzania; and (d) as far as possible, linking local innovation enabling organisations (hubs, incubators etc) and events to private sector funders and other development partners to form ongoing partnerships, rather than providing sponsorship and other support directly.
Timing: To be delivered throughout the final year of the programme, with progress checked quarterly.

While HDIF has made good progress in the last year on expanding support to innovation outside Dar es Salaam, as this work has begun relatively late in the programme cycle there is a greater risk that it will not be sustainable, and partners supported through, for example, Innovation Week and Institutional Capacity Building will not be able to continue their activities without HDIF support.
Recommendation 2: HDIF should focus on “jump starting” support to its partners outside Dar es Salaam to increase the likelihood that these partners will continue to effectively support innovation in their areas after HDIF closes. At minimum, this should include: (a) supporting grantees under ICB to develop real-time lesson learning and sharing plans, appropriate to a one-year implementation. By April 2020; (b) providing intensive support to ICB grantees to develop sustainability plans for when HDIF support ends. By April 2020; (c) providing intensive co-curation to partners hosting Innovation Weeks outside of Dar es Salaam, focused on how they will continue these events in future years. By March 2020, with ongoing coaching and mentoring support to be available throughout the year.

Throughout these activities, HDIF should not lose sight of equity and inclusion considerations, in particular the role of women and girls in innovation in Tanzania.
Recommendation 3: HDIF should make clear in its 2020-21 annual workplan how each activity to support the innovation ecosystem will ensure the active participation and benefit of women and girls. By April 2020.

Overall, in its final year of implementation, the HDIF programme will need to balance strengthening the core of the innovation ecosystem in Tanzania with extending to new partnerships. HDIF and DFID have discussed this as 3 principles for the final year of ecosystem support: Expand, Deepen, and Anchor.

Output Title	HDIF has identified and catalysed the diffusion of innovations in human development.
Output number per LF		2	Output Score	A+
Impact weighting (%):		50	Impact weighting % revised since last AR?	Y (last year’s weighting: 75)

Indicator(s)	Milestone(s) for this review	Progress
2.2 % HDIF funded projects that have achieved at least 80% of their output milestones	25%	50% - Exceeded
2.3 % grantees who rate requested and agreed grant focused TA from HDIF as 6 or better on 10 point scale	60%	100% - Exceeded
2.4 Average speed to process report and fund requests from grantees after 1st disbursement	21 days	16 days - Exceeded
2.5 % grantee self-assessment reports submitted to HDIF on time	80%	95% - Exceeded
2.6 % of Round 3 grantees with gender strategies in place	100%	100% - Met
2.7 Cumulative no. innovative approaches supported by HDIF that are driven or enabled by ICT or mobile technology	Not assessed until 2020 (15)	26 – n/a
2.8 % work plan targets achieved by HDIF in building capacity of GoT in innovation fund management	80%	94% - Exceeded

Provide supporting narrative for the score
This output relates to the performance of grants supported by HDIF. The weighting of this output was reduced this year, reflecting the smaller number of active grants in the HDIF portfolio and the ‘pivot’ in programme focus towards ecosystem support and lesson sharing (outputs 1 and 3).

HDIF currently has 12 active grants, with 7 grants having closed in the last year. HDIF continues to meet or exceed expectations on all indicators for this output, demonstrating highly efficient and effective grantee management processes at this stage in the programme. All indicators also showed improvement from the previous year. Particularly notable is the grantees’ rating of HDIF technical support (indicator 2.3), which has improved year-on-year for the last 4 years, with 77% of grantees now rating HDIF TA as “exceeding their expectations”. Highlights from HDIF’s support to grantees this year include:

All Round 3 grantees have had sustainability strategies in place from the selection phase and continue to implement against these. The programme completion report should document lessons on the extent to which this approach has contributed to the sustainability of innovation grantees.

In response to recommendations in the previous annual review to avoid a ‘cliff edge’ with the end of funding for innovation grants, grantees that have already finished implementation were offered ongoing technical assistance by HDIF to help them design follow-on projects, connect them to funders, and involve them in HDIF events. This offer was taken up by Shule Direct, Nelson Mandela Institute of Science and Technology, and Kishapu District Council (adopters of ICS-implemented pre-paid water meters).

There has been increased lesson sharing and collaboration this year between Round 3 grantees focussed on Early Childhood Development (ECD). Haki Elimu, Karibu Tanzania Organisation (KTO), Ubongo and D-Tree hold quarterly meetings as a group, from which opportunities for collaboration have been identified, for example KTO will use Ubongo’s materials in its early childhood centres.

This year, HDIF has supported COSTECH to launch its first ever rounds of funding support for start-ups and innovation hubs as part of the National Fund for the Advancement of Science and Technology (NFAST). HDIF technical assistance to COSTECH on this included developing a monitoring and evaluation framework with COSTECH for its grants, as well as processes for the selection and mobilisation of grantees. (Indicator 2.8)

HDIF continue to monitor the impact of changes to the regulatory environment for innovators in Tanzania on its grantees. Changes to regulations governing NGOs last year has compelled some of the HDIF grantees, previously registered as companies limited by guarantee, to change their legal status to become NGOs. This has necessitated a change in business model and proposed pathway to sustainability, as NGOs cannot operate a social enterprise model. There are also taxation implications, which grantees are still working to fully understand. HDIF has engaged consortium-partner KPMG to provide clarifications and advise grantees wherever possible.

Last year’s annual review recommended that all grantees be supported to develop their approach to safeguarding. HDIF took this recommendation seriously, and detail on the actions taken on safeguarding is set out in the risk section of this review.

A number of HDIF grantees have now demonstrated contribution to improvements in basic services, as well as evidence of sustainability 3 months or more after programme closure, suggesting achievement at the outcome level for grantees as well as output level. This is described in the summary section above.

Lessons identified this year, and recommendations for the year ahead linked to this output
This year’s review heard feedback from some grantees that the timing of submitting financial information for the closing quarter and receiving payments for the upcoming quarter leads to cash flow issues for one month per quarter.
Recommendation 4: HDIF to explore options to minimise cash flow issues for grantees e.g. receiving requests for payments from grantees one month early. By March 2020, to be implemented in the next UK financial year.

During this Annual Review, DFID Tanzania Human Investment Team sector advisers conducted field visits to grantees in their sectors and provided insightful feedback and technical advice to HDIF and to specific grantees. This closer engagement between HDIF grantees and DFID sector advisers is useful for lesson sharing as well as technical quality assurance.
Recommendation 5: DFID and HDIF to consider regular (e.g. quarterly) meetings between DFID sector advisers and HDIF sector leads (Programme Managers) to monitor progress of specific grantees and share lessons, particularly where there is a strong link between the grantee’s innovation and DFID sector programming. By March 2020, to be implemented as part of the 2020-21 workplan.

Lessons from previous DFID-funded innovation programmes have highlighted the risk that innovation grants are supported for short periods of time and then struggle to continue their innovations after funding ends. As covered in last year’s annual review, Round 3 grantees have a particular challenge to embed their innovations during a relatively shorter implementation period.
Recommendation 6: HDIF to flag to DFID and other Development Partners where there are particular risks to grantee sustainability, or where there may be particular opportunities to scale up innovations. DFID Tanzania staff should engage their networks to explore opportunities to support grantee sustainability through DFID’s global portfolio where possible.

Output Title	HDIF has transformed the focus and quantity of evidence available to key stakeholders on the practice of innovation in human development.
Output number per LF		3	Output Score	A+
Impact weighting (%):		30	Impact weighting % revised since last AR?	Y (last year’s weighting: 15)

Indicator(s)	Milestone(s) for this review	Progress
3.1 Cumulative no. analysis reports exploring and documenting innovation produced by HDIF or partners	9 / [2 this year]	11 – Exceeded / [4 this year]
3.2 Cumulative no. learning documents developed by HDIF or HDIF grantees on grantee innovation diffusion and challenges, with a dissemination strategy in place	44 / [10 this year]	44 – Met / [10 this year]
3.3 % learning documents developed and disseminated by HDIF, partners or grantees that have been disseminated	Cumulative target - 60%	Cumulative achievement - 85% / Achievement this year – 71% / Exceeded
3.4 Cumulative no. engagements held with other funders about participating in HDIF operations, sharing lessons learned or generating evidence on grant making to support innovation in human development	65 / [6 this year]	69 – Exceeded / [10 this year]
3.5 % partners in learning and insight generation who rate requested and agreed TA as 6 or better on a 10-point scale	60%	100% - Exceeded
3.6 HDIF explores and encourages potential scaling of HDIF innovations within DFID’s portfolio by sharing experiences and evidence with related DFID programmes. Cumulative target.	21 / [4 lesson-sharing events held this year]	23 – Exceeded / [6 lesson-sharing events held this year]
3.7 % work plan targets achieved by HDIF in building capacity of GoT (incl. COSTECH) in knowledge management	80%	86% - Met

Provide supporting narrative for the score
This output relates to developing and sharing learning and evidence on innovation for human development with the Government of Tanzania, donors, the private sector, and other partners in the innovation ecosystem. The weighting of this output increased this year to reflect the additional effort expected on lesson documenting and sharing in the final stage of programme implementation. As in Output 1, the HDIF programme has shifted its approach to delivering this output, utilising more of the time and input of the full programme team and adopting a more collaborative approach to ‘co-creating’ knowledge with partners, as opposed to simply reporting lessons. This has seen good results in greater and more meaningful engagement with development partners, private sector and government.

The programme has performed well against this output, meeting or exceeding all logframe targets. Highlights include:

Increasing uptake of HDIF lessons by development partners. The HDIF team are engaged in informing design processes for future support to innovation in Tanzania with UNDP, the EU and Switzerland. This is a promising development for the sustainability of the HDIF programme approach in Tanzania.

Increased and more meaningful engagement with private sector companies, including establishing a relationship with Vodacom to work together to support start ups in the digital sector in Tanzania. Vodacom will sponsor Innovation Week this year, and have been part of the multi-sector Finance for Innovation workshops described in Output 1.

Producing and disseminating learning pieces on HDIF’s overall lessons and reflections on 5 years of investing in social innovation and technology, as well as a study on the effectiveness of pre-paid water meters in Tanzania. The latter is a comparison of three models, two from HDIF grantees and one from DFID Tanzania’s Rural Water programme. In the next year, HDIF will document lessons on support to e-health initiatives in Tanzania, as well as on different funding and support models for innovation.

Continuing to share lessons across DFID and collaborate with DFID programmes. In the last year, HDIF has held lesson-sharing events with DFID Tanzania programmes ACT2, Dar Jobs, and I4ID. HDIF has also worked closely with DFID’s new EdTech Hub, who will now base an adviser in the country to build on many of these lessons and connections, and has presented a DFID-wide ‘DevTalk’ on supporting innovation.

Supporting COSTECH to facilitate better use of innovative research and evidence to inform policy making in Government ministries, through a pilot in Zanzibar with IDS, a HDIF consortium partner. In this pilot, 38 government officials from different ministries took part in a series of training workshops to develop policy briefs on new approaches to policy issues in their ministries. COSTECH officials also attended training at IDS in Sussex on establishing a ‘helpdesk’ to support government officials to access the latest research and evidence on various policy issues. As a result of this work, COSTECH and IDS have formed a strong relationship and intend to form an ongoing partnership to bid for support for similar work after the HDIF programme closes.

Lessons identified this year, and recommendations for the year ahead linked to this
Next year will be the final year of programme implementation, and so documenting, sharing and embedding lessons from the programme will need to be a central focus of the HDIF team’s effort. This includes lessons from individual grantee innovations, as well as of the programme as a whole. HDIF is on track to deliver its major learning piece next year which will compare different models of innovation programming, but should also ensure that lessons from other parts of the programme are captured and shared as effectively as possible in the last year.
Recommendation 7: (a) HDIF to put in place a strategy for co-creating and sharing lessons from the Institutional Capacity Building activity by March 2020; (b) HDIF to consider how to build on the good relationships and potential for lessons sharing demonstrated by ECD-focussed HDIF grantees, for example by working through the Tanzania Early Childhood Development Network (TECDEN) by March 2020; (c) HDIF to work with the DFID WASH Adviser to disseminate findings from the study of pre-paid water meters, intensively and targeted to key decision makers - ongoing.

In the final year of implementation, it will also be crucial for DFID to make the most of the experience from HDIF to inform programming in various sectors in Tanzania as well as DFID’s investments in innovation around the world.
Recommendation 8: DFID Tanzania to ensure that the HDIF programme is connected to regional and global DFID innovation leads including the DFID East Africa Research Hub by March 2020; HDIF to work with DFID’s regional EdTech adviser, to be based in Tanzania, to ensure that lessons on education technology in Tanzania from HDIF can inform the work of the EdTech Hub. By June 2020; DFID to ensure that lessons from HDIF’s final flagship learning document on different models of funding innovation are shared widely within DFID Tanzania and across the organisation, by November 2020.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES (1-2 pages)

Summarise the programme’s theory of change and any major changes in the past year (1/2 page)
The HDIF programme aims to contribute to improved human development through supporting innovation in service delivery. The desired programme impact is: Dialogue and practice in innovation improve basic services in human development in Tanzania. This is supported by two programme outcomes: (A) HDIF intervention accelerates the diffusion of innovative ideas, approaches and solutions to human development challenges, and (B) HDIF intervention accelerates conversations, debates, and policymaking on innovation in human development. Outcome A relates to the performance of grants, and the extent to which interventions have become sustainable beyond the life of the programme. It includes an immediate outcome indicator on number of HDIF-funded innovations that have produced evidence suggesting contribution to improved basic services, and a higher-level outcome indicator on the percentage of HDIF-funded innovations that have been “adapted” i.e. continue to operate in some form, 3 months after HDIF funding ends. Outcome B relates to building an evidence-based national conversation on innovation among innovators, policy-makers, funders, and the private sector. It includes indicators on the uptake of HDIF lessons by policy makers and funders of innovation, and the growth in the number of innovation hubs and other ‘enablers’ in Tanzania, as well as the level of conversation, excitement and media coverage around innovation in Tanzania. The Theory of Change assumes that achieving either of these outcomes would require all three of the outputs discussed above to be delivered.
[note] The concept of innovation ‘adaptation’ is taken from the Springfield Institute Systemic Change Framework for Business in Development, used to manage and measure systemic change processes, which has been used by the HDIF programme as a theoretical framework http://www.springfieldcentre.com/wp-content/uploads/2016/04/Systemic-and-Systemic-Change-clarification-of-concept-V2-BT-260416.pdf
There have been no major changes to the theory of change in the year under review, although, as discussed below, measurement indicators have been changed in order to better monitor progress.

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead (1/2 page)
Outcome and impact indicators were revised this year as recommended in last year’s annual review in order to more accurately measure the progress of the programme. Indicator definitions were clarified, and some outcomes were moved between levels in the logframe to ensure that they are being measured at the right level. As a result, this year the programme outcomes and impact should be more challenging for the programme to meet and require more robust evidence of achievement. (See the 2019 annual review for further detail and justification).

Even against these more challenging indicators and targets, the HDIF programme remains on track to contribute to and exceed the expected outcomes and impact. Examples of achievement under Outcome A (relating to the performance of the grants) are given in the summary section above. HDIF has exceeded the targets for both Outcome A indicators. HDIF is also on track or ahead of target against all Outcome B indicators. Examples of achievement under Outcome B (relating to the wider ecosystem of support to innovation in Tanzania include) include:
- Several donor partners in Tanzania (including UNDP, the EU and the Swiss) have made use of HDIF’s lessons on funding social innovation to design forthcoming innovation programmes in the country. The growing interest in funding innovation from development partners has been notable this year. In the judgement of the reviewers, this shift is, at least in part, attributable to the increased emphasis from the entire HDIF programme team on implementing an effective lesson sharing and influencing strategy. Key elements of this strategy have included: (i) the decision to document and publish the programme’s most important learnings on funding innovation with two years’ of programme implementation remaining, as opposed to at the very end of the programme. This has enabled the programme team to disseminate these lessons intensively with a full staff; (ii) a dissemination approach combining targeted meetings and relationship building where there were promising opportunities for uptake of the HDIF approach, with larger multi-partner workshops focussed on co-creating lessons as opposed to reciting them; and (iii) targeting a mix of partners from different sectors, from government, to large private sector companies, to development partners, and bringing these different partners together in the same room.
- There are currently 49 innovation hubs, enablers and spaces across Tanzania. This represents an additional 9 spaces compared to last year’s reporting. This positive trend on innovation is reflected in responses to a survey conducted by HDIF of innovators, funders and government in Tanzania, in which 83% of respondents reported that they were more likely to invest in or access innovation compared to three years ago.

Although not yet measured, there is also emerging evidence of achievement at the impact level of the logframe. For example, a number of HDIF partners from the Tanzania innovation ecosystem have received support from other funders, suggesting that HDIF has helped to build a core group of local social innovators generating quality ideas, ready for funding. This is one of the key pathways for change in the programme’s theory, and, taken alongside the successful achievement of outcome indicators, is a strong indication of the viability of the HDIF theory of change. In particular, it suggests the importance of combining catalytic finance with broader support to the enabling environment for innovation and deliberate coalition building and lesson sharing among funders.

Explain major changes to the logframe in the past year (1/2 page)
As described above, in the past year indicators at the outcome and impact levels were amended to more accurately measure progress against the theory of change. At the output level, specific changes were made to indicators where, for example, they were no longer relevant, targets had already been reached, or they were continually over-achieved. These specific changes were set out in last year’s annual review recommendations (copied below).

Describe any planned changes to the logframe as a result of this review (1/2 page)
During this year’s annual review, the HDIF and DFID programme teams held a deep dive session on the output level of the logframe, with a DFID Senior Programme Manager who does not work on the programme also joining the workshop to offer some external challenge. It was agreed between the teams that the current structure of outputs in the logframe no longer reflects the priority results needed to anchor programme outcomes during the final year of implementation, and the output indicators no longer measure and incentivise the most important areas. The teams conducted initial workshopping to prioritise key outputs and indicators, balancing the need to set ambitious but achievable targets with the value of maintaining some consistency in monitoring across the life of the programme. Completing this process should be an early priority for the next year.

Recommendation 9: Finalise a revised logframe to reflect the priority outputs for the final year of the programme. To be completed by end February 2020 in order to inform the annual workplanning and budgeting cycle

## D: VALUE FOR MONEY (1-2 pages)

Assess VfM compared to the proposition in the Business Case, based on the past year (1 page)
HDIF’s VfM framework and indicators were revised this year based on recommendations from DFID Tanzania’s VfM lead as part of the last year’s annual review (these are set out in detail in previous year’s recommendations below).

Cost Drivers
The key cost drivers for the programme are grants, which represent 57% of programme budget, followed by programme activities, primarily technical assistance support, which represent 17% of the budget, and personnel fees (of which 50% are milestone based), which represent 12% of the budget.

Economy
Economy is assessed for HDIF by unit costs, budget execution rate, management/admin costs, and realised cost savings. Unit costs for the programme (e.g. for flights and hotels) remain reasonable (average Dar hotel cost £90; average Dar-London flight £513) and are lower than last year. Last year’s annual review recommended that HDIF compare unit costs to other DFID programmes, however it has proved challenging for HDIF to access this information for programmes other than those also implemented by Palladium. This is something for the DFID Tanzania office to reflect on in terms of how we can better compare economy and VfM between our programmes.

HDIF had a budget execution rate of 96% this year, suggesting that the programme's activities are being implemented in a timely manner and that the programme does not incur additional costs that would result from delayed activities. The programme realised cost savings of £25,204 this year as a result of securing multiple quotes for procurement of communications and content production activities.

Efficiency
Efficiency relates to how inputs are translated to outputs. Efficiency VfM indicators include indicators taken from the output level of the programme logframe (1.2, 1.5, 2.2, 2.3, 3.1/3.2, and 3.4) as well as a measure of the speed of funds disbursement from HDIF to their grantees. All of these indicators were exceeded. Fund requests from grantees were disbursed faster than planned (16 days after receipt of funds request against a target of 21), which means that grantees received funds in a timely manner and could implement their innovations as planned; saving costs resulting from unforeseen delays.

Effectiveness
Effectiveness relates to how outputs are translated to outcomes. This measure includes 3 indicators taken from the outcome level of the programme logframe – % of innovations that have contributed to improvements in basic services; % of innovations that are still functioning 3 months after HDIF funding ends; and number of instances in which funders or policy makers utilise learning generated by HDIF interventions to inform support to innovation – all of which were exceeded. HDIF’s effectiveness is also measured by the average budget per grantee in the current portfolio as a proportion of average budget per grantee in the initial programme design. HDIF's average budget per grantee is lower than what was anticipated during the initial programme design. As a result, the programme can engage (fund) a higher number of grantees to implement a larger number of interventions and reach a higher number of beneficiaries presenting better value for money.

Equity
HDIF tracks equity at different levels and has a particular focus on gender equity. At the programme staffing level, 53% of those who have provided technical assistance through the programme have been female, and 100% of bid review teams have included a female member. At the grantee level, 100% of currently active grantees have gender strategies in place for their innovations. At the beneficiary level, 54% of beneficiaries of female. The programme has also made a number of deliberate efforts this year to increase the participation of women and girls in the innovation ecosystem, including targeting women and girls as speakers and facilitators for events during innovation week, and working on gender-focussed learning case studies from grantees, to be finalised next year.

HDIF is currently not reporting equity considerations other than those related to gender. This is an important issue given that access to innovation and funding for innovation globally is often inequitable in multiple ways.
Recommendation 10: HDIF to consider how to fully capture the narrative of who the programme has reached and the impact, with attention to equity, to be reported in the Programme Closure Report. This should draw from existing programme data available on other measures of equity, this could include data on geographical equity, disability, or poverty, in order to provide a better picture of those reached by HDIF interventions. Update on what this reporting might look like by June 2020.

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio (1 page)
As described above, the programme continues to represent value for money, particularly exceeding targets on efficiency and effectiveness. The programme also continues to play an important role in the wider DFID portfolio by providing lessons on innovations in human development with the potential to have a transformational impact. For example, evidence on education technology from HDIF informs DFID Tanzania’s work on education, including through the new DFID EdTech Hub, which will have aregional post based in Tanzania, and HDIF-funded research on pre-payment technology in the water sector will inform DFID’s national water programme in Tanzania. HDIF further maximises value for money by sharing learning across the innovation sector in Tanzania, and with DFID’s global network on innovation, as described earlier in this review.

E: RISK (½ to 1 page)

Overview of programme risk (noting the rating from p.1) and mitigation
DFID Tanzania has a high overall risk appetite for HDIF, in recognition of the fact that, as an innovation programme working with often untested pilot projects, there is a risk that many could fail.

Based on findings from this annual review, the overall risk rating for HDIF remains Moderate. This is because the operating environment has not changed from the previous review hence most of the key programme risks have maintained their rating. The programme remains within DFID’s risk appetite.

Safeguarding was identified as a major risk in the last annual review and was an area of concern given the nature of the work of some HDIF grantees, some of whom work with children and vulnerable people. HDIF significantly stepped up its efforts on safeguarding this year, taking action at all levels of the programme and sharing this learning and good practice with other DFID Tanzania suppliers as part of the DFID Human Investment Team regular suppliers’ day. Mitigating actions on safeguarding risk taken by HDIF at different levels included:
- HDIF staff: introductory sessions held on the importance of safeguarding with emphasis on individual accountability and responsibility; survey of staff experience at work, which highlighted issues including unequal power dynamics, lack of feedback culture, lack of confidence among many female staff to speak up in the HDIF team, and uncomfortable working environment; mitigation measures were put in place including hiring a human capital development firm to support with self-awareness and emotional intelligence training, more transparent team communication, 360 feedback and performance management processes, and even changing the office layout.
- HDIF grantees: HDIF has cascaded these measures and learnings to the grantees by conducting safeguarding training workshops and opportunities for lesson sharing on safeguarding between grantees, as well as conducting safeguarding due diligence on grantees, and closely monitoring grantees’ approaches to safeguarding as part of their regular programme management.

Safeguarding remains a priority area that we closely monitor due to the nature of the programme. For the above-mentioned reasons this risk has been downgraded from major, as it was in the previous review, to moderate.

The external context of innovation in Tanzania remains a major risk given wider issues in the business environment in Tanzania, however efforts have been made to diversify the relationship with Government beyond COSTECH to sector ministries and increase engagement with private sector and universities as recommended in the previous review.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE (1-2 pages)

Performance of partners and DFID, notably on commercial, and financial issues (1-2 pages)
The HDIF programme is delivered through a hybrid contract with Palladium, composing of reimbursables, grants, and milestones. The program has 2 active components as set out below:

Component	Actual Spend (£) Nov 2018 to Jan 2019	Used to fund
203539 - 102: Implementation	3,874,969	Contract with Palladium - Grants and Reimbursables
203539 - 103: Monitoring and Evaluation	0	Manged by DFID - For monitoring and evaluation of the program
TOTAL	3,874,969

Commercial and Programme Management Performance

The programme has so far delivered all contractual milestones on time. The contract is managed through DFID’s Strategic Relationship Management (SRM) process. The next SRM scorecard process to assess supplier performance is expected in February/March 2020.

This year saw significant change within the HDIF team as three key personnel left the programme – Team Leader, Project Director, and Project Manager. Palladium managed this transition well and recruited a high-quality team of new staff to fill these key positions, alongside increasing the responsibility of existing members of the very strong HDIF team. As a result, despite the significant change, programme performance in all the key SRM focus areas of Delivery & Support, Quality, Value & Innovation, and Compliance and Risk improved in the last year. The new team has also driven a transformation in team culture, creating a more open and safe-to-challenge environment, which has in turn contributed to improved programme performance. This is described in more detail in the Risk section.

After a long process, a fifth Contract Amendment for HDIF was successfully agreed between Palladium and DFID this year. This Contract Amendment extends the time for programme implementation from March 2020 to July 2021, but does not increase the budget.

Financial Management

The DFID programme team have noted a significant improvement in financial management by Palladium this year. This has been driven by the responsiveness of the project management team. The programme has been operating on 5% and below variance between the forecast and the actual spend with exception of very few months where the variance exceeded 10% with reasonable supported evidence. Other factors in the improved financial performance this year include:
Timely submission of invoices by 15th of each month with all the required programme spend information and evidence for verification, making it possible for the DFID programme management team to process payments in good time
- Timely submission of financial figures for confirmation by 25th of each month with any updates flagged
- Timely submission of HDIF’s annual workplan which, as of last year, aligns to the UK financial year, with an annual financial forecast informed by an accurate and complete workplan
- As recommended in the previous annual review, this year grants and reimbursables have been separated into two separate invoices to improve efficiency by better tracking imprest account balances for grants, which are paid in advance. Palladium now sends DFID information on the previous spend and account balances when requesting grants funds. DFID has asked for detail on this issue as part of the 2018/19 audit of HDIF to be able to assess the effectiveness of this new process.

Going forward, as part of strengthening both financial and contract management, DFID and HDIF agreed that milestones will continue to be paid monthly, with additional information and evidence provided for verification by Palladium in monthly submissions. As set out above, DFID and HDIF teams are in the process of reviewing the log frame. This review will need to be followed by a review of the list of milestones to ensure that any milestones linked to the logframe are updated in parallel.

Audit Report and Asset Verification
The 2018/2019 audit for HDIF returned an unqualified opinion. The audit was reviewed by the DFID team and recommendations were given. From follow up spot checks and the annual review field visits we were able to see improvements on the issues noted. The 2019/20 audit is underway, we have reviewed the TORs and met the audit team for an inception meeting. Once the report is received we will confirm that outstanding issues from the previous audit have been addressed.

The HDIF programme has acquired various physical assets and maintains an asset register which is updated on a regular basis and shared with DFID. Assets management is routinely monitored by DFID during spot checks and annual reviews.  As part of the 2020 Annual Review, an assets spot check was conducted on 31st October 2019 by the DFID team to assess the status of the assets and whether HDIF has put in place proper assets management controls. This check found persistent issues of the recording of asset locations and discrepancy between asset registers in previous years, which have been raised to the HDIF programme in the past.
HDIF consortium partner KPMG conducted spot checks on all the grantees in 2018.
Date of last narrative financial report(s)	15 November 2019
Date of last audited annual statement (s)	March 2019

Recommendation 11: Contract milestones and targets to be updated in line with the updated logframe by March 2020.
Recommendation 12: HDIF to develop an action plan to respond to all new and outstanding audit recommendations, as well as concerns raised from the DFID asset spot check by April 2020.

G: MONITORING, EVIDENCE & LEARNING (1-2 pages)

Monitoring (1/2 page)
This year DFID has monitored the HDIF programme through the following processes:
- Monthly meetings between the HDIF Team Leader and the DFID SRO and Programme Manager to discuss progress and emerging issues and risks
- Ad hoc meetings and communications with the HDIF country office and headquarters team to ensure good progress of programme activities as well as effective programme management.
- Quarterly meetings with the wider HDIF team following up on the quarterly reports, as well as annual review and audit recommendations.
- An annual review, including a series of field visits to grantees and programme partners and stakeholders, conducted by the DFID SRO and Programme Manager, with additional support from an intern in the DFID Tanzania Human Investment Team and colleague from the British High Commission
- Regular checks and the annual updating of the log frame indicators, reflecting the adaptive nature of the programme.

In addition to HDIF’s regular monitoring and programme management processes with grantees, HDIF has introduced two improvements to monitoring this year:
- Rolled out Data Quality guidelines and tools to all grantees, and conducted Data Quality Assessments of 3 Round 3 grantees (the remaining 4 to be carried out next year). This has resulted in improvements in data use and reporting by all 3 of the grantees, demonstrated in their regular quarterly reporting cycle.
- Integrated grantee’s gender strategies into their regular monitoring frameworks and tracked during quarterly reflection meetings with HDIF.

Evidence (1/2 page)
The original Business Case for HDIF included a plan for an independent evaluation to be conducted of the programme. The evaluation was planned for this reporting year; however, DFID took the decision to postpone the evaluation in order to manage competing priorities. This evaluation will be commissioned next year to inform the programme completion report.

The main objective of the evaluation is to the contribute to the evidence base on the potential impact of the use of innovation and technology on human development outcomes. One challenge for the evaluation will be in comparing different sorts of outcomes from grantees working in different sectors and subsectors.

Learning (1/2 page)
HDIF continues to prioritise learning as a programme output. This year reports were published on (i) the programme’s overarching reflections after 5 years of investing in social innovation in Tanzania, and (ii) a comparative study of pre-paid water meters.

This year also saw HDIF take a new approach to its learning (as described in Output 3 above) to focus on co-creation of lessons through workshops and discussion, both with grantees and external partners. Examples of this include workshops finance for innovation workshops with potential funders of innovation from various sectors to identify key bottlenecks in the innovation funding pipeline, and quarterly roundtable lesson sharing discussions between ECD-focussed grantees in the HDIF portfolio. As described in output 3, HDIF also continues to share lessons with other DFID programmes.

Next year documenting learning will be an even bigger focus for the programme, given that it will be the final year of implementation. The primary learning document HDIF will produce next year will be a comparison of different models of donor programming on innovation, comparing HDIF’s model to others.

Recommendation 13: DFID to commission an independent evaluation to inform the HDIF programme completion report by July 2020

Progress on recommendations from previous reviews (1/2 page)
All but one recommendation from last year’s annual review is complete. The recommendation to commission an independent evaluation of HDIF has been deferred to next year and will inform the programme completion report.

No	Recommendation	Status
1	Focus future output 1 activities on supporting innovation ecosystem players to collaborate more effectively and break up silos. In practice, this means continuing to develop plans for a 'Mawazo Challenge II', consisting of small grant awards to 'clusters' bringing together partners from different sectors of the innovation ecosystem across the country. In the first instance, this should include holding challenge discussions with the HDIF team and external partners to further develop the idea, moving to implementation by Q3 2019.	Complete
2	In order to support the sustainability of Innovation Week, identify a small group of partners to take on some or all of its management. Such potential partners should be engaged in the Innovation Week 2019 planning and delivery process, with a view to taking a lead on fundraising and delivery of Innovation Week 2020. These partners should also seek to connect with private sector companies and foundations to encourage them to contribute to promotion and financing.	Complete
3	Ensure all grantees (including those continuing from Rounds 1 and 2) are supported to develop their approach to safeguarding in their programmes. This could include: running a specific safeguarding training during innovation week, including safeguarding as a session in the next grantee workshop, and offering TA support to help grantees develop their approaches based on expressions of interest.	Complete
4	Be more flexible and proactive in extending financial and technical assistance (TA) support to grantees, where this would support the sustainability of innovations that are improving basic services. In practice this means: / Proactively encourage grantees to apply for extensions, where appropriate / Clearly and explicitly communicate to grantees (including in close out letters and meetings) that support from HDIF’s programme staff continues to be available to them throughout the life of the programme, even after their grants have closed / Budget permitting, and on a case by case basis, make continued consultant TA available to closed grantees and ecosystem partners where this could contribute to grantee sustainability or the sustainability of HDIF	Complete
5	Assess learning product type (e.g. video, short booklet, longer analysis piece etc) and dissemination channel (e.g. meetings, social media, conferences) to understand the most effective means to disseminate output 3 learnings	Complete
6	Disseminate hubs research, Mawazo challenge research, and ecosystem mapping continuously and more intensively as the review found that these pieces were not yet well-known by their key audience.	Complete
7	Focus output 3 engagement more intentionally on the health, education, and WASH sectors, including by: / Continuing to build the sector pillars of HDIF's knowledge and learning strategy / Continuing to focus learning dissemination on sector ministries and development partner sector leads e.g. participating in joint sector reviews, conducting quarterly visits to Dodoma / Considering how to best to engage sector ministries e.g. more frequent visits to Dodoma / Considering where HDIF engagement, with its cross-grantee perspective on innovation for human development, could add value to grantees' own influencing work, for example, supporting grantees to understand how best to work with government to remain compliant with regulation and aligned to sector plans e.g. through sector-focussed workshops for grantees to share learning and hear from HDIF partners and DFID advisers with expertise in that sector / HDIF actively feeding up concerns and practical issues faced by grantees where DFID sector advisers or leadership might be able to unlock something using their own relationships	Complete
8	Evaluate the sustainability of the DPG STI secretariat and leadership function post-HDIF, as well as its strategy to advance innovation in Tanzania. HDIF to table and facilitate the discussion with the DPG as secretariat.	Complete – new multilateral co-chair for DPG STI is in place. Currently identifying a new bilateral co-chair.
9	DFID and HDIF to conduct a deep dive into how best the programme can support COSTECH and a conducive policy and regulatory environment for innovation, particularly in the context of the upcoming STI policy, and increased focus from DPG STI on Government engagement. This should include looking at: / Supporting COSTECH to define their role as relates to other partners working on STI, and specifically how they can play a facilitating role for innovators with other parts of government / HDIF meeting more formally with MoEST and the COSTECH board to broaden the senior management relationship with COSTECH / Increasing clarity on the Knowledge Management pillar of HDIF's support to COSTECH through consortium partner the Institute of Development Studies (University of Sussex) / Ensuring these changes are reflected in the programme logframe	Ongoing – more strategic engagement with COSTECH is taking place but there is a need to look at this again during logframe review
10	HDIF to define more clearly how it will target different parts of the private sector with learning and influencing from the programme. Options to consider include: / Targeting hubs as spaces of collaboration for start-ups and SMEs – Update to hubs mapping to include an analysis of barriers to hub growth e.g. lack of access to finance, regulatory barriers, lack of collaboration / Targeting large private sector companies that could fund and support innovation – gathering learning from innovation week on where this is working well and where and why there are barriers to this engagement / Learning from ‘Mawazo Challenge II’ to include lessons on the role of academic institutions in the innovation ecosystem	Complete
11	DFID and HDIF to develop a strategy for the year for HDIF to engage with DFID policy and programmes. HDIF have been strong at doing this opportunistically and ad hoc, but a more planned, strategic focus will help DFID to make the most of the learning from the programme. This should include: / Engaging with DFID Tanzania’s new Dar Jobs programme given their shared focus on early childhood development / Ensuring grantees focussed on menstrual hygiene management are connected to DFID Tanzania’s I4ID programme and Social Development Adviser / Ensuring grantees focussed on sanitation are linked to the national sanitation campaign, supported by DFID Tanzania / Engaging with DFID Tanzania advisers to share learning through advisory cadre networks	Complete
12	Recognising that the above will require increased staff time and focus on output 3: / HDIF to consider appropriate staffing structures and skill sets required for the team to enable more focus on output 3 / DFID to allocate sufficient staff time to policy influencing and facilitation on innovation for human development	Complete
13	Revise impact and outcome indicators following annual review discussions.	Complete
14	Output indicators to be further updated to ensure they remain relevant and stretching at this stage in the programme. Some specific changes to include: / Add or replace indicators to measure performance of the new activities agreed for Outputs 1 and 3 during this year's annual review / Change or remove indicators that are process-based and consistently over achieved / Remove indicator 1.3 which has already been achieved / Revise indicator 1.5 as next year’s target has already been achieved / Targets for cumulative indicators should increase based on performance of the prior year / Disaggregation by theme is not meaningful in indicators 3.1 and 3.2 as all learning addresses HDIF priority themes by definition - suggest removing / Look at indicators relating to COSTECH (1.6, 2.10, and 3.7) in the context of recommendation 9 to deep dive into HDIF support to COSTECH. Currently these indicators measure delivery against a workplan, which can be changed throughout the year. / Adjust the weighting of the three outputs to reflect the relatively changed level of effort on each at this stage of the programme / Revise gender indicator 2.6 in logframe based on indicators agreed as part of the revised VfM framework (below) / Log frame reporting format should include achieved and target figures for each year in a single spreadsheet for ease of monitoring progress	Complete
15	Revise VfM indicators as follows: / Economy / Current indicators are retained but include a comparison to more than one other programme, as well as comparisons over time / Indicators currently included under efficiency on budget execution rate (indicator 3) and management/admin costs as a percentage of total (indicator 4) are moved to economy. / The full cost of HDIF fee-rates and admin costs are captured in this indicator. For fee rates (indicator 1.g) this should include the personnel fees and milestones budget lines as, according to the contract, milestones represent a performance-based fee payment of 50% of the total fees. For management/admin costs (indicator 4), this should include the personnel fees, milestones, and BAF fees budget lines. / Efficiency / Indicators currently included under efficiency on budget execution rate (indicator 3) and management/admin costs as a percentage of total (indicator 4) to move to economy. / Retain the indicator (5) on speed of funds disbursement / Adopt the following output indicators and targets as efficiency measures: 1.2, 1.5, 2.2, 2.3, 3.1/3.2, and 3.4 / Effectiveness / Retaining the indicator (8) on HDIF supported initiatives that have produced evidence suggesting contribution to improved basic services. But make this a percentage indicator, not cumulative number. / A new indicator on the percentage of grantees that continue to implement projects 3 months after the end of HDIF funding; target 30% / One indicator from each outcome in the logframe / Equity / To be measured by both quantitative and qualitative indicators, and not only gender equity to be tracked. / Quantitative: / Retain indicators and target on staff / Include, disaggregated beneficiary data (gender only). Never include a target. / To add a quantitative indicator: all round 3 grantee have grantee strategies that clearly describe how they include women beneficiaries: Recommend including a target for next AR of 100% / Qualitative: / Provide a summary achievements and intentional efforts that the programme has in place (currently and the future) to ensure equity is achieved, including geographic equity (building the eco system beyond Dar es Salaam), and inclusion of people with disabilities. / Include success stories showing how grantees are achieving equity, where possible	Complete
16	Streamline the DFID-HDIF risk management process to include: / 6 monthly formal submission from Palladium to DFID of an updated risk register / Quarterly discussion of key risks at regular quarterly meetings, in which trends and updates in key risks are noted / Monthly 'heads up' from HDIF to DFID if there are any significant changes in risk or emerging risks. Issues relating to individual grantees to be recorded by the DFID programme manager in the delivery plan.	Ongoing – this has been implemented but these different check in points could be more focussed at the right level
17	Consider potential improvements to the process for the management of the grants line in the programme budget, based on feedback from the 2018/19 audit report when received.	Complete
18	DFID to develop terms of reference and commission an impact evaluation of HDIF	Postponed
19	DFID Tanzania to agree a plan for its work on innovation after the HDIF programme closes, considering how to build lessons from this programme into its future portfolio.	Complete