## Annual Review

Title: Human Development Innovation Fund – Tanzania (HDIF)
Programme Value £ (full life): £39,787,725		Review date: / 13 February 2021
Programme Code: 203539	AMP start date: January 2013	AMP end date: / 31 July 2021

Summary of Programme Performance
Year	2013	2014	2015	2016	2017	2018	2019	2020	2021
Overall Output Score	B	A	A+	A+	A+	A+	A+	A+	A+
Risk Rating	Mod	Min	Maj	Maj	Maj	Maj	Mod	Mod	Mod

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-203539/documents
DevTracker Link to results framework:	https://devtracker.fcdo.gov.uk/projects/GB-1-203539/documents

A. SUMMARY AND OVERVIEW [1-1 ½ pages]

Description of programme [1-2 paragraphs]

The Human Development Innovation Fund (HDIF) aims to improve outcomes in education, health, and water and sanitation in Tanzania by funding and promoting innovations with the potential to transform the delivery of basic services. Since its inception in 2013, the programme has funded 48 grantees through four rounds of funding. Ten grants are currently active. In addition to funding grants, the programme supports the development of Tanzania’s innovation ecosystem by promoting cross-sector collaboration and learning on innovation for human development. The programme is implemented through a contract with Palladium. The Commission for Science and Technology (COSTECH), an agency of the Ministry of Education, Science, and Technology (MoEST), is the key Government of Tanzania partner for the programme.

The year under review was the final full year of implementation for the programme, which will close in July 2021. As recommended in the 2020 annual review, this year the programme focussed on anchoring support for innovation and sharing programme learning among partners in Tanzania, in order to promote the sustainability of programme outcomes. This year was also characterised by disruption as a result of the COVID-19 pandemic, although this did not prevent the programme meeting all output targets.

This year a light-touch, desk based Annual Review was conducted due to the relatively short time remaining before the programme closure review in July 2021, as well as due to Covid-19 restrictions in traveling and meeting with stakeholders. This year’s review considered two overarching questions:
1. How can the programme maximise learning and sustainability of results during the final months of implementation? What has been achieved to date?
2. What impact has the COVID-19 pandemic had on the programme and how successfully has the programme adapted to deliver in this changing context?
Summary supporting narrative for the overall score in this review [1-2 paragraphs]

Overall, the programme has continued to meet or exceed expectations on all indicators this year, earning an overall score of A+. Several HDIF grantees have demonstrated impressive results and have secured paths to sustainability and scale. Highlights include:
- Ubongo Kids, whose Akili and Me edutainment cartoon (reported on in previous Annual Reviews) is now broadcast on free to air TV in 16 African countries and is on track to reach 60 million children by 2025. With school closures due to COVID-19, Ubongo decided to put all of their content under a creative commons license, making it freely available for any partner or individual who wants to use, download, share or distribute it for non-commercial purposes. This has helped Ubongo grow even more rapidly, launching 6 new countries and almost 20 new broadcasters.
- Apopo, whose project to Test, Treat, and Track TB using TB detection rats showed a 36% increase in TB detection rates compared to the baseline, and an increase from 65% to 92% in patient compliance with TB treatment. Elements of the new, integrated TB detection models were successfully replicated by APOPO in Maputo and in Addis Ababa.
- D-Tree, whose digital tool is being used by 2,300 Community Health Volunteers (CHVs) in Zanzibar, has been integrated by the Zanzibar Ministry of Health into their Community Health Strategy, and has secured £1.8 million in additional funding from Fondation Botnar and James Percy Foundation. D-Tree adapted the innovation this year by adding a COVID-19 module to the digital application, using the existing COVID-19 guidelines from the government, to enable CHVs to provide consistent COVID-19 education during their routine visits.

In addition to the success of HDIF grantees, a major achievement this year has been the establishment of a new multi-partner innovation funding and support platform, ‘Funguo’, managed by UNDP and with initial funding expected from the EU and Swiss embassies. Funguo will build on best practice and lessons learned from HDIF to bring together partners from multiple sectors to promote and support innovation in Tanzania. The FCDO have already committed some initial funding to this platform through the centrally managed Africa Technology and Innovation Partnership programme. This is a real success for the UK’s development legacy in Tanzania, attracting multiple new partners to the innovation sector based on the strong performance and effective communications of the HDIF programme.

Major lessons and recommendations for the year ahead [1/2 page]

For the remaining 5 months of programme implementation, a small number of recommendations are included, targeted at ensuring an effective programme closure that maximises the sustainability and uptake of lessons from the programme:
1. FCDO to engage the Funguo programme to oversee the final HDIF programme evaluation by July 2021. This will help to ensure that HDIF lessons-learned are taken up by Funguo.
2. FCDO to sit on the steering board of Funguo from March 2021 as part of its investment through the centrally-managed Africa Technology and Innovation Partnership programme. This will help to ensure that lessons from HDIF inform ongoing support to innovation and technology in Tanzania, and that UK Science, Technology and Innovation objectives are delivered.
3. HDIF to prepare a communications and lessons dissemination plan for the final months of the programme and share this with FCDO by March 2021. This should include plans for communication to Government, other donor partners, and internally to FCDO. FCDO Tanzania programme team and senior leadership to lead and support key HDIF closure and learning communications activities, where appropriate.
4. FCDO and HDIF to consider the best way(s) to ensure that knowledge and learning documents produced by the programme continue to be available to partners in innovation in Tanzania after HDIF closes, by April 2021. If appropriate, this may include handing over ‘ownership’ of these documents to Funguo.
5. HDIF to continue to escalate to FCDO where grantees have particular risks to sustainability, or where there may be particular opportunities to scale up innovations through FCDO’s work, so that FCDO Tanzania staff can engage their networks to support grantee sustainability through FCDO’s global portfolio where possible.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case. [1/2 page]

The HDIF programme aims to contribute to improved human development through supporting innovation in service delivery. The desired programme impact is: Dialogue and practice in innovation improve basic services in human development in Tanzania. This is supported by two programme outcomes: (A) HDIF intervention accelerates the diffusion of innovative ideas, approaches and solutions to human development challenges, and (B) HDIF intervention accelerates conversations, debates, and policymaking on innovation in human development.

Outcome A relates to the performance of grants, and the extent to which interventions have become sustainable beyond the life of the programme. It includes an immediate outcome indicator on number of HDIF-funded innovations that have produced evidence suggesting contribution to improved basic services, and a higher-level outcome indicator on the percentage of HDIF-funded innovations that have been “adapted” i.e. continue to operate in some form, 3 months after HDIF funding ends. Outcome B relates to building an evidence-based national conversation on innovation among innovators, policy-makers, funders, and the private sector. It includes indicators on the uptake of HDIF lessons by policy makers and funders of innovation, and the growth in the number of innovation hubs and other ‘enablers’ in Tanzania, as well as the level of conversation, excitement and media coverage around innovation in Tanzania. The Theory of Change assumes that achieving either of these outcomes would require all three of the outputs to be delivered.

There has been no change to the theory of change this year and no change to the outcome and impact indicators. At the output level, indicators were added or revised at the beginning of the year to remain relevant to activities in the final year of the programme. These changes are discussed in the output section below.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead? [1/2 page]

HDIF remains on track to deliver the expected outcomes and impact. All outcome indicators this year were met or exceeded, for example:
- Four additional HDIF-support initiatives measured within the year have evidence suggesting contribution to improved basic services, bringing the cumulative total to 19 against the target of 17
- Five of the six HDIF grantees that closed this year were assessed as having been “adapted” based on the Springfield Institute Systemic Change framework, meaning that they continue to be implemented and viable 3 months after HDIF funding has ended
- Eight new innovation enablers (i.e. hubs, accelerators, incubators etc) were identified in Tanzania this year, bringing the total number to 57, suggesting continuously growing interest and energy around innovation in Tanzania
- As described above, multiple donor partners (UNDP, EU, Swiss embassy) have indicated their intention to fund innovations in Tanzania after HDIF closes through the new UNDP-administered Funguo innovation programme
- Tanzania has continued to climb the global innovation rankings to 88th globally on the Global Innovation Index, ahead of Rwanda, Ghana, and Nigeria, and just behind Kenya. This reflects growth in innovative ideas in multiple sectors and, although not possible to attribute, it is likely that HDIF as the principal innovation support programme in the country had a catalytic role for part of this growth.
However, the COVID-19 pandemic is likely to limit opportunities for growth in innovation in Tanzania over the coming years. For example, HDIF has noted a reduced engagement from private sector partners in supporting innovation this year as profits have come under pressure during the pandemic and so less resource is available for non-core activities. Similarly, securing donor funding for future support to innovation programming in Tanzania is likely to be increasingly challenging in a context of global economic downturn due to COVID-19.

The 2020 annual review recommended that an independent evaluation of HDIF be undertaken to independently assess programme performance against expected outcomes and impact and to document lessons for future innovation support programming. This recommendation is now expected to be taken forward by the new Funguo programme in order to ensure ownership of findings and integration of lessons into the next phase of innovation system support in Tanzania.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio [1 paragraph]

Given the stage of the programme, with 5 months of implementation remaining, as well as the programme’s continued strong performance, early closure would not represent value for money for FCDO Tanzania. It is recommended that a normal close out process be followed that allows for key closure activities including lesson sharing and good programme management in the closure of grants.

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title	HDIF’s Networking and Media Engagements Continue to Strengthen Tanzania’s Innovation Ecosystem
Output number:		1	Output Score:	A+
Impact weighting (%):		20	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1 Cumulative number of articles or digital media produced by HDIF or HDIF grantees related to grantee innovations or other HDIF activities	430	460 / (Exceeded)
1.2 Cumulative number of HDIF curated/co-curated events or other networking opportunities with a clear targeting approach, disaggregated by events' locations and events that have COSTECH engaged as a collaborator	205 / (40% with COSTECH)	285 / (With COSTECH) (Exceeded)
1.3 Percentage of partners in supporting the innovation ecosystem who, in a survey, rated requested and agreed technical assistance, support or collaboration as 6 or better on a 10-point scale.	60%	95% (Exceeded)
1.4 Number of HDIF engagements (with stakeholders) that have developed into strategic partnerships promoting innovation in human development Tanzania	5	15 (Exceeded)
1.5 Proportion of output milestones achieved by COSTECH in its HDIF-supported 'Innovation Ecosystem Support' activities	70%	100% (Exceeded)
1.6 HDIF Twitter Account Engagement Rate	1.5%	1.9% (Exceeded)
1.7 Continued, active engagement in the broader HDIF network through HDIF's Newsletter	15% open / 2% click through	45% open / 6% click through (Exceeded)

Briefly describe the output’s activities and provide supporting narrative for the score.

Progress exceeded the milestone target on all Output 1 activities this year, leading to an Output 1 score of A+. Highlights included:

Innovation Week continued to be a flagship event for HDIF and all innovation stakeholders in Tanzania. Held just before the influence of COVID-19 and associated restrictions were felt in Tanzania, the event brought together more than 7,000 participants who took part in 240 events and exhibitions across 6 regions (Arusha, Dar es Salaam, Dodoma, Mbeya, Iringa, and Zanzibar). Innovation Week also attracted ten sponsoring partners (up from 7 in the previous year) - Vodacom, UNDP, UNCDF, ESRF, UNICEF, UN Women, Clouds Media, Segal Family Foundation, The Embassy of the Netherlands, and Exim Bank. This shows the continued engagement and interest in innovation from stakeholders across different sectors in Tanzania, which can at least partly be attributed to HDIF’s communications, networking and media work under this output.

HDIF focussed on more strategic engagement with the media this year, building deeper partnerships with specific media houses to promote understanding among journalists about innovation and technology in Tanzania that should continue even when HDIF closes. This included sponsoring a radio programme on Clouds FM to champion conversations about different technologies and innovations pioneered by Tanzanians and sponsoring an award for best reporting on innovation and technology at the annual Excellence in Journalism Awards. The success of these activities is reflected in the strong performance against indicator 1.1.

In May 2020, HDIF worked with local innovation hubs (Seedspace and Ifakara Hub) and development partners (UNDP and the Dutch Embassy) to launch a challenge to amplify local COVID-19 responses from start-ups. 203 applications were received, of which 6 were selected to receive support including a small cash prize, mentoring support from the HDIF team, and 3-months of co-working space subscription from Seedspace. In November 2020, a follow-on challenge was held to focus on recovery and resilience, this time implemented with Seedspace and Ndoto Hub. By delivering these challenges as a partnership between hubs and multiple donor partners, this activity has also contributed to strengthening relationships that form the innovation and technology ‘ecosystem’ in Tanzania.
Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year [1 paragraph]

There have been no changes in the VfM proposition of this output this year, nor significant changes to the costs of major inputs to deliver this output. A more detailed assessment of VfM is provided in Section E and a full VfM review will be conducted as part of the programme closure review.

For Output 1, on equity, it is worth noting that a focus was put this year on deepening support to innovation ecosystems outside Dar es Salaam. This included supporting satellite Innovation Week events in 5 regions outside Dar es Salaam, and supporting innovation enabling organisations outside Dar through a fourth round of grant funding for ‘Innovation Capacity Building’ (more detail under Output 2).

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

Changes were made to output indicators this year in order to ensure the logframe remained relevant and stretching during the final years of programme implementation. Indicator 1.4 was changed from a measure of new innovations mobilised through strategic awards (as no new strategic awards were introduced at this stage of the programme) to a measure of strategic collaborations with the potential to contribute to the sustainability or scalability of HDIF-funded innovations or activities. Indicator 1.6 was changed from a measure of the size of HDIF’s social media following to a measure of level of engagement with social media, which is more stretching and a more engaged audience is more likely to take action to promote innovation in Tanzania. No further logframe changes will be made during the final months of implementation.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

All 2020 annual review recommendations related to Output 1 were completed. These included anchoring the innovation ecosystem by convening a virtual network of innovation hub managers, ensuring learning and sustainability plans were in place for all ‘Innovation Capacity Building’ grantees, and supporting COSTECH to strengthen its vision of becoming a ‘hub of hubs’ by supporting them to provide training for principals of 10 community development colleges in establishing innovation spaces. All recommendations from this year’s annual review are set out in Section A, above.

Output Title	HDIF has Effective and Continually Improving Mechanisms in Place to Diffuse Innovations
Output number:		2	Output Score:	A+
Impact weighting (%):		50	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 Number of beneficiaries reached by HDIF grantees	n/a – no target, tracking only	5,234,407
2.2 Percentage of HDIF funded projects that have achieved at least 80% of their output milestones	30%	69% (Exceeded)
2.3 Percentage of grantees who rate HDIF's assistance, input or collaboration as 6 or better on a 10-point scale	60%	100% (Exceeded)
2.4 Proportion of grantees that report smooth cash flow in each implementing quarter	60%	100% (Exceeded)
2.5 Proportion of HDIF’s grantees that have gender strategies in place	80%	100% / (Exceeded)
2.6 Proportion of grantees that show progress in implementing their sustainability plans	60%	82% / (Exceeded)
2.7 Percentage of work plan targets achieved by HDIF in building the capacity of GoT in innovation fund management	80%	100% / (Exceeded)

Briefly describe the output’s activities and provide supporting narrative for the score.

Progress exceeded the milestone target on all Output 2 activities this year, leading to an Output 2 score of A+. Highlights included:

This reporting year was marked by the signing of 5 new grants with innovation ecosystem enabling organisations under the ‘innovation capacity building’ HDIF funding round, which was developed in the previous reporting year. These were: Smart Codes, R-Labs Iringa, Cube Zanzibar, Anza Entrepreneurs, and Catholic Relief Services. The purpose of this round of funding is to use HDIF grant making and technical and programme management capacity building support to strengthen key actors in the innovation ecosystem in Tanzania, with a particular focus on those based outside Dar es Salaam. All of these grantees have received intensive support from the HDIF programme to quickly begin implementation and, as can be seen in indicators 2.2-2.6, all have the core aspects of their grant management in place, including sustainability strategies and approaches to gender inclusion.

Due to the COVID-19 and associated restrictions, some grantees’ activities could not be delivered within the planned time frame. HDIF received no-cost extension request from 4 grantees and all were approved: Well Told Stories, Ubongo, HIMSO, and Sense International. All extended grantees have now closed. In total, 7 grantees reached the end of their implementation period this reporting year, bringing the total number of completed or terminated grants to 38 out of 48.

- As an adaptive programme, in April/May 2020, grantees were encouraged to adapt their workplans in order to ensure they remained relevant in the context of Covid-19. Webinars were held with all grantees to discuss the impact of Covid and options for workplan revisions. Examples of grantee adaptations include:
  - Dorcas International – Menstrual Hygiene Management for Her project, Handeni District – added messaging on hand washing and hygiene, as well as installing low-cost ‘tippy taps’ in the 25 villages of Handeni District where the project is implemented
  - Well Told Story - Designed and printed 500,000 copies of a special edition Shujaaz comic focused on COVID-19 messaging, which was distributed nationally by the Shujaaz Supafan network, Mwanaspoti and Coca-cola outlets. WTS also introduced a weekly COVID -19 SMS blast to Shujaaz subscribers and a social media campaign.
  - Cube Zanzibar - Working with 6 partners from across the ecosystem in Zanzibar, Cube Zanzibar organised an online hackathon to support youth to create solutions to the impacts of COVID19 on the island. Cube Zanzibar also procured soap and sanitizer making machines and had their products certified by the Zanzibar Food and Drug Administration (ZFDA)
  - Ubongo – in response to school closures and demand for virtual education, Ubongo made all their content, including that developed through HDIF funding, available for free to download under creative commons licence. As a result, Ubongo content was taken up by almost 20 new broadcasters in 6 new countries. In Tanzania, Ubongo also mapped all of their content against the school curriculum to ensure that learning is aligned to the education system, and created a WhatsApp and Facebook chat bot to support parents with early learning at home during COVID -19 school closures and beyond.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year [1 paragraph]

There have been no changes in the VfM proposition of this output this year, nor significant changes to the costs of major inputs to deliver this output. A more detailed assessment of VfM is provided in Section E and a full VfM review will be conducted as part of the programme closure review.

For Output 2, on equity, as recommended by FCDO, HDIF grantees are required to have well-thought-out plans to ensure participation of women and girls in the design and implementation of grantees projects. Grantees are also required to put in place mechanisms to address any potential harm to women and girls that may result from the implementation of these grantees’ projects. These gender strategies are monitored on a quarterly basis, and as reported under output indicator 2.5 100% of grantees have them in place.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

Changes were made to output indicators this year in order to ensure the logframe remained relevant and stretching during the final years of programme implementation:
- Indicator 2.1 was added to track number of beneficiaries reached by HDIF grantees. This measure was added in order to help assess the final impact of the programme when the programme completion report is completed next year.
- Indicator 2.4 was changed from a measure of the speed at which HDIF disburses grants to a measure of grantee cash flow. This reflects a finding from the 2020 annual review that some grantees experienced cash flow issues due to the required timing of submitting financial information for the closing quarter and receiving payments for the upcoming quarter.
- Indicator 2.6 was changed from a measure of grantee completion of regular self-assessment reporting to a measure of progress against sustainability plans. This reflects the greater importance of sustainability plans in the final year of the programme and is intended to ensure that plans are not just ‘pieces of paper’ but are useful and implemented
No further logframe changes will be made during the final months of implementation.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

The recommendation from the 2020 annual review to minimise cash flow issues for grantees was addressed. The recommendation for HDIF to meet on a structured basis with FCDO Tanzania human development sector advisers was partially met as engagement continued on an ad hoc basis, particularly in response to COVID where there was significant collaboration with HDIF education technology initiatives. Regular engagement took place between HDIF and FCDO science, technology and innovation advisers, particularly in the design of the new Funguo innovation platform. The recommendation for the HDIF team to escalate any concerns about specific grantees’ sustainability to FCDO remains relevant and is repeated in this year’s annual review. All recommendations from this year’s annual review are set out in Section A, above.

Output Title	Lessons and Recommendations from HDIF are Increasingly Sought After by Innovation Funders and Policy-makers
Output number:		3	Output Score:	A+
Impact weighting (%):		30	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1 Cumulative number of knowledge products produced by HDIF or its partners (including local hubs or conveners) with a dissemination plan in place, disaggregated by type of knowledge product (analysis report or learning document) and by knowledge products that have been disseminated	58	62 (Exceeded)
3.4 Proportion of partners who report to use HDIF content to inform their behaviour, practices, strategies, or policies regarding innovation for human development	60%	86% / (Exceeded)
3.5 Proportion of HDIF-curated events with an average participant satisfaction rating of 7 or above	60%	100% (Exceeded)
3.6 HDIF explores and encourages potential scaling of HDIF innovations within FCDO's portfolio by sharing experiences and evidence with related FCDO programmes. Cumulative target.	25	26 / (Met)
3.7 Proportion of output milestones achieved by COSTECH in its HDIF-supported knowledge management activities	70%	100% (Exceeded)

Briefly describe the output’s activities and provide supporting narrative for the score.

Progress met or exceeded the milestone target on all Output 3 activities this year, leading to an Output 3 score of A+. Highlights included:

HDIF continues to play an influential role with partners within the Tanzania innovation ecosystem, most notably sharing programme experiences and lessons to shape the design of a new multi-partner innovation support programme, ‘Funguo’ managed by UNDP. HDIF’s experience has been critical in shaping the programme design, which will combine innovation finance with support to innovation incubators/hubs etc and cross-sector and policy dialogue, and helping to secure a next generation of donor support for innovation in Tanzania after the programme closes.

HDIF continues to produce knowledge and learning documents on supporting innovation in Tanzania. This year, the flagship paper was titled ‘Catalysing and Scaling Innovation in Tanzania: A Review of Approaches.’ It outlined challenges and concrete recommendations and ideas for partners looking to support the innovation sector in Tanzania. This paper drove much of HDIF’s engagement with donor and private sector partners this year. HDIF also produced 5 case studies on grantee innovations this year: Apopo, BORDA, Sense, D-Tree and Ubongo. It will be important to ensure that these documents can continue to be accessed after the programme closes, and therefore a recommendation for this year is for FCDO and HDIF to consider the best means to do this.

HDIF continues to support COSTECH through activities reported under this output and under others. This year, the shift in the programme towards more Government-focussed activity continued, with ongoing demand from COSTECH’s relatively new management team for HDIF support. This included support to COSTECH’s BUNI hub to offer hub management training to tertiary and higher learning institutions and to set up 10 new hubs in community development colleges (under the Ministry of Health); support to BUNI to run an entrepreneurship bootcamp for 19 promising young entrepreneurs (including 11 girls); a 3-day innovation capacity-building retreat for COSTECH’s new senior leadership team to ensure consistent knowledge of opportunities and challenges for science, technology and innovation in Tanzania across the management team. This close-working approach with COSTECH has been increasingly successful throughout the period of HDIF implementation and is a lesson that should be carried into any future innovation programming in Tanzania.
Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year [1 paragraph]

There have been no changes in the VfM proposition of this output this year, nor significant changes to the costs of major inputs to deliver this output. A more detailed assessment of VfM is provided in Section E and a full VfM review will be conducted as part of the programme closure review.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

Changes were made to output indicators this year in order to ensure the logframe remained relevant and stretching during the final years of programme implementation:
- Previous indicators 3.1, 3.2, and 3.3, which covered learning documents produced, with a dissemination strategy in place, and then actually disseminated, were combined for simplicity into a single indicator 3.1 to cover learning documents produced and disseminated
- Indicator 3.4 was changed to not only measure number of engagements with stakeholders with the potential to influence actions, but to measure actual influence of HDIF on stakeholder strategies and policies, based on a survey issued to innovation ecosystem partners.
- Indicator 3.5 was tweaked to specifically measure satisfaction with HDIF events, rather than more general HDIF support and collaboration. Having a specific indicator on events recognises the importance of events for networking, collaboration and communications in the HDIF theory of change.
No further logframe changes will be made during the final months of implementation.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

All 2020 annual review recommendations related to Output 3 were completed. These included close working between HDIF and the FCDO science, technology and innovation teams, including the East Africa Research Hub, to ensure HDIF lessons are embedded in future FCDO innovation programming. All recommendations from this year’s annual review are set out in Section A, above.

D: RISK [½ to 1 page]

Overview of risk management [1/2 page]

FCDO Tanzania has a high overall risk appetite for HDIF, in recognition of the fact that, as an innovation programme working with often untested pilot projects, there is a risk that many could fail. There is however, zero tolerance for risk in safeguarding as well as fiduciary risk. The overall programme risk continues to be moderate, which is within the acceptable risk appetite for the office.

Several risks were, through robust mitigation and proper management, successfully closed this reporting year. These included the risk of failure of innovations supported by HDIF and the risk that innovations supported by HDIF might not translate that into at-scale transformation of basic services in Tanzania. Consistent strong results reported through the programme’s logframe have shown that these risks have not materialised.

COVID-19 was identified as a major emerging risk in this reporting year. The HDIF programme took immediate mitigation measures, including revising grantee workplans to accommodate delays in implementation and to find alternative ways of delivering activities under COVID-19 restrictions. After about 3 months, the COVID-19 situation in Tanzania stabilised, and the programme was able to largely revert to normal management. COVID-19 remains a moderate risk on the programme, particularly for the delivery of the annual Innovation Week which will need to adapt to deliver safely in the context of COVID.

Other major risks remain in the programme, including the risk of high turnover of key staff as the project approaches completion. Whilst this is not a new risk, it is a risk that has increased towards the end of the programme. HDIF is mitigating this risk by providing incentives for key staff to stay until the end of the programme and ensuring a clear handover plan for staff who leave.

Safeguarding risk is a priority area that is closely monitored given the nature of the work of some HDIF grantees, some of whom work with children and vulnerable people. During the reporting year, new grantees received training on safeguarding issues, and HDIF staff were provided with new office security protocols developed in collaboration with another FCDO-Palladium programme, I4ID.

During this reporting year, FCDO Tanzania’s central corporate team conducted a check on risk management process and systems for all programmes in the office. Overall, HDIF was rated Green. HDIF risk registers were found to be well updated and further recommendations, e.g. on phrasing of risk descriptions, were provided and taken up.

E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including consideration of VfM measures of economy and efficiency. [max 1 page]

Commercial and Partner Performance

The overall performance of the partners is satisfactory. With a better part of the implementation period falling during the COVID-19 restrictions on operations, the partner was able to quickly adapt and flex their operations to deliver against set targets. Despite the COVID-19 pandemic and restrictions, activities were delivered to quality and the partner produced quality and standard reports within set timelines. The programme has so far delivered all contractual milestones on time. The contract is managed through FCDO’s Strategic Relationship Management (SRM) process. During this reporting year there were no rounds of SRM reporting.

There have been minor changes in the roles and responsibilities of the core Palladium team during this reporting year. The former Team Leader transitioned into the Project Director/Strategic Lead position and the former Deputy Team Leader transitioned into the Team Leader/Country Director position in February 2020. This change has not led to any notable dip in partner performance.

Financial Performance
The general trend of HDIF financial management is satisfactory across the board. With the COVID-19 pandemic, adjustments were made on budgets and forecasts, this ensured variances were managed to an average of below 10% across the year, with only one month where variance exceeded this level. Palladium has maintained robust financial management and reporting mechanisms, giving FCDO sight on detailed financial reporting, including monthly confirmation of figures and providing adequate information accompanying the invoice in the cover email. The FCDO programme team continues to track these trends and advise appropriately.

Component	Budget 2020/21	Expected Spend 2020/21	Used to fund
203539 - 102: Implementation	£3,307,770	£3,109,400.77	Contract with Palladium - Grants and Reimbursables
203539 - 103: Monitoring and Evaluation	£387,895.42	£400,000	For monitoring and evaluation of the programme. Forecast to be spent through Funguo for evaluation and lesson learning from HDIF interventions to inform future innovation programming
TOTAL	£3,695,665.42	£ 3,509,400.77

Audit Report and Asset Verification

HDIF received an unqualified opinion for the 2019/2020 audit. The audit report was reviewed by the FCDO team and recommendations were given although these were relatively minor, including on proper recording of the status of assets and a repeated question on Palladium’s liability for Withholding Tax, which Palladium has followed up for legal advice. FCDO followed up on the recommendations and were able to see improvements on the issues noted. The 2020/21 audit is currently underway. FCDO has reviewed the Terms of Reference and met the audit team for an inception meeting.

The HDIF programme has acquired various physical assets and maintains an asset register which is updated on a regular basis and shared with FCDO. Assets management is routinely monitored by FCDO during spot checks and annual reviews.  As part of the 2021 Annual Review, an updated asset register was shared and a light touch virtual spot check was carried out by picking a few assets and requesting more information and evidence from the partner. No issues were identified for these assets. Proper procedures, including loss reports, were found to have been followed for lost and damaged assets. A physical asset check will be carried out as part of the asset disposition process during programme closure.

Value for Money

There have not been any changes to HDIF’s VfM framework and indicators this year. The key cost drivers during this period are comprised of grants - 45%, subcontractors and consultants - 17%, long and short-term personnel - 18%, and milestone payments - 15%.

On economy, a total of £24,675 savings were realised this reporting year through securing mutliplte quotes for goods and services procured. Additionally, HDIF had a budget execution rate of 90% this year, suggesting that the programme's activities are being implemented in a timely manner, despite the COVID pandemic no additional costs were incurred that would result from delayed activities. On efficiency and effectiveness, all inputs and were translated to outputs and outputs translated to outcomes exceeding the set targets respectively. On equity, grants supported projects in many regions of the country and Innovation Week was extended to the regions with centres in Tanga, Arusha, Zanzibar, Iringa and Mbeya. Gender continues to be a significant focus for the programme, as described above.

A thorough review of VfM will be conducted as part of the programme closure review.

Monitoring and Evaluation
With restrictions on travel for FCDO staff and the decision to conduct a desk based Annual Review, there were no field visits conducted in the reporting period. However, regular monthly review meetings were held virtually throughout the year, giving some level of confidence on delivery. During the start of the COVID-19 period from late March to June, FCDO-HDIF virtual meetings were increased to weekly to track the impact of the pandemic on programme delivery. The Palladium team continued to monitor grantee progress virtually through the start of the pandemic but

Date of last narrative financial report	14th December 2020	Date of last audited annual statement	May 2019