Business Case – November 2023
Summary Sheet
Title: UK – Rwanda Trade and Investment Partnership Programme
Programme Summary: / This business case is anchored on strengthening the UK – Rwanda trade and investment partnership, which is underpinned by the intent to pursue mutual prosperity and inclusive economic development. The proposed programme aims to catalyse sustainable investment into critical sectors such as infrastructure, green and circular economy, finance and professional services, critical minerals, manufacturing, and commercial agriculture by leveraging avenues such as business forums, topical roundtables, trade and investment missions, and capacity building sessions with both government and private sector. It also aims to promote bilateral trade between the UK and Rwanda and support Rwanda to take advantage of trade preferential agreements, diversify its export base, and build capacity for enabling market access for the private sector both within the region and globally. In addition, the programme would enable the British High Commission Kigali to strategically increase its work in showcasing Rwanda as a preferred investment destination as well as a trade and exports hub with adequate resources that would aid such.
What is the rationale for UK Aid spending: / Rwanda is a vibrant nation with a population exceeding 13 million people and a real GDP of $10.388 billion as of the end of 2022. Rwanda aspires to Middle Income Country status by 2035 and High-Income Country status by 2050. The government’s ambition to achieve these goals is reflected in its fiscal transparency, inclusive and market-friendly policies. Rwanda is ranked highly in terms of ease of doing business and it is positioning itself as Must-Go-To business hub in Africa. / Rwanda's investment climate is one of the most attractive in Africa with a dedicated agency - The Rwanda Development Board (RDB) which plays a significant role in attracting and facilitating investment into critical sectors (Manufacturing, Agriculture, Circular Economy, Infrastructure, Climate). The commitment of the Rwanda government has instilled confidence in other countries to strengthen their partnerships on bilateral trade, investment; the UK is one of such countries. The UK and Rwanda have an excellent bilateral relationship. The UK has always been a committed development partner of Rwanda, but beyond this, its commercial ties have deepened over the years with Rwanda becoming an attractive prospect for British investors, with economic growth around 7% and a stable political and business environment. Rwanda’s continued integration into the EAC has guaranteed improved market access, enabling UK companies to do business on a regional scale, and attracting future British investment. / The total trade in goods and services (exports plus imports) between the UK and Rwanda was £42 million in the four quarters to the end of Q1 2023, an increase of 23.5% or £8 million in current prices from the four quarters to the end of Q1 2022. There are around 150 British companies registered in Rwanda and the UK is the biggest investor in the tea sector in Rwanda with more sectors such as mining, textiles being explored. / To further deepen this mutually beneficial relationship, it is important for the British High Commission Kigali to leverage avenues, platforms and programmes that would create and reinforce linkages between the UK and Rwanda businesses; identify and deploy diverse and sustainable investment/ financing instruments; showcase thriving joint ventures and strategically strengthen the capacity of the counterpart agencies on export standards. / While the Government of Rwanda has put in place structures and opportunities for stronger partnership, it is still essential to provide more support hence the proposal of the programme. The programme would encourage and support British business in Rwanda, invest in improving the business climate here, and will enable both countries to prosper.
Programme Value: £4,500,000		Country/Region: Rwanda
Department/Country Office confirmation of review process
Contact Name: Bola Karimu		SRO: Rob Hale
Threshold for final approval of Business Case
Date of Approval of Concept Note	October 2023	Name and role of approver: Anna Wilson – Development Director
Date of Approval of Business Case	November 2023	Name and role of approver: Anna Wilson – Development Director
Programme Code: 400150	AMP Start Date: November 2023	AMP End Date: October, 2028
Overall programme risk rating		Low
[note] Home | National Institute of Statistics Rwanda
[note] Rwanda Development Board (Annual Report 2022) RDB-Annual-Report-2022.pdf
[note] World Bank Country Partnership Framework for the Republic of Rwanda (FY21 – FY26) World Bank Document
[note] FCDO: Policy Paper UK-Rwanda Development Partnership Summary, July 2023 UK–Rwanda development partnership summary, July 2023 - GOV.UK (www.gov.uk)
[note] Department for Business Trade: Trade and Investment Factsheet Trade and Investment Factsheet (publishing.service.gov.uk)
[note] UK-Rwanda commercial relationship - GOV.UK (www.gov.uk)

Strategic Case

Background and Context:
The UK and Rwandan governments have excellent bilateral relations, which has resulted in the UK supporting Rwanda's growth journey with reforms aimed at improving the investment and business climate, tax policy and administration, land reform, and public administration in Rwanda. Rwanda's positive economic trends have been influenced by its excellent governance and bilateral relationships with other nations, including the United Kingdom. The economy of Rwanda grew by 8.2% in 2022, primarily due to increased agricultural production, government investment in infrastructure, foreign capital investment in tourism and hospitality, and an increase in private sector credit.
[note] World Bank Press Release (July 11, 2023) Rwanda Maintains Strong Growth Momentum in Early 2023 Rwanda Maintains Strong Growth Momentum in Early 2023 (worldbank.org)

Total trade in goods and services (exports plus imports) between the UK and Rwanda was £35 million in the four quarters to the end of Q2 2023, an increase of 9.4% or £3 million in current prices from the four quarters to the end of Q2 2022. However, Africa, accounts for just 2.5% of the UK’s trade, with 60% of this accounted for by South Africa and Nigeria. The appetite of UK firms to invest and establish businesses in Rwanda is promising, but a concerted strategy for boosting trade and investment between the two countries is required to make significant progress. Within the context of the middle-power, Rwanda serves as a critical strategic partner to the UK, with significant convening power and influence across Africa (in particular, within the East Africa region). In addition, the Rwandan government sets high ambition on objectives important to the UK such as climate, green growth, and the rights of women and girls.
[note] Department for Business Trade: Trade and Investment Factsheet Trade and Investment Factsheet (publishing.service.gov.uk)

Presently, the UK is supporting trade and investment in Rwanda through British Investment Partnership (BIP) vehicles such as UK Export Finance, British International Investment (BII), Private Infrastructure Development Group (PIDG), and Manufacturing Africa (MA). There are also bilateral programmes that are leveraging private investment in the tea sector (one of Rwanda’s top exports) and supporting crucial infrastructure projects to boost trade. This portfolio of programmes aims to contribute to inclusive economic growth, increase the flow of Foreign Direct Investments (FDIs) and enhance Rwanda's business climate. In addition, they support Rwanda's private sector development in areas such as manufacturing, the circular economy, infrastructure, agriculture, research, and innovation.
[note] FCDO: Policy Paper UK-Rwanda Development Partnership Summary, July 2023 UK–Rwanda development partnership summary, July 2023 - GOV.UK (www.gov.uk)

This business case serves a vehicle to support Rwanda in actualising its long-term strategic plan to become an upper middle-income country by 2035 as well as actualising the trade and investment goals set out in the National Strategy for Transformation – leveraging on UK’s strong convening power, robust and diverse investment toolkit as well as targeted technical assistance, policy influencing and enhanced UK-Rwanda partnerships. The business case covers a period of five years, with pipeline interventions well positioned to further deepen UK’s bilateral economic partnership and the long-term prosperity of both our countries as well as responsive to the needs and demand of the countries.
[note] Rwanda Development Partner: NST1 – Rwanda Development Partner https://vision2050.minecofin.gov.rw/root/nst/nst1

Scope of Work
The planned portfolio of interventions aims to be both proactive and responsive to the market and priorities of the UK and Rwanda in the areas of trade and investments. The interventions would leverage on the UK’s high-level convening power, and strategic diplomatic and bilateral relationship, as well as draw on the good political will of the Rwanda government. It would sequentially outline the efforts and impact of the two countries’ partnership across critical sectors (agriculture, manufacturing, green economy, financial and professional services, infrastructure, and critical minerals).

Within the next five years, the UK-Rwanda Trade and Investment Partnership will be implemented through the following avenues:

  1. Business Forum – There will be a convening of high-level UK-Rwanda Business Forum which will be anchored on the following objectives: i) showcasing Rwanda as a preferred investment destination leveraging its favourable business climate, and strategic position within the EAC region; ii) building sustainable commercial relationships that drive trade and investment growth in Rwanda.
  2. Trade and Investment Missions – Facilitate both inward and outward trade and investment missions aimed at attracting foreign investments to Rwanda with a multi-sector focus particularly in key value-addition sectors – including services, critical minerals, agriculture, infrastructure, and manufacturing. These would help enhance engagement between Rwanda and business leaders in the UK trade-related Government officials, and UK-based Chambers of Commerce as well as The CityUK. In addition, provides an opportunity to facilitate topical roundtable conversations on key sectoral and thematic issues.
  3. Capacity Building and Market Research – Act as a source of knowledge sharing and capacity building channel for both the Government of Rwanda and the private sector on trade preferential agreements – including the Developing Country Trading Scheme (DCTS), which could promote adoption and enhance trade flows between the two countries. In addition, build capacity around investment opportunities and partnerships that could support an increased flow of FDI.
  4. UK-African Investment Summit (UK-AIS) – Support Rwanda’s preparation for the UK-AIS, including working with the Government of Rwanda to maximise the trade opportunities and investment, coordinating delegation as well as putting Rwanda in the fore as a preferred trading partner and investment destination.

Impact and Outcomes that we expect to achieve.
1. The UK-Rwanda Trade and Investment Partnership programme aims to deliver a holistic impact that ensures an increased investment and trade flow into Rwanda. The outcomes will be measured in terms of:
  1. Increased FDI flow into critical sectors in Rwanda.
  2. Increased percentage of trade flows between Rwanda and the UK.
  3. Increase in the number of new UK businesses registered and/or operational in Rwanda.
.
Assurances and compliance with legislation

Gender Equality and Social Inclusion (GESI)

Through each avenue (business forum, investment summit, trade missions, capacity building), there will be an intentional approach to serving women’s owned businesses (channelling sustainable capital to women’s businesses through diverse
instruments) as well prioritising businesses that serve women in Rwanda. In addition, there will be opportunities to showcase women’s businesses during the business forum and investment summit (this will be done in partnership with RDB, Rwanda Association of Manufacturers and Private Sector Federation to identify women-owned businesses.

The programme intends to take deliberate account of small and medium size businesses in the design of the various interventions as well as make reasonable adjustments for people living with disabilities and the cognizance of the unanticipated consequences of the intervention design.

Counter terrorist financing
The programme is at low risk of funding terrorism or money laundering. All funds will be managed by reputable suppliers. Comprehensive due diligence and other governance mechanisms, detailed in the Financial Case, will further mitigate the risk of illicit financing.

Partnership Principles
The programme will not be providing direct budgetary support to the government of Rwanda. Although there will be a significant level of technical support to investment related government agencies such as RDB, and towards supporting investment and trade enabling regulatory and policy reforms, the programme resources will be utilized directly in the creation, promotion of trade and investment opportunities for both UK and Rwanda businesses.

Where the programme is supporting a private investment opportunity also being promoted by a government agency, the programme will actively work to ensure international best practice is followed around human rights issues. Where such practices are not adopted or followed at any point during the specific intervention, and where the programme attempts to influence best practice have failed, the programme will immediately withdraw its support but will continue to strongly advocate for the reinstatement of best practice.

Climate and environment
The programme will mainstream climate considerations into its approach. The programme will support the greening of trade activities, for example linking firms and business to the circular economy. The greening of trade and promotion of circular economy practises have been identified by Government of Rwanda as priorities under both Rwanda’s updated Nationally Determined Contributions (NDCs) under the Paris Agreement climate action plan and the National Circular Economy Action Plan. The programme does not pose a risk to the environment and where possible will look to use policy reform interventions to promote climate smart businesses within the Government. The programme will not invest in fossil fuels or otherwise undermine Rwanda’s commitments to reducing carbon emissions.
[note] Rwanda updated NDC - 2020
[note] Rwanda Circular Economy Action Plan

Appraisal Case

Technical Options for achieving these results.
This section provides justification for the feasible options for implementing and delivering the Strategic Case of the programme in a way that optimises the Value for Money. It concludes with a summary Value for Money (VfM) statement as well as the Theory of Change for the preferred option. The preferred option has been duly evaluated and reviewed by the FCDO Rwanda Green Growth and Trade team as well as consultations with Rwanda counterparts.

The UK – Rwanda Trade and Investment Partnership programme will be implemented by separately contracted service providers under series of competitive tendered process. The implementers would bring together a diverse range of expertise, a high level of flexibility and robust contractual mechanisms to hold the service providers accountable. The service providers would broadly include Professional Conference Organisers (PCO),

Consulting Firms (such as Boston Consulting Group) and FCDO Funded Programmes (including Manufacturing Africa). After the procurement process, the successful service providers would be provided a contract with detailed Terms of Reference which they are mandated to deliver on as part of the overall objectives of the programme. Service provider will be given contract with detailed ToRs and other supporting documents.

BHC Kigali considered a range of strategic options presented and reviewed in the following sections:

  1. Option 1: Do nothing: In this case, FCDO would use its funds to execute different projects and activities. This action, however, would have practical implications, such as reduced or no increase in trade and investment transactions between the UK and Rwanda, no change in FDI flows into critical industries in Rwanda, and limited promotion of Rwanda organisations and partnerships. All of this would have an impact on the effectiveness of other UK-funded bilateral and Centrally Managed Programmes (CMPs), particularly those implemented through British Investment Partnerships like Manufacturing Africa. Given that the programme also intends to commission a number of research projects in selected critical areas, the team's access to evidence that could offer insights into commercially investable ventures would be substantially hampered.

  1. Option 2: Focus only on the Business Forum, Investment Summit, Trade Missions, Roundtables component to increase the visibility of Rwanda as a trade and investment destination. The benefits of this scenario include large trade and investment transactions occurring during and after the business forum, trade missions and investment summit, as well as the promotion of Rwanda as an investment destination and its enterprises. However, the sustainability of the business forum's gains will be impaired due to the Rwanda counterpart's limited expertise on deal and transaction closure, after-care services, standard conformity, and enabling policy frameworks.

  1. Option 3: Improve market access, trade, and investment opportunities through internal human resources only. In this scenario, there would be increased internal capacity for the Rwanda counterparts on deal origination, closure, standard conformity, export frameworks, market-friendly policies, after care-services, but there will be limited avenues to leverage the available UK resources (BIP toolkit) as well as connection with UK businesses which are determinants of GDP growth, FDI inflows for Rwanda.

  1. Option 4: Have a multifaceted and holistic market-system based approach that draws on both internal FCDO capabilities and external resources across diverse trade and investment facilitation components. This scenario is recommended because it strategically integrates all of the

components (business forum, trade missions, roundtables, capacity building, research) to create a comprehensive programme that prioritises the need to strengthen the capacity of Rwanda counterparts; enhancing the sustainability of the FCDO's operations in Rwanda; considerably increasing FDI inflows; and establishing a strong mutually advantageous trade bilateral partnership between the UK and Rwanda.

Theory of Change
Table 1 below represents a simplified Theory of Change (ToR) for this Business Case. It reflects the integrated nature of the interventions / activities and how this ensures that outcomes and impacts are achieved across the scope of work.

UK-Rwanda Trade and Investment Partnerships Programme
(Theory of Change)

Impact

Increased Trade and Investments between the UK and Rwanda

Outcomes

XXX new UK businesses registered and/or operational in Rwanda six months after Business Forum and Investment Summit

XXX number of registered participants at the forum
XXX percentage increase in exports from Rwanda to UK (increased global competitiveness)

Increased number of UK businesses registered and operating in Rwanda.
Improved framework for outward trade from the Rwanda to the UK, leveraging on preferential trade agreements.
Increased trade volumes and value as well as FDI flows between Rwanda and the UK.
Outputs

Commission market research and disseminate of high impact knowledge products, as well as build capacity and capability of the Rwandan market – including private/public.
Facilitate the convening of a Business that brings together key stakeholder from the UK, Rwanda and SSA.
Support the Government of Rwanda in its attendance of the UK-AIS, including organising high-level side events and trade and investment introductions.
Activities

Organise trade and investment missions as well as round table that focuses on critical sectors in Rwanda.

UK-African Investment Summit
Business Forum
Capacity Building & Market Research
Trade & Investment Missions

Components

Commercial Case

British High Commission Kigali will contract a Service Provider (SP) in a competitive tender process through local procurement, to deliver on the first component of the programme – the UK-Rwanda Business Forum. The SP will be from a credible Professional Conference Organiser company or contractor who has extensive experience in preparing, managing and delivering business fora including the design of post forum follow-up process. The local procurement has been chosen for two main reasons. Firstly, the availability of companies with experience and expertise working with Rwanda Development Board (the “hosts”) in managing delivery of similar events. Secondly, the available budget for the business forum follows within the below EU threshold of the Delegated Procurement Officer (DPO), which makes sense to use local procurement to minimise cost and time.

Potential suppliers from within the region will be invited to bid competitively against defined Terms of Reference (ToR) for service contract for the business forum. The ToRs will include some ‘outcome’ focused specifications. Proposals will compete on the basis of delivering the services required of the SP, accounting for the level and quality of inputs proposed, and the cost, which represent the most economically advantageous tender.

To enable FCDO to effectively assess the different bids and determine which offers best value for money, detailed information will be requested on the consultants’ approach, and the costs associated with it, including meetings and presentations for clarifications. This should detail, as a minimum:
- The approach taken to deliver phase 1 and phase 2 of the business forum;
- A breakdown of costs associated with delivery of both phases, including detail of the role of the SP in delivery, i.e. which outputs the SP expects to deliver directly vs those they expect to buy-in externally from FCDO team;
- The inputs the SP expects to be attached to delivery of outputs e.g. consultants time and cost of consultants; material costs;
- The method by which payment is expected by FCDO, with an emphasis of output-based payment and a strong case for any areas where this is not believed to be possible; where output-based payment is used, a proposed approach to generating milestones and clearly specified criteria by which FCDO can assess successful delivery will be expected.

The route to the market for other components of the programme will be determined as the programme evolves and budget become readily available but we expect that service providers will be contracted through local procurement, Expert Advisory Call Down Services (EACDS) or other FCDO frameworks.

Financial Case

British High Commission (BHC) Kigali does not have the required funding available through the current resource allocation. However, the required total funding of £4,500,000 will be available via a bid from the Business Investment Partnerships (BIP) budget dedicated to Growth Gateway, as well as BHC Kigali budget resources for outer years, as the programme evolve, and the budget become readily available.

The first phase of the UK-Rwanda Trade and Investment Partnership programme will use an allocation of £175,000 from the Growth Gateway programme, possibly increasing to £200,000 should resources allow. This £175,000 will include £125,000 non-ODA allocation from the Growth Gateway. This funding will pay for the Professional Conference Organiser (PCO), the venue for the Business forum, for costs linked to the autumn 2023 round tables in London, and other costs relating to the Business forum. Furthermore, an additional £50,000 allocation of ODA from the Business Investment Partnerships (BIP) budget dedicated to Growth Gateway will focus on the coffee cupping event at the Business Forum, widening inclusion at the event and ensuring sectors such as agriculture and manufacturing are well represented.

Table 1: Project budget summary phase1 2023

Component	Non-ODA/ODA	Cost
Component 1: UK-Rwanda Business Forum, Trade and Investment Missions	Non-ODA	£125,000
Component 2: UK-Rwanda Business Forum, Trade and Investment Missions	ODA	£50,000
TOTAL		£ 175,000

The procurement process for identifying service providers will include a financial risk assessment and an assessment of management capacity. Subsequent to appointment, FCDO’s standard approach to disbursement/reimbursable payments, financial monitoring and reporting will be applied. If the SP subcontracts other SPs to deliver some of the components, FCDO standard procurement principles will be followed. The SPs will be expected to provide spending forecasts, which will be tracked through the provision of narrative and financial reports. Performance against project outputs and budget expenditure will be challenged by FCDO for accuracy and consistency. BHC Kigali will ensure that all service providers maintain zero tolerance to corruption and will conduct regular reviews and audits to test their financial and procurement systems to detect any fraud.

Management Case

The UK – Rwanda Trade and Investment Partnership will be managed by the BHC Kigali’s Green Growth and Trade Team. The SRO oversight will be provided by the Team Leader, whilst a G7 PRO Private Sector Development Adviser assisted by a Trade Adviser will manage the day-to-day delivery of the programme. The programme management will be led by a Senior Programme Manager. There will also be short-term support from within FCDO and DBT for the forum and subsequent UK- AIS-2024. To ensure alignment, synergy and coordination with wider UK objectives, the programme team will liaise with BHC Kigali colleagues, other UK Departments such as Department of Business and Trade (DBT), and the central FCDO British Investment Partnership Directorate (BIPD).

The implementation of the different components will be led internally by the Green Growth and Trade Team as well as externally contracted suppliers whose responsibilities include implementing the programme’s strategy, managing the intervention portfolio, and managing the programme’s risks. Intervention partners may include:

  1. Government institutions such as Rwanda Development Board, Ministry of Commerce, Ministry of Infrastructure.

  1. Private sector stakeholders including Rwandan and UK Businesses operating in critical sectors – manufacturing, critical minerals, infrastructure, finance and financial services etc. Private sector associations such as TheCityUK, Private Sector Federation of Rwanda etc

For effective alignment and coordination of strategic goals of the programme, there would be setting up of a steering committee comprising of FCDO and Government of Rwanda counterparts however the committee would be chaired by the Green Growth and Trade Team Leader.

The UK-Rwanda Investment Partnership will contract a Professional Conference Organiser (PCO) to organise the UK-Rwanda Business Forum in January 2024. The scope of work and responsibilities of the PCO over a two phased period. This is details in Annex 2.

Overview of Risks: Risk Classification and Risk Mitigation
This section identifies risks to the successful delivery of the programme as well as mitigating actions:

  1. Risk 1: Change in leadership of key Government agencies.
Risk Type: External context. Rwanda appetite – High
In recent times, key agencies such as Rwanda Development Board (RDB) have witnessed several changes to their leadership team which has significant implication for the implementation of FCDO’s programmes.
Mitigation Measure(s): Reassurance of UK’s support to Rwanda in strengthening institutional capacity and capability to deliver effectively irrespective of the cycle of leadership. Continued support on facilitating effective coordination between Ministries Departments and Agencies.

  1. Risk 2: Fraud involving UK funds.
Risk Type: Fiduciary. Rwanda appetite – Low
In addition to the UK’s strong anti-fraud systems and monitoring mechanisms, Rwanda government also has robust ani-corruption structures – with low-risk environment for fraud. There is also rigorous delivery / supply chain mapping in FCDO programming with strong due diligence checks undertaken. This includes clear protocols for dealing with suspicion of fraud, as well as regular audits - both internal and independent.
Mitigation Measure(s): Having robust systems to avoid fraud involving UK funds
would be a pre-qualification criterion for bidders and most likely bidders have these.
FCDO has well developed systems for dealing with concerns around fraud, and if these
arose, they would be referred to the Fraud Unit in the UK for investigation.

  1. Risk 3: Inability of the service providers to deliver.
Risk Type: Operational delivery (risk). Rwanda appetite – Medium
There is a possibility that the service providers on the various components would not implement and deliver the programme as expected by the FCDO.
Mitigation Measure(s): i) During the contracting bid, the FCDO to consider bidders with high technical capacities (knowledge of the market, expertise and resources); ii) Development of coordination and compliance mechanism that ensures check-in, reporting and feedback platforms.

  1. Risk 5: Lack of certainty around future budget provisions to fully fund the programme.
Risk Type: Budgetary risk. Rwanda appetite – High
There is an increased strain on ODA funding as a result of increased competing priorities which has led to budgetary cuts in FCDO programmes in recent times. There is a significant risk that the programme allocated fuds will be cut mid-way affecting the relationship between the UK and Rwanda as expectations would have been placed on the programme’s objectives (outcomes and impacts).
Mitigation Measure(s): i) Effective demonstration of impact and learnings from the various interventions; ii) Leverage the strong bilateral relationship between the UK and Rwanda to make a case for continued funding in instances of FCDO budget cuts.

Annex 1: UK-Rwanda Business Forum
As part of the UK-Rwanda Trade and Investment Partnership, the British High Commission (BHC) Kigali is organising the first ever UK-Rwanda Business Forum. This aims to catalyse business development and investment between the UK and Rwanda. The Forum will provide an opportunity to raise the profile of UK commercial engagement with Rwanda, to create awareness of specific high potential sectors, and to advance business partnerships and investment agreements.

Objectives of the Business Forum
1. To highlight to UK investors the investment potential in Rwanda, its favourable business climate, and its strategic position at the heart of the EAC region.
2. To bring together UK and Rwanda policy makers, business operators and investors to engage, discover opportunities, strategize, and further trade and investment prospects.
3. To pitch Rwandan business opportunities and lay the groundwork for building sustainable commercial relationships, to drive trade and investment growth in Rwanda, including in the run-up to the UK-African Investment Summit 2024 (UK-AIS 2024).
4. To discuss and develop recommendations to address the existing trade and investment barriers.

Purpose of the forum
The UK has been a key development partner for Rwanda, with the relationship further strengthened recently through the Commonwealth and Rwanda’s role as Chair in Office. With reduced bilateral ODA, especially on economic development, there is space to further boost commercial ties. BHC Kigali wish to build on the momentum created by the recent visit of the UK Prime Minister’s Trade Envoy – Lord Popat – to Rwanda, which helped raise commercial engagement, and build anticipation for UK-AIS 2024.
This Forum would advance this, serving as a high-level platform for the GoR and businesses to pitch investment and trade opportunities and forge partnerships with their counterparts from the UK.
Format
There will be a combination of expert keynote addresses, lively panel discussion, business pitch, in-depth case studies and networking. Speakers will explore debate and consolidate the theme, "Succeeding in Rwanda: Unlocking Growth & Opportunities”.
The Forum will profile the broad investment potential in Rwanda. It will contain presentations of research by Growth Gateway on the most relevant opportunities for UK investors. There will be a focus on the following sectors: Infrastructure, mining and mineral processing, agriculture/horticulture, green energy, IT/Business Process Outsourcing (BPO) and financial services (TBC). Manufacturing will also be considered. We will maximise BHC Kigali’s Gender Equality and Social Inclusion (GESI) strategy in planning.
Side events will include Business to Business (B2B) and Business to Government (B2G) engagement, sector-specific break-out sessions, project visits and networking events.

Ultimately, participants will share experiences, build commercial relationships, unlock business challenges, and develop strategic partnerships. There will also be a specific ‘after-care’ session, giving a chance for existing UK investors to raise obstacles directly with counterparts from the GoR and related agencies.
Day 1: Arrival and pre-event reception at Kigali Convention Centre – with focus on networking, introductions of key UK and GoR officials, and setting expectations.
Day 2: UK-Rwanda Business Forum (KCC & Radisson Blu Hotel). Evening reception at the British residence.
Day 3: Coffee Cupping competition showcasing small holder farmers, Site Visits, Deal Room, Business to Government meetings.
Expected Outcomes
1. Greater understanding amongst UK investors of Rwanda’s comparative advantages as an investment destination in the region.
2. Stronger relationships between UK and Rwandan companies.
3. Better understanding amongst GoR officials of investor challenges.
4. Increased trade in products and services.
5. Increased investment from the UK in the mid-term.
6. Increased interest in and understanding of the UK-African Investment Summit in April 2024 and pipeline of deals which can be announced at the summit.
7. Secure interest and agreement of GoR partners and relevant firms to continue discussion and participation in future UK-Rwanda trade events.

Expected Participation
The Forum shall bring together around 500 participants from UK, Rwanda and other EAC partner states. The audience will be diversified and range from captains of industry, investors, business membership organisations (BMOs), GoR officials, DBT sector leads across Africa, HMTC Africa, FCDO’s SRO for Africa Investment Summit, BII, PIDG and UKEF teams, relevant development partners and potential UK buyers of Rwandan goods and services (horticulture, IT, finance).
Dates, Time, and Venue (TBC)
The Forum is planned for 29th-31st January 2024, with side events either side. Venue is Kigali Convention Centre as the facility was already booked.
Resourcing
BHC Kigali has £275k within our Business Investment Partnerships (BIP) budget dedicated to Growth Gateway (Boston Consulting Group support) this financial year. This will be used to finance research into specific investment opportunities within the Green Economy, which will be presented at the forum [Note these resources are not provided through this business case]. We are also using our BIP voucher to finance research into Electric Vehicle componenet manufacture (through Manufacturing Africa) and to engage Invest Africa for support in attracting investors to the Forum. We also have a non-ODA allocation of £125k from the Growth Gateway, and £50k from the bilateral ODA budget for Rwanda. Staff resource will come from BHC: i.e., Robinson Mugisha, part of Rob Hale’s time and Bola Karimu (Manufacturing and Investment adviser). We have also applied for a civil service fast streamer for 6 months (November to April) to focus on the forum and subsequent UK- AIS-2024. We will also approach DBT for surge support.

Annex 2: Planned Phase of UK-Rwanda Business Forum
Phase One
Forum Registration and Promotion
- Work with the hosts and partners to develop a target list of UK and international companies to invite to the forum.
- Work with UK team to develop a vetted registration system for both UK/Foreign and Rwandan companies, capturing the sector of operations.
- To ensure that the registration process meets the requirements of Rwandan and UK data privacy laws (e.g., attendees will have to acknowledge how their data will be used).
- Prepare marketing materials for the forum, including a website which may be hosted by the PCO or UK/RDB (TBC).
- Develop a tiered sponsorship package for the forum.

Phase Two
Forum Preparation
Work with the hosts in developing the programme for the forum, including identification of an MC, panel members, etc.
- Work closely with the conference venue (KCC) to ensure optimal set up of the venue space in line with the conference programme requirements. This will require amongst others i) plenary hall, ii) breakout rooms, iii) dedicated space for RDB, KIFC and other institutions, iv) co-ordination of the venue’s IT, sound and light engineers to ensure seamless delivery of presentations etc, v) ensure catering services are delivered in line with the hosts’ expectations.
- Work with the PCO, Government partners and businesses to ensure the Business forum is as inclusive as possible. This includes in forum attendance, panel representation and also accessibility requirements.
- Organisation of an exhibition space within KCC and management of the exhibition on behalf of the hosts.
- Work closely with designated panel speakers to ensure they are fully prepared well in advance of the forum.
- Work with the BHC and RDB comms teams to develop and implement a comms strategy for the forum.
- Develop creative approaches to ensure that the right companies are introduced to the right potential partners/investors.
- To explore opportunities for making the Forum carbon neutral and proposing to the hosts appropriate ways in which to do that.

- To set up a programme of investor visits for the 31st January 2024 (the day after the actual forum). These visits will potentially include trips to mining concessions, horticulture farms, IT companies amongst others. The hosts will provide the PCO with details of the potential sites. Attendees at the forum will be expected to sign up to the visits well in advance of the forum for planning purposes, but there should be leeway to expand the numbers if demand increases once the forum is underway.
- To set up a programme of Business to Government (B2G), and Business to Business (B2B) meetings for the 31st January 2024 (the day after the actual forum). These meetings will enable senior access by company representatives to decision makers within the Government of Rwanda, including but not limited to RDB, MINICT, Rwanda Mining Board (RMB), MINECOFIN, MININFRA etc.

Forum Delivery
- To work with the airports authority to establish a conference desk at Kigali International Airport to support attendees, from 28th January through to 2nd February 2024.
- To work with transport providers to ensure that attendees are able to transit the airport to their hotel.
- To engage RCB and airline partners to secure preferential rates for attendees at the forum flying from the region, UK or beyond.
- Work with the venue to ensure the smooth admittance of pre-confirmed attendees at the forum.
- To work with the venue to ensure that set-up on the eve of the forum is as agreed in advance, and that meeting room configurations are undertaken in good time to meet the requirements of various sessions in the forum.
- To work with the MC and the hosts to ensure that sessions are delivered on time as per the event programme.
- To discuss with the hosts in advance the feasibility of delivering a hybrid event and, if agreed, ensuring that this is an option.
- To work with the venue and caterer to ensure refreshments and the lunch are provided on time and to the standards expected in advance.
- To work closely with the hosts to deliver planned side events around the forum – including an evening cocktail at the British High Commission residence in Kigali and other events as yet undetermined.
- To work closely with the hosts to develop a range of entertainment options for attendees to sign up to for the days before and after the forum. These may include: a walking tour of Kigali’s car free zone, art tour of Kimihurura, visit to Nyandungu eco-park.
- To assign someone to lead each of the investor visits (in partnership with the hosts), who will liaise with the visit sites and ensure each visit runs smoothly for investors.
- At the Forum venue to provide conference secretariat with IT equipment (e.g., desktops, laptops, printer, photocopy, scanner).
- Ensure safety protocol during the event.
- Arrange live streaming of events where required.
- Produce audio and video recordings where required.
- To take on any miscellaneous tasks, to ensure smooth management of the event that might arise before, during, or after the event.

Post Forum
- To set up a follow up process, whereby each attendee is asked about their intentions/priorities regarding Rwandan investments or partnership with UK companies. Also, to understand any follow up support required in the future.
- To prepare a report and technical documentation for the hosts with each attendee’s contact details, their requests for additional support and recommendations for follow up.